1066676 | No | Yes | No | MCP | MCP - CDP | 01-Preparation | Basis team support of additional SAP application components or components | TAI | TAI | SI | Onshore | Doherty; Sean | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2016-11-13 | 2016-11-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066677 | No | Yes | No | MCP | MCP - CDP | 01-Preparation | HEC effort and associated hosting costs for additional components or components | TAI | TAI | SI | Onshore | Doherty; Sean | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2016-11-13 | 2016-11-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066678 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Design Security infrastructure for Farmer - Supplier Portal | SEC | SEC | Saputo | Onshore | Sharma; Kush | Saputo | Yes | CapEx | Global | IT - Internal | 4h | 0h | 4h | 2016-08-18 | 2016-09-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066679 | No | No | Yes | MCP | MCP - CDP | 06-Hypercare | Realization of security infrastructure Farmer - Supplier Portal | SEC | SEC | Saputo | Onshore | Sharma; Kush | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-03-31 | 2017-03-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066680 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Cut Over Plan | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2016-10-17 | 2016-10-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066681 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | UAT Test Scehdule | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066683 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Transport Sequence | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2016-11-13 | 2016-11-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066684 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Sprint 1 Review | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Global | IT - Internal | 6h | 0h | 6h | 2016-07-25 | 2016-07-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066685 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Sprint 1 Restospective | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Global | IT - Internal | 2h | 0h | 2h | 2016-07-18 | 2016-07-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066686 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 1 Restospective |  | Missing Stream | Saputo | Onshore | Ault; Rowan | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2016-07-18 | 2016-07-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066687 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 1 Restospective |  | Missing Stream |  |  | Galbraith; Steven |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-07-18 | 2016-07-18 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066688 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 1Testing |  | Missing Stream | Saputo | Onshore | Ault; Rowan | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2016-07-07 | 2016-07-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066689 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 1Testing |  | Missing Stream |  |  | Galbraith; Steven |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-07-07 | 2016-07-07 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066690 | No | Yes | No | MCP | MCP - CDP | 03-Design/Build | Demo and walk-through of Features for release 1 sprint 1 & 2 | TAI | TAI | SI | Onshore | Doherty; Sean | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066691 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 2 Testing |  | Missing Stream | Saputo | Onshore | Ault; Rowan | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066692 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 2 Testing |  | Missing Stream |  |  | Galbraith; Steven |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066693 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 3 Review |  | Missing Stream | Saputo | Onshore | Ault; Rowan | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2016-09-09 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066694 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 3 Review |  | Missing Stream |  |  | Galbraith; Steven |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-09-09 | 2016-09-09 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066695 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Sprint 3 Readiness Check Release 1 | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2016-09-16 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066696 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Sprint 3 Readiness Check Release 1 | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2016-09-19 | 2016-09-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066697 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | UAT Stage Gate Approval Release 1 | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066698 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | UAT Stage Gate Approval Release 1 | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066699 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Sprint 3 Restospective | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066700 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 3 Restospective |  | Missing Stream | Saputo | Onshore | Ault; Rowan | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066701 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 3 Restospective |  | Missing Stream |  |  | Galbraith; Steven |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066702 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Plan for Australia on site testing | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2016-08-29 | 2016-08-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066703 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Licensee commencement of Acceptance Test Procedures for Release 1 |  | Missing Stream | Saputo | Onshore | Ault; Rowan | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2016-11-13 | 2016-11-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066704 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Licensee commencement of Acceptance Test Procedures for Release 1 |  | Missing Stream |  |  | Galbraith; Steven |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-11-13 | 2016-11-13 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066705 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Update Training Materials | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-01-18 | 2017-01-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066706 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Sprint 4 Review | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2016-11-03 | 2016-11-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066707 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 4 Review |  | Missing Stream | Saputo | Onshore | Ault; Rowan | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2016-11-03 | 2016-11-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066708 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 4 Review |  | Missing Stream |  |  | Galbraith; Steven |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-11-03 | 2016-11-03 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066709 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Demo and walk-through of Features for release 2 sprint 4 | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Global | Business | 8h | 0h | 8h | 2016-11-03 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066710 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Demo and walk-through of Features for release 2 sprint 4 | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | CapEx | Global | IT - Internal | 13.5h | 0h | 13.5h | 2016-11-03 | 2017-01-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066711 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Demo and walk-through of Features for release 2 sprint 4 |  | Missing Stream | Saputo | Onshore | Zuliani Pablo | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2016-11-11 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066712 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Demo and walk-through of Features for release 2 sprint 4 | PMO | PMO | Saputo | Onshore | Iñiguez Manuel | Saputo | Yes | CapEx | Global | IT - Internal | 1.5h | 0h | 1.5h | 2016-11-03 | 2016-11-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066713 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Demo and walk-through of Features for release 2 sprint 4 |  | Missing Stream | Saputo | Onshore | Clark; Kirby | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2016-11-03 | 2016-11-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066714 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Demo and walk-through of Features for release 2 sprint 4 |  | Missing Stream | Saputo | Onshore | Buytendorp; John | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2016-11-03 | 2016-11-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066715 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Demo and walk-through of Features for release 2 sprint 4 |  | Missing Stream |  |  | Hayes; AnnL |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-11-03 | 2016-11-03 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066716 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Demo and walk-through of Features for release 2 sprint 4 | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066717 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Sprint 4 Restospective | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Global | IT - Internal | 4h | 0h | 4h | 2016-10-21 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066718 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 4 Restospective |  | Missing Stream | Saputo | Onshore | Ault; Rowan | Saputo | Yes | CapEx | Global | Business | 4h | 0h | 4h | 2016-10-21 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066719 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 4 Restospective |  | Missing Stream |  |  | Galbraith; Steven |  | Yes | CapEx | Global |  | 4h | 0h | 4h | 2016-10-21 | 2016-10-24 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066720 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 4 Testing |  | Missing Stream | Saputo | Onshore | Ault; Rowan | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066721 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 4 Testing |  | Missing Stream |  |  | Galbraith; Steven |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066722 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Sprint 5 Review | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2016-12-06 | 2016-12-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066723 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 5 Review |  | Missing Stream | Saputo | Onshore | Ault; Rowan | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2016-12-06 | 2016-12-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066724 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 5 Review |  | Missing Stream |  |  | Galbraith; Steven |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-12-06 | 2016-12-06 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066725 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Sprint 5 Restospective | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2016-12-06 | 2016-12-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066726 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 5 Restospective |  | Missing Stream | Saputo | Onshore | Ault; Rowan | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2016-12-06 | 2016-12-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066727 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 5 Restospective |  | Missing Stream |  |  | Galbraith; Steven |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-12-06 | 2016-12-06 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066728 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Demo and walk-through of Features for release 2 Sprints 5 and 6 | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2017-01-03 | 2017-01-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066729 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Demo and walk-through of Features for release 2 Sprints 5 and 6 |  | Missing Stream | Saputo | Onshore | Ault; Rowan | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2017-01-03 | 2017-01-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066730 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Demo and walk-through of Features for release 2 Sprints 5 and 6 |  | Missing Stream |  |  | Galbraith; Steven |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-01-03 | 2017-01-03 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066731 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Sprint 6 Restospective | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2017-01-03 | 2017-01-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066732 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 6 Restospective |  | Missing Stream | Saputo | Onshore | Ault; Rowan | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2017-01-03 | 2017-01-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066733 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 6 Restospective |  | Missing Stream |  |  | Galbraith; Steven |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-01-03 | 2017-01-03 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066734 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Sprint 6 Testing | PMO | PMO | Saputo | Onshore | Iñiguez Manuel | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2017-01-05 | 2017-01-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066735 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 6 Testing |  | Missing Stream | Saputo | Onshore | Ault; Rowan | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2017-01-05 | 2017-01-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066736 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 6 Testing |  | Missing Stream |  |  | Galbraith; Steven |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-01-05 | 2017-01-05 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066737 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 7 Review |  | Missing Stream | Saputo | Onshore | Ault; Rowan | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2017-02-17 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066738 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 7 Review |  | Missing Stream |  |  | Galbraith; Steven |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-02-17 | 2017-02-17 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066739 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Sprint 7 Review | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2017-02-17 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066740 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Sprint 7 Restospective | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2017-02-17 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066741 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 7 Restospective |  | Missing Stream | Saputo | Onshore | Ault; Rowan | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2017-02-17 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066742 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 7 Restospective |  | Missing Stream |  |  | Galbraith; Steven |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-02-17 | 2017-02-17 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066743 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 7Testing |  | Missing Stream | Saputo | Onshore | Ault; Rowan | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2017-02-17 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066744 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 7Testing |  | Missing Stream |  |  | Galbraith; Steven |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-02-17 | 2017-02-17 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066745 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Sprint 8 Review | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2017-03-17 | 2017-03-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066746 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 8 Review |  | Missing Stream | Saputo | Onshore | Ault; Rowan | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2017-03-17 | 2017-03-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066747 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 8 Review |  | Missing Stream |  |  | Galbraith; Steven |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-03-17 | 2017-03-17 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066748 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Sprint 8 Restospective | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2017-03-17 | 2017-03-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066749 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 8 Restospective |  | Missing Stream | Saputo | Onshore | Ault; Rowan | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2017-03-17 | 2017-03-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066750 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 8 Restospective |  | Missing Stream |  |  | Galbraith; Steven |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-03-17 | 2017-03-17 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066751 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 8 Readiness Check Release 2 |  | Missing Stream |  |  | PMO |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-03-16 | 2017-03-16 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066752 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Release 2 Features released and SAP notification to Licensee for commencement of Acceptance Test Procedures |  | Missing Stream |  |  | PMO |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-03-16 | 2017-03-16 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066753 | No | No | Yes | MCP | MCP - CDP | 05-Cutover/Go-live | Licensee acceptance and sign-off of Features for release 2 | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2017-03-17 | 2017-03-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066754 | No | No | No | MCP | MCP - CDP | 05-Cutover/Go-live | Licensee acceptance and sign-off of Features for release 2 |  | Missing Stream | Saputo | Onshore | Ault; Rowan | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2017-03-17 | 2017-03-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066755 | No | No | No | MCP | MCP - CDP | 05-Cutover/Go-live | Licensee acceptance and sign-off of Features for release 2 |  | Missing Stream |  |  | Galbraith; Steven |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-03-17 | 2017-03-17 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066756 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Sprint 3 Review | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2016-09-09 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066757 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Sprint 1Testing | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | CapEx | Global | IT - Internal | 20.25h | 0h | 20.25h | 2016-07-07 | 2016-08-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066758 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Sprint 2 Testing | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | CapEx | Global | IT - Internal | 5h | 0h | 5h | 2016-08-15 | 2016-09-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066759 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Sprint 4 Testing | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | CapEx | Global | IT - Internal | 6.5h | 0h | 6.5h | 2017-01-17 | 2017-01-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 4.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066760 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Sprint 5 Testing | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2016-12-08 | 2016-12-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066761 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Sprint 6 Testing | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2017-01-05 | 2017-01-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066762 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Sprint 7Testing | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2017-02-17 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066763 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Provision of Mini-Configuration by Licensee for Release 1 (2week of buffer) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066764 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Provision of Mini-Configuration by Licensee for Release 1 (2week of buffer) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066765 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Provision of Mini-Configuration by Licensee for Release 1 (2week of buffer) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066766 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Provision of Mini-Configuration by Licensee for Release 1 (2week of buffer) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066767 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 1 Provision of test cases and test data by Licensee for Release 1 |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066768 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 1 Provision of test cases and test data by Licensee for Release 1 |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066769 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 1 Provision of test cases and test data by Licensee for Release 1 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066770 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 1 Provision of test cases and test data by Licensee for Release 1 |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066771 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 3 - Provision Australia Master Data |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066772 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 3 - Provision Australia Master Data |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066773 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 3 - Provision Australia Master Data |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066774 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 3 - Provision Australia Master Data |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066775 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 5 Provision of Mini Configuration by Licensee for release 2 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066776 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 5 Provision of Mini Configuration by Licensee for release 2 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066777 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 5 Provision of Mini Configuration by Licensee for release 2 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066778 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Provision of test cases by Licensee for release 2 |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-11-13 | 2016-11-13 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066779 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Provision of test cases by Licensee for release 2 |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-11-13 | 2016-11-13 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066780 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Provision of test cases by Licensee for release 2 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-11-13 | 2016-11-13 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066781 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Provision of test cases by Licensee for release 2 |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-11-13 | 2016-11-13 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066782 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Provision USA/Canada Master Data |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-11-13 | 2016-11-13 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066783 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Provision USA/Canada Master Data |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-11-13 | 2016-11-13 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066784 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Provision USA/Canada Master Data |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-11-13 | 2016-11-13 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066785 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Provision USA/Canada Master Data |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-11-13 | 2016-11-13 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066786 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 3 - LOG - FSD Writing for MCP |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066787 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 3 - OTC - FSD Writing for MCP |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066788 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 3 - PTM - FSD Writing for MCP |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066789 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 3 - PTP - FSD Writing for MCP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066790 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 3 - RTR - FSD Writing for MCP |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066791 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 3 - LOG - FSD Writing for MCP |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066792 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 3 - OTC - FSD Writing for MCP |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066793 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 3 - PTM - FSD Writing for MCP |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066794 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 3 - PTP - FSD Writing for MCP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066795 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 3 - RTR - FSD Writing for MCP |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066796 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 5 Development FUT |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066797 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 5 Development FUT |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066798 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 5 Development FUT |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066799 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 5 Development FUT |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066800 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Sprint 5 Development FUT |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066801 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Configure Objects |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066802 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Set up Data for CDP |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066803 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Identify BPML |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-12-26 | 2016-12-26 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066804 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | RTR CDP Design Decisions |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-11-05 | 2016-11-05 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066805 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | TM CDP Design Decisions |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-12-18 | 2016-12-18 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066806 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Configure Objects |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066807 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Set up Data for CDP |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066808 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Identify BPML |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-12-26 | 2016-12-26 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066809 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Configure Objects |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-08-01 | 2016-08-01 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066810 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Configure Objects |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-08-01 | 2016-08-01 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066811 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Set up Data for CDP |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-10-07 | 2016-10-07 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066812 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Set up Data for CDP |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-10-07 | 2016-10-07 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066813 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Identify BPML |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-09-30 | 2016-09-30 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066814 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Identify BPML |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-09-30 | 2016-09-30 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066815 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Configure Objects |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-08-01 | 2016-08-01 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066816 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Configure Objects |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-08-01 | 2016-08-01 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066817 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Set up Data for CDP |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-09-02 | 2016-09-02 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066818 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Set up Data for CDP |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-09-02 | 2016-09-02 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066819 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Configure Objects |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066820 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Configure Objects |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066821 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Set up Data for CDP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-10-07 | 2016-10-07 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066822 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Set up Data for CDP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-10-07 | 2016-10-07 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066823 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Identify BPML |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-09-30 | 2016-09-30 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066824 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Identify BPML |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-09-30 | 2016-09-30 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066825 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Configure Objects |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066826 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Configure Objects |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066827 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Set up Data for CDP |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-10-07 | 2016-10-07 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066828 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Set up Data for CDP |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-10-07 | 2016-10-07 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066829 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Identify BPML |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-12-09 | 2016-12-09 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066830 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Identify BPML |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-12-09 | 2016-12-09 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066831 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Conduct Design Worshops |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066832 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | RTR CDP Design Decisions |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-12-02 | 2016-12-02 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066833 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | TM CDP Design Decisions |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066836 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Conduct Design Worshops |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066837 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | RTR CDP Design Decisions |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-07-31 | 2016-07-31 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066838 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | TM CDP Design Decisions |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066839 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Conduct Design Worshops |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-10-17 | 2016-10-17 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066840 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Conduct Design Worshops |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-10-17 | 2016-10-17 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066841 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | RTR CDP Design Decisions |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-11-05 | 2016-11-05 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066842 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | TM CDP Design Decisions |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-12-18 | 2016-12-18 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066843 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Conduct Design Worshops |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066844 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | RTR CDP Design Decisions |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-12-02 | 2016-12-02 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066845 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | TM CDP Design Decisions |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066846 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Conduct Design Worshops |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066847 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | RTR CDP Design Decisions |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-07-31 | 2016-07-31 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066848 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | TM CDP Design Decisions |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066849 | No | Yes | No | MCP | MCP - CDP | 99-Global | Sharepoint Access | PMO | PMO | SI | Onshore | Dupont Champion; Francois | IBM | Yes |  |  | IT - External | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066850 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Master Role Design |  | Missing Stream |  |  | _SEC Resource Onshore |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-11-28 | 2016-11-28 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066851 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Security Approach |  | Missing Stream |  |  | _SEC Resource Onshore |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-11-05 | 2016-11-05 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066852 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Security Design Workshops |  | Missing Stream |  |  | _SEC Resource Onshore |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-11-28 | 2016-11-28 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066853 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Security Detailed Design |  | Missing Stream |  |  | _SEC Resource Onshore |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-11-28 | 2016-11-28 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066854 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Derived Role Build |  | Missing Stream |  |  | _SEC Resource Offshore |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066855 | No | No | No | MCP | MCP - CDP | 03-Design/Build | FUT Support Roles |  | Missing Stream |  |  | _SEC Resource Offshore |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066856 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Master Role Build and UT |  | Missing Stream |  |  | _SEC Resource Offshore |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-10-12 | 2016-10-12 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066857 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | SoD Analysis and Remediation | SEC | SEC | SI | Landed Onshore | Manongsong; Melissa | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066858 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Support Role Build and UT |  | Missing Stream |  |  | _SEC Resource Offshore |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066859 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Defect Resolution |  | Missing Stream |  |  | _SEC Resource Offshore |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066860 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Security Role FUT |  | Missing Stream |  |  | _SEC Resource Offshore |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-12-26 | 2016-12-26 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066861 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Composite Role Design |  | Missing Stream |  |  | _SEC Resource Onshore |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066862 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Composite Role Design |  | Missing Stream |  |  | _Saputo SEC Analyst 2 |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066863 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Master Role Design |  | Missing Stream |  |  | _Saputo SEC Analyst 2 |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-11-28 | 2016-11-28 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066864 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Security Approach |  | Missing Stream |  |  | _Saputo SEC Analyst 2 |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-11-05 | 2016-11-05 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066865 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Security Design Workshops |  | Missing Stream |  |  | _Saputo SEC Analyst 2 |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-11-28 | 2016-11-28 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066866 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | Security Detailed Design |  | Missing Stream |  |  | _Saputo SEC Analyst 2 |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-11-28 | 2016-11-28 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066867 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Composite Role Build |  | Missing Stream |  |  | _SEC Resource Offshore |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066868 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Composite Role Build |  | Missing Stream |  |  | _SEC Resource Onshore |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066869 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Composite Role Build | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066870 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Composite Role Build | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066871 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Composite Role Build | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066872 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Derived Role Build |  | Missing Stream |  |  | _SEC Resource Onshore |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066873 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Derived Role Build | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066874 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Derived Role Build | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066875 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Derived Role Build | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066876 | No | Yes | No | MCP | MCP - CDP | 03-Design/Build | Derived Role Build | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066877 | No | No | No | MCP | MCP - CDP | 03-Design/Build | FUT Support Roles |  | Missing Stream |  |  | _SEC Resource Onshore |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066878 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | FUT Support Roles | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066879 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | FUT Support Roles | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066880 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | FUT Support Roles | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066881 | No | Yes | No | MCP | MCP - CDP | 03-Design/Build | FUT Support Roles | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066882 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | FUT Support Roles | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066883 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Master Role Build and UT |  | Missing Stream |  |  | _SEC Resource Onshore |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-10-12 | 2016-10-12 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066884 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Master Role Build and UT | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2016-10-12 | 2016-10-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066885 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Master Role Build and UT | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2016-10-12 | 2016-10-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066886 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Master Role Build and UT | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2016-10-12 | 2016-10-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066887 | No | Yes | No | MCP | MCP - CDP | 03-Design/Build | Master Role Build and UT | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2016-10-12 | 2016-10-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066888 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Master Role Build and UT | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Global | IT - External | 3h | 0h | 3h | 2016-10-12 | 2016-11-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066889 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | SoD Analysis and Remediation | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066890 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | SoD Analysis and Remediation |  | Missing Stream |  |  | _Saputo SEC Analyst 1 |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066891 | Yes | No | No | MCP | MCP - CDP | 03-Design/Build | SoD Analysis and Remediation |  | Missing Stream |  |  | _Saputo SEC Analyst 2 |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066892 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Support Role Build and UT |  | Missing Stream |  |  | _SEC Resource Onshore |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066893 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Support Role Build and UT | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066894 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Support Role Build and UT | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066895 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Support Role Build and UT | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066896 | No | Yes | No | MCP | MCP - CDP | 03-Design/Build | Support Role Build and UT | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066897 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Support Role Build and UT | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066898 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Defect Resolution |  | Missing Stream |  |  | _SEC Resource Onshore |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066899 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Defect Resolution | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Global | IT - External | 3.75h | 0h | 3.75h | 2016-10-10 | 2016-12-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066900 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Defect Resolution | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066901 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Defect Resolution | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Global | IT - External | 45h | 0h | 45h | 2016-10-10 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066902 | No | Yes | No | MCP | MCP - CDP | 03-Design/Build | Defect Resolution | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066903 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Defect Resolution | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Global | IT - External | 4h | 0h | 4h | 2016-10-17 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066904 | No | No | No | MCP | MCP - CDP | 03-Design/Build | Security Role FUT |  | Missing Stream |  |  | _SEC Resource Onshore |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-12-26 | 2016-12-26 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066905 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Security Role FUT | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2016-12-26 | 2016-12-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066906 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Security Role FUT | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2016-12-26 | 2016-12-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066907 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Security Role FUT | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Global | IT - External | 4.25h | 0h | 4.25h | 2016-12-26 | 2016-12-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 4.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066908 | No | Yes | No | MCP | MCP - CDP | 03-Design/Build | Security Role FUT | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2016-12-26 | 2016-12-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066909 | No | No | Yes | MCP | MCP - CDP | 03-Design/Build | Security Role FUT | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2016-12-26 | 2016-12-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066910 | No | No | Yes | MCP | MCP - CDP | 99-Global | Sharepoint Access | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes |  |  | IT - External | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066911 | No | No | No | MCP | MCP - CDP | 99-Global | Sharepoint Access | CDP | CDP | SI | Onshore | Adam; Alexander | SAP | Yes |  |  | IT - External | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066912 | No | Yes | No | MCP | MCP - CDP | 99-Global | Sharepoint Access | CDP | CDP | SI | Onshore | Bahloul; Nassim | SAP | Yes |  |  | IT - External | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066913 | No | Yes | No | MCP | MCP - CDP | 99-Global | Sharepoint Access | CDP | CDP | SI | Onshore | McLaren; Leanne | SAP | Yes |  |  | IT - External | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066914 | No | No | No | MCP | MCP - CDP | 99-Global | Sharepoint Access | CDP | CDP | SI | Onshore | Bisht; Amba | SAP | Yes |  |  | IT - External | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066915 | No | No | No | MCP | MCP - CDP | 99-Global | Sharepoint Access | CDP | CDP | SI | Onshore | Fu; Nenghong | SAP | Yes |  |  | IT - External | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066916 | No | Yes | No | MCP | MCP - CDP | 99-Global | Sharepoint Access | CDP | CDP | SI | Onshore | Gata; Ramanjaneyulu | SAP | Yes |  |  | IT - External | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066917 | No | Yes | No | MCP | MCP - CDP | 99-Global | Sharepoint Access | CDP | CDP | SI | Onshore | Jain; Megha | SAP | Yes |  |  | IT - External | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066918 | No | No | No | MCP | MCP - CDP | 99-Global | Sharepoint Access | CDP | CDP | SI | Onshore | Khatwa; RajeshKumar | SAP | Yes |  |  | IT - External | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066919 | No | Yes | No | MCP | MCP - CDP | 99-Global | Sharepoint Access | PMO | PMO | SI | Onshore | Aflalo; Michael | SAP | Yes |  |  | IT - External | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066920 | No | No | No | MCP | MCP - CDP | 99-Global | Sharepoint Access |  | Missing Stream |  |  | Hayes; AnnL |  | Yes |  |  |  | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066921 | No | No | Yes | MCP | MCP - CDP | 99-Global | Sharepoint Access | PMO | PMO | Saputo | Onshore | Bensoussan; Orly | Saputo | Yes |  |  | IT - Internal | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066922 | No | No | No | MCP | MCP - CDP | 99-Global | Sharepoint Access | PMO | PMO | Saputo | Onshore | Daitchman; Lorne | Saputo | Yes |  |  | IT - Internal | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066923 | No | No | Yes | MCP | MCP - CDP | 99-Global | Sharepoint Access | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes |  |  | Business | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066924 | No | No | No | MCP | MCP - CDP | 99-Global | Sharepoint Access |  | Missing Stream |  |  | Goetsch; Dianne_ |  | Yes |  |  |  | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066925 | No | Yes | No | MCP | MCP - CDP | 99-Global | Sharepoint Access | TAI | TAI | SI | Onshore | Doherty; Sean | Accenture | Yes |  |  | IT - External | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066926 | No | No | No | MCP | MCP - CDP | 99-Global | Sharepoint Access |  | Missing Stream | Saputo | Onshore | Dummer; Kirk | Saputo | Yes |  |  | IT - Internal | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066927 | No | Yes | No | MCP | MCP - CDP | 99-Global | Sharepoint Access | MDG | DC | SI | Onshore | Fonseca; Thiago | Accenture | Yes |  |  | IT - External | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066928 | No | Yes | No | MCP | MCP - CDP | 99-Global | Sharepoint Access | CDP | CDP | SI | Onshore | Glavas; William | SAP | Yes |  |  | IT - External | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066929 | No | No | No | MCP | MCP - CDP | 99-Global | Sharepoint Access | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes |  |  | IT - Internal | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066930 | No | No | Yes | MCP | MCP - CDP | 99-Global | Sharepoint Access | PMO | PMO | SI | Onshore | Ingram; Dave | IBM | Yes |  |  | IT - External | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066931 | No | No | Yes | MCP | MCP - CDP | 99-Global | Sharepoint Access |  | Missing Stream | Saputo | Onshore | Buytendorp; John | Saputo | Yes |  |  | IT - Internal | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066932 | No | No | No | MCP | MCP - CDP | 99-Global | Sharepoint Access |  | Missing Stream | Saputo | Onshore | Clark; Kirby | Saputo | Yes |  |  | Business | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066933 | No | Yes | No | MCP | MCP - CDP | 99-Global | Sharepoint Access | PTP | FUN | SI | Onshore | Lazure; Stephane | IBM | Yes |  |  | IT - External | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066934 | No | No | Yes | MCP | MCP - CDP | 99-Global | Sharepoint Access | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes |  |  | IT - Internal | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066935 | No | No | Yes | MCP | MCP - CDP | 99-Global | Sharepoint Access | PMO | PMO | Saputo | Onshore | Iñiguez Manuel | Saputo | Yes |  |  | IT - Internal | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066936 | No | No | Yes | MCP | MCP - CDP | 99-Global | Sharepoint Access | PMO | PMO | Saputo | Onshore | Martin; Jeff | Saputo | Yes |  |  | Business | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066937 | No | No | Yes | MCP | MCP - CDP | 99-Global | Sharepoint Access | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes |  |  | IT - Internal | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066938 | No | No | Yes | MCP | MCP - CDP | 99-Global | Sharepoint Access | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes |  |  | Business | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066939 | No | No | No | MCP | MCP - CDP | 99-Global | Sharepoint Access |  | Missing Stream | Saputo | Onshore | Zuliani Pablo | Saputo | Yes |  |  | Business | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066940 | No | Yes | Yes | MCP | MCP - CDP | 99-Global | Sharepoint Access | PMO | PMO | SI | Onshore | Porter; Stephanie | IBM | Yes |  |  | IT - External | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066941 | No | No | No | MCP | MCP - CDP | 99-Global | Sharepoint Access | PMO | PMO | Saputo | Onshore | Rivard; Richard | Saputo | Yes |  |  | IT - Internal | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066942 | No | No | No | MCP | MCP - CDP | 99-Global | Sharepoint Access |  | Missing Stream |  |  | Scroggins; Roger |  | Yes |  |  |  | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066943 | No | No | Yes | MCP | MCP - CDP | 99-Global | Sharepoint Access | PMO | PMO | SI | Onshore | Ruggerio; Michael | IBM | Yes |  |  | IT - External | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066944 | No | Yes | No | MCP | MCP - CDP | 99-Global | Sharepoint Access | SEC | SEC | SI | Onshore | Vernon; Franck | Accenture | Yes |  |  | IT - External | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066945 | No | No | No | MCP | MCP - CDP | 99-Global | Sharepoint Access | CDP | CDP | SI | Onshore | Bhasin; Badal | SAP | Yes |  |  | IT - External | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066946 | No | Yes | No | MCP | MCP - CDP | 99-Global | Sharepoint Access | CDP | CDP | SI | Onshore | Tuccia; Dolores | SAP | Yes |  |  | IT - External | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066947 | No | No | Yes | MCP | MCP - CDP | 99-Global | Sharepoint Access | RTR | FUN | Saputo | Onshore | Ethier; Patrice | Saputo | Yes |  |  | IT - Internal | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066948 | No | Yes | No | MCP | MCP - CDP | 99-Global | Sharepoint Access | PTP | FUN | SI | Onshore | Aditya; Kapoor | SAP | Yes |  |  | IT - External | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066949 | No | No | No | MCP | MCP - CDP | 99-Global | Sharepoint Access | CDP | CDP | SI | Onshore | Kayur; Goyal | SAP | Yes |  |  | IT - External | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066950 | No | No | Yes | MCP | MCP - CDP | 99-Global | Sharepoint Access | PMO | PMO | SI | Onshore | Kreuzer; Winfried | SAP | Yes |  |  | IT - External | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066951 | No | No | Yes | MCP | MCP - CDP | 99-Global | Sharepoint Access | PMO | PMO | Saputo | Onshore | Sabir; Kaoutar | Saputo | Yes |  |  | IT - Internal | 0h | 0h | 0h | 2016-07-23 | 2016-07-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066963 | No | No | No | Program | Program |  | Knowledge_Transfer_AMS - DEV |  | Missing Stream | Saputo |  | Dobriya; Raveesh | Saputo | Yes | OpEx | Global |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067030 | No | No | No | Program | Program |  | Provide Solution Architecture Authority | TAI | TAI |  |  | TBD Saputo Solution Arch 2 |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2016-02-01 | 2017-01-16 | No |  |  |  | Late | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067033 | No | No | No | Program | Program |  | TAI Leadership Oversight | DEV | DEV |  |  | TBD Enterprise Technology director |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-03-17 | 2017-03-17 | No |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067034 | No | No | No | Program | Program |  | GD - Provide RTR Application Design Solutions | RTR | FUN |  |  | TBD Saputo Director Finance |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067035 | No | No | No | Program | Program |  | ArG - provide Finance Application Design Solutions | RTR | FUN |  |  | TBD Saputo Director Finance |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067054 | No | No | No | Program | Program |  | Data Owner - Finance, Customer and Vendor | MDG | To Define |  |  | TBD Data Owner FIN Cus Vendor |  | Yes | OpEx | Global |  | 0h | 0h | 0h | 2016-07-29 | 2016-07-29 | No |  |  |  | Late | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067055 | No | No | No | Program | Program |  | Data Owner - Material,Supply Chain | MDG | To Define |  |  | TBD Data Owner Material SupplyChain |  | Yes | OpEx | Global |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067059 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO |  |  | Morel; Maria |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067060 | No | No | No | Program | Program |  | Change Management leadership | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-05-25 | 2017-05-25 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067061 | No | No | No | Program | Program | 01-Preparation | Mobilize Change Management - Saputo | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2015-09-14 | 2015-09-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067062 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067063 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTP | FUN | SI | Onshore | Vasudevan; Ramesh | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067064 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067065 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067066 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067067 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067068 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067069 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067070 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | SI | Onshore | Roloff; Patrick | SAP | Yes | OpEx | Global | IT - External | 19h | 0h | 19h | 2017-06-05 | 2017-08-25 | Yes |  | DMS |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0
1067071 | No | Yes | No | Program | Program | 03-Design/Build | Project Management | SEC | SEC | SI | Offshore | Co; Bryan | Accenture | Yes | CapEx | Global | IT - External | 243h | 0h | 243h | 2017-06-19 | 2017-07-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 36 | 45 | 45 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067072 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - SEC | SEC | SEC | SI | Offshore | Aragon; Marvin | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-07 | 2017-06-13 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067073 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - SEC | SEC | SEC | SI | Offshore | Ballada; EJ | Accenture | Yes | OpEx | Global | IT - External | 46h | 0h | 46h | 2017-06-19 | 2017-07-05 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 22.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067074 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | SI | Onshore | SerranoMartinez; Efren | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067075 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | SI | Onshore | Lakhal; Ahmed | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067076 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - Test | Test | Test | Saputo | Onshore | LagunaElliott; Karol | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-07-07 | 2017-07-07 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067077 | No | No | Yes | Program | Program |  | Provide Release and Environment Solutions | Test | Test | Saputo | Onshore | LagunaElliott; Karol | Saputo | Yes | CapEx | Global | IT - Internal | 1,017h | 663h | 1,680h | 2017-03-06 | 2017-11-16 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 32 | 32 | 40 | 40 | 32 | 40 | 35 | 35 | 35 | 40 | 40 | 32 | 0 | 0
1067078 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | Saputo | Onshore | Barreto; Bruno | Saputo | Yes | OpEx | Global | IT - Internal | 130.25h | 0h | 130.25h | 2017-06-12 | 2017-08-07 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 11.65 | 9 | 13.6 | 14 | 19.45 | 30.43 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0
1067079 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTP | PTP | FUN | SI | Onshore | Chettyar; Vidyasagar | IBM | Yes | OpEx | Global | IT - External | 151h | 0h | 151h | 2017-06-12 | 2017-07-07 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 27 | 36 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067080 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Onshore | Thorat; Yogini | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067081 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | Saputo | Onshore | Gomare; Shankar | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067082 | No | No | Yes | Program | Program |  | Delivery Leadership SAP | PMO | PMO | SI | Onshore | Caldwell; Samantha | SAP | Yes | CapEx | Global | IT - External | 202h | 120h | 322h | 2017-03-01 | 2017-12-29 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4.5 | 13 | 6 | 7.5 | 8 | 8 | 4 | 8 | 8 | 8 | 8 | 4 | 8 | 8 | 8 | 2 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 4 | 8 | 8 | 0
1067083 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Gupta; Debapriya | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-23 | 2017-06-23 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067084 | No | No | Yes | Program | Program |  | TAI - Project SAP Environment Support | TAI | TAI | Saputo | Onshore | Rajan; Sindhu | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 352h | 352h | 2017-08-01 | 2017-11-03 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067085 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | SI | Offshore | Gophane; Rupali | IBM | Yes | OpEx | Global | IT - External | 63h | 0h | 63h | 2017-06-12 | 2017-07-14 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 8 | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067086 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | SI | Offshore | Kusary; Bishwadeep | IBM | Yes | OpEx | Global | IT - External | 10h | 0h | 10h | 2017-06-19 | 2017-06-23 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067087 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | SI | Offshore | Salunke; Sachin | IBM | Yes | OpEx | Global | IT - External | 67.5h | 0h | 67.5h | 2017-06-12 | 2017-07-14 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 22.5 | 0 | 0 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067088 | No | No | Yes | Program | Program |  | TAI - Project SAP Environment Support | TAI | TAI | Saputo | Onshore | Maji; Dinesh | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 352h | 352h | 2017-08-01 | 2017-11-03 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067089 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - BI | BI | BI | Saputo | Onshore | Wilson; Karen | Saputo | Yes | OpEx | Global | IT - Internal | 49.5h | 0h | 49.5h | 2017-07-10 | 2017-07-16 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067090 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - TAI | TAI | TAI | Saputo | Onshore | Smith; Alex | Saputo | Yes | OpEx | Global | IT - Internal | 80h | 0h | 80h | 2017-07-10 | 2017-07-21 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067091 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - TAI | TAI | TAI | SI | Onshore | Chan; Philip | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067092 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | SI | Offshore | Rajenderan; Santhosh | IBM | Yes | OpEx | Global | IT - External | 45h | 0h | 45h | 2017-06-12 | 2017-06-16 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067093 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | SI | Offshore | Morales; Veronica | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-07-21 | 2017-07-21 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067094 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - SEC | SEC | SEC | SI | Offshore | Mendoza; Janinah | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-07 | 2017-06-07 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067095 | No | No | Yes | Program | Program | 03-Design/Build | SEC Project Support | SEC | SEC | SI | Offshore | Lim; Kentzie | Accenture | Yes | CapEx | Global | IT - External | 45h | 0h | 45h | 2016-10-11 | 2017-08-18 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0
1067096 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | OpEx | Global | IT - External | 4h | 0h | 4h | 2017-06-20 | 2017-06-22 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067097 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - Test | Test | Test | SI | Offshore | Bandyopadhyay; Koushik | IBM | Yes | OpEx | Global | IT - External | 157.5h | 0h | 157.5h | 2017-06-05 | 2017-07-07 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 22.5 | 45 | 18 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067098 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-07-21 | 2017-07-21 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067099 | No | Yes | No | Program | Program | 03-Design/Build | Global - Provide Functional Integration Solutions | PMO | PMO | SI | Onshore | West; Dane | IBM | Yes | CapEx | Global | IT - External | 200h | 0h | 200h | 2017-01-09 | 2017-02-10 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067100 | No | No | Yes | Program | Program |  | Delivery Leadership IBM | PMO | PMO | SI | Onshore | Lalchan; Myrtle | IBM | Yes | CapEx | Global | IT - External | 807h | 664h | 1,471h | 2017-01-16 | 2018-01-03 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 29 | 44 | 30 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 28 | 44 | 0
1067101 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067102 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - SEC | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | OpEx | Global | IT - Internal | 70h | 0h | 70h | 2017-06-19 | 2017-06-29 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067103 | No | No | Yes | Program | Program | 03-Design/Build | Security Management | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Global | IT - Internal | 201h | 0h | 201h | 2017-04-03 | 2017-07-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 49 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067104 | No | No | Yes | Program | Program |  | Provide SAP Security Design Solutions | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Global | IT - Internal | 568h | 0h | 568h | 2016-05-30 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067105 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067106 | No | No | Yes | Program | Program |  | GD - Provide Logistics Application Design Solutions | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Global | IT - Internal | 57h | 0h | 57h | 2016-05-16 | 2016-06-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067107 | No | No | Yes | Program | Program |  | ARG - Provide Logistics Application Design Solutions | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 39h | 0h | 39h | 2016-05-18 | 2016-06-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067108 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | OpEx | Global | IT - Internal | 38h | 0h | 38h | 2017-06-12 | 2017-08-11 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0
1067109 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067110 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067111 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | OpEx | Global | IT - External | 112h | 0h | 112h | 2017-06-21 | 2017-07-14 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 24 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067112 | No | Yes | No | Program | Program |  | Delivery Leadership IBM | RTR | FUN | SI | Onshore | Spivey; Greg | IBM | Yes | CapEx | Global | IT - External | 417h | 0h | 417h | 2016-06-06 | 2016-11-11 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067113 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - HR | HR | HR | Saputo | Onshore | Freire; Roberto | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-29 | 2017-06-29 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067114 | No | Yes | No | Program | Program |  | Transfer Pricing & Material Ledger SME | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Global | IT - External | 259h | 0h | 259h | 2016-08-22 | 2016-12-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067115 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | SI | Onshore | Sniezyk; Sebastian | IBM | Yes | OpEx | Global | IT - External | 19h | 0h | 19h | 2017-07-10 | 2017-07-27 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067116 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | OpEx | Global | IT - Internal | 29h | 0h | 29h | 2017-06-12 | 2017-08-03 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067117 | No | No | Yes | Program | Program |  | Onboarding | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | OpEx | Global | IT - Internal | 40h | 0h | 40h | 2016-11-28 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067118 | No | Yes | No | Program | Program | 03-Design/Build | SEC Project Support | SEC | SEC | SI |  | Igwenazor; Stella | Other | Yes | CapEx | Global | IT - External | 272h | 0h | 272h | 2016-11-14 | 2017-03-31 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 12 | 3 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067119 | No | No | Yes | Program | Program | 03-Design/Build | SEC Project Support | SEC | SEC | SI | Onshore | Pal; Gaurav | Accenture | Yes | CapEx | Global | IT - External | 40h | 0h | 40h | 2016-10-11 | 2017-03-17 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067120 | No | No | Yes | Program | AIF (in Program) |  | AIF-Security Design & Proof of Concept | SEC | SEC | SI | Onshore | Pal; Gaurav | Accenture | Yes | CapEx | Global | IT - External | 80h | 0h | 80h | 2017-03-20 | 2017-03-31 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067121 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - SEC | SEC | SEC | SI | Onshore | Pal; Gaurav | Accenture | Yes | OpEx | Global | IT - External | 156h | 0h | 156h | 2017-06-12 | 2017-07-07 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 44 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067122 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - SEC | Non ERP | Non ERP | SI |  | Ponnappa; Esha | Other | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-07 | 2017-06-07 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067123 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Singha; Arnab | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067124 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | OpEx | Global | IT - External | 8h | 0h | 8h | 2017-06-07 | 2017-06-08 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067125 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - TAI | TAI | TAI | SI | Offshore | Nunez; Lawrence | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-07-20 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067126 | No | No | Yes | Program | Program | 03-Design/Build | Build and Manage SAP Environments | TAI | TAI | SI | Offshore | Nunez; Lawrence | Accenture | Yes | CapEx | Global | IT - External | 742.5h | 0h | 742.5h | 2016-09-12 | 2017-09-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 22.5 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 22.5 | 22.5 | 18 | 22.5 | 18 | 18 | 0 | 0 | 0
1067127 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | Saputo | Onshore | Valin; Eric | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-22 | 2017-06-22 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067128 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - BI | BI | BI | SI | Onshore | Sheraz; Ali | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067129 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Kritika; Jain | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067130 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067131 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067132 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | SI | Offshore | Diwa; Karissa | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067133 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067134 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067135 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | SI | Offshore | Alviar; Maricar | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067136 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | SI | Offshore | Mangiliman; Maricar | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067137 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | SI | Offshore | Manalac; Edgar | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067138 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Doppalapudi; Nagaraju | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067139 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | Saputo | Onshore | Therien; Stephane | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-29 | 2017-06-29 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067140 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | SI | Onshore | Esquerro; Alejandro | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067141 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - CM | CM | CM | Saputo | Onshore | Gabra; Rania | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067142 | No | No | Yes | Program | Program |  | PMO-Communication | CM | CM | Saputo | Onshore | Gabra; Rania | Saputo | Yes | OpEx | Global | IT - Internal | 79.02h | 16h | 95.02h | 2016-10-24 | 2017-12-29 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 1.2 | 1.2 | 2.3 | 2.5 | 2 | 2 | 2 | 2 | 2 | 1.22 | 0 | 0 | 0 | 0 | 4.5 | 2.5 | 3.3 | 1.5 | 1 | 9 | 1 | 4 | 0 | 0 | 3 | 0 | 0 | 0 | 5 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 1 | 0 | 0
1067143 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-12 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067144 | No | Yes | No | Program | Program | 03-Design/Build | Design Technical Architecture (Deliverables) | TAI | TAI | SI | Onshore | Kingbo; David | Accenture | Yes | CapEx | Global | IT - External | 136h | 0h | 136h | 2016-08-11 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067145 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - TAI | TAI | TAI | SI | Onshore | Kingbo; David | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-08-25 | 2017-08-25 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067146 | No | Yes | No | Program | Program | 03-Design/Build | Basis Management | TAI | TAI | SI | Onshore | Kingbo; David | Accenture | Yes | CapEx | Global | IT - External | 684h | 0h | 684h | 2017-03-01 | 2017-07-07 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 36 | 32 | 40 | 40 | 32 | 40 | 40 | 34 | 40 | 46 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067147 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-05 | 2017-06-09 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067148 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | OpEx | Global | IT - External | 15h | 0h | 15h | 2017-06-19 | 2017-06-23 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067149 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067150 | No | No | Yes | Program | Enhancement Pack Application (in Program) |  | SAP SP SBX-Test-Support-OTC | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Global | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067151 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067152 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067153 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - SEC | Non ERP | Non ERP | SI | Onshore | Kabir; Fahad | Other | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-07 | 2017-06-07 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067154 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Trivedi; Mohit | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067155 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | OpEx | Global | IT - External | 36h | 0h | 36h | 2017-06-12 | 2017-07-21 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 8 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067156 | No | No | Yes | Program | Program |  | Provide Business Process Design Authority | PMO | PMO | Saputo | Onshore | Lawson; Ted | Saputo | Yes | CapEx | Global | Business | 774h | 850h | 1,624h | 2017-01-18 | 2018-02-02 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 24 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 0 | 30 | 37.5 | 37.5 | 0 | 37.5 | 30 | 37.5 | 37.5 | 30 | 37.5 | 30 | 30 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067157 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | OpEx | Global | IT - External | 54h | 0h | 54h | 2017-08-17 | 2017-08-24 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 36 | 0 | 0 | 0 | 0
1067158 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067159 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067160 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Tewari; Apoorva | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067161 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CDP | CDP | SI | Onshore | Ray; RajeshKumar | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067162 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CDP | CDP | SI | Onshore | Bhasin; Badal | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067163 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | SI | Onshore | Lucinda; Mariana | IBM | Yes | OpEx | Global | IT - External | 10h | 0h | 10h | 2017-07-21 | 2017-08-24 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0
1067164 | No | No | Yes | Program | Program |  | TAI – SolMan Design & Planning & Implementation | TAI | TAI | SI | Onshore | Thayyil; Shajariya | Accenture | Yes | OpEx | Global | IT - External | 582h | 80h | 662h | 2016-10-24 | 2017-09-29 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 56 | 0 | 0 | 40 | 40 | 40 | 40 | 35 | 30 | 32 | 32 | 40 | 35 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 | 5 | 5 | 0 | 0 | 0 | 0
1067165 | No | No | Yes | Program | Program |  | TAI - Technical Monitoring | TAI | TAI | SI | Onshore | Thayyil; Shajariya | Accenture | Yes | OpEx | Global | IT - External | 110h | 0h | 110h | 2016-10-24 | 2017-01-17 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 24 | 40 | 40 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067166 | No | No | Yes | Program | Program |  | TAI - ChaRM | TAI | TAI | SI | Onshore | Thayyil; Shajariya | Accenture | Yes | CapEx | Global | IT - External | 590h | 80h | 670h | 2016-10-24 | 2017-09-29 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 38 | 40 | 56 | 0 | 32 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 28 | 35 | 35 | 0 | 0 | 0 | 0
1067167 | No | No | Yes | Program | Program |  | TAI - Project SAP Environment Support | TAI | TAI | SI | Onshore | Thayyil; Shajariya | Accenture | Yes | CapEx | Global | IT - External | 289h | 0h | 289h | 2017-02-13 | 2017-06-29 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 0 | 0 | 0 | 5 | 10 | 40 | 32 | 40 | 40 | 40 | 35 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067168 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - TAI | TAI | TAI | SI | Onshore | Thayyil; Shajariya | Accenture | Yes | OpEx | Global | IT - External | 5h | 0h | 5h | 2017-06-19 | 2017-06-23 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067169 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067170 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | SI | Onshore | Capelli; Celia | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067171 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067172 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067173 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | OpEx | Global | IT - External | 5h | 0h | 5h | 2017-06-20 | 2017-06-20 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067174 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Perumalla; Shyla | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067175 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067176 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067177 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Basetti; Sunil | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067178 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | SI | Onshore | Koul; Kunal | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067179 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CM | CM | SI | Onshore | Goel; Ronika | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067180 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CM | CM | SI | Offshore | Rudrurkar; Vijay | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067181 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CDP | CDP | SI | Onshore | Kayur; Goyal | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067182 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTP | FUN | SI | Onshore | Aditya; Kapoor | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067183 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067184 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-05 | 2017-08-11 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067185 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - BI | BI | BI | SI | Landed Onshore | Matkar; Mithilesh | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067186 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067187 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Global | IT - Internal | 60h | 0h | 60h | 2017-06-05 | 2017-08-04 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067188 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTP | PTP | FUN | SI | Onshore | Deng; Roy | IBM | Yes | OpEx | Global | IT - External | 17h | 0h | 17h | 2017-08-02 | 2017-08-03 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067189 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067190 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DG | MDG | DG | Saputo | Onshore | Lentz; Jared | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-07-21 | 2017-07-21 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067191 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Ghoshbiswas; Veena | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067192 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - MDG - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | OpEx | Global | IT - External | 80h | 0h | 80h | 2017-06-26 | 2017-07-14 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067193 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | TAI | TAI | SI | Offshore | Imperial; Jhannica | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067194 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - TAI | TAI | TAI | SI | Offshore | Imperial; Jhannica | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-07-21 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067195 | No | No | Yes | Program | Program | 03-Design/Build | Build and Manage SAP Environments | TAI | TAI | SI | Offshore | Imperial; Jhannica | Accenture | Yes | CapEx | Global | IT - External | 1,649.5h | 0h | 1,649.5h | 2016-05-02 | 2017-09-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 27 | 45 | 45 | 45 | 36 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 0 | 0 | 22.5 | 22.5 | 22.5 | 4.5 | 0 | 0 | 0
1067196 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | OpEx | Global | IT - External | 4h | 0h | 4h | 2017-06-07 | 2017-06-07 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067197 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067198 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Gupta; Shubham | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067199 | No | Yes | No | Program | Program | 03-Design/Build | SEC Project Support | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067200 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - SEC | SEC | SEC | SI | Offshore | Olvida; Julio | Accenture | Yes | OpEx | Global | IT - External | 44h | 0h | 44h | 2017-06-07 | 2017-08-02 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067201 | No | Yes | No | Program | Program | 03-Design/Build | SEC Project Support | SEC | SEC | SI | Onshore | Jayasim; Franklin | IBM | Yes | CapEx | Global | IT - External | 46h | 0h | 46h | 2016-11-14 | 2016-11-22 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067202 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | OpEx | Global | IT - External | 11h | 0h | 11h | 2017-06-14 | 2017-06-19 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067203 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - PTP | PTP | FUN | SI | Onshore | Melville; Steven | IBM | Yes | OpEx | Global | IT - External | 154h | 0h | 154h | 2017-06-12 | 2017-07-03 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067204 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067205 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | OpEx | Global | IT - External | 140h | 0h | 140h | 2017-07-17 | 2017-07-28 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067206 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067207 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTP | FUN | SI | Offshore | Manoharan; Anandan | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067208 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - CM | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067209 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067210 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067211 | No | No | Yes | Program | Program | 03-Design/Build | SEC Project Support | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Global | IT - External | 1,677.4h | 0h | 1,677.4h | 2016-10-11 | 2017-08-31 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 18 | 35.5 | 36 | 44.5 | 9 | 45 | 45 | 36 | 45 | 27 | 45 | 43.25 | 42 | 18 | 36 | 27 | 38 | 36 | 45 | 36 | 45 | 36 | 36 | 45 | 45 | 27 | 45 | 45 | 36 | 45 | 49 | 27 | 45 | 27 | 45 | 36 | 0 | 0 | 0
1067212 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - SEC | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-07 | 2017-06-07 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067213 | No | No | Yes | Program | Program | 03-Design/Build | Technical Architecture & Infrastructure (Saputo) | TAI | TAI | Saputo | Onshore | Tengler; David | Saputo | Yes | CapEx | Global | IT - Internal | 224h | 0h | 224h | 2016-06-20 | 2016-07-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067214 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - TAI | TAI | TAI | Saputo | Onshore | Tengler; David | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067215 | No | No | Yes | Program | Program | 03-Design/Build | Basis Management | TAI | TAI | Saputo | Onshore | Tengler; David | Saputo | Yes | CapEx | Global | IT - Internal | 1,332h | 120h | 1,452h | 2016-11-21 | 2017-09-29 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 24 | 40 | 40 | 40 | 40 | 32 | 48 | 40 | 32 | 50 | 56 | 24 | 40 | 40 | 0 | 40 | 10 | 30 | 40 | 0 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 50 | 40 | 0 | 40 | 40 | 0 | 0 | 40 | 0 | 24 | 0 | 0
1067216 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | TAI | TAI | Saputo | Onshore | Tengler; David | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067217 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | Saputo | Onshore | Boisvert; Claude MIS | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067218 | No | No | Yes | Program | AIF (in Program) | 06-Hypercare | AIF-Hypercare | DEV | DEV | Saputo | Onshore | Boisvert; Claude MIS | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067219 | No | No | Yes | Program | Program | 03-Design/Build | Basis Management | TAI | TAI | Saputo | Onshore | Shindadkar; Amol | Saputo | Yes | CapEx | Global | IT - Internal | 576h | 0h | 576h | 2016-11-21 | 2017-03-03 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 24 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067220 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - TAI | TAI | TAI | Saputo | Onshore | Shindadkar; Amol | Saputo | Yes | OpEx | Global | IT - Internal | 60h | 0h | 60h | 2017-06-19 | 2017-08-14 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 10 | 10 | 10 | 10 | 8 | 2 | 0 | 0 | 0 | 0 | 0
1067221 | No | No | Yes | Program | Program |  | TAI - Project SAP Environment Support | TAI | TAI | Saputo | Onshore | Shindadkar; Amol | Saputo | Yes | CapEx | Global | IT - Internal | 645h | 160h | 805h | 2017-02-13 | 2017-09-29 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 40 | 40 | 20 | 20 | 16 | 30 | 20 | 8 | 20 | 20 | 16 | 27 | 20 | 20 | 20 | 16 | 10 | 20 | 23 | 31 | 10 | 24 | 38 | 40 | 48 | 0 | 0 | 0
1067222 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - SEC | SEC | SEC | SI | Offshore | Bobiles; CharmaineAnn | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-07 | 2017-06-20 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067223 | No | No | Yes | Program | Program | 03-Design/Build | SEC Project Support | SEC | SEC | SI | Offshore | Bobiles; CharmaineAnn | Accenture | Yes | CapEx | Global | IT - External | 243h | 0h | 243h | 2017-03-14 | 2017-08-31 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 17 | 4 | 6 | 9 | 0 | 27 | 22.5 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 22.5 | 18 | 22.5 | 18 | 0 | 0 | 0
1067224 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Balchandani; Roma | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067225 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - BI | BI | BI | SI | Onshore | Tata; SreeRama | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067226 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | BI | BI | SI | Onshore | Tata; SreeRama | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067227 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Agarwal; Sunil | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067228 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | Saputo | Onshore | Turner; Jonathan | Saputo | Yes | OpEx | Global | Business | 40h | 0h | 40h | 2017-06-27 | 2017-07-12 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 34 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067229 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | Saputo | Onshore | Montgomery; David | Saputo | Yes | OpEx | Global | IT - Internal | 137h | 0h | 137h | 2017-06-12 | 2017-08-25 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 8 | 0 | 0 | 0 | 0 | 39 | 0 | 22 | 8 | 40 | 0 | 0 | 0 | 0
1067230 | No | No | Yes | Program | Program |  | Delivery Leadership Accenture | PMO | PMO | SI | Offshore | Mortel; Hazel | Accenture | Yes | CapEx | Global | IT - External | 644.5h | 168h | 812.5h | 2017-02-01 | 2017-12-29 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 37.5 | 32 | 10 | 30 | 30 | 26.5 | 19 | 37.5 | 37.5 | 22.5 | 22.5 | 30 | 30 | 37.5 | 34.5 | 12.5 | 12.5 | 12.5 | 12.5 | 7.5 | 10 | 12.5 | 12.5 | 10 | 10 | 12.5 | 12.5 | 10 | 7.5 | 7.5 | 12.5 | 0 | 10
1067231 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | SI | Onshore | Debasis; Dey | IBM | Yes | OpEx | Global | IT - External | 1h | 0h | 1h | 2017-06-21 | 2017-06-21 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067232 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTP | FUN | SI | Onshore | Neurath; Julian | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067233 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | OpEx | Global | IT - Internal | 21.5h | 0h | 21.5h | 2017-06-20 | 2017-08-24 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 7 | 0 | 6.5 | 0 | 0 | 0 | 4 | 1 | 1 | 0 | 0 | 0 | 0
1067234 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - BI | BI | BI | SI | Offshore | Satpathy; Sovan | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067235 | No | No | Yes | Program | Enhancement Pack Application (in Program) |  | SAP SP SBX-Test-Support-BI | BI | BI | SI | Offshore | Satpathy; Sovan | IBM | Yes | CapEx | Global | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067236 | No | No | Yes | Program | Program |  | PDC Team Lead | TAI | TAI | SI | Offshore | Navarro; Ronald | Accenture | Yes | CapEx | Global | IT - External | 145h | 180h | 325h | 2017-03-06 | 2017-09-29 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 5 | 3 | 0 | 1 | 5 | 5 | 4 | 5 | 16 | 5 | 5 | 3 | 4 | 5 | 5 | 5 | 5 | 5 | 4 | 5 | 5 | 5 | 32 | 4 | 0 | 0 | 0
1067237 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - TAI | TAI | TAI | SI | Offshore | Navarro; Ronald | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067238 | No | No | Yes | Program | Program |  | TAI – Tools support | TAI | TAI | SI | Offshore | Navarro; Ronald | Accenture | Yes | OpEx | Global | IT - External | 106h | 0h | 106h | 2016-11-07 | 2017-04-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067239 | No | No | Yes | Program | Program |  | TAI - Project SAP Environment Support | TAI | TAI | SI | Offshore | Navarro; Ronald | Accenture | Yes | CapEx | Global | IT - External | 1,470h | 0h | 1,470h | 2016-11-14 | 2017-09-01 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 27 | 45 | 45 | 36 | 45 | 40 | 45 | 40 | 36 | 45 | 32 | 45 | 40 | 24 | 0 | 8 | 40 | 40 | 32 | 40 | 2 | 40 | 51 | 24 | 32 | 40 | 40 | 40 | 31 | 40 | 32 | 40 | 40 | 40 | 4 | 32 | 0 | 0 | 0
1067240 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | SI | Onshore | Gimenez; Pamela | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067241 | No | No | Yes | Program | Program |  | WorkPlanner - R3D | PMO | PMO | SI | Onshore | Rahal; George | Other | Yes | CapEx | Global | IT - External | 1,904h | 600h | 2,504h | 2016-11-14 | 2017-12-29 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 40 | 40 | 40 | 48 | 56 | 40 | 40 | 40 | 40 | 49 | 72 | 69 | 49 | 40 | 52 | 37 | 40 | 40 | 40 | 58 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 54 | 40 | 40 | 40 | 56 | 40 | 40 | 40 | 40 | 32 | 40 | 0
1067242 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - BI | BI | BI | SI | Onshore | Thakur; Uday | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067243 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - BI | BI | BI | SI | Offshore | Gadgil; Amruta | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067244 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - BI | BI | BI | SI | Offshore | Kokil; Sonal | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067245 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | OpEx | Global | Business | 90h | 0h | 90h | 2017-07-24 | 2017-09-08 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 40 | 0 | 10 | 32 | 0 | 0
1067246 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067247 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CDP | CDP | SI | Onshore | Tuccia; Dolores | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067248 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - HR | HR | HR | Saputo | Onshore | Merdaoui; Badis | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-22 | 2017-06-22 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067249 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | OpEx | Global | IT - Internal | 40h | 0h | 40h | 2017-07-17 | 2017-07-21 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067250 | No | No | Yes | Program | Program |  | Provide Orientation for Development solution | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | CapEx | Global | IT - Internal | 40h | 0h | 40h | 2016-08-08 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067251 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - CM | CM | CM | Saputo | Onshore | Lochner; Andrea | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067252 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - MDG - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | OpEx | Global | IT - External | 80h | 0h | 80h | 2017-07-31 | 2017-08-11 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0
1067253 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - SEC | SEC | SEC | SI | Onshore | Kumar; Sathish | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-07 | 2017-06-07 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067254 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | SEC | SEC | SI | Onshore | Kumar; Sathish | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067255 | No | Yes | No | Program | AIF (in Program) | 02-Analyze | - PDD interface 1 and interface 2 | DEV | DEV | SI | Onshore | Silverman; Joshua | SAP | Yes | CapEx | Global | IT - External | 8h | 0h | 8h | 2017-01-26 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067256 | No | Yes | No | Program | AIF (in Program) | 03-Design/Build | Training documentation and recording (support) | DEV | DEV | SI | Onshore | Silverman; Joshua | SAP | Yes | CapEx | Global | IT - External | 56.5h | 0h | 56.5h | 2017-03-23 | 2017-04-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 14 | 10.5 | 19 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067257 | No | Yes | No | Program | AIF (in Program) | 03-Design/Build | Security/Authorization (support) | DEV | DEV | SI | Onshore | Silverman; Joshua | SAP | Yes | CapEx | Global | IT - External | 10.5h | 0h | 10.5h | 2017-03-06 | 2017-03-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3.5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067258 | No | Yes | No | Program | AIF (in Program) | 04-Test | FUT 2 interfaces, 5 days per interface | DEV | DEV | SI | Onshore | Silverman; Joshua | SAP | Yes | CapEx | Global | IT - External | 32.5h | 0h | 32.5h | 2017-02-13 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.5 | 8 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067259 | No | Yes | No | Program | AIF (in Program) | 04-Test | SIT 2 interfaces, 5 days per interface (support) | DEV | DEV | SI | Onshore | Silverman; Joshua | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067260 | No | Yes | No | Program | AIF (in Program) | 05-Cutover/Go-live | Cutover | DEV | DEV | SI | Onshore | Silverman; Joshua | SAP | Yes | CapEx | Global | IT - External | 1.5h | 0h | 1.5h | 2017-04-26 | 2017-04-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067261 | No | Yes | No | Program | AIF (in Program) | 06-Hypercare | AIF-Hypercare | DEV | DEV | SI | Onshore | Silverman; Joshua | SAP | Yes | CapEx | Global | IT - External | 18.5h | 0h | 18.5h | 2017-04-24 | 2017-05-26 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5 | 6.5 | 3 | 3 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067262 | No | Yes | No | Program | AIF (in Program) | 02-Analyze | #VALUE! | DEV | DEV | SI | Onshore | Silverman; Joshua | SAP | Yes | CapEx | Global | IT - External | 3h | 0h | 3h | 2017-01-23 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067263 | No | Yes | No | Program | AIF (in Program) | 01-Preparation | Post installation activities | DEV | DEV | SI | Onshore | Silverman; Joshua | SAP | Yes | CapEx | Global | IT - External | 10h | 0h | 10h | 2017-01-18 | 2017-01-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067264 | No | Yes | No | Program | AIF (in Program) | 02-Analyze | #VALUE! | DEV | DEV | SI | Onshore | Silverman; Joshua | SAP | Yes | CapEx | Global | IT - External | 1h | 0h | 1h | 2017-01-23 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067265 | No | Yes | No | Program | AIF (in Program) | 01-Preparation | Build demo data to be leveraged in Analyze phase | DEV | DEV | SI | Onshore | Silverman; Joshua | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-01-25 | 2017-01-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067266 | No | Yes | No | Program | AIF (in Program) | 02-Analyze | - get requirements for interface 1 (process flow, Idoc details, key fields, alert details, etc.) | DEV | DEV | SI | Onshore | Silverman; Joshua | SAP | Yes | CapEx | Global | IT - External | 4h | 0h | 4h | 2017-01-24 | 2017-01-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067267 | No | Yes | No | Program | AIF (in Program) | 02-Analyze | - validate BPML, RTM for interface 1 | DEV | DEV | SI | Onshore | Silverman; Joshua | SAP | Yes | CapEx | Global | IT - External | 1h | 0h | 1h | 2017-01-24 | 2017-01-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067268 | No | Yes | No | Program | AIF (in Program) | 02-Analyze | - get requirements for interface 2 (process flow, Idoc details, key fields, alert details, etc.) | DEV | DEV | SI | Onshore | Silverman; Joshua | SAP | Yes | CapEx | Global | IT - External | 4h | 0h | 4h | 2017-01-25 | 2017-01-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067269 | No | Yes | No | Program | AIF (in Program) | 02-Analyze | #VALUE! | DEV | DEV | SI | Onshore | Silverman; Joshua | SAP | Yes | CapEx | Global | IT - External | 4h | 0h | 4h | 2017-01-25 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067270 | No | Yes | No | Program | AIF (in Program) | 02-Analyze | #VALUE! | DEV | DEV | SI | Onshore | Silverman; Joshua | SAP | Yes | CapEx | Global | IT - External | 3h | 0h | 3h | 2017-01-26 | 2017-01-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067271 | No | Yes | No | Program | AIF (in Program) | 02-Analyze | #VALUE! | DEV | DEV | SI | Onshore | Silverman; Joshua | SAP | Yes | CapEx | Global | IT - External | 1h | 0h | 1h | 2017-01-26 | 2017-01-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067272 | No | Yes | No | Program | AIF (in Program) | 02-Analyze | Summary Analyze phase | DEV | DEV | SI | Onshore | Silverman; Joshua | SAP | Yes | CapEx | Global | IT - External | 1h | 0h | 1h | 2017-01-27 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067273 | No | Yes | No | Program | AIF (in Program) | 03-Design/Build | Configuration (2 interfaces) | DEV | DEV | SI | Onshore | Silverman; Joshua | SAP | Yes | CapEx | Global | IT - External | 34.3h | 0h | 34.3h | 2017-01-30 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067274 | No | Yes | No | Program | AIF (in Program) | 03-Design/Build | SDD | DEV | DEV | SI | Onshore | Silverman; Joshua | SAP | Yes | CapEx | Global | IT - External | 11.2h | 0h | 11.2h | 2017-01-30 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067275 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Onshore | Nagarajan; Harish | IBM | Yes | OpEx | Global | IT - External | 45h | 0h | 45h | 2017-06-12 | 2017-06-16 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067276 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - SEC | SEC | SEC | SI | Onshore | Kothapalli; Omni | Accenture | Yes | OpEx | Global | IT - External | 94h | 0h | 94h | 2017-07-03 | 2017-07-14 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067277 | No | No | Yes | Program | Program | 03-Design/Build | SEC Project Support | SEC | SEC | SI | Onshore | Kothapalli; Omni | Accenture | Yes | CapEx | Global | IT - External | 27h | 0h | 27h | 2017-03-06 | 2017-05-26 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 8 | 6 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067278 | No | No | Yes | Program | AIF (in Program) |  | AIF-Security Design & Proof of Concept | SEC | SEC | SI | Onshore | Kothapalli; Omni | Accenture | Yes | CapEx | Global | IT - External | 163h | 0h | 163h | 2017-03-27 | 2017-05-24 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 40 | 38 | 34 | 23 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067279 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - CM | CM | CM | SI | Offshore | Basak; Dipannita | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067280 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | LOG | FUN | SI | Onshore | Thippanna; Ashok | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067281 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | Test | Test | SI | Onshore | Pontes; Andrea | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067282 | No | Yes | No | Program | Program | 03-Design/Build | SEC Project Support | SEC | SEC | SI | Offshore | DeBlas; RahpRelly | Accenture | Yes | CapEx | Global | IT - External | 463h | 0h | 463h | 2016-10-11 | 2017-02-03 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 14 | 32.5 | 42 | 41 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067283 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTP | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | OpEx | Global | IT - External | 8h | 0h | 8h | 2017-08-07 | 2017-08-10 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0
1067284 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  | DMS |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067285 | No | No | Yes | Program | Program |  | DMS KT – RTR - Product Costing - RTR | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  | DMS |  | Late | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067286 | No | No | Yes | Program | Program |  | DMS KT – RTR - Master Data (DDD, DCT) - RTR | RTR | FUN | SI | Onshore | Strobel; Lars | SAP | Yes | CapEx | Global | IT - External | 30.4h | 0h | 30.4h | 2016-10-24 | 2017-05-14 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 10.4 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067287 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | SI | Onshore | Strobel; Lars | SAP | Yes | OpEx | Global | IT - External | 15h | 0h | 15h | 2017-07-15 | 2017-07-17 | Yes |  | DMS |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067288 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Onshore | Poggenbeck; Carsten | SAP | Yes | OpEx | Global | IT - External | 22h | 0h | 22h | 2017-06-07 | 2017-07-14 | Yes |  | DMS |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 2 | 4 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067289 | No | No | Yes | Program | Program |  | DMS KT – PTM - Operations - PTM | PTM | FUN | SI | Onshore | Poggenbeck; Carsten | SAP | Yes | CapEx | Global | IT - External | 10h | 0h | 10h | 2017-04-18 | 2017-04-25 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067290 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - SEC | SEC | SEC | SI | Offshore | Valencia; Jackie | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-07 | 2017-06-07 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067291 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | OpEx | Global | IT - Internal | 99h | 0h | 99h | 2017-06-26 | 2017-07-17 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49.5 | 0 | 49.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067292 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-07-21 | 2017-07-21 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067293 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Onshore | Lu; Richard | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067294 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | OpEx | Global | IT - External | 17h | 0h | 17h | 2017-06-29 | 2017-07-25 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 2 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067295 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | OpEx | Global | IT - Internal | 6h | 0h | 6h | 2017-08-03 | 2017-09-08 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 4 | 0 | 0
1067296 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - SEC | Non ERP | Non ERP | Saputo | Onshore | Tavares; Fernando | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-07 | 2017-06-07 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067297 | No | No | Yes | Program | Program | 03-Design/Build | HARMONI Security/GRC Solution designs | Non ERP | Non ERP | Saputo | Onshore | Tavares; Fernando | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2017-02-24 | 2017-02-24 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067298 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | To Define | SI | Onshore | Manlapaz; Carmel | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067299 | No | No | Yes | Program | Program |  | Provide Release and Environment Solutions | Test | Test | Saputo | Onshore | Lee; Ryan | Saputo | Yes | CapEx | Global | IT - Internal | 1,331h | 712h | 2,043h | 2016-12-05 | 2017-12-11 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 32 | 40 | 40 | 40 | 40 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 35 | 40 | 40 | 32 | 0 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 32 | 32 | 32 | 24 | 40 | 40 | 40 | 24 | 16 | 16 | 40 | 24 | 0 | 0 | 0
1067300 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - Test | Test | Test | Saputo | Onshore | Lee; Ryan | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067301 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | Saputo | Onshore | Atkins; Aaon | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067302 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | OpEx | Global | IT - External | 6h | 0h | 6h | 2017-06-09 | 2017-06-14 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067303 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | To Define | SI | Offshore | Villar; Louare | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067304 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Onshore | Liu; Changning | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067305 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067306 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067307 | No | No | No | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  | DMS |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067308 | No | Yes | No | Program | Program |  | Delivery Leadership IBM | PMO | PMO | SI | Onshore | Dupont Champion; Francois | IBM | Yes | CapEx | Global | IT - External | 1,513h | 0h | 1,513h | 2016-07-11 | 2017-04-28 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 28 | 52 | 45 | 49 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 27 | 17 | 6 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067309 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | SI | Onshore | Dupont Champion; Francois | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067310 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - TAI | TAI | TAI | SI | Offshore | Lledo; Philip | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067311 | No | No | Yes | Program | Program | 03-Design/Build | Build and Manage SAP Environments | TAI | TAI | SI | Offshore | Lledo; Philip | Accenture | Yes | OpEx | Global | IT - External | 45h | 0h | 45h | 2016-09-26 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067312 | No | No | Yes | Program | Program | 03-Design/Build | Build and Manage SAP Environments | TAI | TAI | SI | Offshore | Lledo; Philip | Accenture | Yes | CapEx | Global | IT - External | 350h | 0h | 350h | 2016-09-07 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067313 | No | No | Yes | Program | Program |  | TAI – Tools support | TAI | TAI | SI | Offshore | Lledo; Philip | Accenture | Yes | OpEx | Global | IT - External | 89h | 0h | 89h | 2016-11-14 | 2017-02-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 12 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067314 | No | No | Yes | Program | Program |  | TAI - Project SAP Environment Support | TAI | TAI | SI | Offshore | Lledo; Philip | Accenture | Yes | CapEx | Global | IT - External | 974h | 0h | 974h | 2016-11-14 | 2017-09-01 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 27 | 36 | 45 | 40 | 0 | 0 | 0 | 6 | 5 | 3 | 36 | 45 | 45 | 36 | 45 | 23 | 32 | 45 | 27 | 45 | 45 | 45 | 45 | 9 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 18 | 0 | 0 | 0
1067315 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | OpEx | Global | IT - Internal | 15h | 0h | 15h | 2017-07-06 | 2017-07-20 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067316 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | SI | Onshore | Nieva; Ricardo | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067317 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | SI | Onshore | Rich; Laho | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067318 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTP | PTP | FUN | SI | Onshore | Smith; Adam | IBM | Yes | OpEx | Global | IT - External | 71h | 0h | 71h | 2017-07-04 | 2017-08-11 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 27 | 0 | 0 | 0 | 0 | 0 | 0
1067319 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-06 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067320 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | SI | Onshore | Steve; Leslie | IBM | Yes | OpEx | Global | IT - External | 92h | 0h | 92h | 2017-06-19 | 2017-07-28 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067321 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | OpEx | Global | IT - External | 171h | 0h | 171h | 2017-06-09 | 2017-07-16 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 85 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067322 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - CM | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067323 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | SI | Onshore | Arce; Hugo | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067324 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Bhat; Lavleen | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067325 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Bhat; Lavleen | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067326 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Ambekar; Shilpa | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067327 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Onshore | Velez; Edwin | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067328 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067329 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Revil; Dianne | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067330 | No | Yes | No | Program | Program |  | PMO admin and support | PMO | PMO | SI | Onshore | Imaogene; Bugie | IBM | Yes | CapEx | Global | IT - External | 861h | 0h | 861h | 2016-08-22 | 2017-01-27 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 26 | 44 | 44 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067331 | No | Yes | No | Program | Program |  | Solman Setup | PMO | PMO | SI | Onshore | Imaogene; Bugie | IBM | Yes | CapEx | Global | IT - External | 132h | 0h | 132h | 2017-02-13 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067332 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - SEC | SEC | SEC | SI | Onshore | Vanderveer; Monina | Accenture | Yes | OpEx | Global | IT - External | 32h | 0h | 32h | 2017-07-14 | 2017-07-21 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067333 | No | No | Yes | Program | Program | 03-Design/Build | GD - Design SAP Security Solutions | SEC | SEC | SI | Onshore | Vanderveer; Monina | Accenture | Yes | CapEx | Global | IT - External | 64h | 0h | 64h | 2016-08-24 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067334 | No | No | Yes | Program | Program | 03-Design/Build | Security Management | SEC | SEC | SI | Onshore | Vanderveer; Monina | Accenture | Yes | CapEx | Global | IT - External | 714h | 0h | 714h | 2017-03-20 | 2017-08-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 0 | 41 | 40 | 40 | 40 | 16 | 43 | 42 | 40 | 32 | 32 | 40 | 80 | 60 | 0 | 0 | 0 | 0 | 0 | 40 | 8 | 0 | 0 | 0
1067335 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Verma; Mamta | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067336 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | SI | Onshore | Racey; Michael | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067337 | No | No | Yes | Program | Program |  | Delivery Leadership IBM | PMO | PMO | SI | Onshore | Racey; Michael | IBM | Yes | CapEx | Global | IT - External | 512h | 120h | 632h | 2016-06-20 | 2017-12-29 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 0
1067338 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | Saputo | Onshore | Pavlovski; Victor | Saputo | Yes | OpEx | Global | Business | 48h | 0h | 48h | 2017-06-05 | 2017-08-04 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 8 | 6 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067339 | No | No | Yes | Program | Program |  | DMS SWAT-PTM | PTM | FUN | Saputo | Onshore | Pavlovski; Victor | Saputo | Yes | CapEx | Global | Business | 38h | 0h | 38h | 2017-09-04 | 2017-09-08 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 0
1067340 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - TAI | TAI | TAI | SI |  | Labrie; Yan | Akilon | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-09 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067341 | No | No | Yes | Program | Program | 03-Design/Build | Wintel Admin | TAI | TAI | SI |  | Labrie; Yan | Akilon | Yes | CapEx | Global | IT - External | 1,813.5h | 280h | 2,093.5h | 2016-08-15 | 2017-10-20 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 24 | 31 | 39 | 39 | 44 | 38 | 40 | 36 | 0 | 40 | 40 | 38 | 6 | 40 | 32 | 28 | 40 | 40 | 36 | 40 | 24 | 40 | 40 | 47 | 33 | 24 | 34 | 0 | 0 | 40 | 24 | 24 | 40 | 42 | 42 | 0 | 0 | 0
1067342 | No | No | Yes | Program | Program |  | Delivery Leadership IBM | PMO | PMO | SI | Onshore | Ranchero; Glenn | IBM | Yes | CapEx | Global | IT - External | 880h | 760h | 1,640h | 2017-03-06 | 2018-01-17 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 32 | 32 | 32 | 40 | 40 | 40 | 16 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 32 | 0 | 0
1067343 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | SI | Onshore | Kuhnmuench; Gretchen | Accenture | Yes | OpEx | Global | IT - External | 20h | 0h | 20h | 2017-06-19 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067344 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Onshore | Laferrara; Melisa | Accenture | Yes | OpEx | Global | IT - External | 36.5h | 0h | 36.5h | 2017-06-06 | 2017-07-14 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 7.5 | 11 | 9 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067345 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | SI | Offshore | Agarwal; Sagar | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067346 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | SI | Offshore | Crescini; Eleanor | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067347 | No | Yes | No | Program | Program |  | Delivery Leadership Accenture | PMO | PMO | SI | Offshore | Crescini; Eleanor | Accenture | Yes | CapEx | Global | IT - External | 955h | 0h | 955h | 2016-06-27 | 2017-01-13 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 21 | 22 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067348 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Taneja; Charushree | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067349 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | SI | Onshore | Dirndorfer; Johann | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067350 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Onshore | Dirndorfer; Johann | SAP | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | Yes |  | DMS |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067351 | No | Yes | No | Program | Program |  | Solman Setup | Test | Test | SI | Onshore | Wolk; Rob | IBM | Yes | CapEx | Global | IT - External | 324h | 0h | 324h | 2017-01-02 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 44 | 44 | 38 | 44 | 44 | 44 | 32 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067352 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - CM | CM | CM | Saputo | Onshore | Goldstein; Evan | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067353 | No | No | Yes | Program | Program |  | PMO-Communication | CM | CM | Saputo | Onshore | Goldstein; Evan | Saputo | Yes | OpEx | Global | IT - Internal | 36.05h | 17h | 53.05h | 2016-10-24 | 2017-12-29 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 1.2 | 1.5 | 2.5 | 2 | 2 | 2 | 2 | 2 | 2 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067354 | No | No | Yes | Program | AIF (in Program) | 03-Design/Build | Test case prep | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | CapEx | Global | IT - Internal | 24h | 0h | 24h | 2017-02-06 | 2017-02-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067355 | No | No | Yes | Program | AIF (in Program) | 02-Analyze | - PDD interface 1 and interface 2 | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | CapEx | Global | IT - Internal | 8h | 0h | 8h | 2017-01-26 | 2017-02-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067356 | No | No | Yes | Program | AIF (in Program) | 02-Analyze | #VALUE! | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | CapEx | Global | IT - Internal | 4h | 0h | 4h | 2017-01-26 | 2017-01-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067357 | No | No | Yes | Program | AIF (in Program) | 03-Design/Build | SDD | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | CapEx | Global | IT - Internal | 14.4h | 0h | 14.4h | 2017-01-30 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 3 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067358 | No | No | Yes | Program | AIF (in Program) | 04-Test | FUT 2 interfaces, 5 days per interface | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | CapEx | Global | IT - Internal | 40h | 0h | 40h | 2017-02-15 | 2017-03-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 20 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067359 | No | No | Yes | Program | AIF (in Program) | 04-Test | SIT 2 interfaces, 5 days per interface (support) | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | CapEx | Global | IT - Internal | 40h | 0h | 40h | 2017-02-27 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067360 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067361 | No | No | Yes | Program | AIF (in Program) | 05-Cutover/Go-live | Cutover | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | CapEx | Global | IT - Internal | 9h | 0h | 9h | 2017-04-17 | 2017-04-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067362 | No | No | Yes | Program | AIF (in Program) | 06-Hypercare | AIF-Hypercare | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | CapEx | Global | IT - Internal | 14h | 0h | 14h | 2017-05-01 | 2017-05-26 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067363 | No | No | Yes | Program | Program | 03-Design/Build | SEC Project Support | SEC | SEC | SI | Offshore | Santiago; Perzeus | Accenture | Yes | CapEx | Global | IT - External | 855h | 0h | 855h | 2016-12-15 | 2017-06-04 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 27 | 45 | 45 | 45 | 36 | 45 | 47 | 45 | 45 | 27 | 45 | 45 | 36 | 0 | 0 | 0 | 0 | 45 | 43 | 45 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067364 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CDP | CDP | SI | Onshore | Fu; Nenghong | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067365 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CDP | CDP | SI | Onshore | Khatwa; RajeshKumar | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067366 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CDP | CDP | SI | Onshore | Gata; Ramanjaneyulu | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067367 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CDP | CDP | SI | Onshore | Bisht; Amba | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067368 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CDP | CDP | SI | Onshore | Jain; Megha | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067369 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - BI | BI | BI | SI | Onshore | Chalasani; Rajiv | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067370 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CM | CM | SI | Onshore | Fernandez; Ruth | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067371 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CM | CM | Saputo | Onshore | Ritchot; Justine | Saputo | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067372 | No | No | Yes | Program | Program |  | Program Site Readiness Lead | PMO | PMO | Saputo | Onshore | Steringa; Dan | Saputo | Yes | OpEx | Localization | Business | 994h | 0h | 994h | 2016-09-12 | 2017-04-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 24 | 40 | 40 | 40 | 0 | 40 | 40 | 32 | 0 | 0 | 0 | 40 | 40 | 40 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067373 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | BI | BI | SI | Onshore | Tien; Thang | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067374 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CDP | CDP | SI | Onshore | Bahloul; Nassim | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067375 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CDP | CDP | SI | Onshore | McLaren; Leanne | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067376 | No | Yes | No | Program | Program | 03-Design/Build | GD - Provide Functional Integration Solutions | PMO | PMO | SI | Onshore | Forbes; Jeff | IBM | Yes | CapEx | Global | IT - External | 512.5h | 0h | 512.5h | 2016-08-15 | 2016-12-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067377 | No | Yes | No | Program | Program | 03-Design/Build | Global - Provide Functional Integration Solutions | PMO | PMO | SI | Onshore | Forbes; Jeff | IBM | Yes | CapEx | Global | IT - External | 897h | 0h | 897h | 2016-08-15 | 2017-04-20 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 32 | 40 | 40 | 40 | 40 | 59 | 88 | 64.5 | 40 | 40 | 40 | 40 | 40 | 0 | 40 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067378 | No | Yes | No | Program | Program |  | Delivery Leadership IBM | PMO | PMO | SI | Onshore | Sullivan; Andrea | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2016-02-01 | 2017-01-16 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067379 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | SI | Onshore | Masri; Remi | Accenture | Yes | OpEx | Global | IT - External | 40h | 0h | 40h | 2017-08-07 | 2017-08-11 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0
1067380 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | Saputo | Onshore | Kovacs; Robert | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067381 | No | No | Yes | Program | Program |  | Provide Solution Architecture Authority | PMO | PMO | Saputo | Onshore | Kovacs; Robert | Saputo | Yes | CapEx | Global | IT - Internal | 2,538.33h | 768h | 3,306.33h | 2016-05-30 | 2017-12-29 | Yes |  |  |  | Late | NA | NA | 0 |  |  | 0 | 0 | 32 | 0 | 55.98 | 40 | 40 | 40 | 87 | 86 | 59.1 | 21 | 43.35 | 0 | 46 | 45.9 | 45 | 32 | 40 | 40 | 40 | 40 | 50 | 49 | 45 | 0 | 0 | 0 | 0 | 86 | 56 | 48 | 40 | 60 | 60 | 60 | 60 | 0 | 48 | 0 | 0
1067382 | No | Yes | Yes | Program | Program |  | Provide Solution Architecture Authority | TAI | TAI | Saputo | Onshore | Patel; Rupesh | Saputo | Yes | CapEx | Global | IT - Internal | 594h | 0h | 594h | 2016-05-24 | 2016-09-09 | Yes |  |  |  | Late | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067383 | No | Yes | Yes | Program | Program |  | TAI - Project SAP Environment Support | TAI | TAI | Saputo | Onshore | Patel; Rupesh | Saputo | Yes | CapEx | Global | IT - Internal | 36h | 0h | 36h | 2017-02-13 | 2017-03-03 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067384 | No | Yes | Yes | Program | Program | 03-Design/Build | Basis Management | TAI | TAI | Saputo | Onshore | Patel; Rupesh | Saputo | Yes | CapEx | Global | IT - Internal | 645h | 0h | 645h | 2016-11-21 | 2017-02-24 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 32 | 42 | 42 | 46 | 49 | 62 | 55 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067385 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | TAI | TAI | Saputo | Onshore | Patel; Rupesh | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067386 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | RTR | FUN | Saputo | Onshore | Ethier; Patrice | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067387 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | Saputo | Onshore | Ethier; Patrice | Saputo | Yes | OpEx | Global | IT - Internal | 4h | 0h | 4h | 2017-06-19 | 2017-06-22 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067388 | No | No | Yes | Program | Program |  | DMS SWAT-RTR | RTR | FUN | Saputo | Onshore | Ethier; Patrice | Saputo | Yes | CapEx | Global | IT - Internal | 49h | 30h | 79h | 2017-08-22 | 2017-09-05 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 30 | 0 | 0 | 0
1067389 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Anne; Vikram | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067390 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - CM | CM | CM | SI | Onshore | Fischer; Gillian | IBM | Yes | OpEx | Global | IT - External | 24h | 0h | 24h | 2017-06-12 | 2017-08-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 4 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067391 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | OpEx | Global | IT - External | 133h | 0h | 133h | 2017-06-09 | 2017-09-08 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 9 | 19 | 12 | 20 | 14 | 5 | 14 | 10 | 9 | 5 | 9 | 4 | 0 | 0
1067392 | No | No | Yes | Program | Program |  | Delivery Leadership IBM | PMO | PMO | SI | Onshore | Smith; Stephen | IBM | Yes | CapEx | Global | IT - External | 715h | 0h | 715h | 2017-01-16 | 2017-08-04 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 44 | 44 | 28 | 36 | 39 | 25 | 32 | 0 | 2 | 6 | 44 | 44 | 27 | 31 | 29 | 40 | 40 | 12 | 40 | 0 | 40 | 32 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067393 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - BI | BI | BI | Saputo | Onshore | Chicoine; Luc | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-29 | 2017-06-29 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067394 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - BI | BI | BI | Saputo | Onshore | Archambault; Louis | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-29 | 2017-06-29 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067395 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Onshore | Suryadevara; Laxmi | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067396 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | Test | Test | SI | Onshore | Yadav; Manvender | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067397 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067398 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTP | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | OpEx | Global | IT - External | 32h | 0h | 32h | 2017-06-14 | 2017-07-24 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067399 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067400 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067401 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - SEC | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | OpEx | Global | IT - External | 36h | 0h | 36h | 2017-07-03 | 2017-07-06 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067402 | No | No | Yes | Program | Program | 03-Design/Build | SEC Project Support | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Global | IT - External | 189.65h | 0h | 189.65h | 2016-10-11 | 2017-03-31 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067403 | No | No | Yes | Program | Program | 03-Design/Build | Design Security Solutions and Support Security Project Team | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Global | IT - External | 342h | 0h | 342h | 2016-02-29 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067404 | No | No | Yes | Program | AIF (in Program) |  | AIF-Security Design & Proof of Concept | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-04-07 | 2017-04-07 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067405 | No | No | Yes | Program | Program | 03-Design/Build | Design Security Solutions and Support Security Project Team | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Global | IT - External | 337.5h | 0h | 337.5h | 2016-04-04 | 2016-06-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067406 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - SEC | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-07 | 2017-06-07 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067407 | No | No | Yes | Program | Program | 03-Design/Build | SEC Project Support | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Global | IT - External | 470.7h | 0h | 470.7h | 2016-11-02 | 2017-03-24 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 19.5 | 34 | 14 | 29 | 29.75 | 37.75 | 0 | 0 | 0 | 0 | 0 | 34 | 41.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067408 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067409 | No | No | Yes | Program | Program | 03-Design/Build | DBA Admin | TAI | TAI | Saputo | Onshore | Kendrick; Ludhimila | Saputo | Yes | CapEx | Global | IT - Internal | 96.5h | 72h | 168.5h | 2017-05-30 | 2017-11-03 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 6.5 | 20 | 9 | 10 | 8 | 2 | 0 | 0 | 6 | 5 | 7 | 5 | 8 | 0 | 0 | 0
1067410 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - TAI | TAI | TAI | Saputo | Onshore | Kendrick; Ludhimila | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-29 | 2017-06-29 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067411 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Acosta; Junel | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067412 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Acosta; Junel | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067413 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DM | SI | Offshore | Cheruku; Shiva | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067414 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Calope; Mary | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067415 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | HR | HR | SI | Onshore | Robbins; Doug | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067416 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - HR | HR | HR | SI | Onshore | Robbins; Doug | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067417 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access |  | Missing Stream | Saputo | Onshore | Bertrand; Benoit | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067418 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067419 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | OpEx | Global | IT - External | 11h | 0h | 11h | 2017-06-26 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067420 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-07-07 | 2017-07-07 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067421 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067422 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | TAI | TAI | SI | Offshore | Javier; Kristine | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067423 | No | Yes | No | Program | Program | 03-Design/Build | Build and Manage SAP Environments | TAI | TAI | SI | Offshore | Javier; Kristine | Accenture | Yes | CapEx | Global | IT - External | 789h | 0h | 789h | 2016-05-02 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067424 | No | Yes | No | Program | Program |  | TAI - Project SAP Environment Support | TAI | TAI | SI | Offshore | Javier; Kristine | Accenture | Yes | CapEx | Global | IT - External | 1,000h | 0h | 1,000h | 2016-11-14 | 2017-06-02 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 31 | 45 | 45 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 45 | 45 | 36 | 45 | 27 | 18 | 45 | 45 | 45 | 18 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067425 | No | Yes | No | Program | Program |  | TAI – Tools support | TAI | TAI | SI | Offshore | Javier; Kristine | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-02-24 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067426 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - TAI | TAI | TAI | SI | Offshore | Javier; Kristine | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067427 | No | No | Yes | Program | Enhancement Pack Application (in Program) |  | SAP SP SBX-Test-Support-PTP | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Global | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067428 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067429 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTP | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | OpEx | Global | IT - External | 14h | 0h | 14h | 2017-06-15 | 2017-08-16 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0
1067430 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | TAI | TAI | SI | Offshore | Laciste; Ryanell | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067431 | No | Yes | No | Program | Program | 03-Design/Build | Build and Manage SAP Environments | TAI | TAI | SI | Offshore | Laciste; Ryanell | Accenture | Yes | CapEx | Global | IT - External | 210.9h | 0h | 210.9h | 2016-02-01 | 2016-03-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067432 | No | Yes | No | Program | Program | 03-Design/Build | Design Technical Architecture (Deliverables) | TAI | TAI | SI | Offshore | Laciste; Ryanell | Accenture | Yes | CapEx | Global | IT - External | 23.1h | 0h | 23.1h | 2016-02-01 | 2016-02-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067433 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Dongare; Pranouti | IBM | Yes | OpEx | Global | IT - External | 3h | 0h | 3h | 2017-06-13 | 2017-06-13 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067434 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Dongare; Pranouti | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067435 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Ravi; Shankar | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067436 | No | Yes | No | Program | Program | 03-Design/Build | Basis Management | DEV | DEV | SI | Offshore | Ravi; Shankar | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2016-11-21 | 2016-11-21 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067437 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Singh; Satyanarayan | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067438 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | OpEx | Global | IT - External | 14h | 0h | 14h | 2017-06-14 | 2017-06-19 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067439 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067440 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CM | CM | SI | Onshore | Faleyimu; Dele | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067441 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Bh; Vamsi | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067442 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Arora; Maninder | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067443 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067444 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067445 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | OpEx | Global | IT - External | 8h | 0h | 8h | 2017-07-04 | 2017-07-07 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067446 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | SEC | SEC | SI | Onshore | Ebojoh; Omamerhi | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067447 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | HR | HR | Saputo | Onshore | Centeno; Katya | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067448 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - HR | HR | HR | Saputo | Onshore | Centeno; Katya | Saputo | Yes | OpEx | Global | IT - Internal | 4h | 0h | 4h | 2017-06-19 | 2017-06-22 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067449 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | OpEx | Global | IT - External | 43h | 0h | 43h | 2017-06-12 | 2017-07-14 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 8 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067450 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067451 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | SI | Onshore | Gudipudi; Raghu | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067452 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067453 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-07-21 | 2017-07-21 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067454 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | SI | Offshore | Paniza; Rolly | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067455 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067456 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | OpEx | Global | IT - External | 27h | 0h | 27h | 2017-06-15 | 2017-06-23 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067457 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067458 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067459 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067460 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-07-21 | 2017-07-21 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067461 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | Test | Test | SI | Offshore | Podder; Suman | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067462 | No | Yes | No | Program | Program |  | HP ALM Setup | Test | Test | SI | Offshore | Podder; Suman | IBM | Yes | CapEx | Global | IT - External | 137.5h | 0h | 137.5h | 2016-11-07 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067463 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Chourey; Vandana | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067464 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | OpEx | Global | IT - Internal | 15h | 0h | 15h | 2017-06-19 | 2017-07-28 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067465 | No | No | Yes | Program | Program |  | GD - Provide Logistics Application Design Solutions | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | CapEx | Global | IT - Internal | 434.6h | 0h | 434.6h | 2016-02-01 | 2016-07-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067466 | No | No | Yes | Program | Program |  | ARG - Provide Logistics Application Design Solutions | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | CapEx | Localization | IT - Internal | 210h | 0h | 210h | 2016-03-08 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067467 | No | No | Yes | Program | Program |  | Support Change Management Activities | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | OpEx | Global | IT - Internal | 1h | 0h | 1h | 2016-08-29 | 2016-08-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067468 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067469 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | SI | Offshore | Monge; Natalia | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067470 | No | Yes | No | Program | Program |  | PMO admin and support | PMO | PMO | SI | Offshore | Monge; Natalia | IBM | Yes | CapEx | Global | IT - External | 156h | 0h | 156h | 2016-04-06 | 2016-10-07 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067471 | No | No | No | Program | Program |  | PMO admin and support | PMO | PMO | SI | Offshore | Ramirez; Juan | IBM | Yes | CapEx | Global | IT - External | 535.5h | 0h | 535.5h | 2016-02-22 | 2016-10-07 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067472 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | SI | Offshore | Ramirez; Juan | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067473 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067474 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | OpEx | Global | IT - External | 2h | 0h | 2h | 2017-07-06 | 2017-07-06 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067475 | No | No | Yes | Program | Enhancement Pack Application (in Program) |  | SAP SP SBX-Test-Support-LOG | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Global | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067476 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | OpEx | Global | IT - External | 16h | 0h | 16h | 2017-06-05 | 2017-08-04 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067477 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067478 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | SI | Offshore | Crodua; Michelle | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067479 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | SI | Offshore | Perez; Lou | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067480 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | SI | Offshore | Unde; Paul | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067481 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Jaju; Nikhar | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067482 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Sharma; Namita | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067483 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067484 | No | No | Yes | Program | Program |  | GD - Provide SCM Application Design Solutions | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | CapEx | Global | IT - Internal | 312h | 0h | 312h | 2016-02-01 | 2016-08-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067485 | No | No | Yes | Program | Program |  | ARG - Provide SCM Application Design Solutions | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-24 | 2017-03-24 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067486 | No | No | Yes | Program | Program |  | Support Change Management Activities | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | OpEx | Global | IT - Internal | 120h | 0h | 120h | 2016-05-30 | 2016-06-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067487 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTP | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067488 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CM | CM | SI | Onshore | Pinard; Patricia | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067489 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | SI | Onshore | Ruggerio; Michael | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067490 | No | No | Yes | Program | Program |  | PMO admin and support | PMO | PMO | SI | Onshore | Ruggerio; Michael | IBM | Yes | CapEx | Global | IT - External | 3,022.5h | 660h | 3,682.5h | 2016-04-20 | 2017-12-29 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 23 | 47 | 56 | 76 | 47 | 47 | 36 | 44 | 61 | 70 | 41 | 52 | 51 | 48 | 37 | 39 | 51 | 51 | 60 | 46 | 28 | 44 | 26 | 40 | 27 | 0 | 0 | 40 | 40 | 40 | 62 | 35 | 37.5 | 44 | 44 | 28.5 | 44 | 0
1067491 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | OpEx | Global | IT - External | 106h | 0h | 106h | 2017-06-05 | 2017-08-14 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 48 | 15.65 | 0 | 0 | 0 | 0 | 0 | 5.35 | 6 | 2 | 0 | 0 | 0 | 0 | 0
1067492 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067493 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | SI | Onshore | Ferrante; Alfredo | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067494 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | LOG | FUN | SI | Onshore | Avila; Rafael | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067495 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Lodha; Chetan | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067496 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CM | CM | SI | Onshore | Koso; Melanie | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067497 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | BI | BI | SI | Onshore | Hamsala; Nagendra | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067498 | No | Yes | No | Program | Program | 03-Design/Build | Provide Technical solution for HANA architecture | BI | BI | SI | Onshore | Hamsala; Nagendra | IBM | Yes | CapEx | Global | IT - External | 264h | 0h | 264h | 2016-02-29 | 2016-06-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067499 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTP | FUN | SI | Onshore | Ruetz; Christoph | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067500 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - PTP | PTP | FUN | SI | Onshore | Ruetz; Christoph | SAP | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-08-25 | 2017-08-25 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067501 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTP | FUN | SI | Onshore | Armstrong; Craig | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067502 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067503 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-07-18 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067504 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - SEC | SEC | SEC | SI | Onshore | Khanna; Tara | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-07 | 2017-06-07 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067505 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | SEC | SEC | SI | Onshore | Khanna; Tara | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067506 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | SI | Onshore | Allard; Cynthia | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067507 | No | Yes | No | Program | Program |  | PMO admin and support | PMO | PMO | SI | Onshore | Allard; Cynthia | IBM | Yes | CapEx | Global | IT - External | 617.25h | 0h | 617.25h | 2016-10-03 | 2017-01-20 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 22.75 | 31 | 47 | 35.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067508 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTP | FUN | SI | Onshore | Pethtel; Melanie | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067509 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTP | PTP | FUN | SI | Onshore | Pethtel; Melanie | SAP | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-08-25 | 2017-08-25 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067510 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | SEC | SEC | SI | Onshore | Zwirek; Ian | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067511 | No | Yes | Yes | Program | Program | 10-PCR | PCR TBD - Infrastructure Security | SEC | SEC | SI | Onshore | Zwirek; Ian | Accenture | Yes | CapEx | Global | IT - External | 170h | 0h | 170h | 2016-05-02 | 2016-06-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067512 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CM | CM | Saputo | Onshore | Marcotte; Catherine | Saputo | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067513 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | Test | Test | Saputo | Onshore | Wong; Justin | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067514 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - Test | Test | Test | Saputo | Onshore | Wong; Justin | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067515 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Shinde; Amol | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067516 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | SI | Onshore | Letourneau; Benoit | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067517 | No | Yes | No | Program | Program |  | PMO admin and support | PMO | PMO | SI | Onshore | Letourneau; Benoit | IBM | Yes | CapEx | Global | IT - External | 1,068h | 0h | 1,068h | 2016-02-15 | 2016-08-26 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067518 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | TAI | TAI | SI | Onshore | Sundaresan; Shen | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067519 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access |  | Missing Stream | Saputo | Onshore | Maschio Verónica | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067520 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Raina; Urvashi | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067521 | No | Yes | No | Program | Program | 03-Design/Build | Coordinate Offshore Development Team | DEV | DEV | SI | Offshore | Raina; Urvashi | IBM | Yes | CapEx | Global | IT - External | 413h | 0h | 413h | 2016-03-07 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067522 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Singh; Virender | IBM | Yes | OpEx | Global | IT - External | 79h | 0h | 79h | 2017-06-05 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 9 | 4 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067523 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Singh; Virender | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067524 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Subhedar; Adheesh | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067525 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Subhedar; Adheesh | IBM | Yes | OpEx | Global | IT - External | 11h | 0h | 11h | 2017-06-22 | 2017-07-05 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067526 | No | No | Yes | Program | Enhancement Pack Application (in Program) |  | SAP SP Q1–Dev | DEV | DEV | SI | Offshore | Subhedar; Adheesh | IBM | Yes | CapEx | Global | IT - External | 0h | 180h | 180h | 2017-12-04 | 2018-02-02 | Yes |  |  |  | Future Task | 2017-12-04 | 2018-02-02 | 0 |  | 1000-1300 Quality-1310 Quality 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067527 | No | No | Yes | Program | Enhancement Pack Application (in Program) |  | SAP SP SBX–Dev | DEV | DEV | SI | Offshore | Subhedar; Adheesh | IBM | Yes | CapEx | Global | IT - External | 34h | 0h | 34h | 2017-07-25 | 2017-09-13 | Yes |  |  |  | Future Task | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 2 | 4 | 0 | 0 | 0 | 24 | 0
1067528 | No | No | Yes | Program | Enhancement Pack Application (in Program) |  | SAP SP Q2–Dev | DEV | DEV | SI | Offshore | Subhedar; Adheesh | IBM | Yes | CapEx | Global | IT - External | 0h | 180h | 180h | 2018-02-05 | 2018-04-06 | Yes |  |  |  | Future Task | 2018-02-05 | 2018-04-06 | 0 |  | 1000-1300 Quality-1320 Quality 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067529 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067530 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - MDG - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | OpEx | Global | IT - External | 23h | 0h | 23h | 2017-06-19 | 2017-07-28 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2 | 5 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067531 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067532 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067533 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067534 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-07-21 | 2017-07-21 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067535 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-07-21 | 2017-07-21 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067536 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067537 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067538 | No | No | Yes | Program | Program |  | DMS KT – PTM - Operations - PTM | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Global | IT - External | 14h | 0h | 14h | 2017-04-25 | 2017-05-19 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067539 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | OpEx | Global | IT - External | 120h | 0h | 120h | 2017-07-31 | 2017-08-25 | Yes |  | DMS |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 40 | 40 | 0 | 0 | 0 | 0
1067540 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067541 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Onshore | Goyal; Shinki | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067542 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | TAI | TAI | SI | Onshore | Barman; Tapan | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067543 | No | No | Yes | Program | Program | 03-Design/Build | Build and Manage SAP Environments | TAI | TAI | SI | Onshore | Barman; Tapan | Accenture | Yes | CapEx | Global | IT - External | 1,074h | 0h | 1,074h | 2016-02-29 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067544 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - TAI | TAI | TAI | SI | Onshore | Barman; Tapan | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-08 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067545 | No | No | Yes | Program | Program |  | TAI - Project SAP Environment Support | TAI | TAI | SI | Onshore | Barman; Tapan | Accenture | Yes | CapEx | Global | IT - External | 923h | 160h | 1,083h | 2017-03-06 | 2017-09-29 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 32 | 40 | 32 | 40 | 48 | 40 | 40 | 40 | 32 | 51 | 40 | 0 | 32 | 32 | 40 | 40 | 0 | 16 | 40 | 40 | 40 | 40 | 48 | 0 | 0 | 0
1067546 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Agrawal; Purvi | IBM | Yes | OpEx | Global | IT - External | 13h | 0h | 13h | 2017-06-05 | 2017-06-20 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067547 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Agrawal; Purvi | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067548 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067549 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTP | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | OpEx | Global | IT - External | 153h | 0h | 153h | 2017-06-13 | 2017-08-11 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 10 | 6 | 2 | 2 | 0 | 37 | 43 | 45 | 0 | 0 | 0 | 0 | 0 | 0
1067550 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTP | PTP | FUN | SI | Offshore | Ragusante; Paul | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067551 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTP | FUN | SI | Offshore | Ragusante; Paul | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067552 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | Test | Test | SI | Onshore | Don; Mark | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067553 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067554 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067555 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067556 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTP | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | OpEx | Global | IT - External | 7h | 0h | 7h | 2017-07-10 | 2017-07-13 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067557 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DG | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | OpEx | Global | IT - Internal | 157h | 0h | 157h | 2017-06-12 | 2017-08-17 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 9 | 12 | 14 | 31 | 3 | 6 | 9 | 27 | 31 | 0 | 0 | 0 | 0 | 0
1067558 | No | No | Yes | Program | Program |  | Data Governance Leadership - DG | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | OpEx | Global | IT - Internal | 968.5h | 0h | 968.5h | 2016-03-28 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067559 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067560 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067561 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-07-21 | 2017-07-21 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067562 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067563 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Tayal; Nidhi | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067564 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Tayal; Nidhi | IBM | Yes | OpEx | Global | IT - External | 11h | 0h | 11h | 2017-06-05 | 2017-06-22 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067565 | No | Yes | No | Program | Program | 03-Design/Build | Coordinate Offshore Development Team | DEV | DEV | SI | Offshore | Dipankar; Saha | IBM | Yes | CapEx | Global | IT - External | 94h | 0h | 94h | 2016-04-18 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067566 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Dipankar; Saha | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067567 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Guha; Arundhati | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067568 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Agarwal; Khushbu | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067569 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Agarwal; Khushbu | IBM | Yes | OpEx | Global | IT - External | 6h | 0h | 6h | 2017-06-15 | 2017-07-19 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067570 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Ghosh; Arindam | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067571 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067572 | No | No | Yes | Program | Program |  | Data Maintenance Leadership - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Global | IT - Internal | 481.7h | 0h | 481.7h | 2016-04-11 | 2016-07-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067573 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Global | IT - Internal | 108h | 0h | 108h | 2017-07-10 | 2017-07-21 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067574 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Kalra; Inderjeet | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067575 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Kalra; Inderjeet | IBM | Yes | OpEx | Global | IT - External | 10h | 0h | 10h | 2017-06-14 | 2017-06-22 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067576 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Prakash; Gaurav | IBM | Yes | OpEx | Global | IT - External | 4h | 0h | 4h | 2017-06-14 | 2017-06-23 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067577 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | Prakash; Gaurav | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067578 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067579 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | OpEx | Global | Business | 22.5h | 0h | 22.5h | 2017-06-12 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067580 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | OpEx | Global | Business | 0h | 0h | 0h | 2017-08-25 | 2017-08-25 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067581 | No | No | Yes | Program | Program |  | GD - Provide OTC Process Design Solutions | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Global | Business | 788h | 0h | 788h | 2016-02-01 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067582 | No | No | Yes | Program | Program |  | ARG - Provide OTC Process Design Solutions | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 124h | 0h | 124h | 2016-02-01 | 2016-05-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067583 | No | No | Yes | Program | Program |  | Support Change Management Activities | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | OpEx | Global | Business | 71.5h | 0h | 71.5h | 2016-02-01 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067584 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067585 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067586 | No | No | Yes | Program | Program |  | GD - Provide PTM Process Design Solutions | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | CapEx | Global | Business | 687h | 0h | 687h | 2016-02-01 | 2016-08-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067587 | No | No | Yes | Program | Program |  | ARG - Provide PTM Process Design Solutions | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | CapEx | Localization | Business | 198h | 0h | 198h | 2016-02-22 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067588 | No | No | Yes | Program | Program |  | Support Change Management Activities | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | OpEx | Global | Business | 147h | 0h | 147h | 2016-02-01 | 2016-06-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067589 | No | No | Yes | Program | Program |  | DMS SWAT-PTM | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | CapEx | Global | Business | 28h | 19.17h | 47.17h | 2017-08-28 | 2017-09-12 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0
1067590 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | OpEx | Global | Business | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067591 | No | No | Yes | Program | Program |  | GD - Provide RTR Process Design Solutions | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | CapEx | Global | Business | 466h | 0h | 466h | 2016-02-01 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067592 | No | No | Yes | Program | Program |  | ARG - Provide RTR Process Design Solutions | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | CapEx | Localization | Business | 76h | 0h | 76h | 2016-02-01 | 2016-06-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067593 | No | No | Yes | Program | Program |  | Support Change Management Activities | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | CapEx | Localization | Business | 171.58h | 0h | 171.58h | 2016-02-01 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067594 | No | No | Yes | Program | Program |  | CF - Provide BPC Process Design Solutions | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | CapEx | Global | Business | 107h | 0h | 107h | 2016-02-01 | 2016-07-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067595 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067596 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | OpEx | Global | Business | 10h | 0h | 10h | 2017-06-05 | 2017-06-09 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067597 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067598 | No | No | Yes | Program | Program |  | ARG - Provide Logistics Process Design Solutions | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 144h | 0h | 144h | 2016-02-01 | 2016-07-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067599 | No | No | Yes | Program | Program |  | GD - Provide Logistics Process Design Solutions | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Global | Business | 702h | 0h | 702h | 2016-02-01 | 2016-08-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067600 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | OpEx | Global | Business | 142h | 0h | 142h | 2017-06-12 | 2017-07-03 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 30 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067601 | No | No | Yes | Program | Program |  | Support Change Management Activities | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | OpEx | Global | Business | 74.5h | 0h | 74.5h | 2016-02-01 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067602 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | OpEx | Global | Business | 2h | 0h | 2h | 2017-06-12 | 2017-06-12 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067603 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067604 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067605 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | OpEx | Global | Business | 0h | 0h | 0h | 2017-06-05 | 2017-07-14 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067606 | No | No | Yes | Program | Program |  | DMS SWAT-RTR | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Global | Business | 40h | 30h | 70h | 2017-08-21 | 2017-09-05 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0
1067607 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067608 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | OpEx | Global | Business | 164h | 0h | 164h | 2017-06-12 | 2017-08-25 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 15 | 10 | 57 | 12 | 0 | 54 | 0 | 0 | 0 | 0
1067609 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | Saputo | Onshore | Cook; Darrius | Saputo | Yes | OpEx | Global | Business | 0h | 0h | 0h | 2017-08-25 | 2017-08-25 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067610 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | OTC | FUN | Saputo | Onshore | Cook; Darrius | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067611 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067612 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | OpEx | Global | Business | 13h | 0h | 13h | 2017-06-26 | 2017-07-07 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067613 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | OpEx | Global | Business | 132h | 0h | 132h | 2017-06-12 | 2017-08-18 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 10.5 | 10.5 | 0 | 12 | 10 | 20 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0
1067614 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067615 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067616 | No | No | Yes | Program | Program |  | GD - Provide PTP Process Design Solutions | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Global | Business | 704.87h | 0h | 704.87h | 2016-02-01 | 2016-08-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067617 | No | No | Yes | Program | Program |  | ARG - Provide PTP Process Design Solutions | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 119h | 0h | 119h | 2016-02-01 | 2016-08-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067618 | No | No | Yes | Program | Program |  | Support Change Management Activities | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | OpEx | Global | Business | 67.5h | 0h | 67.5h | 2016-02-03 | 2016-08-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067619 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTP | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | OpEx | Global | Business | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067620 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067621 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | OpEx | Global | Business | 50h | 0h | 50h | 2017-06-12 | 2017-07-07 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 11 | 15 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067622 | No | No | Yes | Program | Program |  | Delivery Leadership IBM | PMO | PMO | SI | Onshore | Ingram; Dave | IBM | Yes | CapEx | Global | IT - External | 2,321h | 0h | 2,321h | 2016-02-01 | 2017-04-21 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 24 | 40 | 40 | 40 | 40 | 40 | 40 | 56 | 40 | 40 | 36 | 0 | 32 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067623 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | SI | Onshore | Ingram; Dave | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067624 | No | No | Yes | Program | Program | 03-Design/Build | Global - Provide Functional Integration Solutions | PMO | PMO | SI | Onshore | Ingram; Dave | IBM | Yes | CapEx | Global | IT - External | 592h | 728h | 1,320h | 2017-04-21 | 2018-01-15 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0
1067625 | No | No | Yes | Program | Program |  | DMS SWAT-PMO | PMO | PMO | SI | Onshore | Ingram; Dave | IBM | Yes | CapEx | Global | IT - External | 104h | 0h | 104h | 2017-08-21 | 2017-09-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 32 | 32 | 0 | 0
1067626 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | To Define | SI | Offshore | Mukherjee; Subhra | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067627 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | To Define | SI | Offshore | Ganesh; Sarumathi | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067628 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | To Define | SI | Offshore | Kumar; Deepak | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067629 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | SI | Onshore | Noel; Alain | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067630 | No | No | Yes | Program | Program |  | Delivery Leadership SAP | PMO | PMO | SI | Onshore | Noel; Alain | SAP | Yes | CapEx | Global | IT - External | 1,968h | 640h | 2,608h | 2016-01-18 | 2017-12-29 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 24 | 40 | 40 | 40 | 40 | 16 | 40 | 40 | 8 | 40 | 0 | 0 | 32 | 40 | 40 | 24 | 40 | 32 | 24 | 40 | 40 | 0 | 0 | 40 | 40 | 16 | 32 | 40 | 40 | 40 | 40 | 32 | 40 | 24 | 32 | 0 | 24 | 0 | 0
1067631 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CDP | CDP | SI | Onshore | Routhier; pierre | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067632 | No | Yes | Yes | Program | Program |  | Services and Support leadership | CDP | CDP | SI | Onshore | Routhier; pierre | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067633 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067634 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067635 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067636 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067637 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067638 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067639 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | OpEx | Global | IT - External | 36h | 0h | 36h | 2017-06-12 | 2017-08-31 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0
1067640 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067641 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | SI | Offshore | Lande; Kiran | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067642 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067643 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | OpEx | Global | IT - External | 47.5h | 0h | 47.5h | 2017-06-05 | 2017-08-18 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2.5 | 8 | 0 | 0 | 2 | 13 | 0 | 5 | 10 | 5 | 0 | 0 | 0 | 0 | 0
1067644 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067645 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067646 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | OpEx | Global | IT - External | 83h | 0h | 83h | 2017-06-12 | 2017-08-18 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 8 | 4 | 5 | 10 | 27 | 3 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0
1067647 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTP | FUN | SI | Offshore | Zute; Sudeep | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067648 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTP | PTP | FUN | SI | Offshore | Zute; Sudeep | IBM | Yes | OpEx | Global | IT - External | 7h | 0h | 7h | 2017-06-19 | 2017-06-27 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067649 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access |  | Missing Stream | Saputo | Onshore | Clark; Kirby | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067650 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | OTC | FUN | Saputo | Onshore | Rubina; Michelle | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067651 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | Saputo | Onshore | Aikens; Curtis | Saputo | Yes | OpEx | Global | Business | 20h | 0h | 20h | 2017-06-26 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067652 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | OTC | FUN | Saputo | Onshore | Aikens; Curtis | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067653 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | RTR | FUN | SI | Onshore | Herrenknecht; Andreas | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067654 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | SI | Onshore | Herrenknecht; Andreas | SAP | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  | DMS |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067655 | No | No | Yes | Program | Program |  | DMS KT – RTR - Product Costing - RTR | RTR | FUN | SI | Onshore | Bodfeld; Frank | SAP | Yes | CapEx | Global | IT - External | 40h | 0h | 40h | 2016-10-24 | 2017-04-27 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067656 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | RTR | FUN | SI | Onshore | Bodfeld; Frank | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067657 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | SI | Onshore | Bodfeld; Frank | SAP | Yes | OpEx | Global | IT - External | 24h | 0h | 24h | 2017-06-19 | 2017-06-21 | Yes |  | DMS |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067658 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | SI | Onshore | Beiderhase; Thomas | SAP | Yes | OpEx | Global | IT - External | 6h | 0h | 6h | 2017-07-04 | 2017-07-27 | Yes |  | DMS |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067659 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | RTR | FUN | SI | Onshore | Beiderhase; Thomas | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067660 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | RTR | FUN | SI | Onshore | Kranich; Oliver | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067661 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | SI | Onshore | Roth; Edgar | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067662 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Onshore | Roth; Edgar | SAP | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | Yes |  | DMS |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067663 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Onshore | Hagelauer; Harald | SAP | Yes | OpEx | Global | IT - External | 68h | 0h | 68h | 2017-06-28 | 2017-09-08 | Yes |  | DMS |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0
1067664 | No | No | Yes | Program | Program |  | DMS KT – PTM - Operations - PTM | PTM | FUN | SI | Onshore | Hagelauer; Harald | SAP | Yes | CapEx | Global | IT - External | 36h | 0h | 36h | 2017-05-04 | 2017-05-15 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067665 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | SI | Onshore | Hagelauer; Harald | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067666 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067667 | No | No | Yes | Program | Program |  | DMS KT – PTM - Raw Material Planning - PTM | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Global | IT - External | 32h | 0h | 32h | 2017-04-18 | 2017-04-21 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067668 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | OpEx | Global | IT - External | 8h | 0h | 8h | 2017-06-13 | 2017-06-21 | Yes |  | DMS |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067669 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | Saputo | Onshore | Durham; Cecil | Saputo | Yes | OpEx | Global | Business | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067670 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | Saputo | Onshore | Durham; Cecil | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067671 | No | Yes | No | Program | Program |  | Provide Solution Architecture Authority | PMO | PMO | SI | Onshore | Rahman; Maiko | SAP | Yes | CapEx | Global | IT - External | 1,933h | 0h | 1,933h | 2016-02-01 | 2017-03-03 | Yes |  |  |  | Late | NA | NA | 0 |  |  | 0 | 0 | 0 | 40 | 32 | 40 | 40 | 24 | 32 | 40 | 40 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067672 | No | Yes | No | Program | Program |  | Provide Solution Architecture Authority - CF | PMO | PMO | SI | Onshore | Rahman; Maiko | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067673 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | SI | Onshore | Rahman; Maiko | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067674 | No | Yes | No | Program | Program |  | Provide Solution Architecture Authority - Argentina | PMO | PMO | SI | Onshore | Rahman; Maiko | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067675 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | TAI | TAI | SI | Onshore | Lau; Kim | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067676 | No | Yes | Yes | Program | Program | 03-Design/Build | Design Technical Architecture (Deliverables) | TAI | TAI | SI | Onshore | Lau; Kim | Accenture | Yes | CapEx | Global | IT - External | 160h | 0h | 160h | 2016-07-18 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067677 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTP | FUN | SI | Onshore | Chandrakanthan; Muthukumar | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067678 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | SI | Onshore | May; Charles | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067679 | No | Yes | No | Program | Program | 03-Design/Build | GD - Design SAP RTR Solution | PMO | PMO | SI | Onshore | May; Charles | IBM | Yes | CapEx | Global | IT - External | 73h | 0h | 73h | 2016-02-03 | 2016-02-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067680 | No | Yes | No | Program | Program | 03-Design/Build | CF - Design SAP RTR Solution | PMO | PMO | SI | Onshore | May; Charles | IBM | Yes | CapEx | Global | IT - External | 9h | 0h | 9h | 2016-02-17 | 2016-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067681 | No | Yes | No | Program | Program | 03-Design/Build | ARG - Design SAP RTR Solution | PMO | PMO | SI | Onshore | May; Charles | IBM | Yes | CapEx | Localization | IT - External | 14h | 0h | 14h | 2016-02-12 | 2016-02-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067682 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067683 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | Saputo | Onshore | Razavinia; Nayereh | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067684 | No | No | Yes | Program | Program |  | Program Control Saputo | PMO | PMO | Saputo | Onshore | Razavinia; Nayereh | Saputo | Yes | OpEx | Global | IT - Internal | 3,005.8h | 647.8h | 3,653.6h | 2016-02-01 | 2018-01-05 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 24 | 34 | 42 | 32 | 8 | 44 | 42 | 44 | 42 | 40 | 40 | 40 | 8 | 40 | 40 | 32 | 32 | 40 | 40 | 40 | 0 | 32 | 40 | 40 | 44 | 32 | 32 | 40 | 40 | 42 | 40 | 41 | 40 | 47 | 43 | 45 | 27 | 0 | 0
1067685 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067686 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | OpEx | Global | IT - External | 5h | 0h | 5h | 2017-06-07 | 2017-06-12 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067687 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTP | FUN | SI | Onshore | Louay; Abuomar | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067688 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Landed Onshore | Tubati; Pavan | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067689 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Landed Onshore | Tubati; Pavan | IBM | Yes | OpEx | Global | IT - External | 13h | 0h | 13h | 2017-06-05 | 2017-06-27 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067690 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTP | FUN | SI | Onshore | Sweetman; kelly | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067691 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | Saputo | Onshore | Tenhagen; Chris | Saputo | Yes | OpEx | Global | Business | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067692 | No | No | Yes | Program | Program |  | Site Assessment Analysis | PTM | FUN | Saputo | Onshore | Tenhagen; Chris | Saputo | Yes | OpEx | Localization | Business | 973h | 0h | 973h | 2016-09-12 | 2017-03-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 24 | 40 | 40 | 32 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067693 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | Saputo | Onshore | Tenhagen; Chris | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067694 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067695 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTP | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | OpEx | Global | IT - Internal | 1h | 0h | 1h | 2017-08-03 | 2017-08-03 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067696 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | LOG | FUN | Saputo | Onshore | Seabrook; Vern | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067697 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | EDI | EDI | Saputo | Onshore | Tanguay; Yves | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067698 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - EDI | EDI | EDI | Saputo | Onshore | Tanguay; Yves | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-14 | 2017-06-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067699 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | Saputo | Onshore | Archambault; Yannick | Saputo | Yes | OpEx | Global | IT - Internal | 20h | 0h | 20h | 2017-06-12 | 2017-07-28 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 6 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067700 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | LOG | FUN | Saputo | Onshore | Archambault; Yannick | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067701 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | OTC | FUN | Saputo | Onshore | Larose; Line | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067702 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | Saputo | Onshore | Larose; Line | Saputo | Yes | OpEx | Global | IT - Internal | 21h | 0h | 21h | 2017-06-12 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067703 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - EDI | EDI | EDI | Saputo | Onshore | Szilbereisz; Norman | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-14 | 2017-06-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067704 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | EDI | EDI | Saputo | Onshore | Szilbereisz; Norman | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067705 | No | No | Yes | Program | Program | 03-Design/Build | HARMONI Security/GRC Solution designs | Non ERP | Non ERP | Saputo | Onshore | Beland; Yves | Saputo | Yes | CapEx | Global | IT - Internal | 462h | 0h | 462h | 2016-05-09 | 2016-11-18 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067706 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | Non ERP | Non ERP | Saputo | Onshore | Beland; Yves | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067707 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - BI | BI | BI | Saputo | Onshore | Arcuri; Rosalie | Saputo | Yes | OpEx | Global | IT - Internal | 32h | 0h | 32h | 2017-06-15 | 2017-06-22 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067708 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | BI | BI | Saputo | Onshore | Arcuri; Rosalie | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067709 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - BI | BI | BI | Saputo | Onshore | McCubbin; Andrew | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-29 | 2017-06-29 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067710 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - BI | BI | BI | Saputo | Onshore | Dupont; Normand | Saputo | Yes | OpEx | Global | IT - Internal | 2h | 0h | 2h | 2017-08-07 | 2017-08-09 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
1067711 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | BI | BI | Saputo | Onshore | Dupont; Normand | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067712 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | Saputo | Onshore | Tremblay; Denis | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067713 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - EDI | EDI | EDI | Saputo | Onshore | Schembari; Jeanne | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-14 | 2017-06-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067714 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-07-07 | 2017-07-07 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067715 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - SEC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067716 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - EDI | EDI | EDI | Saputo | Onshore | Loiselle; Sylvain | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-14 | 2017-06-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067717 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-29 | 2017-06-29 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067718 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067719 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | Saputo | Onshore | Ho; Lien-Chi | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067720 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - EDI | EDI | EDI | Saputo | Onshore | Cecere; Maria | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-14 | 2017-06-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067721 | No | No | Yes | Program | Program |  | DMS SWAT-PTM | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | CapEx | Global | IT - Internal | 46.25h | 46.45h | 92.7h | 2017-08-22 | 2017-09-19 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 21.25 | 0 | 6 | 0
1067722 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | OpEx | Global | IT - Internal | 15.5h | 0h | 15.5h | 2017-07-10 | 2017-09-07 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 2 | 3 | 5 | 4 | 0 | 0
1067723 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067724 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067725 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-07-21 | 2017-07-21 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067726 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - CM | CM | CM | Saputo | Onshore | Bogan; Alina | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067727 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | Non ERP | Non ERP | Saputo | Onshore | Soulis; Fabien | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067728 | No | Yes | Yes | Program | Program | 03-Design/Build | HARMONI Security/GRC Solution designs | Non ERP | Non ERP | Saputo | Onshore | Soulis; Fabien | Saputo | Yes | CapEx | Global | IT - Internal | 143h | 0h | 143h | 2016-05-16 | 2016-11-11 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067729 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | Saputo | Onshore | Amrine; Dave | Saputo | Yes | OpEx | Global | IT - Internal | 18h | 0h | 18h | 2017-07-21 | 2017-08-18 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 8 | 2 | 3 | 0 | 0 | 0 | 0 | 0
1067730 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | RTR | FUN | Saputo | Onshore | Amrine; Dave | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067731 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067732 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067733 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access |  | Missing Stream | Saputo | Onshore | Fischer; Gail | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067734 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | Saputo | Onshore | Iñiguez Manuel | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067735 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | Saputo | Onshore | Leal Fernando | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067736 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access |  | Missing Stream | Saputo | Onshore | Buytendorp; John | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067737 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTP | FUN | Saputo | Onshore | Karch-Hahn; Denise | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067738 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTP | PTP | FUN | Saputo | Onshore | Karch-Hahn; Denise | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-08-25 | 2017-08-25 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067739 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | Saputo | Onshore | Olcott; Lisa | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067740 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | Saputo | Onshore | Olcott; Lisa | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067741 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067742 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | OpEx | Global | IT - Internal | 8h | 0h | 8h | 2017-07-31 | 2017-08-01 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067743 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CDP | CDP | SI | Onshore | Glavas; William | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067744 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CDP | CDP | SI | Onshore | Seidel; Joachim | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067745 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CDP | CDP | SI | Onshore | Adam; Alexander | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067746 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CDP | CDP | SI | Onshore | Mong; Ron | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067747 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067748 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067749 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | SI | Onshore | Mackay; Amy | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067750 | No | Yes | No | Program | Program |  | Delivery Leadership SAP | PMO | PMO | SI | Onshore | Mackay; Amy | SAP | Yes | CapEx | Global | IT - External | 354h | 0h | 354h | 2016-01-25 | 2017-02-27 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 0 | 12 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067751 | No | No | Yes | Program | Program |  | Provide SAP Security Design Solutions | SEC | SEC | Saputo | Onshore | Sharma; Kush | Saputo | Yes | CapEx | Global | IT - Internal | 2,754.5h | 0h | 2,754.5h | 2016-02-04 | 2017-08-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 42.5 | 37 | 50 | 48 | 50 | 62 | 42 | 50 | 53 | 40 | 0 | 0 | 0 | 0 | 32 | 0 | 38 | 48 | 44 | 47 | 38.5 | 59 | 66 | 43 | 49 | 57 | 62 | 53 | 0 | 55 | 46 | 46 | 48 | 48 | 0 | 0 | 0 | 0
1067752 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - SEC | SEC | SEC | Saputo | Onshore | Sharma; Kush | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-29 | 2017-06-29 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067753 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | SEC | SEC | Saputo | Onshore | Sharma; Kush | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067754 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | Non ERP | Non ERP | Saputo | Onshore | Chowdhry; Tanvir | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067755 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | SI | Onshore | Escobedo; Andre | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067756 | No | No | Yes | Program | Program |  | Support CF1 | RTR | FUN | SI | Onshore | OGorman; Jessica | IBM | Yes | OpEx | Global | IT - External | 121h | 0h | 121h | 2016-10-24 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067757 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | SI | Onshore | OGorman; Jessica | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067758 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | RTR | FUN | SI | Onshore | OGorman; Jessica | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067759 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | SI | Onshore | Boesl; Robert | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067760 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Landed Onshore | Chauhan; Sidharth | IBM | Yes | OpEx | Global | IT - External | 4h | 0h | 4h | 2017-06-19 | 2017-06-19 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067761 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Landed Onshore | Chauhan; Sidharth | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067762 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | Saputo | Onshore | Volcy; Carl-Henry | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067763 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | Saputo | Onshore | Costa; Jorge Luis | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067764 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067765 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | SI | Onshore | Nguyen; Bach-Hue | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067766 | No | Yes | Yes | Program | Program |  | PMO admin and support | PMO | PMO | SI | Onshore | Nguyen; Bach-Hue | IBM | Yes | CapEx | Global | IT - External | 289h | 0h | 289h | 2016-02-01 | 2016-03-18 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067767 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | OTC | FUN | SI | Onshore | Lastman; Samantha | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067768 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTP | FUN | SI | Onshore | Chinnasamy; Anand | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067769 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | SI | Onshore | Boersma; Andy | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067770 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | TAI | TAI | SI | Onshore | Mendoza; Hugo | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067771 | No | Yes | No | Program | Program | 03-Design/Build | Design Technical Architecture (Deliverables) | TAI | TAI | SI | Onshore | Mendoza; Hugo | Accenture | Yes | CapEx | Global | IT - External | 828h | 0h | 828h | 2016-02-01 | 2016-07-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067772 | No | Yes | No | Program | Program | 03-Design/Build | Build and Manage SAP Environments | TAI | TAI | SI | Onshore | Mendoza; Hugo | Accenture | Yes | CapEx | Global | IT - External | 60h | 0h | 60h | 2016-02-01 | 2016-02-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067773 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | SI | Onshore | Carabajal; Alan | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067774 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | SI | Onshore | Pietrantoni; Luana | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067775 | No | Yes | No | Program | Program |  | PMO admin and support | PMO | PMO | SI | Onshore | Pietrantoni; Luana | IBM | Yes | CapEx | Global | IT - External | 1,220h | 0h | 1,220h | 2016-01-04 | 2016-08-19 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067776 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | LOG | FUN | SI | Onshore | Gera; Tanvi | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067777 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access |  | Missing Stream | Saputo | Onshore | Addona; Roberto | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067778 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | RTR | FUN | Saputo | Onshore | Baillargeon; Olivier | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067779 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | TAI | TAI | SI | Landed Onshore | Deluao; Nathan | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067780 | No | No | Yes | Program | Program | 03-Design/Build | Build and Manage SAP Environments | TAI | TAI | SI | Landed Onshore | Deluao; Nathan | Accenture | Yes | CapEx | Global | IT - External | 1,136h | 0h | 1,136h | 2016-02-01 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067781 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - TAI | TAI | TAI | SI | Landed Onshore | Deluao; Nathan | Accenture | Yes | OpEx | Global | IT - External | 106h | 0h | 106h | 2017-07-03 | 2017-08-04 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 40 | 10 | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067782 | No | No | Yes | Program | Program |  | TAI – Tools support | TAI | TAI | SI | Landed Onshore | Deluao; Nathan | Accenture | Yes | OpEx | Global | IT - External | 76h | 0h | 76h | 2016-11-14 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067783 | No | No | Yes | Program | Program |  | TAI - Project SAP Environment Support | TAI | TAI | SI | Landed Onshore | Deluao; Nathan | Accenture | Yes | CapEx | Global | IT - External | 480.5h | 160h | 640.5h | 2016-11-28 | 2017-09-29 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 6 | 45 | 45 | 45 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 45 | 30 | 32 | 40 | 40 | 32 | 0 | 0 | 0
1067784 | No | No | Yes | Program | Program | 03-Design/Build | Design Technical Architecture (Deliverables) | TAI | TAI | SI | Landed Onshore | Deluao; Nathan | Accenture | Yes | CapEx | Global | IT - External | 35h | 0h | 35h | 2016-02-01 | 2016-02-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067785 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | TAI | TAI | SI | Offshore | Bohol; Earl Hanzel | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067786 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DM | SI | Onshore | Ingalls; Lindsey | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067787 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - MDG - DM | MDG | DM | SI | Onshore | Ingalls; Lindsey | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067788 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | TAI | TAI | SI | Landed Onshore | Roel; Luis | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067789 | No | No | Yes | Program | Program |  | TAI – SolMan Design & Planning & Implementation | TAI | TAI | SI | Landed Onshore | Roel; Luis | Accenture | Yes | OpEx | Global | IT - External | 417.4h | 40h | 457.4h | 2016-10-24 | 2017-09-29 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 3.2 | 6.4 | 8 | 6.4 | 8 | 12 | 10 | 15 | 11 | 10 | 10 | 5 | 10 | 10 | 10 | 16 | 20 | 10 | 10 | 10 | 10 | 8 | 10 | 10 | 10 | 8 | 12 | 10 | 10 | 10 | 10 | 8 | 8 | 10 | 10 | 10 | 0 | 0 | 0
1067790 | No | No | Yes | Program | Program |  | TAI - Technical Monitoring | TAI | TAI | SI | Landed Onshore | Roel; Luis | Accenture | Yes | OpEx | Global | IT - External | 509.8h | 40h | 549.8h | 2016-10-24 | 2017-09-29 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 6.4 | 12.8 | 16 | 12.8 | 16 | 22 | 15 | 23 | 17 | 15 | 15 | 15 | 10 | 10 | 10 | 0 | 0 | 10 | 10 | 10 | 10 | 8 | 10 | 10 | 10 | 8 | 12 | 5 | 0 | 10 | 10 | 8 | 8 | 10 | 10 | 10 | 0 | 0 | 0
1067791 | No | No | Yes | Program | Program |  | TAI - ChaRM | TAI | TAI | SI | Landed Onshore | Roel; Luis | Accenture | Yes | CapEx | Global | IT - External | 542.8h | 40h | 582.8h | 2016-10-24 | 2017-09-29 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 6.4 | 12.8 | 16 | 12.8 | 16 | 22 | 15 | 22 | 16 | 15 | 15 | 15 | 10 | 10 | 10 | 0 | 0 | 10 | 10 | 10 | 10 | 8 | 10 | 10 | 10 | 8 | 12 | 20 | 20 | 10 | 10 | 8 | 8 | 10 | 10 | 10 | 0 | 0 | 0
1067792 | No | No | Yes | Program | Program | 03-Design/Build | Design Technical Architecture (Deliverables) | TAI | TAI | SI | Landed Onshore | Roel; Luis | Accenture | Yes | CapEx | Global | IT - External | 18h | 0h | 18h | 2016-02-01 | 2016-02-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067793 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - TAI | TAI | TAI | SI | Landed Onshore | Roel; Luis | Accenture | Yes | OpEx | Global | IT - External | 18h | 0h | 18h | 2017-06-12 | 2017-06-22 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067794 | No | No | Yes | Program | Program | 03-Design/Build | Build and Manage SAP Environments | TAI | TAI | SI | Landed Onshore | Roel; Luis | Accenture | Yes | CapEx | Global | IT - External | 1,311h | 0h | 1,311h | 2016-02-01 | 2016-09-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067795 | No | No | Yes | Program | Program |  | TAI - Project SAP Environment Support | TAI | TAI | SI | Landed Onshore | Roel; Luis | Accenture | Yes | CapEx | Global | IT - External | 233h | 40h | 273h | 2017-02-13 | 2017-09-29 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 10 | 10 | 16 | 20 | 10 | 10 | 10 | 10 | 8 | 10 | 10 | 1 | 0 | 12 | 5 | 10 | 10 | 10 | 8 | 8 | 10 | 10 | 10 | 0 | 0 | 0
1067796 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | Saputo | Onshore | Daitchman; Lorne | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067797 | No | No | No | Program | Program |  | Program Leadership Saputo | PMO | PMO | Saputo | Onshore | Daitchman; Lorne | Saputo | Yes | OpEx | Global | IT - Internal | 170h | 0h | 170h | 2016-02-01 | 2016-05-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067798 | No | No | No | Program | Program | 01-Preparation | Mobilize Program - Saputo | PMO | PMO | Saputo | Onshore | Daitchman; Lorne | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-09-14 | 2015-09-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067799 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access |  | Missing Stream | Saputo | Onshore | Skertchly; Mario | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067800 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | Saputo | Onshore | Chausse; Bertrand | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067801 | No | No | No | Program | Program |  | TAI Leadership Oversight | PMO | PMO | Saputo | Onshore | Chausse; Bertrand | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067802 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | Saputo | Onshore | Burdisso Walter | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067803 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | Saputo | Onshore | Rivard; Richard | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067804 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | Saputo | Onshore | Montoya; Jose | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067805 | No | Yes | No | Program | Program |  | Project Management Saputo | PMO | PMO | Saputo | Onshore | Montoya; Jose | Saputo | Yes | CapEx | Localization | IT - Internal | 1,534h | 0h | 1,534h | 2016-05-09 | 2017-04-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 32 | 0 | 40 | 24 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 0 | 0 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067806 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | OpEx | Global | IT - External | 24h | 0h | 24h | 2017-06-19 | 2017-07-14 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 7 | 6 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067807 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067808 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | SI | Onshore | Nelson; Paul | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067809 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067810 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | OpEx | Global | IT - External | 52h | 0h | 52h | 2017-06-12 | 2017-06-18 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067811 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | BI | BI | SI | Offshore | Roychowdhury; Rajibendra | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067812 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | RTR | FUN | SI | Onshore | Lindemann; Ryan | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067813 | No | Yes | No | Program | Program | 03-Design/Build | GD - Design SAP RTR Solution | RTR | FUN | SI | Onshore | Lindemann; Ryan | SAP | Yes | CapEx | Global | IT - External | 134h | 0h | 134h | 2016-06-06 | 2016-08-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067814 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access |  | Missing Stream | Saputo | Onshore | Zuliani Pablo | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067815 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access |  | Missing Stream | Saputo | Onshore | Morel Maria Soledad | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067816 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access |  | Missing Stream | Saputo | Onshore | Orchese Fernando | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067817 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | Non ERP | Non ERP | Saputo | Onshore | Traverso Fabián | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067818 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access |  | Missing Stream | Saputo | Onshore | Altamirano Facundo | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067819 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access |  | Missing Stream | Saputo | Onshore | Coria Sergio | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067820 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access |  | Missing Stream | Saputo | Onshore | Meyer Fernando | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067821 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access |  | Missing Stream | Saputo | Onshore | Paredes Hernán | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067822 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CM | CM | Saputo | Onshore | Strauch Gabriela | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067823 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | RTR | FUN | SI | Offshore | Paradkar; Parag | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067824 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access |  | Missing Stream | Saputo | Onshore | Russo Fernanda | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067825 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CM | CM | Saputo | Onshore | Calvo Laura | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067826 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CM | CM | Saputo | Onshore | Floriani Martin | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067827 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067828 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | Test | Test | Saputo | Onshore | Bensoussan; Tanya | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067829 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - Test | Test | Test | Saputo | Onshore | Bensoussan; Tanya | Saputo | Yes | OpEx | Global | IT - Internal | 24h | 0h | 24h | 2017-06-26 | 2017-08-11 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0
1067830 | No | No | Yes | Program | Program |  | Manage Program Testing Planning and Execution | Test | Test | Saputo | Onshore | Bensoussan; Tanya | Saputo | Yes | CapEx | Global | IT - Internal | 669h | 0h | 669h | 2016-02-08 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067831 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067832 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-07 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067833 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067834 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067835 | No | No | Yes | Program | Enhancement Pack Application (in Program) |  | SAP SP SBX-Test-Support-OTC | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Global | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067836 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067837 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067838 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | SI | Offshore | Manish; Desai | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067839 | No | No | Yes | Program | Program | 03-Design/Build | GD - Provide Functional Integration Solutions | PMO | PMO | SI | Offshore | Manish; Desai | IBM | Yes | CapEx | Global | IT - External | 776h | 0h | 776h | 2016-02-08 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067840 | No | No | Yes | Program | Program | 03-Design/Build | Global - Provide Functional Integration Solutions | PMO | PMO | SI | Offshore | Manish; Desai | IBM | Yes | CapEx | Global | IT - External | 1,784h | 850h | 2,634h | 2016-02-08 | 2018-02-01 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 45 | 45 | 45 | 45 | 36 | 45 | 45 | 45 | 45 | 36 | 45 | 36 | 45 | 36 | 45 | 45 | 45 | 45 | 36 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 36 | 36 | 36 | 36 | 45 | 45 | 45 | 0
1067841 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067842 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | OpEx | Global | IT - External | 7h | 0h | 7h | 2017-06-15 | 2017-06-19 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067843 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | TAI | TAI | SI | Offshore | Catoy; John | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067844 | No | Yes | No | Program | Program | 03-Design/Build | Build and Manage SAP Environments | TAI | TAI | SI | Offshore | Catoy; John | Accenture | Yes | CapEx | Global | IT - External | 1,197.6h | 0h | 1,197.6h | 2016-02-01 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067845 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - TAI | TAI | TAI | SI | Offshore | Catoy; John | Accenture | Yes | OpEx | Global | IT - External | 50h | 0h | 50h | 2017-07-03 | 2017-07-31 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067846 | No | Yes | No | Program | Program | 03-Design/Build | Design Technical Architecture (Deliverables) | TAI | TAI | SI | Offshore | Catoy; John | Accenture | Yes | CapEx | Global | IT - External | 26.4h | 0h | 26.4h | 2016-02-01 | 2016-02-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067847 | No | Yes | No | Program | Program |  | TAI – Tools support | TAI | TAI | SI | Offshore | Catoy; John | Accenture | Yes | OpEx | Global | IT - External | 159.5h | 0h | 159.5h | 2016-10-24 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 45 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067848 | No | Yes | No | Program | Program |  | TAI - Project SAP Environment Support | TAI | TAI | SI | Offshore | Catoy; John | Accenture | Yes | CapEx | Global | IT - External | 768.5h | 0h | 768.5h | 2016-11-14 | 2017-07-31 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 36 | 45 | 45 | 27 | 45 | 36 | 36 | 36 | 45 | 27 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067849 | No | No | Yes | Program | Program |  | PMO Delivery Leadership Saputo | PMO | PMO | Saputo | Onshore | Bensoussan; Orly | Saputo | Yes | CapEx | Global | IT - Internal | 2,291.67h | 736h | 3,027.67h | 2016-02-01 | 2018-02-09 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 24 | 24 | 32 | 38 | 0 | 40 | 40 | 0 | 30 | 0 | 32 | 32 | 32 | 40 | 36.8 | 0 | 24 | 19.2 | 32 | 40 | 40 | 30 | 40 | 40 | 0 | 0 | 32 | 30 | 40 | 35 | 38 | 40 | 38 | 0 | 40 | 0 | 0 | 0 | 0
1067850 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | Saputo | Onshore | Bensoussan; Orly | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067851 | No | No | Yes | Program | Program | 01-Preparation | Mobilize PMO - Saputo | PMO | PMO | Saputo | Onshore | Bensoussan; Orly | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-09-14 | 2015-11-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067852 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | Saputo | Onshore | Michelle Rubina | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067853 | No | No | Yes | Program | Program | 03-Design/Build | Coordinate Offshore Development Team | DEV | DEV | SI | Offshore | HEDA; NAND | IBM | Yes | CapEx | Global | IT - External | 1,021h | 0h | 1,021h | 2016-02-29 | 2016-08-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067854 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | HEDA; NAND | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067855 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Offshore | HEDA; NAND | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067856 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | SI | Onshore | Arora; Mandeep | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067857 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | TAI | TAI | SI | Offshore | Zapata; Michael | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067858 | No | Yes | No | Program | Program |  | TAI – Tools support | TAI | TAI | SI | Offshore | Zapata; Michael | Accenture | Yes | OpEx | Global | IT - External | 82h | 0h | 82h | 2016-11-14 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 9 | 30 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067859 | No | Yes | No | Program | Program | 03-Design/Build | Build and Manage SAP Environments | TAI | TAI | SI | Offshore | Zapata; Michael | Accenture | Yes | CapEx | Global | IT - External | 1,219h | 0h | 1,219h | 2016-02-01 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067860 | No | Yes | No | Program | Program |  | TAI - Project SAP Environment Support | TAI | TAI | SI | Offshore | Zapata; Michael | Accenture | Yes | CapEx | Global | IT - External | 915.5h | 0h | 915.5h | 2016-11-14 | 2017-06-23 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 18 | 0 | 0 | 45 | 0 | 54 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 27 | 18 | 45 | 27 | 45 | 45 | 45 | 45 | 45 | 27 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067861 | No | Yes | No | Program | Program | 03-Design/Build | Design Technical Architecture (Deliverables) | TAI | TAI | SI | Offshore | Zapata; Michael | Accenture | Yes | CapEx | Global | IT - External | 23h | 0h | 23h | 2016-02-01 | 2016-02-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067862 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - TAI | TAI | TAI | SI | Offshore | Zapata; Michael | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-08-25 | 2017-08-25 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067863 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | Saputo | Onshore | Mayhall; Delano | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067864 | No | No | Yes | Program | Program | 03-Design/Build | Development and Integration - Legacy support D&B and Build phases - DC | MDG | DC | Saputo | Onshore | Mayhall; Delano | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067865 | No | No | Yes | Program | Program |  | Data Migration leadership - DC | MDG | DC | Saputo | Onshore | Mayhall; Delano | Saputo | Yes | CapEx | Global | IT - Internal | 870h | 0h | 870h | 2016-03-21 | 2017-06-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067866 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | Saputo | Onshore | Mayhall; Delano | Saputo | Yes | OpEx | Global | IT - Internal | 113h | 0h | 113h | 2017-06-05 | 2017-07-28 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 16 | 10 | 5 | 48 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067867 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | OpEx | Global | IT - External | 86h | 0h | 86h | 2017-06-12 | 2017-09-15 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0
1067868 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067869 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | OTC | FUN | SI | Onshore | Sudhanshu; Mathur | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067870 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access |  | Missing Stream | Saputo | Onshore | Dummer; Kirk | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067871 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067872 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | OpEx | Global | IT - External | 52h | 0h | 52h | 2017-06-12 | 2017-08-04 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 2 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067873 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - CM | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Global | IT - Internal | 20h | 0h | 20h | 2017-07-10 | 2017-07-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067874 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067875 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | To Define | SI | Onshore | El Ouehabi; Hassan | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067876 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | Saputo | Onshore | Leite; Alexandre | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067877 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | TAI | TAI | SI | Onshore | Doherty; Sean | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067878 | No | Yes | No | Program | Program | 03-Design/Build | Technical Architecture & Infrastructure Delivery Lead | TAI | TAI | SI | Onshore | Doherty; Sean | Accenture | Yes | CapEx | Global | IT - External | 1,128h | 0h | 1,128h | 2016-02-01 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067879 | No | Yes | No | Program | Program | 03-Design/Build | Basis Management | TAI | TAI | SI | Onshore | Doherty; Sean | Accenture | Yes | CapEx | Global | IT - External | 543h | 0h | 543h | 2016-11-21 | 2017-02-28 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 32 | 40 | 40 | 40 | 40 | 44 | 40 | 40 | 40 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067880 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | SI | Onshore | Minotti; Daniel | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067881 | No | No | Yes | Program | Program |  | Delivery Leadership Accenture | PMO | PMO | SI | Onshore | Minotti; Daniel | Accenture | Yes | CapEx | Global | IT - External | 1,319h | 204h | 1,523h | 2016-02-01 | 2017-12-29 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 3 | 19 | 20 | 16 | 20 | 30 | 16 | 8 | 7 | 15 | 8 | 13 | 14 | 6 | 10 | 18 | 10 | 10 | 7 | 18 | 10 | 13 | 10 | 13 | 18 | 13 | 14 | 9 | 13 | 19 | 9 | 0 | 15 | 24 | 10 | 10 | 0 | 0 | 0
1067882 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | SEC | SEC | SI | Onshore | Heaton; John | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067883 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | SI | Onshore | Fonseca; Thiago | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067884 | No | Yes | No | Program | Program | 03-Design/Build | GD - Design Data Governance and Migration Solutions - DC | MDG | DC | SI | Onshore | Fonseca; Thiago | Accenture | Yes | CapEx | Global | IT - External | 947.6h | 0h | 947.6h | 2016-02-01 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067885 | No | Yes | No | Program | Program | 03-Design/Build | ARG - Design Data Governance and Migration Solutions - DC | MDG | DC | SI | Onshore | Fonseca; Thiago | Accenture | Yes | CapEx | Global | IT - External | 171.8h | 0h | 171.8h | 2016-02-01 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067886 | No | Yes | No | Program | Program | 03-Design/Build | CF - Design Data Governance and Migration Solutions - DC | MDG | DC | SI | Onshore | Fonseca; Thiago | Accenture | Yes | CapEx | Global | IT - External | 55.6h | 0h | 55.6h | 2016-02-08 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067887 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTP | FUN | SI | Onshore | Lospied; Jerome | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067888 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | SEC | SEC | SI | Onshore | Vernon; Franck | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067889 | No | Yes | No | Program | Program | 03-Design/Build | GD - Design SAP Security Solutions | SEC | SEC | SI | Onshore | Vernon; Franck | Accenture | Yes | CapEx | Global | IT - External | 963h | 0h | 963h | 2016-02-01 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067890 | No | Yes | No | Program | Program | 03-Design/Build | ARG -Design SAP Security Solutions | SEC | SEC | SI | Onshore | Vernon; Franck | Accenture | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-04-04 | 2016-04-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067891 | No | Yes | No | Program | Program | 03-Design/Build | CF - Design SAP Security Solutions | SEC | SEC | SI | Onshore | Vernon; Franck | Accenture | Yes | CapEx | Global | IT - External | 40h | 0h | 40h | 2016-02-08 | 2016-07-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067892 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access |  | Missing Stream |  |  | Holzheimer; Donald |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067893 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | LOG | FUN | SI | Onshore | Bright; Brandon | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067894 | No | Yes | No | Program | Program | 03-Design/Build | GD - Design SAP Logistics Solution | LOG | FUN | SI | Onshore | Bright; Brandon | IBM | Yes | CapEx | Global | IT - External | 856.92h | 0h | 856.92h | 2016-02-01 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067895 | No | Yes | No | Program | Program | 03-Design/Build | ARG - Design SAP Logistics Solution | LOG | FUN | SI | Onshore | Bright; Brandon | IBM | Yes | CapEx | Localization | IT - External | 101.08h | 0h | 101.08h | 2016-02-01 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067896 | No | Yes | No | Program | Program | 03-Design/Build | ARG - Design SAP PTP Solution | PTP | FUN | SI | Onshore | Lazure; Stephane | IBM | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2016-02-15 | 2016-07-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067897 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTP | FUN | SI | Onshore | Lazure; Stephane | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067898 | No | Yes | No | Program | Program | 03-Design/Build | GD - Design SAP PTP Solution | PTP | FUN | SI | Onshore | Lazure; Stephane | IBM | Yes | CapEx | Global | IT - External | 970h | 0h | 970h | 2016-02-01 | 2016-07-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067899 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | SI | Onshore | Novak; Steve | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067900 | No | No | Yes | Program | Program | 03-Design/Build | GD - Design SAP PTM Solution | PTM | FUN | SI | Onshore | Novak; Steve | IBM | Yes | CapEx | Global | IT - External | 869h | 0h | 869h | 2016-02-01 | 2016-08-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067901 | No | No | Yes | Program | Program | 03-Design/Build | ARG - Design SAP PTM Solution | PTM | FUN | SI | Onshore | Novak; Steve | IBM | Yes | CapEx | Localization | IT - External | 140h | 0h | 140h | 2016-02-03 | 2016-08-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067902 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Onshore | Novak; Steve | IBM | Yes | OpEx | Global | IT - External | 122h | 0h | 122h | 2017-06-12 | 2017-07-27 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 62 | 33 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067903 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-20 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067904 | No | No | Yes | Program | Program |  | Provide Solution Architecture Authority | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Global | IT - External | 0h | 680h | 680h | 2017-01-16 | 2017-12-29 | Yes |  |  |  | Late | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067905 | No | No | Yes | Program | Program | 03-Design/Build | GD - Design SAP OTC Solution | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Global | IT - External | 758h | 0h | 758h | 2016-02-01 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067906 | No | No | Yes | Program | Program | 03-Design/Build | ARG - Design SAP OTC Solution | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 438h | 0h | 438h | 2016-02-01 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067907 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067908 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | SI | Onshore | Porter; Stephanie | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067909 | No | Yes | Yes | Program | Program | 03-Design/Build | GD - Provide Functional Integration Solutions | PMO | PMO | SI | Onshore | Porter; Stephanie | IBM | Yes | CapEx | Global | IT - External | 920h | 0h | 920h | 2016-02-02 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067910 | No | Yes | Yes | Program | Program | 03-Design/Build | Global - Provide Functional Integration Solutions | PMO | PMO | SI | Onshore | Porter; Stephanie | IBM | Yes | CapEx | Global | IT - External | 114h | 0h | 114h | 2016-02-10 | 2016-08-19 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067911 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | SI | Onshore | Von Fintel; Dieter | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067912 | No | No | Yes | Program | Program | 03-Design/Build | GD - Development Lead | PMO | PMO | SI | Onshore | Von Fintel; Dieter | IBM | Yes | CapEx | Global | IT - External | 1,086h | 0h | 1,086h | 2016-02-01 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067913 | No | No | Yes | Program | Program | 03-Design/Build | ARG - Development Lead | PMO | PMO | SI | Onshore | Von Fintel; Dieter | IBM | Yes | CapEx | Localization | IT - External | 135h | 0h | 135h | 2016-02-15 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067914 | No | No | Yes | Program | Program | 03-Design/Build | CF - Development Lead | PMO | PMO | SI | Onshore | Von Fintel; Dieter | IBM | Yes | CapEx | Global | IT - External | 20h | 0h | 20h | 2016-02-03 | 2016-05-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067915 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | SI | Onshore | Gilbert; Michael | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067916 | No | Yes | Yes | Program | Program |  | Delivery Leadership IBM | PMO | PMO | SI | Onshore | Gilbert; Michael | IBM | Yes | CapEx | Global | IT - External | 146h | 0h | 146h | 2016-02-01 | 2016-06-02 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067917 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067918 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - PTP | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-07 | 2017-06-13 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067919 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTP | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | OpEx | Global | Business | 154h | 0h | 154h | 2017-06-12 | 2017-07-21 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 24 | 40 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067920 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067921 | No | No | Yes | Program | Program |  | KT-PTP (not AMS) | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Global | Business | 90h | 0h | 90h | 2017-07-24 | 2017-08-18 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0
1067922 | No | No | Yes | Program | Program |  | KT-PTP (not AMS) | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Global | Business | 113h | 10h | 123h | 2017-07-24 | 2017-09-08 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 48 | 0 | 8 | 8 | 2 | 0 | 0 | 0
1067923 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067924 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTP | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | OpEx | Global | Business | 14h | 0h | 14h | 2017-06-27 | 2017-07-13 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067925 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | TAI | TAI | SI | Onshore | Chea; SaySanne | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067926 | No | No | Yes | Program | Program | 03-Design/Build | Design Technical Architecture (Deliverables) | TAI | TAI | SI | Onshore | Chea; SaySanne | Accenture | Yes | CapEx | Global | IT - External | 18h | 0h | 18h | 2016-02-01 | 2016-02-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067927 | No | No | Yes | Program | Program | 03-Design/Build | Build and Manage SAP Environments | TAI | TAI | SI | Onshore | Chea; SaySanne | Accenture | Yes | CapEx | Global | IT - External | 964h | 0h | 964h | 2016-02-01 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067928 | No | No | Yes | Program | Program | 03-Design/Build | Technology implementation plan | TAI | TAI | SI | Onshore | Chea; SaySanne | Accenture | Yes | CapEx | Global | IT - External | 154h | 0h | 154h | 2016-02-22 | 2016-06-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067929 | No | No | Yes | Program | Program |  | TAI - Project SAP Environment Support | TAI | TAI | SI | Onshore | Chea; SaySanne | Accenture | Yes | CapEx | Global | IT - External | 570h | 160h | 730h | 2017-02-13 | 2017-09-29 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 24 | 26 | 40 | 40 | 40 | 40 | 32 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 40 | 0 | 0 | 0
1067930 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - TAI | TAI | TAI | SI | Onshore | Chea; SaySanne | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067931 | No | No | Yes | Program | Program |  | Program Administration Saputo | PMO | PMO | Saputo | Onshore | Sabir; Kaoutar | Saputo | Yes | OpEx | Global | IT - Internal | 2,778h | 1,018h | 3,796h | 2016-02-01 | 2018-03-07 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 8 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 40 | 40 | 40 | 40 | 36 | 32 | 0 | 16 | 0 | 0 | 0 | 0 | 40 | 34 | 40 | 32 | 32 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 32 | 0 | 0
1067932 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | Saputo | Onshore | Sabir; Kaoutar | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067933 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067934 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | OpEx | Global | IT - External | 24h | 0h | 24h | 2017-06-12 | 2017-07-05 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 8 | 2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067935 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | SEC | SEC | SI | Landed Onshore | Manongsong; Melissa | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067936 | No | No | Yes | Program | Program | 03-Design/Build | Design Security Solutions and Support Security Project Team | SEC | SEC | SI | Landed Onshore | Manongsong; Melissa | Accenture | Yes | CapEx | Global | IT - External | 540h | 0h | 540h | 2016-02-01 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067937 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - SEC | SEC | SEC | SI | Landed Onshore | Manongsong; Melissa | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-07 | 2017-06-07 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067938 | No | Yes | Yes | Program | Program | 03-Design/Build | Design Security Solutions and Support Security Project Team | SEC | SEC | SI | Offshore | Maynes; Rosemarie | Accenture | Yes | CapEx | Global | IT - External | 450h | 0h | 450h | 2016-02-15 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067939 | No | Yes | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | SEC | SEC | SI | Offshore | Maynes; Rosemarie | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067940 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067941 | No | No | Yes | Program | Program | 03-Design/Build | Design Security Solutions and Support Security Project Team | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Global | IT - External | 782h | 0h | 782h | 2016-02-01 | 2016-06-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067942 | No | No | Yes | Program | Program | 03-Design/Build | SEC Project Support | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Global | IT - External | 329.85h | 0h | 329.85h | 2016-11-14 | 2017-03-31 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 7.5 | 13.4 | 23.6 | 27.1 | 15 | 31.45 | 0 | 0 | 0 | 0 | 0 | 30 | 22 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067943 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - SEC | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | OpEx | Global | IT - External | 70h | 0h | 70h | 2017-06-12 | 2017-07-28 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 6 | 10 | 27 | 9 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067944 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DM | SI | Offshore | Quinones; Franz | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067945 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DM | MDG | DM | SI | Offshore | Quinones; Franz | Accenture | Yes | OpEx | Global | IT - External | 15h | 0h | 15h | 2017-06-21 | 2017-08-04 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 4 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067946 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | SI | Offshore | Agena; Cherry | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067947 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | SI | Landed Onshore | Lloren; Jerry | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067948 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | SI | Landed Onshore | Lloren; Jerry | Accenture | Yes | OpEx | Global | IT - External | 26h | 0h | 26h | 2017-06-26 | 2017-07-21 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067949 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | SI | Offshore | Cabasagan; Fretsie | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067950 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067951 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - CM | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Global | IT - Internal | 10h | 0h | 10h | 2017-06-12 | 2017-06-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067952 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | DEV | DEV | SI | Landed Onshore | Iyer; Jagdeesh | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067953 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Landed Onshore | Iyer; Jagdeesh | IBM | Yes | OpEx | Global | IT - External | 10h | 0h | 10h | 2017-06-27 | 2017-07-13 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067954 | No | No | Yes | Program | Program |  | PMO admin and support | PMO | PMO | SI | Offshore | Bhide; Chaitanya | IBM | Yes | CapEx | Global | IT - External | 3,438h | 675h | 4,113h | 2016-02-01 | 2017-12-29 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 45 | 45 | 45 | 45 | 36 | 45 | 45 | 45 | 45 | 36 | 45 | 36 | 45 | 27 | 45 | 36 | 45 | 45 | 0 | 45 | 45 | 45 | 45 | 45 | 27 | 36 | 36 | 45 | 45 | 45 | 45 | 45 | 45 | 36 | 31.5 | 45 | 40.5 | 45 | 0
1067955 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | SI | Offshore | Bhide; Chaitanya | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067956 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067957 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067958 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | RTR | FUN | SI | Onshore | Cheng; Katrina | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067959 | No | Yes | No | Program | Program | 03-Design/Build | GD - Design SAP RTR Solution | RTR | FUN | SI | Onshore | Cheng; Katrina | IBM | Yes | CapEx | Global | IT - External | 662h | 0h | 662h | 2016-03-07 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067960 | No | Yes | No | Program | Program | 03-Design/Build | ARG - Design SAP RTR Solution | RTR | FUN | SI | Onshore | Cheng; Katrina | IBM | Yes | CapEx | Localization | IT - External | 245h | 0h | 245h | 2016-03-07 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067961 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067962 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067963 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067964 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | OpEx | Global | IT - External | 66h | 0h | 66h | 2017-07-03 | 2017-07-28 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 12 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067965 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067966 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | OpEx | Global | IT - External | 17h | 0h | 17h | 2017-08-01 | 2017-08-11 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 12 | 0 | 0 | 0 | 0 | 0 | 0
1067967 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | OTC | FUN | SI | Onshore | Kane; Jeremy | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067968 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | SI | Onshore | Kane; Jeremy | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067969 | No | No | Yes | Program | Program |  | Support Change Management Activities | PMO | PMO | Saputo | Onshore | Martin; Jeff | Saputo | Yes | OpEx | Global | Business | 151h | 0h | 151h | 2016-02-01 | 2016-07-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067970 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | Saputo | Onshore | Martin; Jeff | Saputo | Yes | CapEx | Global | Business | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067971 | No | No | Yes | Program | Program |  | Provide Business Process Design Authority | PMO | PMO | Saputo | Onshore | Martin; Jeff | Saputo | Yes | CapEx | Global | Business | 2,343.5h | 2,344.78h | 4,688.28h | 2016-02-01 | 2019-01-08 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 45 | 44 | 40 | 48 | 35 | 44 | 46 | 36 | 40 | 40 | 0 | 54 | 56 | 0 | 42 | 44 | 46 | 0 | 0 | 38 | 46 | 0
1067972 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | To Define | Saputo | Onshore | Teeples; Maja | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067973 | No | Yes | No | Program | Program |  | MDM SS Leadership | MDG | To Define | Saputo | Onshore | Teeples; Maja | Saputo | Yes | OpEx | Global | IT - Internal | 520h | 0h | 520h | 2016-02-01 | 2016-05-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067974 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | To Define | SI | Offshore | Rudra; Sekhar | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067975 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | SEC | SEC | SI | Onshore | Tran; Menard | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067976 | No | Yes | No | Program | Program | 03-Design/Build | Design Security Solutions and Support Security Project Team | SEC | SEC | SI | Onshore | Tran; Menard | Accenture | Yes | CapEx | Global | IT - External | 70h | 0h | 70h | 2016-02-08 | 2016-02-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067977 | No | No | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | CDP | CDP | SI | Onshore | George; Steven | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067978 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067979 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTP | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | OpEx | Global | IT - External | 114h | 0h | 114h | 2017-06-07 | 2017-07-14 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 10 | 10 | 18 | 9 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067980 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067981 | No | Yes | No | Program | Program |  | Delivery Leadership SAP | PMO | PMO | SI | Onshore | Aflalo; Michael | SAP | Yes | CapEx | Global | IT - External | 2,122h | 0h | 2,122h | 2016-02-01 | 2017-04-28 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 16 | 40 | 32 | 40 | 16 | 40 | 40 | 32 | 32 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067982 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | SI | Onshore | Aflalo; Michael | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067983 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | SI | Onshore | Kreuzer; Winfried | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067984 | No | No | Yes | Program | Program | 03-Design/Build | SAP X-Fun SME | PMO | PMO | SI | Onshore | Kreuzer; Winfried | SAP | Yes | CapEx | Global | IT - External | 884h | 0h | 884h | 2016-02-03 | 2017-03-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 8 | 40 | 8 | 4 | 20 | 32 | 4 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067985 | No | No | Yes | Program | Program | 03-Design/Build | SAP-Design Data Management RiCEFW | PMO | PMO | SI | Onshore | Kreuzer; Winfried | SAP | Yes | CapEx | Global | IT - External | 80h | 0h | 80h | 2017-04-03 | 2017-05-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 4 | 0 | 12 | 4 | 12 | 16 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067986 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | SI | Offshore | Checa; Adrian | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067987 | No | Yes | No | Program | Program |  | Delivery Leadership Accenture | PMO | PMO | SI | Offshore | Checa; Adrian | Accenture | Yes | CapEx | Global | IT - External | 819h | 0h | 819h | 2016-02-01 | 2016-06-17 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067988 | No | No | Yes | Program | Program |  | Delivery Leadership Accenture | PMO | PMO | SI | Offshore | Echaure; Joan | Accenture | Yes | CapEx | Global | IT - External | 2,323h | 1,760.4h | 4,083.4h | 2016-02-01 | 2020-09-22 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 25 | 43 | 45 | 40 | 39 | 45 | 45 | 43 | 45 | 41 | 41 | 43 | 35 | 45 | 45 | 0 | 45 | 45 | 36 | 45 | 45 | 45 | 27 | 45 | 27 | 36 | 36 | 36 | 36 | 45 | 45 | 45 | 36 | 45 | 36 | 31 | 36 | 40 | 0
1067989 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | SI | Offshore | Echaure; Joan | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067990 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067991 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067992 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | OpEx | Global | IT - External | 49h | 0h | 49h | 2017-06-14 | 2017-07-14 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067993 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Offshore | Samant; Rupa | IBM | Yes | OpEx | Global | IT - External | 18h | 0h | 18h | 2017-06-19 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067994 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PTM | FUN | SI | Offshore | Samant; Rupa | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067995 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | OTC | FUN | SI | Offshore | Pradhan; Gyan | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067996 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | SI | Offshore | Pradhan; Gyan | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-20 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067997 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | RTR | FUN | SI | Offshore | Deshpande; Anuprita | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067998 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | LOG | FUN | SI | Onshore | Mahoney; Stephen | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067999 | No | Yes | No | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | PMO | PMO | Saputo | Onshore | Patrick; Lara | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068000 | No | Yes | No | Program | Program |  | Create the transport sequence and the Deliverable 'Cutover to Quality Plan and Execution' | PMO | PMO | Saputo | Onshore | Patrick; Lara | Saputo | Yes | CapEx | Global | IT - Internal | 25.6h | 0h | 25.6h | 2016-06-03 | 2016-07-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068001 | No | Yes | No | Program | Program |  | Provide Release and Environment Solutions | PMO | PMO | Saputo | Onshore | Patrick; Lara | Saputo | Yes | CapEx | Global | IT - Internal | 1,129.2h | 0h | 1,129.2h | 2016-02-01 | 2016-09-02 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068002 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068003 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | OpEx | Global | IT - Internal | 20h | 0h | 20h | 2017-07-24 | 2017-08-04 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068004 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | SI | Landed Onshore | Aying; Mae | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-07-21 | 2017-07-21 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068005 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | SI | Landed Onshore | Aying; Mae | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068006 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068007 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068008 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-07-21 | 2017-07-21 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068009 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068010 | No | No | Yes | Program | Program | 01-Preparation | Assign ERP Resources to Plan for Sharepoint access | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2015-10-02 | 2015-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068011 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTP | PTP | FUN | SI | Offshore | Gaikwad; Mitesh | IBM | Yes | OpEx | Global | IT - External | 118h | 0h | 118h | 2017-06-12 | 2017-07-14 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 15 | 36 | 4 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068012 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | SI | Offshore | Jumamil; Jeff | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-07-21 | 2017-07-21 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068013 | No | No | Yes | Program | BW BO Security Design (in Program) | 03-Design/Build | BW BO Security Design | SEC | SEC | SI | Offshore | Guerrero; Mico | Accenture | Yes | CapEx | Global | IT - External | 119h | 0h | 119h | 2017-05-22 | 2017-06-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 28 | 0 | 22.5 | 22.5 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068014 | No | No | Yes | Program | BW BO Build (in Program) | 03-Design/Build | BW BO Build | SEC | SEC | SI | Offshore | Guerrero; Mico | Accenture | Yes | CapEx | Global | IT - External | 65.5h | 0h | 65.5h | 2017-06-05 | 2017-08-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 23 | 0 | 0 | 0 | 0 | 0 | 0
1068015 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - SEC | SEC | SEC | SI | Offshore | Guerrero; Mico | Accenture | Yes | OpEx | Global | IT - External | 21h | 0h | 21h | 2017-07-04 | 2017-08-11 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0
1068016 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Onshore | Stinnes; Derek | IBM | Yes | OpEx | Global | IT - External | 159h | 0h | 159h | 2017-06-05 | 2017-07-10 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 60 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068017 | No | No | Yes | Program | Program |  | DMS SWAT-PTM | PTM | FUN | SI | Onshore | Stinnes; Derek | IBM | Yes | CapEx | Global | IT - External | 88h | 22h | 110h | 2017-08-21 | 2017-09-05 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 0 | 0 | 0
1068018 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | SI | Onshore | Ulaganathan; Karthi | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068019 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Offshore | Singh; Kamna | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068020 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Offshore | Kadam; Sandeep | IBM | Yes | OpEx | Global | IT - External | 39h | 0h | 39h | 2017-06-05 | 2017-09-01 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 4 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0
1068021 | No | No | Yes | Program | Enhancement Pack Application (in Program) |  | SAP SP SBX-Test-Support-PTM | PTM | FUN | SI | Offshore | Kadam; Sandeep | IBM | Yes | CapEx | Global | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068022 | No | Yes | No | Program | Enhancement Pack Application (in Program) | 01-Preparation | Upgrade Overall Project Plan | PMO | PMO | SI | Onshore | Das; Abhranil | IBM | Yes | CapEx | Global | IT - External | 17.52h | 0h | 17.52h | 2017-06-05 | 2017-07-07 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.65 | 3.65 | 3.65 | 3.65 | 2.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068023 | No | Yes | No | Program | Enhancement Pack Application (in Program) | 01-Preparation | Sandbox Upgrade Plan | PMO | PMO | SI | Onshore | Das; Abhranil | IBM | Yes | CapEx | Global | IT - External | 27.18h | 0h | 27.18h | 2017-06-05 | 2017-07-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5.85 | 5.85 | 5.8 | 4.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068024 | No | Yes | No | Program | Enhancement Pack Application (in Program) | 02-Analyze | Prepare for sandbox upgrade | PMO | PMO | SI | Onshore | Das; Abhranil | IBM | Yes | CapEx | Global | IT - External | 33.7h | 0h | 33.7h | 2017-06-05 | 2017-07-07 | Yes |  |  |  | Complete | 2017-06-05 | 2017-09-29 | 0 |  |  | 0 | -55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.85 | 6 | 6 | 6.05 | 8.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068025 | No | Yes | No | Program | Enhancement Pack Application (in Program) | 02-Analyze | Maintenance Planner generated | PMO | PMO | SI | Onshore | Das; Abhranil | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  |  | Complete | 2017-06-05 | 2017-09-29 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068026 | No | Yes | No | Program | Enhancement Pack Application (in Program) | 02-Analyze | SUM tool setup | PMO | PMO | SI | Onshore | Das; Abhranil | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  |  | Complete | 2017-06-05 | 2017-09-29 | 0 |  |  | 5 | -65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068027 | No | Yes | No | Program | Enhancement Pack Application (in Program) | 03-Design/Build | SAP SP SBX -Execute SPS Upgrade | PMO | PMO | SI | Onshore | Das; Abhranil | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | Yes |  |  |  | Complete | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068028 | No | Yes | No | Program | Enhancement Pack Application (in Program) | 03-Design/Build | SAP SP SBX-Update SBX-S1-Upgrade ECC, BW, APO, PO | PMO | PMO | SI | Onshore | Das; Abhranil | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 19 | -50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068029 | No | Yes | No | Program | Enhancement Pack Application (in Program) | 03-Design/Build | SAP SP SBX -Upgrade TM, GBT, EWM, GTS, GW-Fiori | PMO | PMO | SI | Onshore | Das; Abhranil | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-07-11 | 2017-07-11 | Yes |  |  |  | Complete | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068030 | No | Yes | No | Program | Enhancement Pack Application (in Program) | 03-Design/Build | SAP SP SBX-ABAP Remediation (SPDD & SPAU) | PMO | PMO | SI | Onshore | Das; Abhranil | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Complete | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 19 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068031 | No | Yes | No | Program | Enhancement Pack Application (in Program) | 03-Design/Build | SAP SP SBX-Release Transports | PMO | PMO | SI | Onshore | Das; Abhranil | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | Yes |  |  |  | Future Task | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068032 | No | Yes | No | Program | Enhancement Pack Application (in Program) | 04-Test | SAP SP SBX-Identify and write test cases & scripts | PMO | PMO | SI | Onshore | Das; Abhranil | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | Yes |  |  |  | Future Task | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068033 | No | Yes | No | Program | Enhancement Pack Application (in Program) | 04-Test | SAP SP SBX-Execute test scripts | PMO | PMO | SI | Onshore | Das; Abhranil | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | Yes |  |  |  | Future Task | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068034 | No | Yes | No | Program | Enhancement Pack Application (in Program) | 04-Test | SAP SP SBX-Defect Resolution | PMO | PMO | SI | Onshore | Das; Abhranil | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | Yes |  |  |  | Complete | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 45 | -30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068035 | No | Yes | No | Program | Enhancement Pack Application (in Program) | 05-Cutover/Go-live | SAP SP SBX-Transport sequenced and imported | PMO | PMO | SI | Onshore | Das; Abhranil | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-09-11 | 2017-09-11 | Yes |  |  |  | Future Task | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068036 | No | Yes | No | Program | Enhancement Pack Application (in Program) | 05-Cutover/Go-live | SAP SP SBX-Go/No-go decision and Upgrade Implemented in system | PMO | PMO | SI | Onshore | Das; Abhranil | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-09-18 | 2017-09-18 | Yes |  |  |  | Future Task | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 75 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068037 | No | Yes | No | Program | Enhancement Pack Application (in Program) |  | SAP SP-Meeting Cadence | PMO | PMO | SI | Onshore | Das; Abhranil | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068038 | No | Yes | No | Program | Enhancement Pack Application (in Program) |  | SAP SP-Project Management | PMO | PMO | SI | Onshore | Das; Abhranil | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068039 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Onshore | Mooers; Michael | SAP | Yes | OpEx | Global | IT - External | 81.5h | 0h | 81.5h | 2017-07-31 | 2017-08-31 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 16 | 12 | 28 | 18 | 0 | 0 | 0
1068040 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | SI | Onshore | Vargas; Kristin | IBM | Yes | OpEx | Global | IT - External | 20h | 0h | 20h | 2017-07-03 | 2017-08-16 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0
1068041 | No | Yes | No | Program | Program |  | TAI - Project SAP Environment Support | TAI | TAI | SI | Onshore | Kaler; Manpreet | Accenture | Yes | CapEx | Global | IT - External | 96h | 0h | 96h | 2017-07-10 | 2017-07-28 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068042 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 01-Preparation | Upgrade Overall Project Plan | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 159h | 45h | 204h | 2017-07-10 | 2017-09-29 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 10 | 20 | 25 | 15 | 16 | 20 | 25 | 25 | 0 | 0
1068043 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 01-Preparation | Sandbox Upgrade Plan | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 10h | 0h | 10h | 2017-07-10 | 2017-07-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068044 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 02-Analyze | Prepare for sandbox upgrade | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 13h | 0h | 13h | 2017-07-10 | 2017-07-14 | Yes |  |  |  | Complete | 2017-06-05 | 2017-09-29 | 0 |  |  | 0 | -55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068045 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 03-Design/Build | SAP SP SBX -Execute SPS Upgrade | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 15h | 0h | 15h | 2017-07-17 | 2017-07-21 | Yes |  |  |  | Complete | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068046 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 03-Design/Build | SAP SP SBX-Update SBX-S1-Upgrade ECC, BW, APO, PO | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 16h | 0h | 16h | 2017-07-10 | 2017-07-21 | Yes |  |  |  | Future Task | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 19 | -50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068047 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 03-Design/Build | SAP SP SBX -Upgrade TM, GBT, EWM, GTS, GW-Fiori | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 13h | 0h | 13h | 2017-07-11 | 2017-07-21 | Yes |  |  |  | Complete | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068048 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 03-Design/Build | SAP SP SBX-ABAP Remediation (SPDD & SPAU) | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 10h | 0h | 10h | 2017-07-10 | 2017-07-14 | Yes |  |  |  | Complete | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 19 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068049 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 03-Design/Build | SAP SP SBX-Release Transports | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-09-25 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068050 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 04-Test | SAP SP SBX-Identify and write test cases & scripts | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 10h | 20h | 30h | 2017-07-24 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068051 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 04-Test | SAP SP SBX-Execute test scripts | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 123h | 40h | 163h | 2017-07-24 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 20 | 20 | 12 | 16 | 20 | 20 | 0 | 0
1068052 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 04-Test | SAP SP SBX-Defect Resolution | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 18h | 0h | 18h | 2017-08-07 | 2017-08-18 | Yes |  |  |  | Complete | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 45 | -30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 8 | 0 | 0 | 0 | 0 | 0
1068053 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 05-Cutover/Go-live | SAP SP SBX-Transport sequenced and imported | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-09-22 | 2017-09-22 | Yes |  |  |  | Future Task | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068054 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 05-Cutover/Go-live | SAP SP SBX-Go/No-go decision and Upgrade Implemented in system | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-09-18 | 2017-09-18 | Yes |  |  |  | Future Task | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 75 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068055 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 03-Design/Build | SAP SP Q2-Execute SPS Upgrade | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 90h | 90h | 2018-02-05 | 2018-04-06 | Yes |  |  |  | Future Task | 2018-02-05 | 2018-04-06 | 0 |  | 1000-1300 Quality-1320 Quality 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068056 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 03-Design/Build | SAP SP Q2-Upgrade ECC, BW, APO, PO | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 90h | 90h | 2018-02-05 | 2018-04-06 | Yes |  |  |  | Future Task | 2018-02-05 | 2018-04-06 | 0 |  | 1000-1300 Quality-1320 Quality 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068057 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 03-Design/Build | SAP SP Q2-Upgrade TM, GBT, EWM, GTS, GW-Fiori | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 60h | 60h | 2018-02-05 | 2018-03-16 | Yes |  |  |  | Future Task | 2018-02-05 | 2018-03-16 | 0 |  | 1000-1300 Quality-1320 Quality 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068058 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 03-Design/Build | SAP SP Q2-ABAP Remediation (SPDD & SPAU) | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 60h | 60h | 2018-02-05 | 2018-03-16 | Yes |  |  |  | Future Task | 2018-02-05 | 2018-03-16 | 0 |  | 1000-1300 Quality-1320 Quality 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068059 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 03-Design/Build | SAP SP Q2-Release Transports | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2018-02-05 | 2018-02-05 | Yes |  |  |  | Future Task | 2018-02-05 | 2018-02-05 | 0 |  | 1000-1300 Quality-1320 Quality 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068060 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 04-Test | SAP SP Q2-Identify and write test cases & scripts | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 35h | 35h | 2018-02-05 | 2018-03-23 | Yes |  |  |  | Future Task | 2018-02-05 | 2018-03-23 | 0 |  | 1000-1300 Quality-1320 Quality 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068061 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 04-Test | SAP SP Q2-Execute test scripts | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 30h | 30h | 2018-03-19 | 2018-04-06 | Yes |  |  |  | Future Task | 2018-03-19 | 2018-04-06 | 0 |  | 1000-1300 Quality-1320 Quality 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068062 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 04-Test | SAP SP Q2-Defect Resolution | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 30h | 30h | 2018-03-19 | 2018-04-06 | Yes |  |  |  | Future Task | 2018-03-19 | 2018-04-06 | 0 |  | 1000-1300 Quality-1320 Quality 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068063 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 05-Cutover/Go-live | SAP SP Q2-Transport sequenced and imported | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2018-02-05 | 2018-02-05 | Yes |  |  |  | Future Task | 2018-02-05 | 2018-02-05 | 0 |  | 1000-1300 Quality-1320 Quality 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068064 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 05-Cutover/Go-live | SAP SP Q2-Go/No-go decision and Upgrade Implemented in system | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 10h | 10h | 2018-03-26 | 2018-04-06 | Yes |  |  |  | Future Task | 2018-03-26 | 2018-04-06 | 0 |  | 1000-1300 Quality-1320 Quality 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068065 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 03-Design/Build | SAP SP DEV-Execute SPS Upgrade | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 90h | 90h | 2017-10-02 | 2017-12-01 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-12-01 | 0 |  | 1000-1200 Development-1210 Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068066 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 03-Design/Build | SAP SP DEV-Upgrade ECC, BW, APO, PO | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 90h | 90h | 2017-10-02 | 2017-12-01 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-12-01 | 0 |  | 1000-1200 Development-1210 Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068067 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 03-Design/Build | SAP SP DEV-Upgrade TM, GBT, EWM, GTS, GW-Fiori | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 60h | 60h | 2017-10-02 | 2017-11-10 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-11-10 | 0 |  | 1000-1200 Development-1210 Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068068 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 03-Design/Build | SAP SP DEV-ABAP Remediation (SPDD & SPAU) | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 60h | 60h | 2017-10-02 | 2017-11-10 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-11-10 | 0 |  | 1000-1200 Development-1210 Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068069 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 03-Design/Build | SAP SP DEV-Release Transports | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-10-02 | 0 |  | 1000-1200 Development-1210 Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068070 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 04-Test | SAP SP DEV-Identify and write test cases & scripts | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 35h | 35h | 2017-10-02 | 2017-11-17 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-11-17 | 0 |  | 1000-1200 Development-1210 Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068071 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 04-Test | SAP SP DEV-Execute test scripts | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 30h | 30h | 2017-11-13 | 2017-12-01 | Yes |  |  |  | Future Task | 2017-11-13 | 2017-12-01 | 0 |  | 1000-1200 Development-1210 Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068072 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 04-Test | SAP SP DEV-Defect Resolution | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 30h | 30h | 2017-11-13 | 2017-12-01 | Yes |  |  |  | Future Task | 2017-11-13 | 2017-12-01 | 0 |  | 1000-1200 Development-1210 Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068073 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 05-Cutover/Go-live | SAP SP DEV-Transport sequenced and imported | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-11-20 | 2017-11-20 | Yes |  |  |  | Future Task | 2017-11-20 | 2017-11-20 | 0 |  | 1000-1200 Development-1210 Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068074 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 05-Cutover/Go-live | SAP SP DEV-Go/No-go decision and Upgrade Implemented in system | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 10h | 10h | 2017-11-20 | 2017-12-01 | Yes |  |  |  | Future Task | 2017-11-20 | 2017-12-01 | 0 |  | 1000-1200 Development-1210 Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068075 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 03-Design/Build | SAP SP Q1-Execute SPS Upgrade | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 90h | 90h | 2017-12-04 | 2018-02-02 | Yes |  |  |  | Future Task | 2017-12-04 | 2018-02-02 | 0 |  | 1000-1300 Quality-1310 Quality 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068076 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 03-Design/Build | SAP SP Q1-Upgrade ECC, BW, APO, PO | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 90h | 90h | 2017-12-04 | 2018-02-02 | Yes |  |  |  | Future Task | 2017-12-04 | 2018-02-02 | 0 |  | 1000-1300 Quality-1310 Quality 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068077 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 03-Design/Build | SAP SP Q1-Upgrade TM, GBT, EWM, GTS, GW-Fiori | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 60h | 60h | 2017-12-04 | 2018-01-12 | Yes |  |  |  | Future Task | 2017-12-04 | 2018-01-12 | 0 |  | 1000-1300 Quality-1310 Quality 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068078 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 03-Design/Build | SAP SP Q1-ABAP Remediation (SPDD & SPAU) | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 60h | 60h | 2017-12-04 | 2018-01-12 | Yes |  |  |  | Future Task | 2017-12-04 | 2018-01-12 | 0 |  | 1000-1300 Quality-1310 Quality 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068079 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 03-Design/Build | SAP SP Q1-Release Transports | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-12-04 | 2017-12-04 | Yes |  |  |  | Future Task | 2017-12-04 | 2017-12-04 | 0 |  | 1000-1300 Quality-1310 Quality 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068080 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 04-Test | SAP SP Q1-Identify and write test cases & scripts | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 35h | 35h | 2017-12-04 | 2018-01-19 | Yes |  |  |  | Future Task | 2017-12-04 | 2018-01-19 | 0 |  | 1000-1300 Quality-1310 Quality 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068081 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 04-Test | SAP SP Q1-Execute test scripts | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 30h | 30h | 2018-01-15 | 2018-02-02 | Yes |  |  |  | Future Task | 2018-01-15 | 2018-02-02 | 0 |  | 1000-1300 Quality-1310 Quality 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068082 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 04-Test | SAP SP Q1-Defect Resolution | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 30h | 30h | 2018-01-15 | 2018-02-02 | Yes |  |  |  | Future Task | 2018-01-15 | 2018-02-02 | 0 |  | 1000-1300 Quality-1310 Quality 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068083 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 05-Cutover/Go-live | SAP SP Q1-Transport sequenced and imported | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-12-04 | 2017-12-04 | Yes |  |  |  | Future Task | 2017-12-04 | 2017-12-04 | 0 |  | 1000-1300 Quality-1310 Quality 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068084 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 05-Cutover/Go-live | SAP SP Q1-Go/No-go decision and Upgrade Implemented in system | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 10h | 10h | 2018-01-22 | 2018-02-02 | Yes |  |  |  | Future Task | 2018-01-22 | 2018-02-02 | 0 |  | 1000-1300 Quality-1310 Quality 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068085 | No | No | Yes | Program | Enhancement Pack Application (in Program) |  | SAP SP DEV–Dev | TAI | TAI | SI | Offshore | Duggu; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 360h | 360h | 2017-10-02 | 2017-12-01 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-12-01 | 0 |  | 1000-1200 Development-1210 Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068086 | No | No | Yes | Program | Program | 03-Design/Build | Basis Management | TAI | TAI | SI | Onshore | Chakka; Ravi | Accenture | Yes | CapEx | Global | IT - External | 320h | 160h | 480h | 2017-07-10 | 2017-09-29 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0
1068087 | No | No | Yes | Program | Program | 03-Design/Build | Basis Management | TAI | TAI | SI | Onshore | Nezirovic; Samir | Accenture | Yes | CapEx | Global | IT - External | 277.5h | 160h | 437.5h | 2017-07-17 | 2017-09-29 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.5 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0
1068088 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | SI | Onshore | Collins; Daniel | SAP | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  | DMS |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068089 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | Saputo | Onshore | Soni; Shailendra | Saputo | Yes | OpEx | Global | IT - Internal | 48h | 0h | 48h | 2017-06-12 | 2017-08-18 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0
1068090 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | SI | Offshore | Banay; Jeffrey | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-07-21 | 2017-07-21 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068091 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | SI | Offshore | Radhika; Palivela | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068092 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | Saputo | Onshore | Bedard; Martine | Saputo | Yes | OpEx | Global | Business | 34h | 0h | 34h | 2017-06-12 | 2017-06-22 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068093 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | SI | Onshore | Nathan; Ram | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068094 | No | No | Yes | Program | Enhancement Pack Application (in Program) |  | SAP SP SBX-Test-Support-LOG | LOG | FUN | SI | Offshore | Navaratna; Shrikant | IBM | Yes | CapEx | Global | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068095 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | SI | Offshore | Navaratna; Shrikant | IBM | Yes | OpEx | Global | IT - External | 90h | 0h | 90h | 2017-06-19 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068096 | No | No | Yes | Program | Program |  | Delivery Leadership SAP | PMO | PMO | SI | Onshore | Cuzner; Chris | SAP | Yes | CapEx | Global | IT - External | 578h | 480h | 1,058h | 2017-04-28 | 2017-12-29 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 32 | 24 | 24 | 26 | 30 | 32 | 32 | 32 | 26 | 30 | 23 | 32 | 32 | 32 | 31 | 26 | 32 | 25 | 32 | 0
1068097 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | SI | Offshore | Chaturvedi; Himanshu | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068098 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | SI | Onshore | Guru; Kiran | IBM | Yes | OpEx | Global | IT - External | 8h | 0h | 8h | 2017-06-19 | 2017-06-22 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068099 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Dvn; Satya | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-23 | 2017-06-23 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068100 | No | No | Yes | Program | Enhancement Pack Application (in Program) |  | SAP SP Q1–Dev | DEV | DEV | SI | Offshore | MR; Smitha | IBM | Yes | CapEx | Global | IT - External | 0h | 328h | 328h | 2017-12-04 | 2018-02-02 | Yes |  |  |  | Future Task | 2017-12-04 | 2018-02-02 | 0 |  | 1000-1300 Quality-1310 Quality 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068101 | No | No | Yes | Program | Enhancement Pack Application (in Program) |  | SAP SP SBX–Dev | DEV | DEV | SI | Offshore | MR; Smitha | IBM | Yes | CapEx | Global | IT - External | 288h | 90h | 378h | 2017-07-25 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 45 | 36 | 36 | 45 | 45 | 45 | 0
1068102 | No | No | Yes | Program | Enhancement Pack Application (in Program) |  | SAP SP Q2–Dev | DEV | DEV | SI | Offshore | MR; Smitha | IBM | Yes | CapEx | Global | IT - External | 0h | 360h | 360h | 2018-02-05 | 2018-04-06 | Yes |  |  |  | Future Task | 2018-02-05 | 2018-04-06 | 0 |  | 1000-1300 Quality-1320 Quality 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068103 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 03-Design/Build | SAP SP SBX-ABAP Remediation (SPDD & SPAU) | DEV | DEV | SI | Offshore | MR; Smitha | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-09-21 | Yes |  |  |  | Complete | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 19 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068104 | No | No | Yes | Program | Enhancement Pack Application (in Program) | 03-Design/Build | SAP SP SBX-ABAP Remediation (SPDD & SPAU) | DEV | DEV | SI | Offshore | Parida; Sasmita | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-09-21 | Yes |  |  |  | Complete | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 19 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068105 | No | No | Yes | Program | Enhancement Pack Application (in Program) |  | SAP SP SBX–Dev | DEV | DEV | SI | Offshore | Parida; Sasmita | IBM | Yes | CapEx | Global | IT - External | 297h | 90h | 387h | 2017-07-25 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 36 | 36 | 45 | 45 | 45 | 0
1068106 | No | No | Yes | Program | Enhancement Pack Application (in Program) |  | SAP SP Q2–Dev | DEV | DEV | SI | Offshore | Parida; Sasmita | IBM | Yes | CapEx | Global | IT - External | 0h | 360h | 360h | 2018-02-05 | 2018-04-06 | Yes |  |  |  | Future Task | 2018-02-05 | 2018-04-06 | 0 |  | 1000-1300 Quality-1320 Quality 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068107 | No | No | Yes | Program | Enhancement Pack Application (in Program) |  | SAP SP Q1–Dev | DEV | DEV | SI | Offshore | Parida; Sasmita | IBM | Yes | CapEx | Global | IT - External | 0h | 328h | 328h | 2017-12-04 | 2018-02-02 | Yes |  |  |  | Future Task | 2017-12-04 | 2018-02-02 | 0 |  | 1000-1300 Quality-1310 Quality 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068108 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - CM | CM | CM | SI | Onshore | Brown; Genevieve | Other | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068109 | No | No | Yes | Program | Program |  | PMO-Communication | CM | CM | SI | Onshore | Brown; Genevieve | Other | Yes | OpEx | Global | IT - External | 145.32h | 15h | 160.32h | 2016-10-24 | 2017-12-29 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 1.2 | 1.2 | 2 | 2 | 2.3 | 2.1 | 2 | 2 | 2 | 1.22 | 0 | 0 | 0 | 11.25 | 6.5 | 5.5 | 5.25 | 4 | 6 | 3.5 | 5 | 4 | 2.5 | 3.75 | 3.75 | 7 | 3.5 | 2 | 4.5 | 7 | 7 | 3 | 2 | 2.5 | 2.5 | 2.5 | 2 | 2 | 0
1068110 | No | No | Yes | Program | Program |  | TAI - Project SAP Environment Support | TAI | TAI | SI | Offshore | Borromeo; Efren | Accenture | Yes | CapEx | Global | IT - External | 135h | 180h | 315h | 2017-08-01 | 2017-09-29 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 36 | 36 | 27 | 0 | 0 | 0 | 0
1068111 | No | No | Yes | Program | Program |  | PMO admin and support | PMO | PMO | SI | Onshore | NadeauRouthier; Justine | IBM | Yes | CapEx | Global | IT - External | 961h | 2,344.27h | 3,305.27h | 2017-03-27 | 2018-10-01 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 36 | 44 | 44 | 44 | 44 | 44 | 36 | 15 | 14 | 35 | 31 | 26 | 44 | 44 | 44 | 44 | 44 | 36 | 44 | 44 | 36 | 36 | 44 | 0
1068112 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - BI | BI | BI | SI | Offshore | Sable; Dinesh | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068113 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - MDG - DM | MDG | DM | SI | Offshore | Rubi; Nelson | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068114 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Udekar; Vinay | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068115 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Dhanik; Piyush | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068116 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | SI | Offshore | Gattani; Praveen | IBM | Yes | OpEx | Global | IT - External | 37h | 0h | 37h | 2017-06-19 | 2017-07-14 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 12 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068117 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Offshore | Patil; Pralhad | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068118 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Offshore | Chougule; Vinay | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068119 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DM | MDG | DM | Saputo | Onshore | Ansari; MuhammadAkber | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-06-05 | 2017-06-09 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068120 | No | No | Yes | Program | Program | 03-Design/Build | SEC Project Support | SEC | SEC | SI | Offshore | DeGuzman; Patricia | Accenture | Yes | CapEx | Global | IT - External | 216h | 0h | 216h | 2016-10-12 | 2017-08-18 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 45 | 45 | 45 | 27 | 45 | 0 | 0 | 0 | 0 | 0
1068121 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - CM | CM | CM | SI | Onshore | Candy; Paul | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068122 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | SI | Offshore | Patil; Sanjay | IBM | Yes | OpEx | Global | IT - External | 166h | 0h | 166h | 2017-06-12 | 2017-07-24 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 36 | 25 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068123 | No | No | Yes | Program | Enhancement Pack Application (in Program) |  | SAP SP SBX-Test-Support-LOG | LOG | FUN | SI | Offshore | Patil; Sanjay | IBM | Yes | CapEx | Global | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068124 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | SI | Offshore | Munagala; Praveen | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068125 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | SI | Offshore | Alvarez; Ronald | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-07-21 | 2017-07-21 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068126 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Offshore | Deshmukh; Sandip | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068127 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Offshore | Rai; Kaushal | IBM | Yes | OpEx | Global | IT - External | 80h | 0h | 80h | 2017-06-26 | 2017-09-06 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 18 | 0 | 0
1068128 | No | No | Yes | Program | Program | 03-Design/Build | Global - Provide Functional Integration Solutions | PMO | PMO | SI | Offshore | Mitra; Indrajit | IBM | Yes | CapEx | Global | IT - External | 900h | 913h | 1,813h | 2017-04-24 | 2018-02-23 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 39 | 45 | 45 | 45 | 45 | 4 | 45 | 45 | 45 | 45 | 42 | 45 | 45 | 45 | 45 | 34 | 45 | 45 | 36 | 44 | 44
1068129 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Offshore | Shukla; Anant | IBM | Yes | OpEx | Global | IT - External | 45h | 0h | 45h | 2017-07-03 | 2017-07-07 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068130 | No | No | Yes | Program | Enhancement Pack Application (in Program) |  | SAP SP SBX-Test-Support-LOG | PTM | FUN | SI | Offshore | Shukla; Anant | IBM | Yes | CapEx | Global | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068131 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - SEC | SEC | SEC | Saputo | Onshore | Kumar; Kunjan | Saputo | Yes | OpEx | Global | IT - Internal | 136h | 0h | 136h | 2017-06-12 | 2017-07-07 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 32 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068132 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTP | PTP | FUN | SI | Offshore | Umraode; Mayank | IBM | Yes | OpEx | Global | IT - External | 90h | 0h | 90h | 2017-06-12 | 2017-06-23 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068133 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Onshore | Villacorta; Junne | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068134 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | SI | Onshore | Khan; Jamsheed | IBM | Yes | OpEx | Global | IT - External | 7h | 0h | 7h | 2017-07-06 | 2017-07-13 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068135 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - PTM | PTM | FUN | SI | Offshore | Gaikwad; Pradeep | IBM | Yes | OpEx | Global | IT - External | 93h | 0h | 93h | 2017-06-05 | 2017-06-23 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 28 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068136 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | SI | Offshore | Rosal; Gielany | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068137 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | SI | Offshore | Villanueva; Carl | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-12 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068138 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DC | MDG | DC | SI | Offshore | Mendoza; Jeslyn | Accenture | Yes | OpEx | Global | IT - External | 27h | 0h | 27h | 2017-07-04 | 2017-07-07 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068139 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - MDG - DM | MDG | DC | SI | Onshore | DeGuzman; Sheena | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-07-21 | 2017-07-21 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068140 | No | No | Yes | Program | Enhancement Pack Application (in Program) |  | SAP SP SBX-Test-Support-Support | RTR | FUN | SI | Offshore | Kumar; Sameer | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | Yes |  |  |  | Future Task | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068141 | No | No | Yes | Program | Enhancement Pack Application (in Program) |  | SAP SP SBX-Test-Support-RTR | RTR | FUN | SI | Offshore | Kumar; Sameer | IBM | Yes | CapEx | Global | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-06-05 | 2017-09-29 | 0 |  | 1000-1100 Sandbox-1110 Sandbox | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068142 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | SI | Offshore | Kumar; Sameer | IBM | Yes | OpEx | Global | IT - External | 90h | 0h | 90h | 2017-06-05 | 2017-06-21 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 27 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068143 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - SEC | SEC | SEC | SI | Offshore | Quinto; Christian | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-07 | 2017-06-15 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068144 | No | No | Yes | Program | Program | 03-Design/Build | Solution Manager (build) | SEC | SEC | SI | Offshore | Quinto; Christian | Accenture | Yes | CapEx | Global | IT - External | 36h | 0h | 36h | 2017-08-28 | 2017-09-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0
1068145 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - BI | BI | BI | SI | Onshore | Kante; Sai | IBM | Yes | OpEx | Global | IT - External | 54h | 0h | 54h | 2017-07-06 | 2017-08-04 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 8 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068146 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Singh; Vipul | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068147 | No | Yes | No | Program | Program | 03-Design/Build | SEC Project Support | SEC | SEC | SI | Onshore | Gill; Anand | Accenture | Yes | CapEx | Global | IT - External | 69.5h | 0h | 69.5h | 2016-10-11 | 2017-06-04 | Yes |  |  |  | On Schedule | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 | 2.5 | 5 | 4 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068148 | No | Yes | No | Program | Program |  | Knowledge_Transfer_AMS - SEC | SEC | SEC | SI | Onshore | Gill; Anand | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-07 | 2017-06-07 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068149 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - RTR | RTR | FUN | Saputo | Onshore | Lee; Jihoon | Saputo | Yes | OpEx | Global | IT - Internal | 152h | 0h | 152h | 2017-06-12 | 2017-08-04 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 12 | 0 | 5 | 5 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068150 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - LOG | LOG | FUN | SI | Offshore | Dhyani; Subhash | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068151 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | SI | Offshore | Bhardwaj; Smriti | IBM | Yes | OpEx | Global | IT - External | 42h | 0h | 42h | 2017-07-04 | 2017-07-14 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068152 | No | No | Yes | Program | Program |  | Knowledge_Transfer_AMS - OTC | OTC | FUN | SI | Offshore | Verma; Poonam | IBM | Yes | OpEx | Global | IT - External | 9h | 0h | 9h | 2017-06-15 | 2017-06-29 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068204 | No | No | Yes | SCUSA | SCUSA | 01-Preparation | SCUSA-Workshop Preparation Decks-LOG | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes |  | Localization | IT - External | 0h | 0h | 0h | 2017-10-09 | 2017-10-09 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068205 | No | No | Yes | SCUSA | SCUSA | 01-Preparation | SCUSA-Consolidated Workshop Schedule-LOG | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes |  | Localization | IT - External | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068206 | No | No | Yes | SCUSA | SCUSA | 01-Preparation | SCUSA-Requirements Traceability Matrix (RTM)-LOG | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes |  | Localization | IT - External | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068207 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | ACT-FUN.Requirements/Process Design Workshops | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068208 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN.Requirements/Process Design Workshop Decks | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-16 | 2017-08-16 | Yes |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068209 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN-107.Workshop Preparation Decks | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068210 | No | No | Yes | SCUSA | SCUSA |  | Communication Plan | CM | CM | Saputo | Onshore | Gabra; Rania | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 160h | 160h | 2017-09-11 | 2017-12-29 | Yes |  |  | DELIV-CM-106.Communication Plan | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068211 | No | No | Yes | SCUSA | SCUSA | 01-Preparation | SCUSA-Requirements Traceability Matrix (RTM)-PTM | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes |  | Localization | IT - External | 0h | 36h | 36h | 2017-09-05 | 2017-10-06 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068212 | No | No | Yes | SCUSA | SCUSA | 01-Preparation | SCUSA-Consolidated Workshop Schedule-PTM | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes |  | Localization | IT - External | 0h | 16h | 16h | 2017-10-02 | 2017-10-27 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068213 | No | No | Yes | SCUSA | SCUSA | 01-Preparation | SCUSA-Workshop Preparation Decks-PTM | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes |  | Localization | IT - External | 0h | 12h | 12h | 2017-10-10 | 2017-10-27 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068214 | No | Yes | No | SCUSA | SCUSA INTERIM | 01-Preparation | ACT-FUN.Requirements/Process Design Workshops | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068215 | No | Yes | No | SCUSA | SCUSA INTERIM | 01-Preparation | DELIV-FUN-101.Consolidated Workshop Schedule | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068216 | No | Yes | No | SCUSA | SCUSA INTERIM | 01-Preparation | DELIV-FUN-150.Fit/Gap Analysis & Log | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | Yes |  |  | DELIV-FUN-150.Fit/Gap Analysis & Log | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068217 | No | Yes | No | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN.Fit/Gap Workshop Note | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068218 | No | Yes | No | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN.Gap Definition | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-15 | 2017-08-15 | Yes |  |  | WP-FUN.Gap Definition | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068219 | No | Yes | No | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN-107.Workshop Preparation Decks | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068220 | No | Yes | No | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN.Requirements/Process Design Workshop Decks | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | Yes |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068221 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | ACT-FUN.Requirements/Process Design Workshops | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | CapEx | Localization | IT - Internal | 4.5h | 8h | 12.5h | 2017-08-21 | 2017-10-06 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 0 | 0 | 0 | 0
1068222 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN.Gap Definition | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | CapEx | Localization | Business | 40h | 8h | 48h | 2017-09-11 | 2017-09-18 | Yes |  |  | WP-FUN.Gap Definition | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0
1068223 | No | No | Yes | SCUSA | SCUSA |  | Manage Project - SCUSA | PMO | PMO | SI | Onshore | Nirmal; Anup | IBM | Yes | CapEx | Localization | IT - External | 100h | 708.8h | 808.8h | 2017-08-21 | 2018-01-09 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 12 | 44 | 0
1068224 | No | No | Yes | SCUSA | SCUSA | 01-Preparation | SCUSA-Requirements Traceability Matrix (RTM)-PTP | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes |  | Localization | IT - External | 0h | 36h | 36h | 2017-09-05 | 2017-10-06 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068225 | No | No | Yes | SCUSA | SCUSA | 01-Preparation | SCUSA-Workshop Preparation Decks-PTP | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes |  | Localization | IT - External | 0h | 12h | 12h | 2017-10-09 | 2017-10-27 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068226 | No | No | Yes | SCUSA | SCUSA | 01-Preparation | SCUSA-Consolidated Workshop Schedule-PTP | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes |  | Localization | IT - External | 0h | 16h | 16h | 2017-10-02 | 2017-10-27 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068227 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | DELIV-FUN-101.Consolidated Workshop Schedule | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068228 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | DELIV-FUN-150.Fit/Gap Analysis & Log | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | Yes |  |  | DELIV-FUN-150.Fit/Gap Analysis & Log | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068229 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN.Fit/Gap Workshop Note | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068230 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN.Gap Definition | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-02 | 2017-08-02 | Yes |  |  | WP-FUN.Gap Definition | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068231 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN.Requirements/Process Design Workshop Decks | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-16 | 2017-08-16 | Yes |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068232 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN-107.Workshop Preparation Decks | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068233 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | ACT-FUN.Requirements/Process Design Workshops | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068234 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | ACT-FUN.Requirements/Process Design Workshops | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 4h | 8h | 12h | 2017-08-16 | 2017-09-29 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0
1068235 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | ACT-FUN.Requirements/Process Design Workshops | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2017-07-31 | 2017-08-25 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 7 | 10 | 0 | 0 | 0 | 0
1068236 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | DELIV-FUN-101.Consolidated Workshop Schedule | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068237 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | DELIV-FUN-150.Fit/Gap Analysis & Log | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 4h | 8h | 12h | 2017-08-28 | 2017-09-29 | Yes |  |  | DELIV-FUN-150.Fit/Gap Analysis & Log | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
1068238 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN.Fit/Gap Workshop Note | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 4h | 20h | 24h | 2017-08-28 | 2017-09-29 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
1068239 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN.Gap Definition | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 9h | 32h | 41h | 2017-08-15 | 2017-09-29 | Yes |  |  | WP-FUN.Gap Definition | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 8 | 0 | 0 | 0
1068240 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN.Requirements/Process Design Workshop Decks | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 13h | 48h | 61h | 2017-08-14 | 2017-09-29 | Yes |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 12 | 0 | 0 | 0
1068241 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN-107.Workshop Preparation Decks | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 10h | 8h | 18h | 2017-08-14 | 2017-09-29 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 2 | 0 | 0 | 0
1068242 | No | No | Yes | SCUSA | SCUSA |  | Communication Plan | CM | CM | Saputo | Onshore | Goldstein; Evan | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 160h | 160h | 2017-09-11 | 2017-12-29 | Yes |  |  | DELIV-CM-106.Communication Plan | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068243 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | Interface Architecture (POC) | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | CapEx | Localization | IT - Internal | 25h | 0h | 25h | 2017-07-17 | 2017-08-11 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0
1068244 | No | No | Yes | SCUSA | SCUSA |  | Team Lead - Program Site Readiness Lead (Opex) - PMO | PMO | PMO | Saputo | Onshore | Steringa; Dan | Saputo | Yes | OpEx | Localization | Business | 335h | 432h | 767h | 2017-04-24 | 2018-03-16 | Yes |  |  | DELIV-FUN-029.Site Assessment | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 30 | 0 | 40 | 40 | 20 | 0 | 30 | 10 | 24 | 0 | 20 | 20 | 16 | 0 | 15 | 15 | 15 | 0 | 0 | 0 | 0
1068245 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | ACT-FUN.Requirements/Process Design Workshops | RTR | FUN | Saputo | Onshore | Ethier; Patrice | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068246 | No | No | Yes | SCUSA | SCUSA |  | Manage Project - SCUSA | PMO | PMO | SI | Onshore | Smith; Stephen | IBM | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-08-21 | 2017-08-25 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0
1068247 | No | No | Yes | SCUSA | SCUSA |  | Management (Planning, reporting, CR, cross stream integration) - LOG | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 40h | 40h | 2017-09-05 | 2017-09-29 | Yes |  |  | DELIV-CM-011 | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068248 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | DELIV-FUN-150.Fit/Gap Analysis & Log | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 24h | 24h | 2017-09-05 | 2017-10-13 | Yes |  |  | DELIV-FUN-150.Fit/Gap Analysis & Log | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068249 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN.Gap Definition | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 24h | 24h | 2017-09-01 | 2017-10-13 | Yes |  |  | WP-FUN.Gap Definition | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068250 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN.Requirements/Process Design Workshop Decks | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | Yes |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068251 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN-107.Workshop Preparation Decks | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068252 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | ACT-FUN.Requirements/Process Design Workshops | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068253 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN.Fit/Gap Workshop Note | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068254 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | DELIV-FUN-150.Fit/Gap Analysis & Log | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2017-08-28 | 2017-09-01 | Yes |  |  | DELIV-FUN-150.Fit/Gap Analysis & Log | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0
1068255 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | ACT-FUN.Requirements/Process Design Workshops | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 0h | 4h | 4h | 2017-09-05 | 2017-09-15 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068256 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | ACT-FUN.Requirements/Process Design Workshops | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 15.5h | 0h | 15.5h | 2017-08-07 | 2017-09-08 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 2.5 | 8 | 0 | 0
1068257 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | ACT-FUN.Requirements/Process Design Workshops | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 5h | 15h | 20h | 2017-08-28 | 2017-09-25 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0
1068258 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | ACT-FUN.Requirements/Process Design Workshops | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | CapEx | Localization | Business | 24h | 0h | 24h | 2017-08-07 | 2017-08-24 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0
1068259 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | ACT-FUN.Requirements/Process Design Workshops | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068260 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | ACT-FUN.Requirements/Process Design Workshops | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 50h | 0h | 50h | 2017-07-31 | 2017-08-11 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 40 | 0 | 0 | 0 | 0 | 0 | 0
1068261 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN.Gap Definition | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 0h | 24h | 24h | 2017-09-01 | 2017-10-13 | Yes |  |  | WP-FUN.Gap Definition | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068262 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | DELIV-FUN-150.Fit/Gap Analysis & Log | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 0h | 24h | 24h | 2017-09-05 | 2017-10-13 | Yes |  |  | DELIV-FUN-150.Fit/Gap Analysis & Log | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068263 | No | No | Yes | SCUSA | SCUSA |  | Management (Planning, reporting, CR, cross stream integration) - LOG | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 0h | 40h | 40h | 2017-09-05 | 2017-09-29 | Yes |  |  | DELIV-CM-011 | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068264 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | ACT-FUN.Requirements/Process Design Workshops | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-09-01 | 2017-09-08 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068265 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | ACT-FUN.Requirements/Process Design Workshops | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068266 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | ACT-FUN.Requirements/Process Design Workshops | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 32h | 0h | 32h | 2017-08-07 | 2017-08-10 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0
1068267 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | DELIV-FUN-150.Fit/Gap Analysis & Log | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 0h | 48h | 48h | 2017-09-05 | 2017-09-15 | Yes |  |  | DELIV-FUN-150.Fit/Gap Analysis & Log | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068268 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | ACT-FUN.Requirements/Process Design Workshops | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 9h | 11h | 20h | 2017-08-07 | 2017-09-12 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 4 | 0 | 0
1068269 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | ACT-FUN.Requirements/Process Design Workshops | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-07-31 | 2017-08-04 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068270 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | Interface Architecture (POC) | DEV | DEV | SI | Landed Onshore | Tubati; Pavan | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2017-07-17 | 2017-07-20 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068271 | No | No | Yes | SCUSA | SCUSA |  | Team Lead - Site Assessment Analysis (Opex) - PTM | PTM | FUN | Saputo | Onshore | Tenhagen; Chris | Saputo | Yes | OpEx | Localization | Business | 413h | 92h | 505h | 2017-04-17 | 2017-09-27 | Yes |  |  | DELIV-FUN-029.Site Assessment | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 34 | 0 | 0 | 40 | 29 | 37 | 37 | 0 | 0 | 4 | 20 | 20 | 35 | 40 | 0 | 20 | 0 | 25 | 0 | 8 | 0
1068272 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | ACT-FUN.Requirements/Process Design Workshops | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 90h | 90h | 2017-09-05 | 2017-11-03 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068273 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | ACT-FUN.Requirements/Process Design Workshops | OTC | FUN | Saputo | Onshore | Larose; Line | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 2h | 2h | 2017-09-01 | 2017-09-08 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068274 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | ACT-FUN.Requirements/Process Design Workshops | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068275 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | ACT-FUN.Requirements/Process Design Workshops | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-08-07 | 2017-08-18 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0
1068276 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | DELIV-FUN-150.Fit/Gap Analysis & Log | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 19h | 0h | 19h | 2017-08-21 | 2017-08-25 | Yes |  |  | DELIV-FUN-150.Fit/Gap Analysis & Log | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0
1068277 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN.Fit/Gap Workshop Note | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068278 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN.Requirements/Process Design Workshop Decks | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-08-14 | 2017-08-18 | Yes |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0
1068279 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN-107.Workshop Preparation Decks | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2017-08-07 | 2017-08-10 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0
1068280 | No | No | Yes | SCUSA | SCUSA INTERIM |  | Management - SCUSA INTERIM | PMO | PMO | SI | Onshore | Von Fintel; Dieter | IBM | Yes | CapEx | Localization | IT - External | 162h | 547h | 709h | 2017-07-10 | 2018-03-05 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 20 | 22 | 27 | 34 | 32 | 9 | 3 | 0
1068281 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | ACT-FUN.Requirements/Process Design Workshops | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 0h | 2h | 2h | 2017-09-05 | 2017-09-08 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068282 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | ACT-FUN.Requirements/Process Design Workshops | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068283 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN.Fit/Gap Workshop Note | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068284 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN.Requirements/Process Design Workshop Decks | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | Yes |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068285 | No | No | Yes | SCUSA | SCUSA | 01-Preparation | SCUSA-Requirements Traceability Matrix (RTM)-RTR | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes |  | Localization | IT - External | 0h | 36h | 36h | 2017-09-04 | 2017-10-06 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068286 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN-107.Workshop Preparation Decks | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068287 | No | No | Yes | SCUSA | SCUSA | 01-Preparation | SCUSA-Workshop Preparation Decks-RTR | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes |  | Localization | IT - External | 0h | 12h | 12h | 2017-10-09 | 2017-10-27 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068288 | No | No | Yes | SCUSA | SCUSA | 01-Preparation | SCUSA-Consolidated Workshop Schedule-RTR | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes |  | Localization | IT - External | 0h | 16h | 16h | 2017-10-02 | 2017-10-27 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068289 | No | No | Yes | SCUSA | SCUSA | 01-Preparation | SCUSA-Consolidated Workshop Schedule-OTC | OTC | FUN | SI | Onshore | Kane; Jeremy | IBM | Yes |  | Localization | IT - External | 0h | 16h | 16h | 2017-10-02 | 2017-10-27 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068290 | No | No | Yes | SCUSA | SCUSA | 01-Preparation | SCUSA-Workshop Preparation Decks-OTC | OTC | FUN | SI | Onshore | Kane; Jeremy | IBM | Yes |  | Localization | IT - External | 0h | 12h | 12h | 2017-10-09 | 2017-10-27 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068291 | No | No | Yes | SCUSA | SCUSA | 01-Preparation | SCUSA-Requirements Traceability Matrix (RTM)-OTC | OTC | FUN | SI | Onshore | Kane; Jeremy | IBM | Yes |  | Localization | IT - External | 0h | 36h | 36h | 2017-09-04 | 2017-10-06 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068292 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | ACT-FUN.Requirements/Process Design Workshops | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-08-09 | 2017-08-30 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 | 10 | 27 | 0 | 0 | 0
1068293 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | ACT-FUN.Requirements/Process Design Workshops | PTM | FUN | SI | Onshore | Stinnes; Derek | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-01 | 2017-09-08 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068294 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | ACT-FUN.Requirements/Process Design Workshops | LOG | FUN | SI |  | Becker; Ray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-25 | 2017-09-01 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068295 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | DELIV-FUN-101.Consolidated Workshop Schedule | LOG | FUN | SI |  | Becker; Ray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-28 | 2017-07-28 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068296 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | DELIV-FUN-150.Fit/Gap Analysis & Log | LOG | FUN | SI |  | Becker; Ray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | Yes |  |  | DELIV-FUN-150.Fit/Gap Analysis & Log | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068297 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN.Fit/Gap Workshop Note | LOG | FUN | SI |  | Becker; Ray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068298 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN.Gap Definition | LOG | FUN | SI |  | Becker; Ray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-02 | 2017-08-02 | Yes |  |  | WP-FUN.Gap Definition | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068299 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN.Requirements/Process Design Workshop Decks | LOG | FUN | SI |  | Becker; Ray | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-08-16 | 2017-08-22 | Yes |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 12 | 0 | 0 | 0 | 0
1068300 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN-107.Workshop Preparation Decks | LOG | FUN | SI |  | Becker; Ray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068301 | No | No | Yes | SCUSA | SCUSA |  | Communication Plan | CM | CM | SI | Onshore | Brown; Genevieve | Other | Yes | OpEx | Localization | IT - External | 0h | 150h | 150h | 2017-09-18 | 2017-12-29 | Yes |  |  | DELIV-CM-106.Communication Plan | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068302 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | DELIV-FUN-101.Consolidated Workshop Schedule | OTC | FUN | SI | Onshore | Khan; Jamsheed | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2017-07-03 | 2017-07-07 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068303 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | DELIV-FUN-150.Fit/Gap Analysis & Log | OTC | FUN | SI | Onshore | Khan; Jamsheed | IBM | Yes | CapEx | Localization | IT - External | 7h | 0h | 7h | 2017-07-31 | 2017-08-04 | Yes |  |  | DELIV-FUN-150.Fit/Gap Analysis & Log | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068304 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN.Fit/Gap Workshop Note | OTC | FUN | SI | Onshore | Khan; Jamsheed | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068305 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN.Gap Definition | OTC | FUN | SI | Onshore | Khan; Jamsheed | IBM | Yes | CapEx | Localization | IT - External | 63h | 0h | 63h | 2017-08-07 | 2017-09-01 | Yes |  |  | WP-FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 5 | 44 | 0 | 0 | 0
1068306 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN.Requirements/Process Design Workshop Decks | OTC | FUN | SI | Onshore | Khan; Jamsheed | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | Yes |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068307 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | WP-FUN-107.Workshop Preparation Decks | OTC | FUN | SI | Onshore | Khan; Jamsheed | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068308 | No | No | Yes | SCUSA | SCUSA INTERIM | 01-Preparation | ACT-FUN.Requirements/Process Design Workshops | OTC | FUN | SI | Onshore | Khan; Jamsheed | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068310 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | AIF Design workshop |  | Missing Stream |  |  | _GD_SEC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2015-08-31 | 2015-08-31 | No |  |  | To delete-To delete.To delete | Late | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068311 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | AIF Configuration |  | Missing Stream |  |  | _GD_SEC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2015-08-31 | 2015-08-31 | No |  |  | To delete-To delete.To delete | Late | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068312 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | AIF Design workshop |  | Missing Stream |  |  | _GD_SEC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2015-08-31 | 2015-08-31 | No |  |  | To delete-To delete.To delete | Late | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068313 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | AIF Configuration |  | Missing Stream |  |  | _GD_SEC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2015-08-31 | 2015-08-31 | No |  |  | To delete-To delete.To delete | Late | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068314 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | SAP GRC Process Control RTM |  | Missing Stream |  |  | _GD_SEC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-SEC-002B.SAP GRC Process Control RTM | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068315 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Security and Controls Processes |  | Missing Stream |  |  | _GD_SEC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-SEC-110.Security and Controls Processes | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068316 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | SAP GRC Configuration Document (SEC) - Deploy1 |  | Missing Stream |  |  | _GD_SEC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-SEC-220.SAP GRC Configuration Document | Future Task | 2017-06-05 | 2017-06-23 | 1 | Security Build | 1000 D1-1300 B-1335 Security Build | -5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068317 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | SAP Security & GRC Processes (SEC) - Deploy1 |  | Missing Stream |  |  | _GD_SEC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | DELIV-SEC-215.SAP Security & GRC Processes | Complete | 2017-06-05 | 2017-06-23 | 1 | Security Build | 1000 D1-1300 B-1335 Security Build | 20 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068318 | Yes | No | No | SDF | SDF Localisation | 04-Test | SEC Break/Fix SIT1 - SEC Deploy1 |  | Missing Stream |  |  | _GD_SEC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | No |  |  | ACT-SEC.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068319 | Yes | No | No | SDF | SDF Localisation | 04-Test | SEC Break/Fix SIT2 - SEC Deploy1 |  | Missing Stream |  |  | _GD_SEC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-SEC.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068320 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | SU24 authorization objects to custom tcodes |  | Missing Stream |  |  | _GD_SEC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2015-09-18 | 2015-09-18 | No |  |  | To delete-To delete.To delete | Late | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068321 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Addition of 8 custom tcodes to new/existing single master/derived |  | Missing Stream |  |  | _GD_SEC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2015-09-18 | 2015-09-18 | No |  |  | To delete-To delete.To delete | Late | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068322 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Unit/Integration Testing Support |  | Missing Stream |  |  | _GD_SEC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2015-09-18 | 2015-09-18 | No |  |  | To delete-To delete.To delete | Late | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068323 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | SOD Analysis |  | Missing Stream |  |  | _GD_SEC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2015-09-18 | 2015-09-18 | No |  |  | To delete-To delete.To delete | Late | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068324 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Update to Security design |  | Missing Stream |  |  | _GD_SEC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2015-09-18 | 2015-09-18 | No |  |  | To delete-To delete.To delete | Late | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068325 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Tracing of 8 custom tcodes |  | Missing Stream |  |  | _GD_SEC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2015-09-18 | 2015-09-18 | No |  |  | To delete-To delete.To delete | Late | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068326 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Security FUT |  | Missing Stream |  |  | _GD_SEC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2015-09-18 | 2015-09-18 | No |  |  | To delete-To delete.To delete | Late | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068327 | No | No | No | SDF | SDF Localisation | 03-Design/Build | Update conversion FSD & FMD | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  |  | Future Task | 2017-05-08 | 2017-06-02 | 1 | Update conversion FSD & FMD | 1000 D1-1300 B-1321 Update conversion FSD & FMD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068328 | No | No | No | SDF | SDF Localisation | 04-Test | QE3 Transports | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  |  | Future Task | 2017-07-17 | 2017-07-21 | 1 | QE3 Transports | 1000 D1-1400 T-1420 QE3 Transports | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068329 | No | No | No | SDF | SDF Localisation | 04-Test | QE3 Dry Run Prep | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | No |  |  |  | Future Task | 2017-07-24 | 2017-08-04 | 1 | QE3 Dry Run Prep | 1000 D1-1400 T-1430 QE3 Dry Run Prep | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068330 | No | No | No | SDF | SDF Localisation | 04-Test | QE3 Prevalidation | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | No |  |  |  | Future Task | 2017-07-24 | 2017-08-04 | 1 | QE3 Prevalidation | 1000 D1-1400 T-1440 QE3 Prevalidation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068331 | No | No | No | SDF | SDF Localisation | 03-Design/Build | Data Construction | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  |  | Future Task | 2017-05-08 | 2017-07-14 | 2 | Data Construction | 20000 D2-20100 B-20111 Data Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068332 | No | No | No | SDF | SDF Localisation | 03-Design/Build | QE2 Trans Prep | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  |  | Future Task | 2017-07-17 | 2017-07-21 | 2 | QE2 Trans Prep | 20000 D2-20100 B-20112 QE2 Trans Prep | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068333 | No | No | No | SDF | SDF Localisation | 03-Design/Build | QE2 Transports | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | No |  |  |  | Future Task | 2017-07-24 | 2017-07-28 | 2 | QE2 Transports | 20000 D2-20100 B-20113 QE2 Transports | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068334 | No | No | No | SDF | SDF Localisation | 03-Design/Build | GAPs | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  |  | Future Task | 2017-05-08 | 2017-08-26 | 2 | GAPs | 20000 D2-20100 B-20142 GAPs | 0 | -65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068335 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D2-B-FUT | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  |  | Future Task | 2017-07-17 | 2017-07-21 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068336 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D2-B-Security Design | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  |  | Future Task | 2017-07-03 | 2017-07-21 | 2 | Security Design | 20000 D2-20100 B-20225 Security Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068337 | No | No | No | SDF | SDF Localisation | 04-Test | D2-T-QE2 DQ Test | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  |  | Future Task | 2017-09-04 | 2017-09-15 | 2 | QE2 DQ Test | 20000 D2-21000 T-21035 QE2 DQ Test | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068338 | No | No | No | SDF | SDF Localisation | 04-Test | D2-T-SIT 1 & 2 Prep | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  |  | Future Task | 2017-09-04 | 2017-09-15 | 2 | SIT 1 & 2 Prep | 20000 D2-21000 T-21036 SIT 1 & 2 Prep | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068339 | No | No | No | SDF | SDF Localisation | 04-Test | D2-T-Regression Prep | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-10-30 | 2017-10-30 | No |  |  |  | Future Task | 2017-10-30 | 2017-11-03 | 2 | Regression Prep | 20000 D2-21000 T-21052 Regression Prep | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068340 | No | No | No | SDF | SDF Localisation | 04-Test | D2-T-Regression (in QE2) | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-11-06 | 2017-11-06 | No |  |  |  | Future Task | 2017-11-06 | 2017-11-24 | 2 | D2 Regression (in QE2) | 20000 D2-21000 T-21054 D2 Regression (in QE2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068341 | No | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | D3-DQ testing | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2018-02-05 | 2018-02-05 | No |  |  |  | Future Task | 2018-03-05 | 2018-03-09 | 3 | DQ testing | 30000 D3-30100 H-30120 DQ testing | -20 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068342 | No | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | D3-Prod Loads | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2018-03-19 | 2018-03-19 | No |  |  |  | Future Task | 2018-03-19 | 2018-03-30 | 3 | Prod Loads | 30000 D3-30100 H-30130 Prod Loads | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068343 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Technology Implementation Plan |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | DELIV-TAI-001.Technology Implementation Plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068344 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Transport Sequence |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | DELIV-PMO-035.Transport Sequence | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068345 | Yes | No | No | SDF | SDF Localisation | 04-Test | Technology Implementation Plan |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-TAI-001.Technology Implementation Plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068346 | Yes | No | No | SDF | SDF Localisation | 04-Test | Network - Solution Network Document |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-TAI-225.Network - Solution Network Document | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068347 | Yes | No | No | SDF | SDF Localisation | 04-Test | Legacy System Retirement strategy |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-TAI-130.Legacy System Retirement strategy | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068348 | Yes | No | No | SDF | SDF Localisation | 04-Test | Transport Sequence |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-PMO-035.Transport Sequence | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068349 | Yes | No | No | SDF | SDF Localisation | 04-Test | Network - Deployment Plan |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-TAI-470.Network - Deployment Plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068350 | Yes | No | No | SDF | SDF Localisation | 04-Test | Performance Test Scripts |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-19 | 2017-07-19 | No |  |  | DELIV-TST-302.Performance Test Scripts | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068351 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Technology Implementation Plan |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-TAI-001.Technology Implementation Plan | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068352 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | SolMan setup and config for Documentation, Charm and Monitoring |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-TAI.SolMan setup & config for Doc | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068353 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Network - Solution Network Document |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-TAI-225.Network - Solution Network Document | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068354 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Legacy System Retirement strategy |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-TAI-130.Legacy System Retirement strategy | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068355 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Architecture by release Diagrams |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-TAI-104.Architecture by release Diagrams | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068356 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Development Environment |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-TAI-101.Development Environment | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068357 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Sandbox Environment |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-TAI-103.Sandbox Environment | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068358 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | SAP Enablement - Technical Requirements |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-TAI-110.SAP Enablement - Technical Requirements | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068359 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Network - Deployment Plan |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-TAI-470.Network - Deployment Plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068360 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Performance Test Scripts |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-TST-302.Performance Test Scripts | Future Task | NA | NA | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068361 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Technology Implementation Plan |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-TAI-001.Technology Implementation Plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068362 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Network - Solution Network Document |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-TAI-225.Network - Solution Network Document | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068363 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Legacy System Retirement strategy |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-TAI-130.Legacy System Retirement strategy | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068364 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Transport Sequence |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-PMO-035.Transport Sequence | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068365 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - DEV |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | No |  |  | ACT-DEV.Execute Break/Fix | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068366 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Manage defects - DEV |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068367 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Break/Fix - DEV |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | No |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0.13 | 5.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068368 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - DEV |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068369 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Manage defects - DEV |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-01 | 2017-10-01 | No |  |  | To delete-To delete.To delete | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068370 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-01 | 2017-10-01 | No |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068371 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Application Architecture Diagram |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-DEV-001.Application Architecture Diagram | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068372 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - DEV |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-19 | 2017-05-19 | No |  |  | ACT-FUN.Management | Future Task | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068373 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | WRICEFs inventory - DEV |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-26 | 2017-05-26 | No |  |  | DELIV-DEV-102.RICEFW Inventory | Future Task | NA | NA | 1 | GAPs | 1000 D1-1200 A-1211GAPs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068374 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - DEV |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068375 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | WRICEFs - DEV (Design/Build) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | To delete-To delete.To delete | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 15.13 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068376 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Unit testing Development Documentation (FUT) - DEV |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068377 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Assembly Test : Execution - DEV |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068378 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | OSS, PoC, Debug - DEV |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068379 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Build queries - DEV |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068380 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Manage defects (DEV) - Deploy1 (Test) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -5 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068381 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Break/Fix (DEV) - Deploy1 (Test) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068382 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Manage defects - DEV |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068383 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Break/Fix - DEV |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068384 | Yes | No | No | SDF | SDF Localisation | 04-Test | Maintain documentation - DEV |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068385 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - DEV |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068386 | Yes | No | No | SDF | SDF Localisation | 04-Test | OSS, PoC, Debug - DEV |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068387 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Application Architecture Diagram |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-DEV-001.Application Architecture Diagram | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068388 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Development Unit Testing Documentation |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-DEV-320.Development Unit Testing Documentation | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068389 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Interface Approach and Error Handling Strategy |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-DEV-144.Interface Approach and Error Handling Strategy | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068390 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Technical Specification - Report |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-DEV-201.Technical Specification - Report | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068391 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Technical Specification - Interface |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-DEV-202.Technical Specification - Interface | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068392 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Technical Specification -Enhancement |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-DEV-203.Technical Specification -Enhancement | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068393 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Technical Specification - Form |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-DEV-204.Technical Specification - Form | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068394 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Technical Specification - Workflow |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-DEV-205.Technical Specification - Workflow | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068395 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068396 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068397 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | No |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068398 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing WRICEFs (Design/Build) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-10 | 2017-02-10 | No |  |  | To delete-To delete.To delete | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -88 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068399 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing Unit testing Development Documentation (FUT) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-10 | 2017-02-10 | No |  |  | DELIV-DEV-320.Development Unit Testing Documentation | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068400 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing Assembly Test : Execution |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-10 | 2017-02-10 | No |  |  | DELIV-DEV-320.Development Unit Testing Documentation | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068401 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | ILOG012-DEV-INT-STO interface |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-19 | 2017-05-19 | No |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-06-12 | 2017-08-04 | 0 | NA Others | 99000-99100-99130 NA others | -15.88 | -30.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068402 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | ILOG013-DEV-INT-STO goods issue interface (SAP to BPCS) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-21 | 2017-04-21 | No |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-06-12 | 2017-08-04 | 0 | NA Others | 99000-99100-99130 NA others | -35 | -50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068403 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | IOTC010-DEV-INT-Sales order interface |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-16 | 2017-06-16 | No |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | 25 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068404 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | ILOG013-STO goods issue interface (SAP to BPCS) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-26 | 2017-05-26 | No |  |  | DELIV-DEV-202.Technical Specification - Interface | Complete | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068405 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | SDF Interim State Project |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | No |  |  | DELIV-DEV-102.RICEFW Inventory | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068406 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | Interim state - WRICEFs |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | No |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068407 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | Interim state - Unit testing Development Documentation (FUT) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | No |  |  | DELIV-DEV-320.Development Unit Testing Documentation | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068408 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | Assembly Test : Execution |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-20 | 2017-01-20 | No |  |  | DELIV-DEV-320.Development Unit Testing Documentation | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068409 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | OSS, PoC, Debug |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | No |  |  | To delete-To delete.To delete | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068410 | Yes | No | No | SDF | Trade (in SDF) | 03-Design/Build | TPM WRICEFs |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | No |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-08-04 | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068411 | Yes | No | No | SDF | Trade (in SDF) | 03-Design/Build | TPM Unit testing Development Documentation (FUT) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-06-16 | 2017-06-16 | No |  |  | DELIV-DEV-320.Development Unit Testing Documentation | Future Task | 2017-06-12 | 2017-08-04 | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068412 | Yes | No | No | SDF | Trade (in SDF) | 03-Design/Build | TPM Assembly Test : Execution |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-06-16 | 2017-06-16 | No |  |  | DELIV-DEV-320.Development Unit Testing Documentation | Future Task | 2017-06-12 | 2017-08-04 | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068413 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | ILOG014-DEV-INT-PGI from BPCS to SAP |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-14 | 2017-04-14 | No |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-06-12 | 2017-08-04 | 0 | NA Others | 99000-99100-99130 NA others | -40 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068414 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | MCP Mini config and masterdata for US and Canada RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-23 | 2017-02-17 | No |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068415 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | IXXX-DEV-G/L interface |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-19 | 2017-05-19 | No |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068416 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | IXXX-DEV-A/P interface |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-05 | 2017-05-05 | No |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -5 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068417 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | SDF-INT-Construct RTM |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | No |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068418 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | Create BPML |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | No |  |  | DELIV-BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068419 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | SDF-INT-Construct RTM |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | No |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068420 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | Conduct requirements Workshops |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068421 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | Conduct requirements Workshops |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068422 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | FSD-ID-INT- Baseline |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | TBD-Tobedefine.Tbd | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068423 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | DEV FUT-ID-INT- Baseline |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-20 | 2017-01-20 | No |  |  | ACT-FUN.Execute FUT | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068424 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | FSD-ID-INT- Baseline |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | TBD-Tobedefine.Tbd | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068425 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | DEV FUT-ID-INT- Baseline |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-20 | 2017-01-20 | No |  |  | ACT-FUN.Execute FUT | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068426 | Yes | No | No | SDF | SDF Interim State Project | 01-Preparation | Workshop Schedule |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068427 | Yes | No | No | SDF | SDF Interim State Project | 01-Preparation | Environment setup |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | No |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068428 | Yes | No | No | SDF | SDF Interim State Project | 01-Preparation | Workshop Schedule |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068429 | Yes | No | No | SDF | SDF Interim State Project | 01-Preparation | Environment setup |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | No |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068430 | Yes | No | No | SDF | Trade (in SDF) | 03-Design/Build | Trade-Functional Specification (FSD) |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068431 | Yes | No | No | SDF | Trade (in SDF) | 03-Design/Build | Trade-Functional Specification (FSD) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068432 | Yes | No | No | SDF | Trade (in SDF) | 03-Design/Build | TPM Unit testing Development Documentation (FUT) |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-01-20 | 2017-01-20 | No |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-08-18 | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068433 | Yes | No | No | SDF | Trade (in SDF) | 03-Design/Build | TPM Unit testing Development Documentation (FUT) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-01-20 | 2017-01-20 | No |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-08-18 | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068434 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Process Workarounds (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | No |  |  | DELIV-FUN-601.Process Workarounds | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068435 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-29 | 2017-08-29 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068436 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068437 | Yes | No | No | SDF | SDF Localisation | 04-Test | Process Workarounds (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-FUN-601.Process Workarounds | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068438 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | 15 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068439 | Yes | No | No | SDF | SDF Localisation | 04-Test | Training Environment Population and Testing (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Training Environment Population and Testing | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068440 | Yes | No | No | SDF | SDF Localisation | 04-Test | Execute SIT1 (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068441 | Yes | No | No | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Functional Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068442 | Yes | No | No | SDF | SDF Localisation | 04-Test | Execute SIT2 (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 9.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068443 | Yes | No | No | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 13.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068444 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Unit testing Development Documentation (FUT) - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | To delete-To delete.To delete | Complete | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | -10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068445 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Unit testing Development Documentation (FUT) - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | To delete-To delete.To delete | Complete | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | -10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068446 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Configuration - RTR - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-07 | No |  |  | To delete-To delete.To delete | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | -5 | 43.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068447 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | SDD Writing - RTR - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068448 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | SDD Writing - RTR - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068449 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Unit testing Configuration Documentation - RTR - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068450 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Unit testing Configuration Documentation - RTR - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068451 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Gather reporting requierements (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | No |  |  | ACT-FUN.Gather reporting requierement | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068452 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Gather reporting requierements (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | No |  |  | ACT-FUN.Gather reporting requierement | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068453 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Support Cutover plan (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-08 | No |  |  | ACT-FUN.Support Cutover plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068454 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Support Cutover plan (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-07 | 2017-07-14 | No |  |  | ACT-FUN.Support Cutover plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068455 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - RTR (Global) |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-21 | 2017-07-21 | No |  |  | ACT-FUN.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068456 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - RTR (Global) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-21 | 2017-07-21 | No |  |  | ACT-FUN.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068457 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-20 | 2017-06-20 | No |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 1 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068458 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-20 | 2017-06-20 | No |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 1 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068459 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Support (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-15 | 2017-06-15 | No |  |  | ACT-FUN.Mock Support | Future Task | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -2 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068460 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Support (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-15 | 2017-06-15 | No |  |  | ACT-FUN.Mock Support | Future Task | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -2 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068461 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Validate (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-07 | No |  |  | ACT-FUN.Mock Support | Future Task | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068462 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Validate (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-07 | No |  |  | ACT-FUN.Mock Support | Future Task | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068463 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Run Tests - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068464 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Run Tests - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068465 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Manage Defects - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068466 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Manage Defects - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068467 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Break/Fix - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068468 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Break/Fix - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068469 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Prepare (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | No |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068470 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Prepare (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | No |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068471 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Support (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | No |  |  | ACT-FUN.Mock Support | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068472 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Support (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | No |  |  | ACT-FUN.Mock Support | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068473 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Validate (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068474 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Validate (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068475 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Run Tests - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068476 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Run Tests - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068477 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Manage Defects - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068478 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Manage Defects - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068479 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Break/Fix - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068480 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Break/Fix - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068481 | Yes | No | No | SDF | SDF Localisation | 04-Test | Regression - Run Tests (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Execute Regression Test | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 9.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068482 | Yes | No | No | SDF | SDF Localisation | 04-Test | Regression - Run Tests (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Execute Regression Test | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 9.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068483 | Yes | No | No | SDF | SDF Localisation | 04-Test | Regression - Manage defects (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | No |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068484 | Yes | No | No | SDF | SDF Localisation | 04-Test | Regression - Manage defects (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | No |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068485 | Yes | No | No | SDF | SDF Localisation | 04-Test | Documentation - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068486 | Yes | No | No | SDF | SDF Localisation | 04-Test | Documentation - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068487 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068488 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068489 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-14 | 2017-04-14 | No |  |  | ACT-FUN.Management | Future Task | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068490 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-14 | 2017-04-14 | No |  |  | ACT-FUN.Management | Future Task | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068491 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Kickoff - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-14 | 2017-04-14 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -9.88 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068492 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Kickoff - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-14 | 2017-04-14 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -9.88 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068493 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | RTM - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068494 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | RTM - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068495 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Log Gaps - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-27 | 2017-04-27 | No |  |  | WP-FUN.Fit/Gap Workshop Note | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -2 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068496 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Log Gaps - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-27 | 2017-04-27 | No |  |  | WP-FUN.Fit/Gap Workshop Note | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -2 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068497 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068498 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068499 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | BPP (Workshops & Gap Resolution) - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068500 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | BPP (Workshops & Gap Resolution) - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068501 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Data collection templates (DCT) - Explain and collect - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068502 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Data collection templates (DCT) - Explain and collect - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068503 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) - RTR - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | To delete-To delete.To delete | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | -15 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068504 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) - RTR - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | To delete-To delete.To delete | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | -15 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068506 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Business Process Master List (BPML) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068507 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Workshop Preparation Decks |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068508 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Workshop Preparation Decks |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-FUN-150.Fit/Gap Analysis & Log | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068509 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Requirements/Process Design Workshop Decks |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068510 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Demo |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Solution Confirmation Prensentations and Demonstrations | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068511 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Gap Definition |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | WP-FUN.Gap Definition | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068512 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Fit/Gap Workshop Note |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068513 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | PDDs |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-21 | 2017-08-21 | No |  |  | DELIV-FUN-110.PDDs | Future Task | 2017-05-01 | 2017-05-05 | 1 | TBD | 99000-99100-99110 TBD | 80 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068514 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Process Documentation in BWL |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Process Documentation in BWL | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068515 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Demo (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT-FUN.Solution Confirmation Prensentations and Demonstrations | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068516 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Process Workarounds (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-601.Process Workarounds | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068517 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068518 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Enhancement (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-27 | 2017-06-27 | No |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 21 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068519 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Interface (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | No |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 7 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068520 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Workflow (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-205.Functional Specification - Workflow | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068521 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Form (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV-FUN-204.Functional Specification - Form | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 5 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068522 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-220.Solution Design Document (SDD) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068523 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Support Operational Procedures (SOPs) (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-314.Support Operational Procedures (SOPs) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068524 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Support Operational Procedures Inventory (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-214.Support Operational Procedures Inventory | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068525 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Execute Assembly Tests (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT-FUN.Execute Assembly Tests | Future Task | 2017-07-03 | 2017-07-14 | 1 | AT | 1000 D1-1300 B-1312 AT | -25 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068526 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Execute FUT (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068530 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | IXXX-DEV FUT-G/L interface |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | No |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | 50 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068531 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | IXXX-FSD-Product cost interface BPCS to SAP |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -25 | -35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068532 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | IXXX-DEV-Product cost interface BPCS to SAP |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-22 | 2017-05-22 | No |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | 5 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068533 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | IXXX-DEV FUT-Product cost interface BPCS to SAP |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-02 | 2017-06-02 | No |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | 10 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068534 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | DDD |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Complete | 2017-04-17 | 2017-05-05 | 1 | Revise DDDs - Division review | 1000 D1-1200 A-1213 Revise DDDs - Division review | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068535 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | SDF-INT-Workshop-Product costing |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-02 | 2017-03-02 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068536 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | SDF-INT-Workshop-Finance |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-01 | 2017-03-01 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068537 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT Preparation : Component & Scripts (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.UAT Preparation | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068538 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT Preparation : Component & Scripts (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.UAT Preparation | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068539 | Yes | No | No | SDF | SDF Localisation | 04-Test | DR - Prepare (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | No |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068540 | Yes | No | No | SDF | SDF Localisation | 04-Test | DR - Prepare (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | No |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068541 | Yes | No | No | SDF | SDF Localisation | 04-Test | DR - Support (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | No |  |  | ACT-FUN.Dry Run activities | Complete | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068542 | Yes | No | No | SDF | SDF Localisation | 04-Test | DR - Support (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | No |  |  | ACT-FUN.Dry Run activities | Complete | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068543 | Yes | No | No | SDF | SDF Localisation | 04-Test | DR - Validate (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068544 | Yes | No | No | SDF | SDF Localisation | 04-Test | DR - Validate (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068545 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Run Tests - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068546 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Run Tests - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068547 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Manage defects - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068548 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Manage defects - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068549 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Break/Fix - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068550 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Break/Fix - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068551 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Document work around - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068552 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Document work around - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068553 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-05 | 2017-09-05 | No |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068554 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-05 | 2017-09-05 | No |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068555 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-21 | 2017-08-21 | No |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068556 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-21 | 2017-08-21 | No |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068557 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-17 | 2017-09-17 | No |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068558 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-17 | 2017-09-17 | No |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068559 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068560 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068561 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-25 | 2017-09-25 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068562 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-25 | 2017-09-25 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068563 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Manage defects (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-01 | 2017-10-01 | No |  |  | To delete-To delete.To delete | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068564 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Manage defects (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-01 | 2017-10-01 | No |  |  | To delete-To delete.To delete | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068565 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068566 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (RTR) - Deploy1 |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068567 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -35 | -16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068568 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -35 | -16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068598 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | ILOG013-STO goods issue interface (SAP to BPCS) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -95 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068599 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068600 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068601 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT Preparation : Component & Scripts (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.UAT Preparation | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068602 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT Preparation : Component & Scripts (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.UAT Preparation | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068603 | Yes | No | No | SDF | SDF Localisation | 04-Test | DR - Prepare (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | No |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068604 | Yes | No | No | SDF | SDF Localisation | 04-Test | DR - Prepare (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | No |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068605 | Yes | No | No | SDF | SDF Localisation | 04-Test | DR - Support (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068606 | Yes | No | No | SDF | SDF Localisation | 04-Test | DR - Support (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068607 | Yes | No | No | SDF | SDF Localisation | 04-Test | DR - Validate (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068608 | Yes | No | No | SDF | SDF Localisation | 04-Test | DR - Validate (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068609 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-01 | 2017-10-01 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068610 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-01 | 2017-10-01 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068611 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-01 | 2017-10-01 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068612 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-01 | 2017-10-01 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068613 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Manage defects (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-01 | 2017-10-01 | No |  |  | To delete-To delete.To delete | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068614 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Manage defects (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-01 | 2017-10-01 | No |  |  | To delete-To delete.To delete | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068615 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-01 | 2017-10-01 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068616 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-01 | 2017-10-01 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068617 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068618 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration). - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-14 | 2017-04-14 | No |  |  | ACT-FUN.Management | Future Task | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068619 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration). - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-14 | 2017-04-14 | No |  |  | ACT-FUN.Management | Future Task | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068620 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Kickoff - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068621 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Kickoff - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068622 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | RTM - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-18 | 2017-04-18 | No |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068623 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | RTM - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-18 | 2017-04-18 | No |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068624 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Gap log - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | WP-FUN.Fit/Gap Workshop Note | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068625 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Gap log - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | WP-FUN.Fit/Gap Workshop Note | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068626 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Run Tests - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068627 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Run Tests - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068628 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Manage defects - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068629 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Manage defects - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068630 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Break/Fix - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068631 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Break/Fix - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068632 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Document work around |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068633 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Document work around |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068634 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -10 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068635 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -10 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068636 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-18 | 2017-09-18 | No |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068637 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-18 | 2017-09-18 | No |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068638 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-17 | 2017-09-17 | No |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068639 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-17 | 2017-09-17 | No |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068640 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068641 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068642 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068643 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068644 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Support (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | No |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068645 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Support (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | No |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068646 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Validate (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | No |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068647 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Validate (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | No |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068648 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Run Tests - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068649 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Run Tests - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068650 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Manage Defects - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068651 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Manage Defects - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068652 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Break/Fix - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068653 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Break/Fix - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068654 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Prepare (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068655 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Prepare (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068656 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Support (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068657 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Support (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068658 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Validate (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068659 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Validate (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068660 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Run Tests - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068661 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Run Tests - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068662 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Manage Defects - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068663 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Manage Defects - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068664 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Break/Fix - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068665 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Break/Fix - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068666 | Yes | No | No | SDF | SDF Localisation | 04-Test | Regression - Run Tests (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068667 | Yes | No | No | SDF | SDF Localisation | 04-Test | Regression - Run Tests (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068668 | Yes | No | No | SDF | SDF Localisation | 04-Test | Regression - Manage defects (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068669 | Yes | No | No | SDF | SDF Localisation | 04-Test | Regression - Manage defects (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068670 | Yes | No | No | SDF | SDF Localisation | 04-Test | Documentation - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068671 | Yes | No | No | SDF | SDF Localisation | 04-Test | Documentation - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068672 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Process Workarounds (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | No |  |  | DELIV-FUN-601.Process Workarounds | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068673 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068674 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068675 | Yes | No | No | SDF | SDF Localisation | 04-Test | Process Workarounds (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-FUN-601.Process Workarounds | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068676 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | 15 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068677 | Yes | No | No | SDF | SDF Localisation | 04-Test | Training Environment Population and Testing (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Training Environment Population and Testing | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068678 | Yes | No | No | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-28 | 2017-07-28 | No |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 5 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068679 | Yes | No | No | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 5 | 33.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068680 | Yes | No | No | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 4.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068681 | Yes | No | No | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068682 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | SDF Interim State-Workshop-Transportation |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-20 | 2017-02-20 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068683 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | SDF Interim State-Workshop-Production receipts and inventory adjustments |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-20 | 2017-02-20 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068684 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Demo - LOG - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT-FUN.Solution Confirmation Prensentations and Demonstrations | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068685 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Process Workarounds (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-601.Process Workarounds | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068686 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts - LOG - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068687 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | WPB Recordings - LOG - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-403.WPB Recordings | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068688 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Report (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 5.13 | 75.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068689 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Enhancement (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068690 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Interface (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068691 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Workflow (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-205.Functional Specification - Workflow | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068692 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Form (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-204.Functional Specification - Form | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068693 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Support Operational Procedures (SOPs) (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-314.Support Operational Procedures (SOPs) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068694 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Support Operational Procedures Inventory (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-214.Support Operational Procedures Inventory | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068695 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Execute Assembly Tests (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT-FUN.Execute Assembly Tests | Future Task | 2017-07-03 | 2017-07-14 | 1 | AT | 1000 D1-1300 B-1312 AT | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068696 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Execute FUT - LOG (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 5 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068697 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Assembly Test Scenarios/Scripts (LOG) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-TST-307.Assembly Test Scenarios/Scripts | Future Task | 2017-07-03 | 2017-07-14 | 1 | AT | 1000 D1-1300 B-1312 AT | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068698 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Business Process Master List (BPML) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068699 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Workshop Preparation Decks |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068700 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Workshop Preparation Decks |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-FUN-150.Fit/Gap Analysis & Log | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068701 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Requirements/Process Design Workshops |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068702 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Requirements/Process Design Workshop Decks |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068703 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Demo |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Solution Confirmation Prensentations and Demonstrations | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068704 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Fit/Gap Workshop Note |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068705 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Process Documentation in BWL |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Process Documentation in BWL | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068706 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Configuration - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068707 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068708 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068709 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Unit testing Configuration Documentation - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068710 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Unit testing Configuration Documentation - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068711 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Gather reporting requierements - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT-FUN.Gather reporting requierement | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068712 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Gather reporting requierements - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT-FUN.Gather reporting requierement | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068713 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Support Cutover plan - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT-FUN.Support Cutover plan | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068714 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Support Cutover plan - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT-FUN.Support Cutover plan | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068715 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (DB) (Planning, reporting, CR, cross stream integration) - LOG(Global) |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT-MDG.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068716 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (DB) (Planning, reporting, CR, cross stream integration) - LOG(Global) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT-MDG.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068717 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | BPP (Workshops & Gap Resolution) - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068718 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | BPP (Workshops & Gap Resolution) - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068719 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Data collection templates (DCT) - Explain and collect - LOG - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068720 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Data collection templates (DCT) - Explain and collect - LOG - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068721 | Yes | No | No | SDF | SDF Interim State Project | 01-Preparation | Environment setup |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | No |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068722 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | SDF Interim - Conduct requirements/Workshops |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068723 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | SDF Interim - Conduct requirements/Workshops |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068724 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | Contruct RTM |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | No |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068725 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | Contruct RTM |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | No |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068726 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | Create BPML |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | No |  |  | DELIV-BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068727 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | Create BPML |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | No |  |  | DELIV-BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068728 | Yes | No | No | SDF | SDF Interim State Project | 01-Preparation | Workshop Schedule |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068729 | Yes | No | No | SDF | SDF Interim State Project | 01-Preparation | Workshop Schedule |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068730 | Yes | No | No | SDF | SDF Interim State Project | 01-Preparation | Environment setup |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | No |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068731 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | FSD-ID-INT- Baseline |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | TBD-Tobedefine.Tbd | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068732 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | DEV FUT-ID-INT- Baseline |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-20 | 2017-01-20 | No |  |  | ACT-FUN.Execute FUT | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068733 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | FSD-ID-INT- Baseline |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | TBD-Tobedefine.Tbd | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068734 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | ILOG012-FSD-INT-STO interface |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -90 | -30.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068735 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | ILOG013-FSD-INT-STO goods issue interface (SAP to BPCS) |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-24 | 2017-01-24 | No |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -89 | -50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068736 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | ILOG015-FSD-INT-Inventory adjustment interface |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-25 | 2017-01-25 | No |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -88 | -50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068737 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | ILOG012-DEV FUT-INT-STO interface |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-07 | 2017-07-07 | No |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-08-18 | 0 | NA Others | 99000-99100-99130 NA others | -15.88 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068738 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | ILOG013-DEV FUT-INT-STO goods issue interface (SAP to BPCS) |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-22 | 2017-05-26 | No |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-08-18 | 0 | NA Others | 99000-99100-99130 NA others | -40 | -40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068739 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | ILOG015-DEV FUT-INT-Inventory adjustment interface |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-23 | 2017-06-23 | No |  |  | ACT-FUN.Execute FUT | Complete | 2017-07-17 | 2017-08-18 | 0 | NA Others | 99000-99100-99130 NA others | -30 | -35.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068740 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | ILOG013-STO goods issue interface (SAP to BPCS) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT-FUN.Execute FUT | Complete | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | -9 | -28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068741 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | ILOG013-STO goods issue interface (SAP to BPCS) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -95 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068742 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | DEV FUT-ID-INT- Baseline |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-20 | 2017-01-20 | No |  |  | ACT-FUN.Execute FUT | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068743 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | ILOG014-FSD-INT-PGI from BPCS to SAP |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | No |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -40 | -55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068744 | Yes | No | No | SDF | SDF Localisation | 04-Test | Process Workarounds (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-FUN-601.Process Workarounds | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068745 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-10 | 2017-08-10 | No |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | 33 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068746 | Yes | No | No | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068747 | Yes | No | No | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-18 | 2017-07-18 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068748 | Yes | No | No | SDF | SDF Localisation | 04-Test | Training Environment Population and Testing (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Training Environment Population and Testing | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068749 | Yes | No | No | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068750 | Yes | No | No | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068751 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Process Workarounds (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | No |  |  | DELIV-FUN-601.Process Workarounds | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068752 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-01 | 2017-09-01 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068753 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068754 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTP (Global) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | ACT-FUN.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068755 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTP (Global) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | ACT-FUN.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068756 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-23 | 2017-06-23 | No |  |  | ACT-FUN.Mock Support | Future Task | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -5 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068757 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | No |  |  | ACT-FUN.Mock Support | Future Task | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -5 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068758 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Support (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-16 | 2017-06-16 | No |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -5 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068759 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Support (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | No |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -5 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068760 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Validate (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | No |  |  | ACT-FUN.Mock Support | Future Task | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068761 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Validate (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | No |  |  | ACT-FUN.Mock Support | Future Task | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068762 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Run Tests - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068763 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Run Tests - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068764 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Manage Defects - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068765 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Manage Defects - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068766 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Break/Fix - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068767 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Break/Fix - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068768 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Prepare (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Mock Support | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068769 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Prepare (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Mock Support | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068770 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Support (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Mock Support | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068771 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Support (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Mock Support | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068772 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Validate (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Mock Support | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068773 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Validate (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Mock Support | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068774 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Run Tests - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068775 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Run Tests - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068776 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Manage Defects - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068777 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Manage Defects - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068778 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Break/Fix - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068779 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Break/Fix - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068780 | Yes | No | No | SDF | SDF Localisation | 04-Test | Regression - Run Tests (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068781 | Yes | No | No | SDF | SDF Localisation | 04-Test | Regression - Run Tests (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068782 | Yes | No | No | SDF | SDF Localisation | 04-Test | Regression - Manage defects (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068783 | Yes | No | No | SDF | SDF Localisation | 04-Test | Regression - Manage defects (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068784 | Yes | No | No | SDF | SDF Localisation | 04-Test | Documentation - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068785 | Yes | No | No | SDF | SDF Localisation | 04-Test | Documentation - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068786 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Run Tests - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068787 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Run Tests - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068788 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Manage defects - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068789 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Manage defects - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068790 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Break/Fix - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068791 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Break/Fix - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068792 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Document work around - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068793 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Document work around - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068794 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-22 | 2017-08-22 | No |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -19 | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068795 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-22 | 2017-08-22 | No |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -19 | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068796 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-11 | 2017-09-11 | No |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068797 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-11 | 2017-09-11 | No |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068798 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-11 | 2017-09-11 | No |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068799 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-11 | 2017-09-11 | No |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068800 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTP (C&G) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068801 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTP (C&G) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068802 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT Preparation : Component & Scripts (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.UAT Preparation | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068803 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT Preparation : Component & Scripts (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.UAT Preparation | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068804 | Yes | No | No | SDF | SDF Localisation | 04-Test | DR - Prepare (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | No |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068805 | Yes | No | No | SDF | SDF Localisation | 04-Test | DR - Prepare (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | No |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068806 | Yes | No | No | SDF | SDF Localisation | 04-Test | DR - Support (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068807 | Yes | No | No | SDF | SDF Localisation | 04-Test | DR - Support (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068808 | Yes | No | No | SDF | SDF Localisation | 04-Test | DR - Validate (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068809 | Yes | No | No | SDF | SDF Localisation | 04-Test | DR - Validate (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068810 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068811 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068812 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Kickoff - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068813 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Kickoff - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068814 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | RTM - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-14 | 2017-04-14 | No |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -29.88 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068815 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | RTM - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-14 | 2017-04-14 | No |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -29.88 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068816 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Gap log - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-14 | 2017-04-14 | No |  |  | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -22.88 | 70.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068817 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Gap log - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-14 | 2017-04-14 | No |  |  | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -22.88 | 70.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068818 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-01 | 2017-03-01 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -33 | -35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068819 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-01 | 2017-03-01 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -33 | -35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068820 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | Contruct RTM |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | No |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068821 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | Create BPML |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | No |  |  | DELIV-BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068822 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | Conduct requirements Workshops |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068823 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | Conduct requirements Workshops |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068824 | Yes | No | No | SDF | SDF Interim State Project | 01-Preparation | Workshop Schedule |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068825 | Yes | No | No | SDF | SDF Interim State Project | 01-Preparation | Environment setup |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | No |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068826 | Yes | No | No | SDF | SDF Interim State Project | 01-Preparation | Workshop Schedule |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068827 | Yes | No | No | SDF | SDF Interim State Project | 01-Preparation | Environment setup |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | No |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068828 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | BPM-001-Business Process Master List (BPML) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | DELIV-BPM-001.Business Process Master List (BPML) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -35 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068829 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-07 | 2017-06-07 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068830 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-07 | 2017-06-07 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068831 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | BPP (Workshops & Gap Resolution) - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068832 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | BPP (Workshops & Gap Resolution) - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068833 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Data collection templates (DCT) - Explain and collect - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068834 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Data collection templates (DCT) - Explain and collect - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068835 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068836 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068837 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Unit testing Development Documentation (FUT) - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068838 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Unit testing Development Documentation (FUT) - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068839 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Configuration - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068840 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068841 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068842 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Unit testing Configuration Documentation - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068843 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Unit testing Configuration Documentation - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068844 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Gather reporting requierements (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-14 | No |  |  | ACT-FUN.Gather reporting requierement | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068845 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Gather reporting requierements (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-07 | No |  |  | ACT-FUN.Gather reporting requierement | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068846 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Support Cutover plan (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-14 | No |  |  | ACT-FUN.Support Cutover plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068847 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Support Cutover plan (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-14 | No |  |  | ACT-FUN.Support Cutover plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068848 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Workshop Preparation Decks |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068849 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Workshop Preparation Decks |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-FUN-150.Fit/Gap Analysis & Log | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068850 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Requirements/Process Design Workshops |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068851 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Requirements/Process Design Workshop Decks |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068852 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Demo |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Solution Confirmation Prensentations and Demonstrations | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068853 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Gap Definition |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | WP-FUN.Gap Definition | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | 25 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068854 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Fit/Gap Workshop Note |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068855 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | PDDs |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068856 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Process Documentation in BWL |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Process Documentation in BWL | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068857 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-220.Solution Design Document (SDD) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068858 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Support Operational Procedures (SOPs) (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-314.Support Operational Procedures (SOPs) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068859 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Support Operational Procedures Inventory (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-214.Support Operational Procedures Inventory | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068860 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Execute Assembly Tests (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT-FUN.Execute Assembly Tests | Future Task | 2017-07-03 | 2017-07-14 | 1 | AT | 1000 D1-1300 B-1312 AT | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068861 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Execute FUT (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-19 | 2017-06-19 | No |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 20 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068862 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Assembly Test Scenarios/Scripts (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-TST-307.Assembly Test Scenarios/Scripts | Future Task | 2017-07-03 | 2017-07-14 | 1 | AT | 1000 D1-1300 B-1312 AT | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068863 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Demo (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT-FUN.Solution Confirmation Prensentations and Demonstrations | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068864 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Process Workarounds (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-601.Process Workarounds | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068865 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-19 | 2017-06-19 | No |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | -5 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068866 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | WPB Recordings (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-403.WPB Recordings | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068867 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Data Definition Documents (DDD) (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Future Task | 2017-04-17 | 2017-05-05 | 1 | Revise DDDs - Division review | 1000 D1-1200 A-1213 Revise DDDs - Division review | 30 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068868 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Report (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068869 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Enhancement (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068870 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Interface (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-19 | 2017-06-19 | No |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 15 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068871 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Workflow (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-205.Functional Specification - Workflow | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068872 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Form (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-204.Functional Specification - Form | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068873 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | Workshop-Interim state milk procurement |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-06 | 2017-08-06 | No |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068874 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | Workshop-Batch handling |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068875 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | Workshop-Purchasing & A/P |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068876 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | Workshop-QI management and held product |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-15 | 2017-02-15 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068877 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068878 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068879 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-25 | 2017-09-25 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068880 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-25 | 2017-09-25 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068881 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Manage defects (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-01 | 2017-10-01 | No |  |  | To delete-To delete.To delete | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068882 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Manage defects (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-01 | 2017-10-01 | No |  |  | To delete-To delete.To delete | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068883 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-01 | 2017-10-01 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068884 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (PTP) - Deploy1 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-01 | 2017-10-01 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068914 | No | No | No | SDF | SDF Localisation | 04-Test | D3-Dry Run | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2018-02-19 | 2018-02-19 | No |  |  |  | Future Task | 2018-02-19 | 2018-03-02 | 3 | Dry Run | 30000 D3-30100 H-30110 Dry Run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068981 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Program Plan on a Page |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | DELIV-PGM-100.Program Plan on a Page | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068982 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Resource Plan |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | DELIV-PGM-100.Resource Plan | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068983 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Stage Gate Criteria |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | DELIV-PMO-008.Stage Gate Criteria | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068984 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Project Charter |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | DELIV-PMO-300.Project Charter | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068985 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Project Kickoff Presentation |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | DELIV-CM-005.Project Kickoff Presentation | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068986 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Updated Sharepoint Logs |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | WP-PMO.Updated Sharepoint Logs | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068987 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Budget for Deployment |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | DELIV-PMO-099.Budget for Deployment | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068988 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Localization Questionnaire |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | DELIV-PMO-050.Localization Questionnaire | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068989 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Project Logs |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | WP-PMO-020.Project Logs | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068990 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Project Organizational Structure |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | WP-PMO-005.Project Organizational Structure | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068991 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Install / configure BWL/BPM & configure Solution Manager |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | ACT-PMO.Install / configure BWL/BPM & configure Solution Manager | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068993 | Yes | No | No | SDF | SDF Localisation | 04-Test | Detailed Workplan (MSP) |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-PMO-001.Detailed Workplan (MSP) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068994 | Yes | No | No | SDF | SDF Localisation | 04-Test | Program Plan on a Page |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-PGM-100.Program Plan on a Page | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068995 | Yes | No | No | SDF | SDF Localisation | 04-Test | Resource Plan |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-PGM-100.Resource Plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068996 | Yes | No | No | SDF | SDF Localisation | 04-Test | Stage Gate Criteria |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-PMO-008.Stage Gate Criteria | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068997 | Yes | No | No | SDF | SDF Localisation | 04-Test | Project Charter |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-PMO-300.Project Charter | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068998 | Yes | No | No | SDF | SDF Localisation | 04-Test | Production Support Approach |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-PMO-290.Production Support Approach | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068999 | Yes | No | No | SDF | SDF Localisation | 04-Test | Hypercare Approach & Plan |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-PMO-280.Hypercare Approach & Plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069000 | Yes | No | No | SDF | SDF Localisation | 04-Test | Cutover Plan |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-PMO-404.Cutover Plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069001 | Yes | No | No | SDF | SDF Localisation | 04-Test | Cutover Control Room Strategy |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-PMO-407.Cutover Control Room Strategy | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069002 | Yes | No | No | SDF | SDF Localisation | 04-Test | Business Readiness Ramp-Down/Up Workshops |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-PMO.Business Readiness Ramp-Down/Up Workshops | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069003 | Yes | No | No | SDF | SDF Localisation | 04-Test | Cutover Report |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-PMO-408.Cutover Report | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069004 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Detailed Workplan (MSP) |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-PMO-001.Detailed Workplan (MSP) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069005 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Program Plan on a Page |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-PGM-100.Program Plan on a Page | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069006 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Resource Plan |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-PGM-100.Resource Plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069007 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Stage Gate Criteria |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-PMO-008.Stage Gate Criteria | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069008 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Project Charter |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-PMO-300.Project Charter | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069009 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Production Support Approach |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-PMO-290.Production Support Approach | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069010 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Detailed Workplan (MSP) |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-PMO-001.Detailed Workplan (MSP) | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069011 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Program Plan on a Page |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-PGM-100.Program Plan on a Page | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069012 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Resource Plan |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-PGM-100.Resource Plan | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069013 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Stage Gate Criteria |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-PMO-008.Stage Gate Criteria | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069014 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Project Charter |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-PMO-300.Project Charter | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069015 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Configure HPQC Tools |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-PMO.Configure HPQC Tools | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069016 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Detailed Workplan (MSP) |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | DELIV-PMO-001.Detailed Workplan (MSP) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069017 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Program Plan on a Page |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | DELIV-PGM-100.Program Plan on a Page | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069018 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Resource Plan |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | DELIV-PGM-100.Resource Plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069019 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Stage Gate Criteria |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | DELIV-PMO-008.Stage Gate Criteria | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069020 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Project Charter |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | DELIV-PMO-300.Project Charter | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069021 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Production Support Approach |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | DELIV-PMO-290.Production Support Approach | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069022 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Hypercare Approach & Plan |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | DELIV-PMO-280.Hypercare Approach & Plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069023 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover Plan |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | DELIV-PMO-404.Cutover Plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069024 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover Control Room Strategy |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | DELIV-PMO-407.Cutover Control Room Strategy | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069025 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Business Readiness Ramp-Down/Up Workshops |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-PMO.Business Readiness Ramp-Down/Up Workshops | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069026 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover Report |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | DELIV-PMO-408.Cutover Report | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069027 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | HL Cutover Calendar |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | DELIV-PMO-405.HL Cutover Calendar | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069028 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover System and Process Freeze |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | DELIV-PMO-406.Cutover System and Process Freeze | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069029 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Hypercare Schedule |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | DELIV-PMO-502.Hypercare Schedule | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069030 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover and Go-Live Readiness |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | DELIV-PMO-009.Cutover and Go-Live Readiness | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069033 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | Hypercare Report |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | No |  |  | DELIV-PMO-602.Hypercare Report | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069034 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | Hypercare Exit Sign-Off |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | No |  |  | DELIV-PMO-650.Hypercare Exit Sign-Off | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069035 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | Hypercare Issues Log |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | No |  |  | WP-PMO-620.Hypercare Issues Log | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069036 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | Hypercare Lessons Learned Document |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | No |  |  | DELIV-PMO-601.Hypercare Lessons Learned Document | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069088 | No | No | No | SDF | SDF Localisation | 04-Test | D1-T-QE2 SIT1 | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  |  | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069089 | No | No | No | SDF | SDF Localisation | 99-Global | D3-MultiPhases-End User Training | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-12-04 | 2017-12-04 | No |  |  |  | Future Task | 2017-12-04 | 2018-01-26 | 2 | End User Training | 20000 D2-29000 MultiPhases-29060 End User Training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069090 | No | No | No | SDF | SDF Localisation | 99-Global | D2-MultiPhases-Role Mapping | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  |  | Future Task | 2017-07-17 | 2017-08-11 | 2 | Role Mapping | 20000 D2-29000 MultiPhases-29009 Role Mapping | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069130 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069131 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | IOTC010-DEV FUT-INT-Sales order interface |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-18 | 2017-07-18 | No |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | 5 | 35.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069132 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069133 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069134 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-01 | 2017-10-01 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069135 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-01 | 2017-10-01 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069136 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Manage defects (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-01 | 2017-10-01 | No |  |  | To delete-To delete.To delete | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069137 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Manage defects (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-01 | 2017-10-01 | No |  |  | To delete-To delete.To delete | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069138 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-01 | 2017-10-01 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069139 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-01 | 2017-10-01 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069140 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069141 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - OTC |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069142 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | IOTC010-FSD-INT-Sales order interface |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | No |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -90 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069143 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | DDD |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Future Task | 2017-04-17 | 2017-05-05 | 1 | Revise DDDs - Division review | 1000 D1-1200 A-1213 Revise DDDs - Division review | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069144 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Demo (OTC) - Deploy2 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT-FUN.Solution Confirmation Prensentations and Demonstrations | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 99000-99100-99110 TBD | -35 | -55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069145 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Process Workarounds (OTC) - Deploy2 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-601.Process Workarounds | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | -55 | -35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069146 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | WPB Recordings (OTC) - Deploy2 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-403.WPB Recordings | Future Task | 2017-08-21 | 2017-09-01 | 2 | AT | 20000 D2-20100 B-20180 AT | -60 | -35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069147 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification (OTC) - Deploy2 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | -50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069148 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification (OTC) - Deploy2 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | -35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069149 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification (OTC) - Deploy2 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069150 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Workflow (OTC) - Deploy2 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-205.Functional Specification - Workflow | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | -35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069151 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Form (OTC) - Deploy2 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-204.Functional Specification - Form | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | -35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069152 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) (OTC) - Deploy2 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-220.Solution Design Document (SDD) | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069153 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Support Operational Procedures (SOPs) (OTC) - Deploy2 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-314.Support Operational Procedures (SOPs) | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069154 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Support Operational Procedures Inventory (OTC) - Deploy2 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-214.Support Operational Procedures Inventory | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069155 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Execute Assembly Tests (OTC) - Deploy2 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | ACT-FUN.Execute Assembly Tests | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069156 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Assembly Test Scenarios/Scripts (OTC) - Deploy2 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-TST-307.Assembly Test Scenarios/Scripts | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069157 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Business Process Master List (BPML) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-BPM-001.Business Process Master List (BPML) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069158 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Workshop Preparation Decks |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | WP-FUN-107.Workshop Preparation Decks | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069159 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Workshop Preparation Decks |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-FUN-150.Fit/Gap Analysis & Log | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069160 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Requirements/Process Design Workshops |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069161 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Requirements/Process Design Workshop Decks |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069162 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Demo |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Solution Confirmation Prensentations and Demonstrations | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069163 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Gap Definition |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | WP-FUN.Gap Definition | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069164 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Fit/Gap Workshop Note |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | WP-FUN.Fit/Gap Workshop Note | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069165 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | PDDs |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-FUN-110.PDDs | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069166 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Process Documentation in BWL |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Process Documentation in BWL | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069167 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -30 | -30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069168 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -30 | -30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069169 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - OTC (AN) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069170 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - OTC (AN) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069171 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Kickoff - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069172 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Kickoff - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069173 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | RTM - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-14 | 2017-04-14 | No |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -18 | 57.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069174 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | RTM - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-14 | 2017-04-14 | No |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -18 | 57.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069175 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Log Gaps - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-12 | 2017-04-12 | No |  |  | WP-FUN.Fit/Gap Workshop Note | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -15 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069176 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Log Gaps - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-19 | 2017-05-19 | No |  |  | WP-FUN.Fit/Gap Workshop Note | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -15 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069177 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Unit testing Development Documentation (FUT) - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | 2017-05-22 | 2017-07-07 | 2 | FUT | 1000 D1-1300 B-1311 FUT | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069178 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Unit testing Development Documentation (FUT) - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | 2017-05-22 | 2017-07-07 | 2 | FUT | 1000 D1-1300 B-1311 FUT | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069179 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Configuration - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069180 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069181 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069182 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Unit testing Configuration Documentation) - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069183 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Unit testing Configuration Documentation) - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069184 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Gather reporting requierements (OTC) - Deploy2 |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-14 | No |  |  | ACT-FUN.Gather reporting requierement | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069185 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Gather reporting requierements (OTC) - Deploy2 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-14 | No |  |  | ACT-FUN.Gather reporting requierement | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069186 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Support Cutover plan (OTC) - Deploy2 |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-14 | No |  |  | ACT-FUN.Support Cutover plan | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069187 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Support Cutover plan (OTC) - Deploy2 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-14 | No |  |  | ACT-FUN.Support Cutover plan | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069188 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - OTC-(Global) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-07 | 2017-07-14 | No |  |  | ACT-CM.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069189 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - OTC-(Global) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-07 | 2017-07-14 | No |  |  | ACT-CM.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069190 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | BPP (Workshops & Gap Resolution) - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069191 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | BPP (Workshops & Gap Resolution) - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069192 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Data collection templates (DCT) - Explain and collect - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069193 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Data collection templates (DCT) - Explain and collect - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069194 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | 2017-05-29 | 2017-06-30 | 2 | FSDs | 1000 D1-1300 B-1331 FSDs | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069195 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | To delete-To delete.To delete | Complete | 2017-05-29 | 2017-06-30 | 2 | FSDs | 1000 D1-1300 B-1331 FSDs | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069196 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Run Tests - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069197 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Run Tests - OTC |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069198 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Manage defects - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069199 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Manage defects - OTC |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069200 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Break/Fix - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069201 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Break/Fix - OTC |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069202 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Document work around - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069203 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Document work around - OTC |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069204 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -10 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069205 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -10 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069206 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support - OTC (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-18 | 2017-09-18 | No |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069207 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support - OTC (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-18 | 2017-09-18 | No |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069208 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-18 | 2017-09-18 | No |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069209 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-18 | 2017-09-18 | No |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069210 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) (Test) - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069211 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) (Test) - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069212 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-18 | 2017-08-18 | No |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 40 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069213 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-18 | 2017-08-18 | No |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 40 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069214 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Support (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-16 | 2017-06-16 | No |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -5 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069215 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Support (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-16 | 2017-06-16 | No |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -5 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069216 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Validate (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-07 | No |  |  | ACT-FUN.Mock Support | Future Task | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069217 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Validate (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-07 | No |  |  | ACT-FUN.Mock Support | Future Task | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069218 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Run Tests - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069219 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Run Tests - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069220 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Manage Defects - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069221 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Manage Defects - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069222 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Break/Fix - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069223 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Break/Fix - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069224 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Prepare (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Mock Support | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069225 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Prepare (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Mock Support | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069226 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Support (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Mock Support | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069227 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Support (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Mock Support | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069228 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Validate (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Mock Support | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069229 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Validate (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Mock Support | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069230 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Run Tests - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069231 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Run Tests - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069232 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Manage Defects - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069233 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Manage Defects - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069234 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Break/Fix - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069235 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Break/Fix - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069236 | Yes | No | No | SDF | SDF Localisation | 04-Test | Regression - Run Tests (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069237 | Yes | No | No | SDF | SDF Localisation | 04-Test | Regression - Run Tests (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069238 | Yes | No | No | SDF | SDF Localisation | 04-Test | Regression - Manage defects (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069239 | Yes | No | No | SDF | SDF Localisation | 04-Test | Regression - Manage defects (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069240 | Yes | No | No | SDF | SDF Localisation | 04-Test | Documentation - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069241 | Yes | No | No | SDF | SDF Localisation | 04-Test | Documentation - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069242 | Yes | No | No | SDF | Trade (in SDF) | 02-Analyze | Trade-RTM-Global Trade-OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | No |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069243 | Yes | No | No | SDF | Trade (in SDF) | 02-Analyze | Trade-Fit-Gap-Global |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | No |  |  | WP-FUN.Gap Definition | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069244 | Yes | No | No | SDF | Trade (in SDF) | 02-Analyze | PDD-RT Trade Promotion Planning - TPM-OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-04-21 | 2017-04-21 | No |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069245 | Yes | No | No | SDF | Trade (in SDF) | 02-Analyze | PDD-RT Trade Promotion Execution - TPM-OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-04-18 | 2017-04-18 | No |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069246 | Yes | No | No | SDF | Trade (in SDF) | 02-Analyze | PDD-RT Settlements & Claim Reconcilation - TPM-OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-04-10 | 2017-04-10 | No |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069247 | Yes | No | No | SDF | Trade (in SDF) | 02-Analyze | PDD-RT Trade Master Data - TPM-OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069248 | Yes | No | No | SDF | Trade (in SDF) | 02-Analyze | Trade-Gap Resolution-Global |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-02-28 | 2017-02-28 | No |  |  | WP-FUN.Gap Definition | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069249 | Yes | No | No | SDF | Trade (in SDF) | 02-Analyze | Trade-Global Trade scope / Solution validation-OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069250 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT Preparation : Component & Scripts (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.UAT Preparation | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069251 | Yes | No | No | SDF | SDF Localisation | 04-Test | DR - Prepare (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | No |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069252 | Yes | No | No | SDF | SDF Localisation | 04-Test | DR - Support (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069253 | Yes | No | No | SDF | SDF Localisation | 04-Test | DR - Validate (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069254 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | IOTC010-DEV FUT-INT-Sales order interface |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-18 | 2017-07-18 | No |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | 5 | 35.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069255 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | IOTC010-FSD-INT-Sales order interface |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | No |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -90 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069256 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | FSD-ID-INT- Baseline |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | TBD-Tobedefine.Tbd | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069257 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | DEV FUT-ID-INT- Baseline |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-20 | 2017-01-20 | No |  |  | TBD-Tobedefine.Tbd | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069258 | Yes | No | No | SDF | Trade (in SDF) | 03-Design/Build | Trade-Functional Specification (FSD) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | TBD-Tobedefine.Tbd | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069259 | Yes | No | No | SDF | Trade (in SDF) | 03-Design/Build | TPM Unit testing Development Documentation (FUT) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT-FUN.Execute FUT | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069260 | Yes | No | No | SDF | Trade (in SDF) | 03-Design/Build | Trade-Functional Specification (FSD) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | TBD-Tobedefine.Tbd | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069261 | Yes | No | No | SDF | Trade (in SDF) | 03-Design/Build | TPM Unit testing Development Documentation (FUT) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT-FUN.Execute FUT | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069262 | Yes | No | No | SDF | SDF Interim State Project | 01-Preparation | Workshop Schedule |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069263 | Yes | No | No | SDF | SDF Interim State Project | 01-Preparation | Environment setup |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | No |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069264 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | SDF Interim - Conduct requirements Workshops |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069265 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | SDF Interim - Conduct requirements Workshops |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069266 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | SDF Interim - Contruct RTM |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069267 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | SDF Interim - Contruct RTM |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069268 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | SDF Interim - Create BPML |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV-BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069269 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | SDF Interim - Create BPML |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV-BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069270 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC032-DEV FUT-Pricing Files |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-19 | 2017-05-19 | No |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | -30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069271 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC3513-DEV FUT-Pricing Cockpit |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-10 | 2017-05-10 | No |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | -15 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069272 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC034-DEV FUT-Pricing Page Archive (DMS) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 80h | 80h | 2017-07-26 | 2017-08-22 | No |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | 47 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069273 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | IOTC005-DEV FUT-Pricing Notification EDI |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 81h | 81h | 2017-08-07 | 2017-08-25 | No |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | 55 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069274 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC033-FSD-Pricing Cockpit |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -65 | -71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069275 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | FOTC005-DEV FUT-Level 0 Notification Form |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-12 | No |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | 17.38 | 2.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069276 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Test preparation |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-30 | 2017-07-07 | No |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 0 | NA Others | 99000-99100-99130 NA others | -15 | 6.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069277 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | IOTC003-DEV FUT-COM-Pricing Interface From SAP to MRA |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | No |  |  | ACT-FUN.Execute FUT | Complete | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | -45 | -54.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069278 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | IOTC004-DEV FUT-Master data interfaceFrom SAP to MRA |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | No |  |  | ACT-FUN.Execute FUT | Complete | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | -35 | -50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069279 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC032-DEV FUT-Pricing Files |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-19 | 2017-05-19 | No |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | -30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069280 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC3513-DEV FUT-Pricing Cockpit |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-10 | 2017-05-10 | No |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | -15 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069281 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC034-DEV FUT-Pricing Page Program |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-27 | 2017-03-27 | No |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | -40 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069282 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | FOTC005-DEV FUT-Level 0 Notification Form |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-12 | No |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | 17.38 | 2.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069283 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC034-DEV FUT-Pricing Page Archive (DMS) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 12.75h | 12.75h | 2017-07-31 | 2017-08-22 | No |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | 47 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069284 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | IOTC005-DEV FUT-Pricing Notification EDI |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 15h | 15h | 2017-08-07 | 2017-08-25 | No |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | 55 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069285 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | IOTC003-FSD-Pricing Interface From SAP to MRA |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -95 | -85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069286 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | IOTC004-FSD-Master data interface From SAP to MRA |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | No |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -90 | -90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069287 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC032-FSD-Pricing Files |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -80 | -79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069288 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC033-FSD-Pricing Cockpit |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -65 | -71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069289 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC034-FSD-Pricing Page Program |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -80 | -30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069290 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | FOTC005-FSD-Level 0 Notification Form |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | No |  |  | DELIV-FUN-204.Functional Specification - Form | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -60 | -41.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069291 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC034-FSD-Pricing Page Archive (DMS) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | No |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069292 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | IOTC005-FSD-Pricing Notification EDI |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-14 | 2017-03-14 | No |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -54 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069293 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC032-FSD-Pricing Files |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -80 | -79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069294 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | IOTC003-DEV-PL_Pricing Interface From SAP to MRA |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 160h | 0h | 160h | 2017-03-06 | 2017-03-31 | No |  |  | DELIV-DEV-202.Technical Specification - Interface | Complete | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -50 | -60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069295 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Config-COTC0001-Pricing condition types |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-05-19 | 0 | NA Others | 99000-99100-99130 NA others | -5 | 13.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069296 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | SDD-COTC0001-Pricing condition types |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 3h | 3h | 2017-06-30 | 2017-07-07 | No |  |  | WP-PMO-024.Project Logs | Future Task | 2017-05-08 | 2017-05-19 | 0 | NA Others | 99000-99100-99130 NA others | 15 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069297 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | SDD-COTC0001-Pricing condition types |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | WP-PMO-024.Project Logs | Future Task | 2017-05-08 | 2017-05-19 | 0 | NA Others | 99000-99100-99130 NA others | 15 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069298 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Test preparation |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 0 | NA Others | 99000-99100-99130 NA others | -15 | 6.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069299 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | FOTC005-FSD-Level 0 Notification Form |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | No |  |  | DELIV-FUN-204.Functional Specification - Form | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -60 | -41.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069300 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC034-FSD-Pricing Page Archive (DMS) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | No |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069301 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | IOTC005-FSD-Pricing Notification EDI |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-14 | 2017-03-14 | No |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -54 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069302 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | IOTC003-DEV-Pricing Interface From SAP to MRA |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-03 | 2017-03-03 | No |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -50 | -60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069303 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | IOTC004-DEV-Master data interface From SAP to MRA |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-24 | 2017-02-24 | No |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -55 | -60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069304 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC032-DEV-Pricing Files |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | No |  |  | DELIV-DEV-203.Technical Specification -Enhancement | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -44 | -27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069305 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | FSD-ID-INT- Baseline |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | TBD-Tobedefine.Tbd | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069306 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | DEV FUT-ID-INT- Baseline |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-20 | 2017-01-20 | No |  |  | TBD-Tobedefine.Tbd | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069307 | Yes | No | No | SDF | SDF Interim State Project | 01-Preparation | Workshop Schedule |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069308 | Yes | No | No | SDF | SDF Interim State Project | 01-Preparation | Environment setup |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | No |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069309 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 02-Analyze | Commodity Pricing RTM |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069310 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 02-Analyze | Commodity Pricing RTM |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069311 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 02-Analyze | Commodity Pricing BPML |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV-BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069312 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | FSD-ID-COM-Baseline |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | TBD-Tobedefine.Tbd | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069313 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | DEV FUT-ID-COM-Baseline |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-10 | 2017-02-10 | No |  |  | TBD-Tobedefine.Tbd | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069314 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 02-Analyze | Commodity Pricing BPML |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV-BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069315 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | FSD-ID-COM-Baseline |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | TBD-Tobedefine.Tbd | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069316 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | DEV FUT-ID-COM-Baseline |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-10 | 2017-02-10 | No |  |  | TBD-Tobedefine.Tbd | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069317 | Yes | No | No | SDF | Trade (in SDF) | 02-Analyze | Trade-DOM |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | DELIV-MDG-150.Data Object Master (DOM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069318 | Yes | No | No | SDF | SDF Localisation | 04-Test | Process Workarounds (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-FUN-601.Process Workarounds | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069319 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | 15 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069320 | Yes | No | No | SDF | SDF Localisation | 04-Test | Training Environment Population and Testing (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Training Environment Population and Testing | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069321 | Yes | No | No | SDF | SDF Localisation | 04-Test | Execute SIT2 (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069322 | Yes | No | No | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069323 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Process Workarounds (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | No |  |  | DELIV-FUN-601.Process Workarounds | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069324 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069325 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069342 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Process Workarounds (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | No |  |  | DELIV-FUN-601.Process Workarounds | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069362 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069363 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069364 | Yes | No | No | SDF | SDF Localisation | 04-Test | Process Workarounds (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-FUN-601.Process Workarounds | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069365 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-19 | 2017-07-19 | No |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | 5 | 29.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069366 | Yes | No | No | SDF | SDF Localisation | 04-Test | Training Environment Population and Testing (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Training Environment Population and Testing | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069367 | Yes | No | No | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069368 | Yes | No | No | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069369 | Yes | No | No | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069370 | Yes | No | No | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-15 | 2017-08-15 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 17.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069371 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | Conduct requirements Workshops |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069372 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | Contruct RTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | No |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069373 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | Create BPML |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | No |  |  | DELIV-BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069374 | Yes | No | No | SDF | SDF Interim State Project | 01-Preparation | Workshop Schedule |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069375 | Yes | No | No | SDF | SDF Interim State Project | 01-Preparation | Environment setup |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | No |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069376 | Yes | No | No | SDF | SDF Interim State Project | 01-Preparation | Workshop Schedule |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069377 | Yes | No | No | SDF | SDF Interim State Project | 01-Preparation | Environment setup |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | No |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069378 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | Conduct requirements Workshops |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069379 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTM(Global) |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | ACT-FUN.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069380 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTM(Global) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | ACT-FUN.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069381 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-19 | 2017-06-19 | No |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069382 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-19 | 2017-06-19 | No |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069383 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Support (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | No |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069384 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Support (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | No |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069385 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Validate (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | No |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069386 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Validate (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | No |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069387 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Run Tests - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069388 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Run Tests - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069389 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Manage Defects - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069390 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Manage Defects - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069391 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Break/Fix - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069392 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Break/Fix - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069393 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Prepare (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Mock Support | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069394 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Prepare (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Mock Support | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069395 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Support (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Mock Support | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069396 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Support (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Mock Support | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069397 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Validate (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Mock Support | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069398 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Validate (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-FUN.Mock Support | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069399 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Run Tests - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069400 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Run Tests - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069401 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Manage Defects - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069402 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Manage Defects - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069403 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Break/Fix - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069404 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Break/Fix - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | To delete-To delete.To delete | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069405 | Yes | No | No | SDF | SDF Localisation | 04-Test | Regression - Run Tests (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069406 | Yes | No | No | SDF | SDF Localisation | 04-Test | Regression - Run Tests (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069407 | Yes | No | No | SDF | SDF Localisation | 04-Test | Regression - Manage defects (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069408 | Yes | No | No | SDF | SDF Localisation | 04-Test | Regression - Manage defects (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069409 | Yes | No | No | SDF | SDF Localisation | 04-Test | Documentation - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069410 | Yes | No | No | SDF | SDF Localisation | 04-Test | Documentation - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069411 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT Preparation : Component & Scripts (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.UAT Preparation | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069412 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT Preparation : Component & Scripts (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.UAT Preparation | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069413 | Yes | No | No | SDF | SDF Localisation | 04-Test | DR - Prepare (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | No |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069414 | Yes | No | No | SDF | SDF Localisation | 04-Test | DR - Prepare (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | No |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069415 | Yes | No | No | SDF | SDF Localisation | 04-Test | DR - Support (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069416 | Yes | No | No | SDF | SDF Localisation | 04-Test | DR - Support (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069417 | Yes | No | No | SDF | SDF Localisation | 04-Test | DR - Validate (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069418 | Yes | No | No | SDF | SDF Localisation | 04-Test | DR - Validate (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069419 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Run Tests - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069420 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Run Tests - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069421 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Manage defects - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069422 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Manage defects - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069423 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Break/Fix - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069424 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Break/Fix - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069425 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Document work around - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069426 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -24.88 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069427 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -24.88 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069428 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | No |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069429 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | No |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069430 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-10 | 2017-09-10 | No |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069431 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-10 | 2017-09-10 | No |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069432 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069433 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069434 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-24 | 2017-03-24 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069435 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-24 | 2017-03-24 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069436 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Business Process Master List (BPML) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069437 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Workshop Preparation Decks |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069438 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Workshop Preparation Decks |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-FUN-150.Fit/Gap Analysis & Log | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069439 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Requirements/Process Design Workshops |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069440 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Requirements/Process Design Workshop Decks |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069441 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Demo |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Solution Confirmation Prensentations and Demonstrations | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069442 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Fit/Gap Workshop Note |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069443 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | PDDs |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069444 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Process Documentation in BWL |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Process Documentation in BWL | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069445 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Enhancement (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069446 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Interface (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069447 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Workflow (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-205.Functional Specification - Workflow | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069448 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Form (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-204.Functional Specification - Form | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069449 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-220.Solution Design Document (SDD) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069450 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Support Operational Procedures (SOPs) (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-314.Support Operational Procedures (SOPs) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069451 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Support Operational Procedures Inventory (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-214.Support Operational Procedures Inventory | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069452 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Execute Assembly Tests (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT-FUN.Execute Assembly Tests | Future Task | 2017-07-03 | 2017-07-14 | 1 | AT | 1000 D1-1300 B-1312 AT | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069453 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Execute FUT (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 10 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069454 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Assembly Test Scenarios/Scripts (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-TST-307.Assembly Test Scenarios/Scripts | Future Task | 2017-07-03 | 2017-07-14 | 1 | AT | 1000 D1-1300 B-1312 AT | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069455 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Demo (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT-FUN.Solution Confirmation Prensentations and Demonstrations | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069456 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Process Workarounds (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-601.Process Workarounds | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069457 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | -15 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069458 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | WPB Recordings (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-403.WPB Recordings | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069459 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Data Definition Documents (DDD) (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Future Task | 2017-04-17 | 2017-05-05 | 1 | Revise DDDs - Division review | 1000 D1-1200 A-1213 Revise DDDs - Division review | 30 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069460 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Report (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069461 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069462 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069463 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | BPP (Workshops & Gap Resolution) - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069464 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | BPP (Workshops & Gap Resolution) - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069465 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Data collection templates (DCT) - Explain and collect - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069466 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Data collection templates (DCT) - Explain and collect - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069468 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Configuration - PTM - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT-FUN.Configuration | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069469 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) - PTM - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-14 | No |  |  | DELIV-FUN-220.Solution Design Document (SDD) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069470 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) - PTM - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-14 | No |  |  | DELIV-FUN-220.Solution Design Document (SDD) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069471 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Unit testing Configuration Documentation - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069472 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Unit testing Configuration Documentation - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069473 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Gather reporting requierements (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-14 | No |  |  | ACT-FUN.Gather reporting requierement | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069474 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Gather reporting requierements (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-14 | No |  |  | ACT-FUN.Gather reporting requierement | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069475 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Support Cutover plan (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-07 | No |  |  | ACT-FUN.Support Cutover plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069476 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Support Cutover plan (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-14 | No |  |  | ACT-FUN.Support Cutover plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069477 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069478 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069479 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Kickoff - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069480 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Kickoff - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069481 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | RTM - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069482 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | RTM - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069483 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Log Gaps - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069484 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Log Gaps - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069485 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | BPM-001-Business Process Master List (BPML) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | DELIV-BPM-001.Business Process Master List (BPML) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -35 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069486 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | IXXX-DEV-Production receipts interface |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-12 | 2017-05-12 | No |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | 0 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069487 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | IXXX-DEV-Interim State common components |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-05 | 2017-05-05 | No |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -5 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069488 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | SDF Interim State-Workshop-Production scheduling and receipt (OCT. Go-live) |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069489 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069490 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | No |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069491 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-25 | 2017-09-25 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069492 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-25 | 2017-09-25 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069493 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Manage defects (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-01 | 2017-10-01 | No |  |  | To delete-To delete.To delete | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069494 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Manage defects (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-01 | 2017-10-01 | No |  |  | To delete-To delete.To delete | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069495 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-01 | 2017-10-01 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069496 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (PTM) - Deploy1 |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-01 | 2017-10-01 | No |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069497 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | SDF Interim State-Workshop-Production scheduling and receipt (OCT. Go-live) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069498 | Yes | No | No | SDF | SDF Interim State Project | 02-Analyze | SDF Interim State-Workshop-Supply chain planning |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069499 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - MDM | MDG | To Define |  |  | _GD_MDG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT-MDG.MDG - Workshop | Complete | 2017-05-01 | 2017-05-05 | 1 | Data Construction | 1000 D1-1200 A-1214 Data Construction | -60 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069500 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - MDM |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT-MDG.MDG - Workshop | Complete | 2017-05-01 | 2017-05-05 | 1 | Data Construction | 1000 D1-1200 A-1214 Data Construction | -60 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069501 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Source system assessment and map - MDM |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | DELIV-MDG-060.Source system assessment and map | Complete | 2017-05-01 | 2017-05-05 | 1 | Data Construction | 1000 D1-1200 A-1214 Data Construction | -60 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069502 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Data profiling - DC |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | DELIV-MDG-050.Data Profiling | Complete | 2017-05-01 | 2017-05-05 | 1 | Data Construction | 1000 D1-1200 A-1214 Data Construction | -55 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069503 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - Deploy1 - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | No |  |  | ACT-MDG.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069504 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT Preparation : Component & Scripts - MDG - Deploy1 - DM |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | No |  |  | ACT-FUN.UAT Preparation | Future Task | NA | NA | 1 | NA SDF | 99000-99100-99120 NA SDF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069505 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Deploy1 - Saputo - DM |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-21 | 2017-08-21 | No |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | -5 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069506 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Manage defects - MDG - Deploy1 - DM |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | NA | NA | 1 | NA SDF | 99000-99100-99120 NA SDF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069507 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Break/Fix - MDG - Deploy1 - DM |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | NA | NA | 1 | NA SDF | 99000-99100-99120 NA SDF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069508 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Document work around - Deploy1 - DM |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-FUN.Execute UAT | Future Task | NA | NA | 1 | NA SDF | 99000-99100-99120 NA SDF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069509 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - Deploy1 - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | No |  |  | ACT-MDG.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069510 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | Hypercare-Provide end User Support - Deploy1 - Saputo - DM |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-01 | 2017-10-01 | No |  |  | To delete-To delete.To delete | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069511 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | HC - Manage defects - Deploy1 - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-01 | 2017-10-01 | No |  |  | To delete-To delete.To delete | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069512 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | Placeholer |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2015-08-31 | 2015-08-31 | No |  |  | To delete-To delete.To delete | Late | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069513 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | Placeholer |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2015-08-31 | 2015-08-31 | No |  |  | To delete-To delete.To delete | Late | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069514 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | CIA catch up session |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2015-08-31 | 2015-08-31 | No |  |  | To delete-To delete.To delete | Late | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069515 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | CIA finalization session |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2015-08-31 | 2015-08-31 | No |  |  | To delete-To delete.To delete | Late | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069520 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Configuration (HR) - Deploy1 |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | -5 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069523 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Assembly Test Scenarios/Scripts (HR) - Deploy1 |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-TST-307.Assembly Test Scenarios/Scripts | Future Task | 2017-07-03 | 2017-07-14 | 1 | AT | 1000 D1-1300 B-1312 AT | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069524 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Demo (HR) - Deploy1 |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT-FUN.Solution Confirmation Prensentations and Demonstrations | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069525 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Process Workarounds (HR) - Deploy1 |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-601.Process Workarounds | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069526 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (HR) - Deploy1 |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069527 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | WPB Recordings (HR) - Deploy1 |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-403.WPB Recordings | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069528 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Data Definition Documents (DDD) (HR) - Deploy1 |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Future Task | 2017-04-17 | 2017-05-05 | 1 | Revise DDDs - Division review | 1000 D1-1200 A-1213 Revise DDDs - Division review | 30 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069529 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Report (HR) - Deploy1 |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069530 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Enhancement (HR) - Deploy1 |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069531 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Interface (HR) - Deploy1 |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-30 | 2017-05-30 | No |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 1 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069532 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Workflow (HR) - Deploy1 |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-205.Functional Specification - Workflow | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069533 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Form (HR) - Deploy1 |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-204.Functional Specification - Form | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069534 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) (HR) - Deploy1 |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-220.Solution Design Document (SDD) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069535 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Support Operational Procedures (SOPs) (HR) - Deploy1 |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-314.Support Operational Procedures (SOPs) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069536 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Support Operational Procedures Inventory (HR) - Deploy1 |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-214.Support Operational Procedures Inventory | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069537 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Execute Assembly Tests (HR) - Deploy1 |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT-FUN.Execute Assembly Tests | Future Task | 2017-07-03 | 2017-07-14 | 1 | AT | 1000 D1-1300 B-1312 AT | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069538 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Execute FUT (HR) - Deploy1 |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-20 | 2017-06-20 | No |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 21.13 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069539 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Fit/Gap Workshop Note | EDI | EDI | Saputo |  | _GD_EDI-Consultant | Saputo | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069540 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | PDDs | EDI | EDI | Saputo |  | _GD_EDI-Consultant | Saputo | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069541 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Process Documentation in BWL | EDI | EDI | Saputo |  | _GD_EDI-Consultant | Saputo | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Process Documentation in BWL | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069542 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Requirements Traceability Matrix (RTM) | EDI | EDI | Saputo |  | _GD_EDI-Consultant | Saputo | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069543 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Workshop Preparation Decks | EDI | EDI | Saputo |  | _GD_EDI-Consultant | Saputo | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069544 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Workshop Preparation Decks | EDI | EDI | Saputo |  | _GD_EDI-Consultant | Saputo | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069545 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Requirements/Process Design Workshops | EDI | EDI | Saputo |  | _GD_EDI-Consultant | Saputo | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069546 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Requirements/Process Design Workshop Decks | EDI | EDI | Saputo |  | _GD_EDI-Consultant | Saputo | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069547 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Demo | EDI | EDI | Saputo |  | _GD_EDI-Consultant | Saputo | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Solution Confirmation Prensentations and Demonstrations | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069548 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Requirements Traceability Matrix (RTM) |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069549 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Workshop Preparation Decks |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069550 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Workshop Preparation Decks |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069551 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Requirements/Process Design Workshops |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069552 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Requirements/Process Design Workshop Decks |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069553 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Demo |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Solution Confirmation Prensentations and Demonstrations | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069554 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Fit/Gap Workshop Note |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069555 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | PDDs |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069556 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Process Documentation in BWL |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-FUN.Process Documentation in BWL | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069557 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Data Cleansing and Migration Approach - DM |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-MDM-110.Data Cleansing and Migration Approach | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069558 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Data Object Master (DOM) |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-MDG-150.Data Object Master (DOM) | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069559 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Data Construction |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-MDG.Data Construction | Complete | 2017-05-01 | 2017-05-05 | 1 | Data Construction | 1000 D1-1200 A-1214 Data Construction | -10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069560 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Mock Load |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-MDG.Mock Load | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069561 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Mock Validation |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-MDG.Mock Validation | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069562 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Mock Preparation |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-MDG.Mock Preparation | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069563 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Data Validation Sheets |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-MDG.Mock Validation | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069564 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Legacy Data Archiving strategy |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-TAI-140.Legacy Data Archiving strategy | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069565 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | MDG - Workshops |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-MDG.MDG - Workshop | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069566 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Data Maintenance process designs (PDDs) |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-MDG-110.Data Maintenance process designs (PDDs) | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069567 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Communication plan execution and monitoring |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT-CM.Communication plan execution and monitoring | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069568 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Stakeholder Analysis |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-CM-123b.Stakeholder Analysis | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069569 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Change Agents Network |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-CM-124.Change Agents Network | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069570 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Key User Network plan |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-CM-113.Key User Network plan | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069571 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Business Readiness plan |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-CM-112.Business Readiness plan | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069572 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-19 | 2017-05-19 | No |  |  | ACT-FUN.Management | Future Task | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069573 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Kickoff - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-19 | 2017-05-19 | No |  |  | ACT-MDG.MDG - Workshop | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069574 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | RTM - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-19 | 2017-05-19 | No |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069575 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Log Gaps - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | To delete-To delete.To delete | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069576 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Data conversion plan - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-19 | 2017-05-19 | No |  |  | DELIV-MDG-201.Data Conversion Plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069577 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Data Construction - Deploy1 - DC |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT-MDG.Data Construction | Future Task | 2017-05-08 | 2017-06-09 | 1 | Data Construction | 1000 D1-1300 B-1320 Data Construction | 5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069578 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  | ACT-MDG.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069579 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | BPP (Workshops & Gap Resolution) - Deploy1 - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-05 | 2017-05-05 | No |  |  | DELIV-MDG-110.Data Maintenance process designs (PDDs) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069580 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Data collection templates (DCT) - Explain and collect - Deploy1 - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | No |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069581 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Legacy data archiving strategy - Deploy1 - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | No |  |  | DELIV-TAI-140.Legacy Data Archiving strategy | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069582 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Support FUN - Deploy1 - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069583 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Support SEC - Deploy1 - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069584 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) - Deploy1 - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-16 | 2017-06-16 | No |  |  | DELIV-MDG-206.Functional Specification -Conversion | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | -20 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069585 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | WRICEFs - Deploy1 - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069586 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Concept Deck - Deploy1 - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069587 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | WPB Recording - Deploy1 - MDG | MDG | To Define |  |  | _GD_MDG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069588 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | WPB Recording - Deploy1 - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069589 | Yes | No | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - Deploy1 - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | ACT-MDG.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069590 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare - Deploy1 - D&B - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-07 | No |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 4 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069591 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy1 - D&B - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-14 | No |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069592 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Validate - Deploy1 - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | No |  |  | ACT-MDG.Mock Validation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069593 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Run Tests - MDG - Deploy1 - DM |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT-MDG.Execute SIT | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -9.88 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069594 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Manage defects - MDG - Deploy1 - DM |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT-MDG.Execute SIT | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -9.88 | 5.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069595 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 1 - Break/Fix - MDG - Deploy1 - DM |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT-MDG.Execute SIT | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -9.88 | 5.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069596 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Prepare - Deploy1 - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT-MDG.Mock Preparation | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069597 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Execute - Deploy1 - Test - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | No |  |  | ACT-MDG.Mock Load | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069598 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock2 - Validate - Deploy1 - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  | ACT-MDG.Mock Validation | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069599 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Run Tests - MDGM - Deploy1 - DM |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-MDG.Execute SIT | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 1.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069600 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Manage defects - MDG - Deploy1 - DM |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-MDG.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069601 | Yes | No | No | SDF | SDF Localisation | 04-Test | SIT 2 - Break/Fix - MDG - Deploy1 - DM |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-MDG.Execute SIT | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069602 | Yes | No | No | SDF | SDF Localisation | 04-Test | Regression - Run Tests - Deploy1 - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | No |  |  | ACT-MDG.Execute Regression Test | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069603 | Yes | No | No | SDF | SDF Localisation | 04-Test | Regression - Manage defects - Deploy1 - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | No |  |  | ACT-MDG.Execute Regression Test | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069604 | Yes | No | No | SDF | SDF Localisation | 04-Test | Documentation - Deploy1 - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | To delete-To delete.To delete | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069605 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Business Process Master List (BPML) |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069606 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Testing Approach |  | Missing Stream |  |  | _GD_TEST-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-TST-201.Testing Approach | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069646 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 99-Global | WI/Training Materials |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | No |  |  | DELIV-CM-401.Training Materials | Complete | 2017-05-29 | 2017-07-28 | 0 | NA Others | 99000-99100-99130 NA others | -200 | -144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069647 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 99-Global | Role Analysis/Mapping |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | No |  |  | DELIV-CM-218.Role Mapping | Complete | 2017-05-29 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -200 | -120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069648 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Test Defect Log (Test) - Deploy1 |  | Missing Stream |  |  | _GD_TEST-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | WP-Testing.Test Defect Log | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069649 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 02-Analyze | Data Object Master (DOM) |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV-MDG-150.Data Object Master (DOM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069650 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Test Closure Summary (Test) - Deploy1 |  | Missing Stream |  |  | _GD_TEST-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | DELIV-TST-201.Test Closure Summary | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069651 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Test Schedule (Test) - Deploy1 |  | Missing Stream |  |  | _GD_TEST-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | DELIV-TST-200.Test Schedule | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069652 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Manage UAT (Test) - Deploy1 |  | Missing Stream |  |  | _GD_TEST-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | No |  |  | ACT-Test.Management | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069653 | Yes | No | No | SDF | SDF Localisation | 99-Global | Manage Training Logisitics |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | No |  |  | ACT-CM.Manage Training Logisitics | Future Task | 2017-06-26 | 2017-07-28 | 1 | Training Schedule | 1000 D1-1800 MultiPhases-1820 Training Schedule | 70 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069654 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | Change Agents Network Execution and Monitoring |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | No |  |  | ACT-CM.Change Agents Network Execution and Monitoring | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069655 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | Monitor Key users Network |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | No |  |  | ACT-CM.Monitor Key users Network | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069656 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | Value Realization Monitoring |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | No |  |  | ACT-CM.Value Realization Monitoring | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069657 | Yes | No | No | SDF | SDF Localisation | 06-Hypercare | Test Defect Log (Test) - Deploy1 |  | Missing Stream |  |  | _GD_TEST-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | No |  |  | WP-Testing.Test Defect Log | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069658 | Yes | No | No | SDF | SDF Localisation | 99-Global | Training Materials-Elearning course (Design/Build) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | DELIV-CM-401.Training Materials | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | -15 | -59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069659 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Test Closure Summary (Test) - Deploy1 |  | Missing Stream |  |  | _GD_TEST-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-TST-201.Test Closure Summary | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069660 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Test Schedule (Test) - Deploy1 |  | Missing Stream |  |  | _GD_TEST-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-TST-200.Test Schedule | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069661 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Regression Test Scenarios/Scripts (Test) - Deploy1 |  | Missing Stream |  |  | _GD_TEST-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | No |  |  | DELIV-TST-308.Regression Test Scenarios/Scripts | Complete | 2017-06-26 | 2017-07-14 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | -10 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069662 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Test Defect Log (Test) - Deploy1 |  | Missing Stream |  |  | _GD_TEST-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | WP-Testing.Test Defect Log | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069663 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Data Validation Sheets - Deploy1 - D&B - DC |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | WP-MDG.Data Validation Sheets | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069664 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Data Conversion Plan - Deploy1 - DC |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-02 | 2017-06-02 | No |  |  | DELIV-MDG-201.Data Conversion Plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069665 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Legacy Data Archiving strategy - Deploy1 |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-TAI-140.Legacy Data Archiving strategy | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069666 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock Conversion Closure Memo - Deploy1 |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-Mock Conversion Closure Memo | Future Task | 2017-05-08 | 2017-06-09 | 1 | Build and adjust conversion programs | 1000 D1-1300 B-1322 Build and adjust conversion programs | 15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069667 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock Conversion - Deploy1 |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-CON-100.Mock Conversion | Future Task | 2017-05-08 | 2017-06-09 | 1 | Build and adjust conversion programs | 1000 D1-1300 B-1322 Build and adjust conversion programs | 15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069668 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Data Verification Sign-Off Sheets - Deploy1 |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | WP-MDG.Data Verification Sign-Off Sheets | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069669 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Data Loading Procedures - Deploy1 |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-MDG-203.Data Loading Procedures | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069670 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Data Load Sequence - Deploy1 |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-MDG-202.Data Load Sequence | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069671 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Functional Mapping Document - Deploy1 |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-MDG-207.Functional Mapping Document | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069672 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Technical Specification - Conversion - Deploy1 |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-MDG-306.Technical Specification - Conversion | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069673 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | MDG Solution Design Documents (SDDs) - Deploy1 |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-FUN-220.Solution Design Document (SDD) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069674 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Data Maintenance Functional Specification - Deploy1 |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-MDG-205.Data Maintenance Functional Specification | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069675 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Communication plan execution and monitoring (Design/Build) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT-CM.Communication plan execution and monitoring | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069676 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Stakeholder Analysis (Design/Build) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-CM-123b.Stakeholder Analysis | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069677 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Change Impacts Analysis (Design/Build) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV-CM-014.Change Impacts Analysis | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069678 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Change Agents Network Execution and Monitoring (Design/Build) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT-CM.Change Agents Network Execution and Monitoring | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069679 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Transition Plan Execution & Monitoring(Design/Build) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT-CM.Transition Plan Execution & Monitoring | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069680 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Business Readiness Execution & Monitoring (Design/Build) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT-CM.Business Readiness Execution & Monitoring | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069681 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Establish Key users Network(Design/Build) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT-CM.Establish Key users Network | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069682 | Yes | No | No | SDF | SDF Localisation | 99-Global | Role Mapping (Design/Build) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-06-06 | 2017-06-06 | No |  |  | DELIV-CM-218.Role Mapping | Complete | 2017-05-29 | 2017-06-23 | 1 | Role Mapping | 1000 D1-1800 MultiPhases-1810 Role Mapping | 5 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069683 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Transition Plan (Design/Build) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-CM-117.Transition Plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069684 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Knowledge Transfer Plan (Design/Build) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-CM-116.Knowledge Transfer Plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069685 | Yes | No | No | SDF | SDF Localisation | 04-Test | Test Closure Summary (Test) - Deploy1 |  | Missing Stream |  |  | _GD_TEST-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-TST-201.Test Closure Summary | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069686 | Yes | No | No | SDF | SDF Localisation | 04-Test | Test Schedule (Test) - Deploy1 |  | Missing Stream |  |  | _GD_TEST-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-TST-200.Test Schedule | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069687 | Yes | No | No | SDF | SDF Localisation | 04-Test | Regression Test Scenarios/Scripts (Test) - Deploy1 |  | Missing Stream |  |  | _GD_TEST-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-TST-308.Regression Test Scenarios/Scripts | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | -15 | 9.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069688 | Yes | No | No | SDF | SDF Localisation | 04-Test | UAT Test Scenarios/Test Cases/Test Scripts (Test) - Deploy1 |  | Missing Stream |  |  | _GD_TEST-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-FUN-408.UAT Test Scenarios/Test Cases/Test Scripts | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069689 | Yes | No | No | SDF | SDF Localisation | 04-Test | Manage SIT (Test) - Deploy1 |  | Missing Stream |  |  | _GD_TEST-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  | ACT-Test.Management | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069690 | Yes | No | No | SDF | SDF Localisation | 04-Test | Test Defect Log (Test) - Deploy1 |  | Missing Stream |  |  | _GD_TEST-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | WP-Testing.Test Defect Log | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069691 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Data Construction - Deploy1 |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | No |  |  | ACT-MDG.Data Construction | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069692 | Yes | No | No | SDF | SDF Localisation | 03-Design/Build | Mock Conversion Closure Memo - Deploy1 |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-Mock Conversion Closure Memo | Future Task | 2017-06-05 | 2017-06-16 | 1 | QE2 Prevalidation | 1000 D1-1300 B-1325 QE2 Prevalidation | -5 | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069693 | Yes | No | No | SDF | SDF Localisation | 04-Test | Mock Conversion - Deploy1 |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-CON-100.Mock Conversion | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069694 | Yes | No | No | SDF | SDF Localisation | 04-Test | Data Verification Sign-Off Sheets - Deploy1 |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | WP-MDG.Data Verification Sign-Off Sheets | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069695 | Yes | No | No | SDF | SDF Localisation | 04-Test | Data Loading Procedures - Deploy1 |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | DELIV-MDG-203.Data Loading Procedures | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069696 | Yes | No | No | SDF | SDF Localisation | 04-Test | Communication plan execution and monitoring (Test) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-CM.Communication plan execution and monitoring | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069697 | Yes | No | No | SDF | SDF Localisation | 04-Test | Change Agents Network Execution and Monitoring (Test) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-CM.Change Agents Network Execution and Monitoring | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069698 | Yes | No | No | SDF | SDF Localisation | 04-Test | Transition Plan Execution & Monitoring (Test) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-CM.Transition Plan Execution & Monitoring | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069699 | Yes | No | No | SDF | SDF Localisation | 04-Test | Business Readiness Execution & Monitoring (Test) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-CM.Business Readiness Execution & Monitoring | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069700 | Yes | No | No | SDF | SDF Localisation | 04-Test | Establish Key users Network (Test) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-CM.Establish Key users Network | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069701 | Yes | No | No | SDF | SDF Localisation | 99-Global | Role Mapping (Test) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-CM-218.Role Mapping | Future Task | 2017-05-29 | 2017-06-23 | 1 | Role Mapping | 1000 D1-1800 MultiPhases-1810 Role Mapping | 35 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069702 | Yes | No | No | SDF | SDF Localisation | 04-Test | Failure Mode Effect Analysis (FMEA) (Test) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-CM-301.Failure Mode Effect Analysis (FMEA) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069703 | Yes | No | No | SDF | SDF Localisation | 04-Test | Knowledge Transfer Execution & Monitoring (Test) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT-CM.Knowledge Transfer Execution & Monitoring | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069704 | Yes | No | No | SDF | SDF Localisation | 99-Global | Execute Train the Trainer (Test) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | No |  |  | ACT-CM.Execute Train the Trainer | Future Task | 2017-07-17 | 2017-07-28 | 1 | Train the trainer | 1000 D1-1800 MultiPhases-1840 Train the trainer | 10 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069705 | Yes | No | No | SDF | SDF Localisation | 99-Global | Training Curriculum (Test) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-CM-320.Training Curriculum | Future Task | 2017-06-26 | 2017-07-28 | 1 | Training Schedule | 1000 D1-1800 MultiPhases-1820 Training Schedule | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069706 | Yes | No | No | SDF | SDF Localisation | 99-Global | Training Materials (Test) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-CM-401.Training Materials | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 35 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069707 | Yes | No | No | SDF | SDF Localisation | 99-Global | Work Instructions (Test) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-CM-451.Work Instructions | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 35 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069708 | Yes | No | No | SDF | SDF Localisation | 99-Global | Deliver Training to UAT Testers (Test) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | No |  |  | ACT-CM.Deliver Training to UAT Testers | Complete | 2017-08-14 | 2017-09-01 | 1 | UAT Training | 1000 D1-1800 MultiPhases-1870 UAT Training | -35 | -30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069709 | Yes | No | No | SDF | SDF Localisation | 99-Global | Personalised training Plan (Test) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | WP-CM.Personalised training Plan | Future Task | 2017-06-26 | 2017-07-28 | 1 | Training Schedule | 1000 D1-1800 MultiPhases-1820 Training Schedule | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069710 | Yes | No | No | SDF | SDF Localisation | 99-Global | Exercises Book and Data (Test) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | WP-CM.Exercises Book and Data | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 35 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069711 | Yes | No | No | SDF | SDF Localisation | 99-Global | Training Schedule and Logistics (Test) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | DELIV-CM-402.Training Schedule and Logistics | Future Task | 2017-06-26 | 2017-07-28 | 1 | Training Schedule | 1000 D1-1800 MultiPhases-1820 Training Schedule | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069712 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Mock Conversion Closure Memo - Deploy1 |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | No |  |  | DELIV-Mock Conversion Closure Memo | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069713 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Mock Conversion - Deploy1 |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | No |  |  | DELIV-CON-100.Mock Conversion | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069714 | Yes | No | No | SDF | SDF Localisation | 99-Global | Deliver Training to End Users - Deploy1 |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-CM.Deliver Training to End Users | Future Task | 2017-07-31 | 2017-09-22 | 1 | End User Training | 1000 D1-1800 MultiPhases-1850 End User Training | 25 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069715 | Yes | No | No | SDF | SDF Localisation | 99-Global | Manage Training Logisitics - Deploy1 |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-CM.Manage Training Logisitics | Future Task | 2017-06-26 | 2017-07-28 | 1 | Training Schedule | 1000 D1-1800 MultiPhases-1820 Training Schedule | 50 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069716 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Communication plan execution and monitoring - Deploy1 |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-CM.Communication plan execution and monitoring | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069717 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Change Agents Network Execution and Monitoring |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-CM.Change Agents Network Execution and Monitoring | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069718 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Transition Plan Execution & Monitoring |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-CM.Transition Plan Execution & Monitoring | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069719 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Business Readiness Execution & Monitoring |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-CM.Business Readiness Execution & Monitoring | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069720 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Establish Key users Network |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-CM.Establish Key users Network | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069721 | Yes | No | No | SDF | SDF Localisation | 99-Global | Role Mapping |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | DELIV-CM-218.Role Mapping | Future Task | 2017-05-29 | 2017-06-23 | 1 | Role Mapping | 1000 D1-1800 MultiPhases-1810 Role Mapping | 70 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069722 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Knowledge Transfer Execution & Monitoring |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  | ACT-CM.Knowledge Transfer Execution & Monitoring | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069723 | Yes | No | No | SDF | SDF Localisation | 04-Test | Data Construction - Deploy1 |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT-MDG.Data Construction | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069740 | Yes | No | No | SDF | SDF Localisation | 99-Global | Project Management |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | ACT-PMO.Management | Late | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069741 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Communication plan execution and monitoring |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | ACT-CM.Communication plan execution and monitoring | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069742 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Change Management Plan |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | DELIV-CM-250.Change Management Plan | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069745 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Business Process Master List (BPML) | EDI | EDI | Saputo |  | _GD_EDI-Consultant | Saputo | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069746 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Requirements/Process Design Workshop Decks |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -35 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069747 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC3513-DEV-Pricing Cockpit |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-24 | 2017-03-24 | No |  |  | DELIV-DEV-203.Technical Specification -Enhancement | Complete | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -36 | -47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069748 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC034-DEV-Pricing Page Program |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV-DEV-203.Technical Specification -Enhancement | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -85 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069749 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | FOTC005-DEV-Level 0 Notification Form |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-04 | 2017-05-04 | No |  |  | DELIV-DEV-204.Technical Specification - Form | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -6.63 | -7.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069750 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | FOTC006-DEV-Level 2 Notification Form |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | No |  |  | DELIV-DEV-204.Technical Specification - Form | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | 20 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069751 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC034-DEV-Pricing Page Archive (DMS) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | No |  |  | DELIV-DEV-203.Technical Specification -Enhancement | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | 20 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069752 | Yes | No | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | IOTC005-DEV-Pricing Notification EDI |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-23 | 2017-06-23 | No |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069753 | Yes | No | No | SDF | Trade (in SDF) | 02-Analyze | Trade-Kickoff-Global Trade-OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Global |  | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | No |  |  | To delete-To delete.To delete | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069754 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Requirements/Process Design Workshop Decks |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -35 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069755 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | BPM-001-Business Process Master List (BPML) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | DELIV-BPM-001.Business Process Master List (BPML) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -35 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069756 | Yes | No | No | SDF | SDF Localisation | 04-Test | DR - Validate (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069757 | Yes | No | No | SDF | SDF Localisation | 04-Test | DR - Support (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069758 | Yes | No | No | SDF | SDF Localisation | 04-Test | DR - Prepare (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | No |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069759 | Yes | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | UAT Preparation : Component & Scripts (OTC) - Deploy1 |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  | ACT-FUN.UAT Preparation | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069764 | No | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | D2-CG-PRD Transports | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2018-01-08 | 2018-01-08 | No |  |  |  | Future Task | 2018-01-08 | 2018-01-12 | 2 | PRD Transports | 20000 D2-22400 CG-22410 PRD Transports | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069765 | No | No | No | SDF | SDF Localisation | 99-Global | D3-MultiPhases-End User Training | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2018-02-26 | 2018-02-26 | No |  |  |  | Future Task | 2018-02-26 | 2018-03-23 | 3 | End User Training | 30000 D3-39000 MultiPhases-39010 End User Training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069766 | No | No | No | SDF | SDF Localisation | 04-Test | D2-T-Perf. Test (PT): Plan | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  |  | Future Task | 2017-09-04 | 2017-09-29 | 2 | Perf. Test (PT): Plan | 20000 D2-21000 T-21005 Perf. Test (PT): Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069767 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D2-B-QE2 Mock Prep | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | No |  |  |  | Future Task | 2017-07-31 | 2017-08-11 | 2 | QE2 Mock Prep | 20000 D2-20100 B-20110 QE2 Mock Prep | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069768 | No | No | No | SDF | SDF Localisation | 06-Hypercare | D1-H-D1 Hypercare | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | No |  |  |  | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069769 | No | No | No | SDF | SDF Localisation | 99-Global | D1-MultiPhases-Role Mapping | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  |  | Future Task | 2017-05-29 | 2017-06-23 | 1 | Role Mapping | 1000 D1-1800 MultiPhases-1810 Role Mapping | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069770 | No | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | D1-CG: UAT and Regression-QE3 DQ Test | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | No |  |  |  | Future Task | 2017-08-28 | 2017-09-01 | 1 | QE3 DQ Test | 1000 D1-1500 CG: UAT and Regression-1510 QE3 DQ Test | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069771 | No | No | No | SDF | SDF Localisation | 06-Hypercare | D2-H-D2 Hypercare | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2018-02-05 | 2018-02-05 | No |  |  |  | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069772 | No | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | D2-CG: UAT and Regression-DQ Test in QE3 | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-12-04 | 2017-12-04 | No |  |  |  | Future Task | 2017-12-04 | 2017-12-15 | 2 | DQ Test in QE3 | 20000 D2-22000 CG: UAT and Regression-22020 DQ Test in QE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069773 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Detailed Workplan (MSP) |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | DELIV-PMO-001.Detailed Workplan (MSP) | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069774 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D1-B-FS for 6 RICEFW for IS / x For 1st Golive | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  |  | Future Task | 2017-05-08 | 2017-05-19 | 1 | FS for 6 RICEFW for IS / x For 1st Golive | 1000 D1-1300 B-1310 FS for 6 RICEFW for IS / x For 1st Golive | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069775 | No | No | No | SDF | SDF Localisation | 01-Preparation | D1-PP-MOCK 1A Prep | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | No |  |  |  | Complete | 2017-04-03 | 2017-04-14 | 1 | MOCK 1A Prep | 1000 D1-1100 PP-1112 MOCK 1A Prep | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069776 | No | No | No | SDF | SDF Localisation | 02-Analyze | D1-A-Work-shops | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  |  | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069777 | No | No | No | SDF | SDF Localisation | 02-Analyze | D1-A-GAPs | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  |  | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069778 | No | No | No | SDF | SDF Localisation | 02-Analyze | D1-A-FS for 6 RICEFW for IS / x For 1st Golive | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  |  | Future Task | 2017-04-24 | 2017-05-05 | 1 | FS for 6 RICEFW for IS / x For 1st Golive | 1000 D1-1200 A-1212 FS for 6 RICEFW for IS / x For 1st Golive | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069779 | No | No | No | SDF | SDF Localisation | 02-Analyze | D1-A-Revise DDDs - Division review | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  |  | Future Task | 2017-04-17 | 2017-05-05 | 1 | Revise DDDs - Division review | 1000 D1-1200 A-1213 Revise DDDs - Division review | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069780 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | DDD |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Complete | 2017-04-17 | 2017-05-05 | 1 | Revise DDDs - Division review | 1000 D1-1200 A-1213 Revise DDDs - Division review | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069781 | Yes | No | No | SDF | SDF Localisation | 02-Analyze | Business Process Master List (BPML) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | DELIV-BPM-001.Business Process Master List (BPML) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069782 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Requirements/Process Design Workshop Decks |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -35 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069783 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Requirements/Process Design Workshop Decks |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -35 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069784 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | BPM-001-Business Process Master List (BPML) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | DELIV-BPM-001.Business Process Master List (BPML) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -35 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069785 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Requirements/Process Design Workshop Decks |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -35 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069786 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | BPM-001-Business Process Master List (BPML) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | DELIV-BPM-001.Business Process Master List (BPML) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -35 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069787 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Application Architecture Diagram |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | DELIV-DEV-001.Application Architecture Diagram | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069788 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | RICEFW Inventory |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | DELIV-DEV-102.RICEFW Inventory | Complete | 2017-04-24 | 2017-05-05 | 1 | FS for 6 RICEFW for IS / x For 1st Golive | 1000 D1-1200 A-1212 FS for 6 RICEFW for IS / x For 1st Golive | -40 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069789 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | High Level Legacy and EDI impacts and resource plan |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | DELIV-DEV-002.High Level Legacy and EDI impacts and resource plan | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069790 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | Interim state WRICEFs - Developments |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | TBD-Tobedefine.Tbd | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069791 | Yes | No | No | SDF | SDF Interim State Project | 03-Design/Build | Interim state WRICEFs - Developments |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | TBD-Tobedefine.Tbd | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069792 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Technology Implementation Plan |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | DELIV-TAI-001.Technology Implementation Plan | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069793 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | SolMan setup and config for Documentation, Charm and Monitoring |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | ACT-TAI.SolMan setup & config for Doc | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069794 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Technical Architecture Specification |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | DELIV-TAI-002.Technical Architecture Specification | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069795 | No | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | D2-CG-D2 PRD Data Load | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2018-01-15 | 2018-01-15 | No |  |  |  | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069796 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D1-B-FUT | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  |  | Future Task | 2017-05-29 | 2017-06-30 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069797 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D1-B-AT | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  |  | Future Task | 2017-07-03 | 2017-07-14 | 1 | AT | 1000 D1-1300 B-1312 AT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069798 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D1-B-DEV | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  |  | Future Task | 2017-05-08 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069799 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D1-B-Base Config | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  |  | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069800 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D1-B- ..FUT | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-05-22 | 2017-05-22 | No |  |  |  | Future Task | 2017-05-22 | 2017-05-26 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069801 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D1-B-Cycle 1 Config | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  |  | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069802 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D1-B- ...FUT | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | No |  |  |  | Future Task | 2017-06-12 | 2017-06-16 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069803 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D1-B-Cycle 2 Config | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-06-19 | 2017-06-19 | No |  |  |  | Future Task | 2017-06-19 | 2017-06-30 | 1 | Cycle 2 Config | 1000 D1-1300 B-1318 Cycle 2 Config | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069804 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D1-B- ...FUT | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  |  | Future Task | 2017-07-03 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069805 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D1-B-Data Construction | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  |  | Future Task | 2017-05-08 | 2017-06-09 | 1 | Data Construction | 1000 D1-1300 B-1320 Data Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069806 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D1-B-Build and adjust conversion programs | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  |  | Future Task | 2017-05-08 | 2017-06-09 | 1 | Build and adjust conversion programs | 1000 D1-1300 B-1322 Build and adjust conversion programs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069807 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D1-B-SIT 1 & 2 Prep | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | No |  |  |  | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069808 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D1-B-MOCK 1A Prep | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  |  | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069809 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D1-B-QE2 Prevalidation | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  |  | Future Task | 2017-06-05 | 2017-06-16 | 1 | QE2 Prevalidation | 1000 D1-1300 B-1325 QE2 Prevalidation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069810 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D1-B-QE2 MOCK 1A for D1 Scope | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-06-19 | 2017-06-19 | No |  |  |  | Future Task | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069811 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D1-B-QE2 DQ Test | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | No |  |  |  | Future Task | 2017-07-10 | 2017-07-14 | 1 | QE2 DQ Test | 1000 D1-1300 B-1327 QE2 DQ Test | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069812 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D1-B-QE3 TAI System Build | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  |  | Future Task | 2017-07-03 | 2017-07-14 | 1 | QE3 TAI System Build | 1000 D1-1300 B-1328 QE3 TAI System Build | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069813 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D1-B- Data Construction | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  |  | Future Task | 2017-05-08 | 2017-07-14 | 1 | Data Construction | 1000 D1-1300 B-1329 Data Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069814 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D1-B-GAPs | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  |  | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1300 B-1330 GAPs | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069815 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D1-B-Security Design | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  |  | Future Task | 2017-05-15 | 2017-06-02 | 1 | Security Design | 1000 D1-1300 B-1334 Security Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069816 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D1-B-Security Build | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  |  | Future Task | 2017-06-05 | 2017-06-23 | 1 | Security Build | 1000 D1-1300 B-1335 Security Build | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069817 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D1-B-Security FUT | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | No |  |  |  | Future Task | 2017-06-26 | 2017-07-14 | 1 | Security FUT | 1000 D1-1300 B-1336 Security FUT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069818 | No | No | No | SDF | SDF Localisation | 04-Test | D1-T-QE2 Regression | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | No |  |  |  | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069819 | No | No | No | SDF | SDF Localisation | 04-Test | D1-T-QE2 SIT2 | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | No |  |  |  | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069820 | No | No | No | SDF | SDF Localisation | 04-Test | D1-T-QE3 Dry Run for D1 Scope | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | No |  |  |  | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069821 | No | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | D1-CG: UAT and Regression-QE3 UAT for D1 | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | No |  |  |  | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069822 | No | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | D1-CG: UAT and Regression-PRD Trans Prep | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | No |  |  |  | Future Task | 2017-08-28 | 2017-09-01 | 1 | PRD Trans Prep | 1000 D1-1500 CG: UAT and Regression-1512 PRD Trans Prep | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069823 | No | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | D1-CG: UAT and Regression-PRD Transports | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  |  | Future Task | 2017-09-04 | 2017-09-08 | 1 | PRD Transports | 1000 D1-1500 CG: UAT and Regression-1513 PRD Transports | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069824 | No | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | D1-CG: UAT and Regression-D1 PRD Data Load | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-09-11 | 2017-09-11 | No |  |  |  | Future Task | 2017-09-11 | 2017-09-29 | 1 |  | 1000 D1-1500 CG: UAT and Regression-1514 D1 PRD Data Load | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069825 | No | No | No | SDF | SDF Localisation | 99-Global | D1-MultiPhases-Training Schedule | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | No |  |  |  | Future Task | 2017-06-26 | 2017-07-28 | 1 | Training Schedule | 1000 D1-1800 MultiPhases-1820 Training Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069826 | No | No | No | SDF | SDF Localisation | 99-Global | D1-MultiPhases-New Work Instructions | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  |  | Future Task | 2017-07-03 | 2017-08-11 | 1 | New Work Instructions | 1000 D1-1800 MultiPhases-1830 New Work Instructions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069827 | No | No | No | SDF | SDF Localisation | 99-Global | D1-MultiPhases-Train the trainer | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  |  | Future Task | 2017-07-17 | 2017-07-28 | 1 | Train the trainer | 1000 D1-1800 MultiPhases-1840 Train the trainer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069828 | No | No | No | SDF | SDF Localisation | 99-Global | D1-MultiPhases-End User Training | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | No |  |  |  | Future Task | 2017-07-31 | 2017-09-22 | 1 | End User Training | 1000 D1-1800 MultiPhases-1850 End User Training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069829 | No | No | No | SDF | SDF Localisation | 99-Global | D1-MultiPhases-Training Material Localization | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  |  | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069830 | No | No | No | SDF | SDF Localisation | 99-Global | D1-MultiPhases-UAT Training | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  |  | Future Task | 2017-08-14 | 2017-09-01 | 1 | UAT Training | 1000 D1-1800 MultiPhases-1870 UAT Training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069831 | No | No | No | SDF | SDF Localisation | 03-Design/Build | Mock 1B Prevalidation | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | No |  |  |  | Future Task | 2017-07-31 | 2017-08-11 | 2 | QE2 Mock 1B Prevalidation | 20000 D2-20100 B-20120 QE2 Mock 1B Prevalidation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069832 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D2-MOCK 1B (in QE2) | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  |  | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069833 | No | No | No | SDF | SDF Localisation | 03-Design/Build | SIT 1 & 2 Prep | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-08-21 | 2017-08-21 | No |  |  |  | Future Task | 2017-08-21 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069834 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D2 FSDs | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  |  | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069835 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D2-B-DEV | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | No |  |  |  | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069836 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D2-B-FUT | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  |  | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069837 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D2-B-Cycle 1 Config | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | No |  |  |  | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069838 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D2-B-Cycle 2 Config | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | No |  |  |  | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069839 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D2-B- FUT | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  |  | Future Task | 2017-08-14 | 2017-08-18 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069840 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D2-B-AT | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-08-21 | 2017-08-21 | No |  |  |  | Future Task | 2017-08-21 | 2017-09-01 | 2 | AT | 20000 D2-20100 B-20180 AT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069841 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D2-B-Security Build | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | No |  |  |  | Future Task | 2017-07-24 | 2017-08-11 | 2 | Security Build | 20000 D2-20100 B-20230 Security Build | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069842 | No | No | No | SDF | SDF Localisation | 03-Design/Build | D2-B-Security FUT | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | No |  |  |  | Future Task | 2017-08-14 | 2017-09-01 | 2 | Security FUT | 20000 D2-20100 B-20240 Security FUT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069843 | No | No | No | SDF | SDF Localisation | 04-Test | D2-T-PT: Design | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | No |  |  |  | Future Task | 2017-10-02 | 2017-10-20 | 2 | PT: Design | 20000 D2-21000 T-21010 PT: Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069844 | No | No | No | SDF | SDF Localisation | 04-Test | D2-T-PT: Build & Test | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-10-23 | 2017-10-23 | No |  |  |  | Future Task | 2017-10-23 | 2017-11-10 | 2 | PT: Build & Test | 20000 D2-21000 T-21020 PT: Build & Test | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069845 | No | No | No | SDF | SDF Localisation | 04-Test | D2-T-PT: Metrics | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-11-13 | 2017-11-13 | No |  |  |  | Future Task | 2017-11-13 | 2017-11-24 | 2 | PT: Metrics | 20000 D2-21000 T-21030 PT: Metrics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069846 | No | No | No | SDF | SDF Localisation | 04-Test | D2-T-SIT 1 (in QE2) | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-09-18 | 2017-09-18 | No |  |  |  | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069847 | No | No | No | SDF | SDF Localisation | 04-Test | D2-T-SIT 2 (in QE2) | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-10-09 | 2017-10-09 | No |  |  |  | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069848 | No | No | No | SDF | SDF Localisation | 04-Test | D2-T-QE1 Refresh | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-09-11 | 2017-09-11 | No |  |  |  | Future Task | 2017-09-11 | 2017-09-22 | 2 | QE1 Refresh | 20000 D2-21000 T-21060 QE1 Refresh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069849 | No | No | No | SDF | SDF Localisation | 04-Test | D2-T-QE1 Trans Prep | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-09-11 | 2017-09-11 | No |  |  |  | Future Task | 2017-09-11 | 2017-09-15 | 2 | QE1 Trans Prep | 20000 D2-21000 T-21070 QE1 Trans Prep | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069850 | No | No | No | SDF | SDF Localisation | 04-Test | D2-T-QE1 Transports | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-09-18 | 2017-09-18 | No |  |  |  | Future Task | 2017-09-18 | 2017-09-22 | 2 | QE1 Transports | 20000 D2-21000 T-21080 QE1 Transports | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069851 | No | No | No | SDF | SDF Localisation | 04-Test | D2-T-Mock 2 Prevalidation (in QE1 ) | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-09-25 | 2017-09-25 | No |  |  |  | Future Task | 2017-09-25 | 2017-10-06 | 2 | Mock 2 Prevalidation (in QE1 ) | 20000 D2-21000 T-21090 Mock 2 Prevalidation (in QE1 ) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069852 | No | No | No | SDF | SDF Localisation | 04-Test | D2-T-QE1 MOCK 2 (Require QE3 Refresh) | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-10-09 | 2017-10-09 | No |  |  |  | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069853 | No | No | No | SDF | SDF Localisation | 04-Test | D2-T-DQ Test in QE1 | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-10-30 | 2017-10-30 | No |  |  |  | Future Task | 2017-10-30 | 2017-11-10 | 2 | DQ Test in QE1 | 20000 D2-21000 T-21110 DQ Test in QE1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069854 | No | No | No | SDF | SDF Localisation | 04-Test | D2-T-QE3 Trans Prep | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-10-16 | 2017-10-16 | No |  |  |  | Future Task | 2017-10-16 | 2017-10-20 | 2 | QE3 Trans Prep | 20000 D2-21000 T-21120 QE3 Trans Prep | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069855 | No | No | No | SDF | SDF Localisation | 04-Test | D2-T-QE3 Transports | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-10-23 | 2017-10-23 | No |  |  |  | Future Task | 2017-10-23 | 2017-10-27 | 2 | QE3 Transports | 20000 D2-21000 T-21130 QE3 Transports | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069856 | No | No | No | SDF | SDF Localisation | 04-Test | D2-T-QE3 Dry Run Prevalidation | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-10-30 | 2017-10-30 | No |  |  |  | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069857 | No | No | No | SDF | SDF Localisation | 04-Test | D2-T-D2 / D3 Dry Run in QE3 | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-11-13 | 2017-11-13 | No |  |  |  | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069858 | No | No | No | SDF | SDF Localisation | 99-Global | D2-MultiPhases-Training Schedule | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-08-21 | 2017-08-21 | No |  |  |  | Future Task | 2017-08-21 | 2017-09-22 | 2 | Training Schedule | 20000 D2-29000 MultiPhases-29010 Training Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069859 | No | No | No | SDF | SDF Localisation | 99-Global | D2-MultiPhases-New Work Instructions | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-09-25 | 2017-09-25 | No |  |  |  | Future Task | 2017-09-25 | 2017-11-03 | 2 | New Work Instructions | 20000 D2-29000 MultiPhases-29020 New Work Instructions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069860 | No | No | No | SDF | SDF Localisation | 99-Global | D2-MultiPhases-UAT Training | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-11-13 | 2017-11-13 | No |  |  |  | Future Task | 2017-11-13 | 2017-12-01 | 2 | UAT Training | 20000 D2-29000 MultiPhases-29030 UAT Training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069861 | No | No | No | SDF | SDF Localisation | 99-Global | D2-MultiPhases-Training Material Localization | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-09-18 | 2017-09-18 | No |  |  |  | Future Task | 2017-09-18 | 2017-11-03 | 2 | Training Material Localization | 20000 D2-29000 MultiPhases-29040 Training Material Localization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069862 | No | No | No | SDF | SDF Localisation | 99-Global | D2-MultiPhases-Train the trainer | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-11-20 | 2017-11-20 | No |  |  |  | Future Task | 2017-11-20 | 2017-12-01 | 2 | Train the trainer | 20000 D2-29000 MultiPhases-29050 Train the trainer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069863 | No | No | No | SDF | SDF Localisation | 06-Hypercare | D3-H-D3 Hypercare | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2018-04-02 | 2018-04-02 | No |  |  |  | Future Task | 2018-04-02 | 2018-04-27 | 3 | D3 Hypercare | 30000 D3-30100 H-30200 D3 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069864 | No | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | D2-CG: UAT and Regression-D2/D3 UAT in QE3 | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-12-04 | 2017-12-04 | No |  |  |  | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069865 | No | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | D2-CG: UAT and Regression-PRD Trans Prep | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-12-18 | 2017-12-18 | No |  |  |  | Future Task | 2017-12-18 | 2017-12-22 | 2 | PRD Trans Prep | 20000 D2-22000 CG: UAT and Regression-22040 PRD Trans Prep | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069866 | No | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | D2-Project Shut down | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-12-25 | 2017-12-25 | No |  |  |  | Future Task | 2017-12-25 | 2018-01-05 | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069872 | No | No | No | SDF | SDF Localisation | 01-Preparation | D1-PP-Revise DDDs - Division review | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | No |  |  |  | Future Task | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069873 | No | No | No | SDF | SDF Localisation | 04-Test | D2-T-FUT | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  |  | Future Task | 2017-09-04 | 2017-09-29 | 2 | FUT | 20000 D2-21000 T-21160 D2 FUT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069874 | No | No | No | SDF | SDF Localisation | 04-Test | D2-T-DEV | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | No |  |  |  | Future Task | 2017-09-04 | 2017-09-15 | 2 | DEV | 20000 D2-21000 T-21170 D2 DEV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069875 | No | No | No | SDF | SDF Localisation | 02-Analyze | D1-A-Data Construction | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  |  | Future Task | 2017-05-01 | 2017-05-05 | 1 | Data Construction | 1000 D1-1200 A-1214 Data Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069876 | No | No | No | SDF | SDF Localisation | 02-Analyze | D1-A-Update conversion FSD & FMD | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  |  | Future Task | 2017-05-01 | 2017-05-05 | 1 | Update conversion FSD & FMD | 1000 D1-1200 A-1215 Update conversion FSD & FMD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069877 | No | No | No | SDF | SDF Localisation | 02-Analyze | D1-A-MOCK 1A Prep | PMO | PMO | Saputo |  | _POP_Generic | Saputo | Yes |  |  |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  |  | Future Task | 2017-04-17 | 2017-05-05 | 1 | MOCK 1A Prep | 1000 D1-1200 A-1216 MOCK 1A Prep | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069878 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | SAP GRC Process Control RTM |  | Missing Stream |  |  | _GD_SEC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | DELIV-SEC-002B.SAP GRC Process Control RTM | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069879 | Yes | No | No | SDF | SDF Localisation | 01-Preparation | Security and Controls Requirements |  | Missing Stream |  |  | _GD_SEC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | DELIV-SEC-002.Security and Controls Requirements | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069880 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Enhancement (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Raizada; Pravar | IBM | Yes | CapEx | Localization | IT - External | 0h | 132h | 132h | 2017-09-05 | 2017-09-29 | Yes |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069881 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Mackie; Emily | IBM | Yes | CapEx | Localization | IT - External | 0h | 44h | 44h | 2017-09-11 | 2017-09-15 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069882 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Mackie; Emily | IBM | Yes | CapEx | Localization | IT - External | 0h | 72h | 72h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069883 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Mackie; Emily | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069884 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Mackie; Emily | IBM | Yes | CapEx | Localization | IT - External | 0h | 72h | 72h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069885 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Mackie; Emily | IBM | Yes | CapEx | Localization | IT - External | 0h | 72h | 72h | 2017-12-04 | 2017-12-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069886 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Mackie; Emily | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-04 | 2017-12-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069887 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Demo (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2017-06-19 | 2017-07-20 | Yes |  |  | ACT-FUN.Solution Confirmation Prensentations and Demonstrations | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069888 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT-FUN.Management | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069889 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - LOG | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069890 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Gap log - LOG | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-04-18 | 2017-05-25 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069891 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - LOG | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 162h | 0h | 162h | 2017-04-18 | 2017-06-02 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 20 | 38 | 32 | 34 | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069892 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | RTM - LOG | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-04-17 | 2017-05-05 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069893 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069894 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069895 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Support (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069896 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 7h | 0h | 7h | 2017-03-17 | 2017-03-22 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069897 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2017-03-13 | 2017-04-13 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 16 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069898 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-04-06 | 2017-04-06 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -23 | -19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069899 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069900 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 19h | 0h | 19h | 2017-04-06 | 2017-04-28 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069901 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Data Definition Documents (DDD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2017-05-01 | 2017-05-18 | Yes |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Future Task | 2017-04-17 | 2017-05-05 | 1 | Revise DDDs - Division review | 1000 D1-1200 A-1213 Revise DDDs - Division review | 10 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069902 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 41h | 0h | 41h | 2017-05-22 | 2017-06-09 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 26 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069903 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 122h | 31h | 153h | 2017-06-05 | 2017-07-13 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 36.5 | 36.5 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069904 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2017-06-26 | 2017-06-29 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-19 | 2017-06-30 | 1 | Cycle 2 Config | 1000 D1-1300 B-1318 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069905 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | Yes |  |  | DELIV-FUN-220.Solution Design Document (SDD) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069906 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-28 | 2017-06-28 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 20 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069907 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 10h | 10h | 2017-06-30 | 2017-07-14 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 20 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069908 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 10h | 10h | 2017-06-30 | 2017-07-14 | Yes |  |  | DELIV-FUN-220.Solution Design Document (SDD) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069909 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-06-30 | 2017-07-14 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-19 | 2017-06-30 | 1 | Cycle 2 Config | 1000 D1-1300 B-1318 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069910 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069911 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - LOG | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069912 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Data Definition Documents (DDD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | Yes |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Future Task | 2017-04-17 | 2017-05-05 | 1 | Revise DDDs - Division review | 1000 D1-1200 A-1213 Revise DDDs - Division review | 10 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069913 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069914 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | SDF Interim State-Workshop-Transportation | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-04-07 | 2017-04-10 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069915 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069916 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069917 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-29 | 2017-03-29 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -23 | -19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069918 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-03-22 | 2017-03-22 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069919 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069920 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069921 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069922 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Support (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069923 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (DB) (Planning, reporting, CR, cross stream integration) - LOG(Global) | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 344h | 0h | 344h | 2017-06-12 | 2017-09-08 | Yes |  |  | ACT-MDG.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 44 | 36 | 0 | 44 | 0 | 0
1069924 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration). - LOG | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 156h | 0h | 156h | 2017-04-11 | 2017-05-26 | Yes |  |  | ACT-FUN.Management | Future Task | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 44 | 0 | 44 | 20 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069925 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - LOG | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069926 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Roloff; Patrick | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  | DMS | ACT-FUN.Functional Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069927 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Roloff; Patrick | SAP | Yes | CapEx | Localization | IT - External | 32.25h | 16h | 48.25h | 2017-08-14 | 2017-09-01 | Yes |  | DMS | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 13.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.25 | 0 | 0 | 0 | 0 | 0
1069928 | No | No | Yes | SDF | SDF Localisation | 99-Global | Project Support | SEC | SEC | SI | Offshore | Aragon; Marvin | Accenture | Yes | CapEx | Localization | IT - External | 135h | 135h | 270h | 2017-08-14 | 2017-09-27 | Yes |  |  |  | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 0 | 0 | 0
1069929 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover - Prepare- SEC - Deploy 1 | SEC | SEC | SI | Offshore | Ballada; EJ | Accenture | Yes | CapEx | Localization | IT - External | 0h | 18h | 18h | 2017-08-28 | 2017-09-15 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -15 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069930 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT- Break/Fix- SEC - Deploy 1 | SEC | SEC | SI | Offshore | Ballada; EJ | Accenture | Yes | CapEx | Localization | IT - External | 0h | 21h | 21h | 2017-08-30 | 2017-09-19 | Yes |  |  |  | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069931 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover - Support- SEC - Deploy 1 | SEC | SEC | SI | Offshore | Ballada; EJ | Accenture | Yes | CapEx | Localization | IT - External | 0h | 26h | 26h | 2017-09-18 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069932 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SAP Security & GRC Processes (SEC) - Deploy1 | SEC | SEC | SI | Offshore | Ballada; EJ | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-04 | 2017-08-04 | Yes |  |  | DELIV-SEC-215.SAP Security & GRC Processes | Complete | 2017-06-05 | 2017-06-23 | 1 | Security Build | 1000 D1-1300 B-1335 Security Build | 20 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069933 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | GRC (SEC) - Deploy1 | SEC | SEC | SI | Offshore | Ballada; EJ | Accenture | Yes | CapEx | Localization | IT - External | 76.5h | 23.5h | 100h | 2017-07-31 | 2017-09-06 | Yes |  |  | DELIV-SEC-215.SAP Security & GRC Processes | Future Task | 2017-06-05 | 2017-06-23 | 1 | Security Build | 1000 D1-1300 B-1335 Security Build | 25 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 13.5 | 18 | 18 | 9 | 0 | 0 | 0
1069934 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) - Deploy1 - DC | MDG | DC | SI | Onshore | Lakhal; Ahmed | Accenture | Yes | CapEx | Localization | IT - External | 72h | 0h | 72h | 2017-05-15 | 2017-05-26 | Yes |  |  | DELIV-MDG-206.Functional Specification -Conversion | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | -20 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069935 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Prepare Mock1 - Deploy1 - DC | MDG | DC | SI | Onshore | Lakhal; Ahmed | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-26 | 2017-05-26 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069936 | No | Yes | No | SDF | SDF Localisation | 02-Analyze | Kickoff - DC | MDG | DC | SI | Onshore | Lakhal; Ahmed | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | Yes |  |  | ACT-MDG.MDG - Workshop | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069937 | No | Yes | No | SDF | SDF Localisation | 02-Analyze | Data conversion plan - MDG - DC | MDG | DC | SI | Onshore | Lakhal; Ahmed | Accenture | Yes | CapEx | Localization | IT - External | 158h | 0h | 158h | 2017-04-03 | 2017-04-28 | Yes |  |  | DELIV-MDG-201.Data Conversion Plan | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 38 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069938 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Data collection templates (DCT) - Explain and collect - Deploy1 - DC | MDG | DC | SI | Onshore | Lakhal; Ahmed | Accenture | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2017-05-01 | 2017-05-12 | Yes |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069939 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Data Validation Sheets - Deploy1 - Test - DC | MDG | DC | SI | Onshore | Lakhal; Ahmed | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-16 | 2017-06-16 | Yes |  |  | WP-MDG.Data Validation Sheets | Complete | 2017-06-05 | 2017-06-16 | 1 | QE2 Prevalidation | 1000 D1-1300 B-1325 QE2 Prevalidation | -1 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069940 | No | Yes | No | SDF | SDF Localisation | 05-Cutover/Go-live | Mock Load - Deploy1 - DC | MDG | DC | SI | Onshore | Lakhal; Ahmed | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069941 | No | Yes | No | SDF | SDF Localisation | 05-Cutover/Go-live | Mock1 Validation - Deploy1 - CG- DC | MDG | DC | SI | Onshore | Lakhal; Ahmed | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-05 | 2017-07-05 | Yes |  |  | ACT-MDG.Mock Validation | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069942 | No | Yes | No | SDF | SDF Localisation | 05-Cutover/Go-live | Mock1 Preparation - Deploy1 - CG - DC | MDG | DC | SI | Onshore | Lakhal; Ahmed | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-04 | 2017-07-04 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069943 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Barreto; Bruno | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 48h | 48h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | -5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069944 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Barreto; Bruno | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 48h | 48h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069945 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Support (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Barreto; Bruno | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 15h | 15h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069946 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Barreto; Bruno | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 48h | 48h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069947 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Barreto; Bruno | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 48h | 48h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069948 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Regression - Run Tests (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Barreto; Bruno | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 84h | 84h | 2017-11-06 | 2017-11-24 | Yes |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-12-04 | 2017-12-22 | 2 | Q? Regression | 20000 D2-22000 CG: UAT and Regression-22010 Q? Regression | -20 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069949 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Barreto; Bruno | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-04 | 2017-12-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069950 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Barreto; Bruno | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-04 | 2017-12-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069951 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Barreto; Bruno | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 100h | 100h | 2018-01-15 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -5 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069952 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Barreto; Bruno | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 150h | 150h | 2018-02-05 | 2018-03-02 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069953 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Barreto; Bruno | Saputo | Yes | CapEx | Localization | IT - Internal | 32h | 0h | 32h | 2017-06-26 | 2017-07-14 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-21 | 2017-09-01 | 2 | AT | 20000 D2-20100 B-20180 AT | -45 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.4 | 8.8 | 8.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069954 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (OTC) - Deploy1 | OTC | FUN | Saputo | Onshore | Barreto; Bruno | Saputo | Yes | CapEx | Localization | IT - Internal | 12h | 0h | 12h | 2017-07-17 | 2017-07-21 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069955 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | TPM Unit testing Development Documentation (FUT) | OTC | FUN | Saputo | Onshore | Barreto; Bruno | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 20h | 20h | 2017-05-29 | 2017-09-29 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069956 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Functional Specification (FSD) | OTC | FUN | Saputo | Onshore | Barreto; Bruno | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069957 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Report (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Barreto; Bruno | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 20h | 20h | 2017-09-05 | 2017-09-29 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069958 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Barreto; Bruno | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 20h | 20h | 2017-09-05 | 2017-09-29 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069959 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Support Mock1 (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Barreto; Bruno | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 10h | 10h | 2017-09-05 | 2017-09-15 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-09-25 | 2017-10-06 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -30 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069960 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Barreto; Bruno | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 20h | 20h | 2017-09-05 | 2017-09-15 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 10 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069961 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Configuration - RTR - Deploy1 | RTR | FUN | SI | Offshore | Chakraborty; Sujoy | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-07-03 | 2017-07-07 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | -5 | 43.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069962 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | Data migration | RTR | FUN | SI | Offshore | Chakraborty; Sujoy | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-07-04 | 2017-07-14 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069963 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute Assembly Tests (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Chakraborty; Sujoy | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-07-04 | 2017-07-21 | Yes |  |  | ACT-FUN.Execute Assembly Tests | Future Task | 2017-07-03 | 2017-07-14 | 1 | AT | 1000 D1-1300 B-1312 AT | -25 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069964 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | IXXX-DEV FUT-G/L interface | RTR | FUN | SI | Offshore | Chakraborty; Sujoy | IBM | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2017-07-31 | 2017-08-02 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | 50 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069965 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | PDD-Reconcialition process design | RTR | FUN | SI | Offshore | Chakraborty; Sujoy | IBM | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-07-04 | 2017-08-04 | Yes |  |  | DELIV-FUN-110.PDDs | Future Task | 2017-05-01 | 2017-05-05 | 0 | NA Others | 99000-99100-99130 NA others | 25 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069966 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Chakraborty; Sujoy | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-08-02 | 2017-08-09 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 27 | 0 | 0 | 0 | 0 | 0 | 0
1069967 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Chakraborty; Sujoy | IBM | Yes | CapEx | Localization | IT - External | 35h | 0h | 35h | 2017-09-05 | 2017-09-08 | Yes |  |  | ACT-FUN.Functional Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0
1069968 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Chakraborty; Sujoy | IBM | Yes | CapEx | Localization | IT - External | 0h | 24h | 24h | 2017-08-08 | 2017-08-28 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 13.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069969 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Chakraborty; Sujoy | IBM | Yes | CapEx | Localization | IT - External | 62h | 0h | 62h | 2017-08-14 | 2017-09-01 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 9.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 17 | 0 | 0 | 0
1069970 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Chettyar; Vidyasagar | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2017-08-07 | 2017-08-25 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069971 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Chettyar; Vidyasagar | IBM | Yes | CapEx | Localization | IT - External | 0h | 35h | 35h | 2017-09-05 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069972 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Nehra; Mohit | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069973 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy1 (Design/Build) | DEV | DEV | SI | Offshore | Nehra; Mohit | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069974 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | SI | Offshore | Nehra; Mohit | IBM | Yes | CapEx | Localization | IT - External | 432h | 24h | 456h | 2017-06-20 | 2017-09-20 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 45 | 36 | 36 | 45 | 0 | 45 | 0
1069975 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Nehra; Mohit | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-09-04 | 2017-09-08 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0
1069976 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | SI | Offshore | Nehra; Mohit | IBM | Yes | CapEx | Localization | IT - External | 0h | 35h | 35h | 2017-08-28 | 2017-09-29 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069977 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | SI | Offshore | Nehra; Mohit | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2016-12-28 | 2017-10-31 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069978 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing WRICEFs (Design/Build) | DEV | DEV | SI | Offshore | Nehra; Mohit | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-01-11 | 2017-11-03 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -88 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069979 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | SI | Offshore | Nehra; Mohit | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069980 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Nehra; Mohit | IBM | Yes | CapEx | Localization | IT - External | 0h | 135h | 135h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069981 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Nehra; Mohit | IBM | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069982 | No | No | Yes | SDF | SDF Localisation | 99-Global | Cutover planners | CM | CM | SI | Onshore | Sonone; Ram | IBM | Yes | CapEx | Localization | IT - External | 414h | 642h | 1,056h | 2017-07-17 | 2017-12-15 | Yes |  |  |  | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 44 | 44 | 44 | 62 | 44 | 44 | 0
1069983 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT 1 - Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | Saputo | Onshore | Gomare; Shankar | Saputo | Yes | CapEx | Localization | IT - Internal | 35h | 0h | 35h | 2017-07-10 | 2017-07-21 | Yes |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069984 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | Saputo | Onshore | Gomare; Shankar | Saputo | Yes | CapEx | Localization | IT - Internal | 7h | 0h | 7h | 2017-05-29 | 2017-06-02 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069985 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | WRICEFs inventory - DEV | DEV | DEV | Saputo | Onshore | Gomare; Shankar | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | DELIV-DEV-102.RICEFW Inventory | Future Task | NA | NA | 1 | GAPs | 1000 D1-1200 A-1211GAPs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069986 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | WRICEFs - DEV (Design/Build) | DEV | DEV | Saputo | Onshore | Gomare; Shankar | Saputo | Yes | CapEx | Localization | IT - Internal | 184h | 0h | 184h | 2017-06-05 | 2017-07-14 | Yes |  |  | To delete-To delete.To delete | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 15.13 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 28 | 28 | 31 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069987 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | Saputo | Onshore | Gomare; Shankar | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069988 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | Saputo | Onshore | Gomare; Shankar | Saputo | Yes | CapEx | Localization | IT - Internal | 181h | 36h | 217h | 2017-06-20 | 2017-09-21 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 35 | 35 | 0 | 32 | 0 | 9 | 0
1069989 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | Saputo | Onshore | Gomare; Shankar | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069990 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | Saputo | Onshore | Gomare; Shankar | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 120h | 120h | 2017-10-10 | 2017-11-17 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069991 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Break/Fix - DEV | DEV | DEV | Saputo | Onshore | Gomare; Shankar | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0.13 | 5.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069992 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | Saputo | Onshore | Gomare; Shankar | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069993 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | Saputo | Onshore | Gomare; Shankar | Saputo | Yes | CapEx | Localization | IT - Internal | 83h | 0h | 83h | 2017-09-05 | 2017-09-18 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 41 | 0
1069994 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | Saputo | Onshore | Gomare; Shankar | Saputo | Yes | CapEx | Localization | IT - Internal | 3h | 60h | 63h | 2017-08-28 | 2017-08-30 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
1069995 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Gupta; Debapriya | IBM | Yes | CapEx | Localization | IT - External | 2h | 28h | 30h | 2017-08-23 | 2017-09-12 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
1069996 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Gupta; Debapriya | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069997 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | SI | Offshore | Gupta; Debapriya | IBM | Yes | CapEx | Localization | IT - External | 251h | 50h | 301h | 2017-02-13 | 2017-08-10 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 45 | 45 | 36 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069998 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing WRICEFs (Design/Build) | DEV | DEV | SI | Offshore | Gupta; Debapriya | IBM | Yes | CapEx | Localization | IT - External | 74.5h | 48h | 122.5h | 2017-02-13 | 2017-11-03 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -88 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 14 | 0 | 15.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069999 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Gupta; Debapriya | IBM | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070000 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Gupta; Debapriya | IBM | Yes | CapEx | Localization | IT - External | 0h | 135h | 135h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070001 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | SI | Offshore | Gupta; Debapriya | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070002 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | SI | Offshore | Gupta; Debapriya | IBM | Yes | CapEx | Localization | IT - External | 0h | 35h | 35h | 2017-08-28 | 2017-09-29 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070003 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy1 (Design/Build) | DEV | DEV | SI | Offshore | Gupta; Debapriya | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070004 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | SI | Offshore | Gupta; Debapriya | IBM | Yes | CapEx | Localization | IT - External | 110h | 50h | 160h | 2017-07-31 | 2017-09-25 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 36 | 8 | 0 | 16 | 22 | 11 | 0
1070005 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Execute FUT | OTC | FUN | SI | Offshore | Gophane; Rupali | IBM | Yes | CapEx | Global | IT - External | 53h | 0h | 53h | 2017-06-12 | 2017-07-07 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-08-18 | 0 | NA Others | 99000-99100-99130 NA others | -30 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 15 | 9 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070006 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Cycle1 Configuration | OTC | FUN | SI | Offshore | Gophane; Rupali | IBM | Yes | CapEx | Global | IT - External | 72h | 45h | 117h | 2017-06-06 | 2017-11-03 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 0 | NA Others | 99000-99100-99130 NA others | -15 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 15 | 10 | 1 | 0 | 10 | 10 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070007 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Cycle2 Configuration | OTC | FUN | SI | Offshore | Gophane; Rupali | IBM | Yes | CapEx | Global | IT - External | 67h | 3h | 70h | 2017-06-27 | 2017-08-24 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 0 | NA Others | 99000-99100-99130 NA others | -20 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 11 | 0 | 0 | 0 | 10 | 20 | 11 | 6 | 0 | 0 | 0 | 0
1070008 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-SIT Test Scenarios/Scripts | OTC | FUN | SI | Offshore | Gophane; Rupali | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-07-14 | 2017-07-14 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 0 | NA Others | 99000-99100-99130 NA others | -25 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070009 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Functional Specification (FSD) | OTC | FUN | SI | Offshore | Gophane; Rupali | IBM | Yes | CapEx | Global | IT - External | 105h | 9h | 114h | 2017-06-12 | 2017-08-30 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | 5 | 85.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 9 | 0 | 15 | 10 | 9 | 10 | 14 | 9 | 7 | 2 | 0 | 0 | 0
1070010 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Baseline configuration - OTC | OTC | FUN | SI | Offshore | Gophane; Rupali | IBM | Yes | CapEx | Global | IT - External | 56h | 0h | 56h | 2017-05-15 | 2017-06-06 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-06-26 | 2017-07-14 | 0 | NA Others | 99000-99100-99130 NA others | -30 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 10 | 20 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070011 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-Master Data | OTC | FUN | SI | Offshore | Gophane; Rupali | IBM | Yes | CapEx | Global | IT - External | 90h | 0h | 90h | 2017-05-01 | 2017-06-09 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 10 | 10 | 5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070012 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-System prototype set-up | OTC | FUN | SI | Offshore | Gophane; Rupali | IBM | Yes | CapEx | Global | IT - External | 322h | 320h | 642h | 2017-05-01 | 2017-11-03 | Yes |  |  | ACT-FUN.Solution Confirmation Prensentations and Demonstrations | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 15 | 25 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 24 | 25 | 11 | 16 | 23 | 43 | 45 | 0 | 0
1070013 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-PDDs | OTC | FUN | SI | Offshore | Kusary; Bishwadeep | IBM | Yes | CapEx | Global | IT - External | 126h | 0h | 126h | 2017-05-01 | 2017-05-19 | Yes |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070014 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Baseline configuration - OTC | OTC | FUN | SI | Offshore | Kusary; Bishwadeep | IBM | Yes | CapEx | Global | IT - External | 90h | 0h | 90h | 2017-05-22 | 2017-06-02 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-06-26 | 2017-07-14 | 0 | NA Others | 99000-99100-99130 NA others | -30 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070015 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Functional Specification (FSD) | OTC | FUN | SI | Offshore | Kusary; Bishwadeep | IBM | Yes | CapEx | Global | IT - External | 132.5h | 0h | 132.5h | 2017-06-12 | 2017-09-08 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | 5 | 85.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 15 | 0 | 15 | 25 | 10 | 15 | 10 | 0 | 0 | 0 | 0 | 20 | 0 | 0
1070016 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-SIT Test Scenarios/Scripts | OTC | FUN | SI | Offshore | Kusary; Bishwadeep | IBM | Yes | CapEx | Global | IT - External | 75h | 105h | 180h | 2017-07-10 | 2017-11-03 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 0 | NA Others | 99000-99100-99130 NA others | -25 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 5 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 0 | 0
1070017 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Cycle2 Configuration | OTC | FUN | SI | Offshore | Kusary; Bishwadeep | IBM | Yes | CapEx | Global | IT - External | 192h | 0h | 192h | 2017-06-26 | 2017-08-18 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 0 | NA Others | 99000-99100-99130 NA others | -20 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 30 | 0 | 10 | 0 | 35 | 45 | 36 | 0 | 0 | 0 | 0 | 0
1070018 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Cycle1 Configuration | OTC | FUN | SI | Offshore | Kusary; Bishwadeep | IBM | Yes | CapEx | Global | IT - External | 107.5h | 0h | 107.5h | 2017-06-05 | 2017-07-28 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 0 | NA Others | 99000-99100-99130 NA others | -15 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 22.5 | 0 | 0 | 0 | 0 | 10 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070019 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Execute FUT | OTC | FUN | SI | Offshore | Kusary; Bishwadeep | IBM | Yes | CapEx | Global | IT - External | 86h | 270h | 356h | 2017-06-19 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-08-18 | 0 | NA Others | 99000-99100-99130 NA others | -30 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 36 | 20 | 0 | 0 | 0
1070020 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Ujeniya; Ashok | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-04 | 2017-12-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070021 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Support-D2 | OTC | FUN | SI | Onshore | Ujeniya; Ashok | IBM | Yes | OpEx | Localization | IT - External | 0h | 20h | 20h | 2018-01-03 | 2018-02-02 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-09-18 | 2017-11-03 | 2 | Training Material Localization | 20000 D2-29000 MultiPhases-29040 Training Material Localization | -10 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070022 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Ujeniya; Ashok | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-04 | 2017-12-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070023 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Ujeniya; Ashok | IBM | Yes | CapEx | Localization | IT - External | 0h | 28h | 28h | 2018-01-03 | 2018-01-12 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -30 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070024 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Ujeniya; Ashok | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2018-01-15 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -5 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070025 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Ujeniya; Ashok | IBM | Yes | CapEx | Localization | IT - External | 0h | 200h | 200h | 2018-01-29 | 2018-03-23 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070026 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute Assembly Tests (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Ujeniya; Ashok | IBM | Yes | CapEx | Localization | IT - External | 32h | 10h | 42h | 2017-08-14 | 2017-08-25 | Yes |  |  | ACT-FUN.Execute Assembly Tests | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 19 | 0 | 0 | 0 | 0
1070027 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Ujeniya; Ashok | IBM | Yes | CapEx | Localization | IT - External | 68h | 24h | 92h | 2017-06-19 | 2017-08-28 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | -25 | 16.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 21 | 0 | 0 | 11 | 24 | 1 | 4 | 0 | 0 | 0 | 0
1070028 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Ujeniya; Ashok | IBM | Yes | CapEx | Localization | IT - External | 54h | 32h | 86h | 2017-06-19 | 2017-09-07 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-21 | 2017-09-01 | 2 | AT | 20000 D2-20100 B-20180 AT | -45 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 45 | 0 | 0 | 0
1070029 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT - OTC- Deploy2 | OTC | FUN | SI | Onshore | Ujeniya; Ashok | IBM | Yes | CapEx | Localization | IT - External | 99h | 0h | 99h | 2017-06-12 | 2017-07-28 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 13 | 28 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070030 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | SDD-COTC0001-Pricing condition types | OTC | FUN | SI | Onshore | Ujeniya; Ashok | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-05-29 | 2017-07-28 | Yes |  |  | WP-PMO-024.Project Logs | Future Task | 2017-05-08 | 2017-05-19 | 0 | NA Others | 99000-99100-99130 NA others | 15 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 11 | 17 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070031 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Support (OTC) - Deploy1 | OTC | FUN | SI | Onshore | Ujeniya; Ashok | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-07-31 | 2017-08-14 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -5 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 3 | 0 | 0 | 0 | 0 | 0
1070032 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (OTC) - Deploy1 | OTC | FUN | SI | Onshore | Ujeniya; Ashok | IBM | Yes | CapEx | Localization | IT - External | 29h | 7h | 36h | 2017-07-17 | 2017-08-08 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0
1070033 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Salunke; Sachin | IBM | Yes | CapEx | Localization | IT - External | 105h | 0h | 105h | 2017-06-26 | 2017-09-01 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-21 | 2017-09-01 | 2 | AT | 20000 D2-20100 B-20180 AT | -45 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 36 | 45 | 0 | 0 | 0
1070034 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (OTC) - Deploy1 | OTC | FUN | SI | Offshore | Salunke; Sachin | IBM | Yes | CapEx | Localization | IT - External | 96h | 24h | 120h | 2017-07-17 | 2017-08-23 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 20 | 16 | 0 | 0 | 0 | 0 | 0
1070035 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (OTC) - Deploy1 | OTC | FUN | SI | Offshore | Salunke; Sachin | IBM | Yes | CapEx | Localization | IT - External | 120h | 164h | 284h | 2017-07-17 | 2017-10-13 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0
1070036 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Salunke; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-18 | 2017-09-18 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070037 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Salunke; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 75h | 75h | 2017-10-16 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070038 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Salunke; Sachin | IBM | Yes | CapEx | Localization | IT - External | 36h | 170h | 206h | 2017-09-04 | 2017-11-03 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 10 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0
1070039 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Salunke; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-11 | 2017-09-11 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | -5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070040 | No | No | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Accenture) - DC | AMS | AMS | SI | Offshore | Valencia; Heherson | Accenture AMS | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070041 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 configuration (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Rajenderan; Santhosh | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-07-31 | 2017-08-11 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | 25 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 25 | 0 | 0 | 0 | 0 | 0 | 0
1070042 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Support Mock1 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Rajenderan; Santhosh | IBM | Yes | CapEx | Localization | IT - External | 0h | 43h | 43h | 2017-08-25 | 2017-09-15 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-09-25 | 2017-10-06 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -25 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070043 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Report (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Rajenderan; Santhosh | IBM | Yes | CapEx | Localization | IT - External | 0h | 15h | 15h | 2017-08-04 | 2017-08-11 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 5.13 | 75.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070044 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Rajenderan; Santhosh | IBM | Yes | CapEx | Localization | IT - External | 0h | 97h | 97h | 2017-06-30 | 2017-08-11 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-19 | 2017-06-30 | 1 | Cycle 2 Config | 1000 D1-1300 B-1318 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070045 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Rajenderan; Santhosh | IBM | Yes | CapEx | Localization | IT - External | 126h | 0h | 126h | 2017-07-04 | 2017-07-28 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 30 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070046 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Rajenderan; Santhosh | IBM | Yes | CapEx | Localization | IT - External | 90h | 3.27h | 93.27h | 2017-07-10 | 2017-08-14 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 20 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 15 | 25 | 20 | 0 | 0 | 0 | 0 | 0 | 0
1070047 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Rajenderan; Santhosh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070048 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Rajenderan; Santhosh | IBM | Yes | CapEx | Localization | IT - External | 0h | 10h | 10h | 2017-08-14 | 2017-08-18 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070049 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Rajenderan; Santhosh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070050 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Rajenderan; Santhosh | IBM | Yes | CapEx | Localization | IT - External | 0h | 35h | 35h | 2017-08-07 | 2017-08-11 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 4.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070051 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 configuration (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Rajenderan; Santhosh | IBM | Yes | CapEx | Localization | IT - External | 123h | 0h | 123h | 2017-08-14 | 2017-09-08 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 36 | 30 | 30 | 0 | 0
1070052 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Rajenderan; Santhosh | IBM | Yes | CapEx | Localization | IT - External | 75h | 0h | 75h | 2017-08-28 | 2017-09-15 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | -8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 45 | 0
1070053 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Rajenderan; Santhosh | IBM | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070054 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Rajenderan; Santhosh | IBM | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070055 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Rajenderan; Santhosh | IBM | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070056 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Rajenderan; Santhosh | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070057 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy2 (Accenture) - DC | MDG | DC | SI | Offshore | Morales; Veronica | Accenture | Yes | CapEx | Localization | IT - External | 171h | 0h | 171h | 2017-07-03 | 2017-07-28 | Yes |  |  | ACT-MDG.Build ETL programs | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 36 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070058 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Morales; Veronica | Accenture | Yes | CapEx | Localization | IT - External | 54h | 0h | 54h | 2017-07-31 | 2017-08-11 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-07-31 | 2017-08-11 | 2 | QE2 Mock Prep | 20000 D2-20100 B-20110 QE2 Mock Prep | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 9 | 0 | 0 | 0 | 0 | 0 | 0
1070059 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Morales; Veronica | Accenture | Yes | CapEx | Localization | IT - External | 86h | 0h | 86h | 2017-08-14 | 2017-08-24 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 39 | 0 | 0 | 0 | 0
1070060 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Morales; Veronica | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-08-28 | 2017-09-01 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0
1070061 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Morales; Veronica | Accenture | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-09-04 | 2017-09-07 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 14.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0
1070062 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Morales; Veronica | Accenture | Yes | CapEx | Localization | IT - External | 36h | 29h | 65h | 2017-09-11 | 2017-10-02 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0
1070063 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Morales; Veronica | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070064 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Morales; Veronica | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070065 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Morales; Veronica | Accenture | Yes | CapEx | Localization | IT - External | 0h | 95h | 95h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070066 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Morales; Veronica | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-22 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070067 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Morales; Veronica | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-10-30 | 2017-12-07 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 0 | 18.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070068 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Morales; Veronica | Accenture | Yes | CapEx | Localization | IT - External | 0h | 65h | 65h | 2017-10-30 | 2017-12-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070069 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Morales; Veronica | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -4.88 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070070 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Morales; Veronica | Accenture | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -50 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070071 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Morales; Veronica | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070072 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Morales; Veronica | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070073 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Morales; Veronica | Accenture | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070074 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy2 - HC - (Accenture) - DC | MDG | DC | SI | Offshore | Morales; Veronica | Accenture | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2018-02-05 | 2018-03-02 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | -17.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070075 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | SDF Build/Support (SEC) - Deploy1 | SEC | SEC | SI | Offshore | Mendoza; Janinah | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-04 | 2017-07-04 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-05 | 2017-06-23 | 1 | Security Build | 1000 D1-1300 B-1335 Security Build | 20 | 86.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070076 | No | No | Yes | SDF | SDF Localisation | 99-Global | Project Support | SEC | SEC | SI | Offshore | Lim; Kentzie | Accenture | Yes | CapEx | Localization | IT - External | 171h | 99h | 270h | 2017-08-02 | 2017-09-26 | Yes |  |  |  | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 45 | 0 | 36 | 27 | 36 | 0 | 0
1070077 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070078 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-10-09 | 2017-10-09 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070079 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 0h | 48h | 48h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070080 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-10-10 | 2017-10-13 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070081 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 0h | 48h | 48h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070082 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-08-18 | 2017-09-15 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | -8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070083 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Report (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 74h | 0h | 74h | 2017-08-21 | 2017-09-01 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 55 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 32 | 0 | 0 | 0
1070084 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 0h | 54h | 54h | 2017-08-07 | 2017-08-25 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 4.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070085 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 0h | 16h | 16h | 2017-08-04 | 2017-08-11 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 5 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070086 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070087 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Support (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070088 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-21 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070089 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 48h | 0h | 48h | 2017-07-31 | 2017-08-11 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 20 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0
1070090 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Report (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 75h | 0h | 75h | 2017-08-14 | 2017-09-08 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 5.13 | 75.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 32 | 0 | 0
1070091 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 0h | 260h | 260h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070092 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Support Mock1 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-08-25 | 2017-09-15 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-09-25 | 2017-10-06 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -25 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070093 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-08-28 | 2017-09-15 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070094 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070095 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070096 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 0h | 10h | 10h | 2017-07-07 | 2017-08-11 | Yes |  |  | DELIV-FUN-220.Solution Design Document (SDD) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070097 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 44.5h | 0h | 44.5h | 2017-08-28 | 2017-09-15 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-19 | 2017-06-30 | 1 | Cycle 2 Config | 1000 D1-1300 B-1318 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 40.5 | 0
1070098 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | PDDs | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-26 | 2017-05-26 | Yes |  |  | DELIV-FUN-110.PDDs | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070099 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070100 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070101 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Support (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070102 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Scenarios/Scripts (Test) - Deploy2 | Test | Test | SI | Offshore | Bandyopadhyay; Koushik | IBM | Yes | CapEx | Localization | IT - External | 0h | 35h | 35h | 2017-09-05 | 2017-09-11 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-11-24 | 2 | SIT 1 & 2 Prep | 20000 D2-21000 T-21036 SIT 1 & 2 Prep | -9 | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070103 | No | No | Yes | SDF | SDF Localisation | 04-Test | Manage SIT1 (Test) - Deploy2 | Test | Test | SI | Offshore | Bandyopadhyay; Koushik | IBM | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-09-11 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-11-24 | 2 | TBD | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | -5 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070104 | No | No | Yes | SDF | SDF Localisation | 04-Test | Manage SIT2 (Test) - Deploy2 | Test | Test | SI | Offshore | Bandyopadhyay; Koushik | IBM | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-10-02 | 2017-10-20 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-10-20 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070105 | No | No | Yes | SDF | SDF Localisation | 04-Test | Regression Test Scenarios/Scripts (Test) - Deploy2 | Test | Test | SI | Offshore | Bandyopadhyay; Koushik | IBM | Yes | CapEx | Localization | IT - External | 0h | 285h | 285h | 2017-09-05 | 2017-11-20 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-11-24 | 2 | QE2 Regression | 20000 D2-21000 T-21052 Regression Prep | -9 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070106 | No | No | Yes | SDF | SDF Localisation | 04-Test | Manage SIT (Test) - Deploy1 | Test | Test | SI | Offshore | Bandyopadhyay; Koushik | IBM | Yes | CapEx | Localization | IT - External | 350h | 0h | 350h | 2017-07-10 | 2017-08-25 | Yes |  |  | ACT-Test.Management | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0
1070107 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Manage UAT (Test) - Deploy1 | Test | Test | SI | Offshore | Bandyopadhyay; Koushik | IBM | Yes | CapEx | Localization | IT - External | 98h | 0h | 98h | 2017-08-28 | 2017-09-15 | Yes |  |  | ACT-Test.Management | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 36 | 44 | 0
1070108 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | CapEx | Localization | IT - External | 53h | 0h | 53h | 2017-07-31 | 2017-08-07 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-07-31 | 2017-08-11 | 2 | QE2 Mock Prep | 20000 D2-20100 B-20110 QE2 Mock Prep | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070109 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | CapEx | Localization | IT - External | 54h | 0h | 54h | 2017-09-04 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | 0
1070110 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-08 | 2017-09-15 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070111 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | CapEx | Localization | IT - External | 92h | 0h | 92h | 2017-08-21 | 2017-09-01 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 14.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 44 | 0 | 0 | 0
1070112 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 65h | 65h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070113 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070114 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070115 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | CapEx | Localization | IT - External | 45h | 50h | 95h | 2017-09-11 | 2017-10-10 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0
1070116 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-10-30 | 2017-12-07 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 0 | 18.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070117 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 65h | 65h | 2017-10-30 | 2017-12-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070118 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -4.88 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070119 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-11-03 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -50 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070120 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-22 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070121 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070122 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070123 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070124 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy2 - HC - (Accenture) - DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2018-02-05 | 2018-03-02 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | -17.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070125 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | CapEx | Localization | IT - External | 157h | 0h | 157h | 2017-07-10 | 2017-07-30 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 59 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070126 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | CapEx | Localization | IT - External | 50h | 0h | 50h | 2017-06-26 | 2017-07-06 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070127 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) - Deploy1 - DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2017-05-22 | 2017-05-24 | Yes |  |  | DELIV-MDG-206.Functional Specification -Conversion | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | -20 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070128 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Prepare Mock1 - Deploy1 - DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2017-06-10 | 2017-06-12 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070129 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | CapEx | Localization | IT - External | 49h | 0h | 49h | 2017-06-28 | 2017-08-18 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 0 | 0 | 0
1070130 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | CapEx | Localization | IT - External | 129h | 0h | 129h | 2017-06-19 | 2017-08-13 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 30 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 38 | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 0
1070131 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Mock Load - Deploy1 - DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070132 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Mock1 Validation - Deploy1 - CG- DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-05 | 2017-07-05 | Yes |  |  | ACT-MDG.Mock Validation | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070133 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Mock1 Preparation - Deploy1 - CG - DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-04 | 2017-07-04 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070134 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | CapEx | Localization | IT - External | 64h | 0h | 64h | 2017-06-12 | 2017-06-18 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 15 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070135 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Data conversion plan - MDG - DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-04-24 | 2017-04-28 | Yes |  |  | DELIV-MDG-201.Data Conversion Plan | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070136 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Data collection templates (DCT) - Explain and collect - Deploy1 - DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | CapEx | Localization | IT - External | 176h | 0h | 176h | 2017-05-01 | 2017-06-02 | Yes |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 16 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070137 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Data Validation Sheets - Deploy1 - Test - DC | MDG | DC | SI | Onshore | Samson; Valerie | Accenture | Yes | CapEx | Localization | IT - External | 54h | 0h | 54h | 2017-06-05 | 2017-06-09 | Yes |  |  | WP-MDG.Data Validation Sheets | Complete | 2017-06-05 | 2017-06-16 | 1 | QE2 Prevalidation | 1000 D1-1300 B-1325 QE2 Prevalidation | -1 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070138 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - SEC | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 830h | 830h | 2017-09-05 | 2018-04-13 | Yes |  |  |  | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070139 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF Build/Support (SEC) - Deploy1 | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 301h | 0h | 301h | 2017-07-24 | 2017-09-08 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-05 | 2017-06-23 | 1 | Security Build | 1000 D1-1300 B-1335 Security Build | 20 | 86.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 47 | 43 | 44 | 42 | 43 | 34 | 0 | 0
1070140 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Analyze - Security Design | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 42h | 0h | 42h | 2017-05-23 | 2017-05-26 | Yes |  |  | DELIV-SEC-002.Security and Controls Requirements | Complete | NA | NA | 1 | TBD | 1000 D1-1300 B-1334 Security Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070141 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Preperation - Security Design | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | DELIV-SEC-002.Security and Controls Requirements | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070142 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy2 | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-10-10 | 2017-10-13 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070143 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy2 | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 40h | 40h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070144 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy2 | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 10h | 10h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070145 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (LOG) - Deploy1 | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 20h | 20h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070146 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Manage defects (LOG) - Deploy1 | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 20h | 20h | 2017-10-02 | 2017-10-27 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070147 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (LOG) - Deploy1 | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 160h | 160h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070148 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | DM TAI SDF Dev Installation and Configuration - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-01 | 2017-05-05 | 1 | Data Construction | 1000 D1-1200 A-1214 Data Construction | -35 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070149 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Data Conversion Plan - Deploy1 - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-07 | 2017-07-07 | Yes |  |  | DELIV-MDG-201.Data Conversion Plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070150 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-18 | 2017-08-18 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070151 | No | No | Yes | SDF | SDF Localisation | 99-Global | Team Lead - MDG - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Localization | IT - External | 136h | 1,288h | 1,424h | 2017-07-31 | 2018-04-03 | Yes |  |  | DELIV-FUN-029.Site Assessment | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 32 | 40 | 0 | 0 | 0
1070152 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - OTC | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -30 | -30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070153 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2017-03-21 | 2017-03-30 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070154 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 52h | 0h | 52h | 2017-03-21 | 2017-03-31 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070155 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-04-03 | 2017-04-06 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -25 | -13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070156 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-27 | 2017-03-27 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | -5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070157 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-04-10 | 2017-04-11 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -10 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070158 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTP) - Deploy1 | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 76h | 2.4h | 78.4h | 2017-08-28 | 2017-09-11 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 32 | 0 | 0
1070159 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | RTM - PTP | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 202h | 0h | 202h | 2017-05-22 | 2017-06-23 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -29.88 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 30 | 44 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070160 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - PTP | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 132h | 0h | 132h | 2017-04-17 | 2017-05-05 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070161 | No | Yes | No | SDF | SDF Interim State Project | 02-Analyze | SDF-INT-Workshop-Product costing | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-02 | 2017-03-02 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070162 | No | Yes | No | SDF | SDF Interim State Project | 02-Analyze | SDF-INT-Workshop-Finance | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-01 | 2017-03-01 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070163 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (HR) - Deploy1 | HR | HR | Saputo | Onshore | Freire; Roberto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 21h | 21h | 2017-09-05 | 2017-09-15 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070164 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (HR) - Deploy1 | HR | HR | Saputo | Onshore | Freire; Roberto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 27h | 27h | 2017-10-02 | 2017-12-01 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070165 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (HR) - Deploy1 | HR | HR | Saputo | Onshore | Freire; Roberto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070166 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Gap Definition | HR | HR | Saputo | Onshore | Freire; Roberto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-02 | 2017-06-02 | Yes |  |  | WP-FUN.Gap Definition | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | 1 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070167 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (HR) - Deploy1 | HR | HR | Saputo | Onshore | Freire; Roberto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-29 | 2017-06-29 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 21.13 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070168 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (HR) - Deploy1 | HR | HR | Saputo | Onshore | Freire; Roberto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-21 | 2017-07-21 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -20 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070169 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 48h | 48h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | -5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070170 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 48h | 48h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070171 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-04 | 2017-12-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070172 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-04 | 2017-12-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070173 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Regression - Run Tests (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 84h | 84h | 2017-11-06 | 2017-11-24 | Yes |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-12-04 | 2017-12-22 | 2 | Q? Regression | 20000 D2-22000 CG: UAT and Regression-22010 Q? Regression | -20 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070174 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 48h | 48h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070175 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 48h | 48h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070176 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Support (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 15h | 15h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070177 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -10 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070178 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 60h | 0h | 60h | 2017-07-03 | 2017-07-07 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-21 | 2017-09-01 | 2 | AT | 20000 D2-20100 B-20180 AT | -45 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070179 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (OTC) - Deploy1 | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 53h | 16h | 69h | 2017-07-17 | 2017-09-01 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 0 | 32 | 8 | 0 | 0 | 0 | 0 | 0
1070180 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 10h | 0h | 10h | 2017-04-03 | 2017-04-07 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | -5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070181 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 28.55h | 0h | 28.55h | 2017-04-03 | 2017-04-07 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -25 | -13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070182 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070183 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 8h | 0h | 8h | 2017-03-13 | 2017-03-17 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070184 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | RTM - OTC | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 48h | 0h | 48h | 2017-04-17 | 2017-05-26 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -18 | 57.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 24 | 0 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070185 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Log Gaps - OTC | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 57h | 0h | 57h | 2017-04-17 | 2017-05-26 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -15 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 10 | 10 | 6 | 2 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070186 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - OTC | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -30 | -30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070187 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Functional Specification (FSD) | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070188 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | TPM Unit testing Development Documentation (FUT) | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 20h | 20h | 2017-05-29 | 2017-09-29 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070189 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 20h | 20h | 2017-09-05 | 2017-09-15 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 10 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070190 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Support Mock1 (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 10h | 10h | 2017-09-05 | 2017-09-15 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-09-25 | 2017-10-06 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -30 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070191 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 20h | 20h | 2017-09-05 | 2017-09-29 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070192 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Report (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 20h | 20h | 2017-09-05 | 2017-09-29 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070193 | No | Yes | No | SDF | SDF Localisation | 01-Preparation | Preperation - Security Design | SEC | SEC | SI |  | Igwenazor; Stella | Other | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-04-03 | 2017-04-13 | Yes |  |  | DELIV-SEC-002.Security and Controls Requirements | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070194 | No | Yes | No | SDF | SDF Localisation | 02-Analyze | Analyze - Security Design | SEC | SEC | SI |  | Igwenazor; Stella | Other | Yes | CapEx | Localization | IT - External | 35h | 0h | 35h | 2017-04-17 | 2017-04-28 | Yes |  |  | DELIV-SEC-002.Security and Controls Requirements | Complete | NA | NA | 1 | TBD | 1000 D1-1300 B-1334 Security Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070195 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SEC-Build - SEC Deploy2 | SEC | SEC | SI | Onshore | Pal; Gaurav | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-08-28 | 2017-09-15 | Yes |  |  |  | Future Task | 2017-07-24 | 2017-08-11 | 2 | Security Build | 20000 D2-20100 B-20230 Security Build | 20 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070196 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SEC-FUT - SEC Deploy2 | SEC | SEC | SI | Onshore | Pal; Gaurav | Accenture | Yes | CapEx | Localization | IT - External | 26h | 14h | 40h | 2017-09-01 | 2017-09-11 | Yes |  |  |  | Future Task | 2017-08-14 | 2017-09-01 | 2 | Security FUT | 20000 D2-20100 B-20240 Security FUT | 14 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 18 | 0 | 0
1070197 | No | No | Yes | SDF | SDF Localisation | 04-Test | SEC Break/Fix SIT1 - SEC Deploy2 | SEC | SEC | SI | Onshore | Pal; Gaurav | Accenture | Yes | CapEx | Localization | IT - External | 0h | 120h | 120h | 2017-09-18 | 2017-10-06 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070198 | No | No | Yes | SDF | SDF Localisation | 04-Test | SEC Break/Fix SIT2 - SEC Deploy2 | SEC | SEC | SI | Onshore | Pal; Gaurav | Accenture | Yes | CapEx | Localization | IT - External | 0h | 120h | 120h | 2017-10-10 | 2017-10-27 | Yes |  |  |  | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070199 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 configuration (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | 25 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070200 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Support (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070201 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070202 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070203 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - LOG | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-05 | 2017-05-05 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070204 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | RTM - LOG | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-05 | 2017-05-05 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070205 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Gap Definition | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-06-12 | 2017-06-16 | Yes |  |  | WP-FUN.Gap Definition | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -5 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070206 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070207 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Report (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-08-21 | 2017-08-25 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 55 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0
1070208 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 configuration (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 15h | 15h | 2017-08-11 | 2017-08-18 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070209 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 70h | 5h | 75h | 2017-08-28 | 2017-09-11 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | -8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 0 | 0
1070210 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-10-09 | 2017-10-09 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070211 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 100h | 100h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070212 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2017-06-26 | 2017-08-11 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 20 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0
1070213 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 5 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070214 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Support (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070215 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070216 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 18h | 18h | 2017-08-14 | 2017-09-01 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070217 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070218 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-08-31 | 2017-08-31 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 5 | 33.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0
1070219 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-06-30 | 2017-08-11 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-19 | 2017-06-30 | 1 | Cycle 2 Config | 1000 D1-1300 B-1318 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070220 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-06-30 | 2017-08-04 | Yes |  |  | DELIV-FUN-220.Solution Design Document (SDD) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070221 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-06-30 | 2017-07-14 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070222 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070223 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Support Mock1 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 85h | 85h | 2017-08-21 | 2017-09-15 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-09-25 | 2017-10-06 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -25 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070224 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 260h | 260h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070225 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Report (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-08-14 | 2017-08-18 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 5.13 | 75.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0
1070226 | No | Yes | No | SDF | SDF Localisation | 01-Preparation | Data profiling - DC | MDG | DC | SI | Onshore | Mierski; Pawel | SAP | Yes | CapEx | Localization | IT - External | 200h | 0h | 200h | 2017-03-13 | 2017-04-15 | Yes |  |  | DELIV-MDG-050.Data Profiling | Complete | 2017-05-01 | 2017-05-05 | 1 | Data Construction | 1000 D1-1200 A-1214 Data Construction | -55 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070227 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (RTR) - Deploy1 | RTR | FUN | Saputo | Onshore | Valin; Eric | Saputo | Yes | CapEx | Localization | IT - Internal | 5h | 0h | 5h | 2017-07-17 | 2017-08-04 | Yes |  |  | ACT-FUN.Functional Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070228 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (RTR) - Deploy1 | RTR | FUN | Saputo | Onshore | Valin; Eric | Saputo | Yes | CapEx | Localization | IT - Internal | 2h | 6h | 8h | 2017-08-07 | 2017-08-17 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 13.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
1070229 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (RTR) - Deploy1 | RTR | FUN | Saputo | Onshore | Valin; Eric | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 15h | 15h | 2017-09-01 | 2017-09-11 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070230 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Requirements/Process Design Workshops | RTR | FUN | Saputo | Onshore | Valin; Eric | Saputo | Yes | CapEx | Localization | IT - Internal | 25h | 0h | 25h | 2017-06-20 | 2017-07-21 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 4 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070231 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - RTR | RTR | FUN | Saputo | Onshore | Valin; Eric | Saputo | Yes | CapEx | Localization | IT - Internal | 50h | 0h | 50h | 2017-04-03 | 2017-05-25 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -9.88 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 32 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070232 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | RTR | FUN | Saputo | Onshore | Valin; Eric | Saputo | Yes | CapEx | Localization | IT - Internal | 16h | 0h | 16h | 2017-03-13 | 2017-03-21 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070233 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | SDF-INT-Workshop-Product costing | RTR | FUN | Saputo | Onshore | Valin; Eric | Saputo | Yes | CapEx | Localization | IT - Internal | 9h | 0h | 9h | 2017-03-02 | 2017-03-31 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070234 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) - Deploy1 - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 98h | 0h | 98h | 2017-05-15 | 2017-05-29 | Yes |  |  | DELIV-MDG-206.Functional Specification -Conversion | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | -20 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070235 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 67.5h | 0h | 67.5h | 2017-06-17 | 2017-07-21 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 15 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 0 | 18 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070236 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Data Validation Sheets - Deploy1 - Test - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-07 | 2017-07-07 | Yes |  |  | WP-MDG.Data Validation Sheets | Complete | 2017-06-05 | 2017-06-16 | 1 | QE2 Prevalidation | 1000 D1-1300 B-1325 QE2 Prevalidation | -1 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070237 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Mock Load - Deploy1 - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-28 | 2017-07-28 | Yes |  |  | ACT-MDG.Mock Load | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070238 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Mock1 Validation - Deploy1 - CG- DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-28 | 2017-07-28 | Yes |  |  | ACT-MDG.Mock Validation | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070239 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Mock1 Preparation - Deploy1 - CG - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-28 | 2017-07-28 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070240 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 63h | 0h | 63h | 2017-06-26 | 2017-08-11 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 30 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 18 | 0 | 0 | 0 | 0 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0
1070241 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy1 - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 43h | 0h | 43h | 2017-06-12 | 2017-06-16 | Yes |  |  | ACT-MDG.Build ETL programs | Complete | 2017-05-08 | 2017-06-09 | 1 | Build and adjust conversion programs | 1000 D1-1300 B-1322 Build and adjust conversion programs | 15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070242 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 43.5h | 0h | 43.5h | 2017-07-04 | 2017-08-11 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0
1070243 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Data Migration development - Deploy1 - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 154.5h | 0h | 154.5h | 2017-05-29 | 2017-06-25 | Yes |  |  | ACT-MDG.Data Construction | Complete | 2017-05-08 | 2017-06-09 | 1 | Data Construction | 1000 D1-1300 B-1320 Data Construction | 15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 47.5 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070244 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 98h | 0h | 98h | 2017-07-10 | 2017-08-20 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 45 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0
1070245 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2017-06-17 | 2017-06-30 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 0 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070246 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070247 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070248 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-22 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070249 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-10-30 | 2017-12-07 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 0 | 18.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070250 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-10-30 | 2017-12-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070251 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -4.88 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070252 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -50 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070253 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 5h | 20h | 25h | 2017-09-11 | 2017-09-26 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0
1070254 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 20h | 20h | 40h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0
1070255 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 15h | 30h | 45h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0
1070256 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-08-14 | 2017-08-25 | Yes |  |  | ACT-MDG.Mock Load | Complete | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 10.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 24 | 0 | 0 | 0 | 0
1070257 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 114h | 0h | 114h | 2017-08-01 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 15 | 24 | 7.5 | 22.5 | 0 | 0
1070258 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 37.5h | 0h | 37.5h | 2017-08-14 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 22.5 | 0 | 0
1070259 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 5h | 20h | 25h | 2017-09-11 | 2017-09-26 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0
1070260 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy1 - HC - (Accenture) - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -21.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070261 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 45h | 235h | 280h | 2017-08-28 | 2017-11-03 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 10 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0
1070262 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0h | 192.53h | 192.53h | 2017-08-28 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070263 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 50h | 0h | 50h | 2017-07-17 | 2017-07-21 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-21 | 2017-09-01 | 2 | AT | 20000 D2-20100 B-20180 AT | -45 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070264 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-16 | 2017-06-16 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070265 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT - OTC- Deploy2 | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 185h | 52.53h | 237.53h | 2017-06-05 | 2017-09-01 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 25 | 25 | 0 | 0 | 45 | 45 | 5 | 0 | 0 | 0 | 0 | 0
1070266 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 53h | 3h | 56h | 2017-05-08 | 2017-08-07 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-05-19 | 2 | Base Config | 1000 D1-1300 B-1314 Base Config | -5 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 10 | 0 | 0 | 5 | 20 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070267 | No | No | Yes | SDF | SDF Interim State Project | 01-Preparation | Environment setup | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-01-09 | 2017-01-20 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 5 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070268 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-08-14 | 2017-08-20 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | -15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0
1070269 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 48h | 0h | 48h | 2017-08-21 | 2017-08-24 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | -25 | 16.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0
1070270 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | SDF-INT-Workshop-Finance | RTR | FUN | Saputo | Onshore | Therien; Stephane | Saputo | Yes | CapEx | Localization | IT - Internal | 9h | 0h | 9h | 2017-03-01 | 2017-03-30 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070271 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | RTR | FUN | Saputo | Onshore | Therien; Stephane | Saputo | Yes | CapEx | Localization | IT - Internal | 14h | 0h | 14h | 2017-03-20 | 2017-03-22 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070272 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - RTR | RTR | FUN | Saputo | Onshore | Therien; Stephane | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-05-19 | 2017-05-19 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -9.88 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070273 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Requirements/Process Design Workshops | RTR | FUN | Saputo | Onshore | Therien; Stephane | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 18h | 18h | 2017-07-03 | 2017-09-18 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 4 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070274 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (RTR) - Deploy1 | RTR | FUN | Saputo | Onshore | Therien; Stephane | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 16h | 16h | 2017-08-25 | 2017-09-01 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070275 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (RTR) - Deploy1 | RTR | FUN | Saputo | Onshore | Therien; Stephane | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Functional Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070276 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | PDDs | RTR | FUN | Saputo | Onshore | Therien; Stephane | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 8h | 8h | 2017-08-21 | 2017-08-22 | Yes |  |  | DELIV-FUN-110.PDDs | Future Task | 2017-05-01 | 2017-05-05 | 1 | TBD | 99000-99100-99110 TBD | 80 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070277 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (RTR) - Deploy1 | RTR | FUN | Saputo | Onshore | Therien; Stephane | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 16h | 16h | 2017-09-01 | 2017-09-11 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 13.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070278 | No | No | Yes | SDF | SDF Localisation | 04-Test | Communication Plan (Test) | CM | CM | Saputo | Onshore | Gabra; Rania | Saputo | Yes | OpEx | Localization | IT - Internal | 90h | 0h | 90h | 2017-07-17 | 2017-08-25 | Yes |  |  | DELIV-CM-106.Communication Plan | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 21 | 37 | 0 | 0 | 0 | 0
1070279 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Communication Plan (Cutover/Go-live) - Deploy1 | CM | CM | Saputo | Onshore | Gabra; Rania | Saputo | Yes | OpEx | Localization | IT - Internal | 109h | 50h | 159h | 2017-08-28 | 2017-09-29 | Yes |  |  | DELIV-CM-106.Communication Plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 34 | 35 | 0
1070280 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | Communication plan execution and monitoring | CM | CM | Saputo | Onshore | Gabra; Rania | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 225h | 225h | 2017-10-02 | 2017-12-01 | Yes |  |  | ACT-CM.Communication plan execution and monitoring | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070281 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Communication Plan (Preparation) | CM | CM | Saputo | Onshore | Gabra; Rania | Saputo | Yes | OpEx | Localization | IT - Internal | 126h | 0h | 126h | 2017-03-20 | 2017-04-13 | Yes |  |  | DELIV-CM-106.Communication Plan | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 30.5 | 26 | 27.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070282 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Communication Plan (Analyze) | CM | CM | Saputo | Onshore | Gabra; Rania | Saputo | Yes | OpEx | Localization | IT - Internal | 144h | 0h | 144h | 2017-04-17 | 2017-07-13 | Yes |  |  | DELIV-CM-106.Communication Plan | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 27 | 27 | 18 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070283 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Communication Plan (Design/Build) | CM | CM | Saputo | Onshore | Gabra; Rania | Saputo | Yes | OpEx | Localization | IT - Internal | 170h | 0h | 170h | 2017-05-29 | 2017-08-04 | Yes |  |  | DELIV-CM-106.Communication Plan | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 36 | 26 | 13 | 13 | 26 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070284 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | SDF Interim State-Workshop-Production scheduling and receipt (OCT. Go-live) | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-02-27 | 2017-03-28 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070285 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 0h | 44h | 44h | 2017-09-25 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070286 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 0h | 436h | 436h | 2017-10-02 | 2017-12-15 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070287 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTM(Global) | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 356h | 0h | 356h | 2017-07-17 | 2017-09-04 | Yes |  |  | ACT-FUN.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 58 | 44 | 44 | 44 | 61 | 61 | 0 | 0 | 0
1070288 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTM | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 272h | 0h | 272h | 2017-06-05 | 2017-07-16 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 44 | 44 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070289 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | IXXX-DEV FUT-Production receipts interface | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-19 | 2017-06-23 | Yes |  |  | ACT-FUN.Execute FUT | Complete | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | 20 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070290 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-09-05 | 2017-09-18 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 15 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070291 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070292 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - PTM | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-24 | 2017-03-24 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070293 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTM | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 273h | 0h | 273h | 2017-04-17 | 2017-06-02 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 52 | 44 | 44 | 44 | 35 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070294 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-03-13 | 2017-03-17 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -15.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070295 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 75h | 0h | 75h | 2017-03-20 | 2017-03-31 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -20 | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070296 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2017-04-03 | 2017-04-13 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -20 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070297 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070298 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 34h | 0h | 34h | 2017-04-17 | 2017-04-21 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -8.88 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070299 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | SDF Interim State-Workshop-Supply chain planning | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2017-02-20 | 2017-03-31 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070300 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 0h | 96h | 96h | 2017-12-04 | 2017-12-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070301 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 0h | 184h | 184h | 2017-12-04 | 2018-01-12 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -30 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070302 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 0h | 132h | 132h | 2018-01-15 | 2018-01-30 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -8 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070303 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 0h | 120h | 120h | 2018-02-05 | 2018-03-30 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070304 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 3h | 0h | 3h | 2017-04-04 | 2017-04-07 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -8.88 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070305 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070306 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -20 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070307 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -20 | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070308 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -15.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070309 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 6.6h | 6.6h | 2017-08-28 | 2017-09-22 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -24.88 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070310 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 20h | 20h | 2017-08-28 | 2017-09-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070311 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 10h | 10h | 2017-08-28 | 2017-09-29 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070312 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - PTM | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-24 | 2017-03-24 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070313 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -20 | -16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070314 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 5h | 0h | 5h | 2017-03-20 | 2017-03-22 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | -9.88 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070315 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - PTP | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070316 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | RTM - PTP | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 152h | 0h | 152h | 2017-03-06 | 2017-08-04 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -29.88 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 6 | 3 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 40 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070317 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Gap log - PTP | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 9h | 0h | 9h | 2017-03-29 | 2017-04-10 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -22.88 | 70.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070318 | No | No | Yes | SDF | SDF Interim State Project | 01-Preparation | Environment setup | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-01-09 | 2017-01-13 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070319 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 0h | 135h | 135h | 2017-09-05 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070320 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 0h | 270h | 270h | 2017-09-05 | 2017-11-03 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 10 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070321 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 21h | 23h | 44h | 2017-06-19 | 2017-08-28 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | -25 | 16.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 | 12 | 0 | 0 | 0 | 0
1070322 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT - OTC- Deploy2 | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 20h | 24h | 44h | 2017-06-12 | 2017-08-14 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0
1070323 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-08-07 | 2017-08-24 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 16 | 8 | 0 | 0 | 0 | 0
1070324 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 32h | 24h | 56h | 2017-06-26 | 2017-08-25 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-21 | 2017-09-01 | 2 | AT | 20000 D2-20100 B-20180 AT | -45 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0
1070325 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B - Vendor Master - Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-06-09 | 1 | Build and adjust conversion programs | 1000 D1-1300 B-1322 Build and adjust conversion programs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070326 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B - Financial Objects - Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-06-09 | 1 | Build and adjust conversion programs | 1000 D1-1300 B-1322 Build and adjust conversion programs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070327 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test - Vendor Master - Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070328 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test - SIT 1 - Financial Objects - Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070329 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B-Dual Maintenance Design and Documentation-FIN-SI - Deploy1 - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | CapEx | Localization | IT - Internal | 5h | 0h | 5h | 2017-07-01 | 2017-08-04 | Yes |  |  |  | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070330 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B-FUT Spare Parts-VM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-04 | 2017-08-04 | Yes |  |  |  | Future Task | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 42 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070331 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B-Dual Maintenance Design and Documentation-VM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 5h | 0h | 5h | 2017-07-03 | 2017-08-04 | Yes |  |  |  | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070332 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B-FUT Spare Parts-FIN-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-04 | 2017-08-04 | Yes |  |  |  | Future Task | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 42 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070333 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test-'Smoke'' Test Planning and Scheduling-FIN-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | Yes |  |  |  | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070334 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test-'Smoke'' Test Planning and Scheduling-VM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | Yes |  |  |  | Future Task | 2017-07-17 | 2017-08-25 | 1 | TBD | 99000-99100-99110 TBD | 20 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070335 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test - SIT 2 - Financial Objects - Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 2h | 0h | 2h | 2017-08-11 | 2017-08-11 | Yes |  |  | ACT-FUN.Execute SIT | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0.13 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
1070336 | No | No | Yes | SDF | SDF Localisation | 99-Global | Data Governance – Change Process - DG | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | Yes |  |  | DELIV-MDG-100.Data Governance Procedures | Future Task | NA | NA | 9 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070337 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | C/G-Business Cutover Plan-VM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-09-18 | 2017-09-18 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070338 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HYP-Dual Maintenance Execution-FIN-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070339 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HYP-Dual Maintenance Execution-VM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070340 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HYP-End User Support-FIN-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070341 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HYP-End User Support-VM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070342 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HYP-Smoke Test Execution-FIN-SI - Deploy1 - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070343 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HYP-Smoke Test Execution-VM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070344 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Support - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 6h | 51h | 57h | 2017-08-21 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 60 | 48.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0
1070345 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 48h | 48h | 2017-08-31 | 2017-09-21 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | -5 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070346 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover Prepare - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 20h | 28h | 48h | 2017-08-30 | 2017-09-15 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -15 | -8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0
1070347 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover Suport - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 30h | 30h | 2017-09-11 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070348 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | Hypercare-Provide end User Support - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 360h | 360h | 2017-10-02 | 2017-12-01 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070349 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Support - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 70h | 70h | 2017-12-18 | 2018-02-02 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-11-03 | 2 | Training Material Localization | 20000 D2-29000 MultiPhases-29040 Training Material Localization | 55 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070350 | No | No | Yes | SDF | SDF Localisation | 04-Test | Regression Testing - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 30h | 30h | 2017-11-06 | 2017-11-24 | Yes |  |  |  | Future Task | 2017-11-06 | 2017-11-24 | 2 | D2 Regression (in QE2) | 20000 D2-21000 T-21054 D2 Regression (in QE2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070351 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | Hypercare-Provide end User Support - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 320h | 320h | 2018-02-05 | 2018-03-30 | Yes |  |  |  | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070352 | No | No | Yes | SDF | SDF Localisation | 99-Global | Team Lead - MDG - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 95h | 0h | 95h | 2016-10-24 | 2017-08-18 | Yes |  |  | DELIV-FUN-029.Site Assessment | On Schedule | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 50 | 40 | 0 | 0 | 0 | 0 | 0
1070353 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Trivedi; Mohit | IBM | Yes | CapEx | Localization | IT - External | 4.5h | 0h | 4.5h | 2017-07-31 | 2017-08-04 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070354 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Trivedi; Mohit | IBM | Yes | CapEx | Localization | IT - External | 18.5h | 0h | 18.5h | 2017-08-07 | 2017-09-01 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 | 4.5 | 5 | 0 | 0 | 0
1070355 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy1 (Design/Build) | DEV | DEV | SI | Offshore | Trivedi; Mohit | IBM | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2017-06-27 | 2017-07-28 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5 | 5.5 | 5 | 4.5 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070356 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | SI | Offshore | Trivedi; Mohit | IBM | Yes | CapEx | Localization | IT - External | 88.5h | 0h | 88.5h | 2017-06-27 | 2017-09-15 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6.5 | 7 | 7 | 7 | 6.5 | 6 | 7 | 6.5 | 11.5 | 11.5 | 0
1070357 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | SI | Offshore | Trivedi; Mohit | IBM | Yes | CapEx | Localization | IT - External | 0h | 15h | 15h | 2017-08-28 | 2017-09-29 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070358 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | SI | Offshore | Trivedi; Mohit | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070359 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Trivedi; Mohit | IBM | Yes | CapEx | Localization | IT - External | 0h | 15h | 15h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070360 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | SI | Offshore | Trivedi; Mohit | IBM | Yes | CapEx | Localization | IT - External | 18.7h | 55.3h | 74h | 2017-02-13 | 2017-10-31 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.2 | 0 | 6.5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070361 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing WRICEFs (Design/Build) | DEV | DEV | SI | Offshore | Trivedi; Mohit | IBM | Yes | CapEx | Localization | IT - External | 0h | 8h | 8h | 2017-02-13 | 2017-07-28 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -88 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070362 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Trivedi; Mohit | IBM | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070363 | No | Yes | No | SDF | SDF Interim State Project | 03-Design/Build | Data migration | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070364 | No | Yes | No | SDF | SDF Interim State Project | 03-Design/Build | IXXX-FSD-G/L interface | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 61h | 0h | 61h | 2017-04-24 | 2017-05-07 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -25 | -30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070365 | No | Yes | No | SDF | SDF Interim State Project | 03-Design/Build | Support to Data | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070366 | No | Yes | No | SDF | SDF Interim State Project | 03-Design/Build | PDD-Reconcialition process design | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2017-06-19 | 2017-07-27 | Yes |  |  | DELIV-FUN-110.PDDs | Future Task | 2017-05-01 | 2017-05-05 | 0 | NA Others | 99000-99100-99130 NA others | 25 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 32 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070367 | No | Yes | No | SDF | SDF Interim State Project | 03-Design/Build | Support to Data (financial Data object mapping) | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-05-08 | 2017-05-26 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070368 | No | Yes | No | SDF | SDF Interim State Project | 03-Design/Build | Workshop-Design Map GL Posting | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 124h | 0h | 124h | 2017-05-29 | 2017-06-30 | Yes |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 12 | 35 | 36 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070369 | No | Yes | No | SDF | SDF Interim State Project | 03-Design/Build | Workshop-Design Interim state financial reporting | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 86h | 0h | 86h | 2017-05-23 | 2017-07-31 | Yes |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 31 | 0 | 2 | 0 | 38 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070370 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-05-29 | 2017-06-30 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | -14 | 72.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 2 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070371 | No | Yes | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing WRICEFs (Design/Build) | DEV | DEV | SI | Onshore | Gilbert; Marc | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-24 | 2017-02-24 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -88 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070372 | No | Yes | No | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -10 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070373 | No | Yes | No | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-27 | 2017-03-27 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -25 | -13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070374 | No | Yes | No | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070375 | No | Yes | No | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-27 | 2017-03-27 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | -5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070376 | No | Yes | No | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-03-13 | 2017-03-17 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070377 | No | Yes | No | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - OTC | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-03-06 | 2017-03-10 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -30 | -30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070378 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 0h | 125h | 125h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070379 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-09-05 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070380 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 0h | 120h | 120h | 2017-09-25 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070381 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 0h | 140h | 140h | 2017-09-05 | 2017-09-29 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 15 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070382 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Report (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070383 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Gather reporting requierements (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | Yes |  |  | ACT-FUN.Gather reporting requierement | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070384 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - OTC-(Global) | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 0h | 134h | 134h | 2017-07-04 | 2017-09-01 | Yes |  |  | ACT-CM.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070385 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (OTC) - Deploy1 | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 0h | 48h | 48h | 2017-09-05 | 2017-09-15 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070386 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - OTC | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 84h | 0h | 84h | 2017-04-19 | 2017-07-07 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070387 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | RTM - OTC | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 62h | 0h | 62h | 2017-03-22 | 2017-04-21 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -18 | 57.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 18 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070388 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-03-13 | 2017-03-14 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070389 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-04-06 | 2017-04-06 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | -5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070390 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-03-15 | 2017-04-03 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 18 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070391 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-04-05 | 2017-04-05 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -25 | -13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070392 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-04-11 | 2017-04-11 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -10 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070393 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 132h | 0h | 132h | 2017-06-26 | 2017-09-01 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-21 | 2017-09-01 | 2 | AT | 20000 D2-20100 B-20180 AT | -45 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 0 | 0 | 0
1070394 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) (Test) - OTC | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2017-07-17 | 2017-08-04 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070395 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (OTC) - Deploy1 | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 30h | 0h | 30h | 2017-07-17 | 2017-08-04 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070396 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (OTC) - Deploy1 | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 162h | 0h | 162h | 2017-07-17 | 2017-08-18 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 24 | 24 | 44 | 44 | 0 | 0 | 0 | 0 | 0
1070397 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 36h | 20h | 56h | 2017-09-05 | 2017-09-15 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 10 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0
1070398 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - OTC | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-03-06 | 2017-03-09 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -30 | -30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070399 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 0h | 135h | 135h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070400 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 0h | 135h | 135h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070401 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Regression - Run Tests (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 0h | 135h | 135h | 2017-11-06 | 2017-11-24 | Yes |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-12-04 | 2017-12-22 | 2 | Q? Regression | 20000 D2-22000 CG: UAT and Regression-22010 Q? Regression | -20 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070402 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Support-D2 | RTR | FUN | SI | Onshore | Lucinda; Mariana | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-11 | 2017-10-06 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-09-18 | 2017-11-03 | 2 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | -5 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070403 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Lucinda; Mariana | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070404 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Lucinda; Mariana | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070405 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Lucinda; Mariana | IBM | Yes | CapEx | Localization | IT - External | 0h | 15h | 15h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070406 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - RTR | RTR | FUN | SI | Onshore | Lucinda; Mariana | IBM | Yes | CapEx | Localization | IT - External | 71h | 0h | 71h | 2017-04-18 | 2017-05-12 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -9.88 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 27 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070407 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | RTR | FUN | SI | Onshore | Lucinda; Mariana | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-04-10 | 2017-04-13 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070408 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | RTM - RTR | RTR | FUN | SI | Onshore | Lucinda; Mariana | IBM | Yes | CapEx | Localization | IT - External | 70h | 0h | 70h | 2017-04-17 | 2017-05-19 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070409 | No | No | Yes | SDF | SDF Localisation | 04-Test | Support training team - RTR | RTR | FUN | SI | Onshore | Lucinda; Mariana | IBM | Yes | OpEx | Localization | IT - External | 0h | 60h | 60h | 2017-08-21 | 2017-09-29 | Yes |  |  | DELIV-CM-401.Training Materials | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 60 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070410 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Enhancement (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Lucinda; Mariana | IBM | Yes | CapEx | Localization | IT - External | 50h | 266.57h | 316.57h | 2017-08-14 | 2017-10-27 | Yes |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 4 | 18 | 0 | 0 | 0
1070411 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Form (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Lucinda; Mariana | IBM | Yes | CapEx | Localization | IT - External | 9h | 81h | 90h | 2017-08-28 | 2017-09-27 | Yes |  |  | DELIV-FUN-204.Functional Specification - Form | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0
1070412 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Interface (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Lucinda; Mariana | IBM | Yes | CapEx | Localization | IT - External | 268h | 40h | 308h | 2017-06-07 | 2017-08-25 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 7 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 36 | 44 | 44 | 36 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0
1070413 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Lucinda; Mariana | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-08-28 | 2017-09-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070414 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Lucinda; Mariana | IBM | Yes | CapEx | Localization | IT - External | 0h | 45h | 45h | 2017-08-30 | 2017-09-19 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070415 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Lucinda; Mariana | IBM | Yes | CapEx | Localization | IT - External | 0h | 29h | 29h | 2017-09-01 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070416 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT 1 - Manage defects (DEV) - Deploy1 (Test) | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 23.5h | 0h | 23.5h | 2017-07-10 | 2017-07-14 | Yes |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -5 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070417 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT 1 - Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | Yes |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070418 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 14.5h | 0h | 14.5h | 2016-12-28 | 2017-06-02 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5 | 3 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070419 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070420 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | WRICEFs - DEV (Design/Build) | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 123.5h | 0h | 123.5h | 2017-06-05 | 2017-07-07 | Yes |  |  | To delete-To delete.To delete | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 15.13 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 29 | 25 | 20.5 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070421 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | WRICEFs inventory - DEV | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 13.5h | 0h | 13.5h | 2017-05-23 | 2017-06-02 | Yes |  |  | DELIV-DEV-102.RICEFW Inventory | Future Task | NA | NA | 1 | GAPs | 1000 D1-1200 A-1211GAPs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070422 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Break/Fix - DEV | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0.13 | 5.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070423 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 151h | 0h | 151h | 2017-06-19 | 2017-09-15 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 14 | 15 | 23 | 27.5 | 22.5 | 14.5 | 16.5 | 16 | 0
1070424 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 120h | 120h | 2017-10-10 | 2017-11-17 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070425 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070426 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 57.5h | 0h | 57.5h | 2017-07-17 | 2017-08-04 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.5 | 15.5 | 9.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070427 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 1h | 69.07h | 70.07h | 2017-09-15 | 2017-10-16 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
1070428 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 8h | 0h | 8h | 2017-08-07 | 2017-08-31 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1 | 2.5 | 3 | 0 | 0 | 0
1070429 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | CapEx | Localization | IT - External | 9h | 21h | 30h | 2017-08-23 | 2017-09-12 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0
1070430 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070431 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy1 (Design/Build) | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | CapEx | Localization | IT - External | 79h | 0h | 79h | 2017-07-22 | 2017-08-21 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 23 | 17 | 13 | 7 | 7 | 0 | 0 | 0 | 0
1070432 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | CapEx | Localization | IT - External | 147h | 0h | 147h | 2017-08-08 | 2017-09-15 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 13 | 38 | 45 | 45 | 0
1070433 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-08-28 | 2017-09-29 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070434 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 115h | 115h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070435 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 170h | 170h | 2017-10-09 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070436 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070437 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | CapEx | Localization | IT - External | 5h | 70h | 75h | 2017-02-13 | 2017-10-31 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070438 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing WRICEFs (Design/Build) | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | CapEx | Localization | IT - External | 30h | 50h | 80h | 2017-07-18 | 2017-11-03 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -88 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 18 | 0 | 0 | 0 | 0 | 0
1070439 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070440 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | RTM - LOG | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-18 | 2017-04-18 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070441 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Gap log - LOG | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-05 | 2017-05-05 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070442 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070443 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070444 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Support (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070445 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Report (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 15h | 15h | 2017-08-04 | 2017-08-11 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 5.13 | 75.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070446 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 260h | 260h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070447 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 88h | 44h | 132h | 2017-08-28 | 2017-09-19 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 44 | 0
1070448 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Support Mock1 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-25 | 2017-08-25 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-09-25 | 2017-10-06 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -25 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070449 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070450 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 10h | 10h | 2017-06-30 | 2017-07-14 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070451 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-06-30 | 2017-08-04 | Yes |  |  | DELIV-FUN-220.Solution Design Document (SDD) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070452 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Data Definition Documents (DDD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | Yes |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Future Task | 2017-04-17 | 2017-05-05 | 1 | Revise DDDs - Division review | 1000 D1-1200 A-1213 Revise DDDs - Division review | 10 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070453 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-06-30 | 2017-08-04 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-19 | 2017-06-30 | 1 | Cycle 2 Config | 1000 D1-1300 B-1318 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070454 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2017-08-07 | 2017-08-25 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 4.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 44 | 0 | 0 | 0 | 0
1070455 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 5h | 5h | 2017-08-04 | 2017-08-11 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 5 | 33.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070456 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-08-14 | 2017-08-18 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0
1070457 | No | No | Yes | SDF | SDF Localisation | 04-Test | Regression - Manage defects (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | Yes |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070458 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-08-04 | 2017-08-11 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 5 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070459 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070460 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Support (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070461 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-21 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070462 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 44h | 16h | 60h | 2017-07-31 | 2017-09-01 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 20 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070463 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070464 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-10-09 | 2017-10-09 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070465 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-10-10 | 2017-10-13 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070466 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070467 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 35h | 35h | 2017-08-18 | 2017-09-15 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | -8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070468 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 configuration (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070469 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Report (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2017-08-14 | 2017-09-08 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 55 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070470 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 35h | 0h | 35h | 2017-09-05 | 2017-09-08 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0
1070471 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Materials-Work Instructions/Job aids (Design/Build) | CM | CM | SI | Onshore | Goel; Ronika | IBM | Yes | OpEx | Localization | IT - External | 558h | 45h | 603h | 2017-06-12 | 2017-09-21 | Yes |  |  | DELIV-CM-451.Work Instructions | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 10 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 27 | 27 | 45 | 45 | 54 | 45 | 27 | 18 | 45 | 45 | 45 | 45 | 0
1070472 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | DM TAI SDF Dev Installation and Configuration - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 95h | 0h | 95h | 2017-03-27 | 2017-04-24 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-01 | 2017-05-05 | 1 | Data Construction | 1000 D1-1200 A-1214 Data Construction | -35 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 37 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070473 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) - Deploy1 - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 218h | 0h | 218h | 2017-05-01 | 2017-06-02 | Yes |  |  | DELIV-MDG-206.Functional Specification -Conversion | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | -20 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 56 | 44 | 30 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070474 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Data collection templates (DCT) - Explain and collect - Deploy1 - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 26.5h | 0h | 26.5h | 2017-05-01 | 2017-05-26 | Yes |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.5 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070475 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Prepare Mock1 - Deploy1 - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 87h | 0h | 87h | 2017-05-01 | 2017-06-08 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 5 | 15 | 18 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070476 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 56h | 0h | 56h | 2017-04-17 | 2017-04-28 | Yes |  |  | ACT-MDG.MDG - Workshop | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070477 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Data conversion plan - MDG - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 80h | 0h | 80h | 2017-04-10 | 2017-04-24 | Yes |  |  | DELIV-MDG-201.Data Conversion Plan | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070478 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Mock1 Preparation - Deploy1 - CG - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-04 | 2017-07-04 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070479 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Mock1 Validation - Deploy1 - CG- DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-05 | 2017-07-05 | Yes |  |  | ACT-MDG.Mock Validation | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070480 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Mock Load - Deploy1 - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-26 | 2017-07-26 | Yes |  |  | ACT-MDG.Mock Load | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070481 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Data Validation Sheets - Deploy1 - Test - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 63.5h | 0h | 63.5h | 2017-06-12 | 2017-07-07 | Yes |  |  | WP-MDG.Data Validation Sheets | Complete | 2017-06-05 | 2017-06-16 | 1 | QE2 Prevalidation | 1000 D1-1300 B-1325 QE2 Prevalidation | -1 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 10 | 24 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070482 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy1 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 82h | 0h | 82h | 2017-06-12 | 2017-07-21 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 14 | 0 | 0 | 15 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070483 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy1 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 58h | 0h | 58h | 2017-06-12 | 2017-07-28 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 10 | 10 | 3 | 10 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070484 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy1 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 84h | 0h | 84h | 2017-06-13 | 2017-07-21 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 25 | 26 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070485 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy1 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 82h | 0h | 82h | 2017-06-19 | 2017-07-28 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 30 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 25 | 0 | 10 | 8 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070486 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) - Deploy2 (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 7.5h | 0h | 7.5h | 2017-07-31 | 2017-08-25 | Yes |  |  | DELIV-MDG-206.Functional Specification -Conversion | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 45 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 1.25 | 1.25 | 2.5 | 0 | 0 | 0 | 0
1070487 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Mapping Document - Deploy2 (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 19.25h | 0h | 19.25h | 2017-07-31 | 2017-08-25 | Yes |  |  | DELIV-MDG-207.Functional Mapping Document | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.5 | 1.25 | 1.25 | 1.25 | 0 | 0 | 0 | 0
1070488 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 15h | 15h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070489 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 15h | 15h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070490 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 15h | 15h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070491 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy2 (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 38.25h | 0h | 38.25h | 2017-07-24 | 2017-08-25 | Yes |  |  | ACT-MDG.Build ETL programs | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 1.25 | 22 | 0 | 0 | 0 | 0
1070492 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 29h | 0h | 29h | 2017-07-24 | 2017-08-04 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070493 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 40h | 0h | 40h | 2017-07-24 | 2017-08-18 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 30 | 0 | 0 | 0 | 0 | 0
1070494 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 51h | 0h | 51h | 2017-07-24 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 22.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 15 | 0 | 0 | 0 | 5 | 21 | 0 | 0
1070495 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 55h | 9h | 64h | 2017-07-24 | 2017-09-12 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 33.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 24 | 8 | 0 | 0 | 16 | 0 | 0
1070496 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 15h | 15h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070497 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 10h | 0h | 10h | 2017-07-31 | 2017-09-06 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-07-31 | 2017-08-11 | 2 | QE2 Mock Prep | 20000 D2-20100 B-20110 QE2 Mock Prep | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 1.25 | 0 | 1.25 | 3 | 2 | 0 | 0
1070498 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 21.25h | 0h | 21.25h | 2017-07-31 | 2017-09-05 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1.25 | 10 | 3 | 2 | 0 | 0
1070499 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 11h | 0h | 11h | 2017-07-31 | 2017-09-07 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 1.25 | 0 | 1.25 | 3 | 3 | 0 | 0
1070500 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 17.25h | 4h | 21.25h | 2017-07-31 | 2017-09-11 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.25 | 0 | 10 | 4 | 2 | 0 | 0
1070501 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Validation - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 35h | 35h | 2017-09-18 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070502 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Execute - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 35h | 35h | 2017-09-18 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 0.13 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070503 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Preparation - Deploy2 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 35h | 35h | 2017-09-18 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070504 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy1 - HC - (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 80h | 80h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070505 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070506 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070507 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070508 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070509 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Manage Defect - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 35h | 35h | 2017-09-18 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 0.13 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070510 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 70h | 70h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 5 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070511 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 70h | 70h | 2017-11-13 | 2018-01-02 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070512 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 70h | 70h | 2017-11-13 | 2018-01-02 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070513 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 70h | 70h | 2017-11-13 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070514 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy2 - HC - (Saputo) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 160h | 160h | 2018-02-05 | 2018-03-02 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | -18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070515 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy2 - HC - (Accenture) - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2018-02-05 | 2018-03-02 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | -17.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070516 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070517 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070518 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070519 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-22 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070520 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -50 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070521 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -4.88 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070522 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 65h | 65h | 2017-10-30 | 2017-12-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070523 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 55h | 55h | 2017-10-30 | 2017-12-07 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 0 | 18.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070524 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 110h | 110h | 2017-09-08 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070525 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 75h | 75h | 2017-09-08 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070526 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-09-11 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070527 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-09-08 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070528 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 58h | 0h | 58h | 2017-08-14 | 2017-08-18 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 14.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 0 | 0 | 0 | 0
1070529 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 32h | 5h | 37h | 2017-09-05 | 2017-09-15 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0
1070530 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 93h | 0h | 93h | 2017-08-21 | 2017-09-01 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 45 | 0 | 0 | 0
1070531 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-19 | 2017-06-30 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 30 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070532 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-21 | 2017-07-28 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070533 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-24 | 2017-07-28 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070534 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 55h | 0h | 55h | 2017-07-31 | 2017-08-11 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-07-31 | 2017-08-11 | 2 | QE2 Mock Prep | 20000 D2-20100 B-20110 QE2 Mock Prep | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 15 | 0 | 0 | 0 | 0 | 0 | 0
1070535 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2017-07-17 | 2017-07-28 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 15 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070536 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 50h | 50h | 2017-10-30 | 2017-12-01 | Yes |  |  |  | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | -25 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070537 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | Hypercare-Provide end User Support - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 160h | 160h | 2018-02-05 | 2018-03-30 | Yes |  |  |  | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070538 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT 1-Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 45h | 45h | 2017-09-18 | 2017-10-06 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070539 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT 2-Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 30h | 30h | 2017-10-09 | 2017-10-27 | Yes |  |  |  | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070540 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Preparation - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 30h | 30h | 60h | 2017-08-28 | 2017-09-13 | Yes |  |  |  | Future Task | 2017-08-21 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 0 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 0 | 0
1070541 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Support - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 220h | 220h | 2017-12-04 | 2018-02-16 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-11-03 | 2 | Training Material Localization | 20000 D2-29000 MultiPhases-29040 Training Material Localization | 55 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070542 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | Hypercare-Provide end User Support - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 180h | 180h | 2017-10-02 | 2017-12-01 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070543 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover Suport - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 30h | 30h | 2017-09-11 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070544 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover Prepare - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 3h | 5h | 8h | 2017-08-30 | 2017-09-15 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -15 | -8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
1070545 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-25 | 2017-09-01 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | -5 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070546 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT 2 - Run Tests - MDGM - Deploy1 - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | CapEx | Localization | IT - Internal | 88h | 0h | 88h | 2017-08-07 | 2017-08-25 | Yes |  |  | ACT-MDG.Execute SIT | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 1.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 18 | 40 | 0 | 0 | 0 | 0
1070547 | No | No | Yes | SDF | SDF Localisation | 04-Test | KT-DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 32h | 0h | 32h | 2017-08-07 | 2017-08-17 | Yes |  |  |  | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 22 | 0 | 0 | 0 | 0 | 0
1070548 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTP) - Deploy2 | PTP | FUN | SI | Onshore | Deng; Roy | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-09-11 | 2017-09-22 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 20 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070549 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | MCP Mini config and masterdata for US and Canada | PTP | FUN | SI | Onshore | Deng; Roy | IBM | Yes | CapEx | Localization | IT - External | 74h | 170h | 244h | 2017-01-23 | 2017-10-27 | Yes |  |  | ACT-FUN.Configuration | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070550 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Deng; Roy | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-08-07 | 2017-08-18 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070551 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Deng; Roy | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2017-09-05 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070552 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Deng; Roy | IBM | Yes | CapEx | Localization | IT - External | 36h | 24h | 60h | 2017-09-05 | 2017-09-26 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0
1070553 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Deng; Roy | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070554 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTP) - Deploy2 | PTP | FUN | SI | Onshore | Deng; Roy | IBM | Yes | CapEx | Localization | IT - External | 44h | 26h | 70h | 2017-08-28 | 2017-10-10 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | -50 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0
1070555 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTP) - Deploy2 | PTP | FUN | SI | Onshore | Deng; Roy | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070556 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTP) - Deploy2 | PTP | FUN | SI | Onshore | Deng; Roy | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070557 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTP) - Deploy2 | PTP | FUN | SI | Onshore | Deng; Roy | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070558 | No | Yes | No | SDF | SDF Interim State Project | 02-Analyze | Workshop-QI management and held product | OTC | FUN | SI | Onshore | Dodds; Elaine | IBM | Yes | CapEx | Localization | IT - External | 46h | 0h | 46h | 2017-03-01 | 2017-04-04 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 15 | 18 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070559 | No | Yes | No | SDF | SDF Interim State Project | 02-Analyze | Workshop-Batch handling | OTC | FUN | SI | Onshore | Dodds; Elaine | IBM | Yes | CapEx | Localization | IT - External | 110h | 0h | 110h | 2017-03-10 | 2017-04-04 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 26 | 44 | 27 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070560 | No | Yes | No | SDF | SDF Interim State Project | 03-Design/Build | ILOG012-DEV FUT-INT-STO interface | OTC | FUN | SI | Onshore | Dodds; Elaine | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-23 | 2017-06-23 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-08-18 | 0 | NA Others | 99000-99100-99130 NA others | -15.88 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070561 | No | Yes | No | SDF | SDF Interim State Project | 03-Design/Build | ILOG013-DEV FUT-INT-STO goods issue interface (SAP to BPCS) | OTC | FUN | SI | Onshore | Dodds; Elaine | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-26 | 2017-05-26 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-08-18 | 0 | NA Others | 99000-99100-99130 NA others | -40 | -40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070562 | No | Yes | No | SDF | SDF Interim State Project | 03-Design/Build | ILOG015-DEV FUT-INT-Inventory adjustment interface | OTC | FUN | SI | Onshore | Dodds; Elaine | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-06 | 2017-06-06 | Yes |  |  | ACT-FUN.Execute FUT | Complete | 2017-07-17 | 2017-08-18 | 0 | NA Others | 99000-99100-99130 NA others | -30 | -35.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070563 | No | Yes | No | SDF | SDF Interim State Project | 02-Analyze | SDF Interim State-Workshop-Production receipts and inventory adjustments | OTC | FUN | SI | Onshore | Dodds; Elaine | IBM | Yes | CapEx | Localization | IT - External | 51h | 0h | 51h | 2017-02-28 | 2017-04-03 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 21 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070564 | No | Yes | No | SDF | SDF Interim State Project | 03-Design/Build | ILOG015-FSD-INT-Inventory adjustment interface | OTC | FUN | SI | Onshore | Dodds; Elaine | IBM | Yes | CapEx | Localization | IT - External | 61h | 0h | 61h | 2017-02-10 | 2017-02-27 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -88 | -50 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 44 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070565 | No | Yes | No | SDF | SDF Interim State Project | 03-Design/Build | ILOG013-FSD-INT-STO goods issue interface (SAP to BPCS) | OTC | FUN | SI | Onshore | Dodds; Elaine | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-01-24 | 2017-02-09 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -89 | -50 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070566 | No | Yes | No | SDF | SDF Interim State Project | 02-Analyze | SDF Interim - Conduct requirements/Workshops | OTC | FUN | SI | Onshore | Dodds; Elaine | IBM | Yes | CapEx | Localization | IT - External | 235h | 0h | 235h | 2016-12-12 | 2017-01-20 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 24 | 35 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070567 | No | Yes | No | SDF | SDF Interim State Project | 02-Analyze | Contruct RTM | OTC | FUN | SI | Onshore | Dodds; Elaine | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070568 | No | Yes | No | SDF | SDF Interim State Project | 02-Analyze | Create BPML | OTC | FUN | SI | Onshore | Dodds; Elaine | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  | DELIV-BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070569 | No | Yes | No | SDF | SDF Interim State Project | 02-Analyze | Log Gaps | OTC | FUN | SI | Onshore | Dodds; Elaine | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-12-05 | 2016-12-09 | Yes |  |  | WP-FUN.Gap Definition | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070570 | No | Yes | No | SDF | SDF Interim State Project | 02-Analyze | Conduct Design Workshops | OTC | FUN | SI | Onshore | Dodds; Elaine | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070571 | No | Yes | No | SDF | SDF Interim State Project | 02-Analyze | Perform Gap Resolution | OTC | FUN | SI | Onshore | Dodds; Elaine | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070572 | No | Yes | No | SDF | SDF Interim State Project | 03-Design/Build | ILOG012-FSD-INT-STO interface | OTC | FUN | SI | Onshore | Dodds; Elaine | IBM | Yes | CapEx | Localization | IT - External | 125h | 0h | 125h | 2017-01-23 | 2017-04-07 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -90 | -30.88 | 0 | 0 | 0 | 0 | 44 | 44 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070573 | No | Yes | No | SDF | SDF Interim State Project | 03-Design/Build | ILOG013-STO goods issue interface (SAP to BPCS) | OTC | FUN | SI | Onshore | Dodds; Elaine | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-03-31 | 2017-04-03 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -95 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070574 | No | Yes | No | SDF | SDF Interim State Project | 03-Design/Build | IOTC010-FSD-INT-Sales order interface | OTC | FUN | SI | Onshore | Dodds; Elaine | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-03-30 | 2017-04-03 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -90 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070575 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) - Deploy1 - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-02 | 2017-06-02 | Yes |  |  | DELIV-MDG-206.Functional Specification -Conversion | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | -20 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070576 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Prepare Mock1 - Deploy1 - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-02 | 2017-06-02 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070577 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) - Deploy2 (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 6h | 6h | 2017-07-31 | 2017-09-01 | Yes |  |  | DELIV-MDG-206.Functional Specification -Conversion | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 45 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070578 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy1 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-21 | 2017-07-28 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070579 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy1 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-21 | 2017-07-28 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 30 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070580 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy1 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-21 | 2017-07-28 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070581 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Mapping Document - Deploy2 (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 6h | 6h | 2017-07-31 | 2017-09-01 | Yes |  |  | DELIV-MDG-207.Functional Mapping Document | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070582 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Preparation - Deploy2 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 35h | 35h | 2017-09-18 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070583 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Execute - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 35h | 35h | 2017-09-18 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 0.13 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070584 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Validation - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 35h | 35h | 2017-09-18 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070585 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 6h | 6h | 2017-08-25 | 2017-09-01 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070586 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 6h | 6h | 2017-08-28 | 2017-09-01 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070587 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 6h | 6h | 2017-08-28 | 2017-09-01 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070588 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 6h | 6h | 2017-08-28 | 2017-09-01 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-07-31 | 2017-08-11 | 2 | QE2 Mock Prep | 20000 D2-20100 B-20110 QE2 Mock Prep | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070589 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 104h | 0h | 104h | 2017-08-14 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 33.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 0 | 0 | 30 | 0 | 0
1070590 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 46h | 0h | 46h | 2017-08-07 | 2017-08-14 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0
1070591 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 55.5h | 0h | 55.5h | 2017-08-21 | 2017-08-25 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 22.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55.5 | 0 | 0 | 0 | 0
1070592 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 37.5h | 0h | 37.5h | 2017-07-24 | 2017-08-04 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070593 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy1 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-21 | 2017-07-28 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070594 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy2 (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-24 | 2017-07-28 | Yes |  |  | ACT-MDG.Build ETL programs | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070595 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 10h | 10h | 2017-09-15 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070596 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 43.5h | 5h | 48.5h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43.5 | 0
1070597 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 10h | 10h | 2017-09-15 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070598 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 10h | 10h | 2017-09-15 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070599 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy1 - HC - (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 80h | 80h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070600 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 70h | 70h | 2017-11-13 | 2018-01-04 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070601 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 72h | 72h | 2017-11-13 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070602 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 70h | 70h | 2017-11-13 | 2018-01-04 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070603 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 70h | 70h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 5 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070604 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Manage Defect - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 35h | 35h | 2017-09-18 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 0.13 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070605 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070606 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070607 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070608 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070609 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy2 - HC - (Saputo) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 160h | 160h | 2018-02-05 | 2018-03-02 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | -18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070610 | No | No | Yes | SDF | SDF Localisation | 99-Global | Data Cleansing - DG | MDG | DG | Saputo | Onshore | Lentz; Jared | Saputo | Yes | OpEx | Localization | IT - Internal | 20h | 28h | 48h | 2017-07-17 | 2017-12-22 | Yes |  |  | DELIV-MDG-050.Data Profiling | Future Task | NA | NA | 9 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070611 | No | No | Yes | SDF | SDF Localisation | 99-Global | Data Profiling (Saputo) - DG | MDG | DG | Saputo | Onshore | Lentz; Jared | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | Yes |  |  | DELIV-MDG-050.Data Profiling | Complete | NA | NA | 9 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070612 | No | No | Yes | SDF | SDF Localisation | 99-Global | Data quality - DG | MDG | DG | Saputo | Onshore | Lentz; Jared | Saputo | Yes | OpEx | Localization | IT - Internal | 237h | 568h | 805h | 2017-07-24 | 2017-12-26 | Yes |  |  | DELIV-MDG-101.Data Governance Policies & Quality | Future Task | NA | NA | 9 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 40 | 40 | 40 | 40 | 32 | 40 | 0
1070613 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Data profiling - DG | MDG | DG | Saputo | Onshore | Lentz; Jared | Saputo | Yes | OpEx | Localization | IT - Internal | 89h | 0h | 89h | 2017-02-13 | 2017-04-21 | Yes |  |  | DELIV-MDG-050.Data Profiling | Complete | 2017-05-01 | 2017-05-05 | 1 | Data Construction | 1000 D1-1200 A-1214 Data Construction | -55 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 28 | 15 | 6 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070614 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Data Cleansing - (Preparation) - DG | MDG | DG | Saputo | Onshore | Lentz; Jared | Saputo | Yes | OpEx | Localization | IT - Internal | 32h | 0h | 32h | 2017-02-13 | 2017-06-08 | Yes |  |  | DELIV-MDM-110.Data Cleansing and Migration Approach | Complete | 2017-05-01 | 2017-05-05 | 1 | Data Construction | 1000 D1-1200 A-1214 Data Construction | -55 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070615 | No | Yes | No | SDF | SDF Localisation | 99-Global | Team Lead - MDG - DM | MDG | DM | SI | Onshore | Gireesh; Mangeshi | Accenture | Yes | OpEx | Localization | IT - External | 152h | 0h | 152h | 2017-07-04 | 2017-07-28 | Yes |  |  | DELIV-FUN-029.Site Assessment | On Schedule | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070616 | No | Yes | No | SDF | SDF Localisation | 04-Test | Test - Material Master - SI - Deploy1 - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-21 | 2017-07-21 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070617 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | D&B - Material Master - SI - Deploy1 - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-07 | 2017-07-07 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-06-09 | 1 | Build and adjust conversion programs | 1000 D1-1300 B-1322 Build and adjust conversion programs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070618 | No | Yes | No | SDF | SDF Interim State Project | 02-Analyze | Conduct Design Workshops | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070619 | No | Yes | No | SDF | SDF Interim State Project | 02-Analyze | Perform Gap Resolution | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2016-12-05 | 2016-12-16 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070620 | No | Yes | No | SDF | SDF Interim State Project | 02-Analyze | SDF Interim - Conduct requirements Workshops | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 160h | 0h | 160h | 2016-12-19 | 2017-01-20 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 36 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070621 | No | Yes | No | SDF | SDF Interim State Project | 02-Analyze | SDF Interim - Contruct RTM | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-20 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070622 | No | Yes | No | SDF | SDF Interim State Project | 02-Analyze | SDF Interim - Create BPML | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | DELIV-BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070623 | No | Yes | No | SDF | SDF Interim State Project | 02-Analyze | Log Gaps | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  | WP-FUN.Gap Definition | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070624 | No | Yes | No | SDF | SDF Interim State Project | 03-Design/Build | IOTC010-DEV FUT-INT-Sales order interface | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-18 | 2017-07-18 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | 5 | 35.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070625 | No | Yes | No | SDF | SDF Interim State Project | 03-Design/Build | IOTC010-FSD-INT-Sales order interface | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 68h | 0h | 68h | 2017-01-23 | 2017-02-10 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -90 | -10 | 0 | 0 | 0 | 0 | 24 | 24 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070626 | No | Yes | No | SDF | SDF Interim State Project | 03-Design/Build | ILOG013-STO goods issue interface (SAP to BPCS) | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | Yes |  |  | ACT-FUN.Execute FUT | Complete | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | -9 | -28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070627 | No | Yes | No | SDF | SDF Interim State Project | 03-Design/Build | ILOG013-STO goods issue interface (SAP to BPCS) | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 64h | 0h | 64h | 2017-01-23 | 2017-02-10 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -95 | -25 | 0 | 0 | 0 | 0 | 20 | 20 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070628 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing WRICEFs (Design/Build) | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-06-30 | 2017-11-03 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -88 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070629 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | CapEx | Localization | IT - External | 181h | 102h | 283h | 2017-02-13 | 2017-10-31 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 9 | 0 | 9 | 19 | 20 | 34 | 45 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 6 | 0 | 0 | 0 | 0
1070630 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070631 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | CapEx | Localization | IT - External | 0h | 150h | 150h | 2017-10-09 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070632 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | CapEx | Localization | IT - External | 0h | 115h | 115h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070633 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | CapEx | Localization | IT - External | 92h | 0h | 92h | 2017-08-28 | 2017-09-13 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 26 | 21 | 0
1070634 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy1 (Design/Build) | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | CapEx | Localization | IT - External | 271h | 0h | 271h | 2017-06-27 | 2017-08-11 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 31 | 40 | 45 | 45 | 45 | 36 | 0 | 0 | 0 | 0 | 0 | 0
1070635 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | CapEx | Localization | IT - External | 43h | 16h | 59h | 2017-06-27 | 2017-09-19 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 24 | 0
1070636 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070637 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | CapEx | Localization | IT - External | 50h | 0h | 50h | 2017-08-14 | 2017-08-24 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 30 | 0 | 0 | 0 | 0
1070638 | No | No | Yes | SDF | SDF Localisation | 99-Global | Project Support | SEC | SEC | SI | Offshore | Olvida; Julio | Accenture | Yes | CapEx | Localization | IT - External | 0h | 360h | 360h | 2017-08-25 | 2017-10-27 | Yes |  |  |  | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070639 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Interface (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 106h | 0h | 106h | 2017-06-07 | 2017-08-03 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 7 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 35 | 0 | 0 | 0 | 4 | 0 | 39 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070640 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 0h | 77h | 77h | 2017-09-05 | 2017-09-18 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070641 | No | No | Yes | SDF | SDF Localisation | 04-Test | Regression - Run Tests (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 59h | 0h | 59h | 2017-08-07 | 2017-08-24 | Yes |  |  | ACT-FUN.Execute Regression Test | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 9.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 22 | 28 | 0 | 0 | 0 | 0
1070642 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2017-08-07 | 2017-08-18 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 13.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 15 | 0 | 0 | 0 | 0 | 0
1070643 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 87h | 0h | 87h | 2017-08-07 | 2017-09-01 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 9.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 3 | 14 | 39 | 0 | 0 | 0
1070644 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 65h | 0h | 65h | 2017-07-26 | 2017-08-04 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070645 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 0h | 33.25h | 33.25h | 2017-08-30 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070646 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 6h | 4h | 10h | 2017-08-28 | 2017-09-15 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
1070647 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 120h | 0h | 120h | 2017-07-03 | 2017-07-26 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Complete | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | 5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 39 | 36 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070648 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 61h | 0h | 61h | 2017-05-31 | 2017-07-21 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | -14 | 72.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 19 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070649 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 11h | 0h | 11h | 2017-07-05 | 2017-07-21 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 15 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070650 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 0h | 15h | 15h | 2017-09-05 | 2017-09-22 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070651 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070652 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070653 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 configuration (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 0h | 10h | 10h | 2017-08-14 | 2017-09-15 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | 35 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070654 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 configuration (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 0h | 2h | 2h | 2017-09-05 | 2017-09-15 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070655 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Enhancement (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 0h | 14h | 14h | 2017-09-05 | 2017-09-15 | Yes |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070656 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 0h | 15h | 15h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070657 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-10-16 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070658 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 0h | 75h | 75h | 2017-09-18 | 2017-10-13 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070659 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 0h | 79h | 79h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070660 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-25 | 2017-10-13 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070661 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | WPB Recordings - RTR - Deploy1 | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 0h | 12h | 12h | 2017-07-04 | 2017-07-06 | Yes |  |  | DELIV-FUN-403.WPB Recordings | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070662 | No | Yes | No | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | SI | Offshore | Kumar; Bijendra | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-28 | 2016-12-28 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070663 | No | Yes | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing WRICEFs (Design/Build) | DEV | DEV | SI | Offshore | Kumar; Bijendra | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-11 | 2017-01-11 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -88 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070664 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 configuration (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-07-31 | 2017-08-11 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | 25 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070665 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070666 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | RTM - LOG | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2017-04-17 | 2017-04-23 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070667 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Support (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-07-05 | 2017-07-07 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070668 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070669 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070670 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070671 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-10-01 | 2017-10-01 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070672 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-06-30 | 2017-08-11 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-19 | 2017-06-30 | 1 | Cycle 2 Config | 1000 D1-1300 B-1318 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070673 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 96h | 0h | 96h | 2017-07-31 | 2017-08-11 | Yes |  |  | DELIV-FUN-220.Solution Design Document (SDD) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 44 | 0 | 0 | 0 | 0 | 0 | 0
1070674 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 15h | 30h | 45h | 2017-06-26 | 2017-08-11 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070675 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-06-19 | 2017-06-23 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070676 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 80h | 12h | 92h | 2017-08-28 | 2017-09-15 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | -8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 36 | 0 | 0
1070677 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0h | 120h | 120h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070678 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0h | 120h | 120h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070679 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0h | 10h | 10h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070680 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0h | 15h | 15h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070681 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Support Mock1 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 44h | 40h | 84h | 2017-08-21 | 2017-09-15 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-09-25 | 2017-10-06 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -25 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0
1070682 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-08-14 | 2017-08-18 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0
1070683 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Support (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070684 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0h | 32h | 32h | 2017-08-07 | 2017-08-11 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 4.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070685 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070686 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070687 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 30h | 60h | 90h | 2017-07-31 | 2017-08-10 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070688 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-08-07 | 2017-08-18 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 40 | 0 | 0 | 0 | 0 | 0
1070689 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 120h | 120h | 2017-09-25 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070690 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070691 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 125h | 125h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070692 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 configuration (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 20h | 4h | 24h | 2017-08-03 | 2017-08-08 | Yes |  |  | ACT-FUN.Management | Future Task | 2017-06-19 | 2017-06-30 | 1 | Cycle 2 Config | 1000 D1-1300 B-1318 Cycle 2 Config | 10 | 26.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070693 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Configuration - PTM - Deploy1 | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-07-03 | 2017-07-07 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070694 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-06-05 | 2017-07-20 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | -15 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070695 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-08-28 | 2017-09-08 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070696 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 45h | 16h | 61h | 2017-08-28 | 2017-09-08 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0
1070697 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 60h | 0h | 60h | 2017-07-21 | 2017-07-28 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070698 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 50h | 13.33h | 63.33h | 2017-08-21 | 2017-09-08 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 17.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0
1070699 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 53h | 0h | 53h | 2017-07-10 | 2017-07-16 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | 5 | 29.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070700 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-11 | 2017-09-29 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 15 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070701 | No | No | Yes | SDF | SDF Interim State Project | 01-Preparation | Environment setup | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070702 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 108h | 0h | 108h | 2017-05-22 | 2017-06-23 | Yes |  |  | ACT-FUN.Management | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 45 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070703 | No | No | Yes | SDF | SDF Localisation | 99-Global | Deliver Training to UAT Testers (Test) | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT-CM.Deliver Training to UAT Testers | Complete | 2017-08-14 | 2017-09-01 | 1 | UAT Training | 1000 D1-1800 MultiPhases-1870 UAT Training | -35 | -30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070704 | No | No | Yes | SDF | SDF Localisation | 99-Global | Technical training (Test) | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | OpEx | Localization | IT - Internal | 8h | 1h | 9h | 2017-07-24 | 2017-07-28 | Yes |  |  | ACT-CM.Execute Train the Trainer | Future Task | 2017-07-17 | 2017-07-28 | 1 | Train the trainer | 1000 D1-1800 MultiPhases-1840 Train the trainer | -4.13 | 11.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070705 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Materials-Training materials translation (Design/Build) | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | OpEx | Localization | IT - Internal | 4h | 45.65h | 49.65h | 2017-06-12 | 2017-10-19 | Yes |  |  | DELIV-CM-401.Training Materials | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 10 | 58.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070706 | No | No | Yes | SDF | SDF Localisation | 99-Global | Deliver Training to End Users | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 20h | 20h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-CM.Deliver Training to End Users | Future Task | 2017-07-31 | 2017-09-22 | 1 | End User Training | 1000 D1-1800 MultiPhases-1850 End User Training | 45 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070707 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Courses-Create/Update course ppt (Design/Build) | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | OpEx | Localization | IT - Internal | 77h | 0h | 77h | 2017-06-26 | 2017-07-14 | Yes |  |  | DELIV-CM-402.Training Schedule and Logistics | Complete | 2017-06-26 | 2017-07-28 | 1 | Training Schedule | 1000 D1-1800 MultiPhases-1820 Training Schedule | 0 | -8.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070708 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Materials-Traininng Data (exercise book) (Design/Build) | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | OpEx | Localization | IT - Internal | 48h | 219h | 267h | 2017-06-26 | 2017-10-13 | Yes |  |  | DELIV-CM-401.Training Materials | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 20 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 0 | 0 | 35 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0
1070709 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Materials-Concept slides (Design/Build) | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | OpEx | Localization | IT - Internal | 79h | 0h | 79h | 2017-06-19 | 2017-07-07 | Yes |  |  | DELIV-CM-401.Training Materials | Complete | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 15 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070710 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Materials-Concept slides (Localization) (Design/Build) | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | OpEx | Localization | IT - Internal | 1h | 55.22h | 56.22h | 2017-07-03 | 2017-10-24 | Yes |  |  | DELIV-CM-401.Training Materials | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 10 | 61.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070711 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Materials-Concept slides (Interim) (Design/Build) | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 55.52h | 55.52h | 2017-07-04 | 2017-10-24 | Yes |  |  | DELIV-CM-401.Training Materials | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 10 | 61.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070712 | No | No | Yes | SDF | SDF Localisation | 99-Global | Onboard DTC | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 7h | 7h | 2017-06-30 | 2017-07-10 | Yes |  |  | ACT-CM.Management | Future Task | 2017-06-26 | 2017-07-28 | 1 | Training Schedule | 1000 D1-1800 MultiPhases-1820 Training Schedule | -65 | 9.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070713 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF Build/Support (SEC) - Deploy1 | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Localization | IT - External | 0h | 225h | 225h | 2017-07-28 | 2017-08-31 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-05 | 2017-06-23 | 1 | Security Build | 1000 D1-1300 B-1335 Security Build | 20 | 86.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070714 | No | No | Yes | SDF | SDF Localisation | 99-Global | Project Support | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Localization | IT - External | 0h | 495h | 495h | 2017-08-21 | 2017-11-03 | Yes |  |  |  | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070715 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | Saputo | Onshore | Boisvert; Claude MIS | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070716 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | Saputo | Onshore | Boisvert; Claude MIS | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-07 | 2017-08-21 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070717 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | Saputo | Onshore | Boisvert; Claude MIS | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 57h | 57h | 2017-09-01 | 2017-09-29 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070718 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | Saputo | Onshore | Boisvert; Claude MIS | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 120h | 120h | 2017-10-10 | 2017-11-17 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070719 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Break/Fix - DEV | DEV | DEV | Saputo | Onshore | Boisvert; Claude MIS | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0.13 | 5.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070720 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | Saputo | Onshore | Boisvert; Claude MIS | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070721 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT 1 - Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | Saputo | Onshore | Boisvert; Claude MIS | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | Yes |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070722 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | Saputo | Onshore | Boisvert; Claude MIS | Saputo | Yes | CapEx | Localization | IT - Internal | 41h | 0h | 41h | 2017-05-22 | 2017-06-02 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070723 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | WRICEFs - DEV (Design/Build) | DEV | DEV | Saputo | Onshore | Boisvert; Claude MIS | Saputo | Yes | CapEx | Localization | IT - Internal | 90h | 0h | 90h | 2017-06-05 | 2017-06-22 | Yes |  |  | To delete-To delete.To delete | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 15.13 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 35 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070724 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | WRICEFs inventory - DEV | DEV | DEV | Saputo | Onshore | Boisvert; Claude MIS | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | DELIV-DEV-102.RICEFW Inventory | Future Task | NA | NA | 1 | GAPs | 1000 D1-1200 A-1211GAPs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070725 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | Saputo | Onshore | Boisvert; Claude MIS | Saputo | Yes | CapEx | Localization | IT - Internal | 196h | 0h | 196h | 2017-08-07 | 2017-09-14 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 35 | 35 | 28 | 28 | 0
1070726 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | Saputo | Onshore | Boisvert; Claude MIS | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070727 | No | No | Yes | SDF | SDF Localisation | 04-Test | SEC Break/Fix SIT1 - SEC Deploy1 | SEC | SEC | SI | Offshore | Bobiles; CharmaineAnn | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-31 | 2017-08-04 | Yes |  |  | ACT-SEC.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070728 | No | No | Yes | SDF | SDF Localisation | 04-Test | SEC Break/Fix SIT2 - SEC Deploy1 | SEC | SEC | SI | Offshore | Bobiles; CharmaineAnn | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-07 | 2017-08-25 | Yes |  |  | ACT-SEC.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070729 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT- Break/Fix- SEC - Deploy 1 | SEC | SEC | SI | Offshore | Bobiles; CharmaineAnn | Accenture | Yes | CapEx | Localization | IT - External | 29.5h | 120h | 149.5h | 2017-09-01 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 20.5 | 0 | 0
1070730 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - PTM | PTM | FUN | Saputo | Onshore | Turner; Jonathan | Saputo | Yes | CapEx | Localization | Business | 23h | 0h | 23h | 2017-04-17 | 2017-06-22 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 8 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070731 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Log Gaps - PTM | PTM | FUN | Saputo | Onshore | Turner; Jonathan | Saputo | Yes | CapEx | Localization | Business | 27h | 0h | 27h | 2017-04-17 | 2017-06-02 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070732 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTM | PTM | FUN | Saputo | Onshore | Turner; Jonathan | Saputo | Yes | CapEx | Localization | Business | 122h | 0h | 122h | 2017-04-17 | 2017-05-19 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 34 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070733 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTM | PTM | FUN | Saputo | Onshore | Turner; Jonathan | Saputo | Yes | CapEx | Localization | Business | 35h | 0h | 35h | 2017-06-12 | 2017-06-23 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070734 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Turner; Jonathan | Saputo | Yes | CapEx | Localization | Business | 0h | 20h | 20h | 2017-09-05 | 2017-09-08 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070735 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Turner; Jonathan | Saputo | Yes | CapEx | Localization | Business | 0h | 120h | 120h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070736 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Turner; Jonathan | Saputo | Yes | CapEx | Localization | Business | 0h | 360h | 360h | 2017-09-25 | 2017-11-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070737 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support - OTC (HR) - Deploy1 |  | Missing Stream | Saputo | Onshore | Edouard-Jacques; Jennifer | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 4h | 4h | 2017-09-25 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070738 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (HR) - Deploy1 |  | Missing Stream | Saputo | Onshore | Edouard-Jacques; Jennifer | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 54h | 54h | 2017-09-06 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070739 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (HR) - Deploy1 |  | Missing Stream | Saputo | Onshore | Edouard-Jacques; Jennifer | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 36h | 36h | 2017-10-02 | 2017-12-01 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070740 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy2 | PTM | FUN | Saputo | Onshore | Montgomery; David | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-09-05 | 2017-09-18 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 15 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070741 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | DEV FUT-ID-COM-Baseline | OTC | FUN | SI | Onshore | Debasis; Dey | IBM | Yes | CapEx | Localization | IT - External | 0h | 120h | 120h | 2017-02-13 | 2017-09-29 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070742 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Support-D2 | OTC | FUN | SI | Onshore | Debasis; Dey | IBM | Yes | OpEx | Localization | IT - External | 0h | 20h | 20h | 2018-01-03 | 2018-02-02 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-09-18 | 2017-11-03 | 2 | Training Material Localization | 20000 D2-29000 MultiPhases-29040 Training Material Localization | -10 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070743 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Debasis; Dey | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-12-27 | 2018-01-05 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070744 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC032-FSD-Pricing Files | OTC | FUN | SI | Onshore | Debasis; Dey | IBM | Yes | CapEx | Localization | IT - External | 160h | 0h | 160h | 2017-02-13 | 2017-03-09 | Yes |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -80 | -79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070745 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | FOTC005-FSD-Level 0 Notification Form | OTC | FUN | SI | Onshore | Debasis; Dey | IBM | Yes | CapEx | Localization | IT - External | 55h | 0h | 55h | 2017-03-13 | 2017-03-24 | Yes |  |  | DELIV-FUN-204.Functional Specification - Form | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -60 | -41.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070746 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | IOTC005-FSD-Pricing Notification EDI | OTC | FUN | SI | Onshore | Debasis; Dey | IBM | Yes | CapEx | Localization | IT - External | 96h | 0h | 96h | 2017-04-18 | 2017-06-16 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -54 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 25 | 28 | 18 | 5 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070747 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT - OTC- Deploy2 | OTC | FUN | SI | Onshore | Debasis; Dey | IBM | Yes | CapEx | Localization | IT - External | 48h | 0h | 48h | 2017-06-05 | 2017-07-06 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 9 | 0 | 10 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070748 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Debasis; Dey | IBM | Yes | CapEx | Localization | IT - External | 10h | 14.43h | 24.43h | 2017-06-23 | 2017-07-14 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070749 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Debasis; Dey | IBM | Yes | CapEx | Localization | IT - External | 16h | 6.05h | 22.05h | 2017-06-26 | 2017-09-01 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-21 | 2017-09-01 | 2 | AT | 20000 D2-20100 B-20180 AT | -45 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0
1070750 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (OTC) - Deploy1 | OTC | FUN | SI | Onshore | Debasis; Dey | IBM | Yes | CapEx | Localization | IT - External | 42h | 38.8h | 80.8h | 2017-08-14 | 2017-09-07 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 34 | 0 | 0 | 0
1070751 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Debasis; Dey | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-10 | 2017-07-14 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070752 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | FOTC006-FSD-Level 2 Notification Form | OTC | FUN | SI | Onshore | Debasis; Dey | IBM | Yes | CapEx | Localization | IT - External | 66h | 0h | 66h | 2017-03-27 | 2017-05-10 | Yes |  |  | DELIV-FUN-204.Functional Specification - Form | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -45 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 12 | 5 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070753 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | FOTC006-DEV FUT-Level 2 Notification Form | OTC | FUN | SI | Onshore | Debasis; Dey | IBM | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2017-08-14 | 2017-08-25 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | 38 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0
1070754 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC032-DEV FUT-Pricing Files | OTC | FUN | SI | Onshore | Debasis; Dey | IBM | Yes | CapEx | Localization | IT - External | 77h | 32h | 109h | 2017-05-15 | 2017-07-18 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | -30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 18 | 0 | 13 | 30 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070755 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC033-FSD-Pricing Cockpit | OTC | FUN | SI | Onshore | Debasis; Dey | IBM | Yes | CapEx | Localization | IT - External | 49h | 0h | 49h | 2017-03-06 | 2017-03-23 | Yes |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -65 | -71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 5 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070756 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC3513-DEV FUT-Pricing Cockpit | OTC | FUN | SI | Onshore | Debasis; Dey | IBM | Yes | CapEx | Localization | IT - External | 27h | 16h | 43h | 2017-05-11 | 2017-07-21 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | -15 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 2 | 6 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070757 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 40h | 40h | 2017-08-29 | 2017-09-20 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070758 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 40h | 40h | 2017-08-29 | 2017-09-20 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070759 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-07-21 | 2017-08-04 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070760 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | CapEx | Localization | IT - Internal | 41.5h | 48.5h | 90h | 2017-08-07 | 2017-09-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 18 | 2.5 | 0 | 0 | 0 | 0
1070761 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 40h | 40h | 2017-07-21 | 2017-08-04 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070762 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-08-15 | 2017-09-20 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 17.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070763 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | SDF Interim State-Workshop-Supply chain planning | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | CapEx | Localization | IT - Internal | 31h | 0h | 31h | 2017-03-09 | 2017-03-31 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070764 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | Workshop-QI management and held product | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-16 | 2017-02-16 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070765 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - LOG | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | CapEx | Localization | Business | 20h | 0h | 20h | 2017-04-17 | 2017-04-27 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070766 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | RTM - LOG | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | CapEx | Localization | Business | 20h | 0h | 20h | 2017-04-21 | 2017-05-16 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 16 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070767 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | CapEx | Localization | Business | 76h | 0h | 76h | 2017-03-13 | 2017-03-30 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 24 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070768 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | CapEx | Localization | Business | 2h | 0h | 2h | 2017-03-29 | 2017-04-10 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -23 | -19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070769 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070770 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | CapEx | Localization | Business | 12h | 0h | 12h | 2017-04-03 | 2017-04-12 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070771 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy2 | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | CapEx | Localization | Business | 0h | 270h | 270h | 2017-09-18 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070772 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy2 | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | CapEx | Localization | Business | 0h | 135h | 135h | 2017-10-09 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070773 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | SDF Interim State-Workshop-Transportation | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | CapEx | Localization | Business | 52h | 0h | 52h | 2017-03-06 | 2017-03-30 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070774 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Gap Definition | HR | HR | Saputo | Onshore | Merdaoui; Badis | Saputo | Yes | CapEx | Localization | IT - Internal | 40h | 0h | 40h | 2017-05-29 | 2017-06-16 | Yes |  |  | WP-FUN.Gap Definition | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | 1 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 19 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070775 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (HR) - Deploy1 | HR | HR | Saputo | Onshore | Merdaoui; Badis | Saputo | Yes | CapEx | Localization | IT - Internal | 12.5h | 0h | 12.5h | 2017-08-28 | 2017-08-31 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5 | 0 | 0 | 0
1070776 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support - OTC (HR) - Deploy1 | HR | HR | Saputo | Onshore | Merdaoui; Badis | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 5h | 5h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070777 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (HR) - Deploy1 | HR | HR | Saputo | Onshore | Merdaoui; Badis | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 42h | 42h | 2017-09-05 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070778 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (HR) - Deploy1 | HR | HR | Saputo | Onshore | Merdaoui; Badis | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 23h | 23h | 2017-09-05 | 2017-09-29 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070779 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (HR) - Deploy1 | HR | HR | Saputo | Onshore | Merdaoui; Badis | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 7h | 7h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070780 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (HR) - Deploy1 | HR | HR | Saputo | Onshore | Merdaoui; Badis | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 161h | 161h | 2017-10-02 | 2017-12-01 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070781 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (HR) - Deploy1 | HR | HR | Saputo | Onshore | Merdaoui; Badis | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 18h | 18h | 2017-10-02 | 2017-12-01 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070782 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (HR) - Deploy1 | HR | HR | Saputo | Onshore | Merdaoui; Badis | Saputo | Yes | CapEx | Localization | IT - Internal | 12h | 0h | 12h | 2017-07-24 | 2017-08-14 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -20 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
1070783 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (HR) - Deploy1 | HR | HR | Saputo | Onshore | Merdaoui; Badis | Saputo | Yes | CapEx | Localization | IT - Internal | 40h | 0h | 40h | 2017-06-20 | 2017-07-14 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 21.13 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 11 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070784 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Interface (HR) - Deploy1 | HR | HR | Saputo | Onshore | Merdaoui; Badis | Saputo | Yes | CapEx | Localization | IT - Internal | 11h | 0h | 11h | 2017-07-18 | 2017-07-21 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 1 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070785 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070786 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - DEV | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | CapEx | Localization | IT - Internal | 40h | 0h | 40h | 2017-08-28 | 2017-09-01 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0
1070787 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 120h | 120h | 2017-10-10 | 2017-11-17 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070788 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-09-01 | 2017-09-29 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070789 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-18 | 2017-08-25 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070790 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070791 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | CapEx | Localization | IT - Internal | 152h | 0h | 152h | 2017-06-20 | 2017-09-15 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 32 | 40 | 0
1070792 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070793 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | CapEx | Localization | IT - Internal | 74h | 0h | 74h | 2017-02-13 | 2017-06-02 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 20 | 8 | 0 | 0 | 0 | 0 | 0 | 12 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070794 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing WRICEFs (Design/Build) | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-11 | 2017-01-11 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -88 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070795 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT 1 - Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | Yes |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070796 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | WRICEFs inventory - DEV | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-05-26 | 2017-05-26 | Yes |  |  | DELIV-DEV-102.RICEFW Inventory | Future Task | NA | NA | 1 | GAPs | 1000 D1-1200 A-1211GAPs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070797 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | WRICEFs - DEV (Design/Build) | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | CapEx | Localization | IT - Internal | 104h | 0h | 104h | 2017-06-05 | 2017-06-29 | Yes |  |  | To delete-To delete.To delete | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 15.13 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070798 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT 1 - Manage defects (DEV) - Deploy1 (Test) | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | CapEx | Localization | IT - Internal | 40h | 0h | 40h | 2017-07-10 | 2017-07-14 | Yes |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -5 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070799 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Design/Build) | CM | CM | Saputo | Onshore | Lochner; Andrea | Saputo | Yes | OpEx | Localization | IT - Internal | 224h | 0h | 224h | 2017-06-05 | 2017-07-21 | Yes |  |  | ACT-CM.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 41 | 32 | 33 | 38 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070800 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration)- CM(Global) | CM | CM | Saputo | Onshore | Lochner; Andrea | Saputo | Yes | OpEx | Localization | IT - Internal | 243h | 141h | 384h | 2017-07-24 | 2017-10-10 | Yes |  |  | ACT-CM.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 37 | 36 | 46 | 0 | 0 | 35 | 49 | 0
1070801 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Analyze) | CM | CM | Saputo | Onshore | Lochner; Andrea | Saputo | Yes | OpEx | Localization | IT - Internal | 147h | 0h | 147h | 2017-05-08 | 2017-06-02 | Yes |  |  | ACT-CM.Management | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 32 | 34 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070802 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Localized Audience Analysis | CM | CM | Saputo | Onshore | Lochner; Andrea | Saputo | Yes | OpEx | Localization | IT - Internal | 35h | 0h | 35h | 2017-03-20 | 2017-04-07 | Yes |  |  | DELIV-CM-019.Audience Analysis | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070803 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Change Impact Localized | CM | CM | Saputo | Onshore | Lochner; Andrea | Saputo | Yes | OpEx | Localization | IT - Internal | 20h | 0h | 20h | 2017-03-13 | 2017-03-17 | Yes |  |  | DELIV-CM-014.Change Impacts Analysis | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070804 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Localized Business Readiness Plan | CM | CM | Saputo | Onshore | Lochner; Andrea | Saputo | Yes | OpEx | Localization | IT - Internal | 3h | 0h | 3h | 2017-03-20 | 2017-03-23 | Yes |  |  | DELIV-CM-112.Business Readiness plan | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070805 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshops Prep & Execute | CM | CM | Saputo | Onshore | Lochner; Andrea | Saputo | Yes | OpEx | Localization | IT - Internal | 30h | 0h | 30h | 2017-03-20 | 2017-03-24 | Yes |  |  | DELIV-CM-014.Change Impacts Analysis | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070806 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Stakeholder Analysis | CM | CM | Saputo | Onshore | Lochner; Andrea | Saputo | Yes | OpEx | Localization | IT - Internal | 8h | 0h | 8h | 2017-03-20 | 2017-03-31 | Yes |  |  | DELIV-CM-123b.Stakeholder Analysis | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070807 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Stakeholder Map | CM | CM | Saputo | Onshore | Lochner; Andrea | Saputo | Yes | OpEx | Localization | IT - Internal | 20h | 0h | 20h | 2017-03-13 | 2017-03-17 | Yes |  |  | DELIV-CM-123a.Stakeholder Map and Assessment | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070808 | No | No | Yes | SDF | SDF Localisation | 99-Global | SDF-Manage Project | PMO | PMO | SI | Onshore | Nirmal; Anup | IBM | Yes | CapEx | Localization | IT - External | 903h | 0h | 903h | 2017-03-27 | 2017-08-25 | Yes |  |  | ACT-PMO.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 43 | 40 | 44 | 44 | 0 | 44 | 28 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 0 | 0 | 0 | 0
1070809 | No | Yes | No | SDF | SDF Localisation | 04-Test | Test - SIT 1 - Financial Objects - SI - Deploy1 - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | OpEx | Localization | IT - External | 80h | 0h | 80h | 2017-08-14 | 2017-08-25 | Yes |  |  | ACT-FUN.Execute SIT | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0
1070810 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | D&B - Financial Objects - SI - Deploy1 - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-07 | 2017-07-07 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-06-09 | 1 | Build and adjust conversion programs | 1000 D1-1300 B-1322 Build and adjust conversion programs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070811 | No | Yes | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover Prepare - Deploy1 - SI - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2017-08-28 | 2017-08-31 | Yes |  |  |  | Complete | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -15 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0
1070812 | No | Yes | No | SDF | SDF Localisation | 04-Test | Test - SIT 2 - Financial Objects - SI - Deploy1 - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070813 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover - Prepare- SEC - Deploy 1 | SEC | SEC | SI | Onshore | Kothapalli; Omni | Accenture | Yes | CapEx | Localization | IT - External | 0h | 48h | 48h | 2017-08-28 | 2017-09-15 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -15 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070814 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover - Support- SEC - Deploy 1 | SEC | SEC | SI | Onshore | Kothapalli; Omni | Accenture | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-09-18 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070815 | No | No | Yes | SDF | SDF Localisation | 04-Test | SEC Break/Fix SIT2 - SEC Deploy1 | SEC | SEC | SI | Onshore | Kothapalli; Omni | Accenture | Yes | CapEx | Localization | IT - External | 0h | 8h | 8h | 2017-08-25 | 2017-09-08 | Yes |  |  | ACT-SEC.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070816 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | Hypercare-Break/Fix - Deploy1 | SEC | SEC | SI | Onshore | Kothapalli; Omni | Accenture | Yes | CapEx | Localization | IT - External | 0h | 200h | 200h | 2017-10-02 | 2017-11-03 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070817 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF Build/Support (SEC) - Deploy1 | SEC | SEC | SI | Onshore | Kothapalli; Omni | Accenture | Yes | CapEx | Localization | IT - External | 200h | 0h | 200h | 2017-07-31 | 2017-09-01 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-05 | 2017-06-23 | 1 | Security Build | 1000 D1-1300 B-1335 Security Build | 20 | 86.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0
1070818 | No | No | Yes | SDF | SDF Localisation | 99-Global | Create Training Data in trg environment | CM | CM | SI | Offshore | Basak; Dipannita | IBM | Yes | OpEx | Localization | IT - External | 0h | 23.58h | 23.58h | 2017-09-11 | 2017-10-13 | Yes |  |  | DELIV-CM-402.Training Schedule and Logistics | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 12 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070819 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Materials-Work Instructions/Job aids (Design/Build) | CM | CM | SI | Offshore | Basak; Dipannita | IBM | Yes | OpEx | Localization | IT - External | 621h | 0h | 621h | 2017-06-12 | 2017-09-22 | Yes |  |  | DELIV-CM-451.Work Instructions | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 10 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 36 | 45 | 45 | 45 | 54 | 45 | 45 | 36 | 45 | 45 | 45 | 45 | 45
1070820 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTP (Global) | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | CapEx | Localization | IT - External | 254h | 206h | 460h | 2017-07-10 | 2017-10-16 | Yes |  |  | ACT-FUN.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 40 | 40 | 36 | 40 | 40 | 34 | 20 | 0 | 0
1070821 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -22.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070822 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-03-27 | 2017-03-31 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -17 | -12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070823 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - PTP | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-01 | 2017-03-01 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -33 | -35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070824 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTP | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | CapEx | Localization | IT - External | 78h | 0h | 78h | 2017-04-17 | 2017-06-16 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 24 | 4 | 4 | 4 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070825 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | CapEx | Localization | IT - External | 14h | 0h | 14h | 2017-04-10 | 2017-04-12 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -20 | -16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070826 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-04-03 | 2017-04-06 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | -9.88 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070827 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-10 | 2017-04-10 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070828 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTP) - Deploy2 | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-10-09 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070829 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-09-25 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070830 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | CapEx | Localization | IT - External | 26h | 4h | 30h | 2017-08-28 | 2017-09-11 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 16 | 0 | 0
1070831 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  | DMS | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070832 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | DMS GD Fit/Gap - RTR | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-05-02 | 2017-05-15 | Yes |  | DMS | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070833 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | DMS GD Fit/Gap - RTR | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-04-19 | 2017-04-28 | Yes |  | DMS | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -18 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070834 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | DMS Configuration/UT - Costing SDF - RTR - Deploy1 | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | Yes |  | DMS | To delete-To delete.To delete | Complete | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | -5 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070835 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 0h | 16h | 16h | 2017-08-11 | 2017-08-25 | Yes |  | DMS | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 13.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070836 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 0h | 8h | 8h | 2017-08-25 | 2017-09-01 | Yes |  | DMS | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070837 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 configuration (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 0h | 12h | 12h | 2017-08-14 | 2017-09-01 | Yes |  | DMS | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070838 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Strobel; Lars | SAP | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2017-08-16 | 2017-09-03 | Yes |  | DMS | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 13.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 16 | 0 | 0 | 0
1070839 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Strobel; Lars | SAP | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-08-28 | 2017-08-31 | Yes |  | DMS | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0
1070840 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Strobel; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 117.37h | 117.37h | 2017-08-30 | 2017-09-26 | Yes |  | DMS | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070841 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Strobel; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-07-04 | 2017-08-11 | Yes |  | DMS | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 15 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070842 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | DMS Configuration/UT - Costing SDF - RTR - Deploy1 | RTR | FUN | SI | Onshore | Strobel; Lars | SAP | Yes | CapEx | Localization | IT - External | 104h | 0h | 104h | 2017-06-05 | 2017-08-28 | Yes |  | DMS | To delete-To delete.To delete | Complete | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | -5 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 4 | 8 | 12 | 8 | 5 | 7 | 0 | 0 | 0 | 1 | 44 | 0 | 0 | 0 | 0
1070843 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | DMS GD Fit/Gap - RTR | RTR | FUN | SI | Onshore | Strobel; Lars | SAP | Yes | CapEx | Localization | IT - External | 33.6h | 0h | 33.6h | 2017-04-24 | 2017-05-18 | Yes |  | DMS | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -18 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070844 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | DMS Master Data specifications SDF (DDD) - RTR | RTR | FUN | SI | Onshore | Strobel; Lars | SAP | Yes | CapEx | Localization | IT - External | 72h | 0h | 72h | 2017-04-24 | 2017-05-12 | Yes |  | DMS | DELIV-FUN-149.Data Definition Documents (DDD) | Complete | 2017-04-17 | 2017-05-05 | 1 | Revise DDDs - Division review | 1000 D1-1200 A-1213 Revise DDDs - Division review | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 20 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070845 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | DMS GD Fit/Gap - RTR | RTR | FUN | SI | Onshore | Strobel; Lars | SAP | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2017-04-24 | 2017-05-05 | Yes |  | DMS | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070846 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Poggenbeck; Carsten | SAP | Yes | CapEx | Localization | IT - External | 0h | 120h | 120h | 2018-02-05 | 2018-03-30 | Yes |  | DMS | ACT-FUN.Functional Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070847 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Poggenbeck; Carsten | SAP | Yes | CapEx | Localization | IT - External | 0h | 132h | 132h | 2018-01-15 | 2018-01-30 | Yes |  | DMS | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -8 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070848 | No | No | Yes | SDF | SDF Localisation | 04-Test | DR - Support (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Poggenbeck; Carsten | SAP | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-11-20 | 2017-12-01 | Yes |  | DMS | ACT-FUN.Dry Run activities | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070849 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Poggenbeck; Carsten | SAP | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-12-04 | 2017-12-29 | Yes |  | DMS | ACT-FUN.Execute UAT | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070850 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Poggenbeck; Carsten | SAP | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-12-04 | 2017-12-29 | Yes |  | DMS | ACT-FUN.Functional Break/Fix | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070851 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Poggenbeck; Carsten | SAP | Yes | CapEx | Localization | IT - External | 0h | 44h | 44h | 2017-09-25 | 2017-09-29 | Yes |  | DMS | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070852 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Poggenbeck; Carsten | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-25 | 2017-09-25 | Yes |  | DMS | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070853 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Poggenbeck; Carsten | SAP | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-10-02 | 2017-12-15 | Yes |  | DMS | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070854 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Poggenbeck; Carsten | SAP | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-09-11 | 2017-09-22 | Yes |  | DMS | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070855 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Poggenbeck; Carsten | SAP | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-08-28 | 2017-09-22 | Yes |  | DMS | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070856 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | DMS Master Data specifications SDF (DDD) - PTM | PTM | FUN | SI | Onshore | Poggenbeck; Carsten | SAP | Yes | CapEx | Localization | IT - External | 86h | 0h | 86h | 2017-04-17 | 2017-05-18 | Yes |  | DMS | DELIV-FUN-149.Data Definition Documents (DDD) | Complete | 2017-04-17 | 2017-05-05 | 1 | Revise DDDs - Division review | 1000 D1-1200 A-1213 Revise DDDs - Division review | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 28 | 0 | 12 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070857 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | DMS Configuration/UT - Operations - PTM - Deploy1 | PTM | FUN | SI | Onshore | Poggenbeck; Carsten | SAP | Yes | CapEx | Localization | IT - External | 98h | 0h | 98h | 2017-05-29 | 2017-07-23 | Yes |  | DMS | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | -5 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 36 | 22 | 12 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070858 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | DMS Test Preparation - PTM - Deploy1 | PTM | FUN | SI | Onshore | Poggenbeck; Carsten | SAP | Yes | CapEx | Localization | IT - External | 0h | 16h | 16h | 2017-07-24 | 2017-08-04 | Yes |  | DMS | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070859 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | DMS GD Fit/Gap - PTM | PTM | FUN | SI | Onshore | Poggenbeck; Carsten | SAP | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-04-13 | 2017-04-13 | Yes |  | DMS | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070860 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | GRC (SEC) - Deploy1 | SEC | SEC | SI | Offshore | Valencia; Jackie | Accenture | Yes | CapEx | Localization | IT - External | 234.75h | 0h | 234.75h | 2017-07-10 | 2017-08-25 | Yes |  |  | DELIV-SEC-215.SAP Security & GRC Processes | Future Task | 2017-06-05 | 2017-06-23 | 1 | Security Build | 1000 D1-1300 B-1335 Security Build | 25 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 36 | 45 | 27 | 26.5 | 19.25 | 36 | 0 | 0 | 0 | 0
1070861 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SAP Security & GRC Processes (SEC) - Deploy1 | SEC | SEC | SI | Offshore | Valencia; Jackie | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-07-03 | 2017-07-07 | Yes |  |  | DELIV-SEC-215.SAP Security & GRC Processes | Complete | 2017-06-05 | 2017-06-23 | 1 | Security Build | 1000 D1-1300 B-1335 Security Build | 20 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070862 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT- Break/Fix- SEC - Deploy 1 | SEC | SEC | SI | Offshore | Valencia; Jackie | Accenture | Yes | CapEx | Localization | IT - External | 72h | 45h | 117h | 2017-08-30 | 2017-09-15 | Yes |  |  |  | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 45 | 0 | 0
1070863 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover - Support- SEC - Deploy 1 | SEC | SEC | SI | Offshore | Valencia; Jackie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-09-18 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070864 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | Hypercare-Break/Fix - Deploy1 | SEC | SEC | SI | Offshore | Valencia; Jackie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-10-02 | 2017-11-03 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070865 | No | No | Yes | SDF | SDF Localisation | 04-Test | SEC Break/Fix SIT1 - SEC Deploy2 | SEC | SEC | SI | Offshore | Valencia; Jackie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 75h | 75h | 2017-09-18 | 2017-10-06 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070866 | No | No | Yes | SDF | SDF Localisation | 04-Test | SEC Break/Fix SIT2 - SEC Deploy2 | SEC | SEC | SI | Offshore | Valencia; Jackie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-10-10 | 2017-10-27 | Yes |  |  |  | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070867 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT 2-Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-21 | 2017-08-25 | Yes |  |  |  | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 5 | 6.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070868 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover Prepare - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 40h | 40h | 2017-09-05 | 2017-09-15 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -15 | -8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070869 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover Suport - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 40h | 40h | 2017-09-18 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070870 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | Hypercare-Provide end User Support - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 180h | 180h | 2017-10-02 | 2017-12-01 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070871 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover Suport - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 120h | 120h | 2018-01-08 | 2018-02-16 | Yes |  |  |  | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070872 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-04 | 2017-12-22 | Yes |  |  |  | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | -25 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070873 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | Hypercare-Provide end User Support - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 160h | 160h | 2018-02-05 | 2018-03-30 | Yes |  |  |  | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070874 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy2 (Accenture) - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-24 | 2017-07-28 | Yes |  |  | ACT-MDG.Build ETL programs | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070875 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | CapEx | Localization | IT - External | 0h | 5h | 5h | 2017-09-08 | 2017-09-15 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-07-31 | 2017-08-11 | 2 | QE2 Mock Prep | 20000 D2-20100 B-20110 QE2 Mock Prep | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070876 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | CapEx | Localization | IT - External | 3h | 5h | 8h | 2017-07-31 | 2017-09-13 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070877 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | CapEx | Localization | IT - External | 0h | 5h | 5h | 2017-09-08 | 2017-09-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070878 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | CapEx | Localization | IT - External | 116h | 0h | 116h | 2017-08-01 | 2017-09-01 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 30 | 29 | 15 | 24 | 0 | 0 | 0
1070879 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-08-01 | 2017-09-01 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 10 | 15 | 9 | 8 | 0 | 0 | 0
1070880 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070881 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-08-01 | 2017-09-01 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 5 | 3 | 4 | 0 | 0 | 0
1070882 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | CapEx | Localization | IT - External | 0h | 5h | 5h | 2017-09-08 | 2017-09-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 14.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070883 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | CapEx | Localization | IT - External | 5h | 55h | 60h | 2017-09-04 | 2017-10-06 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0
1070884 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070885 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070886 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070887 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | CapEx | Localization | IT - External | 40h | 65h | 105h | 2017-09-04 | 2017-10-11 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -50 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0
1070888 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -4.88 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070889 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-10-30 | 2017-12-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070890 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-10-30 | 2017-12-07 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 0 | 18.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070891 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy2 - HC - (Accenture) - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2018-02-05 | 2018-03-02 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | -17.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070892 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-03-20 | 2017-03-31 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070893 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-04-03 | 2017-04-07 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -23 | -19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070894 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 53h | 0h | 53h | 2017-04-03 | 2017-04-18 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 20 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070895 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 21h | 0h | 21h | 2017-04-06 | 2017-04-13 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070896 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 68h | 0h | 68h | 2017-03-13 | 2017-03-19 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070897 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2017-07-11 | 2017-07-31 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 9 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070898 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration). - LOG | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 224h | 0h | 224h | 2017-04-13 | 2017-05-29 | Yes |  |  | ACT-FUN.Management | Future Task | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 44 | 35 | 34 | 33 | 36 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070899 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (DB) (Planning, reporting, CR, cross stream integration) - LOG(Global) | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 624h | 241h | 865h | 2017-05-29 | 2017-10-23 | Yes |  |  | ACT-MDG.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 33 | 30 | 49 | 30 | 19 | 35 | 33 | 22 | 53 | 51 | 62 | 57 | 68 | 55 | 0 | 0
1070900 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 39h | 0h | 39h | 2017-06-06 | 2017-07-07 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 9 | 10 | 5 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070901 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Data Definition Documents (DDD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2017-05-01 | 2017-05-19 | Yes |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Future Task | 2017-04-17 | 2017-05-05 | 1 | Revise DDDs - Division review | 1000 D1-1200 A-1213 Revise DDDs - Division review | 10 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070902 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | RTM - LOG | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 55h | 0h | 55h | 2017-04-19 | 2017-06-02 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 12 | 7 | 3 | 7 | 8 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070903 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Gap log - LOG | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2017-04-24 | 2017-05-12 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070904 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 38h | 0h | 38h | 2017-05-22 | 2017-06-19 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 4 | 3 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070905 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2017-05-29 | 2017-06-02 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070906 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-05-22 | 2017-07-28 | Yes |  |  | DELIV-FUN-220.Solution Design Document (SDD) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 4 | 1 | 1 | 4 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070907 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-07-03 | 2017-07-07 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-19 | 2017-06-30 | 1 | Cycle 2 Config | 1000 D1-1300 B-1318 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070908 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2017-06-26 | 2017-07-07 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 20 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070909 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - LOG | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070910 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy2 | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 260h | 260h | 2018-02-05 | 2018-03-30 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070911 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (PTM) - Deploy2 | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 10h | 10h | 2018-01-03 | 2018-01-12 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -30 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070912 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy2 | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 10h | 10h | 2018-01-03 | 2018-01-12 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -8 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070913 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy2 | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 45h | 45h | 2017-12-04 | 2017-12-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070914 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy2 | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 30h | 30h | 2017-12-04 | 2017-12-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070915 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 280h | 280h | 2017-09-25 | 2017-11-24 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070916 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 10h | 10h | 2017-08-28 | 2017-09-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070917 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 5h | 5h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070918 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 120h | 120h | 2017-10-02 | 2017-12-01 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070919 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - PTM | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 20.5h | 0h | 20.5h | 2017-04-19 | 2017-06-01 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 | 0 | 0 | 0 | 7.5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070920 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 4.68h | 4.68h | 2017-09-01 | 2017-09-22 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -24.88 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070921 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 11.97h | 11.97h | 2017-08-28 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070922 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 0h | 125h | 125h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070923 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 0h | 15h | 15h | 2017-09-25 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070924 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 0h | 115h | 115h | 2017-09-25 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070925 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 0h | 48h | 48h | 2017-09-11 | 2017-09-29 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 15 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070926 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 35h | 63h | 98h | 2017-08-28 | 2017-09-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0
1070927 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 20h | 20h | 40h | 2017-07-31 | 2017-08-09 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070928 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 75h | 0h | 75h | 2017-08-07 | 2017-08-24 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 17.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 27 | 8 | 0 | 0 | 0 | 0
1070929 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 0h | 75h | 75h | 2017-08-28 | 2017-09-15 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070930 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2017-08-04 | 2017-08-18 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070931 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 38h | 0h | 38h | 2017-08-21 | 2017-09-01 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 10 | 0 | 0 | 0
1070932 | No | No | Yes | SDF | SDF Interim State Project | 01-Preparation | Environment setup | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 84h | 0h | 84h | 2017-01-09 | 2017-02-13 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070933 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 45h | 15h | 60h | 2017-05-15 | 2017-07-05 | Yes |  |  | ACT-FUN.Management | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 10 | 5 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070934 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTM(Global) | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 0h | 65h | 65h | 2017-07-10 | 2017-12-01 | Yes |  |  | ACT-FUN.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070935 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Gap Definition | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 48h | 0h | 48h | 2017-05-29 | 2017-06-23 | Yes |  |  | WP-FUN.Gap Definition | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 13 | 10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070936 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 0h | 15h | 15h | 2017-09-18 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070937 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy2 | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-10-16 | 2017-10-20 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070938 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (LOG) - Deploy1 | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 220h | 220h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070939 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Manage defects (LOG) - Deploy1 | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 20h | 20h | 2017-10-02 | 2017-10-27 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070940 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (LOG) - Deploy1 | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 20h | 20h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070941 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy2 | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 10h | 10h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070942 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy2 | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 40h | 40h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070943 | No | Yes | No | SDF | Commodities Pricing (in SDF) | 01-Preparation | Commodity Pricing - MRA - RTM | PMO | PMO | SI | Onshore | Dupont Champion; Francois | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-08 | 2016-11-08 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070944 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) - Deploy1 - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-02 | 2017-06-02 | Yes |  |  | DELIV-MDG-206.Functional Specification -Conversion | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | -20 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070945 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Prepare Mock1 - Deploy1 - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-02 | 2017-06-02 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070946 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy2 - HC - (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 160h | 160h | 2018-02-05 | 2018-03-02 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | -18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070947 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070948 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070949 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070950 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070951 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Manage Defect - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 9h | 24h | 33h | 2017-09-11 | 2017-10-19 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 0.13 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0
1070952 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 70h | 70h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 5 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070953 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 70h | 70h | 2017-11-13 | 2018-01-05 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070954 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 70h | 70h | 2017-11-13 | 2018-01-05 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070955 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 72h | 72h | 2017-11-13 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070956 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy1 - HC - (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 107h | 107h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070957 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Preparation - Deploy2 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 33h | 33h | 2017-09-18 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070958 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Execute - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 41h | 0h | 41h | 2017-09-11 | 2017-09-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 0.13 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0
1070959 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Validation - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 33h | 33h | 2017-09-18 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070960 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 76h | 0h | 76h | 2017-08-07 | 2017-09-01 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 8 | 54 | 0 | 0 | 0
1070961 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 29h | 0h | 29h | 2017-08-07 | 2017-08-18 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-07-31 | 2017-08-11 | 2 | QE2 Mock Prep | 20000 D2-20100 B-20110 QE2 Mock Prep | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 10 | 0 | 0 | 0 | 0 | 0
1070962 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 52h | 0h | 52h | 2017-08-07 | 2017-08-25 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0
1070963 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 40h | 0h | 40h | 2017-08-07 | 2017-08-18 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 35 | 0 | 0 | 0 | 0 | 0
1070964 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy1 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-12 | 2017-06-20 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070965 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy2 (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 36h | 0h | 36h | 2017-07-10 | 2017-07-21 | Yes |  |  | ACT-MDG.Build ETL programs | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070966 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 3h | 3h | 2017-07-24 | 2017-09-22 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070967 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 3h | 3h | 2017-09-15 | 2017-09-22 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070968 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 3h | 3h | 2017-09-15 | 2017-09-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 22.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070969 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-09-01 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 33.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070970 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 7h | 7h | 2017-09-15 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070971 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 7h | 7h | 2017-09-15 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070972 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 7h | 7h | 2017-09-15 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070973 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 7h | 7h | 2017-09-15 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070974 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) - Deploy2 (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 37h | 0h | 37h | 2017-07-31 | 2017-09-08 | Yes |  |  | DELIV-MDG-206.Functional Specification -Conversion | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 45 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0
1070975 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Mapping Document - Deploy2 (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 5h | 5h | 10h | 2017-07-31 | 2017-09-22 | Yes |  |  | DELIV-MDG-207.Functional Mapping Document | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0
1070976 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy1 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 8h | 0h | 8h | 2017-07-10 | 2017-08-07 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
1070977 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy1 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-21 | 2017-08-11 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 30 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070978 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy1 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 14h | 0h | 14h | 2017-07-10 | 2017-07-21 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070979 | No | No | Yes | SDF | SDF Localisation | 04-Test | Regression - Run Tests (OTC) - Deploy1 | OTC | FUN | SI | Onshore | Nieva; Ricardo | Accenture | Yes | CapEx | Localization | IT - External | 62h | 48h | 110h | 2017-08-07 | 2017-09-08 | Yes |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 12 | 20 | 0 | 0 | 0
1070980 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Regression - Run Tests (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Nieva; Ricardo | Accenture | Yes | CapEx | Localization | IT - External | 0h | 135h | 135h | 2017-11-06 | 2017-11-24 | Yes |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-12-04 | 2017-12-22 | 2 | Q? Regression | 20000 D2-22000 CG: UAT and Regression-22010 Q? Regression | -20 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070981 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Nieva; Ricardo | Accenture | Yes | CapEx | Localization | IT - External | 0h | 200h | 200h | 2018-01-29 | 2018-03-23 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070982 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Support (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Rich; Laho | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-10-16 | 2017-11-03 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070983 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Rich; Laho | IBM | Yes | CapEx | Localization | IT - External | 0h | 75h | 75h | 2017-10-16 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070984 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Rich; Laho | IBM | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-09-18 | 2017-10-13 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070985 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Functional Specification (FSD) | OTC | FUN | SI | Onshore | Rich; Laho | IBM | Yes | CapEx | Global | IT - External | 0h | 10h | 10h | 2017-05-29 | 2017-09-08 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070986 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trande-RTM | OTC | FUN | SI | Onshore | Rich; Laho | IBM | Yes | CapEx | Global | IT - External | 210h | 0h | 210h | 2017-02-06 | 2017-04-13 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 44 | 28 | 27 | 27 | 24 | 20 | 20 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070987 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-BPML | OTC | FUN | SI | Onshore | Rich; Laho | IBM | Yes | CapEx | Global | IT - External | 40h | 0h | 40h | 2017-01-30 | 2017-02-03 | Yes |  |  | DELIV-BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070988 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Baseline configuration - OTC | OTC | FUN | SI | Onshore | Rich; Laho | IBM | Yes | CapEx | Global | IT - External | 88h | 0h | 88h | 2017-06-05 | 2017-07-01 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-06-26 | 2017-07-14 | 0 | NA Others | 99000-99100-99130 NA others | -30 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070989 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Cycle1 Configuration | OTC | FUN | SI | Onshore | Rich; Laho | IBM | Yes | CapEx | Global | IT - External | 72h | 35h | 107h | 2017-07-04 | 2017-09-29 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 0 | NA Others | 99000-99100-99130 NA others | -15 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0
1070990 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Cycle2 Configuration | OTC | FUN | SI | Onshore | Rich; Laho | IBM | Yes | CapEx | Global | IT - External | 44h | 50h | 94h | 2017-08-14 | 2017-09-29 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 0 | NA Others | 99000-99100-99130 NA others | -20 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0
1070991 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-SIT Test Scenarios/Scripts | OTC | FUN | SI | Onshore | Rich; Laho | IBM | Yes | CapEx | Global | IT - External | 44h | 68h | 112h | 2017-08-21 | 2017-09-26 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 0 | NA Others | 99000-99100-99130 NA others | -25 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0
1070992 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Functional Specification (FSD) | OTC | FUN | SI | Onshore | Rich; Laho | IBM | Yes | CapEx | Global | IT - External | 212h | 0h | 212h | 2017-06-12 | 2017-08-11 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | 5 | 85.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 36 | 0 | 0 | 44 | 0 | 0 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0
1070993 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Execute FUT | OTC | FUN | SI | Onshore | Rich; Laho | IBM | Yes | CapEx | Global | IT - External | 0h | 154h | 154h | 2017-07-14 | 2017-09-01 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-08-18 | 0 | NA Others | 99000-99100-99130 NA others | -30 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070994 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-PDDs | OTC | FUN | SI | Onshore | Rich; Laho | IBM | Yes | CapEx | Global | IT - External | 120h | 0h | 120h | 2017-05-01 | 2017-05-26 | Yes |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 39 | 36 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070995 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-Fit-Gap-Global | OTC | FUN | SI | Onshore | Rich; Laho | IBM | Yes | CapEx | Global | IT - External | 79h | 0h | 79h | 2017-03-13 | 2017-04-28 | Yes |  |  | WP-FUN.Gap Definition | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 30 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070996 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | PDD-RT Trade Promotion Execution - TPM-OTC | OTC | FUN | SI | Onshore | Rich; Laho | IBM | Yes | CapEx | Global | IT - External | 1h | 0h | 1h | 2017-04-18 | 2017-04-18 | Yes |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070997 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | PDD-RT Settlements & Claim Reconcilation - TPM-OTC | OTC | FUN | SI | Onshore | Rich; Laho | IBM | Yes | CapEx | Global | IT - External | 11h | 0h | 11h | 2017-04-10 | 2017-04-26 | Yes |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070998 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | PDD-RT Trade Master Data - TPM-OTC | OTC | FUN | SI | Onshore | Rich; Laho | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070999 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-RTM-Global Trade-OTC | OTC | FUN | SI | Onshore | Rich; Laho | IBM | Yes | CapEx | Global | IT - External | 74h | 0h | 74h | 2017-04-03 | 2017-04-28 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 32 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071000 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-Global Trade scope / Solution validation-OTC | OTC | FUN | SI | Onshore | Rich; Laho | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071001 | No | No | Yes | SDF | Trade (in SDF) | 99-Global | Management -Trade-TPM-OTC | OTC | FUN | SI | Onshore | Rich; Laho | IBM | Yes | CapEx | Global | IT - External | 20h | 0h | 20h | 2017-04-03 | 2017-05-08 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071002 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-Gap Resolution-Global | OTC | FUN | SI | Onshore | Rich; Laho | IBM | Yes | CapEx | Global | IT - External | 69h | 0h | 69h | 2017-03-27 | 2017-06-02 | Yes |  |  | WP-FUN.Gap Definition | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 20 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071003 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | PDD-RT Trade Promotion Planning - TPM-OTC | OTC | FUN | SI | Onshore | Rich; Laho | IBM | Yes | CapEx | Global | IT - External | 2h | 0h | 2h | 2017-04-21 | 2017-04-27 | Yes |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071004 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Rich; Laho | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2017-09-25 | 2017-10-06 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | -5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071005 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | TPM Unit testing Development Documentation (FUT) | OTC | FUN | SI | Onshore | Rich; Laho | IBM | Yes | CapEx | Global | IT - External | 0h | 40h | 40h | 2017-05-29 | 2017-09-29 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071006 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Smith; Adam | IBM | Yes | CapEx | Localization | IT - External | 0h | 120h | 120h | 2017-09-25 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071007 | No | No | Yes | SDF | SDF Localisation | 99-Global | Project Support | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-25 | 2017-09-01 | Yes |  |  |  | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071008 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy2 (Accenture) - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-07-31 | 2017-08-04 | Yes |  |  | ACT-MDG.Build ETL programs | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071009 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-08-07 | 2017-08-11 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-07-31 | 2017-08-11 | 2 | QE2 Mock Prep | 20000 D2-20100 B-20110 QE2 Mock Prep | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0
1071010 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | CapEx | Localization | IT - External | 74h | 0h | 74h | 2017-08-15 | 2017-08-25 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 38 | 0 | 0 | 0 | 0
1071011 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | CapEx | Localization | IT - External | 0h | 8h | 8h | 2017-09-01 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071012 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071013 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | CapEx | Localization | IT - External | 0h | 95h | 95h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071014 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | CapEx | Localization | IT - External | 36h | 34h | 70h | 2017-09-11 | 2017-10-06 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0
1071015 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | CapEx | Localization | IT - External | 0h | 65h | 65h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071016 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-08-28 | 2017-09-01 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 14.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0
1071017 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-22 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071018 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-10-30 | 2017-12-07 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 0 | 18.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071019 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | CapEx | Localization | IT - External | 0h | 65h | 65h | 2017-10-30 | 2017-12-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071020 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -4.88 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071021 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -50 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071022 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071023 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071024 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071025 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy2 - HC - (Accenture) - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2018-02-05 | 2018-03-02 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | -17.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071026 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (DB) (Planning, reporting, CR, cross stream integration) - LOG(Global) | LOG | FUN | SI | Onshore | Steve; Leslie | IBM | Yes | CapEx | Localization | IT - External | 0h | 1,276h | 1,276h | 2017-05-30 | 2018-03-30 | Yes |  |  | ACT-MDG.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071027 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | Workshop-QI management and held product | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-02-15 | 2017-05-12 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071028 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 0h | 44h | 44h | 2017-09-25 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071029 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-25 | 2017-09-25 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071030 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Report (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 0h | 10h | 10h | 2017-10-30 | 2017-11-03 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071031 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-07-17 | 2017-08-04 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071032 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-08-07 | 2017-08-25 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071033 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 9h | 11h | 20h | 2017-06-05 | 2017-07-31 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 10 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071034 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-08-28 | 2017-09-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071035 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-09-11 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071036 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071037 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-07-21 | 2017-08-11 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071038 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-08-15 | 2017-09-06 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 17.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071039 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Log Gaps - PTM | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2017-04-17 | 2017-06-23 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071040 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Support-D2 PTM | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 0h | 10h | 10h | 2017-10-02 | 2017-11-03 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-11-03 | 2 | Training Material Localization | 20000 D2-29000 MultiPhases-29040 Training Material Localization | 10 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071041 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Support-D1 PTM | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 0h | 6h | 6h | 2017-09-11 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-05-22 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 80 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071042 | No | Yes | No | SDF | SDF Localisation | 02-Analyze | Value Realization Plan | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | Yes |  |  | DELIV-CM-210.Value Realization Plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071043 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Cutover Planning | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | Yes |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071044 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Failure Mode Effect Analysis (Design/Build) | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | OpEx | Localization | IT - Internal | 20h | 0h | 20h | 2017-05-08 | 2017-06-27 | Yes |  |  | DELIV-CM-301.Failure Mode Effect Analysis (FMEA) | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071045 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Value Realization Plan (Design/Build) | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | Yes |  |  | DELIV-CM-210.Value Realization Plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071046 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Hypercare Planning | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | Yes |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071047 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (RTR) - Deploy1 | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-09-11 | 2017-09-22 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071048 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (RTR) - Deploy1 | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 245h | 245h | 2017-10-02 | 2017-11-17 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071049 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (RTR) - Deploy1 | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-10-10 | 2017-11-24 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071050 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (RTR) - Deploy1 | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 14h | 1h | 15h | 2017-08-14 | 2017-08-31 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 13.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 11 | 1 | 0 | 0 | 0
1071051 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (RTR) - Deploy1 | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-08-28 | 2017-09-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071052 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (RTR) - Deploy1 | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2017-07-31 | 2017-08-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071053 | No | No | Yes | SDF | SDF Localisation | 04-Test | DR - Support (RTR) - Deploy1 | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 26h | 0h | 26h | 2017-07-31 | 2017-08-18 | Yes |  |  | ACT-FUN.Dry Run activities | Complete | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 9 | 9 | 0 | 0 | 0 | 0 | 0
1071054 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (RTR) - Deploy1 | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 24h | 24h | 2017-09-08 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071055 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (RTR) - Deploy1 | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2017-07-17 | 2017-08-08 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 15 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0
1071056 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 configuration (RTR) - Deploy2 | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 3h | 12h | 15h | 2017-08-14 | 2017-08-25 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | 35 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0
1071057 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (RTR) - Deploy1 | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 63h | 37h | 100h | 2017-05-31 | 2017-08-30 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | -14 | 72.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 19 | 22 | 0 | 0 | 2 | 18 | 0 | 0 | 0 | 0
1071058 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDD Writing - RTR - Deploy1 | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-23 | 2017-06-23 | Yes |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071059 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (RTR) - Deploy1 | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-08-08 | 2017-08-09 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 1 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0
1071060 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | Workshop-Interim state standard cost interfaces | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-04-25 | 2017-05-18 | Yes |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071061 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | SDF-INT-Workshop-Product costing | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 43h | 0h | 43h | 2017-03-02 | 2017-04-04 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 17 | 6 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071062 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | RTM - RTR | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 29h | 0h | 29h | 2017-04-24 | 2017-07-06 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071063 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (RTR) - Deploy1 | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 105.78h | 105.78h | 2017-08-30 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071064 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - RTR | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2017-02-27 | 2017-04-06 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -35 | -16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071065 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - RTR | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 29h | 0h | 29h | 2017-04-17 | 2017-04-21 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -9.88 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071066 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071067 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071068 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071069 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -35 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071070 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | -15 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071071 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - SEC | SEC | SEC | SI | Onshore | Vanderveer; Monina | Accenture | Yes | CapEx | Localization | IT - External | 32h | 865.07h | 897.07h | 2017-09-05 | 2018-04-10 | Yes |  |  |  | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0
1071072 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Pavlovski; Victor | Saputo | Yes | CapEx | Localization | Business | 0h | 120h | 120h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071073 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Pavlovski; Victor | Saputo | Yes | CapEx | Localization | Business | 0h | 360h | 360h | 2017-09-25 | 2017-11-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071074 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Pavlovski; Victor | Saputo | Yes | CapEx | Localization | Business | 0h | 35h | 35h | 2017-09-05 | 2017-09-08 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071075 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | Communication plan execution and monitoring | CM | CM | Saputo | Onshore | Goldstein; Evan | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 225h | 225h | 2017-10-02 | 2017-12-01 | Yes |  |  | ACT-CM.Communication plan execution and monitoring | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071076 | No | No | Yes | SDF | SDF Localisation | 04-Test | Communication Plan (Test) | CM | CM | Saputo | Onshore | Goldstein; Evan | Saputo | Yes | OpEx | Localization | IT - Internal | 100h | 0h | 100h | 2017-07-17 | 2017-08-25 | Yes |  |  | DELIV-CM-106.Communication Plan | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 30 | 25 | 25 | 0 | 0 | 0 | 0
1071077 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Communication Plan (Cutover/Go-live) - Deploy1 | CM | CM | Saputo | Onshore | Goldstein; Evan | Saputo | Yes | OpEx | Localization | IT - Internal | 85h | 25h | 110h | 2017-08-28 | 2017-09-22 | Yes |  |  | DELIV-CM-106.Communication Plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 25 | 0
1071078 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Communication Plan (Preparation) | CM | CM | Saputo | Onshore | Goldstein; Evan | Saputo | Yes | OpEx | Localization | IT - Internal | 43h | 0h | 43h | 2017-03-20 | 2017-04-13 | Yes |  |  | DELIV-CM-106.Communication Plan | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 10 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071079 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Communication Plan (Design/Build) | CM | CM | Saputo | Onshore | Goldstein; Evan | Saputo | Yes | OpEx | Localization | IT - Internal | 141.5h | 0h | 141.5h | 2017-05-29 | 2017-08-04 | Yes |  |  | DELIV-CM-106.Communication Plan | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 20.5 | 15 | 20 | 4 | 12 | 0 | 0 | 25 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071080 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Communication Plan (Analyze) | CM | CM | Saputo | Onshore | Goldstein; Evan | Saputo | Yes | OpEx | Localization | IT - Internal | 85.95h | 0h | 85.95h | 2017-04-17 | 2017-05-26 | Yes |  |  | DELIV-CM-106.Communication Plan | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20.95 | 3 | 20 | 14 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071081 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | CapEx | Localization | IT - Internal | 46h | 0h | 46h | 2017-07-24 | 2017-08-11 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 13 | 18 | 0 | 0 | 0 | 0 | 0 | 0
1071082 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | CapEx | Localization | IT - Internal | 26h | 0h | 26h | 2017-08-07 | 2017-08-25 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 6 | 0 | 0 | 0 | 0
1071083 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | CapEx | Localization | IT - Internal | 28h | 42h | 70h | 2017-08-28 | 2017-09-18 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 14 | 0
1071084 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | CapEx | Localization | IT - Internal | 122h | 3h | 125h | 2017-06-20 | 2017-09-18 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 0 | 15 | 20 | 20 | 20 | 17 | 0
1071085 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071086 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT 1 - Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | Yes |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071087 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | CapEx | Localization | IT - Internal | 116h | 0h | 116h | 2017-02-13 | 2017-06-02 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 10 | 5 | 1 | 0 | 0 | 0 | 7 | 19 | 20 | 16 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071088 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071089 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | WRICEFs inventory - DEV | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | DELIV-DEV-102.RICEFW Inventory | Future Task | NA | NA | 1 | GAPs | 1000 D1-1200 A-1211GAPs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071090 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | WRICEFs - DEV (Design/Build) | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | CapEx | Localization | IT - Internal | 160h | 0h | 160h | 2017-06-05 | 2017-07-14 | Yes |  |  | To delete-To delete.To delete | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 15.13 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 30 | 27 | 20 | 33 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071091 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Break/Fix - DEV | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0.13 | 5.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071092 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 120h | 120h | 2017-10-10 | 2017-11-17 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071093 | No | No | Yes | SDF | SDF Localisation | 99-Global | Project Support | SEC | SEC | SI | Offshore | Santiago; Perzeus | Accenture | Yes | CapEx | Localization | IT - External | 81h | 166.5h | 247.5h | 2017-07-31 | 2017-10-04 | Yes |  |  |  | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 9 | 9 | 13.5 | 9 | 18 | 0 | 0
1071094 | No | No | Yes | SDF | SDF Localisation | 99-Global | Team Lead - Program Site Readiness Lead (Opex) - PMO | PMO | PMO | Saputo | Onshore | Steringa; Dan | Saputo | Yes | OpEx | Localization | Business | 215h | 141h | 356h | 2017-05-01 | 2018-02-20 | Yes |  |  | DELIV-FUN-029.Site Assessment | On Schedule | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 36 | 0 | 0 | 20 | 20 | 10 | 30 | 8 | 0 | 20 | 20 | 16 | 0 | 10 | 10 | 5 | 0 | 0 | 0 | 0
1071095 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Data Conversion Plan - Deploy1 - DC | MDG | DC | SI | Onshore | Masri; Remi | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-02 | 2017-06-02 | Yes |  |  | DELIV-MDG-201.Data Conversion Plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071096 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Masri; Remi | Accenture | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2017-07-10 | 2017-07-13 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071097 | No | No | Yes | SDF | SDF Localisation | 99-Global | Team Lead - MDG - DC | MDG | DC | SI | Onshore | Masri; Remi | Accenture | Yes | CapEx | Localization | IT - External | 176h | 243h | 419h | 2017-07-31 | 2018-01-30 | Yes |  |  | DELIV-FUN-029.Site Assessment | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 40 | 40 | 40 | 24 | 0 | 0
1071098 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Onshore | Masri; Remi | Accenture | Yes | CapEx | Localization | IT - External | 32h | 31h | 63h | 2017-09-11 | 2017-10-11 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0
1071099 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Masri; Remi | Accenture | Yes | CapEx | Localization | IT - External | 0h | 59h | 59h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071100 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Masri; Remi | Accenture | Yes | CapEx | Localization | IT - External | 0h | 61h | 61h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071101 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Masri; Remi | Accenture | Yes | CapEx | Localization | IT - External | 0h | 63h | 63h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071102 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Masri; Remi | Accenture | Yes | CapEx | Localization | IT - External | 0h | 51h | 51h | 2017-10-30 | 2017-12-07 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 0 | 18.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071103 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Masri; Remi | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-10-30 | 2017-12-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071104 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Masri; Remi | Accenture | Yes | CapEx | Localization | IT - External | 0h | 63h | 63h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -4.88 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071105 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Masri; Remi | Accenture | Yes | CapEx | Localization | IT - External | 0h | 63h | 63h | 2017-11-03 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -50 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071106 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Masri; Remi | Accenture | Yes | CapEx | Localization | IT - External | 0h | 54h | 54h | 2017-12-22 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071107 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Masri; Remi | Accenture | Yes | CapEx | Localization | IT - External | 0h | 54h | 54h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071108 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Masri; Remi | Accenture | Yes | CapEx | Localization | IT - External | 0h | 54h | 54h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071109 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Masri; Remi | Accenture | Yes | CapEx | Localization | IT - External | 0h | 54h | 54h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071110 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - RTR | RTR | FUN | Saputo | Onshore | Ethier; Patrice | Saputo | Yes | CapEx | Localization | IT - Internal | 5h | 0h | 5h | 2017-05-29 | 2017-06-02 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071111 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - RTR | RTR | FUN | Saputo | Onshore | Ethier; Patrice | Saputo | Yes | CapEx | Localization | IT - Internal | 36h | 0h | 36h | 2017-04-17 | 2017-05-26 | Yes |  |  | ACT-FUN.Management | Future Task | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 10 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071112 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | RTR | FUN | Saputo | Onshore | Ethier; Patrice | Saputo | Yes | CapEx | Localization | IT - Internal | 5h | 0h | 5h | 2017-03-20 | 2017-03-24 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071113 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - RTR (Global) | RTR | FUN | Saputo | Onshore | Ethier; Patrice | Saputo | Yes | CapEx | Localization | IT - Internal | 35h | 34h | 69h | 2017-07-17 | 2017-09-06 | Yes |  |  | ACT-FUN.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0
1071114 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Change Impact Analysis | CM | CM | SI | Onshore | Fischer; Gillian | IBM | Yes | OpEx | Localization | IT - External | 66h | 0h | 66h | 2017-04-24 | 2017-05-26 | Yes |  |  | DELIV-CM-014.Change Impacts Analysis | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 13 | 20 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071115 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Process Role Catalog | CM | CM | SI | Onshore | Fischer; Gillian | IBM | Yes | OpEx | Localization | IT - External | 54h | 0h | 54h | 2017-04-17 | 2017-05-26 | Yes |  |  | DELIV-CM-008.Process Role Catalog | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 12 | 4 | 12 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071116 | No | No | Yes | SDF | SDF Localisation | 99-Global | Process Role Catalog (Design/Build) | CM | CM | SI | Onshore | Fischer; Gillian | IBM | Yes | OpEx | Localization | IT - External | 45h | 0h | 45h | 2017-05-29 | 2017-07-06 | Yes |  |  | DELIV-CM-008.Process Role Catalog | Complete | 2017-05-29 | 2017-06-23 | 1 | Role Mapping | 1000 D1-1800 MultiPhases-1810 Role Mapping | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 6 | 8 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071117 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Transition Plan Execution & Monitoring | CM | CM | SI | Onshore | Fischer; Gillian | IBM | Yes | OpEx | Localization | IT - External | 3h | 0h | 3h | 2017-05-03 | 2017-05-05 | Yes |  |  | ACT-CM.Management | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071118 | No | No | Yes | SDF | SDF Localisation | 04-Test | Establish Key users Network (Test) | CM | CM | SI | Onshore | Fischer; Gillian | IBM | Yes | OpEx | Localization | IT - External | 63h | 16h | 79h | 2017-07-17 | 2017-09-12 | Yes |  |  | ACT-CM.Establish Key users Network | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 12 | 20 | 6 | 0 | 8 | 0 | 8 | 0 | 0
1071119 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Change Impacts Analysis (Design/Build) | CM | CM | SI | Onshore | Fischer; Gillian | IBM | Yes | OpEx | Localization | IT - External | 5h | 25.4h | 30.4h | 2017-06-12 | 2017-07-13 | Yes |  |  | DELIV-CM-014.Change Impacts Analysis | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071120 | No | No | Yes | SDF | SDF Localisation | 99-Global | Role Mapping (Design/Build) | CM | CM | SI | Onshore | Fischer; Gillian | IBM | Yes | OpEx | Localization | IT - External | 217h | 0h | 217h | 2017-06-05 | 2017-07-14 | Yes |  |  | DELIV-CM-218.Role Mapping | Complete | 2017-05-29 | 2017-06-23 | 1 | Role Mapping | 1000 D1-1800 MultiPhases-1810 Role Mapping | 5 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 22 | 43 | 52 | 35 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071121 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Establish Key users Network(Design/Build) | CM | CM | SI | Onshore | Fischer; Gillian | IBM | Yes | OpEx | Localization | IT - External | 6h | 3.63h | 9.63h | 2017-06-06 | 2017-07-14 | Yes |  |  | ACT-CM.Establish Key users Network | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071122 | No | No | Yes | SDF | SDF Localisation | 04-Test | Transition Plan Execution & Monitoring (Test) | CM | CM | SI | Onshore | Fischer; Gillian | IBM | Yes | OpEx | Localization | IT - External | 46.5h | 0h | 46.5h | 2017-07-17 | 2017-09-08 | Yes |  |  | ACT-CM.Transition Plan Execution & Monitoring | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 6 | 10 | 0 | 0 | 0 | 0.5 | 20 | 0 | 0
1071123 | No | No | Yes | SDF | SDF Localisation | 04-Test | Business Readiness Execution & Monitoring (Test) | CM | CM | SI | Onshore | Fischer; Gillian | IBM | Yes | OpEx | Localization | IT - External | 16h | 4h | 20h | 2017-08-21 | 2017-09-11 | Yes |  |  | ACT-CM.Business Readiness Execution & Monitoring | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 12 | 0 | 0
1071124 | No | No | Yes | SDF | SDF Localisation | 99-Global | Role Mapping (Test) | CM | CM | SI | Onshore | Fischer; Gillian | IBM | Yes | OpEx | Localization | IT - External | 144.5h | 0h | 144.5h | 2017-07-17 | 2017-09-01 | Yes |  |  | DELIV-CM-218.Role Mapping | Future Task | 2017-05-29 | 2017-06-23 | 1 | Role Mapping | 1000 D1-1800 MultiPhases-1810 Role Mapping | 35 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 15 | 0 | 20 | 12 | 23 | 49.5 | 0 | 0 | 0
1071125 | No | Yes | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing WRICEFs (Design/Build) | DEV | DEV | SI | Offshore | D; Kavya | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-24 | 2017-02-24 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -88 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071126 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | SDF Interim State-Workshop-Supply chain planning | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-03-16 | 2017-04-13 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071127 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | SDF Interim State-Workshop-Production scheduling and receipt (OCT. Go-live) | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-03-14 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071128 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - PTM | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-04-17 | 2017-04-21 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071129 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | RTM - PTM | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 56h | 0h | 56h | 2017-04-17 | 2017-07-13 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 4 | 8 | 0 | 0 | 0 | 0 | 15 | 11 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071130 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Log Gaps - PTM | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-04-17 | 2017-04-27 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071131 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 55h | 0h | 55h | 2017-06-19 | 2017-08-04 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | -15 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 15 | 20 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071132 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Deploy1 | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | -5 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071133 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-07-04 | 2017-07-14 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 10 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071134 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 40h | 50h | 90h | 2017-07-17 | 2017-08-08 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071135 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 30h | 30h | 60h | 2017-07-17 | 2017-08-10 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 15 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071136 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-08-07 | 2017-08-25 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 0 | 0 | 0 | 0
1071137 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 18h | 42h | 60h | 2017-08-07 | 2017-09-05 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 17.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 9 | 0 | 0 | 0 | 0
1071138 | No | No | Yes | SDF | SDF Localisation | 04-Test | Regression - Run Tests (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | Yes |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071139 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 0h | 110h | 110h | 2017-08-28 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071140 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-08-28 | 2017-09-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071141 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2017-04-03 | 2017-04-06 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -15.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071142 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2017-04-03 | 2017-04-13 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -20 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071143 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | DDD | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 33h | 0h | 33h | 2017-05-08 | 2017-06-01 | Yes |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Complete | 2017-04-17 | 2017-05-05 | 1 | Revise DDDs - Division review | 1000 D1-1200 A-1213 Revise DDDs - Division review | 15 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071144 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2017-05-15 | 2017-06-02 | Yes |  |  | ACT-FUN.Management | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071145 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-04-03 | 2017-04-06 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071146 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-04-24 | 2017-05-12 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -8.88 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071147 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-08-14 | 2017-09-22 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -24.88 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071148 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Report (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-10-30 | 2017-12-15 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071149 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-10-30 | 2017-12-15 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071150 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 0h | 44h | 44h | 2017-09-25 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071151 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 0h | 190h | 190h | 2017-10-02 | 2017-12-15 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071152 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-10-02 | 2017-12-15 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071153 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 19h | 4h | 23h | 2017-07-17 | 2017-08-07 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | 5 | 29.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071154 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 0h | 120h | 120h | 2018-02-05 | 2018-03-30 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071155 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-12-04 | 2017-12-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071156 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 0h | 132h | 132h | 2018-01-15 | 2018-01-30 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -8 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071157 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 0h | 88h | 88h | 2018-01-15 | 2018-01-26 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -30 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071158 | No | No | Yes | SDF | SDF Localisation | 04-Test | DR - Support (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-11-20 | 2017-12-01 | Yes |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071159 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-12-04 | 2017-12-29 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071160 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Support-D2 PTM | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 0h | 22h | 22h | 2017-10-02 | 2017-12-15 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-11-03 | 2 | Training Material Localization | 20000 D2-29000 MultiPhases-29040 Training Material Localization | 10 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071161 | No | No | Yes | SDF | SDF Localisation | 99-Global | SDF-Manage Project | PMO | PMO | SI | Onshore | Smith; Stephen | IBM | Yes | CapEx | Localization | IT - External | 128h | 606.4h | 734.4h | 2017-03-27 | 2018-01-01 | Yes |  |  | ACT-PMO.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 48 | 40 | 0
1071162 | No | No | Yes | SDF | SDF Localisation | 99-Global | Cutover planners | PMO | PMO | SI | Onshore | Smith; Stephen | IBM | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2017-07-31 | 2017-08-18 | Yes |  |  |  | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0
1071163 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy2 | BI | BI | Saputo | Onshore | Archambault; Louis | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 40h | 40h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071164 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTP) - Deploy2 | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-09-11 | 2017-09-22 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 20 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071165 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | Workshop-Purchasing & A/P | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-03-06 | 2017-03-06 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071166 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 0h | 45h | 45h | 2017-05-23 | 2017-09-15 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 11 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071167 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 8h | 52h | 60h | 2017-08-30 | 2017-10-05 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0
1071168 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 24h | 36h | 60h | 2017-08-28 | 2017-09-11 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0
1071169 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 0h | 120h | 120h | 2017-09-25 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071170 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTP) - Deploy2 | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-09-18 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071171 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTP) - Deploy2 | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071172 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTP) - Deploy2 | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071173 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTP) - Deploy2 | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071174 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2017-08-01 | 2017-08-04 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071175 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 48h | 43.2h | 91.2h | 2017-08-07 | 2017-09-11 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0
1071176 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2017-08-14 | 2017-08-16 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0
1071177 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2017-07-25 | 2017-07-28 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071178 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 0h | 120h | 120h | 2018-02-05 | 2018-03-30 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071179 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 0h | 132h | 132h | 2018-01-15 | 2018-01-30 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -8 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071180 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-12-04 | 2017-12-29 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071181 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Support-D1 PTM | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 0h | 6h | 6h | 2017-09-11 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-05-22 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 80 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071182 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 0h | 88h | 88h | 2018-01-15 | 2018-01-26 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -30 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071183 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-12-04 | 2017-12-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071184 | No | No | Yes | SDF | SDF Localisation | 04-Test | DR - Support (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-11-20 | 2017-12-01 | Yes |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071185 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Support-D2 PTM | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 0h | 22h | 22h | 2017-10-02 | 2017-12-15 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-11-03 | 2 | Training Material Localization | 20000 D2-29000 MultiPhases-29040 Training Material Localization | 10 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071186 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 17h | 43h | 60h | 2017-07-20 | 2017-08-07 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071187 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-08-15 | 2017-09-06 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 17.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071188 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-10-02 | 2017-12-15 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071189 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-08-28 | 2017-09-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071190 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 67h | 0h | 67h | 2017-08-07 | 2017-08-17 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 23 | 0 | 0 | 0 | 0 | 0
1071191 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 80h | 10h | 90h | 2017-07-24 | 2017-08-04 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071192 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-06-05 | 2017-07-14 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 10 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071193 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 0h | 220h | 220h | 2017-09-25 | 2017-12-15 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071194 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 0h | 44h | 44h | 2017-09-25 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071195 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 0h | 87.37h | 87.37h | 2017-08-28 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071196 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF Build/Support (SEC) - Deploy1 | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 180h | 0h | 180h | 2017-07-04 | 2017-08-25 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-05 | 2017-06-23 | 1 | Security Build | 1000 D1-1300 B-1335 Security Build | 20 | 86.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 36 | 45 | 45 | 0 | 0 | 0 | 0
1071197 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SEC-Build - SEC Deploy2 | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 27h | 57.5h | 84.5h | 2017-08-28 | 2017-09-19 | Yes |  |  |  | Future Task | 2017-07-24 | 2017-08-11 | 2 | Security Build | 20000 D2-20100 B-20230 Security Build | 20 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0
1071198 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover - Support- SEC - Deploy 1 | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-09-18 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071199 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | Hypercare-Break/Fix - Deploy1 | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 100h | 100h | 2017-10-02 | 2017-11-03 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071200 | No | No | Yes | SDF | SDF Localisation | 04-Test | SEC Break/Fix SIT1 - SEC Deploy2 | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 75h | 75h | 2017-09-18 | 2017-10-06 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071201 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SEC-FUT - SEC Deploy2 | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-09-01 | 2017-09-14 | Yes |  |  |  | Future Task | 2017-08-14 | 2017-09-01 | 2 | Security FUT | 20000 D2-20100 B-20240 Security FUT | 14 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071202 | No | No | Yes | SDF | SDF Localisation | 04-Test | SEC Break/Fix SIT2 - SEC Deploy2 | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 75h | 75h | 2017-10-10 | 2017-10-27 | Yes |  |  |  | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071203 | No | No | Yes | SDF | SDF Localisation | 04-Test | SEC Break/Fix SIT2 - SEC Deploy2 | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 75h | 75h | 2017-10-10 | 2017-10-27 | Yes |  |  |  | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071204 | No | No | Yes | SDF | SDF Localisation | 04-Test | SEC Break/Fix SIT1 - SEC Deploy2 | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 75h | 75h | 2017-09-18 | 2017-10-06 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071205 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SEC-FUT - SEC Deploy2 | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-09-01 | 2017-09-14 | Yes |  |  |  | Future Task | 2017-08-14 | 2017-09-01 | 2 | Security FUT | 20000 D2-20100 B-20240 Security FUT | 14 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071206 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SEC-Build - SEC Deploy2 | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 50h | 10h | 60h | 2017-08-28 | 2017-09-11 | Yes |  |  |  | Future Task | 2017-07-24 | 2017-08-11 | 2 | Security Build | 20000 D2-20100 B-20230 Security Build | 20 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0
1071207 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (HR) - Deploy1 | HR | HR | SI | Onshore | Robbins; Doug | IBM | Yes | CapEx | Localization | IT - External | 11h | 0h | 11h | 2017-08-07 | 2017-09-14 | Yes |  |  | ACT-FUN.Functional Break/Fix | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 2 | 0 | 0 | 5 | 0
1071208 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Gap Definition | HR | HR | SI | Onshore | Robbins; Doug | IBM | Yes | CapEx | Localization | IT - External | 11h | 0h | 11h | 2017-05-03 | 2017-06-16 | Yes |  |  | WP-FUN.Gap Definition | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | 1 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071209 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (HR) - Deploy1 | HR | HR | SI | Onshore | Robbins; Doug | IBM | Yes | CapEx | Localization | IT - External | 0h | 110h | 110h | 2017-10-02 | 2017-12-01 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071210 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (HR) - Deploy1 | HR | HR | SI | Onshore | Robbins; Doug | IBM | Yes | CapEx | Localization | IT - External | 0h | 28h | 28h | 2017-10-02 | 2017-12-01 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071211 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support - OTC (HR) - Deploy1 | HR | HR | SI | Onshore | Robbins; Doug | IBM | Yes | CapEx | Localization | IT - External | 0h | 12h | 12h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071212 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (HR) - Deploy1 | HR | HR | SI | Onshore | Robbins; Doug | IBM | Yes | CapEx | Localization | IT - External | 0h | 12h | 12h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071213 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (HR) - Deploy1 | HR | HR | SI | Onshore | Robbins; Doug | IBM | Yes | CapEx | Localization | IT - External | 0h | 16h | 16h | 2017-09-05 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071214 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Interface (HR) - Deploy1 | HR | HR | SI | Onshore | Robbins; Doug | IBM | Yes | CapEx | Localization | IT - External | 22h | 0h | 22h | 2017-06-20 | 2017-08-31 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 1 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 10 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0
1071215 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (HR) - Deploy1 | HR | HR | SI | Onshore | Robbins; Doug | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-07-28 | 2017-09-06 | Yes |  |  | ACT-FUN.Functional Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -16 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
1071216 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071217 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 configuration (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-07-31 | 2017-08-04 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | 25 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071218 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Support (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071219 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071220 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071221 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-11 | 2017-08-11 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 20 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071222 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 28h | 28h | 2017-08-04 | 2017-08-11 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 5 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071223 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 24h | 24h | 2017-08-07 | 2017-08-25 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 4.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071224 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071225 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071226 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Support (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071227 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 configuration (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 115h | 0h | 115h | 2017-08-14 | 2017-09-01 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 27 | 44 | 0 | 0 | 0
1071228 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071229 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2017-08-14 | 2017-09-15 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | -8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071230 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071231 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071232 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071233 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Data Definition Documents (DDD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | Yes |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Future Task | 2017-04-17 | 2017-05-05 | 1 | Revise DDDs - Division review | 1000 D1-1200 A-1213 Revise DDDs - Division review | 10 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071234 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-08-07 | 2017-08-11 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-19 | 2017-06-30 | 1 | Cycle 2 Config | 1000 D1-1300 B-1318 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0
1071235 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 22h | 0h | 22h | 2017-05-08 | 2017-06-22 | Yes |  |  | DELIV-FUN-220.Solution Design Document (SDD) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 3 | 11 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071236 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071237 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071238 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Gap log - LOG | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 11h | 0h | 11h | 2017-05-04 | 2017-05-19 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071239 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Support Mock1 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 54h | 54h | 2017-08-21 | 2017-09-15 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-09-25 | 2017-10-06 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -25 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071240 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 71h | 0h | 71h | 2017-09-06 | 2017-09-15 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 10 | 16.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 44 | 0
1071241 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071242 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - LOG | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 60h | 0h | 60h | 2017-04-17 | 2017-05-23 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 9 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071243 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 0h | 85h | 85h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071244 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 0h | 120h | 120h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071245 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | IXXX-DEV FUT-Interim State common components | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2017-05-22 | 2017-05-26 | Yes |  |  | ACT-FUN.Execute FUT | Complete | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | 0 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071246 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - PTM | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-17 | 2017-05-12 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071247 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Log Gaps - PTM | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-04-17 | 2017-06-16 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071248 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | DDD | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2017-05-08 | 2017-06-16 | Yes |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Complete | 2017-04-17 | 2017-05-05 | 1 | Revise DDDs - Division review | 1000 D1-1200 A-1213 Revise DDDs - Division review | 15 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071249 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | IXXX-FSD-Production receipts interface | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 35h | 0h | 35h | 2017-04-24 | 2017-04-28 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -25 | -35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071250 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | IXXX-DEV FUT-Production receipts interface | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 69h | 0h | 69h | 2017-06-19 | 2017-07-07 | Yes |  |  | ACT-FUN.Execute FUT | Complete | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | 20 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 24 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071251 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | Configuration-PPDS config for manual entry of planned order | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-06-12 | 2017-06-16 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-05-19 | 0 | NA Others | 99000-99100-99130 NA others | 25 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071252 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | Configuration-Output condition for process order interface | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 19h | 0h | 19h | 2017-05-15 | 2017-05-19 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-05-19 | 0 | NA Others | 99000-99100-99130 NA others | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071253 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 0h | 53h | 53h | 2017-09-05 | 2017-09-22 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 15 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071254 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 119h | 0h | 119h | 2017-05-15 | 2017-06-30 | Yes |  |  | ACT-FUN.Management | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 21 | 20 | 20 | 0 | 20 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071255 | No | No | Yes | SDF | SDF Interim State Project | 01-Preparation | Environment setup | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 50h | 0h | 50h | 2017-01-09 | 2017-01-27 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 30 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071256 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-04-03 | 2017-04-07 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -20 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071257 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 42h | 0h | 42h | 2017-03-13 | 2017-03-31 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -15.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 10 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071258 | No | No | Yes | SDF | SDF Localisation | 04-Test | Regression - Run Tests (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | Yes |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071259 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 0h | 88h | 88h | 2017-08-28 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071260 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 120h | 0h | 120h | 2017-07-17 | 2017-08-04 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071261 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 30h | 30h | 60h | 2017-07-17 | 2017-08-10 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071262 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 116h | 0h | 116h | 2017-08-07 | 2017-08-24 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 36 | 0 | 0 | 0 | 0
1071263 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 14h | 46h | 60h | 2017-08-07 | 2017-08-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 17.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 4 | 0 | 0 | 0 | 0
1071264 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 50h | 0h | 50h | 2017-07-03 | 2017-07-14 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | -15 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071265 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Deploy1 | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Global | IT - External | 5h | 0h | 5h | 2017-06-02 | 2017-06-23 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | -5 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071266 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-07-07 | 2017-07-13 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 10 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071267 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-04 | 2017-04-04 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -8.88 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071268 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071269 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 0h | 54h | 54h | 2017-08-28 | 2017-09-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071270 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | SDF Interim State-Workshop-Supply chain planning | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-03-16 | 2017-04-07 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071271 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | SDF Interim State-Workshop-Production scheduling and receipt (OCT. Go-live) | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-02-27 | 2017-03-29 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071272 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-07-10 | 2017-07-14 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | 5 | 29.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071273 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 0h | 75h | 75h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071274 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071275 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 16h | 14h | 30h | 2017-08-11 | 2017-08-28 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 7 | 7 | 0 | 0 | 0 | 0
1071276 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTP) - Deploy2 | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071277 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTP) - Deploy2 | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071278 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTP) - Deploy2 | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-09-18 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071279 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTP) - Deploy2 | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071280 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 0h | 120h | 120h | 2017-09-25 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071281 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (PTP) - Deploy2 | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 20h | 10h | 30h | 2017-08-28 | 2017-09-12 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | -5 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0
1071282 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 5h | 25h | 30h | 2017-09-04 | 2017-09-18 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0
1071283 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 10h | 50h | 60h | 2017-08-28 | 2017-09-15 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0
1071284 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2017-06-12 | 2017-07-28 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 11 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071285 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-06-26 | 2017-08-11 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | -5 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0
1071286 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Interface (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 20h | 30h | 50h | 2017-06-20 | 2017-09-06 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 15 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0
1071287 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2017-06-19 | 2017-06-30 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 20 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071288 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 21h | 0h | 21h | 2017-07-17 | 2017-07-21 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071289 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 38h | 0h | 38h | 2017-08-07 | 2017-09-08 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 3 | 4 | 5 | 10 | 0 | 0
1071290 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (PTP) - Deploy2 | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-09-11 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071291 | No | No | Yes | SDF | SDF Interim State Project | 01-Preparation | Environment setup | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 39h | 0h | 39h | 2017-01-09 | 2017-01-20 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071292 | No | Yes | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing WRICEFs (Design/Build) | DEV | DEV | SI | Offshore | Dongare; Pranouti | IBM | Yes | CapEx | Localization | IT - External | 175h | 0h | 175h | 2017-02-20 | 2017-05-26 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -88 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071293 | No | Yes | No | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | SI | Offshore | Dongare; Pranouti | IBM | Yes | CapEx | Localization | IT - External | 115h | 0h | 115h | 2017-02-13 | 2017-06-16 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 37 | 36 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071294 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071295 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071296 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Support (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071297 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2017-06-19 | 2017-06-20 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071298 | No | No | Yes | SDF | SDF Interim State Project | 01-Preparation | Environment setup | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071299 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG014-DEV FUT-INT-PGI from BPCS to SAP | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-07 | 2017-07-07 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-08-18 | 0 | NA Others | 99000-99100-99130 NA others | -10 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071300 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG012-FSD-INT-STO interface | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 19h | 0h | 19h | 2017-04-03 | 2017-05-19 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -90 | -30.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 12 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071301 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG013-FSD-INT-STO goods issue interface (SAP to BPCS) | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2017-01-24 | 2017-04-21 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -89 | -50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071302 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG015-FSD-INT-Inventory adjustment interface | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-03-14 | 2017-04-21 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -88 | -50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 2 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071303 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG012-DEV FUT-INT-STO interface | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 12h | 2h | 14h | 2017-08-07 | 2017-08-15 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-08-18 | 0 | NA Others | 99000-99100-99130 NA others | -15.88 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0
1071304 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG013-DEV FUT-INT-STO goods issue interface (SAP to BPCS) | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 26h | 0h | 26h | 2017-05-22 | 2017-06-23 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-08-18 | 0 | NA Others | 99000-99100-99130 NA others | -40 | -40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 13 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071305 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG015-DEV FUT-INT-Inventory adjustment interface | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 29h | 0h | 29h | 2017-06-05 | 2017-06-23 | Yes |  |  | ACT-FUN.Execute FUT | Complete | 2017-07-17 | 2017-08-18 | 0 | NA Others | 99000-99100-99130 NA others | -30 | -35.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 4 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071306 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Support Mock1 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 17h | 55h | 72h | 2017-08-31 | 2017-09-15 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-09-25 | 2017-10-06 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -25 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0
1071307 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Report (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 33h | 0h | 33h | 2017-08-07 | 2017-08-11 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 5.13 | 75.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0
1071308 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 0h | 260h | 260h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071309 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - LOG | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 23h | 0h | 23h | 2017-04-18 | 2017-06-13 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071310 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG015-DEV-INT-Inventory adjustment interface - LOG | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 14h | 0h | 14h | 2017-05-15 | 2017-06-02 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071311 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | Configuration-STO output conditions & ALE | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 29h | 0h | 29h | 2017-04-24 | 2017-05-05 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-06-19 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -40 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071312 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 46h | 0h | 46h | 2017-05-29 | 2017-06-19 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 12 | 18 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071313 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 33h | 0h | 33h | 2017-06-08 | 2017-06-28 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 12 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071314 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-07-07 | 2017-08-04 | Yes |  |  | DELIV-FUN-220.Solution Design Document (SDD) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071315 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 70h | 2h | 72h | 2017-06-21 | 2017-09-11 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-19 | 2017-06-30 | 1 | Cycle 2 Config | 1000 D1-1300 B-1318 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 0 | 6 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0
1071316 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-10-10 | 2017-10-13 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071317 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071318 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-10-09 | 2017-10-09 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071319 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 62h | 24.78h | 86.78h | 2017-08-21 | 2017-09-18 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | -8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 35 | 0
1071320 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071321 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 configuration (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 9h | 1h | 10h | 2017-09-11 | 2017-09-15 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0
1071322 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Report (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-08-17 | 2017-08-23 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 55 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 9 | 0 | 0 | 0 | 0
1071323 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Support (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071324 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071325 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071326 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 4.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071327 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 121h | 1h | 122h | 2017-06-29 | 2017-08-31 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 20 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 58 | 0 | 18 | 0 | 27 | 0 | 0 | 0
1071328 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | IXXX-DEV FUT-Interim State common components | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-22 | 2017-05-22 | Yes |  |  | ACT-FUN.Execute FUT | Complete | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | 0 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071329 | No | Yes | No | SDF | SDF Localisation | 99-Global | Onboard DTC | CM | CM | SI | Onshore | Faleyimu; Dele | IBM | Yes | OpEx | Localization | IT - External | 2.4h | 0h | 2.4h | 2017-03-27 | 2017-03-31 | Yes |  |  | ACT-CM.Management | Future Task | 2017-06-26 | 2017-07-28 | 1 | Training Schedule | 1000 D1-1800 MultiPhases-1820 Training Schedule | -65 | 9.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071330 | No | Yes | No | SDF | SDF Localisation | 99-Global | Training Materials-Traininng Data (exercise book) (Design/Build) | CM | CM | SI | Onshore | Faleyimu; Dele | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | DELIV-CM-401.Training Materials | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 20 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071331 | No | Yes | No | SDF | SDF Localisation | 99-Global | Training Materials-Work Instructions/Job aids (Design/Build) | CM | CM | SI | Onshore | Faleyimu; Dele | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | DELIV-CM-451.Work Instructions | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 10 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071332 | No | Yes | No | SDF | SDF Localisation | 99-Global | Training Materials-Training materials translation (Design/Build) | CM | CM | SI | Onshore | Faleyimu; Dele | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-15 | Yes |  |  | DELIV-CM-401.Training Materials | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 10 | 58.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071333 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 0h | 35h | 35h | 2017-08-07 | 2017-08-11 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 4.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071334 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-25 | 2017-08-25 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071335 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-21 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071336 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 configuration (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 101h | 0h | 101h | 2017-08-14 | 2017-09-01 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 20 | 45 | 0 | 0 | 0
1071337 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 0h | 120h | 120h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071338 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 76h | 0h | 76h | 2017-08-21 | 2017-09-10 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | -8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 51 | 0 | 0
1071339 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071340 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071341 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Support Mock1 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 42h | 33h | 75h | 2017-09-11 | 2017-09-22 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-09-25 | 2017-10-06 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -25 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0
1071342 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 0h | 120h | 120h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071343 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-26 | 2017-05-26 | Yes |  |  | DELIV-FUN-220.Solution Design Document (SDD) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071344 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 150h | 0h | 150h | 2017-07-10 | 2017-08-11 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-19 | 2017-06-30 | 1 | Cycle 2 Config | 1000 D1-1300 B-1318 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 35 | 45 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0
1071345 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071346 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 83h | 0h | 83h | 2017-06-05 | 2017-07-07 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 10 | 12 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071347 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - LOG | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 33h | 0h | 33h | 2017-04-24 | 2017-05-19 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 11 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071348 | No | No | Yes | SDF | SDF Interim State Project | 01-Preparation | Environment setup | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2017-01-09 | 2017-01-13 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071349 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Support (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-07-20 | 2017-07-21 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071350 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071351 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-07-10 | 2017-07-14 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071352 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071353 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 configuration (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-07-31 | 2017-08-04 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | 25 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071354 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Gap Definition | HR | HR | Saputo | Onshore | Centeno; Katya | Saputo | Yes | CapEx | Localization | IT - Internal | 22.5h | 0h | 22.5h | 2017-05-02 | 2017-06-19 | Yes |  |  | WP-FUN.Gap Definition | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | 1 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0.5 | 2 | 2 | 5 | 5 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071355 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (HR) - Deploy1 | HR | HR | Saputo | Onshore | Centeno; Katya | Saputo | Yes | CapEx | Localization | IT - Internal | 13h | 0h | 13h | 2017-08-07 | 2017-08-10 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0
1071356 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (HR) - Deploy1 | HR | HR | Saputo | Onshore | Centeno; Katya | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 71h | 71h | 2017-09-05 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071357 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (HR) - Deploy1 | HR | HR | Saputo | Onshore | Centeno; Katya | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 6h | 6h | 2017-09-05 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071358 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support - OTC (HR) - Deploy1 | HR | HR | Saputo | Onshore | Centeno; Katya | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 10h | 10h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071359 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (HR) - Deploy1 | HR | HR | Saputo | Onshore | Centeno; Katya | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 9h | 9h | 2017-09-05 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071360 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (HR) - Deploy1 | HR | HR | Saputo | Onshore | Centeno; Katya | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 98h | 98h | 2017-10-02 | 2017-12-01 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071361 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Support-D1 HR | HR | HR | Saputo | Onshore | Centeno; Katya | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 9h | 9h | 2017-09-05 | 2017-09-29 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 70 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071362 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (HR) - Deploy1 | HR | HR | Saputo | Onshore | Centeno; Katya | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 14h | 14h | 2017-10-02 | 2017-12-01 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071363 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (HR) - Deploy1 | HR | HR | Saputo | Onshore | Centeno; Katya | Saputo | Yes | CapEx | Localization | IT - Internal | 6h | 0h | 6h | 2017-07-31 | 2017-08-04 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -20 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071364 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (HR) - Deploy1 | HR | HR | Saputo | Onshore | Centeno; Katya | Saputo | Yes | CapEx | Localization | IT - Internal | 20h | 0h | 20h | 2017-07-11 | 2017-08-18 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 21.13 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 7 | 1.5 | 0 | 0 | 8.5 | 0 | 0 | 0 | 0 | 0
1071365 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Interface (HR) - Deploy1 | HR | HR | Saputo | Onshore | Centeno; Katya | Saputo | Yes | CapEx | Localization | IT - Internal | 24h | 0h | 24h | 2017-06-13 | 2017-07-24 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 1 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 7.5 | 8 | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071366 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-06-19 | 2017-07-14 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | -25 | 16.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071367 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-06-12 | 2017-06-16 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | -15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071368 | No | Yes | No | SDF | SDF Interim State Project | 03-Design/Build | Configuration-Sales Order output conditions & ALE | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2017-04-26 | 2017-06-09 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-05-19 | 0 | NA Others | 99000-99100-99130 NA others | -8 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 10 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071369 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 10 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071370 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2017-07-10 | 2017-07-28 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071371 | No | Yes | No | SDF | SDF Localisation | 04-Test | Execute SIT1 (OTC) - Deploy1 | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 132h | 0h | 132h | 2017-07-17 | 2017-08-24 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 25 | 20 | 15 | 36 | 16 | 0 | 0 | 0 | 0
1071372 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 55h | 0h | 55h | 2017-05-08 | 2017-06-09 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-05-19 | 2 | Base Config | 1000 D1-1300 B-1314 Base Config | -5 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071373 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-05-29 | 2017-06-30 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 5 | 0 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071374 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Execute FUT - OTC- Deploy2 | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2017-06-12 | 2017-08-24 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 16 | 10 | 4 | 0 | 0 | 0 | 15 | 0 | 20 | 0 | 0 | 0 | 0
1071375 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 38h | 0h | 38h | 2017-06-27 | 2017-08-04 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-21 | 2017-09-01 | 2 | AT | 20000 D2-20100 B-20180 AT | -45 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 15 | 0 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071376 | No | Yes | No | SDF | SDF Interim State Project | 01-Preparation | Environment setup | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2017-01-09 | 2017-01-20 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071377 | No | Yes | No | SDF | SDF Interim State Project | 03-Design/Build | IOTC010-FSD-INT-Sales order interface | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 75h | 0h | 75h | 2017-01-23 | 2017-05-26 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -90 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 10 | 12 | 15 | 10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071378 | No | Yes | No | SDF | SDF Interim State Project | 03-Design/Build | IOTC010-DEV FUT-INT-Sales order interface | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 38h | 0h | 38h | 2017-05-29 | 2017-07-14 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | 5 | 35.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 10 | 5 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071379 | No | Yes | No | SDF | SDF Interim State Project | 03-Design/Build | ILOG013-STO goods issue interface (SAP to BPCS) | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-01-14 | 2017-05-26 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -95 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071380 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 63h | 0h | 63h | 2017-07-24 | 2017-08-02 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071381 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Data Migration development - Deploy1 - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 67.5h | 0h | 67.5h | 2017-06-05 | 2017-06-16 | Yes |  |  | ACT-MDG.Data Construction | Complete | 2017-05-08 | 2017-06-09 | 1 | Data Construction | 1000 D1-1300 B-1320 Data Construction | 15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071382 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 52h | 0h | 52h | 2017-06-26 | 2017-06-30 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071383 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy1 - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 41.5h | 0h | 41.5h | 2017-06-12 | 2017-06-18 | Yes |  |  | ACT-MDG.Build ETL programs | Complete | 2017-05-08 | 2017-06-09 | 1 | Build and adjust conversion programs | 1000 D1-1300 B-1322 Build and adjust conversion programs | 15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071384 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 81h | 0h | 81h | 2017-06-12 | 2017-07-21 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071385 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 52h | 0h | 52h | 2017-06-19 | 2017-06-25 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 30 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071386 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) - Deploy1 - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 135h | 0h | 135h | 2017-05-15 | 2017-06-02 | Yes |  |  | DELIV-MDG-206.Functional Specification -Conversion | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | -20 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071387 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Mock Load - Deploy1 - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071388 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Data Validation Sheets - Deploy1 - Test - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  | WP-MDG.Data Validation Sheets | Complete | 2017-06-05 | 2017-06-16 | 1 | QE2 Prevalidation | 1000 D1-1300 B-1325 QE2 Prevalidation | -1 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071389 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 42.5h | 0h | 42.5h | 2017-07-03 | 2017-07-07 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 15 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071390 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Mock1 Validation - Deploy1 - CG- DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-05 | 2017-07-05 | Yes |  |  | ACT-MDG.Mock Validation | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071391 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Mock1 Preparation - Deploy1 - CG - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-04 | 2017-07-04 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071392 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071393 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -50 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071394 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -4.88 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071395 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-10-30 | 2017-12-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071396 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-10-30 | 2017-12-07 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 0 | 18.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071397 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-22 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071398 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071399 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071400 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 107h | 0h | 107h | 2017-08-05 | 2017-08-18 | Yes |  |  | ACT-MDG.Mock Load | Complete | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 10.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 45 | 53 | 0 | 0 | 0 | 0 | 0
1071401 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 45h | 20h | 65h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0
1071402 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-09-15 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071403 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 104h | 0h | 104h | 2017-08-21 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 27 | 45 | 0 | 0
1071404 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-11 | 2017-09-15 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071405 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071406 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071407 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy1 - HC - (Accenture) - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -21.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071408 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-22 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071409 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071410 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071411 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071412 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -50 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071413 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -4.88 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071414 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 65h | 65h | 2017-10-30 | 2017-12-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071415 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-10-30 | 2017-12-07 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 0 | 18.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071416 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy2 - HC - (Accenture) - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2018-02-05 | 2018-03-02 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | -17.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071417 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 18h | 18h | 2017-09-01 | 2017-09-15 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071418 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 154h | 0h | 154h | 2017-08-09 | 2017-09-01 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 45 | 37 | 45 | 0 | 0 | 0
1071419 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 63h | 0h | 63h | 2017-07-31 | 2017-08-08 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-07-31 | 2017-08-11 | 2 | QE2 Mock Prep | 20000 D2-20100 B-20110 QE2 Mock Prep | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 18 | 0 | 0 | 0 | 0 | 0 | 0
1071420 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 18h | 18h | 2017-09-01 | 2017-09-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 14.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071421 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 65h | 65h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071422 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071423 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 95h | 95h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071424 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071425 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy2 (Accenture) - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 176h | 0h | 176h | 2017-07-03 | 2017-07-28 | Yes |  |  | ACT-MDG.Build ETL programs | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 36 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071426 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - LOG | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071427 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG013-STO goods issue interface (SAP to BPCS) | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -95 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071428 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071429 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071430 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-29 | 2017-03-29 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -23 | -19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071431 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071432 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071433 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (DB) (Planning, reporting, CR, cross stream integration) - LOG(Global) | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | CapEx | Localization | IT - Internal | 141.5h | 154h | 295.5h | 2017-06-19 | 2017-09-25 | Yes |  |  | ACT-MDG.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 40 | 0 | 0 | 37.5 | 6 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0
1071434 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration). - LOG | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | CapEx | Localization | IT - Internal | 72h | 0h | 72h | 2017-05-08 | 2017-06-16 | Yes |  |  | ACT-FUN.Management | Future Task | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 15 | 8 | 10 | 5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071435 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG012-FSD-INT-STO interface | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -90 | -30.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071436 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG013-FSD-INT-STO goods issue interface (SAP to BPCS) | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-24 | 2017-01-24 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -89 | -50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071437 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG015-FSD-INT-Inventory adjustment interface | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-25 | 2017-01-25 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -88 | -50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071438 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Gap log - LOG | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | CapEx | Localization | IT - Internal | 11h | 0h | 11h | 2017-05-08 | 2017-05-12 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071439 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) - RTR - Deploy1 | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 7h | 0h | 7h | 2017-07-04 | 2017-07-05 | Yes |  |  | To delete-To delete.To delete | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | -15 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071440 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 configuration (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-08-14 | 2017-09-15 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | 35 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071441 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-07-17 | 2017-08-11 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 15 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071442 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 73h | 0h | 73h | 2017-08-07 | 2017-08-24 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 9.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 30 | 0 | 0 | 0 | 0
1071443 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 3h | 57h | 60h | 2017-08-28 | 2017-09-14 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 13.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
1071444 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | IRTR015 Mass Non PO Invoice and Credit Memo upload - RTR - Deploy1 | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 61h | 0h | 61h | 2017-06-27 | 2017-07-14 | Yes |  |  | DELIV-FUN-204.Functional Specification - Form | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 11 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071445 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 23h | 0h | 23h | 2017-07-17 | 2017-07-25 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071446 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Functional Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071447 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2017-05-31 | 2017-06-22 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | -14 | 72.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071448 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 7h | 7h | 2017-08-21 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071449 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 configuration (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 2h | 2h | 2017-09-05 | 2017-09-15 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071450 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Support Mock1 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-21 | 2017-10-20 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-09-25 | 2017-10-06 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -25 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071451 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Interface (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-29 | 2017-07-27 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071452 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 4h | 4h | 2017-08-30 | 2017-09-15 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071453 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 4h | 4h | 2017-08-28 | 2017-09-15 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071454 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071455 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 15h | 15h | 2017-09-05 | 2017-09-22 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071456 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Enhancement (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-05 | 2017-09-22 | Yes |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071457 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071458 | No | No | Yes | SDF | SDF Interim State Project | 01-Preparation | Environment setup | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-01-10 | 2017-02-08 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071459 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - RTR | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2017-04-24 | 2017-04-28 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -9.88 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071460 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 24h | 24h | 2017-09-05 | 2017-09-08 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071461 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 110h | 110h | 2017-07-31 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071462 | No | No | Yes | SDF | SDF Localisation | 04-Test | Regression - Run Tests (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-08-07 | 2017-08-22 | Yes |  |  | ACT-FUN.Execute Regression Test | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 9.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 4 | 0 | 0 | 0 | 0
1071463 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Interface (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 127h | 0h | 127h | 2017-06-13 | 2017-08-04 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 7 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 32 | 0 | 0 | 0 | 37 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071464 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Enhancement (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2017-06-27 | 2017-07-07 | Yes |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 21 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071465 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Form (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 100h | 0h | 100h | 2017-06-12 | 2017-09-01 | Yes |  |  | DELIV-FUN-204.Functional Specification - Form | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 5 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 2 | 0 | 0 | 0 | 38 | 0 | 0 | 1 | 8 | 33 | 0 | 0 | 0
1071466 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-10-16 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071467 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071468 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 59h | 59h | 2017-09-18 | 2017-10-13 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071469 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-09-18 | 2017-10-13 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071470 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-07-17 | 2017-08-11 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0
1071471 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - LOG | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 63.5h | 0h | 63.5h | 2017-04-18 | 2017-05-12 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5 | 38 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071472 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 55h | 0h | 55h | 2017-05-22 | 2017-06-16 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 29 | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071473 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 67h | 0h | 67h | 2017-05-29 | 2017-07-07 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 5 | 10 | 7 | 8 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071474 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 0h | 35h | 35h | 2017-06-30 | 2017-08-18 | Yes |  |  | DELIV-FUN-220.Solution Design Document (SDD) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071475 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 161h | 0h | 161h | 2017-06-19 | 2017-09-08 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-19 | 2017-06-30 | 1 | Cycle 2 Config | 1000 D1-1300 B-1318 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 16 | 15 | 15 | 11 | 20 | 20 | 12 | 16 | 15 | 15 | 0 | 0
1071476 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Data Definition Documents (DDD) (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-05-01 | 2017-06-09 | Yes |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Future Task | 2017-04-17 | 2017-05-05 | 1 | Revise DDDs - Division review | 1000 D1-1200 A-1213 Revise DDDs - Division review | 10 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071477 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Support Mock1 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 40h | 49h | 89h | 2017-08-28 | 2017-09-26 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-09-25 | 2017-10-06 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -25 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 20 | 0
1071478 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Support (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071479 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 35h | 55h | 90h | 2017-09-04 | 2017-09-26 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 10 | 16.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 25 | 0
1071480 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 0h | 108h | 108h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071481 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 0h | 24h | 24h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071482 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 0h | 24h | 24h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071483 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 0h | 108h | 108h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071484 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 31h | 0h | 31h | 2017-08-14 | 2017-09-08 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 5 | 10 | 0 | 0
1071485 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 55h | 0h | 55h | 2017-07-24 | 2017-08-11 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 5 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 15 | 0 | 0 | 0 | 0 | 0 | 0
1071486 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 13h | 0h | 13h | 2017-08-07 | 2017-08-18 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 5 | 33.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 0 | 0 | 0 | 0 | 0
1071487 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-08-14 | 2017-09-01 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 4.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 16 | 15 | 0 | 0 | 0
1071488 | No | No | Yes | SDF | SDF Interim State Project | 01-Preparation | Environment setup | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-01-09 | 2017-01-20 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071489 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 58h | 0h | 58h | 2017-06-26 | 2017-08-11 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 15 | 20 | 8 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0
1071490 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Support (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 38h | 0h | 38h | 2017-06-26 | 2017-07-21 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071491 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 97h | 0h | 97h | 2017-05-15 | 2017-06-16 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 5 | 23 | 20 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071492 | No | Yes | No | SDF | SDF Localisation | 04-Test | Mock2Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Crodua; Michelle | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-01 | 2017-08-01 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071493 | No | Yes | No | SDF | SDF Localisation | 04-Test | Mock2- Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Crodua; Michelle | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-15 | 2017-09-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071494 | No | Yes | No | SDF | SDF Localisation | 04-Test | Mock2Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Crodua; Michelle | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-01 | 2017-08-01 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071495 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Crodua; Michelle | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071496 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Crodua; Michelle | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 14.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071497 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Crodua; Michelle | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-07-31 | 2017-08-11 | 2 | QE2 Mock Prep | 20000 D2-20100 B-20110 QE2 Mock Prep | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071498 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Crodua; Michelle | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071499 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy2 (Accenture) - DC | MDG | DC | SI | Offshore | Crodua; Michelle | Accenture | Yes | CapEx | Localization | IT - External | 216h | 0h | 216h | 2017-07-04 | 2017-08-04 | Yes |  |  | ACT-MDG.Build ETL programs | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 45 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071500 | No | Yes | No | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy2 - HC - (Accenture) - DC | MDG | DC | SI | Offshore | Crodua; Michelle | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2018-02-05 | 2018-02-05 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | -17.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071501 | No | Yes | No | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Crodua; Michelle | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-10-30 | 2017-10-30 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071502 | No | Yes | No | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Crodua; Michelle | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-12-01 | 2017-12-01 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 0 | 18.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071503 | No | Yes | No | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Crodua; Michelle | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-11-06 | 2017-11-06 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -4.88 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071504 | No | Yes | No | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Crodua; Michelle | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-11-06 | 2017-11-06 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -50 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071505 | No | Yes | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Crodua; Michelle | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-12-25 | 2017-12-25 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071506 | No | Yes | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Crodua; Michelle | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-12-25 | 2017-12-25 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071507 | No | Yes | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Crodua; Michelle | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-12-25 | 2017-12-25 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071508 | No | Yes | No | SDF | SDF Localisation | 04-Test | Mock2- Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Crodua; Michelle | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-01 | 2017-08-01 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071509 | No | Yes | No | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Crodua; Michelle | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-12-22 | 2017-12-22 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071510 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-23 | 2017-03-23 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -17 | -12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071511 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -20 | -16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071512 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -22.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071513 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | -9.88 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071514 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-10 | 2017-04-10 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071515 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTP | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | CapEx | Localization | IT - Internal | 103h | 0h | 103h | 2017-05-29 | 2017-06-16 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 43 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071516 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - PTP | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-01 | 2017-03-01 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -33 | -35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071517 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTP (Global) | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | CapEx | Localization | IT - Internal | 185h | 105h | 290h | 2017-07-17 | 2017-08-21 | Yes |  |  | ACT-FUN.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 48 | 39 | 48 | 0 | 0 | 0 | 0 | 0
1071518 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTP | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | CapEx | Localization | IT - Internal | 208h | 0h | 208h | 2017-06-07 | 2017-07-13 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 28 | 88 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071519 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-10-02 | 2017-11-17 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071520 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 230h | 230h | 2017-09-25 | 2017-11-17 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071521 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-11 | 2017-09-22 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071522 | No | No | Yes | SDF | SDF Localisation | 04-Test | DR - Support (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 50h | 0h | 50h | 2017-07-31 | 2017-08-21 | Yes |  |  | ACT-FUN.Dry Run activities | Complete | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 36 | 0 | 0 | 0 | 0 | 0
1071523 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2017-09-08 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071524 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 12h | 30h | 42h | 2017-08-28 | 2017-09-15 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0
1071525 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2017-07-10 | 2017-07-12 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 1 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071526 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDD Writing - RTR - Deploy1 | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-23 | 2017-06-23 | Yes |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071527 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - RTR | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-04-17 | 2017-04-21 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -9.88 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071528 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071529 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 7h | 0h | 7h | 2017-03-20 | 2017-03-24 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071530 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | RTM - RTR | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-17 | 2017-04-18 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071531 | No | Yes | No | SDF | SDF Interim State Project | 02-Analyze | Workshop-Batch handling | PTP | FUN | SI | Onshore | Ruetz; Christoph | SAP | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2017-03-13 | 2017-03-24 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071532 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTP) - Deploy1 | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 31h | 0h | 31h | 2017-07-17 | 2017-09-01 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 15 | 8 | 0 | 0 | 0
1071533 | No | No | Yes | SDF | SDF Interim State Project | 01-Preparation | Environment setup | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 13h | 0h | 13h | 2017-01-10 | 2017-01-30 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 5 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071534 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 70h | 0h | 70h | 2017-06-19 | 2017-08-23 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 15 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 6 | 10 | 14 | 0 | 10 | 5 | 3 | 6 | 6 | 0 | 0 | 0 | 0
1071535 | No | No | Yes | SDF | SDF Localisation | 04-Test | Regression - Run Tests (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-08-07 | 2017-08-24 | Yes |  |  | ACT-FUN.Execute Regression Test | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 9.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 3 | 0 | 0 | 0 | 0
1071536 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-09-05 | 2017-09-18 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071537 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-05-22 | 2017-06-22 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | -14 | 72.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 0 | 18 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071538 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | SDF-INT-Workshop-Finance | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2017-03-01 | 2017-04-06 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071539 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - RTR | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-05-01 | 2017-08-04 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 3 | 5 | 10 | 2 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071540 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - RTR (Global) | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 69h | 90h | 159h | 2017-07-17 | 2017-11-03 | Yes |  |  | ACT-FUN.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 10 | 10 | 15 | 6 | 4 | 15 | 0 | 0 | 0
1071541 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 35h | 35h | 2017-08-21 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071542 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071543 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 configuration (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 10h | 10h | 2017-08-14 | 2017-09-15 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | 35 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071544 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 configuration (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 2h | 2h | 2017-09-05 | 2017-09-15 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071545 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Enhancement (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 10h | 10h | 2017-09-05 | 2017-09-15 | Yes |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071546 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 15h | 15h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071547 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 15h | 15h | 2017-09-05 | 2017-09-22 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071548 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071549 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 4h | 4h | 2017-08-28 | 2017-09-15 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071550 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | IXXX-DEV FUT-G/L interface | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-08-09 | 2017-08-21 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | 50 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 | 2 | 0 | 0 | 0 | 0
1071551 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | PDD-Reconcialition process design | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 22h | 0h | 22h | 2017-07-04 | 2017-09-01 | Yes |  |  | DELIV-FUN-110.PDDs | Future Task | 2017-05-01 | 2017-05-05 | 0 | NA Others | 99000-99100-99130 NA others | 25 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 7 | 7 | 0 | 0 | 0
1071552 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Interface (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 30h | 0h | 30h | 2017-07-18 | 2017-07-24 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 7 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071553 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-25 | 2017-10-13 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071554 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 44h | 44h | 2017-09-18 | 2017-10-13 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071555 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 49h | 49h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071556 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-10-16 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071557 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Schedule-Course Offerings (Design/Build) | Test | Test | Saputo | Onshore | Wong; Justin | Saputo | Yes | OpEx | Localization | IT - Internal | 4h | 35.28h | 39.28h | 2017-07-17 | 2017-08-01 | Yes |  |  | DELIV-CM-402.Training Schedule and Logistics | Future Task | 2017-06-26 | 2017-07-28 | 1 | Training Schedule | 1000 D1-1800 MultiPhases-1820 Training Schedule | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071558 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Manage UAT (Test) - Deploy1 | Test | Test | Saputo | Onshore | Wong; Justin | Saputo | Yes | CapEx | Localization | IT - Internal | 40h | 160h | 200h | 2017-08-28 | 2017-09-29 | Yes |  |  | ACT-Test.Management | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0
1071559 | No | No | Yes | SDF | SDF Localisation | 04-Test | Manage SIT (Test) - Deploy1 | Test | Test | Saputo | Onshore | Wong; Justin | Saputo | Yes | CapEx | Localization | IT - Internal | 276h | 0h | 276h | 2017-07-10 | 2017-08-25 | Yes |  |  | ACT-Test.Management | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 38 | 38 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0
1071560 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | SI | Offshore | Singh; Virender | IBM | Yes | CapEx | Localization | IT - External | 87h | 56h | 143h | 2017-02-13 | 2017-10-31 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 5 | 28 | 24 | 0 | 0 | 9 | 4 | 9 | 0 | 0 | 0 | 0 | 2 | 0 | 0
1071561 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Singh; Virender | IBM | Yes | CapEx | Localization | IT - External | 0h | 165h | 165h | 2017-10-09 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071562 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing WRICEFs (Design/Build) | DEV | DEV | SI | Offshore | Singh; Virender | IBM | Yes | CapEx | Localization | IT - External | 128h | 130.4h | 258.4h | 2017-04-24 | 2017-11-03 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -88 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 36 | 9 | 9 | 18 | 9 | 0 | 0 | 13 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071563 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | SI | Offshore | Singh; Virender | IBM | Yes | CapEx | Localization | IT - External | 233h | 18h | 251h | 2017-07-17 | 2017-09-18 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 9 | 12 | 36 | 32 | 28 | 31 | 40 | 27 | 0
1071564 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy1 (Design/Build) | DEV | DEV | SI | Offshore | Singh; Virender | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-07-20 | 2017-08-03 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 17 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071565 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | SI | Offshore | Singh; Virender | IBM | Yes | CapEx | Localization | IT - External | 39h | 0h | 39h | 2017-09-06 | 2017-09-18 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 36 | 0
1071566 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Singh; Virender | IBM | Yes | CapEx | Localization | IT - External | 0h | 135h | 135h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071567 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | SI | Offshore | Singh; Virender | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071568 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Singh; Virender | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071569 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Singh; Virender | IBM | Yes | CapEx | Localization | IT - External | 26h | 0h | 26h | 2017-08-18 | 2017-08-29 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 14 | 0 | 0 | 0
1071570 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Subhedar; Adheesh | IBM | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2017-08-23 | 2017-08-27 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0
1071571 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Subhedar; Adheesh | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-08-04 | 2017-08-08 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 12 | 0 | 0 | 0 | 0 | 0 | 0
1071572 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | SI | Offshore | Subhedar; Adheesh | IBM | Yes | CapEx | Localization | IT - External | 121h | 20h | 141h | 2017-06-20 | 2017-09-20 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 30 | 7 | 34 | 18 | 0 | 11 | 15 | 0
1071573 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | SI | Offshore | Subhedar; Adheesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 110h | 110h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071574 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Subhedar; Adheesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071575 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | SI | Offshore | Subhedar; Adheesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2016-12-28 | 2017-10-31 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071576 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | SI | Offshore | Subhedar; Adheesh | IBM | Yes | CapEx | Localization | IT - External | 78h | 25h | 103h | 2017-08-28 | 2017-09-18 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 24 | 5 | 0
1071577 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing WRICEFs (Design/Build) | DEV | DEV | SI | Offshore | Subhedar; Adheesh | IBM | Yes | CapEx | Localization | IT - External | 966h | 120h | 1,086h | 2017-02-20 | 2017-11-03 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -88 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 44 | 44 | 44 | 44 | 44 | 35 | 36 | 44 | 37 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 33 | 40 | 22 | 44 | 44 | 34 | 6 | 23 | 2 | 0 | 0 | 0 | 0 | 0
1071578 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Subhedar; Adheesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 95h | 95h | 2017-10-09 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071579 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | D&B - Customer Master - SI - Deploy1 - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | OpEx | Localization | IT - External | 46h | 0h | 46h | 2017-06-20 | 2017-07-21 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-06-09 | 1 | Build and adjust conversion programs | 1000 D1-1300 B-1322 Build and adjust conversion programs | 31 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 6 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071580 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | D&B - Vendor Master - SI - Deploy1 - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | OpEx | Localization | IT - External | 45h | 0h | 45h | 2017-06-20 | 2017-07-21 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-06-09 | 1 | Build and adjust conversion programs | 1000 D1-1300 B-1322 Build and adjust conversion programs | 31 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 10 | 6 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071581 | No | Yes | No | SDF | SDF Localisation | 04-Test | Test - Customer Master - SI - Deploy1 - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | OpEx | Localization | IT - External | 7h | 0h | 7h | 2017-07-19 | 2017-07-26 | Yes |  |  | ACT-FUN.Execute SIT | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | -13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071582 | No | Yes | No | SDF | SDF Localisation | 04-Test | Test - Vendor Master - SI - Deploy1 - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | OpEx | Localization | IT - External | 13h | 0h | 13h | 2017-07-19 | 2017-07-28 | Yes |  |  | ACT-FUN.Execute SIT | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | -13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071583 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071584 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071585 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Support (LOG) - Deploy1 | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071586 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071587 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy1 | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-07-24 | 2017-08-11 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 5 | 33.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071588 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 14h | 1h | 15h | 2017-08-07 | 2017-08-21 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 4.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0
1071589 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy1 | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 49h | 0h | 49h | 2017-07-24 | 2017-08-04 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 5 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071590 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-08-14 | 2017-09-01 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071591 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (LOG) - Deploy2 | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-09-05 | 2017-09-15 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | -55 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071592 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Support (LOG) - Deploy1 | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071593 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071594 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 0h | 150h | 150h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071595 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (LOG) - Deploy2 | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 86.5h | 0h | 86.5h | 2017-08-14 | 2017-09-15 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | -8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 11.5 | 14 | 12 | 35 | 0
1071596 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 configuration (LOG) - Deploy2 | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 116.5h | 0h | 116.5h | 2017-08-14 | 2017-09-08 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 32.5 | 30 | 24 | 0 | 0
1071597 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-10-09 | 2017-10-09 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071598 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-18 | 2017-09-18 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071599 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 0h | 145h | 145h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071600 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (LOG) - Deploy2 | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-08-28 | 2017-09-15 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 10 | 16.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0
1071601 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Support Mock1 (LOG) - Deploy2 | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 0h | 35h | 35h | 2017-08-21 | 2017-09-15 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-09-25 | 2017-10-06 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -25 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071602 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 69h | 0h | 69h | 2017-07-10 | 2017-08-11 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-19 | 2017-06-30 | 1 | Cycle 2 Config | 1000 D1-1300 B-1318 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 24 | 30 | 0 | 0 | 0 | 0 | 0 | 0
1071603 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) (LOG) - Deploy1 | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 0h | 5h | 5h | 2017-06-30 | 2017-07-07 | Yes |  |  | DELIV-FUN-220.Solution Design Document (SDD) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071604 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 24.3h | 0h | 24.3h | 2017-06-26 | 2017-07-07 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.3 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071605 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (LOG) - Deploy1 | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 30.9h | 0h | 30.9h | 2017-06-05 | 2017-06-25 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.3 | 10.3 | 10.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071606 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-21 | 2017-07-21 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071607 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Data Migration development - Deploy1 - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 121.5h | 0h | 121.5h | 2017-06-05 | 2017-06-23 | Yes |  |  | ACT-MDG.Data Construction | Complete | 2017-05-08 | 2017-06-09 | 1 | Data Construction | 1000 D1-1300 B-1320 Data Construction | 15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 54 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071608 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 99h | 0h | 99h | 2017-07-20 | 2017-08-04 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071609 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 83h | 0h | 83h | 2017-06-19 | 2017-07-14 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 30 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.5 | 30 | 0 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071610 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 105.5h | 0h | 105.5h | 2017-06-27 | 2017-07-21 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 27 | 22.5 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071611 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy1 - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-16 | 2017-06-16 | Yes |  |  | ACT-MDG.Build ETL programs | Complete | 2017-05-08 | 2017-06-09 | 1 | Build and adjust conversion programs | 1000 D1-1300 B-1322 Build and adjust conversion programs | 15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071612 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Mock1 Preparation - Deploy1 - CG - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-04 | 2017-07-04 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071613 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Mock1 Validation - Deploy1 - CG- DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-05 | 2017-07-05 | Yes |  |  | ACT-MDG.Mock Validation | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071614 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-21 | 2017-07-21 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 15 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071615 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Data Validation Sheets - Deploy1 - Test - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-07 | 2017-07-07 | Yes |  |  | WP-MDG.Data Validation Sheets | Complete | 2017-06-05 | 2017-06-16 | 1 | QE2 Prevalidation | 1000 D1-1300 B-1325 QE2 Prevalidation | -1 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071616 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Mock Load - Deploy1 - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071617 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) - Deploy1 - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 108h | 0h | 108h | 2017-05-15 | 2017-06-02 | Yes |  |  | DELIV-MDG-206.Functional Specification -Conversion | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | -20 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 36 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071618 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy1 - HC - (Accenture) - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -21.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071619 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 79h | 0h | 79h | 2017-08-14 | 2017-08-25 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 53 | 0 | 0 | 0 | 0
1071620 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-09-15 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071621 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 25h | 20h | 45h | 2017-09-12 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0
1071622 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071623 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-08-07 | 2017-09-07 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0
1071624 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 116h | 0h | 116h | 2017-08-07 | 2017-09-01 | Yes |  |  | ACT-MDG.Mock Load | Complete | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 10.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 26 | 0 | 45 | 0 | 0 | 0
1071625 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 20h | 30h | 50h | 2017-09-12 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0
1071626 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071627 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071628 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071629 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-22 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071630 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-10-30 | 2017-12-07 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 0 | 18.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071631 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 85h | 85h | 2017-10-30 | 2017-12-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071632 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -4.88 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071633 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -50 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071634 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-01 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 14.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071635 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-01 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071636 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-01 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071637 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy2 (Accenture) - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 180h | 0h | 180h | 2017-07-03 | 2017-07-28 | Yes |  |  | ACT-MDG.Build ETL programs | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071638 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 99h | 0h | 99h | 2017-08-21 | 2017-09-01 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 45 | 0 | 0 | 0
1071639 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-09-04 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0
1071640 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-07-31 | 2017-08-11 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-07-31 | 2017-08-11 | 2 | QE2 Mock Prep | 20000 D2-20100 B-20110 QE2 Mock Prep | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0
1071641 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 55h | 0h | 55h | 2017-08-14 | 2017-08-18 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 14.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0
1071642 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071643 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 45h | 40h | 85h | 2017-09-11 | 2017-10-13 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0
1071644 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 0h | 65h | 65h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071645 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 0h | 100h | 100h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071646 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy2 - HC - (Accenture) - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2018-02-05 | 2018-03-02 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | -17.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071647 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071648 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-22 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071649 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071650 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071651 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -4.88 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071652 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -50 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071653 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 0h | 55h | 55h | 2017-10-30 | 2017-12-07 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 0 | 18.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071654 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 0h | 65h | 65h | 2017-10-30 | 2017-12-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071655 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-09-11 | 2017-09-22 | Yes |  | DMS | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071656 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | DMS – PDD Updates - PTM | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | Yes |  | DMS | DELIV-FUN-110.PDDs | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071657 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | DMS Configuration/UT - Operations - PTM - Deploy1 | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 100h | 0h | 100h | 2017-06-09 | 2017-07-21 | Yes |  | DMS | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | -5 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 36 | 0 | 0 | 16 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071658 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | DMS GD Fit/Gap - PTM | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-04-24 | 2017-05-12 | Yes |  | DMS | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071659 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | DMS GD Fit/Gap - PTM | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-05-02 | 2017-05-04 | Yes |  | DMS | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071660 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | DMS Test Preparation - PTM - Deploy1 | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-07-24 | 2017-07-28 | Yes |  | DMS | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071661 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | DMS SDD Reconciliation - PTM - Deploy1 | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2017-08-07 | 2017-08-08 | Yes |  | DMS | DELIV-FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0
1071662 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 44h | 44h | 2017-09-25 | 2017-09-29 | Yes |  | DMS | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071663 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-08-28 | 2017-09-22 | Yes |  | DMS | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071664 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-25 | 2017-09-25 | Yes |  | DMS | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071665 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-10-02 | 2017-12-15 | Yes |  | DMS | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071666 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 88h | 88h | 2018-01-15 | 2018-01-26 | Yes |  | DMS | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -30 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071667 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 132h | 132h | 2018-01-15 | 2018-01-30 | Yes |  | DMS | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -8 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071668 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 120h | 120h | 2018-02-05 | 2018-03-30 | Yes |  | DMS | ACT-FUN.Functional Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071669 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-12-04 | 2017-12-29 | Yes |  | DMS | ACT-FUN.Execute UAT | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071670 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-12-04 | 2017-12-29 | Yes |  | DMS | ACT-FUN.Functional Break/Fix | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071671 | No | No | Yes | SDF | SDF Localisation | 04-Test | DR - Support (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-11-20 | 2017-12-01 | Yes |  | DMS | ACT-FUN.Dry Run activities | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071672 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Support-D2 PTM | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 22h | 22h | 2017-10-02 | 2017-12-15 | Yes |  | DMS |  | Future Task | 2017-09-18 | 2017-11-03 | 2 | Training Material Localization | 20000 D2-29000 MultiPhases-29040 Training Material Localization | 10 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071673 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | Build DEV 2 | TAI | TAI | SI | Onshore | Barman; Tapan | Accenture | Yes | CapEx | Localization | IT - External | 176h | 0h | 176h | 2016-11-21 | 2016-12-23 | Yes |  |  | DELIV-TAI-101.Development Environment | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071674 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Agrawal; Purvi | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071675 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Agrawal; Purvi | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-08-28 | 2017-09-14 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 9 | 5 | 0
1071676 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | SI | Offshore | Agrawal; Purvi | IBM | Yes | CapEx | Localization | IT - External | 0h | 45h | 45h | 2016-12-28 | 2017-10-31 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071677 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing WRICEFs (Design/Build) | DEV | DEV | SI | Offshore | Agrawal; Purvi | IBM | Yes | CapEx | Localization | IT - External | 390h | 80h | 470h | 2017-03-17 | 2017-11-03 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -88 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 30 | 0 | 36 | 31 | 36 | 45 | 4 | 0 | 0 | 30 | 38 | 39 | 31 | 37 | 6 | 8 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0
1071678 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | SI | Offshore | Agrawal; Purvi | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-01 | 2017-09-29 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071679 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | SI | Offshore | Agrawal; Purvi | IBM | Yes | CapEx | Localization | IT - External | 174h | 0h | 174h | 2017-07-07 | 2017-09-15 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 18 | 26 | 36 | 15 | 36 | 40 | 0
1071680 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy1 (Design/Build) | DEV | DEV | SI | Offshore | Agrawal; Purvi | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-06-30 | 2017-07-28 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071681 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Agrawal; Purvi | IBM | Yes | CapEx | Localization | IT - External | 0h | 140h | 140h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071682 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Agrawal; Purvi | IBM | Yes | CapEx | Localization | IT - External | 0h | 95h | 95h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071683 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | SI | Offshore | Agrawal; Purvi | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071684 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-09-05 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071685 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 45h | 30h | 75h | 2017-09-04 | 2017-09-20 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0
1071686 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTP) - Deploy2 | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-08-25 | 2017-09-22 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | -50 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071687 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTP) - Deploy2 | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-09-11 | 2017-09-22 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 20 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071688 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 0h | 55h | 55h | 2017-07-19 | 2017-08-25 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071689 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-07-25 | 2017-07-31 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071690 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 46h | 0h | 46h | 2017-08-21 | 2017-09-01 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 36 | 0 | 0 | 0
1071691 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-12-04 | 2017-12-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071692 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-12-04 | 2017-12-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071693 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Support (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071694 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 15h | 15h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071695 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-09-11 | 2017-09-25 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071696 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-10-02 | 2017-10-20 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071697 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-10-02 | 2017-10-20 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071698 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-08-30 | 2017-09-15 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071699 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-09-08 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071700 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 8h | 45h | 53h | 2017-08-29 | 2017-09-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0
1071701 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 5h | 10h | 15h | 2017-08-14 | 2017-08-28 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 13.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0
1071702 | No | No | Yes | SDF | SDF Localisation | 04-Test | DR - Support (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 42h | 0h | 42h | 2017-08-21 | 2017-09-01 | Yes |  |  | ACT-FUN.Dry Run activities | Complete | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 22 | 0 | 0 | 0
1071703 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-21 | 2017-07-21 | Yes |  |  | ACT-FUN.Functional Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071704 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-20 | 2017-06-20 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 1 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071705 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDD Writing - RTR - Deploy1 | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-16 | 2017-06-16 | Yes |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071706 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - RTR | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071707 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071708 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071709 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | -15 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071710 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -35 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071711 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 3h | 0h | 3h | 2017-03-13 | 2017-03-28 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071712 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - RTR | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -35 | -16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071713 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - RTR | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 54h | 0h | 54h | 2017-04-21 | 2017-05-12 | Yes |  |  | ACT-FUN.Management | Future Task | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 35 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071714 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Log Gaps - RTR | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-05-01 | 2017-05-01 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -2 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071715 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | SDF-INT-Workshop-Finance | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-03-28 | 2017-04-12 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071716 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - RTR (Global) | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 570h | 570h | 2017-09-08 | 2018-02-16 | Yes |  |  | ACT-FUN.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071717 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - RTR | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-13 | 2017-04-13 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -9.88 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071718 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | RTM - RTR | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071719 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | Workshop-Design Interim state financial reporting | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-16 | 2017-06-16 | Yes |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071720 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | Support to Data (financial Data object mapping) | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071721 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | PDD-Reconcialition process design | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 6h | 6h | 2017-07-04 | 2017-07-21 | Yes |  |  | DELIV-FUN-110.PDDs | Future Task | 2017-05-01 | 2017-05-05 | 0 | NA Others | 99000-99100-99130 NA others | 25 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071722 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | Workshop-Design Map GL Posting | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | Yes |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071723 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTP) - Deploy2 | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-09-11 | 2017-09-22 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 20 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071724 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - PTP | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 74h | 0h | 74h | 2017-04-24 | 2017-05-05 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071725 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | RTM - PTP | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 48h | 0h | 48h | 2017-04-26 | 2017-06-15 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -29.88 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071726 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Gap log - PTP | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-04-17 | 2017-04-21 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -22.88 | 70.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071727 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - PTP | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-01 | 2017-03-01 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -33 | -35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071728 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-04-10 | 2017-04-13 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071729 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | -9.88 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071730 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | MCP Mini config and masterdata for US and Canada | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 50h | 0h | 50h | 2017-01-23 | 2017-02-24 | Yes |  |  | ACT-FUN.Configuration | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071731 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTP) - Deploy2 | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-09-01 | 2017-09-29 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | -50 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071732 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTP) - Deploy2 | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071733 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTP) - Deploy2 | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071734 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-08-28 | 2017-10-06 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071735 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTP) - Deploy2 | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071736 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 20h | 40h | 60h | 2017-08-07 | 2017-08-25 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0
1071737 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 0h | 110h | 110h | 2017-09-25 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071738 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-09-05 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071739 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-03-27 | 2017-03-31 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -17 | -12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071740 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 46h | 0h | 46h | 2017-04-03 | 2017-04-07 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -20 | -16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071741 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-03-13 | 2017-03-16 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -22.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071742 | No | No | Yes | SDF | SDF Localisation | 99-Global | Data quality - DG | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | OpEx | Localization | IT - Internal | 219h | 600.8h | 819.8h | 2017-07-24 | 2018-06-20 | Yes |  |  | DELIV-MDG-101.Data Governance Policies & Quality | Future Task | NA | NA | 9 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 5 | 9 | 53 | 49 | 43 | 50 | 0
1071743 | No | No | Yes | SDF | SDF Localisation | 99-Global | Data Governance – Change Process - DG | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | OpEx | Localization | IT - Internal | 3h | 0h | 3h | 2017-07-24 | 2017-07-28 | Yes |  |  | DELIV-MDG-100.Data Governance Procedures | Future Task | NA | NA | 9 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071744 | No | No | Yes | SDF | SDF Localisation | 99-Global | Policies, Standards, Business Rules and Metrics - DG | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | OpEx | Localization | IT - Internal | 6h | 0h | 6h | 2017-07-24 | 2017-07-28 | Yes |  |  | DELIV-MDG-101.Data Governance Policies & Quality | Complete | NA | NA | 9 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071745 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071746 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-22 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071747 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 0h | 55h | 55h | 2017-10-30 | 2017-12-07 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 0 | 18.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071748 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 0h | 100h | 100h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071749 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -4.88 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071750 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 0h | 65h | 65h | 2017-10-30 | 2017-12-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071751 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071752 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -50 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071753 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071754 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy2 - HC - (Accenture) - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2018-02-05 | 2018-03-02 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | -17.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071755 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 0h | 65h | 65h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071756 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071757 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 45h | 25h | 70h | 2017-09-11 | 2017-10-03 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0
1071758 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-09-04 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 14.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0
1071759 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 81h | 0h | 81h | 2017-08-07 | 2017-08-18 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 36 | 0 | 0 | 0 | 0 | 0
1071760 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 92h | 0h | 92h | 2017-08-21 | 2017-09-01 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 45 | 0 | 0 | 0
1071761 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-07-31 | 2017-08-04 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-07-31 | 2017-08-11 | 2 | QE2 Mock Prep | 20000 D2-20100 B-20110 QE2 Mock Prep | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071762 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy2 (Accenture) - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 171h | 0h | 171h | 2017-07-04 | 2017-07-28 | Yes |  |  | ACT-MDG.Build ETL programs | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071763 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | SI | Offshore | Tayal; Nidhi | IBM | Yes | CapEx | Localization | IT - External | 0h | 35h | 35h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071764 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Tayal; Nidhi | IBM | Yes | CapEx | Localization | IT - External | 0h | 120h | 120h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071765 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy1 (Design/Build) | DEV | DEV | SI | Offshore | Tayal; Nidhi | IBM | Yes | CapEx | Localization | IT - External | 26h | 0h | 26h | 2017-06-27 | 2017-06-30 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071766 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | SI | Offshore | Tayal; Nidhi | IBM | Yes | CapEx | Localization | IT - External | 222h | 23h | 245h | 2017-07-31 | 2017-09-20 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 31 | 34 | 36 | 37 | 25 | 29 | 0
1071767 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | SI | Offshore | Tayal; Nidhi | IBM | Yes | CapEx | Localization | IT - External | 8h | 38.9h | 46.9h | 2017-08-28 | 2017-09-29 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0
1071768 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing WRICEFs (Design/Build) | DEV | DEV | SI | Offshore | Tayal; Nidhi | IBM | Yes | CapEx | Localization | IT - External | 22h | 40h | 62h | 2017-06-21 | 2017-11-03 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -88 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071769 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | SI | Offshore | Tayal; Nidhi | IBM | Yes | CapEx | Localization | IT - External | 72h | 50h | 122h | 2017-02-13 | 2017-10-31 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 9 | 13 | 5.5 | 14 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071770 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Tayal; Nidhi | IBM | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071771 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Tayal; Nidhi | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-09-04 | 2017-09-14 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 16 | 0
1071772 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Tayal; Nidhi | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071773 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Agarwal; Khushbu | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-08-01 | 2017-08-11 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 10 | 0 | 0 | 0 | 0 | 0 | 0
1071774 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Agarwal; Khushbu | IBM | Yes | CapEx | Localization | IT - External | 6.5h | 0h | 6.5h | 2017-08-24 | 2017-08-24 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.5 | 0 | 0 | 0 | 0
1071775 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | SI | Offshore | Agarwal; Khushbu | IBM | Yes | CapEx | Localization | IT - External | 163.5h | 0h | 163.5h | 2017-06-20 | 2017-09-15 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 8 | 26 | 18 | 26 | 39 | 45 | 0
1071776 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | SI | Offshore | Agarwal; Khushbu | IBM | Yes | CapEx | Localization | IT - External | 92h | 45h | 137h | 2016-12-28 | 2017-10-31 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 9 | 0 | 7 | 0 | 18 | 45 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 0
1071777 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing WRICEFs (Design/Build) | DEV | DEV | SI | Offshore | Agarwal; Khushbu | IBM | Yes | CapEx | Localization | IT - External | 0h | 45h | 45h | 2017-09-01 | 2017-11-03 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -88 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071778 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | SI | Offshore | Agarwal; Khushbu | IBM | Yes | CapEx | Localization | IT - External | 25h | 20.63h | 45.63h | 2017-08-28 | 2017-09-29 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 6 | 0 | 0
1071779 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Agarwal; Khushbu | IBM | Yes | CapEx | Localization | IT - External | 0h | 150h | 150h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071780 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Agarwal; Khushbu | IBM | Yes | CapEx | Localization | IT - External | 0h | 130h | 130h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071781 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | SI | Offshore | Agarwal; Khushbu | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071782 | No | No | Yes | SDF | SDF Localisation | 99-Global | Team Lead - MDG - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 332h | 1,500h | 1,832h | 2017-07-24 | 2018-03-30 | Yes |  |  | DELIV-FUN-029.Site Assessment | On Schedule | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 64 | 64 | 56 | 46 | 52 | 0 | 0 | 0
1071783 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test-RT Execution Plan-FIN-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-25 | 2017-08-25 | Yes |  |  |  | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071784 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test-RT Execution Plan-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-25 | 2017-08-25 | Yes |  |  |  | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071785 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test-RT Execution Plan-VM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-25 | 2017-08-25 | Yes |  |  |  | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071786 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test-SIT, UAT Execution Plan-FIN-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | Yes |  |  |  | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071787 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test-SIT, UAT Execution Plan-VM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | Yes |  |  |  | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071788 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test-SIT, UAT Execution Plan-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | Yes |  |  |  | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071789 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | SI | Offshore | Kalra; Inderjeet | IBM | Yes | CapEx | Localization | IT - External | 0h | 110h | 110h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071790 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Kalra; Inderjeet | IBM | Yes | CapEx | Localization | IT - External | 0h | 110h | 110h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071791 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Kalra; Inderjeet | IBM | Yes | CapEx | Localization | IT - External | 0h | 130h | 130h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071792 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | SI | Offshore | Kalra; Inderjeet | IBM | Yes | CapEx | Localization | IT - External | 61h | 11.63h | 72.63h | 2017-08-28 | 2017-09-21 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 2 | 20 | 0
1071793 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | SI | Offshore | Kalra; Inderjeet | IBM | Yes | CapEx | Localization | IT - External | 124h | 16h | 140h | 2017-08-07 | 2017-09-19 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 24 | 14 | 14 | 33 | 24 | 0
1071794 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy1 (Design/Build) | DEV | DEV | SI | Offshore | Kalra; Inderjeet | IBM | Yes | CapEx | Localization | IT - External | 31h | 0h | 31h | 2017-06-26 | 2017-07-28 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 4 | 8 | 2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071795 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing WRICEFs (Design/Build) | DEV | DEV | SI | Offshore | Kalra; Inderjeet | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-17 | 2017-02-17 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -88 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071796 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | SI | Offshore | Kalra; Inderjeet | IBM | Yes | CapEx | Localization | IT - External | 24h | 80.72h | 104.72h | 2017-02-13 | 2017-10-31 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 0 | 0 | 3 | 4 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
1071797 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Kalra; Inderjeet | IBM | Yes | CapEx | Localization | IT - External | 17h | 0h | 17h | 2017-07-31 | 2017-08-04 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071798 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Kalra; Inderjeet | IBM | Yes | CapEx | Localization | IT - External | 57h | 0h | 57h | 2017-08-07 | 2017-08-28 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 30 | 0 | 0 | 0 | 0
1071799 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Prakash; Gaurav | IBM | Yes | CapEx | Localization | IT - External | 5h | 25h | 30h | 2017-09-06 | 2017-09-20 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0
1071800 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Prakash; Gaurav | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071801 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | SI | Offshore | Prakash; Gaurav | IBM | Yes | CapEx | Localization | IT - External | 11h | 106h | 117h | 2017-02-13 | 2017-10-31 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071802 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing WRICEFs (Design/Build) | DEV | DEV | SI | Offshore | Prakash; Gaurav | IBM | Yes | CapEx | Localization | IT - External | 11h | 40h | 51h | 2017-04-12 | 2017-11-03 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -88 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071803 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy1 (Design/Build) | DEV | DEV | SI | Offshore | Prakash; Gaurav | IBM | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2017-05-29 | 2017-09-07 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 19 | 6 | 0 | 0
1071804 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | SI | Offshore | Prakash; Gaurav | IBM | Yes | CapEx | Localization | IT - External | 161h | 40h | 201h | 2017-08-01 | 2017-09-15 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 31 | 0 | 36 | 36 | 30 | 0 | 0
1071805 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | SI | Offshore | Prakash; Gaurav | IBM | Yes | CapEx | Localization | IT - External | 0h | 35h | 35h | 2017-08-28 | 2017-09-29 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071806 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Prakash; Gaurav | IBM | Yes | CapEx | Localization | IT - External | 0h | 145h | 145h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071807 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Prakash; Gaurav | IBM | Yes | CapEx | Localization | IT - External | 0h | 120h | 120h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071808 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | SI | Offshore | Prakash; Gaurav | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071809 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (OTC) - Deploy1 | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 71h | 7h | 78h | 2017-07-31 | 2017-09-11 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 25 | 20 | 0 | 5 | 8 | 0 | 0
1071810 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 15h | 0h | 15h | 2017-06-26 | 2017-07-14 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-21 | 2017-09-01 | 2 | AT | 20000 D2-20100 B-20180 AT | -45 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071811 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (OTC) - Deploy1 | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 66h | 0h | 66h | 2017-07-31 | 2017-09-08 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 15 | 15 | 0 | 15 | 12 | 0 | 0
1071812 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - OTC | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -30 | -30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071813 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 0h | 180h | 180h | 2018-01-29 | 2018-03-30 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071814 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 0h | 10h | 10h | 2018-01-03 | 2018-01-12 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -30 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071815 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Support-D2 | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | OpEx | Localization | Business | 0h | 35h | 35h | 2017-11-06 | 2017-12-22 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-09-18 | 2017-11-03 | 2 | Training Material Localization | 20000 D2-29000 MultiPhases-29040 Training Material Localization | -10 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071816 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Support (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 0h | 60h | 60h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071817 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 0h | 30h | 30h | 2017-09-25 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071818 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 0h | 10h | 10h | 2018-01-15 | 2018-01-26 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -5 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071819 | No | No | Yes | SDF | SDF Localisation | 04-Test | DR - Support (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 0h | 45h | 45h | 2017-11-13 | 2017-12-01 | Yes |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071820 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 0h | 20h | 20h | 2017-10-16 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071821 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 0h | 30h | 30h | 2017-10-16 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071822 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 0h | 30h | 30h | 2017-12-04 | 2017-12-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071823 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 0h | 30h | 30h | 2017-12-04 | 2017-12-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071824 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Report (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 0h | 5h | 5h | 2017-09-05 | 2017-09-08 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071825 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Support Mock1 (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 0h | 25h | 25h | 2017-09-05 | 2017-09-08 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-09-25 | 2017-10-06 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -30 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071826 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | TPM Unit testing Development Documentation (FUT) | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Global | Business | 0h | 10h | 10h | 2017-05-29 | 2017-09-29 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071827 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 0h | 30h | 30h | 2017-09-25 | 2017-10-06 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | -5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071828 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 5h | 0h | 5h | 2017-09-05 | 2017-09-08 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 10 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0
1071829 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Log Gaps - OTC | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 43.5h | 0h | 43.5h | 2017-04-17 | 2017-07-07 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -15 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 5 | 5 | 10 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071830 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | RTM - OTC | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 28.5h | 0h | 28.5h | 2017-04-17 | 2017-05-19 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -18 | 57.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 5 | 8 | 3 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071831 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - OTC | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 100h | 0h | 100h | 2017-04-17 | 2017-05-12 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 28 | 25 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071832 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 4h | 0h | 4h | 2017-04-10 | 2017-04-13 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -10 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071833 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071834 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 4h | 0h | 4h | 2017-04-06 | 2017-04-13 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | -5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071835 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 18h | 0h | 18h | 2017-04-03 | 2017-04-13 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -25 | -13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071836 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071837 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | IOTC010-FSD-INT-Sales order interface | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -90 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071838 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 8h | 0h | 8h | 2017-04-03 | 2017-04-06 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -25 | -13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071839 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 10h | 0h | 10h | 2017-03-13 | 2017-03-17 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071840 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 10h | 0h | 10h | 2017-03-13 | 2017-03-17 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071841 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-03-27 | 2017-03-30 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | -5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071842 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -10 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071843 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - OTC-(Global) | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 231h | 1,320h | 1,551h | 2017-05-29 | 2018-03-30 | Yes |  |  | ACT-CM.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 15 | 20 | 20 | 16 | 40 | 20 | 10 | 5 | 0 | 0 | 0 | 30 | 30 | 0 | 0 | 0
1071844 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) (Test) - OTC | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071845 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - OTC (AN) | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 165h | 0h | 165h | 2017-04-17 | 2017-05-26 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 33 | 20 | 35 | 30 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071846 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - OTC | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 10h | 0h | 10h | 2017-03-06 | 2017-03-10 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -30 | -30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071847 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTM | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | CapEx | Localization | Business | 36h | 0h | 36h | 2017-05-29 | 2017-06-16 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 18 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071848 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTM(Global) | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | CapEx | Localization | Business | 79h | 560h | 639h | 2017-08-07 | 2017-12-01 | Yes |  |  | ACT-FUN.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 24 | 35 | 0 | 0 | 0 | 0
1071849 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTM | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | CapEx | Localization | Business | 93h | 0h | 93h | 2017-04-17 | 2017-06-23 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 16 | 6 | 8 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071850 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG015-FSD-INT-Inventory adjustment interface | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-25 | 2017-01-25 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -88 | -50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071851 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG013-FSD-INT-STO goods issue interface (SAP to BPCS) | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-24 | 2017-01-24 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -89 | -50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071852 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG012-FSD-INT-STO interface | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -90 | -30.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071853 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - RTR (Global) | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | CapEx | Localization | Business | 68h | 0h | 68h | 2017-07-31 | 2017-09-01 | Yes |  |  | ACT-FUN.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 8 | 45 | 0 | 0 | 0
1071854 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - RTR | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | CapEx | Localization | Business | 92.4h | 0h | 92.4h | 2017-04-10 | 2017-07-28 | Yes |  |  | ACT-FUN.Management | Future Task | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.4 | 30 | 10 | 11 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071855 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | CapEx | Localization | Business | 38.5h | 0h | 38.5h | 2017-03-20 | 2017-04-13 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 5 | 5 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071856 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - RTR | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | CapEx | Localization | Business | 68h | 0h | 68h | 2017-05-29 | 2017-06-30 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 11.9 | 10 | 25 | 11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071857 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG013-FSD-INT-STO goods issue interface (SAP to BPCS) | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-24 | 2017-01-24 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -89 | -50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071858 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG012-FSD-INT-STO interface | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -90 | -30.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071859 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG015-FSD-INT-Inventory adjustment interface | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-25 | 2017-01-25 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -88 | -50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071860 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG013-STO goods issue interface (SAP to BPCS) | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -95 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071861 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (DB) (Planning, reporting, CR, cross stream integration) - LOG(Global) | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 218h | 292.8h | 510.8h | 2017-06-05 | 2017-11-03 | Yes |  |  | ACT-MDG.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 25 | 25 | 0 | 90 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071862 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration). - LOG | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 193h | 0h | 193h | 2017-04-17 | 2017-06-02 | Yes |  |  | ACT-FUN.Management | Future Task | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 30 | 20 | 38 | 20 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071863 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 5h | 0h | 5h | 2017-04-03 | 2017-04-07 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071864 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 20h | 0h | 20h | 2017-04-03 | 2017-04-07 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071865 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-03-29 | 2017-03-29 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -23 | -19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071866 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 82h | 0h | 82h | 2017-03-13 | 2017-03-31 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 25 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071867 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 5h | 0h | 5h | 2017-03-13 | 2017-03-17 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071868 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Gap log - LOG | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 20h | 0h | 20h | 2017-04-17 | 2017-04-21 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071869 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - LOG | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071870 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 0h | 30h | 30h | 2017-12-04 | 2017-12-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071871 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 0h | 40h | 40h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071872 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 0h | 25h | 25h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071873 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 0h | 40h | 40h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071874 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 0h | 310h | 310h | 2018-01-15 | 2018-03-30 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -5 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071875 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 0h | 20h | 20h | 2018-01-03 | 2018-01-12 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -30 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071876 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Support (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 0h | 15h | 15h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071877 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Regression - Run Tests (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 0h | 15h | 15h | 2017-11-06 | 2017-11-24 | Yes |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-12-04 | 2017-12-22 | 2 | Q? Regression | 20000 D2-22000 CG: UAT and Regression-22010 Q? Regression | -20 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071878 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 0h | 30h | 30h | 2017-12-04 | 2017-12-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071879 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Support-D2 | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | OpEx | Localization | Business | 0h | 67h | 67h | 2017-09-05 | 2017-12-22 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-09-18 | 2017-11-03 | 2 | Training Material Localization | 20000 D2-29000 MultiPhases-29040 Training Material Localization | -10 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071880 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 19h | 0h | 19h | 2017-06-19 | 2017-07-19 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-21 | 2017-09-01 | 2 | AT | 20000 D2-20100 B-20180 AT | -45 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071881 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 5h | 5h | 10h | 2017-09-05 | 2017-09-15 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 10 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0
1071882 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 0h | 20h | 20h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | -5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071883 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (OTC) - Deploy1 | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 0h | 25h | 25h | 2017-10-23 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071884 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - OTC | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 123.5h | 0h | 123.5h | 2017-04-17 | 2017-06-16 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 16 | 2 | 2 | 0 | 0 | 29.5 | 20 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071885 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - OTC | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 20h | 0h | 20h | 2017-03-06 | 2017-03-10 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -30 | -30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071886 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Log Gaps - OTC | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 59h | 0h | 59h | 2017-04-10 | 2017-05-19 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -15 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 8 | 20 | 12 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071887 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | RTM - OTC | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 65h | 0h | 65h | 2017-04-17 | 2017-05-26 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -18 | 57.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 15 | 16 | 10 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071888 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -10 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071889 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071890 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 22h | 0h | 22h | 2017-03-20 | 2017-03-24 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071891 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 12h | 0h | 12h | 2017-04-10 | 2017-04-13 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -25 | -13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071892 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 4h | 0h | 4h | 2017-04-10 | 2017-04-13 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | -5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071893 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | IOTC010-FSD-INT-Sales order interface | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 13h | 0h | 13h | 2017-01-25 | 2017-03-10 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -90 | -10 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071894 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (OTC) - Deploy1 | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 43h | 55h | 98h | 2017-08-07 | 2017-09-13 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 15 | 0 | 8 | 0 | 0 | 0
1071895 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (OTC) - Deploy1 | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 30h | 56h | 86h | 2017-07-24 | 2017-08-11 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071896 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | Workshop-Batch handling | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 35h | 0h | 35h | 2017-03-06 | 2017-03-31 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071897 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Requirements/Process Design Workshops | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 40h | 0h | 40h | 2017-07-10 | 2017-07-14 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 4 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071898 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071899 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | SDF-INT-Workshop-Product costing | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-03-02 | 2017-03-02 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071900 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (RTR) - Deploy1 | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 94h | 94h | 2017-08-21 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071901 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Support (RTR) - Deploy1 | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-06-15 | 2017-06-15 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -2 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071902 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT Preparation : Component & Scripts (RTR) - Deploy1 | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 59h | 59h | 2017-08-21 | 2017-09-22 | Yes |  |  | ACT-FUN.UAT Preparation | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071903 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | Workshop-Purchasing & A/P | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 6h | 0h | 6h | 2017-03-13 | 2017-03-15 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071904 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | Workshop-QI management and held product | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 11h | 0h | 11h | 2017-03-06 | 2017-03-10 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071905 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG015-FSD-INT-Inventory adjustment interface | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 13h | 0h | 13h | 2017-01-25 | 2017-02-03 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -88 | -50 | 0 | 0 | 0 | 0 | 1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071906 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG013-FSD-INT-STO goods issue interface (SAP to BPCS) | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 11h | 0h | 11h | 2017-01-24 | 2017-03-03 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -89 | -50 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071907 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG012-FSD-INT-STO interface | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 12h | 0h | 12h | 2017-01-23 | 2017-02-28 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -90 | -30.88 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071908 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | SDF Interim State-Workshop-Production receipts and inventory adjustments | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 43h | 0h | 43h | 2017-03-06 | 2017-03-17 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071909 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 0h | 120h | 120h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071910 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 0h | 360h | 360h | 2017-09-25 | 2017-11-24 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071911 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 0h | 56.85h | 56.85h | 2017-08-28 | 2017-09-08 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071912 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | SDF Interim State-Workshop-Production scheduling and receipt (OCT. Go-live) | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 33h | 0h | 33h | 2017-02-27 | 2017-03-31 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071913 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - PTM | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 125h | 0h | 125h | 2017-04-17 | 2017-06-23 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 38 | 37 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071914 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Log Gaps - PTM | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 187h | 0h | 187h | 2017-04-17 | 2017-07-21 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 8 | 4 | 0 | 0 | 0 | 0 | 46 | 12 | 48 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071915 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | SDF Interim State-Workshop-Supply chain planning | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 86h | 0h | 86h | 2017-02-27 | 2017-04-07 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 36 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071916 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (OTC) - Deploy1 | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 120h | 33.75h | 153.75h | 2017-07-31 | 2017-09-14 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 20 | 40 | 0 | 0 | 0
1071917 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 70h | 0h | 70h | 2017-06-26 | 2017-07-21 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-21 | 2017-09-01 | 2 | AT | 20000 D2-20100 B-20180 AT | -45 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071918 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071919 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 10h | 0h | 10h | 2017-04-10 | 2017-04-14 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | -5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071920 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 15h | 0h | 15h | 2017-04-10 | 2017-04-14 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -25 | -13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071921 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071922 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 40h | 0h | 40h | 2017-04-03 | 2017-04-07 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -10 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071923 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC3513-DEV FUT-Pricing Cockpit | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 10h | 0h | 10h | 2017-06-26 | 2017-06-30 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | -15 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071924 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Log Gaps - OTC | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 60h | 0h | 60h | 2017-04-10 | 2017-05-05 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -15 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 20 | 20 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071925 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - OTC | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 117h | 0h | 117h | 2017-05-01 | 2017-06-09 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 40 | 32 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071926 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | RTM - OTC | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 70h | 0h | 70h | 2017-04-10 | 2017-05-05 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -18 | 57.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 20 | 20 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071927 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC034-FSD-Pricing Page Program | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 135h | 0h | 135h | 2017-03-20 | 2017-05-19 | Yes |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -80 | -30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 5 | 5 | 0 | 0 | 5 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071928 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | FOTC005-FSD-Level 0 Notification Form | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 10h | 0h | 10h | 2017-04-10 | 2017-04-28 | Yes |  |  | DELIV-FUN-204.Functional Specification - Form | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -60 | -41.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071929 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC034-FSD-Pricing Page Archive (DMS) | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | Yes |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071930 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | IOTC005-FSD-Pricing Notification EDI | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 40h | 0h | 40h | 2017-03-14 | 2017-06-23 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -54 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071931 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | DEV FUT-ID-COM-Baseline | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 0h | 62h | 62h | 2017-02-10 | 2017-09-22 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071932 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 0h | 10h | 10h | 2017-10-02 | 2017-10-06 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | -5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071933 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 16h | 16h | 32h | 2017-09-05 | 2017-09-15 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 10 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0
1071934 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (OTC) - Deploy1 | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 125h | 0h | 125h | 2017-07-17 | 2017-08-25 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 40 | 20 | 20 | 20 | 20 | 0 | 0 | 0 | 0
1071935 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC032-DEV FUT-Pricing Files | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 60h | 0h | 60h | 2017-05-15 | 2017-06-30 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | -30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071936 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC034-DEV FUT-Pricing Page Program | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 40h | 0h | 40h | 2017-05-08 | 2017-05-12 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | -40 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071937 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Support-D2 | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | OpEx | Localization | Business | 0h | 216h | 216h | 2017-09-05 | 2017-12-15 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-09-18 | 2017-11-03 | 2 | Training Material Localization | 20000 D2-29000 MultiPhases-29040 Training Material Localization | -10 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071938 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 0h | 20h | 20h | 2017-10-02 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071939 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Support (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 0h | 15h | 15h | 2017-10-09 | 2017-10-27 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071940 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 0h | 60h | 60h | 2018-01-15 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -5 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071941 | No | No | Yes | SDF | SDF Localisation | 04-Test | DR - Prepare (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 0h | 10h | 10h | 2017-11-06 | 2017-11-10 | Yes |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071942 | No | No | Yes | SDF | SDF Localisation | 04-Test | DR - Support (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 0h | 20h | 20h | 2017-11-13 | 2017-12-01 | Yes |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071943 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 0h | 30h | 30h | 2017-10-09 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071944 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 0h | 45h | 45h | 2017-10-09 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071945 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 0h | 20h | 20h | 2017-12-04 | 2017-12-15 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071946 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 0h | 40h | 40h | 2017-12-04 | 2017-12-15 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071947 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 0h | 40h | 40h | 2018-01-01 | 2018-01-12 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -30 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071948 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 0h | 240h | 240h | 2018-02-05 | 2018-03-30 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071949 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - OTC | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 10h | 0h | 10h | 2017-03-13 | 2017-03-17 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -30 | -30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071950 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | SDF Interim State-Workshop-Transportation | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 17.5h | 0h | 17.5h | 2017-03-14 | 2017-03-31 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 | 9.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071951 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Gap log - LOG | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 36h | 12h | 48h | 2017-04-17 | 2017-09-22 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071952 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Data Definition Documents (DDD) (LOG) - Deploy1 | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 101h | 0h | 101h | 2017-05-01 | 2017-07-13 | Yes |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Future Task | 2017-04-17 | 2017-05-05 | 1 | Revise DDDs - Division review | 1000 D1-1200 A-1213 Revise DDDs - Division review | 10 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 8 | 10 | 14 | 9 | 10.5 | 10.5 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071953 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (LOG) - Deploy1 | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 0h | 240h | 240h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071954 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy2 | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 0h | 90h | 90h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071955 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG012-FSD-INT-STO interface | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 8h | 0h | 8h | 2017-01-23 | 2017-03-17 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -90 | -30.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071956 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG013-FSD-INT-STO goods issue interface (SAP to BPCS) | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 8h | 0h | 8h | 2017-01-24 | 2017-03-17 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -89 | -50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071957 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG015-FSD-INT-Inventory adjustment interface | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 15.5h | 0h | 15.5h | 2017-01-25 | 2017-03-31 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -88 | -50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071958 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | RTM - LOG | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 55h | 0h | 55h | 2017-04-17 | 2017-06-02 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 10 | 9 | 9 | 8 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071959 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - LOG | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 99h | 0h | 99h | 2017-04-17 | 2017-06-30 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 10 | 9 | 9 | 8 | 10 | 14 | 9 | 10.5 | 10.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071960 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG013-STO goods issue interface (SAP to BPCS) | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 6h | 0h | 6h | 2017-01-16 | 2017-03-17 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -95 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071961 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 43.5h | 0h | 43.5h | 2017-03-13 | 2017-03-31 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 29 | 8.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071962 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 10.5h | 0h | 10.5h | 2017-04-03 | 2017-04-07 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -23 | -19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071963 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 20.5h | 0h | 20.5h | 2017-04-03 | 2017-04-13 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071964 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 20.5h | 0h | 20.5h | 2017-04-03 | 2017-04-13 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071965 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 4h | 0h | 4h | 2017-03-20 | 2017-03-28 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -22.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071966 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 32h | 0h | 32h | 2017-04-03 | 2017-04-06 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -20 | -16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071967 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 25h | 0h | 25h | 2017-03-27 | 2017-03-30 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -17 | -12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071968 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG015-FSD-INT-Inventory adjustment interface | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-25 | 2017-01-25 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -88 | -50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071969 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG013-FSD-INT-STO goods issue interface (SAP to BPCS) | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-24 | 2017-01-24 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -89 | -50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071970 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG012-FSD-INT-STO interface | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -90 | -30.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071971 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - PTP | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 4.5h | 0h | 4.5h | 2017-03-06 | 2017-03-10 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -33 | -35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071972 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTP | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 112h | 0h | 112h | 2017-04-17 | 2017-06-02 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 45 | 0 | 0 | 10 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071973 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | -9.88 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071974 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 7h | 0h | 7h | 2017-04-10 | 2017-04-13 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071975 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTP (Global) | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 51.5h | 173.5h | 225h | 2017-07-24 | 2017-09-25 | Yes |  |  | ACT-FUN.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 8.5 | 10.5 | 6 | 14.5 | 0 | 0 | 0 | 0
1071976 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | Workshop-Purchasing & A/P | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 17h | 0h | 17h | 2017-03-21 | 2017-06-09 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071977 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (RTR) - Deploy1 | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 0h | 94h | 94h | 2017-08-21 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071978 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT Preparation : Component & Scripts (RTR) - Deploy1 | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 0h | 51h | 51h | 2017-09-05 | 2017-09-22 | Yes |  |  | ACT-FUN.UAT Preparation | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071979 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Support (RTR) - Deploy1 | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-06-15 | 2017-06-15 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -2 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071980 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | SDF-INT-Workshop-Finance | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 24h | 0h | 24h | 2017-03-20 | 2017-06-07 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071981 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 9h | 0h | 9h | 2017-03-24 | 2017-04-12 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071982 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - RTR | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 18h | 0h | 18h | 2017-04-18 | 2017-04-21 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -9.88 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071983 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | Workshop-Design Interim state financial reporting | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-05-22 | 2017-05-22 | Yes |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071984 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Requirements/Process Design Workshops | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 77.5h | 0h | 77.5h | 2017-06-05 | 2017-07-07 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 4 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 17.5 | 19 | 16 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071985 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 48h | 0h | 48h | 2017-05-24 | 2017-06-23 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | -14 | 72.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 4 | 10 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071986 | No | No | Yes | SDF | SDF Interim State Project | 01-Preparation | Environment setup | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071987 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - RTR | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 47h | 0h | 47h | 2017-04-24 | 2017-06-23 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -9.88 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 1 | 0 | 0 | 0 | 5 | 3 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071988 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 3h | 0h | 3h | 2017-03-13 | 2017-04-07 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071989 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071990 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 configuration (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 39h | 10h | 49h | 2017-08-14 | 2017-09-15 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | 35 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 4 | 24 | 0 | 0 | 0
1071991 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2017-07-25 | 2017-08-04 | Yes |  |  | ACT-FUN.Functional Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071992 | No | No | Yes | SDF | SDF Localisation | 04-Test | DR - Support (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-08-15 | 2017-09-03 | Yes |  |  | ACT-FUN.Dry Run activities | Complete | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
1071993 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-07-31 | 2017-08-11 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0
1071994 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-08-14 | 2017-09-01 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 13.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 12 | 0 | 0 | 0
1071995 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | WPB Recordings (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | DELIV-FUN-403.WPB Recordings | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071996 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Interface (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-07 | 2017-06-07 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 7 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071997 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 15h | 15h | 2017-08-21 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071998 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Interface (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2017-08-21 | 2017-08-24 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0
1071999 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 84h | 3h | 87h | 2017-06-26 | 2017-09-08 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 15 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 24 | 17 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0
1072000 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | IRTR018 – EDI gaps - RTR | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-07-10 | 2017-07-14 | Yes |  |  | To delete-To delete.To delete | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 30 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072001 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 15h | 15h | 2017-09-05 | 2017-09-22 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072002 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 4h | 4h | 2017-08-28 | 2017-09-15 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072003 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072004 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072005 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 45h | 45h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072006 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 58h | 58h | 2017-09-05 | 2017-09-18 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072007 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Enhancement (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-05 | 2017-09-15 | Yes |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072008 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 configuration (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 2h | 2h | 2017-09-05 | 2017-09-15 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072009 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 65h | 65h | 2017-09-18 | 2017-10-13 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072010 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 15h | 15h | 2017-09-25 | 2017-10-13 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072011 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 15h | 15h | 2017-10-16 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072012 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 94h | 94h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072013 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | WPB Recordings - RTR - Deploy1 | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 9h | 4h | 13h | 2017-06-29 | 2017-07-14 | Yes |  |  | DELIV-FUN-403.WPB Recordings | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072014 | No | No | Yes | SDF | SDF Interim State Project | 01-Preparation | Environment setup | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-01-09 | 2017-01-11 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072015 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT - OTC- Deploy2 | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072016 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Baseline configuration - OTC | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Global | IT - External | 53h | 0h | 53h | 2017-05-15 | 2017-06-23 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-06-26 | 2017-07-14 | 0 | NA Others | 99000-99100-99130 NA others | -30 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 8 | 0 | 10 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072017 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-07-17 | 2017-07-21 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-21 | 2017-09-01 | 2 | AT | 20000 D2-20100 B-20180 AT | -45 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072018 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-06-12 | 2017-06-16 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072019 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 34h | 0h | 34h | 2017-05-08 | 2017-06-23 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-05-19 | 2 | Base Config | 1000 D1-1300 B-1314 Base Config | -5 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 15 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072020 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Execute FUT | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Global | IT - External | 17h | 82h | 99h | 2017-08-07 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-08-18 | 0 | NA Others | 99000-99100-99130 NA others | -30 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 | 0 | 10 | 0 | 0 | 0
1072021 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Functional Specification (FSD) | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Global | IT - External | 147h | 30h | 177h | 2017-06-12 | 2017-10-06 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | 5 | 85.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 10 | 20 | 0 | 25 | 0 | 10 | 20 | 10 | 8 | 24 | 0 | 0 | 0 | 0
1072022 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-SIT Test Scenarios/Scripts | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Global | IT - External | 20h | 123h | 143h | 2017-08-02 | 2017-11-03 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 0 | NA Others | 99000-99100-99130 NA others | -25 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 10 | 2 | 0 | 5 | 0 | 0 | 0
1072023 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Cycle1 Configuration | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Global | IT - External | 87h | 0h | 87h | 2017-06-26 | 2017-07-28 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 0 | NA Others | 99000-99100-99130 NA others | -15 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 9 | 20 | 20 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072024 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Cycle2 Configuration | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Global | IT - External | 99h | 34h | 133h | 2017-07-31 | 2017-09-20 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 0 | NA Others | 99000-99100-99130 NA others | -20 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 20 | 24 | 12 | 30 | 0 | 0 | 0
1072025 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072026 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-10-09 | 2017-10-13 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | -20 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072027 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 configuration (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-10-09 | 2017-11-03 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072028 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - OTC-(Global) | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 0h | 72h | 72h | 2017-07-05 | 2017-11-03 | Yes |  |  | ACT-CM.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072029 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 configuration (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072030 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Report (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 0h | 27h | 27h | 2017-10-02 | 2017-10-06 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072031 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-PDDs | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Global | IT - External | 75h | 0h | 75h | 2017-05-08 | 2017-06-01 | Yes |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 15 | 6 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072032 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-Gap Resolution-Global | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Global | IT - External | 30h | 0h | 30h | 2017-03-27 | 2017-06-09 | Yes |  |  | WP-FUN.Gap Definition | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072033 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-Global Trade scope / Solution validation-OTC | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Global | IT - External | 5h | 0h | 5h | 2017-04-17 | 2017-04-21 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072034 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-RTM-Global Trade-OTC | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Global | IT - External | 28h | 0h | 28h | 2017-03-27 | 2017-04-21 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 9 | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072035 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-Fit-Gap-Global | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Global | IT - External | 56h | 0h | 56h | 2017-03-13 | 2017-04-21 | Yes |  |  | WP-FUN.Gap Definition | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 25 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072036 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-16 | 2017-06-16 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | -15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072037 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-07 | 2017-07-07 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | -25 | 16.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072038 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 94h | 94h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072039 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-10-16 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072040 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-25 | 2017-10-13 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072041 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 67h | 67h | 2017-09-18 | 2017-10-13 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072042 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 configuration (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 2h | 2h | 2017-09-05 | 2017-09-15 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072043 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 configuration (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 10h | 10h | 2017-08-14 | 2017-09-15 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | 35 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072044 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072045 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Enhancement (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 10h | 10h | 2017-09-05 | 2017-09-15 | Yes |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072046 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 15h | 15h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072047 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 15h | 15h | 2017-09-05 | 2017-09-22 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072048 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072049 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 4h | 4h | 2017-08-28 | 2017-09-15 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072050 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 15h | 15h | 2017-08-21 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072051 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 4h | 4h | 2017-08-30 | 2017-09-15 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072052 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-07-17 | 2017-08-04 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 31 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072053 | No | No | Yes | SDF | SDF Localisation | 04-Test | Regression - Run Tests (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 7h | 0h | 7h | 2017-08-07 | 2017-08-29 | Yes |  |  | ACT-FUN.Execute Regression Test | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 9.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0
1072054 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 58h | 0h | 58h | 2017-07-17 | 2017-08-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 9 | 3 | 5 | 20 | 10 | 0 | 0 | 0 | 0
1072055 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 59h | 31h | 90h | 2017-08-07 | 2017-09-08 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 9.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 19 | 20 | 0 | 0 | 0
1072056 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 13h | 20h | 33h | 2017-08-28 | 2017-09-14 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 13.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0
1072057 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 78h | 78h | 2017-09-05 | 2017-09-18 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072058 | No | No | Yes | SDF | SDF Interim State Project | 01-Preparation | Environment setup | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072059 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 65h | 0h | 65h | 2017-05-24 | 2017-07-07 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | -14 | 72.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 20 | 13 | 13 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072060 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | SDF-INT-Workshop-Product costing | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 3h | 0h | 3h | 2017-03-02 | 2017-04-04 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072061 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 83h | 0h | 83h | 2017-05-24 | 2017-06-23 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | -14 | 72.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 28 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072062 | No | No | Yes | SDF | SDF Interim State Project | 01-Preparation | Environment setup | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072063 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072064 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072065 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Assembly Test Scenarios/Scripts (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | Yes |  |  | DELIV-TST-307.Assembly Test Scenarios/Scripts | Future Task | 2017-07-03 | 2017-07-14 | 1 | AT | 1000 D1-1300 B-1312 AT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072066 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 35h | 0h | 35h | 2017-07-03 | 2017-07-12 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Complete | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | 5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072067 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | WPB Recordings (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-07-03 | 2017-07-07 | Yes |  |  | DELIV-FUN-403.WPB Recordings | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072068 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 configuration (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-08-21 | 2017-08-25 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | 25 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0
1072069 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072070 | No | No | Yes | SDF | SDF Interim State Project | 01-Preparation | Environment setup | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-01-09 | 2017-01-20 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072071 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | SDF Interim State-Workshop-Transportation | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 15.5h | 0h | 15.5h | 2017-02-20 | 2017-04-10 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 5 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072072 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Support (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 31h | 0h | 31h | 2017-07-17 | 2017-07-28 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072073 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-07-03 | 2017-07-14 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072074 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2017-07-07 | 2017-07-07 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072075 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | SDF Interim State-Workshop-Production receipts and inventory adjustments | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 2.5h | 0h | 2.5h | 2017-03-21 | 2017-03-23 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072076 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 20h | 16h | 36h | 2017-09-11 | 2017-09-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0
1072077 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 69h | 13.85h | 82.85h | 2017-06-29 | 2017-08-29 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 20 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 10 | 3 | 10 | 15 | 15 | 0 | 10 | 0 | 0 | 0 | 0
1072078 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-08-07 | 2017-08-11 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 5 | 33.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0
1072079 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 30h | 0h | 30h | 2017-07-24 | 2017-08-04 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 5 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072080 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-08-07 | 2017-08-18 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 4.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0
1072081 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072082 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Support (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072083 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-21 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072084 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 20h | 28h | 48h | 2017-09-11 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0
1072085 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 15h | 30h | 45h | 2017-08-21 | 2017-09-18 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | -8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 5 | 0
1072086 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 48h | 48h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072087 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-10-13 | 2017-10-13 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072088 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072089 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Support Mock1 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 28h | 38.87h | 66.87h | 2017-08-21 | 2017-09-15 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-09-25 | 2017-10-06 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -25 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 8 | 0 | 0
1072090 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-10-09 | 2017-10-09 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072091 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - LOG | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-05 | 2017-05-05 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072092 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-06-12 | 2017-06-13 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072093 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072094 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-06-30 | 2017-08-11 | Yes |  |  | DELIV-FUN-220.Solution Design Document (SDD) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072095 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 12h | 8h | 20h | 2017-09-05 | 2017-09-22 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-19 | 2017-06-30 | 1 | Cycle 2 Config | 1000 D1-1300 B-1318 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0
1072096 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Data Definition Documents (DDD) (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | Yes |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Future Task | 2017-04-17 | 2017-05-05 | 1 | Revise DDDs - Division review | 1000 D1-1200 A-1213 Revise DDDs - Division review | 10 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072097 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 260h | 260h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072098 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Report (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 26h | 0h | 26h | 2017-08-14 | 2017-09-08 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 5.13 | 75.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 16 | 0 | 0
1072099 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-01 | 2017-09-01 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 10 | 16.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072100 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | Workshop-Purchasing & A/P | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2017-03-20 | 2017-04-06 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072101 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 60h | 0h | 60h | 2017-07-31 | 2017-09-03 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | 25 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 20 | 16 | 13 | 0 | 0 | 0
1072102 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 16h | 2h | 18h | 2017-08-07 | 2017-08-25 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 9.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0
1072103 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 0h | 21h | 21h | 2017-08-21 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072104 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 0h | 3h | 3h | 2017-07-04 | 2017-09-08 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 15 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072105 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 0h | 15h | 15h | 2017-09-05 | 2017-09-22 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072106 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 0h | 4h | 4h | 2017-08-28 | 2017-09-15 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072107 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 0h | 4h | 4h | 2017-08-30 | 2017-09-15 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072108 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072109 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072110 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 0h | 45h | 45h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072111 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 0h | 58h | 58h | 2017-09-05 | 2017-09-18 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072112 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Enhancement (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-05 | 2017-09-15 | Yes |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072113 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 configuration (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 0h | 2h | 2h | 2017-09-05 | 2017-09-15 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072114 | No | No | Yes | SDF | SDF Localisation | 04-Test | Regression - Run Tests (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 30h | 0h | 30h | 2017-08-07 | 2017-09-01 | Yes |  |  | ACT-FUN.Execute Regression Test | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 9.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 12 | 10 | 3 | 0 | 0 | 0
1072115 | No | No | Yes | SDF | SDF Interim State Project | 01-Preparation | Environment setup | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-01-16 | 2017-01-30 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072116 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | IXXX-DEV FUT-A/P interface | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 47h | 0h | 47h | 2017-06-20 | 2017-07-28 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | 21 | 14.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 20 | 12 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072117 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | IXXX-FSD-A/P interface | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 13h | 0h | 13h | 2017-04-24 | 2017-05-05 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -25 | -40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072118 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 96h | 0h | 96h | 2017-05-24 | 2017-08-11 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | -14 | 72.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 0 | 13 | 12 | 0 | 0 | 0 | 10 | 18 | 13 | 0 | 0 | 0 | 0 | 0 | 0
1072119 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | SDF-INT-Workshop-Finance | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-03-01 | 2017-04-21 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072120 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Interface (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 72h | 0h | 72h | 2017-06-12 | 2017-09-01 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 7 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 19 | 0 | 0 | 0 | 0 | 10 | 14 | 0 | 0 | 0 | 15 | 0 | 0 | 0
1072121 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 0h | 61h | 61h | 2017-09-18 | 2017-10-13 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072122 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 0h | 18h | 18h | 2017-09-25 | 2017-10-13 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072123 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-10-16 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072124 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072125 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | IOTC010-FSD-INT-Sales order interface | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-04-24 | 2017-04-28 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -90 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072126 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Zute; Sudeep | IBM | Yes | CapEx | Localization | IT - External | 39h | 0h | 39h | 2017-08-28 | 2017-09-08 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 23 | 0 | 0
1072127 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Zute; Sudeep | IBM | Yes | CapEx | Localization | IT - External | 41h | 0h | 41h | 2017-08-07 | 2017-08-20 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 17 | 0 | 0 | 0 | 0 | 0
1072128 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | Workshop-Purchasing & A/P | PTP | FUN | SI | Offshore | Zute; Sudeep | IBM | Yes | CapEx | Localization | IT - External | 7h | 0h | 7h | 2017-03-20 | 2017-04-05 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072129 | No | No | Yes | SDF | SDF Interim State Project | 01-Preparation | Environment setup | PTP | FUN | SI | Offshore | Zute; Sudeep | IBM | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2017-01-09 | 2017-06-16 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072130 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (PTP) - Deploy2 | PTP | FUN | SI | Offshore | Zute; Sudeep | IBM | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-09-11 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072131 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Zute; Sudeep | IBM | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-07-18 | 2017-08-20 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 13 | 0 | 25 | 0 | 0 | 0 | 0 | 0
1072132 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Zute; Sudeep | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-07-17 | 2017-09-08 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 20 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 9 | 0 | 9 | 0 | 0
1072133 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Zute; Sudeep | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-08-07 | 2017-08-24 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 23 | 0 | 0 | 0 | 0
1072134 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Zute; Sudeep | IBM | Yes | CapEx | Localization | IT - External | 43h | 0h | 43h | 2017-07-24 | 2017-08-04 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072135 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Interface (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Zute; Sudeep | IBM | Yes | CapEx | Localization | IT - External | 26h | 0h | 26h | 2017-06-19 | 2017-06-30 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 15 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072136 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Zute; Sudeep | IBM | Yes | CapEx | Localization | IT - External | 19h | 0h | 19h | 2017-06-19 | 2017-07-07 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | -5 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072137 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Zute; Sudeep | IBM | Yes | CapEx | Localization | IT - External | 21h | 0h | 21h | 2017-06-12 | 2017-07-06 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 11 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072138 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Zute; Sudeep | IBM | Yes | CapEx | Localization | IT - External | 0h | 120h | 120h | 2017-09-25 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072139 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTP (Global) | PTP | FUN | SI | Offshore | Zute; Sudeep | IBM | Yes | CapEx | Localization | IT - External | 19h | 101h | 120h | 2017-07-10 | 2017-10-17 | Yes |  |  | ACT-FUN.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 10 | 0 | 0
1072140 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Zute; Sudeep | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-05 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072141 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTP) - Deploy2 | PTP | FUN | SI | Offshore | Zute; Sudeep | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072142 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTP) - Deploy2 | PTP | FUN | SI | Offshore | Zute; Sudeep | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072143 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTP) - Deploy2 | PTP | FUN | SI | Offshore | Zute; Sudeep | IBM | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-09-18 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072144 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTP) - Deploy2 | PTP | FUN | SI | Offshore | Zute; Sudeep | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072145 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | RTM - OTC | OTC | FUN | Saputo | Onshore | Aikens; Curtis | Saputo | Yes | CapEx | Localization | Business | 19.25h | 0h | 19.25h | 2017-05-29 | 2017-07-07 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -18 | 57.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.25 | 0 | 0 | 0 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072146 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Data Definition Documents (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Aikens; Curtis | Saputo | Yes | CapEx | Localization | Business | 29.25h | 0h | 29.25h | 2017-05-29 | 2017-06-23 | Yes |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Complete | 2017-09-25 | 2017-10-06 | 2 | TBD | 99000-99100-99110 TBD | -85 | -50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.25 | 5 | 13 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072147 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Aikens; Curtis | Saputo | Yes | CapEx | Localization | Business | 140h | 5h | 145h | 2017-06-19 | 2017-09-05 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | -25 | 16.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 35 | 0 | 25 | 0 | 0 | 0
1072148 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (OTC) - Deploy1 | OTC | FUN | Saputo | Onshore | Aikens; Curtis | Saputo | Yes | CapEx | Localization | Business | 0h | 45h | 45h | 2017-10-02 | 2017-12-01 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072149 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (OTC) - Deploy1 | OTC | FUN | Saputo | Onshore | Aikens; Curtis | Saputo | Yes | CapEx | Localization | Business | 0h | 12h | 12h | 2017-07-28 | 2017-08-11 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072150 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Aikens; Curtis | Saputo | Yes | CapEx | Localization | Business | 40h | 0h | 40h | 2017-06-12 | 2017-07-14 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | -15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072151 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (OTC) - Deploy1 | OTC | FUN | Saputo | Onshore | Aikens; Curtis | Saputo | Yes | CapEx | Localization | Business | 60h | 0h | 60h | 2017-08-14 | 2017-09-01 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 40 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 40 | 15 | 0 | 0 | 0
1072152 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | OTC | FUN | Saputo | Onshore | Aikens; Curtis | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-03-27 | 2017-03-27 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -25 | -13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072153 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | DMS GD Fit/Gap - RTR | RTR | FUN | SI | Onshore | Bodfeld; Frank | SAP | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-05-08 | 2017-05-12 | Yes |  | DMS | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072154 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | DMS Configuration/UT - Costing SDF - RTR - Deploy1 | RTR | FUN | SI | Onshore | Bodfeld; Frank | SAP | Yes | CapEx | Localization | IT - External | 124h | 0h | 124h | 2017-05-23 | 2017-07-07 | Yes |  | DMS | To delete-To delete.To delete | Complete | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | -5 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 24 | 24 | 24 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072155 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Bodfeld; Frank | SAP | Yes | CapEx | Localization | IT - External | 64h | 0h | 64h | 2017-07-24 | 2017-08-04 | Yes |  | DMS | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072156 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Bodfeld; Frank | SAP | Yes | CapEx | Localization | IT - External | 72h | 0h | 72h | 2017-07-04 | 2017-07-20 | Yes |  | DMS | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 15 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072157 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Bodfeld; Frank | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-21 | 2017-07-28 | Yes |  | DMS | ACT-FUN.Functional Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072158 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Bodfeld; Frank | SAP | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2017-08-07 | 2017-08-18 | Yes |  | DMS | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 9.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0
1072159 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Bodfeld; Frank | SAP | Yes | CapEx | Localization | IT - External | 0h | 12h | 12h | 2017-08-18 | 2017-08-28 | Yes |  | DMS | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 13.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072160 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Bodfeld; Frank | SAP | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-08-28 | 2017-09-22 | Yes |  | DMS | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072161 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Bodfeld; Frank | SAP | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-08-30 | 2017-09-26 | Yes |  | DMS | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072162 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - RTR | RTR | FUN | SI | Onshore | Beiderhase; Thomas | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | Yes |  | DMS | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072163 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - RTR (Global) | RTR | FUN | SI | Onshore | Beiderhase; Thomas | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-08-07 | Yes |  | DMS | ACT-FUN.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072164 | No | No | Yes | SDF | SDF Localisation | 99-Global | DMS Management - RTR - Deploy1 | RTR | FUN | SI | Onshore | Beiderhase; Thomas | SAP | Yes | CapEx | Localization | IT - External | 23h | 0h | 23h | 2017-05-29 | 2017-08-03 | Yes |  | DMS | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072165 | No | No | Yes | SDF | SDF Localisation | 99-Global | DMS Management - RTR | RTR | FUN | SI | Onshore | Beiderhase; Thomas | SAP | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2017-04-10 | 2017-05-04 | Yes |  | DMS | ACT-FUN.Management | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 14 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072166 | No | No | Yes | SDF | SDF Localisation | 99-Global | DMS Management - PTM | RTR | FUN | SI | Onshore | Beiderhase; Thomas | SAP | Yes | CapEx | Global | IT - External | 44h | 0h | 44h | 2017-05-04 | 2017-05-29 | Yes |  | DMS | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 40 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072167 | No | No | Yes | SDF | SDF Localisation | 99-Global | DMS Management - PTM | RTR | FUN | SI | Onshore | Beiderhase; Thomas | SAP | Yes | CapEx | Localization | IT - External | 30h | 0h | 30h | 2017-04-18 | 2017-04-27 | Yes |  | DMS | ACT-FUN.Management | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072168 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTM(Global) | RTR | FUN | SI | Onshore | Beiderhase; Thomas | SAP | Yes | CapEx | Localization | IT - External | 10h | 378h | 388h | 2017-08-07 | 2017-09-25 | Yes |  | DMS | ACT-FUN.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0
1072169 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | DMS Configuration/UT - Operations - PTM - Deploy1 | PTM | FUN | SI | Onshore | Hagelauer; Harald | SAP | Yes | CapEx | Localization | IT - External | 64h | 0h | 64h | 2017-06-08 | 2017-07-07 | Yes |  | DMS | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | -5 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 16 | 12 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072170 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Hagelauer; Harald | SAP | Yes | CapEx | Localization | IT - External | 0h | 44h | 44h | 2017-09-25 | 2017-09-29 | Yes |  | DMS | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072171 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Hagelauer; Harald | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-25 | 2017-09-25 | Yes |  | DMS | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072172 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Hagelauer; Harald | SAP | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-10-02 | 2017-12-15 | Yes |  | DMS | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072173 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Hagelauer; Harald | SAP | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-09-11 | 2017-09-22 | Yes |  | DMS | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072174 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Hagelauer; Harald | SAP | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-08-28 | 2017-09-22 | Yes |  | DMS | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072175 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-08-28 | 2017-09-22 | Yes |  | DMS | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072176 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-10-02 | 2017-12-15 | Yes |  | DMS | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072177 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-09-11 | 2017-09-22 | Yes |  | DMS | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072178 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-25 | 2017-09-25 | Yes |  | DMS | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072179 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 0h | 44h | 44h | 2017-09-25 | 2017-09-29 | Yes |  | DMS | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072180 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | DMS SDD Raw Milk Planning - PTM - Deploy1 | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-07-31 | 2017-08-04 | Yes |  | DMS | DELIV-FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072181 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | DMS Configuration/UT - Planning SDF - PTM - Deploy1 | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 84h | 0h | 84h | 2017-06-12 | 2017-07-28 | Yes |  | DMS | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 16 | 16 | 0 | 0 | 12 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072182 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | DMS – PDD Updates - PTM | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | Yes |  | DMS | DELIV-FUN-110.PDDs | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072183 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | DMS Test Preparation - PTM - Deploy1 | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-07-31 | 2017-08-04 | Yes |  | DMS | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072184 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | DMS GD Fit/Gap - PTM | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2017-04-10 | 2017-04-13 | Yes |  | DMS | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072185 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 0h | 120h | 120h | 2018-02-05 | 2018-03-30 | Yes |  | DMS | ACT-FUN.Functional Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072186 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 0h | 132h | 132h | 2018-01-15 | 2018-01-30 | Yes |  | DMS | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -8 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072187 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-12-04 | 2017-12-29 | Yes |  | DMS | ACT-FUN.Execute UAT | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072188 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 0h | 88h | 88h | 2018-01-15 | 2018-01-26 | Yes |  | DMS | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -30 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072189 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-12-04 | 2017-12-29 | Yes |  | DMS | ACT-FUN.Functional Break/Fix | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072190 | No | No | Yes | SDF | SDF Localisation | 04-Test | DR - Support (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-11-20 | 2017-12-01 | Yes |  | DMS | ACT-FUN.Dry Run activities | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072191 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Durham; Cecil | Saputo | Yes | CapEx | Localization | Business | 0h | 35h | 35h | 2017-08-28 | 2017-09-01 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072192 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Durham; Cecil | Saputo | Yes | CapEx | Localization | Business | 0h | 120h | 120h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072193 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Durham; Cecil | Saputo | Yes | CapEx | Localization | Business | 0h | 360h | 360h | 2017-09-25 | 2017-11-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072194 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Materials-Work Instructions/Job aids (Design/Build) | PTM | FUN | Saputo | Onshore | Durham; Cecil | Saputo | Yes | OpEx | Localization | Business | 167h | 0h | 167h | 2017-07-24 | 2017-09-08 | Yes |  |  | DELIV-CM-451.Work Instructions | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 10 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 48 | 0 | 0 | 40 | 17 | 32 | 0 | 0
1072195 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - LOG | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072196 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT - LOG (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 0h | 6h | 6h | 2017-08-14 | 2017-08-18 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 5 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072197 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072198 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 configuration (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 9.8h | 0h | 9.8h | 2017-07-31 | 2017-08-09 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | 25 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4.8 | 0 | 0 | 0 | 0 | 0 | 0
1072199 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 13h | 0h | 13h | 2017-04-07 | 2017-04-26 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072200 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072201 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 5.8h | 0h | 5.8h | 2017-03-29 | 2017-04-03 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -23 | -19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072202 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 11.8h | 0h | 11.8h | 2017-03-13 | 2017-03-31 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072203 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-04-04 | 2017-04-07 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072204 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | RTM - LOG | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-28 | 2017-04-28 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072205 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - LOG | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-05 | 2017-05-05 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072206 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Data Definition Documents (DDD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 12.6h | 0h | 12.6h | 2017-05-01 | 2017-06-16 | Yes |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Future Task | 2017-04-17 | 2017-05-05 | 1 | Revise DDDs - Division review | 1000 D1-1200 A-1213 Revise DDDs - Division review | 10 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.8 | 6.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072207 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-28 | 2017-08-04 | Yes |  |  | DELIV-FUN-220.Solution Design Document (SDD) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072208 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Gap log - LOG | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 8.8h | 1h | 9.8h | 2017-06-05 | 2017-08-18 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072209 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Report (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-11 | 2017-08-11 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 5.13 | 75.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072210 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 0h | 32h | 32h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072211 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | PDDs | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-16 | 2017-06-16 | Yes |  |  | DELIV-FUN-110.PDDs | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072212 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 5.4h | 0h | 5.4h | 2017-06-13 | 2017-06-16 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072213 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 5h | 12h | 17h | 2017-07-31 | 2017-08-11 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-19 | 2017-06-30 | 1 | Cycle 2 Config | 1000 D1-1300 B-1318 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072214 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 17.8h | 0h | 17.8h | 2017-06-05 | 2017-06-30 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 4.8 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072215 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Support Mock1 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 26h | 12h | 38h | 2017-08-21 | 2017-09-08 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-09-25 | 2017-10-06 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -25 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 5 | 6 | 0 | 0
1072216 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 0h | 72h | 72h | 2017-09-18 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072217 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 0h | 72h | 72h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072218 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 0h | 96h | 96h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072219 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 17h | 28h | 45h | 2017-08-28 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 12 | 0
1072220 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-10-09 | 2017-10-09 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072221 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 111h | 2h | 113h | 2017-08-14 | 2017-09-18 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | -8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 29 | 34 | 19.6 | 18.4 | 0
1072222 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072223 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-21 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072224 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Support (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 4.8h | 0h | 4.8h | 2017-08-04 | 2017-08-11 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3.8 | 0 | 0 | 0 | 0 | 0 | 0
1072225 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2017-08-07 | 2017-08-11 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 4.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0
1072226 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 36.2h | 0h | 36.2h | 2017-06-27 | 2017-08-04 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 20 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2 | 20 | 2 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072227 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | SI | Landed Onshore | Tubati; Pavan | IBM | Yes | CapEx | Localization | IT - External | 0h | 75h | 75h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072228 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Landed Onshore | Tubati; Pavan | IBM | Yes | CapEx | Localization | IT - External | 0h | 95h | 95h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072229 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy1 (Design/Build) | DEV | DEV | SI | Landed Onshore | Tubati; Pavan | IBM | Yes | CapEx | Localization | IT - External | 38h | 0h | 38h | 2017-07-03 | 2017-07-28 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072230 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | SI | Landed Onshore | Tubati; Pavan | IBM | Yes | CapEx | Localization | IT - External | 46h | 5h | 51h | 2017-09-05 | 2017-09-22 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 30 | 0
1072231 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing WRICEFs (Design/Build) | DEV | DEV | SI | Landed Onshore | Tubati; Pavan | IBM | Yes | CapEx | Localization | IT - External | 46h | 26h | 72h | 2017-02-20 | 2017-09-29 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -88 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 30 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072232 | No | No | Yes | SDF | SDF Interim State Project | 01-Preparation | Conduct Kick Offs | DEV | DEV | SI | Landed Onshore | Tubati; Pavan | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2016-10-11 | 2016-10-14 | Yes |  |  | DELIV-DEV-102.RICEFW Inventory | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072233 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | DELIV - Gaps analyze for DEV | DEV | DEV | SI | Landed Onshore | Tubati; Pavan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  | DELIV-DEV-102.RICEFW Inventory | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072234 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | DELIV - Functional Workshops | DEV | DEV | SI | Landed Onshore | Tubati; Pavan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  | DELIV-DEV-102.RICEFW Inventory | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072235 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | Framework FSD/Testing | DEV | DEV | SI | Landed Onshore | Tubati; Pavan | IBM | Yes | CapEx | Localization | IT - External | 109h | 0h | 109h | 2016-11-07 | 2017-01-18 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072236 | No | No | Yes | SDF | SDF Interim State Project | 01-Preparation | DELIV - Connectivity PoC | DEV | DEV | SI | Landed Onshore | Tubati; Pavan | IBM | Yes | CapEx | Localization | IT - External | 54h | 0h | 54h | 2016-10-17 | 2016-10-26 | Yes |  |  | DELIV-DEV-102.RICEFW Inventory | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072237 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Landed Onshore | Tubati; Pavan | IBM | Yes | CapEx | Localization | IT - External | 0h | 120h | 120h | 2017-10-09 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072238 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | SDF Interim State Project | DEV | DEV | SI | Landed Onshore | Tubati; Pavan | IBM | Yes | CapEx | Localization | IT - External | 60h | 0h | 60h | 2016-10-31 | 2017-02-02 | Yes |  |  | DELIV-DEV-102.RICEFW Inventory | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072239 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | SI | Landed Onshore | Tubati; Pavan | IBM | Yes | CapEx | Localization | IT - External | 242h | 80h | 322h | 2016-12-28 | 2017-10-31 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 8 | 0 | 8 | 10 | 10 | 10 | 10 | 6 | 7 | 7 | 8 | 8 | 6 | 27 | 20 | 14 | 26 | 20 | 0 | 0 | 0 | 0 | 16 | 0 | 0
1072240 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Landed Onshore | Tubati; Pavan | IBM | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2017-07-31 | 2017-08-04 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072241 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Landed Onshore | Tubati; Pavan | IBM | Yes | CapEx | Localization | IT - External | 79h | 0h | 79h | 2017-08-07 | 2017-09-01 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 24 | 0 | 25 | 0 | 0 | 0
1072242 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | SI | Landed Onshore | Tubati; Pavan | IBM | Yes | CapEx | Localization | IT - External | 71h | 21h | 92h | 2017-06-20 | 2017-09-20 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 20 | 0 | 19 | 4 | 14 | 0
1072243 | No | No | Yes | SDF | SDF Localisation | 99-Global | Team Lead - Site Assessment Analysis (Opex) - PTM | PTM | FUN | Saputo | Onshore | Tenhagen; Chris | Saputo | Yes | OpEx | Localization | Business | 244h | 2h | 246h | 2017-04-17 | 2017-09-12 | Yes |  |  | DELIV-FUN-029.Site Assessment | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 6 | 40 | 40 | 0 | 3 | 3 | 3 | 40 | 0 | 20 | 20 | 20 | 5 | 0 | 0 | 20 | 0 | 0 | 0 | 8 | 0
1072244 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG012-FSD-INT-STO interface | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -90 | -30.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072245 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG013-FSD-INT-STO goods issue interface (SAP to BPCS) | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 8h | 0h | 8h | 2017-01-24 | 2017-03-16 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -89 | -50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072246 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG015-FSD-INT-Inventory adjustment interface | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-25 | 2017-01-25 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -88 | -50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072247 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTP) - Deploy1 | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 24h | 0h | 24h | 2017-08-29 | 2017-08-31 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0
1072248 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Gap log - PTP | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-29 | 2017-03-29 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -22.88 | 70.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072249 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTP) - Deploy1 | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 40h | 40h | 2017-08-28 | 2017-09-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072250 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (PTP) - Deploy1 | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 3h | 11h | 14h | 2017-08-22 | 2017-09-15 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -19 | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0
1072251 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTP) - Deploy1 | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 40h | 40h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072252 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate (PTP) - Deploy1 | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 8h | 8h | 2017-09-11 | 2017-10-06 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072253 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-10 | 2017-04-10 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072254 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-23 | 2017-03-23 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -17 | -12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072255 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 1h | 0h | 1h | 2017-04-03 | 2017-04-03 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -20 | -16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072256 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | -9.88 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072257 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - PTP | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072258 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | Workshop-Purchasing & A/P | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 40h | 0h | 40h | 2017-03-13 | 2017-04-19 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072259 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | Workshop-QI management and held product | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-15 | 2017-02-15 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072260 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTP | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 18h | 0h | 18h | 2017-06-07 | 2017-06-16 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072261 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Gap Definition | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 48h | 48h | 2017-06-30 | 2017-08-24 | Yes |  |  | WP-FUN.Gap Definition | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | 25 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072262 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-13 | 2017-03-17 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -22.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072263 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Collect requierements | EDI | EDI | Saputo | Onshore | Tanguay; Yves | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-22 | 2017-03-22 | Yes |  |  | DELIV-DEV-302.EDI Inventory | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -20 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072264 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Gap Definition | EDI | EDI | Saputo | Onshore | Tanguay; Yves | Saputo | Yes | CapEx | Localization | IT - Internal | 15.5h | 0h | 15.5h | 2017-06-07 | 2017-06-21 | Yes |  |  | WP-FUN.Gap Definition | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | 19.13 | 47.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 11 | 2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072265 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | EDI Build (EDI) - Deploy2 | EDI | EDI | Saputo | Onshore | Tanguay; Yves | Saputo | Yes | CapEx | Localization | IT - Internal | 139.5h | 46h | 185.5h | 2017-08-14 | 2017-09-25 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 33.75 | 23.5 | 29.25 | 24 | 0
1072266 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy2 | LOG | FUN | Saputo | Onshore | Archambault; Yannick | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-10-16 | 2017-10-20 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072267 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy2 | LOG | FUN | Saputo | Onshore | Archambault; Yannick | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 50h | 50h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072268 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (LOG) - Deploy1 | LOG | FUN | Saputo | Onshore | Archambault; Yannick | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 20h | 20h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072269 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Manage defects (LOG) - Deploy1 | LOG | FUN | Saputo | Onshore | Archambault; Yannick | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 20h | 20h | 2017-10-02 | 2017-10-27 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072270 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (LOG) - Deploy1 | LOG | FUN | Saputo | Onshore | Archambault; Yannick | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 200h | 200h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072271 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - OTC (AN) | OTC | FUN | Saputo | Onshore | Larose; Line | Saputo | Yes | CapEx | Localization | IT - Internal | 147h | 0h | 147h | 2017-04-24 | 2017-06-23 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 37 | 0 | 16 | 16 | 0 | 17 | 2 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072272 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - OTC | OTC | FUN | Saputo | Onshore | Larose; Line | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -30 | -30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072273 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | OTC | FUN | Saputo | Onshore | Larose; Line | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -10 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072274 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | OTC | FUN | Saputo | Onshore | Larose; Line | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072275 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | OTC | FUN | Saputo | Onshore | Larose; Line | Saputo | Yes | CapEx | Localization | IT - Internal | 16h | 0h | 16h | 2017-03-14 | 2017-03-17 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072276 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | OTC | FUN | Saputo | Onshore | Larose; Line | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-27 | 2017-03-27 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -25 | -13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072277 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | OTC | FUN | Saputo | Onshore | Larose; Line | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-27 | 2017-03-27 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | -5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072278 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | IOTC010-FSD-INT-Sales order interface | OTC | FUN | Saputo | Onshore | Larose; Line | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -90 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072279 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - OTC-(Global) | OTC | FUN | Saputo | Onshore | Larose; Line | Saputo | Yes | CapEx | Localization | IT - Internal | 116h | 1,449.67h | 1,565.67h | 2017-06-13 | 2018-03-30 | Yes |  |  | ACT-CM.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 32 | 10 | 40 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072280 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) (Test) - OTC | OTC | FUN | Saputo | Onshore | Larose; Line | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072281 | No | No | Yes | SDF | SDF Localisation | 99-Global | Team Lead - EDI | EDI | EDI | Saputo | Onshore | Szilbereisz; Norman | Saputo | Yes | CapEx | Localization | IT - Internal | 217h | 351h | 568h | 2017-07-17 | 2017-11-24 | Yes |  |  |  | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 28 | 41 | 30 | 0 | 0 | 31 | 31 | 33 | 0
1072282 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | Saputo | Onshore | Tremblay; Denis | Saputo | Yes | CapEx | Localization | IT - Internal | 299h | 0h | 299h | 2017-06-20 | 2017-09-15 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 28 | 33 | 35 | 35 | 35 | 35 | 28 | 35 | 0
1072283 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | Saputo | Onshore | Tremblay; Denis | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 120h | 120h | 2017-10-10 | 2017-11-17 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072284 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | Saputo | Onshore | Tremblay; Denis | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072285 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | Saputo | Onshore | Tremblay; Denis | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072286 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | Saputo | Onshore | Tremblay; Denis | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 75h | 75h | 2017-08-28 | 2017-09-29 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072287 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | Saputo | Onshore | Tremblay; Denis | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 45h | 45h | 2017-08-07 | 2017-08-25 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072288 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | Saputo | Onshore | Tremblay; Denis | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072289 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | WRICEFs - DEV (Design/Build) | DEV | DEV | Saputo | Onshore | Tremblay; Denis | Saputo | Yes | CapEx | Localization | IT - Internal | 183.5h | 0h | 183.5h | 2017-06-05 | 2017-07-14 | Yes |  |  | To delete-To delete.To delete | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 15.13 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 28 | 28 | 30 | 27.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072290 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | WRICEFs inventory - DEV | DEV | DEV | Saputo | Onshore | Tremblay; Denis | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | DELIV-DEV-102.RICEFW Inventory | Future Task | NA | NA | 1 | GAPs | 1000 D1-1200 A-1211GAPs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072291 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | Saputo | Onshore | Tremblay; Denis | Saputo | Yes | CapEx | Localization | IT - Internal | 37h | 0h | 37h | 2017-05-15 | 2017-06-02 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 12 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072292 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT 1 - Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | Saputo | Onshore | Tremblay; Denis | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | Yes |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072293 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Break/Fix - DEV | DEV | DEV | Saputo | Onshore | Tremblay; Denis | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0.13 | 5.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072294 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | EDI Build (EDI) - Deploy2 | EDI | EDI | Saputo | Onshore | Schembari; Jeanne | Saputo | Yes | CapEx | Localization | IT - Internal | 150.75h | 72.1h | 222.85h | 2017-07-25 | 2017-10-02 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.25 | 10.5 | 19.25 | 29.75 | 17.25 | 0 | 26.5 | 31.25 | 0
1072295 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy1 - HC - (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 80h | 80h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072296 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Manage Defect - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 40h | 40h | 2017-09-18 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 0.13 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072297 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 70h | 70h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 5 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072298 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 72h | 72h | 2017-11-13 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072299 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 70h | 70h | 2017-11-13 | 2018-01-04 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072300 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 70h | 70h | 2017-11-13 | 2018-01-04 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072301 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072302 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072303 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072304 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072305 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy2 - HC - (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 160h | 160h | 2018-02-05 | 2018-03-02 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | -18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072306 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy2 (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 28h | 0h | 28h | 2017-07-10 | 2017-07-13 | Yes |  |  | ACT-MDG.Build ETL programs | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072307 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy1 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-28 | 2017-08-04 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072308 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 10h | 10h | 2017-09-01 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 33.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072309 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 13h | 13h | 2017-09-01 | 2017-09-15 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 22.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072310 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 15h | 15h | 2017-09-05 | 2017-09-22 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072311 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 10h | 10h | 2017-07-24 | 2017-09-15 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072312 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 15h | 15h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072313 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 15h | 15h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072314 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 15h | 15h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072315 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 15h | 15h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072316 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 12h | 13h | 25h | 2017-08-14 | 2017-09-20 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0
1072317 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 54h | 0h | 54h | 2017-08-14 | 2017-08-25 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 31 | 0 | 0 | 0 | 0
1072318 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 35h | 0h | 35h | 2017-08-28 | 2017-09-01 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0
1072319 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 35h | 0h | 35h | 2017-08-07 | 2017-08-11 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-07-31 | 2017-08-11 | 2 | QE2 Mock Prep | 20000 D2-20100 B-20110 QE2 Mock Prep | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0
1072320 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Preparation - Deploy2 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 40h | 40h | 2017-09-18 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072321 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Execute - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 40h | 40h | 2017-09-18 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 0.13 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072322 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Validation - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 40h | 40h | 2017-09-18 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072323 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) - Deploy2 (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 4h | 4h | 2017-07-31 | 2017-09-15 | Yes |  |  | DELIV-MDG-206.Functional Specification -Conversion | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 45 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072324 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy1 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-12 | 2017-06-26 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072325 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy1 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-28 | 2017-08-04 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 30 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072326 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy1 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-28 | 2017-08-04 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072327 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Mapping Document - Deploy2 (Saputo) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 4h | 4h | 2017-07-31 | 2017-09-15 | Yes |  |  | DELIV-MDG-207.Functional Mapping Document | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072328 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) - Deploy1 - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-02 | 2017-06-02 | Yes |  |  | DELIV-MDG-206.Functional Specification -Conversion | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | -20 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072329 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Prepare Mock1 - Deploy1 - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 50h | 0h | 50h | 2017-05-29 | 2017-06-02 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072330 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy1 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-04 | 2017-07-07 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072331 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy1 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-19 | 2017-06-23 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 30 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072332 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy1 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-30 | 2017-07-07 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072333 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Validation - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 35h | 35h | 2017-09-18 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072334 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Execute - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 35h | 35h | 2017-09-18 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 0.13 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072335 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Preparation - Deploy2 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 35h | 35h | 2017-09-18 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072336 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 82h | 0h | 82h | 2017-08-14 | 2017-08-25 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-07-31 | 2017-08-11 | 2 | QE2 Mock Prep | 20000 D2-20100 B-20110 QE2 Mock Prep | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 49 | 0 | 0 | 0 | 0
1072337 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 56h | 0h | 56h | 2017-08-07 | 2017-08-13 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0
1072338 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 24h | 0h | 24h | 2017-08-16 | 2017-08-31 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0
1072339 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 6h | 6h | 2017-09-01 | 2017-09-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072340 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 14h | 9h | 23h | 2017-09-05 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 6 | 0
1072341 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 10h | 10h | 2017-09-15 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072342 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 51h | 0h | 51h | 2017-09-05 | 2017-09-17 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 35 | 0
1072343 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 6h | 10h | 16h | 2017-09-05 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0
1072344 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 61h | 0h | 61h | 2017-07-24 | 2017-08-17 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0
1072345 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 12h | 12h | 2017-09-05 | 2017-09-22 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072346 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 2h | 22h | 24h | 2017-08-21 | 2017-09-27 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 22.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
1072347 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 1h | 1h | 2017-09-01 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 33.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072348 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy1 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-30 | 2017-07-07 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072349 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy2 (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 79h | 0h | 79h | 2017-07-10 | 2017-08-07 | Yes |  |  | ACT-MDG.Build ETL programs | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072350 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy2 - HC - (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 160h | 160h | 2018-02-05 | 2018-03-02 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | -18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072351 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072352 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072353 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072354 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 70h | 70h | 2017-11-13 | 2018-01-04 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072355 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 70h | 70h | 2017-11-13 | 2018-01-04 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072356 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 72h | 72h | 2017-11-13 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072357 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 70h | 70h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 5 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072358 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Manage Defect - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 35h | 35h | 2017-09-18 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 0.13 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072359 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072360 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy1 - HC - (Saputo) - DC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 80h | 80h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072361 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTM | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072362 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTM(Global) | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 1,360h | 1,360h | 2017-08-07 | 2018-03-30 | Yes |  |  | ACT-FUN.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072363 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT 1 - Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | Saputo | Onshore | Ho; Lien-Chi | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | Yes |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072364 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | WRICEFs inventory - DEV | DEV | DEV | Saputo | Onshore | Ho; Lien-Chi | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | DELIV-DEV-102.RICEFW Inventory | Future Task | NA | NA | 1 | GAPs | 1000 D1-1200 A-1211GAPs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072365 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | Saputo | Onshore | Ho; Lien-Chi | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-12-28 | 2016-12-30 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072366 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | WRICEFs - DEV (Design/Build) | DEV | DEV | Saputo | Onshore | Ho; Lien-Chi | Saputo | Yes | CapEx | Localization | IT - Internal | 172h | 0h | 172h | 2017-06-07 | 2017-07-14 | Yes |  |  | To delete-To delete.To delete | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 15.13 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 35 | 28 | 28 | 31 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072367 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | Saputo | Onshore | Ho; Lien-Chi | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072368 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | Saputo | Onshore | Ho; Lien-Chi | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 36h | 36h | 2017-08-08 | 2017-08-25 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072369 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | Saputo | Onshore | Ho; Lien-Chi | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-08-28 | 2017-09-22 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072370 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | Saputo | Onshore | Ho; Lien-Chi | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072371 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | Saputo | Onshore | Ho; Lien-Chi | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 120h | 120h | 2017-10-10 | 2017-11-17 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072372 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Break/Fix - DEV | DEV | DEV | Saputo | Onshore | Ho; Lien-Chi | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0.13 | 5.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072373 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | Saputo | Onshore | Ho; Lien-Chi | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 40h | 40h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072374 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | Saputo | Onshore | Ho; Lien-Chi | Saputo | Yes | CapEx | Localization | IT - Internal | 121h | 0h | 121h | 2017-06-20 | 2017-09-15 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 4 | 0 | 0 | 0 | 0 | 14 | 33 | 0
1072375 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | EDI Build (EDI) - Deploy2 | EDI | EDI | Saputo | Onshore | Cecere; Maria | Saputo | Yes | CapEx | Localization | IT - Internal | 65h | 147h | 212h | 2017-08-21 | 2017-10-17 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.5 | 17.5 | 14 | 16 | 0
1072376 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 50h | 50h | 2017-08-28 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072377 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 120h | 120h | 2017-10-02 | 2017-12-01 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072378 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 5h | 5h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072379 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 280h | 280h | 2017-09-25 | 2017-11-24 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072380 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 18h | 18h | 2017-08-28 | 2017-09-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072381 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 8h | 8h | 2017-07-28 | 2017-08-25 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072382 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 6h | 6h | 2017-07-28 | 2017-08-31 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072383 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 10h | 10h | 2017-08-14 | 2017-09-11 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072384 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 15h | 15h | 2017-08-15 | 2017-09-13 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 17.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072385 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy2 | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 30h | 30h | 2017-12-04 | 2017-12-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072386 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy2 | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 45h | 45h | 2017-12-04 | 2017-12-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072387 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy2 | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 260h | 260h | 2018-02-05 | 2018-03-30 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072388 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test-RT Execution - Montreal-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | Yes |  |  |  | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072389 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test-'Smoke'' Test Planning and Scheduling-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | Yes |  |  |  | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072390 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B-Dual Maintenance Design and Documentation-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 3h | 0h | 3h | 2017-08-15 | 2017-08-17 | Yes |  |  |  | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0
1072391 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B-FUT Spare Parts-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-04 | 2017-08-04 | Yes |  |  |  | Future Task | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 42 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072392 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test-Defect Management-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 38h | 0h | 38h | 2017-07-31 | 2017-08-04 | Yes |  |  |  | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072393 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test-Defect Workarounds/OPLs-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-18 | 2017-08-18 | Yes |  |  |  | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072394 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test - Material Master - Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 44h | 0h | 44h | 2017-08-14 | 2017-08-18 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | -15 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0
1072395 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B - Material Master - Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 30h | 0h | 30h | 2017-06-19 | 2017-06-26 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-06-09 | 1 | Build and adjust conversion programs | 1000 D1-1300 B-1322 Build and adjust conversion programs | 30 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072396 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | Hypercare-Provide end User Support - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 320h | 320h | 2018-02-05 | 2018-03-30 | Yes |  |  |  | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072397 | No | No | Yes | SDF | SDF Localisation | 99-Global | Team Lead - MDG - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 10h | 60h | 70h | 2016-10-24 | 2018-03-30 | Yes |  |  | DELIV-FUN-029.Site Assessment | On Schedule | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072398 | No | No | Yes | SDF | SDF Localisation | 04-Test | Regression Testing - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 30h | 30h | 2017-11-06 | 2017-11-24 | Yes |  |  |  | Future Task | 2017-11-06 | 2017-11-24 | 2 | D2 Regression (in QE2) | 20000 D2-21000 T-21054 D2 Regression (in QE2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072399 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Support - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 68h | 0h | 68h | 2017-08-21 | 2017-09-01 | Yes |  |  |  | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 60 | 48.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 28 | 0 | 0 | 0
1072400 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | Hypercare-Provide end User Support - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 360h | 360h | 2017-10-02 | 2017-12-01 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072401 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | CapEx | Localization | IT - Internal | 18h | 36h | 54h | 2017-08-28 | 2017-09-15 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | -5 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0
1072402 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover Suport - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 30h | 30h | 2017-09-11 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072403 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover Prepare - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 35h | 35h | 2017-09-01 | 2017-09-19 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -15 | -8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072404 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Support - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 70h | 70h | 2017-12-18 | 2018-02-02 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-11-03 | 2 | Training Material Localization | 20000 D2-29000 MultiPhases-29040 Training Material Localization | 55 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072405 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HYP-Smoke Test Execution-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072406 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HYP-End User Support-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072407 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HYP-Dual Maintenance Execution-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072408 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | C/G-Business Cutover Plan-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-09-18 | 2017-09-18 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072409 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B-Dual Maintenance Training-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | Yes |  |  |  | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 70 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072410 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test-Train the Trainer (TTT)-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | Yes |  |  |  | Future Task | 2017-07-17 | 2017-07-28 | 1 | Train the trainer | 1000 D1-1800 MultiPhases-1840 Train the trainer | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072411 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Run Tests - MDG - MM - Saputo- Deploy1 - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | Yes |  |  |  | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072412 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B-Training: Concept Slides Final Review-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-04 | 2017-08-04 | Yes |  |  |  | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 35 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072413 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B-Training: Job Aids Review-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-04 | 2017-08-04 | Yes |  |  |  | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 35 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072414 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B-Training: Work Instructions Review-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-04 | 2017-08-04 | Yes |  |  |  | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 35 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072415 | No | No | Yes | SDF | SDF Localisation | 99-Global | Create Training Data in trg environment | CM | CM | Saputo | Onshore | Bogan; Alina | Saputo | Yes | OpEx | Localization | IT - Internal | 43h | 29.98h | 72.98h | 2017-06-22 | 2017-09-18 | Yes |  |  | DELIV-CM-402.Training Schedule and Logistics | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 12 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0
1072416 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Materials-Traininng Data (exercise book) (Design/Build) | CM | CM | Saputo | Onshore | Bogan; Alina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 5.72h | 5.72h | 2017-10-03 | 2017-11-03 | Yes |  |  | DELIV-CM-401.Training Materials | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 20 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072417 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Materials-Work Instructions/Job aids (Design/Build) | CM | CM | Saputo | Onshore | Bogan; Alina | Saputo | Yes | OpEx | Localization | IT - Internal | 353h | 0h | 353h | 2017-06-12 | 2017-09-08 | Yes |  |  | DELIV-CM-451.Work Instructions | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 10 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 30.5 | 34 | 43 | 33.5 | 0 | 0 | 8.5 | 40 | 44.5 | 40 | 40 | 32 | 0 | 0
1072418 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Data Definition Documents (RTR) - Deploy2 | RTR | FUN | Saputo | Onshore | Amrine; Dave | Saputo | Yes | CapEx | Localization | IT - Internal | 35h | 0h | 35h | 2017-08-07 | 2017-09-01 | Yes |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 9 | 10 | 10 | 0 | 0 | 0
1072419 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Support Mock1 (RTR) - Deploy2 | RTR | FUN | Saputo | Onshore | Amrine; Dave | Saputo | Yes | CapEx | Localization | IT - Internal | 10h | 20h | 30h | 2017-08-21 | 2017-09-05 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-09-25 | 2017-10-06 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -25 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 8 | 0 | 0 | 0
1072420 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Support (RTR) - Deploy1 | RTR | FUN | Saputo | Onshore | Amrine; Dave | Saputo | Yes | CapEx | Localization | IT - Internal | 35h | 0h | 35h | 2017-07-24 | 2017-08-25 | Yes |  |  | ACT-FUN.Mock Support | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 4 | 10 | 10 | 0 | 0 | 0 | 0
1072421 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (RTR) - Deploy1 | RTR | FUN | Saputo | Onshore | Amrine; Dave | Saputo | Yes | CapEx | Localization | IT - Internal | 25h | 0h | 25h | 2017-07-17 | 2017-08-04 | Yes |  |  | ACT-FUN.Functional Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072422 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (RTR) - Deploy1 | RTR | FUN | Saputo | Onshore | Amrine; Dave | Saputo | Yes | CapEx | Localization | IT - Internal | 32h | 0h | 32h | 2017-08-07 | 2017-09-01 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 13.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 11 | 10 | 9 | 0 | 0 | 0
1072423 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | Workshop-Design Interim state financial reporting | RTR | FUN | Saputo | Onshore | Amrine; Dave | Saputo | Yes | CapEx | Localization | IT - Internal | 14h | 0h | 14h | 2017-06-12 | 2017-07-05 | Yes |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072424 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | RTM - RTR | RTR | FUN | Saputo | Onshore | Amrine; Dave | Saputo | Yes | CapEx | Localization | IT - Internal | 62h | 0h | 62h | 2017-04-17 | 2017-05-26 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 20 | 15 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072425 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Data Definition Documents (DDD) (RTR) - Deploy1 | RTR | FUN | Saputo | Onshore | Amrine; Dave | Saputo | Yes | CapEx | Localization | IT - Internal | 110h | 0h | 110h | 2017-06-05 | 2017-08-04 | Yes |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Complete | 2017-04-17 | 2017-05-05 | 1 | Revise DDDs - Division review | 1000 D1-1200 A-1213 Revise DDDs - Division review | 35 | 78.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 9 | 0 | 2 | 13 | 20 | 27 | 11 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072426 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | DM TAI SDF Dev Installation and Configuration - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 12h | 0h | 12h | 2017-04-03 | 2017-06-11 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-01 | 2017-05-05 | 1 | Data Construction | 1000 D1-1200 A-1214 Data Construction | -35 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072427 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Prepare Mock1 - Deploy1 - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 56.5h | 0h | 56.5h | 2017-05-22 | 2017-06-09 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.5 | 6 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072428 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Data collection templates (DCT) - Explain and collect - Deploy1 - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 28h | 0h | 28h | 2017-05-15 | 2017-05-19 | Yes |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072429 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) - Deploy1 - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 105h | 0h | 105h | 2017-05-01 | 2017-06-19 | Yes |  |  | DELIV-MDG-206.Functional Specification -Conversion | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | -20 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 9 | 25 | 0 | 24 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072430 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Data Validation Sheets - Deploy1 - Test - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 9h | 0h | 9h | 2017-06-22 | 2017-07-06 | Yes |  |  | WP-MDG.Data Validation Sheets | Complete | 2017-06-05 | 2017-06-16 | 1 | QE2 Prevalidation | 1000 D1-1300 B-1325 QE2 Prevalidation | -1 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072431 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy1 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 39h | 0h | 39h | 2017-06-12 | 2017-07-20 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 2 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072432 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Data profiling - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 134h | 0h | 134h | 2017-03-06 | 2017-05-25 | Yes |  |  | DELIV-MDG-050.Data Profiling | Complete | 2017-05-01 | 2017-05-05 | 1 | Data Construction | 1000 D1-1200 A-1214 Data Construction | -55 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 46 | 0 | 0 | 0 | 0 | 11 | 0 | 10 | 21 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072433 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Mock Load - Deploy1 - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-03 | 2017-07-07 | Yes |  |  | ACT-MDG.Mock Load | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072434 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Mock1 Preparation - Deploy1 - CG - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-04 | 2017-07-04 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072435 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Mock1 Validation - Deploy1 - CG- DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 8h | 0h | 8h | 2017-07-05 | 2017-07-07 | Yes |  |  | ACT-MDG.Mock Validation | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072436 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 34h | 0h | 34h | 2017-04-17 | 2017-04-21 | Yes |  |  | ACT-MDG.MDG - Workshop | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072437 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Data Cleansing - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 128h | 0h | 128h | 2017-04-03 | 2017-04-28 | Yes |  |  | DELIV-MDM-110.Data Cleansing and Migration Approach | Complete | 2017-05-01 | 2017-05-05 | 1 | Data Construction | 1000 D1-1200 A-1214 Data Construction | -20 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 49 | 6 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072438 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy1 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 23.5h | 0h | 23.5h | 2017-06-19 | 2017-07-20 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 7 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072439 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy1 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 97h | 0h | 97h | 2017-06-12 | 2017-07-14 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 10 | 5 | 8 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072440 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy1 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 142h | 0h | 142h | 2017-06-17 | 2017-07-20 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 30 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 48.5 | 52 | 15 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072441 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Mapping Document - Deploy2 (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 5h | 5h | 2017-07-31 | 2017-09-15 | Yes |  |  | DELIV-MDG-207.Functional Mapping Document | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072442 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) - Deploy2 (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 1h | 13h | 14h | 2017-07-31 | 2017-09-15 | Yes |  |  | DELIV-MDG-206.Functional Specification -Conversion | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 45 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
1072443 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy2 (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-04 | 2017-08-11 | Yes |  |  | ACT-MDG.Build ETL programs | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072444 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 2h | 12h | 14h | 2017-09-08 | 2017-10-12 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 33.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
1072445 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 15h | 15h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072446 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 10h | 0h | 10h | 2017-07-31 | 2017-08-04 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 22.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072447 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 10h | 10h | 2017-09-08 | 2017-09-22 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072448 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 62h | 0h | 62h | 2017-07-24 | 2017-07-30 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072449 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 15h | 15h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072450 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 15h | 15h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072451 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 15h | 15h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072452 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 53h | 0h | 53h | 2017-08-31 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 34 | 0 | 0
1072453 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 103h | 0h | 103h | 2017-07-31 | 2017-08-25 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 13 | 0 | 56 | 0 | 0 | 0 | 0
1072454 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 69h | 0h | 69h | 2017-08-14 | 2017-08-20 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 0 | 0 | 0 | 0 | 0
1072455 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 75.5h | 0h | 75.5h | 2017-07-31 | 2017-08-23 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-07-31 | 2017-08-11 | 2 | QE2 Mock Prep | 20000 D2-20100 B-20110 QE2 Mock Prep | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.5 | 50 | 0 | 4 | 0 | 0 | 0 | 0
1072456 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Preparation - Deploy2 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 35h | 35h | 2017-09-18 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072457 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Execute - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 35h | 35h | 2017-09-18 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 0.13 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072458 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Validation - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 35h | 35h | 2017-09-18 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072459 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy1 - HC - (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072460 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Manage Defect - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 35h | 35h | 2017-09-18 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 0.13 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072461 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 70h | 70h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 5 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072462 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 70h | 70h | 2017-11-13 | 2018-01-01 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072463 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 72h | 72h | 2017-11-13 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072464 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 70h | 70h | 2017-11-13 | 2018-01-01 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072465 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-26 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072466 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-26 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072467 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-26 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072468 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-26 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072469 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy2 - HC - (Saputo) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 160h | 160h | 2018-02-05 | 2018-03-02 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | -18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072470 | No | No | Yes | SDF | SDF Localisation | 99-Global | Team Lead - MDG - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | OpEx | Localization | IT - Internal | 16h | 61h | 77h | 2016-10-24 | 2018-03-26 | Yes |  |  | DELIV-FUN-029.Site Assessment | On Schedule | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0
1072471 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | Hypercare-Provide end User Support - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 320h | 320h | 2018-02-05 | 2018-03-30 | Yes |  |  |  | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072472 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Support - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 260h | 260h | 2017-12-18 | 2018-02-16 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-11-03 | 2 | Training Material Localization | 20000 D2-29000 MultiPhases-29040 Training Material Localization | 55 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072473 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Preparation - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | OpEx | Localization | IT - Internal | 50h | 20h | 70h | 2017-08-28 | 2017-09-18 | Yes |  |  |  | Future Task | 2017-08-21 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 0 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 18 | 12 | 0
1072474 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT 1-Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-09-18 | 2017-10-06 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072475 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 140h | 140h | 2017-12-04 | 2018-01-05 | Yes |  |  |  | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | -25 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072476 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT 2-Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-10-09 | 2017-10-27 | Yes |  |  |  | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072477 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover Prepare - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 395h | 395h | 2017-10-30 | 2018-04-13 | Yes |  |  |  | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -95 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072478 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover Prepare - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | OpEx | Localization | IT - Internal | 13h | 20h | 33h | 2017-08-30 | 2017-09-19 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -15 | -8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 10 | 0
1072479 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover Suport - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 30h | 30h | 2017-09-11 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072480 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | Hypercare-Provide end User Support - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 180h | 180h | 2017-10-02 | 2017-12-01 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072481 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Support - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-23 | 2017-08-25 | Yes |  |  |  | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 60 | 48.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072482 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B - Customer Master - Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-06-09 | 1 | Build and adjust conversion programs | 1000 D1-1300 B-1322 Build and adjust conversion programs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072483 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test - Customer Master - Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | OpEx | Localization | IT - Internal | 36h | 0h | 36h | 2017-07-31 | 2017-08-25 | Yes |  |  | ACT-FUN.Execute SIT | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 24 | 0 | 0 | 0 | 0
1072484 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-08-15 | 2017-09-05 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 17.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072485 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 20h | 40h | 60h | 2017-07-31 | 2017-08-16 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072486 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-25 | 2017-09-25 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072487 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 0h | 44h | 44h | 2017-09-25 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072488 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-10-02 | 2017-12-15 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072489 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-09-11 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072490 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-08-28 | 2017-09-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072491 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 5h | 15h | 20h | 2017-06-05 | 2017-08-23 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 10 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0
1072492 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-07-17 | 2017-08-04 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072493 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-08-07 | 2017-08-25 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072494 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2017-05-15 | 2017-08-11 | Yes |  |  | ACT-FUN.Management | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0
1072495 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Demo (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2017-08-14 | 2017-08-17 | Yes |  |  | ACT-FUN.Solution Confirmation Prensentations and Demonstrations | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0
1072496 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 0h | 132h | 132h | 2018-01-15 | 2018-01-30 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -8 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072497 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 0h | 120h | 120h | 2018-02-05 | 2018-03-30 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072498 | No | No | Yes | SDF | SDF Localisation | 04-Test | DR - Support (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-11-20 | 2017-12-01 | Yes |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072499 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-12-04 | 2017-12-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072500 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 0h | 88h | 88h | 2018-01-15 | 2018-01-26 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -30 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072501 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy2 | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-12-04 | 2017-12-29 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072502 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - SEC | SEC | SEC | Saputo | Onshore | Sharma; Kush | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 750h | 750h | 2017-09-11 | 2018-04-06 | Yes |  |  |  | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072503 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Landed Onshore | Chauhan; Sidharth | IBM | Yes | CapEx | Localization | IT - External | 30h | 0h | 30h | 2017-07-31 | 2017-08-04 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072504 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Landed Onshore | Chauhan; Sidharth | IBM | Yes | CapEx | Localization | IT - External | 47h | 3h | 50h | 2017-08-07 | 2017-09-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 10 | 0 | 7 | 0 | 0 | 0
1072505 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | SDF-Localization-Developments (PP) | DEV | DEV | SI | Landed Onshore | Chauhan; Sidharth | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | DELIV-DEV-102.RICEFW Inventory | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072506 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | WRICEFs inventory - DEV | DEV | DEV | SI | Landed Onshore | Chauhan; Sidharth | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-02 | 2017-06-02 | Yes |  |  | DELIV-DEV-102.RICEFW Inventory | Future Task | NA | NA | 1 | GAPs | 1000 D1-1200 A-1211GAPs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072507 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy1 (Design/Build) | DEV | DEV | SI | Landed Onshore | Chauhan; Sidharth | IBM | Yes | CapEx | Localization | IT - External | 53h | 0h | 53h | 2017-06-26 | 2017-07-21 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 16 | 15 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072508 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | SDF Interim State Project | DEV | DEV | SI | Landed Onshore | Chauhan; Sidharth | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2017-01-10 | 2017-01-11 | Yes |  |  | DELIV-DEV-102.RICEFW Inventory | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072509 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing WRICEFs (Design/Build) | DEV | DEV | SI | Landed Onshore | Chauhan; Sidharth | IBM | Yes | CapEx | Localization | IT - External | 172h | 52h | 224h | 2017-02-13 | 2017-11-03 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -88 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 10 | 10 | 0 | 20 | 18 | 20 | 20 | 20 | 20 | 4 | 12 | 6 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072510 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | SI | Landed Onshore | Chauhan; Sidharth | IBM | Yes | CapEx | Localization | IT - External | 131h | 16h | 147h | 2017-07-10 | 2017-09-19 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 14 | 14 | 10 | 24 | 24 | 16 | 19 | 0
1072511 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | SI | Landed Onshore | Chauhan; Sidharth | IBM | Yes | CapEx | Localization | IT - External | 15h | 50h | 65h | 2017-09-11 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0
1072512 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Landed Onshore | Chauhan; Sidharth | IBM | Yes | CapEx | Localization | IT - External | 0h | 95h | 95h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072513 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Landed Onshore | Chauhan; Sidharth | IBM | Yes | CapEx | Localization | IT - External | 0h | 75h | 75h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072514 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | SI | Landed Onshore | Chauhan; Sidharth | IBM | Yes | CapEx | Localization | IT - External | 0h | 110h | 110h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072515 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | Framework FSD/Testing | DEV | DEV | SI | Landed Onshore | Chauhan; Sidharth | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072516 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | SI | Landed Onshore | Chauhan; Sidharth | IBM | Yes | CapEx | Localization | IT - External | 245h | 70h | 315h | 2017-05-29 | 2017-11-10 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 14 | 10 | 18 | 20 | 15 | 20 | 24 | 0 | 0 | 24 | 20 | 20 | 20 | 10 | 0
1072517 | No | No | Yes | SDF | SDF Localisation | 99-Global | Manage TAI Infrastructure | PMO | PMO | Saputo | Onshore | Volcy; Carl-Henry | Saputo | Yes | CapEx | Localization | IT - Internal | 60h | 280h | 340h | 2017-08-28 | 2017-12-29 | Yes |  |  |  | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 20
1072518 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT 1 - Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | Saputo | Onshore | Costa; Jorge Luis | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | Yes |  |  | To delete-To delete.To delete | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072519 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | WRICEFs - DEV (Design/Build) | DEV | DEV | Saputo | Onshore | Costa; Jorge Luis | Saputo | Yes | CapEx | Localization | IT - Internal | 178h | 0h | 178h | 2017-06-07 | 2017-07-14 | Yes |  |  | To delete-To delete.To delete | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 15.13 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 35 | 28 | 28 | 31 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072520 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | Saputo | Onshore | Costa; Jorge Luis | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-05-26 | 2017-05-26 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072521 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | Saputo | Onshore | Costa; Jorge Luis | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072522 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | Saputo | Onshore | Costa; Jorge Luis | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072523 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Break/Fix - DEV | DEV | DEV | Saputo | Onshore | Costa; Jorge Luis | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0.13 | 5.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072524 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | Saputo | Onshore | Costa; Jorge Luis | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 120h | 120h | 2017-10-10 | 2017-11-17 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072525 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | Saputo | Onshore | Costa; Jorge Luis | Saputo | Yes | CapEx | Localization | IT - Internal | 105h | 0h | 105h | 2017-07-17 | 2017-08-04 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072526 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | Saputo | Onshore | Costa; Jorge Luis | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 75h | 75h | 2017-08-28 | 2017-09-29 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072527 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | Saputo | Onshore | Costa; Jorge Luis | Saputo | Yes | CapEx | Localization | IT - Internal | 133h | 0h | 133h | 2017-06-20 | 2017-09-15 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 28 | 35 | 0
1072528 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | Saputo | Onshore | Costa; Jorge Luis | Saputo | Yes | CapEx | Localization | IT - Internal | 28h | 0h | 28h | 2017-08-07 | 2017-08-10 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0
1072529 | No | Yes | No | SDF | SDF Localisation | 02-Analyze | Kickoff - RTR | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Localization | IT - External | 7h | 0h | 7h | 2017-04-17 | 2017-04-18 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -9.88 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072530 | No | Yes | No | SDF | SDF Localisation | 02-Analyze | Kickoff - LOG | LOG | FUN | SI | Onshore | Gera; Tanvi | IBM | Yes | CapEx | Localization | IT - External | 79.2h | 0h | 79.2h | 2017-04-17 | 2017-05-05 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.2 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072531 | No | Yes | No | SDF | SDF Interim State Project | 02-Analyze | SDF Interim State-Workshop-Production receipts and inventory adjustments | LOG | FUN | SI | Onshore | Gera; Tanvi | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-02-20 | 2017-02-24 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072532 | No | Yes | No | SDF | SDF Localisation | 99-Global | Team Lead - MDG - DM | MDG | DM | SI | Onshore | Ingalls; Lindsey | Accenture | Yes | OpEx | Localization | IT - External | 60h | 0h | 60h | 2017-06-19 | 2017-06-30 | Yes |  |  | DELIV-FUN-029.Site Assessment | On Schedule | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072533 | No | Yes | No | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2017-03-31 | 2017-04-10 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -20 | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072534 | No | Yes | No | SDF | SDF Localisation | 02-Analyze | Log Gaps - PTM | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072535 | No | Yes | No | SDF | SDF Localisation | 02-Analyze | Kickoff - PTM | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072536 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) - PTM - Deploy1 | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2017-05-15 | 2017-07-14 | Yes |  |  | To delete-To delete.To delete | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 9 | 5 | 0 | 0 | 5 | 4 | 38 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072537 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Configuration - PTM - Deploy1 | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2017-05-15 | 2017-05-17 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072538 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | DM TAI SDF Dev Installation and Configuration - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-01 | 2017-05-05 | 1 | Data Construction | 1000 D1-1200 A-1214 Data Construction | -35 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072539 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Mock1 Preparation - Deploy1 - CG - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072540 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Data conversion plan - MDG - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 84h | 0h | 84h | 2017-04-10 | 2017-04-21 | Yes |  |  | DELIV-MDG-201.Data Conversion Plan | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072541 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-04-24 | 2017-04-28 | Yes |  |  | ACT-MDG.MDG - Workshop | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072542 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Data collection templates (DCT) - Explain and collect - Deploy1 - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 76h | 0h | 76h | 2017-05-16 | 2017-06-02 | Yes |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 16 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072543 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Mock Load - Deploy1 - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | Yes |  |  | ACT-MDG.Mock Load | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072544 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Mock1 Validation - Deploy1 - CG- DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-24 | 2017-07-24 | Yes |  |  | ACT-MDG.Mock Validation | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072545 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Data Validation Sheets - Deploy1 - Test - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 54h | 0h | 54h | 2017-06-19 | 2017-06-23 | Yes |  |  | WP-MDG.Data Validation Sheets | Complete | 2017-06-05 | 2017-06-16 | 1 | QE2 Prevalidation | 1000 D1-1300 B-1325 QE2 Prevalidation | -1 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072546 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Prepare Mock1 - Deploy1 - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 71h | 0h | 71h | 2017-05-08 | 2017-06-09 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 16 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072547 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) - Deploy1 - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 93h | 0h | 93h | 2017-05-01 | 2017-05-19 | Yes |  |  | DELIV-MDG-206.Functional Specification -Conversion | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | -20 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 25 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072548 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-24 | 2017-07-28 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072549 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 66h | 0h | 66h | 2017-06-26 | 2017-08-11 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 30 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0
1072550 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 74h | 0h | 74h | 2017-06-26 | 2017-08-18 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 42 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0
1072551 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 152h | 0h | 152h | 2017-07-10 | 2017-08-04 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 32 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072552 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy2 - HC - (Accenture) - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2018-02-05 | 2018-03-02 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | -17.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072553 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -4.88 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072554 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -50 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072555 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-22 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072556 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072557 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072558 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072559 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-21 | 2017-07-28 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 15 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072560 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 60h | 0h | 60h | 2017-08-14 | 2017-09-01 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-07-31 | 2017-08-11 | 2 | QE2 Mock Prep | 20000 D2-20100 B-20110 QE2 Mock Prep | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 40 | 0 | 0 | 0
1072561 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2017-08-07 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 40 | 0 | 32 | 0 | 0
1072562 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-08 | 2017-09-15 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072563 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-09-11 | 2017-09-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 14.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0
1072564 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 20h | 48h | 68h | 2017-09-11 | 2017-10-20 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0
1072565 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072566 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 0h | 65h | 65h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072567 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 0h | 100h | 100h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072568 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 0h | 55h | 55h | 2017-10-30 | 2017-12-07 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 0 | 18.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072569 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 0h | 65h | 65h | 2017-10-30 | 2017-12-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072570 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Manage UAT (Test) - Deploy1 | Test | Test | Saputo | Onshore | Bensoussan; Tanya | Saputo | Yes | CapEx | Localization | IT - Internal | 112h | 88h | 200h | 2017-08-28 | 2017-09-18 | Yes |  |  | ACT-Test.Management | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 32 | 40 | 0
1072571 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Scenarios/Scripts (Test) - Deploy1 | Test | Test | Saputo | Onshore | Bensoussan; Tanya | Saputo | Yes | CapEx | Global | IT - Internal | 16h | 0h | 16h | 2017-06-19 | 2017-07-14 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Complete | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | -5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072572 | No | No | Yes | SDF | SDF Localisation | 04-Test | Manage SIT (Test) - Deploy1 | Test | Test | Saputo | Onshore | Bensoussan; Tanya | Saputo | Yes | CapEx | Localization | IT - Internal | 182h | 0h | 182h | 2017-07-24 | 2017-08-25 | Yes |  |  | ACT-Test.Management | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 37 | 35 | 40 | 40 | 0 | 0 | 0 | 0
1072573 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - PTM | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072574 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Log Gaps - PTM | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072575 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | DDD | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2017-06-14 | 2017-06-16 | Yes |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Complete | 2017-04-17 | 2017-05-05 | 1 | Revise DDDs - Division review | 1000 D1-1200 A-1213 Revise DDDs - Division review | 15 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072576 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 126h | 0h | 126h | 2017-05-17 | 2017-07-14 | Yes |  |  | ACT-FUN.Management | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 21 | 45 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072577 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Deploy1 | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | -5 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072578 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 100h | 0h | 100h | 2017-07-17 | 2017-07-28 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072579 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 8h | 46.5h | 54.5h | 2017-06-19 | 2017-07-20 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 10 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072580 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2017-07-05 | 2017-07-07 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | -15 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072581 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 0h | 52h | 52h | 2017-08-15 | 2017-09-01 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 17.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072582 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-08-07 | 2017-08-18 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 40 | 0 | 0 | 0 | 0 | 0
1072583 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-07-21 | 2017-08-11 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072584 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-08-28 | 2017-09-08 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072585 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-08-28 | 2017-09-15 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072586 | No | No | Yes | SDF | SDF Localisation | 04-Test | Regression - Run Tests (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | Yes |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072587 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-05 | 2017-09-29 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 15 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072588 | No | No | Yes | SDF | SDF Interim State Project | 01-Preparation | Environment setup | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072589 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 90h | 5h | 95h | 2017-07-31 | 2017-08-25 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | 5 | 29.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 40 | 0 | 0 | 0 | 0
1072590 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 configuration (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 18h | 27h | 45h | 2017-07-03 | 2017-07-07 | Yes |  |  | ACT-FUN.Management | Future Task | 2017-06-19 | 2017-06-30 | 1 | Cycle 2 Config | 1000 D1-1300 B-1318 Cycle 2 Config | 10 | 26.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072591 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 configuration (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 73h | 0h | 73h | 2017-06-19 | 2017-06-30 | Yes |  |  | ACT-FUN.Management | Complete | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072592 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072593 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 0h | 100h | 100h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072594 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 0h | 100h | 100h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072595 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 0h | 85h | 85h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072596 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | PDD-FS Trade Promotion Planning - TPM-OTC | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-03-23 | 2017-03-23 | Yes |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072597 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | PDD-FS Trade Promotion Execution - TPM-OTC | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-03-22 | 2017-03-22 | Yes |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072598 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | PDD-FS Settlements & Claim Reconcilation - TPM-OTC | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-03-22 | 2017-03-22 | Yes |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072599 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | PDD-FS Trade Master Data - TPM-OTC | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-03-22 | 2017-03-22 | Yes |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072600 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - LOG | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2017-04-18 | 2017-04-28 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072601 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072602 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-19 | 2017-06-23 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-19 | 2017-06-30 | 1 | Cycle 2 Config | 1000 D1-1300 B-1318 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072603 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | Yes |  |  | DELIV-FUN-220.Solution Design Document (SDD) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072604 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 72h | 0h | 72h | 2017-07-05 | 2017-07-14 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072605 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072606 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Support Mock1 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 0h | 45h | 45h | 2017-08-21 | 2017-09-11 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-09-25 | 2017-10-06 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -25 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072607 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-09-05 | 2017-09-15 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 10 | 16.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072608 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 configuration (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 125h | 0h | 125h | 2017-08-16 | 2017-09-01 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 45 | 0 | 0 | 0
1072609 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-09-04 | 2017-09-15 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | -8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0
1072610 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 0h | 135h | 135h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072611 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 0h | 135h | 135h | 2017-10-09 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072612 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-10-09 | 2017-10-09 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072613 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-18 | 2017-09-18 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072614 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 50h | 0h | 50h | 2017-08-07 | 2017-08-11 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 4.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0
1072615 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 50h | 0h | 50h | 2017-07-17 | 2017-08-04 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072616 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Support (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072617 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-21 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072618 | No | No | Yes | SDF | SDF Interim State Project | 01-Preparation | Environment setup | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072619 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072620 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072621 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Support (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 100h | 0h | 100h | 2017-07-17 | 2017-07-28 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072622 | No | No | Yes | SDF | SDF Interim State Project | 01-Preparation | Environment setup | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-01-09 | 2017-01-27 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072623 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | CapEx | Localization | IT - External | 0h | 93h | 93h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072624 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | CapEx | Localization | IT - External | 0h | 140h | 140h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072625 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072626 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-09-05 | 2017-09-15 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 15 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072627 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-07-31 | 2017-08-04 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | 5 | 29.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072628 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | CapEx | Localization | IT - External | 0h | 69h | 69h | 2017-08-28 | 2017-09-15 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072629 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | CapEx | Localization | IT - External | 0h | 88h | 88h | 2017-08-28 | 2017-09-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072630 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | CapEx | Localization | IT - External | 96h | 0h | 96h | 2017-08-07 | 2017-08-24 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 32 | 24 | 0 | 0 | 0 | 0
1072631 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | CapEx | Localization | IT - External | 24h | 28h | 52h | 2017-08-14 | 2017-08-31 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 17.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 16 | 0 | 0 | 0 | 0
1072632 | No | No | Yes | SDF | SDF Localisation | 04-Test | Regression - Run Tests (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | Yes |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072633 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Deploy1 | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | CapEx | Global | IT - External | 35h | 0h | 35h | 2017-06-02 | 2017-06-23 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | -5 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072634 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | CapEx | Localization | IT - External | 78h | 0h | 78h | 2017-06-27 | 2017-07-14 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | -15 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 10 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072635 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Gap Definition | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | CapEx | Localization | IT - External | 50h | 0h | 50h | 2017-05-29 | 2017-06-09 | Yes |  |  | WP-FUN.Gap Definition | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072636 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | CapEx | Localization | IT - External | 75h | 0h | 75h | 2017-07-17 | 2017-08-04 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072637 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | CapEx | Localization | IT - External | 35h | 0h | 35h | 2017-07-24 | 2017-08-11 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0
1072638 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | CapEx | Localization | IT - External | 50h | 0h | 50h | 2017-07-10 | 2017-07-28 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 10 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072639 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - PTM | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | CapEx | Localization | IT - External | 86h | 0h | 86h | 2017-04-17 | 2017-05-26 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 15 | 20 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072640 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Log Gaps - PTM | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | CapEx | Localization | IT - External | 52h | 0h | 52h | 2017-04-17 | 2017-05-26 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 20 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072641 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | DDD | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2017-05-08 | 2017-05-19 | Yes |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Complete | 2017-04-17 | 2017-05-05 | 1 | Revise DDDs - Division review | 1000 D1-1200 A-1213 Revise DDDs - Division review | 15 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072642 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | CapEx | Localization | IT - External | 128h | 0h | 128h | 2017-05-29 | 2017-07-07 | Yes |  |  | ACT-FUN.Management | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 45 | 10 | 8 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072643 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Support (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072644 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-06-19 | 2017-06-23 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072645 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072646 | No | No | Yes | SDF | SDF Interim State Project | 01-Preparation | Environment setup | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-01-09 | 2017-01-20 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072647 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-21 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072648 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Support (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072649 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 0h | 35h | 35h | 2017-08-07 | 2017-08-11 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 4.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072650 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 0h | 10h | 10h | 2017-08-14 | 2017-08-18 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072651 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-06-26 | 2017-06-30 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 20 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072652 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-10-09 | 2017-10-09 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072653 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 0h | 45h | 45h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072654 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-10-10 | 2017-10-13 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072655 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072656 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-08-18 | 2017-09-15 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | -8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072657 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 configuration (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 0h | 36h | 36h | 2017-08-11 | 2017-08-31 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072658 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Report (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-08-21 | 2017-08-24 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 55 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0
1072659 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Support Mock1 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-08-21 | 2017-09-15 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-09-25 | 2017-10-06 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -25 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072660 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 0h | 260h | 260h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072661 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-06-26 | 2017-06-30 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072662 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 105h | 0h | 105h | 2017-06-26 | 2017-09-15 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0
1072663 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-08 | 2017-08-21 | Yes |  |  | DELIV-FUN-220.Solution Design Document (SDD) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072664 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 53h | 0h | 53h | 2017-06-27 | 2017-09-03 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-19 | 2017-06-30 | 1 | Cycle 2 Config | 1000 D1-1300 B-1318 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 0 | 0 | 0
1072665 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - LOG | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2017-04-17 | 2017-04-21 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072666 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 configuration (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 107h | 0h | 107h | 2017-07-31 | 2017-08-11 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | 25 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 45 | 0 | 0 | 0 | 0 | 0 | 0
1072667 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072668 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | HEDA; NAND | IBM | Yes | CapEx | Localization | IT - External | 43h | 0h | 43h | 2017-08-14 | 2017-09-01 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 12 | 15 | 0 | 0 | 0
1072669 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | HEDA; NAND | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-07-17 | 2017-08-11 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0
1072670 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | SDF-Localization-Developments (PP) | DEV | DEV | SI | Offshore | HEDA; NAND | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | DELIV-DEV-102.RICEFW Inventory | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072671 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | SI | Offshore | HEDA; NAND | IBM | Yes | CapEx | Localization | IT - External | 136h | 60h | 196h | 2017-02-13 | 2017-10-31 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 25 | 25 | 25 | 20 | 8 | 10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072672 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | WRICEFs inventory - DEV | DEV | DEV | SI | Offshore | HEDA; NAND | IBM | Yes | CapEx | Localization | IT - External | 39h | 0h | 39h | 2017-05-01 | 2017-06-16 | Yes |  |  | DELIV-DEV-102.RICEFW Inventory | Future Task | NA | NA | 1 | GAPs | 1000 D1-1200 A-1211GAPs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 12 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072673 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing WRICEFs (Design/Build) | DEV | DEV | SI | Offshore | HEDA; NAND | IBM | Yes | CapEx | Localization | IT - External | 23h | 50h | 73h | 2017-03-14 | 2017-11-03 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -88 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 0 | 5 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072674 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy1 (Design/Build) | DEV | DEV | SI | Offshore | HEDA; NAND | IBM | Yes | CapEx | Localization | IT - External | 103h | 0h | 103h | 2017-06-19 | 2017-08-04 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 15 | 3 | 10 | 20 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072675 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | SI | Offshore | HEDA; NAND | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072676 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | HEDA; NAND | IBM | Yes | CapEx | Localization | IT - External | 0h | 160h | 160h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072677 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | HEDA; NAND | IBM | Yes | CapEx | Localization | IT - External | 0h | 130h | 130h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072678 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | SI | Offshore | HEDA; NAND | IBM | Yes | CapEx | Localization | IT - External | 20h | 10h | 30h | 2017-09-04 | 2017-09-29 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 5 | 0
1072679 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | SI | Offshore | HEDA; NAND | IBM | Yes | CapEx | Localization | IT - External | 205h | 0h | 205h | 2017-07-10 | 2017-09-15 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 10 | 5 | 20 | 30 | 20 | 24 | 30 | 30 | 30 | 0
1072680 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Data Conversion Plan - Deploy1 - DC | MDG | DC | Saputo | Onshore | Mayhall; Delano | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-02 | 2017-06-02 | Yes |  |  | DELIV-MDG-201.Data Conversion Plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072681 | No | No | Yes | SDF | SDF Localisation | 99-Global | Team Lead - MDG - DC | MDG | DC | Saputo | Onshore | Mayhall; Delano | Saputo | Yes | CapEx | Localization | IT - Internal | 597h | 1,615h | 2,212h | 2017-06-05 | 2018-05-04 | Yes |  |  | DELIV-FUN-029.Site Assessment | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 56 | 52 | 54 | 0 | 60 | 52 | 42 | 64 | 55 | 55 | 59 | 0 | 0 | 0 | 0
1072682 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-08-28 | 2017-09-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072683 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-09-11 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072684 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072685 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-25 | 2017-09-25 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072686 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | CapEx | Localization | IT - External | 0h | 44h | 44h | 2017-09-25 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072687 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Support-D1 PTM | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | CapEx | Localization | IT - External | 0h | 6h | 6h | 2017-09-11 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-05-22 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 80 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072688 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Support-D2 PTM | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | CapEx | Localization | IT - External | 0h | 10h | 10h | 2017-10-02 | 2017-11-03 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-11-03 | 2 | Training Material Localization | 20000 D2-29000 MultiPhases-29040 Training Material Localization | 10 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072689 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - LOG | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072690 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072691 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2017-05-23 | 2017-05-26 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072692 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 332h | 0h | 332h | 2017-06-19 | 2017-08-25 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-19 | 2017-06-30 | 1 | Cycle 2 Config | 1000 D1-1300 B-1318 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 32 | 40 | 0 | 30 | 30 | 40 | 40 | 40 | 0 | 0 | 0 | 0
1072693 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2017-05-29 | 2017-06-09 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072694 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | PDDs | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | Yes |  |  | DELIV-FUN-110.PDDs | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072695 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 0h | 84h | 84h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072696 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 0h | 84h | 84h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072697 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 0h | 48h | 48h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072698 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 0h | 48h | 48h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072699 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Support Mock1 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 0h | 16h | 16h | 2017-08-21 | 2017-08-25 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-09-25 | 2017-10-06 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -25 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072700 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 72h | 0h | 72h | 2017-08-28 | 2017-09-08 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 32 | 0 | 0
1072701 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-08-28 | 2017-09-15 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072702 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - LOG | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 200h | 0h | 200h | 2017-04-17 | 2017-05-19 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072703 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Data Definition Documents (DDD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | Yes |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Future Task | 2017-04-17 | 2017-05-05 | 1 | Revise DDDs - Division review | 1000 D1-1200 A-1213 Revise DDDs - Division review | 10 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072704 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2017-06-30 | 2017-08-31 | Yes |  |  | DELIV-FUN-220.Solution Design Document (SDD) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072705 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072706 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-04-03 | 2017-04-07 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -23 | -19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072707 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 60h | 0h | 60h | 2017-03-13 | 2017-03-31 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072708 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072709 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2017-04-03 | 2017-04-13 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072710 | No | Yes | No | SDF | SDF Localisation | 99-Global | Role Mapping (Design/Build) | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 83h | 0h | 83h | 2017-06-07 | 2017-07-07 | Yes |  |  | DELIV-CM-218.Role Mapping | Complete | 2017-05-29 | 2017-06-23 | 1 | Role Mapping | 1000 D1-1800 MultiPhases-1810 Role Mapping | 5 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 8 | 48 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072711 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Transition Plan Execution & Monitoring(Design/Build) | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-30 | 2017-06-30 | Yes |  |  | ACT-CM.Transition Plan Execution & Monitoring | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072712 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Change Impacts Analysis (Design/Build) | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 5h | 0h | 5h | 2017-06-05 | 2017-06-09 | Yes |  |  | DELIV-CM-014.Change Impacts Analysis | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072713 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Establish Key users Network(Design/Build) | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 26h | 0h | 26h | 2017-06-05 | 2017-07-14 | Yes |  |  | ACT-CM.Establish Key users Network | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072714 | No | Yes | No | SDF | SDF Localisation | 99-Global | Role Mapping (Test) | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | DELIV-CM-218.Role Mapping | Future Task | 2017-05-29 | 2017-06-23 | 1 | Role Mapping | 1000 D1-1800 MultiPhases-1810 Role Mapping | 35 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072715 | No | Yes | No | SDF | SDF Localisation | 04-Test | Transition Plan Execution & Monitoring (Test) | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-CM.Transition Plan Execution & Monitoring | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072716 | No | Yes | No | SDF | SDF Localisation | 04-Test | Establish Key users Network (Test) | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-CM.Establish Key users Network | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072717 | No | Yes | No | SDF | SDF Localisation | 99-Global | Process Role Catalog (Design/Build) | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 30h | 0h | 30h | 2017-05-29 | 2017-07-07 | Yes |  |  | DELIV-CM-008.Process Role Catalog | Complete | 2017-05-29 | 2017-06-23 | 1 | Role Mapping | 1000 D1-1800 MultiPhases-1810 Role Mapping | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072718 | No | Yes | No | SDF | SDF Localisation | 02-Analyze | Process Role Catalog | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 49h | 0h | 49h | 2017-05-08 | 2017-05-19 | Yes |  |  | DELIV-CM-008.Process Role Catalog | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072719 | No | Yes | No | SDF | SDF Localisation | 02-Analyze | Transition Plan Execution & Monitoring | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-19 | 2017-04-19 | Yes |  |  | ACT-CM.Management | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072720 | No | Yes | No | SDF | SDF Localisation | 02-Analyze | Change Impact Analysis | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 39h | 0h | 39h | 2017-04-17 | 2017-05-12 | Yes |  |  | DELIV-CM-014.Change Impacts Analysis | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 10 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072721 | No | Yes | No | SDF | SDF Localisation | 99-Global | Management (Design/Build) | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 72h | 0h | 72h | 2017-05-29 | 2017-07-27 | Yes |  |  | ACT-CM.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072722 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Leite; Alexandre | Saputo | Yes | CapEx | Localization | IT - Internal | 145h | 0h | 145h | 2017-08-07 | 2017-08-25 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | -15 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 48.5 | 46.5 | 0 | 0 | 0 | 0
1072723 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Customer hierarchy (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Leite; Alexandre | Saputo | Yes | CapEx | Global | IT - Internal | 0h | 110h | 110h | 2017-07-04 | 2017-09-05 | Yes |  |  | ACT-FUN.Configuration | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072724 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | SDF Build/Support (SEC) - Deploy1 | SEC | SEC | SI | Onshore | Vernon; Franck | Accenture | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2017-07-10 | 2017-07-14 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-05 | 2017-06-23 | 1 | Security Build | 1000 D1-1300 B-1335 Security Build | 20 | 86.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072725 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Novak; Steve | IBM | Yes | CapEx | Localization | IT - External | 0h | 396h | 396h | 2017-10-02 | 2017-12-01 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072726 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Novak; Steve | IBM | Yes | CapEx | Localization | IT - External | 0h | 44h | 44h | 2017-09-25 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072727 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Novak; Steve | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-09-11 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072728 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Novak; Steve | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-08-28 | 2017-09-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072729 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTM | PTM | FUN | SI | Onshore | Novak; Steve | IBM | Yes | CapEx | Localization | IT - External | 84h | 0h | 84h | 2017-04-17 | 2017-05-05 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072730 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - OTC | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-03-09 | 2017-03-10 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -30 | -30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072731 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - OTC (AN) | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 144h | 0h | 144h | 2017-04-17 | 2017-05-26 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 27 | 29 | 15 | 15 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072732 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Log Gaps - OTC | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 64h | 0h | 64h | 2017-04-17 | 2017-05-19 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -15 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 15 | 15 | 10 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072733 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-04-03 | 2017-04-07 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072734 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-04-03 | 2017-04-07 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | -5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072735 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-04-03 | 2017-04-07 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -25 | -13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072736 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2017-03-13 | 2017-03-16 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072737 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-04-03 | 2017-04-14 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -10 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072738 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) (Test) - OTC | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-07-24 | 2017-07-28 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072739 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - OTC-(Global) | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 228h | 0h | 228h | 2017-05-29 | 2017-08-25 | Yes |  |  | ACT-CM.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 20 | 14 | 19 | 19 | 19 | 0 | 22 | 19 | 24 | 20 | 14 | 25 | 0 | 0 | 0 | 0
1072740 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | MCP Mini config and masterdata for US and Canada | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-04-03 | 2017-04-06 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072741 | No | No | Yes | SDF | SDF Interim State Project | 99-Global | Management - SDF | PMO | PMO | SI | Onshore | Von Fintel; Dieter | IBM | Yes | CapEx | Localization | IT - External | 1,583h | 509h | 2,092h | 2016-10-03 | 2018-02-26 | Yes |  |  | ACT-PMO.Management | On Schedule | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 34 | 43 | 43 | 44 | 44 | 43 | 44 | 27 | 44 | 44 | 0 | 44 | 44 | 44 | 36 | 44 | 38 | 44 | 44 | 44 | 35 | 44 | 35 | 44 | 44 | 44 | 40 | 0 | 40 | 39 | 24 | 22 | 17 | 10 | 12 | 26 | 41 | 0
1072742 | No | No | Yes | SDF | SDF Interim State Project | 99-Global | Management | PMO | PMO | SI | Onshore | Von Fintel; Dieter | IBM | Yes | CapEx | Localization | IT - External | 35h | 0h | 35h | 2016-10-10 | 2016-10-14 | Yes |  |  | ACT-PMO.Management | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072743 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | IXXX-FSD-Interim State common components | PMO | PMO | SI | Onshore | Von Fintel; Dieter | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-04-24 | 2017-04-25 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -25 | -40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072744 | No | Yes | No | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - PTP - Ariba | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Global | IT - External | 83h | 0h | 83h | 2017-03-06 | 2017-04-07 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -30 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 35 | 0 | 20 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072745 | No | Yes | No | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTP ARIBA | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Global | IT - External | 68h | 0h | 68h | 2017-04-17 | 2017-06-30 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 20 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072746 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - PTP | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 128h | 0h | 128h | 2017-04-24 | 2017-06-09 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 10 | 15 | 13 | 10 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072747 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 30h | 0h | 30h | 2017-04-03 | 2017-04-07 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -20 | -16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072748 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-04-10 | 2017-04-10 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072749 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Gap log - PTP | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 69h | 0h | 69h | 2017-05-01 | 2017-06-02 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -22.88 | 70.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 15 | 10 | 10 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072750 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | RTM - PTP | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 70h | 0h | 70h | 2017-04-17 | 2017-05-26 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -29.88 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 10 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072751 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-03-23 | 2017-03-23 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -17 | -12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072752 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | Workshop-Purchasing & A/P | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 40h | 0h | 40h | 2017-03-20 | 2017-03-24 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072753 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTP) - Deploy1 | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 0h | 70h | 70h | 2017-09-05 | 2017-09-15 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072754 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (PTP) - Deploy1 | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-06-23 | 2017-06-23 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -5 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072755 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTP (Global) | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 0h | 20h | 20h | 2017-07-10 | 2017-09-01 | Yes |  |  | ACT-FUN.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072756 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTP) - Deploy1 | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 50h | 0h | 50h | 2017-08-07 | 2017-08-11 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0
1072757 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Run Tests - PTP | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072758 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTP | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-06-07 | 2017-06-07 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072759 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTP) - Deploy1 | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-07-18 | 2017-07-18 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072760 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTP) - Deploy1 | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Localization | Business | 102.5h | 47.5h | 150h | 2017-08-10 | 2017-09-11 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | 33 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 44.5 | 16 | 39 | 0 | 0 | 0
1072761 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTP | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-06-07 | 2017-06-07 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072762 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTP (Global) | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Localization | Business | 35h | 10h | 45h | 2017-08-10 | 2017-09-08 | Yes |  |  | ACT-FUN.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 22 | 4 | 0 | 0 | 0
1072763 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (PTP) - Deploy1 | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -5 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072764 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Support (PTP) - Deploy1 | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Localization | Business | 29h | 0h | 29h | 2017-07-10 | 2017-07-14 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -5 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072765 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTP) - Deploy1 | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Localization | Business | 8h | 0h | 8h | 2017-07-03 | 2017-07-06 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | -5 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072766 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTP) - Deploy1 | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Localization | Business | 0h | 35h | 35h | 2017-09-05 | 2017-09-08 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072767 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Gap log - PTP | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-05-19 | 2017-05-19 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -22.88 | 70.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072768 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTP) - Deploy2 | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Localization | Business | 0h | 60h | 60h | 2017-09-11 | 2017-09-21 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 20 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072769 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | RTM - PTP | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Localization | Business | 14h | 0h | 14h | 2017-05-08 | 2017-06-28 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -29.88 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072770 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - PTP | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Localization | Business | 10h | 0h | 10h | 2017-04-19 | 2017-04-21 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072771 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | Build DEV 2 | TAI | TAI | SI | Onshore | Chea; SaySanne | Accenture | Yes | CapEx | Localization | IT - External | 119h | 0h | 119h | 2016-10-24 | 2016-11-25 | Yes |  |  | DELIV-TAI-101.Development Environment | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072772 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - OTC | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-03-06 | 2017-03-17 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -30 | -30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072773 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-04 | 2017-12-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072774 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 43h | 0h | 43h | 2017-05-29 | 2017-07-07 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 15 | 4 | 7 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072775 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT - OTC- Deploy2 | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 29h | 30h | 59h | 2017-06-05 | 2017-07-28 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072776 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 9h | 8h | 17h | 2017-06-26 | 2017-07-14 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-21 | 2017-09-01 | 2 | AT | 20000 D2-20100 B-20180 AT | -45 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072777 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 63h | 0h | 63h | 2017-05-08 | 2017-07-14 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-05-19 | 2 | Base Config | 1000 D1-1300 B-1314 Base Config | -5 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 10 | 9 | 5 | 4 | 9 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072778 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (OTC) - Deploy1 | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072779 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (OTC) - Deploy1 | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 0h | 10h | 10h | 2017-07-17 | 2017-07-21 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072780 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-23 | 2017-06-23 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | -25 | 16.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072781 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 34h | 0h | 34h | 2017-06-05 | 2017-07-28 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | -15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 10 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072782 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-04-15 | 2017-04-17 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -10 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072783 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 22h | 0h | 22h | 2017-03-27 | 2017-04-17 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -25 | -13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072784 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 22h | 0h | 22h | 2017-03-20 | 2017-03-24 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072785 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 23h | 0h | 23h | 2017-03-27 | 2017-04-07 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | -5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072786 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 13h | 0h | 13h | 2017-03-13 | 2017-03-24 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072787 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Log Gaps - OTC | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 64h | 0h | 64h | 2017-04-10 | 2017-06-26 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -15 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 5 | 10 | 10 | 15 | 10 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072788 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | RTM - OTC | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 41h | 0h | 41h | 2017-04-10 | 2017-05-19 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -18 | 57.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 5 | 5 | 5 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072789 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - OTC | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 72h | 0h | 72h | 2017-04-17 | 2017-05-30 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 10 | 20 | 0 | 14 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072790 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | SDD-COTC0001-Pricing condition types | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 26h | 6h | 32h | 2017-05-29 | 2017-07-21 | Yes |  |  | WP-PMO-024.Project Logs | Future Task | 2017-05-08 | 2017-05-19 | 0 | NA Others | 99000-99100-99130 NA others | 15 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 10 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072791 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | Hypercare-Break/Fix - Deploy1 | SEC | SEC | SI | Landed Onshore | Manongsong; Melissa | Accenture | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-10-02 | 2017-10-13 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072792 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover - Support- SEC - Deploy 1 | SEC | SEC | SI | Landed Onshore | Manongsong; Melissa | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-09-18 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072793 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | Hypercare-Break/Fix - Deploy1 | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 0h | 100h | 100h | 2017-10-02 | 2017-11-03 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072794 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover - Support- SEC - Deploy 1 | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-09-18 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072795 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SEC-Build - SEC Deploy2 | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 9h | 20h | 29h | 2017-08-28 | 2017-09-08 | Yes |  |  |  | Future Task | 2017-07-24 | 2017-08-11 | 2 | Security Build | 20000 D2-20100 B-20230 Security Build | 20 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0
1072796 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SEC-FUT - SEC Deploy2 | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2017-09-01 | 2017-09-14 | Yes |  |  |  | Future Task | 2017-08-14 | 2017-09-01 | 2 | Security FUT | 20000 D2-20100 B-20240 Security FUT | 14 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072797 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT- Break/Fix- SEC - Deploy 1 | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 0h | 65h | 65h | 2017-08-30 | 2017-09-19 | Yes |  |  |  | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072798 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF Build/Support (SEC) - Deploy1 | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 89h | 0h | 89h | 2017-07-31 | 2017-09-03 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-05 | 2017-06-23 | 1 | Security Build | 1000 D1-1300 B-1335 Security Build | 20 | 86.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 36 | 8 | 0 | 0 | 0
1072799 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Composite Role Build (SEC) - Deploy1 | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 34h | 55h | 89h | 2017-07-10 | 2017-08-01 | Yes |  |  | DELIV-SEC-003.Security Role Design & Build | Future Task | 2017-06-05 | 2017-06-23 | 1 | Security Build | 1000 D1-1300 B-1335 Security Build | 25 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072800 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Derived Role Build (SEC) - Deploy1 | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 70h | 48h | 118h | 2017-07-10 | 2017-08-04 | Yes |  |  | DELIV-SEC-003.Security Role Design & Build | Future Task | 2017-06-05 | 2017-06-23 | 1 | Security Build | 1000 D1-1300 B-1335 Security Build | 25 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 16 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072801 | No | No | Yes | SDF | SDF Localisation | 04-Test | SEC Break/Fix SIT1 - SEC Deploy2 | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 0h | 75h | 75h | 2017-09-18 | 2017-10-06 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072802 | No | No | Yes | SDF | SDF Localisation | 04-Test | SEC Break/Fix SIT2 - SEC Deploy2 | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 0h | 75h | 75h | 2017-10-10 | 2017-10-27 | Yes |  |  |  | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072803 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test - Customer Master - SI - Deploy1 - DM | MDG | DM | SI | Offshore | Quinones; Franz | Accenture | Yes | OpEx | Localization | IT - External | 38.5h | 0h | 38.5h | 2017-07-24 | 2017-08-25 | Yes |  |  | ACT-FUN.Execute SIT | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | -13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 2 | 12.5 | 10 | 0 | 0 | 0 | 0
1072804 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test - Vendor Master - SI - Deploy1 - DM | MDG | DM | SI | Offshore | Quinones; Franz | Accenture | Yes | OpEx | Localization | IT - External | 30.5h | 0h | 30.5h | 2017-07-24 | 2017-08-25 | Yes |  |  | ACT-FUN.Execute SIT | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | -13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 7 | 2.5 | 10 | 5 | 0 | 0 | 0 | 0
1072805 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B - Customer Master - SI - Deploy1 - DM | MDG | DM | SI | Offshore | Quinones; Franz | Accenture | Yes | OpEx | Localization | IT - External | 7h | 0h | 7h | 2017-07-17 | 2017-07-28 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-06-09 | 1 | Build and adjust conversion programs | 1000 D1-1300 B-1322 Build and adjust conversion programs | 31 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072806 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B - Vendor Master - SI - Deploy1 - DM | MDG | DM | SI | Offshore | Quinones; Franz | Accenture | Yes | OpEx | Localization | IT - External | 12h | 0h | 12h | 2017-07-17 | 2017-07-26 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-06-09 | 1 | Build and adjust conversion programs | 1000 D1-1300 B-1322 Build and adjust conversion programs | 31 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072807 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B-Resolve Retrofit Issues with MM-FIN-SI - Deploy1 - DM | MDG | DM | SI | Offshore | Quinones; Franz | Accenture | Yes | CapEx | Localization | IT - External | 7.5h | 0h | 7.5h | 2017-08-21 | 2017-08-25 | Yes |  |  |  | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 0 | 0 | 0
1072808 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B-Resolve Retrofit Issues with MM-MM-SI - Deploy1 - DM | MDG | DM | SI | Offshore | Quinones; Franz | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-20 | 2017-07-20 | Yes |  |  |  | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072809 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B-Resolve Retrofit Issues with MM-VM-SI - Deploy1 - DM | MDG | DM | SI | Offshore | Quinones; Franz | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-11 | 2017-08-11 | Yes |  |  |  | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072810 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover Prepare - Deploy1 - SI - DM | MDG | DM | SI | Offshore | Quinones; Franz | Accenture | Yes | CapEx | Localization | IT - External | 32.5h | 0h | 32.5h | 2017-08-29 | 2017-09-08 | Yes |  |  |  | Complete | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -15 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 14.5 | 0 | 0
1072811 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | FUT - Deploy2 - SI - DM | MDG | DM | SI | Offshore | Quinones; Franz | Accenture | Yes | CapEx | Localization | IT - External | 30.5h | 0h | 30.5h | 2017-09-05 | 2017-09-15 | Yes |  |  |  | Complete | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 35 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 22.5 | 0
1072812 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | Hypercare-Provide end User Support - Deploy1 - SI - DM | MDG | DM | SI | Offshore | Quinones; Franz | Accenture | Yes | CapEx | Localization | IT - External | 0h | 360h | 360h | 2017-10-02 | 2017-12-01 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072813 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | Hypercare-Provide end User Support - Deploy2 - SI - DM | MDG | DM | SI | Offshore | Quinones; Franz | Accenture | Yes | CapEx | Localization | IT - External | 0h | 320h | 320h | 2018-02-05 | 2018-03-30 | Yes |  |  |  | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072814 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy2 (Accenture) - DC | MDG | DC | SI | Landed Onshore | Lloren; Jerry | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-07-24 | 2017-07-28 | Yes |  |  | ACT-MDG.Build ETL programs | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072815 | No | No | Yes | SDF | SDF Localisation | 99-Global | Deliver Training to UAT Testers (Test) | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 10h | 0h | 10h | 2017-06-26 | 2017-06-30 | Yes |  |  | ACT-CM.Deliver Training to UAT Testers | Complete | 2017-08-14 | 2017-09-01 | 1 | UAT Training | 1000 D1-1800 MultiPhases-1870 UAT Training | -35 | -30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072816 | No | No | Yes | SDF | SDF Localisation | 99-Global | Execute Train the Trainer (Test) | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 180h | 180h | 2017-07-31 | 2017-09-29 | Yes |  |  | ACT-CM.Execute Train the Trainer | Future Task | 2017-07-17 | 2017-07-28 | 1 | Train the trainer | 1000 D1-1800 MultiPhases-1840 Train the trainer | 10 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072817 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Curriculum (Design/Build) | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 10h | 0h | 10h | 2017-06-12 | 2017-06-16 | Yes |  |  | ACT-CM.Execute Train the Trainer | Complete | 2017-06-26 | 2017-07-28 | 1 | Training Schedule | 1000 D1-1800 MultiPhases-1820 Training Schedule | -15 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072818 | No | No | Yes | SDF | SDF Localisation | 99-Global | Onboard DTC | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 21h | 5h | 26h | 2017-04-07 | 2017-07-13 | Yes |  |  | ACT-CM.Management | Future Task | 2017-06-26 | 2017-07-28 | 1 | Training Schedule | 1000 D1-1800 MultiPhases-1820 Training Schedule | -65 | 9.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072819 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Courses-Create/Validate courses structure (Design/Build) | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 10h | 0h | 10h | 2017-06-12 | 2017-06-16 | Yes |  |  | DELIV-CM-402.Training Schedule and Logistics | Complete | 2017-06-26 | 2017-07-28 | 1 | Training Schedule | 1000 D1-1800 MultiPhases-1820 Training Schedule | -10 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072820 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Plans-Create/Update plans (Design/Build) | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | DELIV-CM-220.Training Plan | Future Task | 2017-06-26 | 2017-07-28 | 1 | Training Schedule | 1000 D1-1800 MultiPhases-1820 Training Schedule | -10 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072821 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | User Personlized Training Plan (Design/Build) | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 10h | 0h | 10h | 2017-06-12 | 2017-06-30 | Yes |  |  | DELIV-CM-220.Training Plan | Complete | 2017-06-26 | 2017-07-28 | 1 | Training Schedule | 1000 D1-1800 MultiPhases-1820 Training Schedule | -10 | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072822 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Schedule-Course Offerings (Design/Build) | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 80h | 80h | 2017-07-10 | 2017-08-04 | Yes |  |  | DELIV-CM-402.Training Schedule and Logistics | Future Task | 2017-06-26 | 2017-07-28 | 1 | Training Schedule | 1000 D1-1800 MultiPhases-1820 Training Schedule | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072823 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training ScheduleEnd-User Enrollments (Design/Build) | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 240h | 240h | 2017-07-10 | 2017-09-29 | Yes |  |  | DELIV-CM-402.Training Schedule and Logistics | Future Task | 2017-06-26 | 2017-07-28 | 1 | Training Schedule | 1000 D1-1800 MultiPhases-1820 Training Schedule | 10 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072824 | No | No | Yes | SDF | SDF Localisation | 99-Global | Technical training (Test) | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 25h | 25h | 2017-07-10 | 2017-07-28 | Yes |  |  | ACT-CM.Execute Train the Trainer | Future Task | 2017-07-17 | 2017-07-28 | 1 | Train the trainer | 1000 D1-1800 MultiPhases-1840 Train the trainer | -4.13 | 11.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072825 | No | No | Yes | SDF | SDF Localisation | 99-Global | Knowledge transfer (Test) | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 14.73h | 14.73h | 2017-07-10 | 2017-07-27 | Yes |  |  | ACT-CM.Execute Train the Trainer | Future Task | 2017-07-17 | 2017-07-28 | 1 | Train the trainer | 1000 D1-1800 MultiPhases-1840 Train the trainer | -15 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072826 | No | No | Yes | SDF | SDF Localisation | 99-Global | Execute Train the Trainer - Deploy1 | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 152h | 152h | 2017-08-28 | 2017-09-22 | Yes |  |  | ACT-CM.Execute Train the Trainer | Future Task | 2017-07-17 | 2017-07-28 | 1 | Train the trainer | 1000 D1-1800 MultiPhases-1840 Train the trainer | 30 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072827 | No | No | Yes | SDF | SDF Localisation | 99-Global | Deliver Training to End Users | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 20h | 20h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-CM.Deliver Training to End Users | Future Task | 2017-07-31 | 2017-09-22 | 1 | End User Training | 1000 D1-1800 MultiPhases-1850 End User Training | 45 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072828 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Landed Onshore | Iyer; Jagdeesh | IBM | Yes | CapEx | Localization | IT - External | 57h | 0h | 57h | 2017-08-07 | 2017-08-18 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 29 | 0 | 0 | 0 | 0 | 0
1072829 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Landed Onshore | Iyer; Jagdeesh | IBM | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-07-31 | 2017-08-04 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072830 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy1 (Design/Build) | DEV | DEV | SI | Landed Onshore | Iyer; Jagdeesh | IBM | Yes | CapEx | Localization | IT - External | 115h | 0h | 115h | 2017-06-28 | 2017-07-27 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 22 | 11 | 44 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072831 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | SI | Landed Onshore | Iyer; Jagdeesh | IBM | Yes | CapEx | Localization | IT - External | 117h | 114h | 231h | 2017-06-21 | 2017-10-06 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 26 | 11 | 0 | 8 | 4 | 16 | 15 | 0 | 0 | 0 | 28 | 0
1072832 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | SI | Landed Onshore | Iyer; Jagdeesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-08-28 | 2017-09-29 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072833 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Landed Onshore | Iyer; Jagdeesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 95h | 95h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072834 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Landed Onshore | Iyer; Jagdeesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 115h | 115h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072835 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | SI | Landed Onshore | Iyer; Jagdeesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 110h | 110h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072836 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing WRICEFs (Design/Build) | DEV | DEV | SI | Landed Onshore | Iyer; Jagdeesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-24 | 2017-02-24 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -88 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072837 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | SI | Landed Onshore | Iyer; Jagdeesh | IBM | Yes | CapEx | Localization | IT - External | 61h | 93h | 154h | 2017-02-13 | 2017-10-05 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 8 | 6 | 9 | 0 | 2 | 6 | 3 | 4 | 5 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0
1072838 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072839 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 configuration (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-08-08 | 2017-08-11 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | 25 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0
1072840 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072841 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-04-10 | 2017-04-14 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072842 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072843 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | PDDs | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-16 | 2017-06-16 | Yes |  |  | DELIV-FUN-110.PDDs | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072844 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072845 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072846 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Support (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072847 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | RTM - LOG | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 55h | 0h | 55h | 2017-04-17 | 2017-05-12 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 9 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072848 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 0h | 35h | 35h | 2017-08-07 | 2017-08-25 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 4.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072849 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-07-17 | 2017-07-21 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 20 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072850 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 44h | 1h | 45h | 2017-07-24 | 2017-08-07 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 5 | 33.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072851 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-08-28 | 2017-08-31 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 5 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0
1072852 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Delete-Functional Specification (FSD) - LOG | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072853 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 0h | 45h | 45h | 2017-08-14 | 2017-09-01 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072854 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072855 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Support (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072856 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Support Mock1 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 0h | 39h | 39h | 2017-08-21 | 2017-09-01 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-09-25 | 2017-10-06 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -25 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072857 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 0h | 72h | 72h | 2017-10-09 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072858 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 0h | 15h | 15h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072859 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 0h | 72h | 72h | 2017-10-09 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072860 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072861 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-08-21 | 2017-08-25 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | -8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0
1072862 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 configuration (LOG) - Deploy2 | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-08-14 | 2017-08-18 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0
1072863 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - LOG | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-04-17 | 2017-04-17 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072864 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 33h | 0h | 33h | 2017-05-19 | 2017-06-09 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072865 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 66h | 0h | 66h | 2017-06-16 | 2017-07-07 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 11 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072866 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2017-07-10 | 2017-08-04 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-19 | 2017-06-30 | 1 | Cycle 2 Config | 1000 D1-1300 B-1318 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072867 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-16 | 2017-06-16 | Yes |  |  | DELIV-FUN-220.Solution Design Document (SDD) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072868 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Gap log - LOG | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-04-17 | 2017-05-05 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072869 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Data Definition Documents (DDD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | Yes |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Future Task | 2017-04-17 | 2017-05-05 | 1 | Revise DDDs - Division review | 1000 D1-1200 A-1213 Revise DDDs - Division review | 10 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072870 | No | No | Yes | SDF | SDF Localisation | 04-Test | Manage SIT1 (Test) - Deploy2 | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Localization | IT - External | 0h | 264h | 264h | 2017-09-11 | 2017-10-20 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-11-24 | 2 | TBD | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | -5 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072871 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Scenarios/Scripts (Test) - Deploy2 | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Localization | IT - External | 0h | 44h | 44h | 2017-09-05 | 2017-09-11 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-11-24 | 2 | SIT 1 & 2 Prep | 20000 D2-21000 T-21036 SIT 1 & 2 Prep | -9 | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072872 | No | No | Yes | SDF | SDF Localisation | 04-Test | Regression Test Scenarios/Scripts (Test) - Deploy2 | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Localization | IT - External | 0h | 176h | 176h | 2017-10-17 | 2017-11-13 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-11-24 | 2 | QE2 Regression | 20000 D2-21000 T-21052 Regression Prep | -9 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072873 | No | No | Yes | SDF | SDF Localisation | 04-Test | Manage Regression (Test) - Deploy2 | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Localization | IT - External | 0h | 66h | 66h | 2017-11-27 | 2017-12-15 | Yes |  |  | ACT-Test.Management | Future Task | 2017-11-06 | 2017-11-24 | 2 | Q? Regression | 20000 D2-21000 T-21054 D2 Regression (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072874 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Scenarios/Scripts (Test) - Deploy1 | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Global | IT - External | 88h | 0h | 88h | 2017-07-03 | 2017-07-14 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Complete | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | -5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072875 | No | No | Yes | SDF | SDF Localisation | 04-Test | Manage SIT (Test) - Deploy1 | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Localization | IT - External | 264h | 0h | 264h | 2017-07-17 | 2017-08-25 | Yes |  |  | ACT-Test.Management | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 44 | 44 | 44 | 0 | 0 | 0 | 0
1072876 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Manage UAT (Test) - Deploy1 | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2017-08-28 | 2017-09-08 | Yes |  |  | ACT-Test.Management | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 0 | 0
1072877 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Demo (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 9h | 9h | 2017-06-30 | 2017-07-21 | Yes |  |  | ACT-FUN.Solution Confirmation Prensentations and Demonstrations | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072878 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 6h | 6h | 2017-05-15 | 2017-07-21 | Yes |  |  | ACT-FUN.Management | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072879 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-08-28 | 2017-09-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072880 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-06-05 | 2017-07-14 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 10 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072881 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-10-02 | 2017-12-15 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072882 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-09-11 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072883 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-08-07 | 2017-08-25 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072884 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-07-17 | 2017-08-04 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072885 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 44h | 44h | 2017-09-25 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072886 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-25 | 2017-09-25 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072887 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 14h | 46h | 60h | 2017-08-28 | 2017-09-11 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 17.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0
1072888 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-07-21 | 2017-08-11 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072889 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 0h | 15h | 15h | 2017-12-04 | 2017-12-22 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -30 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072890 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 0h | 12h | 12h | 2017-12-04 | 2017-12-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072891 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Support-D1 | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 0h | 16h | 16h | 2017-09-11 | 2017-09-29 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 75 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072892 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-12-04 | 2017-12-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072893 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 0h | 9h | 9h | 2017-10-09 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072894 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 0h | 16h | 16h | 2017-09-25 | 2017-10-20 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072895 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 0h | 10h | 10h | 2017-09-25 | 2017-10-20 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072896 | No | No | Yes | SDF | SDF Localisation | 04-Test | DR - Support (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 0h | 16h | 16h | 2017-11-06 | 2017-11-17 | Yes |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -5 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072897 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Support (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 0h | 9h | 9h | 2017-10-09 | 2017-10-27 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072898 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | Workshop-Purchasing & A/P | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 7h | 0h | 7h | 2017-03-27 | 2017-03-30 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072899 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-10-02 | 2017-11-17 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072900 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 0h | 190h | 190h | 2017-10-02 | 2017-11-17 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072901 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 15h | 14h | 29h | 2017-08-28 | 2017-09-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0
1072902 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 0h | 15h | 15h | 2017-09-11 | 2017-09-25 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072903 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Enhancement (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 0h | 5h | 5h | 2017-09-05 | 2017-09-29 | Yes |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072904 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 0h | 4h | 4h | 2017-09-25 | 2017-09-29 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072905 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 0h | 5h | 5h | 2017-09-25 | 2017-09-29 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072906 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2017-08-08 | 2017-08-25 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 13.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 7 | 15 | 0 | 0 | 0 | 0
1072907 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 19h | 0h | 19h | 2017-07-17 | 2017-07-28 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 15 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072908 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-07-24 | 2017-08-04 | Yes |  |  | ACT-FUN.Functional Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072909 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 12h | 3h | 15h | 2017-07-24 | 2017-08-25 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 4 | 2 | 0.5 | 3 | 0 | 0 | 0 | 0
1072910 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 0h | 10h | 10h | 2017-09-08 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072911 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 configuration (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 25h | 5h | 30h | 2017-08-14 | 2017-09-29 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | 35 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 10 | 11 | 0 | 0 | 0
1072912 | No | No | Yes | SDF | SDF Localisation | 04-Test | DR - Support (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 13h | 0h | 13h | 2017-07-31 | 2017-08-14 | Yes |  |  | ACT-FUN.Dry Run activities | Complete | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 7.5 | 0.5 | 0 | 0 | 0 | 0 | 0
1072913 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 7h | 75h | 82h | 2017-08-29 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0
1072914 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDD Writing - RTR - Deploy1 | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-06-19 | 2017-06-23 | Yes |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072915 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 7.5h | 0h | 7.5h | 2017-06-20 | 2017-07-07 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 1 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072916 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Interface (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 24h | 5.5h | 29.5h | 2017-06-07 | 2017-07-31 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 7 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.5 | 10 | 0 | 0 | 1 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072917 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | SDF-INT-Construct RTM | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2017-04-03 | 2017-04-05 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072918 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | RTM - RTR | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-04-27 | 2017-05-19 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072919 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - RTR | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 186.5h | 0h | 186.5h | 2017-04-27 | 2017-06-23 | Yes |  |  | ACT-FUN.Management | Future Task | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 18 | 15 | 32 | 16 | 21.5 | 30 | 30 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072920 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - RTR | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-19 | 2017-05-19 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -9.88 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072921 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Log Gaps - RTR | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 32.2h | 0h | 32.2h | 2017-04-27 | 2017-06-05 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -2 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 11 | 5 | 3.2 | 4.5 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072922 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - RTR | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 30h | 0h | 30h | 2017-02-27 | 2017-03-31 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -35 | -16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 4 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072923 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | SDF-INT-Workshop-Finance | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-03-01 | 2017-03-29 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072924 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | IXXX-DEV FUT-A/P interface | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 0h | 2.28h | 2.28h | 2017-07-03 | 2017-07-18 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | 21 | 14.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072925 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 29h | 15h | 44h | 2017-05-23 | 2017-07-18 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | -14 | 72.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 13 | 0 | 0 | 0 | 0 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072926 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - RTR | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 61.5h | 0h | 61.5h | 2017-06-12 | 2017-07-20 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.5 | 0 | 20 | 9 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072927 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - RTR (Global) | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 104h | 465h | 569h | 2017-07-24 | 2018-02-09 | Yes |  |  | ACT-FUN.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 19 | 14 | 20 | 10 | 16 | 0 | 0 | 0
1072928 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - RTR | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072929 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Configuration - RTR - Deploy1 | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 43.5h | 0h | 43.5h | 2017-06-05 | 2017-06-30 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | -5 | 43.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 9.5 | 15 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072930 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 41h | 0h | 41h | 2017-03-13 | 2017-03-30 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072931 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 11h | 0h | 11h | 2017-03-13 | 2017-03-31 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -35 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072932 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 4.3h | 0h | 4.3h | 2017-03-13 | 2017-03-17 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | -15 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072933 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 5.5h | 0h | 5.5h | 2017-03-13 | 2017-03-20 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072934 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072935 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - OTC-(Global) | OTC | FUN | SI | Onshore | Kane; Jeremy | IBM | Yes | CapEx | Localization | IT - External | 0h | 1,320h | 1,320h | 2017-07-04 | 2018-03-30 | Yes |  |  | ACT-CM.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072936 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - PTP | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 124h | 0h | 124h | 2017-04-17 | 2017-06-12 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 47 | 0 | 14 | 0 | 0 | 0 | 9 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072937 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | RTM - PTP | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 52h | 0h | 52h | 2017-04-26 | 2017-06-21 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -29.88 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 9 | 0 | 0 | 0 | 10 | 9 | 11 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072938 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Gap log - PTP | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 43h | 0h | 43h | 2017-04-25 | 2017-05-24 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -22.88 | 70.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 18 | 0 | 11 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072939 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 60h | 0h | 60h | 2017-05-23 | 2017-06-30 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 11 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 11 | 9 | 0 | 10 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072940 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | Workshop-Purchasing & A/P | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-03-22 | 2017-04-05 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072941 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 17h | 0h | 17h | 2017-03-27 | 2017-03-30 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -17 | -12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072942 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-04-07 | 2017-04-07 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -20 | -16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072943 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | -9.88 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072944 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 17h | 0h | 17h | 2017-04-13 | 2017-04-14 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072945 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 63h | 0h | 63h | 2017-06-26 | 2017-08-11 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | -5 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 3 | 10 | 33 | 0 | 0 | 0 | 0 | 0 | 0
1072946 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Interface (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 50h | 0h | 50h | 2017-06-19 | 2017-08-14 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 15 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 23 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0
1072947 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2017-06-29 | 2017-07-07 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 20 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072948 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 83h | 7h | 90h | 2017-08-14 | 2017-09-12 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 24 | 0 | 0 | 8 | 0
1072949 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 19h | 11h | 30h | 2017-08-08 | 2017-09-06 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 4 | 5 | 8 | 0 | 0
1072950 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 35h | 25h | 60h | 2017-07-17 | 2017-08-02 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072951 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 24h | 11.6h | 35.6h | 2017-07-20 | 2017-08-23 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 8 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
1072952 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTP) - Deploy2 | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-09-18 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072953 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTP) - Deploy2 | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-10-09 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072954 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTP) - Deploy2 | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072955 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTP) - Deploy2 | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2017-10-09 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072956 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-09-25 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072957 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 8h | 22h | 30h | 2017-09-15 | 2017-10-02 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0
1072958 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-08-31 | 2017-09-14 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 40 | 32 | 0
1072959 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare PP Workshops (complex Gaps) | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 13h | 0h | 13h | 2017-03-14 | 2017-03-21 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -25 | -22.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072960 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare for Kickoff - PTP | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-03-01 | 2017-03-10 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -33 | -35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072961 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | Workshop-Batch handling | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 96.5h | 0h | 96.5h | 2017-02-20 | 2017-03-30 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.5 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072962 | No | No | Yes | SDF | SDF Interim State Project | 01-Preparation | Environment setup | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 22h | 0h | 22h | 2017-01-09 | 2017-02-06 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072963 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072964 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072965 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-07-19 | 2017-08-07 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072966 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 40h | 20h | 60h | 2017-08-21 | 2017-09-06 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 17.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0
1072967 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 50h | 0h | 50h | 2017-07-20 | 2017-08-04 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | 5 | 29.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072968 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2017-08-28 | 2017-09-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072969 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 0h | 125h | 125h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072970 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-09-05 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072971 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 59h | 0h | 59h | 2017-06-19 | 2017-06-30 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072972 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 108h | 0h | 108h | 2017-07-17 | 2017-07-31 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072973 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-08-07 | 2017-08-18 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 40 | 0 | 0 | 0 | 0 | 0
1072974 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-05 | 2017-09-15 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 15 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072975 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2017-03-27 | 2017-04-03 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -20 | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072976 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - PTM | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 37h | 0h | 37h | 2017-04-17 | 2017-05-25 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 13 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072977 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Log Gaps - PTM | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-04-17 | 2017-07-06 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072978 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | DDD | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2017-05-08 | 2017-05-12 | Yes |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Complete | 2017-04-17 | 2017-05-05 | 1 | Revise DDDs - Division review | 1000 D1-1200 A-1213 Revise DDDs - Division review | 15 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072979 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 53h | 0h | 53h | 2017-06-02 | 2017-06-13 | Yes |  |  | ACT-FUN.Management | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 26 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072980 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - PTM | PTM | FUN | SI | Offshore | Samant; Rupa | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072981 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Log Gaps - PTM | PTM | FUN | SI | Offshore | Samant; Rupa | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -10 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072982 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | DDD | PTM | FUN | SI | Offshore | Samant; Rupa | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-05-29 | 2017-06-01 | Yes |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Complete | 2017-04-17 | 2017-05-05 | 1 | Revise DDDs - Division review | 1000 D1-1200 A-1213 Revise DDDs - Division review | 15 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072983 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Samant; Rupa | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT-FUN.Management | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072984 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Samant; Rupa | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-09-05 | 2017-09-15 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 15 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072985 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Samant; Rupa | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2017-08-28 | 2017-09-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072986 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Samant; Rupa | IBM | Yes | CapEx | Localization | IT - External | 76h | 14h | 90h | 2017-08-07 | 2017-08-28 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 18 | 28 | 0 | 0 | 0 | 0
1072987 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Samant; Rupa | IBM | Yes | CapEx | Localization | IT - External | 91h | 0h | 91h | 2017-07-18 | 2017-08-04 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 35 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072988 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Samant; Rupa | IBM | Yes | CapEx | Localization | IT - External | 0h | 65h | 65h | 2017-09-05 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072989 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Samant; Rupa | IBM | Yes | CapEx | Localization | IT - External | 0h | 125h | 125h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072990 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Samant; Rupa | IBM | Yes | CapEx | Localization | IT - External | 20h | 40h | 60h | 2017-08-16 | 2017-08-28 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 17.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 8 | 0 | 0 | 0 | 0
1072991 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Samant; Rupa | IBM | Yes | CapEx | Localization | IT - External | 56h | 4h | 60h | 2017-07-18 | 2017-08-14 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 10 | 10 | 20 | 0 | 0 | 0 | 0 | 0 | 0
1072992 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Samant; Rupa | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072993 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Samant; Rupa | IBM | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072994 | No | No | Yes | SDF | SDF Interim State Project | 01-Preparation | Environment setup | PTM | FUN | SI | Offshore | Samant; Rupa | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-01-09 | 2017-02-03 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072995 | No | No | Yes | SDF | SDF Interim State Project | 01-Preparation | Environment setup | OTC | FUN | SI | Offshore | Pradhan; Gyan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072996 | No | Yes | No | SDF | SDF Interim State Project | 01-Preparation | Environment setup | RTR | FUN | SI | Offshore | Deshpande; Anuprita | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072997 | No | Yes | No | SDF | SDF Localisation | 02-Analyze | Data Definition Documents (DDD) (LOG) - Deploy1 | LOG | FUN | SI | Onshore | Mahoney; Stephen | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | Yes |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Future Task | 2017-04-17 | 2017-05-05 | 1 | Revise DDDs - Division review | 1000 D1-1200 A-1213 Revise DDDs - Division review | 10 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072998 | No | Yes | No | SDF | SDF Localisation | 02-Analyze | Kickoff - LOG | LOG | FUN | SI | Onshore | Mahoney; Stephen | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072999 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | DM TAI SDF Dev Installation and Configuration - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 99h | 0h | 99h | 2017-03-13 | 2017-05-05 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-01 | 2017-05-05 | 1 | Data Construction | 1000 D1-1200 A-1214 Data Construction | -35 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 18 | 18 | 27 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073000 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | DM TAI SDF Prod Installation and Configuration - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 18h | 0h | 18h | 2017-04-05 | 2017-04-07 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-01 | 2017-05-05 | 1 | Data Construction | 1000 D1-1200 A-1214 Data Construction | -18 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073001 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | DM RDS Installation and Configuration - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 171h | 0h | 171h | 2017-03-27 | 2017-05-19 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-01 | 2017-05-05 | 1 | Data Construction | 1000 D1-1200 A-1214 Data Construction | -25 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 9 | 18 | 0 | 0 | 36 | 36 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073002 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 45h | 0h | 45h | 2017-05-22 | 2017-05-26 | Yes |  |  | ACT-MDG.MDG - Workshop | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073003 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) - Deploy1 - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 12h | 0h | 12h | 2017-06-05 | 2017-06-05 | Yes |  |  | DELIV-MDG-206.Functional Specification -Conversion | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | -20 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073004 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Prepare Mock1 - Deploy1 - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 48h | 0h | 48h | 2017-06-06 | 2017-06-09 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073005 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy1 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 62h | 0h | 62h | 2017-06-12 | 2017-06-19 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073006 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy1 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 53h | 0h | 53h | 2017-06-21 | 2017-06-26 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073007 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy1 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 78h | 0h | 78h | 2017-06-26 | 2017-07-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 30 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073008 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy1 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 33h | 0h | 33h | 2017-07-17 | 2017-07-28 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073009 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 102h | 0h | 102h | 2017-07-10 | 2017-07-23 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073010 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy1 - HC - (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 100h | 100h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073011 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy2 - HC - (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 160h | 160h | 2018-02-05 | 2018-03-02 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | -18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073012 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073013 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073014 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073015 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 73h | 73h | 2017-11-13 | 2018-01-02 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073016 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 72h | 72h | 2017-11-13 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073017 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073018 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 70h | 70h | 2017-11-13 | 2018-01-02 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073019 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Manage Defect - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 35h | 35h | 2017-09-18 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 0.13 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073020 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 70h | 70h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 5 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073021 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy2 (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 30h | 0h | 30h | 2017-07-24 | 2017-07-28 | Yes |  |  | ACT-MDG.Build ETL programs | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073022 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 86h | 0h | 86h | 2017-08-07 | 2017-08-28 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 56 | 0 | 0 | 0 | 0
1073023 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 42h | 10h | 52h | 2017-08-07 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 33.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 32 | 0 | 0 | 0 | 0 | 0
1073024 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 15h | 15h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073025 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 15h | 15h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073026 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 15h | 15h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073027 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 15h | 15h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073028 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy1 - CG - (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 50h | 10h | 60h | 2017-07-31 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 22.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073029 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Validation - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 35h | 35h | 2017-09-18 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073030 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Execute - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 35h | 35h | 2017-09-18 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 0.13 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073031 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Preparation - Deploy2 - D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 35h | 35h | 2017-09-18 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073032 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 10h | 10h | 2017-09-01 | 2017-09-15 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-07-31 | 2017-08-11 | 2 | QE2 Mock Prep | 20000 D2-20100 B-20110 QE2 Mock Prep | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073033 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 46h | 0h | 46h | 2017-08-07 | 2017-08-17 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 26 | 0 | 0 | 0 | 0 | 0
1073034 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 10h | 10h | 2017-09-01 | 2017-09-15 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073035 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy2- D&B (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 10h | 10h | 2017-09-01 | 2017-09-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073036 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) - Deploy2 (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 10h | 10h | 2017-07-31 | 2017-09-15 | Yes |  |  | DELIV-MDG-206.Functional Specification -Conversion | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 45 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073037 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Mapping Document - Deploy2 (Saputo) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 68h | 0h | 68h | 2017-07-31 | 2017-09-04 | Yes |  |  | DELIV-MDG-207.Functional Mapping Document | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | 0 | 0
1073038 | No | No | Yes | SDF | SDF Localisation | 99-Global | Team Lead - MDG - DC | MDG | DC | SI | Landed Onshore | Aying; Mae | Accenture | Yes | CapEx | Localization | IT - External | 332h | 1,112h | 1,444h | 2017-07-10 | 2018-03-08 | Yes |  |  | DELIV-FUN-029.Site Assessment | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 44 | 40 | 40 | 54 | 46 | 40 | 24 | 0 | 0
1073039 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy2 (Accenture) - DC | MDG | DC | SI | Landed Onshore | Aying; Mae | Accenture | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2017-07-04 | 2017-07-07 | Yes |  |  | ACT-MDG.Build ETL programs | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073040 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Data Migration development - Deploy1 - DC | MDG | DC | SI | Landed Onshore | Aying; Mae | Accenture | Yes | CapEx | Localization | IT - External | 64h | 0h | 64h | 2017-06-05 | 2017-06-21 | Yes |  |  | ACT-MDG.Data Construction | Complete | 2017-05-08 | 2017-06-09 | 1 | Data Construction | 1000 D1-1300 B-1320 Data Construction | 15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 48 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073041 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Landed Onshore | Aying; Mae | Accenture | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-06-26 | 2017-06-30 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 15 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073042 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Data Conversion Plan - Deploy1 - DC | MDG | DC | SI | Landed Onshore | Aying; Mae | Accenture | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-06-12 | 2017-06-18 | Yes |  |  | DELIV-MDG-201.Data Conversion Plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073043 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy1 - DC | MDG | DC | SI | Landed Onshore | Aying; Mae | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | Yes |  |  | ACT-MDG.Build ETL programs | Complete | 2017-05-08 | 2017-06-09 | 1 | Build and adjust conversion programs | 1000 D1-1300 B-1322 Build and adjust conversion programs | 15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073044 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Landed Onshore | Aying; Mae | Accenture | Yes | CapEx | Localization | IT - External | 26h | 0h | 26h | 2017-06-22 | 2017-07-07 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 30 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073045 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy2 (Accenture) - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 153h | 0h | 153h | 2017-07-03 | 2017-07-27 | Yes |  |  | ACT-MDG.Build ETL programs | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 36 | 45 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073046 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-08 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-07-31 | 2017-08-11 | 2 | QE2 Mock Prep | 20000 D2-20100 B-20110 QE2 Mock Prep | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073047 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 224h | 0h | 224h | 2017-07-31 | 2017-09-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 59 | 30 | 0 | 0 | 45 | 0
1073048 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-08 | 2017-09-15 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073049 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-08-28 | 2017-09-01 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0
1073050 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 22.5h | 0h | 22.5h | 2017-08-14 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 14.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 0 | 0
1073051 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 22.5h | 50.5h | 73h | 2017-09-04 | 2017-10-11 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 0 | 0
1073052 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 0h | 65h | 65h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073053 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 0h | 100h | 100h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073054 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-10-30 | 2017-12-07 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 0 | 18.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073055 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 0h | 65h | 65h | 2017-10-30 | 2017-12-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073056 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -4.88 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073057 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -50 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073058 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073059 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073060 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073061 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy2 - HC - (Accenture) - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2018-02-05 | 2018-03-02 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | -17.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073062 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-22 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073063 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy1 - HC - (Accenture) - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -21.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073064 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 6h | 30h | 36h | 2017-09-12 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0
1073065 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 84h | 0h | 84h | 2017-08-15 | 2017-08-25 | Yes |  |  | ACT-MDG.Mock Load | Complete | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 10.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 39 | 0 | 0 | 0 | 0
1073066 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 82h | 0h | 82h | 2017-07-31 | 2017-08-11 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 37 | 0 | 0 | 0 | 0 | 0 | 0
1073067 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 23h | 20h | 43h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0
1073068 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073069 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 16h | 20h | 36h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0
1073070 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 110h | 0h | 110h | 2017-08-07 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 15 | 15 | 27 | 45 | 0 | 0
1073071 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-10-30 | 2017-12-07 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 0 | 18.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073072 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -50 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073073 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -4.88 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073074 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-10-30 | 2017-12-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073075 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-22 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073076 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073077 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073078 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073079 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 85.5h | 0h | 85.5h | 2017-06-19 | 2017-07-14 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 33.5 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073080 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-06-28 | 2017-07-02 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 30 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073081 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy1 - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 59h | 0h | 59h | 2017-06-12 | 2017-06-18 | Yes |  |  | ACT-MDG.Build ETL programs | Complete | 2017-05-08 | 2017-06-09 | 1 | Build and adjust conversion programs | 1000 D1-1300 B-1322 Build and adjust conversion programs | 15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073082 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 47h | 0h | 47h | 2017-07-21 | 2017-07-30 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073083 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Data Migration development - Deploy1 - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 64h | 0h | 64h | 2017-06-05 | 2017-06-25 | Yes |  |  | ACT-MDG.Data Construction | Complete | 2017-05-08 | 2017-06-09 | 1 | Data Construction | 1000 D1-1300 B-1320 Data Construction | 15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073084 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 99h | 0h | 99h | 2017-06-15 | 2017-07-21 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 46 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073085 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Mock Load - Deploy1 - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073086 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Mock1 Validation - Deploy1 - CG- DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-05 | 2017-07-05 | Yes |  |  | ACT-MDG.Mock Validation | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073087 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Mock1 Preparation - Deploy1 - CG - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-04 | 2017-07-04 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073088 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) - Deploy1 - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 223h | 0h | 223h | 2017-05-01 | 2017-06-02 | Yes |  |  | DELIV-MDG-206.Functional Specification -Conversion | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | -20 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 45 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073089 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-06-13 | 2017-06-22 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 15 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073090 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Data Validation Sheets - Deploy1 - Test - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-07 | 2017-07-07 | Yes |  |  | WP-MDG.Data Validation Sheets | Complete | 2017-06-05 | 2017-06-16 | 1 | QE2 Prevalidation | 1000 D1-1300 B-1325 QE2 Prevalidation | -1 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073091 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | DEV FUT-ID-COM-Baseline | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 0h | 120h | 120h | 2017-02-13 | 2017-09-29 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073092 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (OTC) - Deploy1 | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 113h | 41h | 154h | 2017-07-17 | 2017-09-12 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 14 | 33 | 33 | 0 | 25 | 0 | 0 | 0
1073093 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC034-FSD-Pricing Page Program | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 257.55h | 0h | 257.55h | 2017-02-06 | 2017-05-19 | Yes |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -80 | -30 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 24 | 20 | 25 | 27 | 24 | 34 | 5 | 15 | 0 | 5 | 0 | 10 | 10.55 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073094 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | IOTC004-FSD-Master data interface From SAP to MRA | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2017-01-23 | 2017-02-24 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -90 | -90 | 0 | 0 | 0 | 0 | 40 | 0 | 12 | 16 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073095 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | IOTC003-DEV FUT-COM-Pricing Interface From SAP to MRA | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 56.68h | 0h | 56.68h | 2017-03-20 | 2017-04-21 | Yes |  |  | ACT-FUN.Execute FUT | Complete | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | -45 | -54.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 25 | 10 | 10.68 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073096 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | IOTC004-DEV FUT-Master data interfaceFrom SAP to MRA | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 78.32h | 0h | 78.32h | 2017-04-03 | 2017-04-28 | Yes |  |  | ACT-FUN.Execute FUT | Complete | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | -35 | -50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 13.32 | 15 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073097 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC034-DEV FUT-Pricing Page Program | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 73h | 0h | 73h | 2017-03-27 | 2017-07-25 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | -40 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 4 | 5 | 0 | 5 | 5 | 5 | 3 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073098 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | IOTC003-FSD-Pricing Interface From SAP to MRA | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 85h | 0h | 85h | 2017-01-16 | 2017-03-03 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -95 | -85 | 0 | 0 | 0 | 40 | 0 | 40 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073099 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (OTC) - Deploy1 | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2017-07-31 | 2017-08-25 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 7 | 7 | 40 | 0 | 0 | 0 | 0
1073100 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Test preparation | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 153.4h | 0h | 153.4h | 2017-06-05 | 2017-07-25 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 0 | NA Others | 99000-99100-99130 NA others | -15 | 6.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 30 | 38.4 | 40 | 0 | 24 | 5 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073101 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC3513-DEV FUT-Pricing Cockpit | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 14.35h | 0h | 14.35h | 2017-05-01 | 2017-05-26 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | -15 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 4.35 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073102 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Config-COTC0001-Pricing condition types | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-05-01 | 2017-06-07 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-05-19 | 0 | NA Others | 99000-99100-99130 NA others | -5 | 13.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073103 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | SDD-COTC0001-Pricing condition types | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 1.6h | 15.2h | 16.8h | 2017-06-19 | 2017-07-28 | Yes |  |  | WP-PMO-024.Project Logs | Future Task | 2017-05-08 | 2017-05-19 | 0 | NA Others | 99000-99100-99130 NA others | 15 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073104 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 01-Preparation | Commodity Pricing - MRA - Prepare kick Off | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 325h | 0h | 325h | 2016-10-17 | 2017-01-13 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 24 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073105 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 01-Preparation | Commodity Pricing - MRA - RTM | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 93h | 0h | 93h | 2016-11-08 | 2016-12-14 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073106 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC033-FSD-Pricing Cockpit | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-02-27 | 2017-03-13 | Yes |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -65 | -71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073107 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC032-FSD-Pricing Files | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-02-06 | 2017-03-13 | Yes |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -80 | -79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073108 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | IOTC005-FSD-Pricing Notification EDI | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 43.8h | 0h | 43.8h | 2017-03-14 | 2017-06-08 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -54 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 12.8 | 2 | 2 | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073109 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | FOTC005-FSD-Level 0 Notification Form | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-03-13 | 2017-03-24 | Yes |  |  | DELIV-FUN-204.Functional Specification - Form | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -60 | -41.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073110 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | FOTC006-DEV FUT-Level 2 Notification Form | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 71h | 5h | 76h | 2017-07-13 | 2017-09-05 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | 38 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 20 | 20 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0
1073111 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | FOTC006-FSD-Level 2 Notification Form | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 29.3h | 0h | 29.3h | 2017-05-01 | 2017-06-09 | Yes |  |  | DELIV-FUN-204.Functional Specification - Form | Complete | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -45 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 7.3 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073112 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | EOTC032-DEV FUT-Pricing Files | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 65.5h | 0h | 65.5h | 2017-04-10 | 2017-06-16 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | -30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 0 | 0 | 0 | 0 | 24.5 | 20 | 2 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073113 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Support-D2 | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | OpEx | Localization | IT - External | 0h | 20h | 20h | 2018-01-01 | 2018-02-02 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-09-18 | 2017-11-03 | 2 | Training Material Localization | 20000 D2-29000 MultiPhases-29040 Training Material Localization | -10 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073114 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-04 | 2017-12-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073115 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-04 | 2017-12-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073116 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 0h | 28h | 28h | 2018-01-01 | 2018-01-12 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -30 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073117 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2018-01-15 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -5 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073118 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 0h | 200h | 200h | 2018-01-29 | 2018-03-23 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073119 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - PTP | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073120 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Gap log - PTP | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 4.5h | 0h | 4.5h | 2017-04-17 | 2017-06-06 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -22.88 | 70.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0.5 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073121 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTP) - Deploy2 | PTP | FUN | SI | Offshore | Gaikwad; Mitesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-09-11 | 2017-09-22 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 20 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073122 | No | No | Yes | SDF | SDF Localisation | 04-Test | Regression - Run Tests (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Gaikwad; Mitesh | IBM | Yes | CapEx | Localization | IT - External | 10h | 15h | 25h | 2017-08-07 | 2017-08-25 | Yes |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 0 | 0 | 0 | 0
1073123 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Gaikwad; Mitesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-09-25 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073124 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTP) - Deploy2 | PTP | FUN | SI | Offshore | Gaikwad; Mitesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073125 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTP) - Deploy2 | PTP | FUN | SI | Offshore | Gaikwad; Mitesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073126 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTP) - Deploy2 | PTP | FUN | SI | Offshore | Gaikwad; Mitesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073127 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTP) - Deploy2 | PTP | FUN | SI | Offshore | Gaikwad; Mitesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 150h | 150h | 2017-08-21 | 2017-10-27 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | -50 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073128 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTP) - Deploy2 | PTP | FUN | SI | Offshore | Gaikwad; Mitesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-09-18 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073129 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Gaikwad; Mitesh | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-07-19 | 2017-08-04 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 7 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073130 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Gaikwad; Mitesh | IBM | Yes | CapEx | Localization | IT - External | 47h | 0h | 47h | 2017-07-17 | 2017-07-21 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073131 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Gaikwad; Mitesh | IBM | Yes | CapEx | Localization | IT - External | 11h | 19h | 30h | 2017-08-11 | 2017-08-28 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 6 | 0 | 0 | 0 | 0
1073132 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Gaikwad; Mitesh | IBM | Yes | CapEx | Localization | IT - External | 81h | 0h | 81h | 2017-08-07 | 2017-08-18 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 36 | 0 | 0 | 0 | 0 | 0
1073133 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Gaikwad; Mitesh | IBM | Yes | CapEx | Localization | IT - External | 46h | 4h | 50h | 2017-07-04 | 2017-08-23 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 20 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 34 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
1073134 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Interface (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Gaikwad; Mitesh | IBM | Yes | CapEx | Localization | IT - External | 7h | 13h | 20h | 2017-06-19 | 2017-07-31 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 15 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073135 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Gaikwad; Mitesh | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2017-06-19 | 2017-07-07 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | -5 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073136 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Gaikwad; Mitesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 11 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073137 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy2 | PTP | FUN | SI | Offshore | Gaikwad; Mitesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 129h | 129h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073138 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Gaikwad; Mitesh | IBM | Yes | CapEx | Localization | IT - External | 81h | 0h | 81h | 2017-08-28 | 2017-09-08 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 36 | 0 | 0
1073139 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Gaikwad; Mitesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-08-28 | 2017-09-15 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073140 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy1 | PTP | FUN | SI | Offshore | Gaikwad; Mitesh | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2017-07-04 | 2017-07-07 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | -15 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073141 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Deploy1 | PTP | FUN | SI | Offshore | Gaikwad; Mitesh | IBM | Yes | CapEx | Global | IT - External | 5h | 0h | 5h | 2017-05-23 | 2017-06-23 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | -5 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073142 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (PTM) - Deploy1 | PTP | FUN | SI | Offshore | Gaikwad; Mitesh | IBM | Yes | CapEx | Localization | IT - External | 41h | 0h | 41h | 2017-06-19 | 2017-07-14 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 10 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 4 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073143 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTM) - Deploy1 | PTP | FUN | SI | Offshore | Gaikwad; Mitesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073144 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy1 | PTP | FUN | SI | Offshore | Gaikwad; Mitesh | IBM | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2017-07-17 | 2017-08-04 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073145 | No | No | Yes | SDF | SDF Localisation | 04-Test | Regression - Run Tests (PTM) - Deploy1 | PTP | FUN | SI | Offshore | Gaikwad; Mitesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | Yes |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073146 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTM) - Deploy1 | PTP | FUN | SI | Offshore | Gaikwad; Mitesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-18 | 2017-08-18 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 17.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073147 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy1 | PTP | FUN | SI | Offshore | Gaikwad; Mitesh | IBM | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2017-08-21 | 2017-08-24 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0
1073148 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy1 | PTP | FUN | SI | Offshore | Gaikwad; Mitesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-08-28 | 2017-09-08 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073149 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTP | FUN | SI | Offshore | Gaikwad; Mitesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-08-28 | 2017-09-08 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073150 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Data Migration development - Deploy1 - DC | MDG | DC | SI | Offshore | Jumamil; Jeff | Accenture | Yes | CapEx | Localization | IT - External | 206h | 0h | 206h | 2017-06-01 | 2017-06-30 | Yes |  |  | ACT-MDG.Data Construction | Complete | 2017-05-08 | 2017-06-09 | 1 | Data Construction | 1000 D1-1300 B-1320 Data Construction | 15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 45 | 45 | 49 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073151 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jumamil; Jeff | Accenture | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-07-24 | 2017-08-06 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073152 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy1 - DC | MDG | DC | SI | Offshore | Jumamil; Jeff | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-16 | 2017-06-16 | Yes |  |  | ACT-MDG.Build ETL programs | Complete | 2017-05-08 | 2017-06-09 | 1 | Build and adjust conversion programs | 1000 D1-1300 B-1322 Build and adjust conversion programs | 15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073153 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jumamil; Jeff | Accenture | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073154 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jumamil; Jeff | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073155 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jumamil; Jeff | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073156 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jumamil; Jeff | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-22 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073157 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jumamil; Jeff | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-10-30 | 2017-12-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073158 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jumamil; Jeff | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -4.88 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073159 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jumamil; Jeff | Accenture | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -50 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073160 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jumamil; Jeff | Accenture | Yes | CapEx | Localization | IT - External | 0h | 85h | 85h | 2017-10-30 | 2017-12-07 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 0 | 18.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073161 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Jumamil; Jeff | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-21 | 2017-07-21 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073162 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Jumamil; Jeff | Accenture | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2017-07-05 | 2017-07-07 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 30 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073163 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jumamil; Jeff | Accenture | Yes | CapEx | Localization | IT - External | 79h | 0h | 79h | 2017-08-10 | 2017-09-01 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 21 | 30 | 27 | 0 | 0 | 0
1073164 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jumamil; Jeff | Accenture | Yes | CapEx | Localization | IT - External | 27h | 20h | 47h | 2017-09-06 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0
1073165 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jumamil; Jeff | Accenture | Yes | CapEx | Localization | IT - External | 40h | 20h | 60h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0
1073166 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jumamil; Jeff | Accenture | Yes | CapEx | Localization | IT - External | 8h | 20h | 28h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0
1073167 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jumamil; Jeff | Accenture | Yes | CapEx | Localization | IT - External | 26h | 0h | 26h | 2017-08-17 | 2017-09-05 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 18 | 0 | 0
1073168 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jumamil; Jeff | Accenture | Yes | CapEx | Localization | IT - External | 78h | 0h | 78h | 2017-08-07 | 2017-08-25 | Yes |  |  | ACT-MDG.Mock Load | Complete | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 10.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 22 | 12 | 0 | 0 | 0 | 0
1073169 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Jumamil; Jeff | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-21 | 2017-07-21 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 15 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073170 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Jumamil; Jeff | Accenture | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-07-05 | 2017-07-21 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073171 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Jumamil; Jeff | Accenture | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073172 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy1 - HC - (Accenture) - DC | MDG | DC | SI | Offshore | Jumamil; Jeff | Accenture | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -21.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073173 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | PTM | FUN | SI | Onshore | Stinnes; Derek | IBM | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2017-03-21 | 2017-03-30 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -20 | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073174 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTM | PTM | FUN | SI | Onshore | Stinnes; Derek | IBM | Yes | CapEx | Localization | IT - External | 81h | 0h | 81h | 2017-06-05 | 2017-06-23 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 17 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073175 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTM(Global) | PTM | FUN | SI | Onshore | Stinnes; Derek | IBM | Yes | CapEx | Localization | IT - External | 27h | 1,408h | 1,435h | 2017-08-07 | 2018-03-30 | Yes |  |  | ACT-FUN.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0
1073176 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - PTM | PTM | FUN | SI | Onshore | Stinnes; Derek | IBM | Yes | CapEx | Localization | IT - External | 150h | 0h | 150h | 2017-04-17 | 2017-06-05 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 2 | 0 | 12 | 0 | 36 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073177 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Support (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Ulaganathan; Karthi | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-10-09 | 2017-11-03 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073178 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Ulaganathan; Karthi | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073179 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trande-RTM | OTC | FUN | SI | Onshore | Ulaganathan; Karthi | IBM | Yes | CapEx | Global | IT - External | 73h | 0h | 73h | 2017-03-20 | 2017-04-21 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 14 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073180 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-RTM-Global Trade-OTC | OTC | FUN | SI | Onshore | Ulaganathan; Karthi | IBM | Yes | CapEx | Global | IT - External | 26h | 0h | 26h | 2017-04-10 | 2017-04-28 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 2 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073181 | No | No | Yes | SDF | Trade (in SDF) | 99-Global | Management -Trade-TPM-OTC | OTC | FUN | SI | Onshore | Ulaganathan; Karthi | IBM | Yes | CapEx | Global | IT - External | 448h | 0h | 448h | 2017-04-03 | 2017-09-01 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 13 | 10 | 10 | 44 | 44 | 24 | 24 | 19 | 24 | 24 | 24 | 0 | 28 | 40 | 40 | 0 | 0 | 8 | 24 | 14 | 24 | 0 | 0 | 0
1073182 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-Global Trade scope / Solution validation-OTC | OTC | FUN | SI | Onshore | Ulaganathan; Karthi | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073183 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-Gap Resolution-Global | OTC | FUN | SI | Onshore | Ulaganathan; Karthi | IBM | Yes | CapEx | Global | IT - External | 25h | 0h | 25h | 2017-04-03 | 2017-04-28 | Yes |  |  | WP-FUN.Gap Definition | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073184 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-Fit-Gap-Global | OTC | FUN | SI | Onshore | Ulaganathan; Karthi | IBM | Yes | CapEx | Global | IT - External | 53h | 0h | 53h | 2017-03-13 | 2017-04-28 | Yes |  |  | WP-FUN.Gap Definition | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 12 | 12 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073185 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - OTC-(Global) | OTC | FUN | SI | Onshore | Ulaganathan; Karthi | IBM | Yes | CapEx | Localization | IT - External | 0h | 1,250h | 1,250h | 2017-07-05 | 2018-03-30 | Yes |  |  | ACT-CM.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073186 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Cycle2 Configuration | OTC | FUN | SI | Onshore | Ulaganathan; Karthi | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 0 | NA Others | 99000-99100-99130 NA others | -20 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073187 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-SIT Test Scenarios/Scripts | OTC | FUN | SI | Onshore | Ulaganathan; Karthi | IBM | Yes | CapEx | Global | IT - External | 10h | 145h | 155h | 2017-08-21 | 2017-10-10 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 0 | NA Others | 99000-99100-99130 NA others | -25 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0
1073188 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Cycle1 Configuration | OTC | FUN | SI | Onshore | Ulaganathan; Karthi | IBM | Yes | CapEx | Global | IT - External | 50h | 0h | 50h | 2017-07-03 | 2017-07-28 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 0 | NA Others | 99000-99100-99130 NA others | -15 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 4 | 4 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073189 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Functional Specification (FSD) | OTC | FUN | SI | Onshore | Ulaganathan; Karthi | IBM | Yes | CapEx | Global | IT - External | 60h | 0h | 60h | 2017-06-05 | 2017-06-23 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | 5 | 85.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073190 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Execute FUT | OTC | FUN | SI | Onshore | Ulaganathan; Karthi | IBM | Yes | CapEx | Global | IT - External | 60h | 0h | 60h | 2017-08-14 | 2017-09-01 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-08-18 | 0 | NA Others | 99000-99100-99130 NA others | -30 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 0
1073191 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Baseline configuration - OTC | OTC | FUN | SI | Onshore | Ulaganathan; Karthi | IBM | Yes | CapEx | Global | IT - External | 56h | 0h | 56h | 2017-05-15 | 2017-06-02 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-06-26 | 2017-07-14 | 0 | NA Others | 99000-99100-99130 NA others | -30 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073192 | No | Yes | No | SDF | SDF Localisation | 99-Global | SDF-Manage Project | PMO | PMO | SI | Onshore | Hargrave; D'Anna | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-27 | 2017-03-27 | Yes |  |  | ACT-PMO.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073193 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Singh; Kamna | IBM | Yes | CapEx | Localization | IT - External | 0h | 64h | 64h | 2017-09-25 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073194 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Singh; Kamna | IBM | Yes | CapEx | Localization | IT - External | 0h | 100h | 100h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073195 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Singh; Kamna | IBM | Yes | CapEx | Localization | IT - External | 0h | 66h | 66h | 2017-09-05 | 2017-09-22 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 15 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073196 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Singh; Kamna | IBM | Yes | CapEx | Localization | IT - External | 98h | 0h | 98h | 2017-06-09 | 2017-07-07 | Yes |  |  | ACT-FUN.Management | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 14 | 36 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073197 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Singh; Kamna | IBM | Yes | CapEx | Localization | IT - External | 50h | 0h | 50h | 2017-07-17 | 2017-07-21 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073198 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Singh; Kamna | IBM | Yes | CapEx | Localization | IT - External | 120h | 0h | 120h | 2017-08-07 | 2017-08-24 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 0 | 0 | 0 | 0
1073199 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Singh; Kamna | IBM | Yes | CapEx | Localization | IT - External | 50h | 0h | 50h | 2017-07-24 | 2017-07-28 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073200 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Singh; Kamna | IBM | Yes | CapEx | Localization | IT - External | 10h | 50h | 60h | 2017-08-07 | 2017-08-15 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 17.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0
1073201 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Singh; Kamna | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-19 | 2017-07-19 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | 5 | 29.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073202 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Singh; Kamna | IBM | Yes | CapEx | Localization | IT - External | 43h | 0h | 43h | 2017-06-05 | 2017-07-16 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | -15 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073203 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Singh; Kamna | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-05 | 2017-09-15 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073204 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Singh; Kamna | IBM | Yes | CapEx | Localization | IT - External | 0h | 100h | 100h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073205 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Singh; Kamna | IBM | Yes | CapEx | Localization | IT - External | 60h | 0h | 60h | 2017-06-05 | 2017-08-04 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 10 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073206 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Kadam; Sandeep | IBM | Yes | CapEx | Localization | IT - External | 0h | 125h | 125h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073207 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Kadam; Sandeep | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-05-15 | 2017-06-23 | Yes |  |  | ACT-FUN.Management | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073208 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Kadam; Sandeep | IBM | Yes | CapEx | Localization | IT - External | 0h | 120h | 120h | 2017-09-25 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073209 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Kadam; Sandeep | IBM | Yes | CapEx | Localization | IT - External | 0h | 45h | 45h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073210 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Kadam; Sandeep | IBM | Yes | CapEx | Localization | IT - External | 50h | 0h | 50h | 2017-06-05 | 2017-08-24 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | -15 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 40 | 0 | 0 | 0 | 0
1073211 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Kadam; Sandeep | IBM | Yes | CapEx | Localization | IT - External | 0h | 67h | 67h | 2017-08-28 | 2017-09-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073212 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Kadam; Sandeep | IBM | Yes | CapEx | Localization | IT - External | 50h | 0h | 50h | 2017-07-10 | 2017-07-28 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | 5 | 29.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073213 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Kadam; Sandeep | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-08-15 | 2017-09-06 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 17.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073214 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Kadam; Sandeep | IBM | Yes | CapEx | Localization | IT - External | 25h | 35h | 60h | 2017-07-24 | 2017-08-18 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0
1073215 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Kadam; Sandeep | IBM | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2017-08-07 | 2017-08-20 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 50 | 0 | 0 | 0 | 0 | 0
1073216 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Kadam; Sandeep | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-08-28 | 2017-09-08 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073217 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Kadam; Sandeep | IBM | Yes | CapEx | Localization | IT - External | 100h | 0h | 100h | 2017-07-17 | 2017-08-04 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073218 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Deploy1 | PTM | FUN | SI | Offshore | Kadam; Sandeep | IBM | Yes | CapEx | Global | IT - External | 15h | 0h | 15h | 2017-05-22 | 2017-06-02 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | -5 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073219 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Kadam; Sandeep | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-09-11 | 2017-09-29 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 15 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073220 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Torrecampo; Rey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-22 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073221 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Torrecampo; Rey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -50 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073222 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Torrecampo; Rey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073223 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Torrecampo; Rey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073224 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Torrecampo; Rey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073225 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Torrecampo; Rey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -4.88 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073226 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Torrecampo; Rey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 65h | 65h | 2017-10-30 | 2017-12-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073227 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Torrecampo; Rey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 55h | 55h | 2017-10-30 | 2017-12-07 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 0 | 18.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073228 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy2 - HC - (Accenture) - DC | MDG | DC | SI | Offshore | Torrecampo; Rey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2018-02-05 | 2018-03-02 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | -17.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073229 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Torrecampo; Rey | Accenture | Yes | CapEx | Localization | IT - External | 63h | 0h | 63h | 2017-08-14 | 2017-09-05 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 45 | 9 | 0 | 0
1073230 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Torrecampo; Rey | Accenture | Yes | CapEx | Localization | IT - External | 101h | 0h | 101h | 2017-08-09 | 2017-08-25 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 29 | 45 | 0 | 0 | 0 | 0
1073231 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Torrecampo; Rey | Accenture | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2017-08-07 | 2017-08-18 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-07-31 | 2017-08-11 | 2 | QE2 Mock Prep | 20000 D2-20100 B-20110 QE2 Mock Prep | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 7 | 0 | 0 | 0 | 0 | 0
1073232 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Torrecampo; Rey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 100h | 100h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073233 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Torrecampo; Rey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 65h | 65h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073234 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Torrecampo; Rey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073235 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Torrecampo; Rey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 10h | 10h | 2017-09-08 | 2017-09-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 14.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073236 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Torrecampo; Rey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073237 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy2 (Accenture) - DC | MDG | DC | SI | Offshore | Torrecampo; Rey | Accenture | Yes | CapEx | Localization | IT - External | 306h | 0h | 306h | 2017-07-03 | 2017-09-15 | Yes |  |  | ACT-MDG.Build ETL programs | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 36 | 45 | 0
1073238 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | SI | Offshore | Mitkari; Bharati | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073239 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing WRICEFs (Design/Build) | DEV | DEV | SI | Offshore | Mitkari; Bharati | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-01-11 | 2017-11-03 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -88 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073240 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Mitkari; Bharati | IBM | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073241 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Mitkari; Bharati | IBM | Yes | CapEx | Localization | IT - External | 0h | 135h | 135h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073242 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | SI | Offshore | Mitkari; Bharati | IBM | Yes | CapEx | Localization | IT - External | 0h | 35h | 35h | 2017-08-28 | 2017-09-29 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073243 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | SI | Offshore | Mitkari; Bharati | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2016-12-28 | 2017-10-31 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073244 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Mitkari; Bharati | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073245 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | SI | Offshore | Mitkari; Bharati | IBM | Yes | CapEx | Localization | IT - External | 441h | 0h | 441h | 2017-07-03 | 2017-09-15 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 45 | 27 | 36 | 18 | 45 | 45 | 0
1073246 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Mitkari; Bharati | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-08-07 | 2017-08-25 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073247 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTM | FUN | SI | Onshore | Mooers; Michael | SAP | Yes | CapEx | Localization | IT - External | 0h | 96.32h | 96.32h | 2017-09-05 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073248 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Vargas; Kristin | IBM | Yes | CapEx | Localization | IT - External | 27h | 95.63h | 122.63h | 2017-08-28 | 2017-09-20 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0
1073249 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Vargas; Kristin | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-09-05 | 2017-09-15 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073250 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Vargas; Kristin | IBM | Yes | CapEx | Localization | IT - External | 34h | 0h | 34h | 2017-05-31 | 2017-07-05 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | -14 | 72.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073251 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | Workshop-Design Interim state financial reporting | RTR | FUN | SI | Onshore | Vargas; Kristin | IBM | Yes | CapEx | Localization | IT - External | 23h | 0h | 23h | 2017-05-22 | 2017-06-30 | Yes |  |  | WP-FUN.Requirements/Process Design Workshop Decks | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073252 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Gather reporting requierements (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Vargas; Kristin | IBM | Yes | CapEx | Localization | IT - External | 70h | 37h | 107h | 2017-07-03 | 2017-08-22 | Yes |  |  | ACT-FUN.Gather reporting requierement | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 44 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0
1073253 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Interface (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Vargas; Kristin | IBM | Yes | CapEx | Localization | IT - External | 58h | 0h | 58h | 2017-06-07 | 2017-07-28 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 7 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073254 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Vargas; Kristin | IBM | Yes | CapEx | Localization | IT - External | 0h | 24h | 24h | 2017-09-08 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073255 | No | No | Yes | SDF | SDF Localisation | 04-Test | Regression - Run Tests (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Vargas; Kristin | IBM | Yes | CapEx | Localization | IT - External | 69h | 0h | 69h | 2017-08-07 | 2017-08-25 | Yes |  |  | ACT-FUN.Execute Regression Test | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 9.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 17 | 44 | 0 | 0 | 0 | 0
1073256 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Vargas; Kristin | IBM | Yes | CapEx | Localization | IT - External | 48h | 0h | 48h | 2017-07-24 | 2017-08-04 | Yes |  |  | ACT-FUN.Functional Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073257 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Vargas; Kristin | IBM | Yes | CapEx | Localization | IT - External | 31h | 0h | 31h | 2017-07-24 | 2017-08-08 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0
1073258 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Vargas; Kristin | IBM | Yes | CapEx | Localization | IT - External | 27h | 3h | 30h | 2017-08-07 | 2017-09-01 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 13.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 0 | 9 | 0 | 0 | 0
1073259 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Vargas; Kristin | IBM | Yes | CapEx | Localization | IT - External | 8h | 37h | 45h | 2017-09-01 | 2017-09-21 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0
1073260 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Patel; Jinal | IBM | Yes | CapEx | Localization | IT - External | 119h | 0h | 119h | 2017-08-28 | 2017-09-15 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 36 | 40 | 0
1073261 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTP) - Deploy2 | PTP | FUN | SI | Onshore | Patel; Jinal | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073262 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTP) - Deploy2 | PTP | FUN | SI | Onshore | Patel; Jinal | IBM | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073263 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTP) - Deploy2 | PTP | FUN | SI | Onshore | Patel; Jinal | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073264 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTP) - Deploy2 | PTP | FUN | SI | Onshore | Patel; Jinal | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073265 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Patel; Jinal | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-09-25 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073266 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (PTP) - Deploy2 | PTP | FUN | SI | Onshore | Patel; Jinal | IBM | Yes | CapEx | Localization | IT - External | 0h | 150h | 150h | 2017-08-14 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073267 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Interface (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Patel; Jinal | IBM | Yes | CapEx | Localization | IT - External | 95h | 85h | 180h | 2017-06-26 | 2017-09-05 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 15 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 9 | 28 | 0 | 8 | 20 | 0 | 0 | 0 | 0
1073268 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Patel; Jinal | IBM | Yes | CapEx | Localization | IT - External | 75h | 135h | 210h | 2017-06-19 | 2017-10-03 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 20 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 16 | 14 | 0 | 8 | 20 | 1 | 0 | 2 | 0
1073269 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Patel; Jinal | IBM | Yes | CapEx | Localization | IT - External | 87h | 0h | 87h | 2017-07-17 | 2017-08-11 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 15 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0
1073270 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test-Defect Management-FIN-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 10h | 0h | 10h | 2017-07-31 | 2017-08-04 | Yes |  |  |  | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073271 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test-Defect Management-VM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-04 | 2017-08-04 | Yes |  |  |  | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073272 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test-Defect Workarounds/OPLs-FIN-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-11 | 2017-08-11 | Yes |  |  |  | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073273 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test-RT Execution - Montreal-VM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | Yes |  |  |  | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073274 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test-'Smoke'' Test Planning and Scheduling-FIN-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | Yes |  |  |  | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073275 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test-Defect Workarounds/OPLs-VM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-11 | 2017-08-11 | Yes |  |  |  | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073276 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test-RT Execution - Montreal-FIN-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | Yes |  |  |  | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073277 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | Hypercare-Provide end User Support - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 320h | 320h | 2018-02-05 | 2018-03-30 | Yes |  |  |  | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073278 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover Suport - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-09-11 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073279 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | CapEx | Localization | IT - Internal | 10h | 70h | 80h | 2017-08-28 | 2017-09-11 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | -5 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0
1073280 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Support - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 15h | 45h | 60h | 2017-08-21 | 2017-09-25 | Yes |  |  |  | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 60 | 48.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0
1073281 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT 2-Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 30h | 30h | 2017-10-10 | 2017-10-27 | Yes |  |  |  | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073282 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 120h | 120h | 2017-12-04 | 2017-12-22 | Yes |  |  |  | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | -25 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073283 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT 1-Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 30h | 30h | 2017-09-18 | 2017-10-06 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073284 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Support - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 140h | 140h | 2017-12-18 | 2018-02-02 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-11-03 | 2 | Training Material Localization | 20000 D2-29000 MultiPhases-29040 Training Material Localization | 55 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073285 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Preparation - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 30h | 30h | 2017-08-21 | 2017-09-08 | Yes |  |  |  | Future Task | 2017-08-21 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 0 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073286 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HYP-Dual Maintenance Execution-VM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073287 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HYP-End User Support-FIN-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073288 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HYP-Smoke Test Execution-VM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073289 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HYP-Smoke Test Execution-FIN-SI - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073290 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HYP-End User Support-VM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073291 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B-Training: Job Aids Review-VM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-04 | 2017-08-04 | Yes |  |  |  | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 35 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073292 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B-Training: Work Instructions Review-FIN-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-04 | 2017-08-04 | Yes |  |  |  | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 35 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073293 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B-Training: Work Instructions Review-VM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-04 | 2017-08-04 | Yes |  |  |  | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 35 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073294 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test - Vendor Master - Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073295 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HYP-Dual Maintenance Execution-FIN-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073296 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B-Training: Concept Slides Final Review-VM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-04 | 2017-08-04 | Yes |  |  |  | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 35 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073297 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B-Training: Job Aids Review-FIN-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-04 | 2017-08-04 | Yes |  |  |  | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 35 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073298 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B-Dual Maintenance Training-VM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | Yes |  |  |  | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 70 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073299 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B-Training: Concept Slides Final Review-FIN-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-04 | 2017-08-04 | Yes |  |  |  | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 35 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073300 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Run Tests - MDG - VM - Saputo- Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | Yes |  |  |  | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073301 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test-Train the Trainer (TTT)-VM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-04 | 2017-08-04 | Yes |  |  |  | Future Task | 2017-07-17 | 2017-07-28 | 1 | Train the trainer | 1000 D1-1800 MultiPhases-1840 Train the trainer | 5.13 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073302 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Run Tests - MDG - FIN - Saputo- Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 30h | 0h | 30h | 2017-08-28 | 2017-09-01 | Yes |  |  |  | Complete | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0.13 | -4.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0
1073303 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B-Dual Maintenance Training-FIN-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | Yes |  |  |  | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 70 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073304 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test-Train the Trainer (TTT)-FIN-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-04 | 2017-08-04 | Yes |  |  |  | Future Task | 2017-07-17 | 2017-07-28 | 1 | Train the trainer | 1000 D1-1800 MultiPhases-1840 Train the trainer | 5.13 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073305 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | C/G-Business Cutover Plan-VM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-09-18 | 2017-09-18 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073306 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test - SIT 2 - Financial Objects - Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 15h | 0h | 15h | 2017-08-07 | 2017-08-11 | Yes |  |  | ACT-FUN.Execute SIT | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0.13 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0
1073307 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT 1 - Run Tests - MDG - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | CapEx | Localization | IT - Internal | 10h | 0h | 10h | 2017-07-31 | 2017-08-04 | Yes |  |  | ACT-MDG.Execute SIT | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -9.88 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073308 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT 1 - Manage defects - MDG - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | CapEx | Localization | IT - Internal | 10h | 0h | 10h | 2017-07-31 | 2017-08-04 | Yes |  |  | ACT-MDG.Execute SIT | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -9.88 | 5.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073309 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT 1 - Break/Fix - MDG - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | CapEx | Localization | IT - Internal | 10h | 0h | 10h | 2017-07-31 | 2017-08-04 | Yes |  |  | ACT-MDG.Execute SIT | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | -9.88 | 5.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073310 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT Preparation : Component & Scripts - MDG - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-04 | 2017-08-04 | Yes |  |  | ACT-FUN.UAT Preparation | Future Task | NA | NA | 1 | NA SDF | 99000-99100-99120 NA SDF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073311 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT 2 - Run Tests - MDGM - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | CapEx | Localization | IT - Internal | 15h | 0h | 15h | 2017-08-14 | 2017-08-18 | Yes |  |  | ACT-MDG.Execute SIT | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 1.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0
1073312 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT 2 - Manage defects - MDG - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | CapEx | Localization | IT - Internal | 15h | 0h | 15h | 2017-08-14 | 2017-08-18 | Yes |  |  | ACT-MDG.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0
1073313 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT 2 - Break/Fix - MDG - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | CapEx | Localization | IT - Internal | 15h | 0h | 15h | 2017-08-14 | 2017-08-18 | Yes |  |  | ACT-MDG.Execute SIT | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0
1073314 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test - SIT 1 - Financial Objects - Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073315 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Manage defects - MDG - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-09-22 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | NA | NA | 1 | NA SDF | 99000-99100-99120 NA SDF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073316 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Break/Fix - MDG - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-09-22 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | NA | NA | 1 | NA SDF | 99000-99100-99120 NA SDF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073317 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Document work around - Deploy1 - DM | MDG | DM | Saputo | Onshore | Shiva Kumar; Madan Kumar | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-09-22 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | NA | NA | 1 | NA SDF | 99000-99100-99120 NA SDF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073318 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Prepare Workshop Materials | PTM | FUN | Saputo | Onshore | Soni; Shailendra | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-04 | 2017-04-04 | Yes |  |  | WP-FUN-107.Workshop Preparation Decks | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -8.88 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073319 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Conduct PP Workshops | PTM | FUN | Saputo | Onshore | Soni; Shailendra | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-20 | 2017-03-23 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -20 | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073320 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Soni; Shailendra | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 280h | 280h | 2017-09-25 | 2017-11-24 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073321 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Soni; Shailendra | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 120h | 120h | 2017-10-02 | 2017-12-01 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073322 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Soni; Shailendra | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 18h | 18h | 2017-08-28 | 2017-09-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073323 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Soni; Shailendra | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 12h | 12h | 2017-08-28 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073324 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Soni; Shailendra | Saputo | Yes | CapEx | Localization | IT - Internal | 5h | 4.33h | 9.33h | 2017-08-28 | 2017-09-22 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -24.88 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0
1073325 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | Saputo | Onshore | Soni; Shailendra | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 9h | 9h | 2017-08-28 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073326 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy2 | PTM | FUN | Saputo | Onshore | Soni; Shailendra | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 260h | 260h | 2018-02-05 | 2018-03-30 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073327 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy2 | PTM | FUN | Saputo | Onshore | Soni; Shailendra | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 10h | 10h | 2018-01-04 | 2018-01-12 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -8 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073328 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (PTM) - Deploy2 | PTM | FUN | Saputo | Onshore | Soni; Shailendra | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 10h | 10h | 2018-01-04 | 2018-01-12 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -30 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073329 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy2 | PTM | FUN | Saputo | Onshore | Soni; Shailendra | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 45h | 45h | 2017-12-04 | 2017-12-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073330 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy2 | PTM | FUN | Saputo | Onshore | Soni; Shailendra | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 30h | 30h | 2017-12-04 | 2017-12-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073331 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Mock Load - Deploy1 - DC | MDG | DC | SI | Offshore | Banay; Jeffrey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073332 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Data Validation Sheets - Deploy1 - Test - DC | MDG | DC | SI | Offshore | Banay; Jeffrey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-02 | 2017-06-02 | Yes |  |  | WP-MDG.Data Validation Sheets | Complete | 2017-06-05 | 2017-06-16 | 1 | QE2 Prevalidation | 1000 D1-1300 B-1325 QE2 Prevalidation | -1 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073333 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Banay; Jeffrey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-14 | 2017-07-14 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 15 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073334 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) - Deploy1 - DC | MDG | DC | SI | Offshore | Banay; Jeffrey | Accenture | Yes | CapEx | Localization | IT - External | 126h | 0h | 126h | 2017-05-15 | 2017-06-02 | Yes |  |  | DELIV-MDG-206.Functional Specification -Conversion | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | -20 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073335 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Mock1 Validation - Deploy1 - CG- DC | MDG | DC | SI | Offshore | Banay; Jeffrey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-05 | 2017-07-05 | Yes |  |  | ACT-MDG.Mock Validation | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073336 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Mock1 Preparation - Deploy1 - CG - DC | MDG | DC | SI | Offshore | Banay; Jeffrey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-04 | 2017-07-04 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073337 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Banay; Jeffrey | Accenture | Yes | CapEx | Localization | IT - External | 63h | 0h | 63h | 2017-07-10 | 2017-07-21 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073338 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy1 - DC | MDG | DC | SI | Offshore | Banay; Jeffrey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-16 | 2017-06-16 | Yes |  |  | ACT-MDG.Build ETL programs | Complete | 2017-05-08 | 2017-06-09 | 1 | Build and adjust conversion programs | 1000 D1-1300 B-1322 Build and adjust conversion programs | 15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073339 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Banay; Jeffrey | Accenture | Yes | CapEx | Localization | IT - External | 129h | 0h | 129h | 2017-06-19 | 2017-07-07 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 30 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 40 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073340 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Banay; Jeffrey | Accenture | Yes | CapEx | Localization | IT - External | 126h | 0h | 126h | 2017-07-24 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 36 | 0 | 0 | 0 | 0 | 45 | 0 | 0
1073341 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Data Migration development - Deploy1 - DC | MDG | DC | SI | Offshore | Banay; Jeffrey | Accenture | Yes | CapEx | Localization | IT - External | 92h | 0h | 92h | 2017-06-05 | 2017-06-18 | Yes |  |  | ACT-MDG.Data Construction | Complete | 2017-05-08 | 2017-06-09 | 1 | Data Construction | 1000 D1-1300 B-1320 Data Construction | 15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073342 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Banay; Jeffrey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-16 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073343 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy1 - HC - (Accenture) - DC | MDG | DC | SI | Offshore | Banay; Jeffrey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -21.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073344 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Banay; Jeffrey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-10-30 | 2017-12-07 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 0 | 18.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073345 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Banay; Jeffrey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 135h | 135h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -50 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073346 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Banay; Jeffrey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -4.88 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073347 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Banay; Jeffrey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 85h | 85h | 2017-10-30 | 2017-12-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073348 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Banay; Jeffrey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-12-15 | 2017-12-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073349 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Banay; Jeffrey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073350 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Banay; Jeffrey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073351 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Banay; Jeffrey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073352 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Banay; Jeffrey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073353 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Banay; Jeffrey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-11 | 2017-09-15 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073354 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Banay; Jeffrey | Accenture | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-08-29 | 2017-09-01 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0
1073355 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Banay; Jeffrey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-09-15 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073356 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Banay; Jeffrey | Accenture | Yes | CapEx | Localization | IT - External | 45h | 20h | 65h | 2017-09-12 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0
1073357 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Banay; Jeffrey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073358 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Banay; Jeffrey | Accenture | Yes | CapEx | Localization | IT - External | 128h | 0h | 128h | 2017-08-08 | 2017-08-25 | Yes |  |  | ACT-MDG.Mock Load | Complete | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 10.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 38 | 0 | 0 | 0 | 0
1073359 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 configuration (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Maity; Sudip | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-09-05 | 2017-09-29 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073360 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Maity; Sudip | IBM | Yes | CapEx | Localization | IT - External | 0h | 55h | 55h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | -5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073361 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Functional Specification (FSD) | OTC | FUN | SI | Onshore | Maity; Sudip | IBM | Yes | CapEx | Global | IT - External | 0h | 20h | 20h | 2017-05-29 | 2017-09-15 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073362 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Cycle1 Configuration | OTC | FUN | SI | Onshore | Maity; Sudip | IBM | Yes | CapEx | Global | IT - External | 60h | 0h | 60h | 2017-06-19 | 2017-08-04 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 0 | NA Others | 99000-99100-99130 NA others | -15 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073363 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Cycle2 Configuration | OTC | FUN | SI | Onshore | Maity; Sudip | IBM | Yes | CapEx | Global | IT - External | 140h | 0h | 140h | 2017-07-04 | 2017-08-25 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 0 | NA Others | 99000-99100-99130 NA others | -20 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 40 | 40 | 40 | 0 | 0 | 0 | 0
1073364 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Functional Specification (FSD) | OTC | FUN | SI | Onshore | Maity; Sudip | IBM | Yes | CapEx | Global | IT - External | 40h | 140h | 180h | 2017-06-26 | 2017-09-21 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | 5 | 85.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0
1073365 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-SIT Test Scenarios/Scripts | OTC | FUN | SI | Onshore | Maity; Sudip | IBM | Yes | CapEx | Global | IT - External | 40h | 50h | 90h | 2017-08-28 | 2017-10-17 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 0 | NA Others | 99000-99100-99130 NA others | -25 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0
1073366 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | TPM Unit testing Development Documentation (FUT) | OTC | FUN | SI | Onshore | Maity; Sudip | IBM | Yes | CapEx | Global | IT - External | 0h | 40h | 40h | 2017-05-29 | 2017-09-29 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073367 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Maity; Sudip | IBM | Yes | CapEx | Localization | IT - External | 0h | 10h | 10h | 2017-09-05 | 2017-09-15 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 10 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073368 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Maity; Sudip | IBM | Yes | CapEx | Localization | IT - External | 0h | 100h | 100h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073369 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Maity; Sudip | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073370 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Maity; Sudip | IBM | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073371 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Maity; Sudip | IBM | Yes | CapEx | Localization | IT - External | 72h | 0h | 72h | 2017-07-04 | 2017-07-14 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-05-19 | 2 | Base Config | 1000 D1-1300 B-1314 Base Config | -5 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073372 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Maity; Sudip | IBM | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-06-05 | 2017-07-21 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | -15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073373 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Maity; Sudip | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-19 | 2017-06-19 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | -25 | 16.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073374 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (OTC) - Deploy1 | OTC | FUN | Saputo | Onshore | Bedard; Martine | Saputo | Yes | CapEx | Localization | Business | 99h | 9h | 108h | 2017-07-17 | 2017-08-29 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 5 | 18 | 0 | 40 | 25 | 0 | 0 | 0 | 0
1073375 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Bedard; Martine | Saputo | Yes | CapEx | Localization | Business | 0h | 30h | 30h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | -5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073376 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Bedard; Martine | Saputo | Yes | CapEx | Localization | Business | 10h | 10h | 20h | 2017-09-05 | 2017-09-15 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 10 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0
1073377 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Data Definition Documents (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Bedard; Martine | Saputo | Yes | CapEx | Localization | Business | 88h | 0h | 88h | 2017-06-12 | 2017-07-28 | Yes |  |  | DELIV-FUN-149.Data Definition Documents (DDD) | Complete | 2017-09-25 | 2017-10-06 | 2 | TBD | 99000-99100-99110 TBD | -85 | -50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 8 | 0 | 20 | 26 | 4 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073378 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Bedard; Martine | Saputo | Yes | CapEx | Localization | Business | 14h | 0h | 14h | 2017-07-03 | 2017-07-14 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-21 | 2017-09-01 | 2 | AT | 20000 D2-20100 B-20180 AT | -45 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073379 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (OTC) - Deploy1 | OTC | FUN | Saputo | Onshore | Bedard; Martine | Saputo | Yes | CapEx | Localization | Business | 40h | 34h | 74h | 2017-08-28 | 2017-09-19 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0
1073380 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Bedard; Martine | Saputo | Yes | CapEx | Localization | Business | 0h | 160h | 160h | 2018-01-29 | 2018-03-23 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073381 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Bedard; Martine | Saputo | Yes | CapEx | Localization | Business | 0h | 10h | 10h | 2018-01-04 | 2018-01-12 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -30 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073382 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Support-D2 | OTC | FUN | Saputo | Onshore | Bedard; Martine | Saputo | Yes | OpEx | Localization | Business | 0h | 150h | 150h | 2017-09-05 | 2017-12-22 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-09-18 | 2017-11-03 | 2 | Training Material Localization | 20000 D2-29000 MultiPhases-29040 Training Material Localization | -10 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073383 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Bedard; Martine | Saputo | Yes | CapEx | Localization | Business | 0h | 15h | 15h | 2017-12-04 | 2017-12-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073384 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Bedard; Martine | Saputo | Yes | CapEx | Localization | Business | 0h | 15h | 15h | 2017-12-04 | 2017-12-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073385 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Bedard; Martine | Saputo | Yes | CapEx | Localization | Business | 0h | 60h | 60h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073386 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Bedard; Martine | Saputo | Yes | CapEx | Localization | Business | 0h | 30h | 30h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073387 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Prepare (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Bedard; Martine | Saputo | Yes | CapEx | Localization | Business | 0h | 10h | 10h | 2017-10-02 | 2017-10-06 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-09-25 | 2017-10-06 | 2 | TBD | 99000-99100-99110 TBD | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073388 | No | No | Yes | SDF | SDF Localisation | 04-Test | DR - Support (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Bedard; Martine | Saputo | Yes | CapEx | Localization | Business | 0h | 30h | 30h | 2017-11-13 | 2017-12-01 | Yes |  |  | ACT-FUN.Dry Run activities | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073389 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Bedard; Martine | Saputo | Yes | CapEx | Localization | Business | 0h | 60h | 60h | 2018-01-15 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -5 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073390 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Support (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Bedard; Martine | Saputo | Yes | CapEx | Localization | Business | 0h | 20h | 20h | 2017-10-10 | 2017-10-20 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073391 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (OTC) - Deploy2 | OTC | FUN | Saputo | Onshore | Bedard; Martine | Saputo | Yes | CapEx | Localization | Business | 0h | 60h | 60h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073392 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Interface (RTR) - Deploy1 | RTR | FUN | SI | Onshore | Nathan; Ram | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-07 | 2017-06-09 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 7 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073393 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Navaratna; Shrikant | IBM | Yes | CapEx | Localization | IT - External | 0h | 48h | 48h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073394 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 configuration (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Navaratna; Shrikant | IBM | Yes | CapEx | Localization | IT - External | 30h | 10h | 40h | 2017-08-21 | 2017-09-06 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0
1073395 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Navaratna; Shrikant | IBM | Yes | CapEx | Localization | IT - External | 15h | 52.35h | 67.35h | 2017-08-21 | 2017-09-15 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | -8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0
1073396 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Navaratna; Shrikant | IBM | Yes | CapEx | Localization | IT - External | 20h | 76h | 96h | 2017-09-18 | 2017-10-02 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
1073397 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Navaratna; Shrikant | IBM | Yes | CapEx | Localization | IT - External | 0h | 108h | 108h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073398 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Navaratna; Shrikant | IBM | Yes | CapEx | Localization | IT - External | 25h | 11h | 36h | 2017-09-18 | 2017-09-25 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
1073399 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Support Mock1 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Navaratna; Shrikant | IBM | Yes | CapEx | Localization | IT - External | 70h | 9h | 79h | 2017-08-21 | 2017-09-11 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-09-25 | 2017-10-06 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -25 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 10 | 45 | 0 | 0
1073400 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Navaratna; Shrikant | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-10-09 | 2017-10-09 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073401 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Navaratna; Shrikant | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-08-28 | 2017-09-01 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0
1073402 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Navaratna; Shrikant | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073403 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Navaratna; Shrikant | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-08-07 | 2017-08-11 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 4.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0
1073404 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Navaratna; Shrikant | IBM | Yes | CapEx | Localization | IT - External | 60h | 0h | 60h | 2017-07-03 | 2017-09-15 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-19 | 2017-06-30 | 1 | Cycle 2 Config | 1000 D1-1300 B-1318 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0
1073405 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Navaratna; Shrikant | IBM | Yes | CapEx | Localization | IT - External | 163h | 0h | 163h | 2017-07-17 | 2017-08-18 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 20 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 45 | 43 | 45 | 0 | 0 | 0 | 0 | 0
1073406 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy1 | LOG | FUN | SI |  | Becker; Ray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-18 | 2017-08-18 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 4.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073407 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (DB) (Planning, reporting, CR, cross stream integration) - LOG(Global) | LOG | FUN | SI |  | Becker; Ray | IBM | Yes | CapEx | Localization | IT - External | 323h | 392h | 715h | 2017-05-30 | 2017-09-11 | Yes |  |  | ACT-MDG.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 45 | 40 | 44 | 38 | 28 | 40 | 0 | 0 | 0
1073408 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy1 | LOG | FUN | SI |  | Becker; Ray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073409 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy2 | LOG | FUN | SI |  | Becker; Ray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-10-09 | 2017-10-09 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073410 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy2 | LOG | FUN | SI |  | Becker; Ray | IBM | Yes | CapEx | Localization | IT - External | 0h | 8h | 8h | 2017-09-22 | 2017-09-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073411 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy2 | LOG | FUN | SI |  | Becker; Ray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-10-09 | 2017-10-13 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073412 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy2 | LOG | FUN | SI |  | Becker; Ray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-29 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073413 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Badoni; Vijay | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073414 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Badoni; Vijay | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-04 | 2017-12-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073415 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Badoni; Vijay | IBM | Yes | CapEx | Localization | IT - External | 0h | 75h | 75h | 2017-10-09 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073416 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Badoni; Vijay | IBM | Yes | CapEx | Localization | IT - External | 0h | 100h | 100h | 2017-12-04 | 2018-01-05 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073417 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Badoni; Vijay | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-10-09 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073418 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Badoni; Vijay | IBM | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2018-02-26 | 2018-03-23 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073419 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Badoni; Vijay | IBM | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2018-01-15 | 2018-01-19 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -5 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073420 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Badoni; Vijay | IBM | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2018-01-01 | 2018-01-05 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -30 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073421 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Support-D2 | OTC | FUN | SI | Onshore | Badoni; Vijay | IBM | Yes | OpEx | Localization | IT - External | 0h | 20h | 20h | 2018-01-22 | 2018-02-02 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-09-18 | 2017-11-03 | 2 | Training Material Localization | 20000 D2-29000 MultiPhases-29040 Training Material Localization | -10 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073422 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Badoni; Vijay | IBM | Yes | CapEx | Localization | IT - External | 132h | 116.87h | 248.87h | 2017-07-10 | 2017-09-25 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 0 | 0 | 0
1073423 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Badoni; Vijay | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-06-19 | 2017-10-06 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-21 | 2017-09-01 | 2 | AT | 20000 D2-20100 B-20180 AT | -45 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073424 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Regression - Manage defects (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Badoni; Vijay | IBM | Yes | CapEx | Localization | IT - External | 0h | 66h | 66h | 2017-11-06 | 2017-11-22 | Yes |  |  | ACT-FUN.Execute Regression Test | Future Task | 2017-12-04 | 2017-12-22 | 2 | Q? Regression | 20000 D2-22000 CG: UAT and Regression-22010 Q? Regression | -20 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073425 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Badoni; Vijay | IBM | Yes | CapEx | Localization | IT - External | 0h | 95h | 95h | 2017-09-11 | 2017-10-06 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | -5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073426 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Badoni; Vijay | IBM | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-10-30 | 2017-11-22 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073427 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Chaturvedi; Himanshu | IBM | Yes | CapEx | Localization | IT - External | 0h | 94h | 94h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073428 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Chaturvedi; Himanshu | IBM | Yes | CapEx | Localization | IT - External | 0h | 15h | 15h | 2017-10-16 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073429 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Chaturvedi; Himanshu | IBM | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-09-25 | 2017-10-13 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073430 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Chaturvedi; Himanshu | IBM | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-09-18 | 2017-10-13 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073431 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Chaturvedi; Himanshu | IBM | Yes | CapEx | Localization | IT - External | 91h | 0h | 91h | 2017-07-17 | 2017-07-28 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073432 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Chaturvedi; Himanshu | IBM | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-07-20 | 2017-08-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 5 | 0 | 16 | 6 | 8 | 0 | 0 | 0
1073433 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Configuration - RTR - Deploy1 | RTR | FUN | SI | Offshore | Chaturvedi; Himanshu | IBM | Yes | CapEx | Localization | IT - External | 41.5h | 12.5h | 54h | 2017-07-03 | 2017-07-20 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | -5 | 43.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 15 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073434 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Unit testing Configuration Documentation - RTR - Deploy1 | RTR | FUN | SI | Offshore | Chaturvedi; Himanshu | IBM | Yes | CapEx | Localization | IT - External | 52.5h | 0h | 52.5h | 2017-07-03 | 2017-07-14 | Yes |  |  | To delete-To delete.To delete | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073435 | No | No | Yes | SDF | SDF Localisation | 04-Test | Regression - Run Tests (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Chaturvedi; Himanshu | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2017-08-07 | 2017-08-22 | Yes |  |  | ACT-FUN.Execute Regression Test | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 9.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0
1073436 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Chaturvedi; Himanshu | IBM | Yes | CapEx | Localization | IT - External | 0h | 15h | 15h | 2017-09-05 | 2017-09-22 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073437 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Chaturvedi; Himanshu | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073438 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Chaturvedi; Himanshu | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073439 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 configuration (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Chaturvedi; Himanshu | IBM | Yes | CapEx | Localization | IT - External | 0h | 2h | 2h | 2017-09-05 | 2017-09-15 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073440 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Enhancement (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Chaturvedi; Himanshu | IBM | Yes | CapEx | Localization | IT - External | 0h | 10h | 10h | 2017-09-05 | 2017-09-15 | Yes |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073441 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 configuration (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Chaturvedi; Himanshu | IBM | Yes | CapEx | Localization | IT - External | 0h | 10h | 10h | 2017-08-14 | 2017-09-15 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | 35 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073442 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Chaturvedi; Himanshu | IBM | Yes | CapEx | Localization | IT - External | 0h | 15h | 15h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073443 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Chaturvedi; Himanshu | IBM | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2017-08-08 | 2017-08-18 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 13.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 8 | 0 | 0 | 0 | 0 | 0
1073444 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Chaturvedi; Himanshu | IBM | Yes | CapEx | Localization | IT - External | 68h | 22h | 90h | 2017-08-07 | 2017-09-07 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 9.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 16 | 22 | 10 | 0 | 0 | 0
1073445 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Chaturvedi; Himanshu | IBM | Yes | CapEx | Localization | IT - External | 12h | 28.67h | 40.67h | 2017-08-30 | 2017-09-15 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0
1073446 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Chaturvedi; Himanshu | IBM | Yes | CapEx | Localization | IT - External | 15h | 4h | 19h | 2017-08-28 | 2017-09-15 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0
1073447 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Chaturvedi; Himanshu | IBM | Yes | CapEx | Localization | IT - External | 0h | 82h | 82h | 2017-09-05 | 2017-09-18 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073448 | No | No | No | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | CDP | CDP | SI | Onshore | Chaudhary; Shubham | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-18 | 2017-08-25 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073449 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Guru; Kiran | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073450 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Guru; Kiran | IBM | Yes | CapEx | Localization | IT - External | 0h | 75h | 75h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073451 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Guru; Kiran | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073452 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Execute FUT | OTC | FUN | SI | Onshore | Guru; Kiran | IBM | Yes | CapEx | Global | IT - External | 69h | 0h | 69h | 2017-06-05 | 2017-07-14 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-08-18 | 0 | NA Others | 99000-99100-99130 NA others | -30 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 14 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073453 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Functional Specification (FSD) | OTC | FUN | SI | Onshore | Guru; Kiran | IBM | Yes | CapEx | Global | IT - External | 103h | 0h | 103h | 2017-06-05 | 2017-08-11 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | 5 | 85.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 10 | 10 | 4 | 13 | 24 | 9 | 0 | 10 | 9 | 0 | 0 | 0 | 0 | 0 | 0
1073454 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Cycle1 Configuration | OTC | FUN | SI | Onshore | Guru; Kiran | IBM | Yes | CapEx | Global | IT - External | 245h | 0h | 245h | 2017-06-05 | 2017-08-18 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 0 | NA Others | 99000-99100-99130 NA others | -15 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 20 | 26 | 0 | 0 | 0 | 35 | 44 | 34 | 32 | 39 | 0 | 0 | 0 | 0 | 0
1073455 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-SIT Test Scenarios/Scripts | OTC | FUN | SI | Onshore | Guru; Kiran | IBM | Yes | CapEx | Global | IT - External | 0h | 32.8h | 32.8h | 2017-07-10 | 2017-08-31 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 0 | NA Others | 99000-99100-99130 NA others | -25 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073456 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Cycle2 Configuration | OTC | FUN | SI | Onshore | Guru; Kiran | IBM | Yes | CapEx | Global | IT - External | 139h | 60h | 199h | 2017-06-26 | 2017-09-29 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 0 | NA Others | 99000-99100-99130 NA others | -20 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 23 | 0 | 0 | 0 | 0 | 3 | 5 | 44 | 44 | 0 | 0 | 0
1073457 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Baseline configuration - OTC | OTC | FUN | SI | Onshore | Guru; Kiran | IBM | Yes | CapEx | Global | IT - External | 80h | 0h | 80h | 2017-05-23 | 2017-06-02 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-06-26 | 2017-07-14 | 0 | NA Others | 99000-99100-99130 NA others | -30 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073458 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-Gap Resolution-Global | OTC | FUN | SI | Onshore | Guru; Kiran | IBM | Yes | CapEx | Global | IT - External | 18.25h | 0h | 18.25h | 2017-03-22 | 2017-04-28 | Yes |  |  | WP-FUN.Gap Definition | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.25 | 5 | 3 | 0 | 1 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073459 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-Global Trade scope / Solution validation-OTC | OTC | FUN | SI | Onshore | Guru; Kiran | IBM | Yes | CapEx | Global | IT - External | 7h | 0h | 7h | 2017-04-24 | 2017-04-28 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073460 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-RTM-Global Trade-OTC | OTC | FUN | SI | Onshore | Guru; Kiran | IBM | Yes | CapEx | Global | IT - External | 83.87h | 0h | 83.87h | 2017-03-20 | 2017-04-28 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.25 | 16.78 | 10.83 | 27 | 10 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073461 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | PDD-FS Trade Promotion Execution - TPM-OTC | OTC | FUN | SI | Onshore | Guru; Kiran | IBM | Yes | CapEx | Global | IT - External | 15.1h | 0h | 15.1h | 2017-03-22 | 2017-04-21 | Yes |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 3.75 | 5.85 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073462 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | PDD-FS Settlements & Claim Reconcilation - TPM-OTC | OTC | FUN | SI | Onshore | Guru; Kiran | IBM | Yes | CapEx | Global | IT - External | 22.25h | 0h | 22.25h | 2017-03-22 | 2017-04-28 | Yes |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 3.75 | 5 | 1 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073463 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | PDD-FS Trade Master Data - TPM-OTC | OTC | FUN | SI | Onshore | Guru; Kiran | IBM | Yes | CapEx | Global | IT - External | 16.32h | 0h | 16.32h | 2017-03-22 | 2017-04-28 | Yes |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 2.82 | 5 | 1 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073464 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-PDDs | OTC | FUN | SI | Onshore | Guru; Kiran | IBM | Yes | CapEx | Global | IT - External | 132h | 0h | 132h | 2017-05-01 | 2017-05-19 | Yes |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073465 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-Fit-Gap-Global | OTC | FUN | SI | Onshore | Guru; Kiran | IBM | Yes | CapEx | Global | IT - External | 85.17h | 0h | 85.17h | 2017-03-13 | 2017-04-27 | Yes |  |  | WP-FUN.Gap Definition | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.5 | 7.67 | 8 | 12 | 27 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073466 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | PDD-FS Trade Promotion Planning - TPM-OTC | OTC | FUN | SI | Onshore | Guru; Kiran | IBM | Yes | CapEx | Global | IT - External | 16.07h | 0h | 16.07h | 2017-03-23 | 2017-04-21 | Yes |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 4.25 | 6.32 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073467 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 configuration (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Guru; Kiran | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-09-05 | 2017-09-29 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073468 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | TPM Unit testing Development Documentation (FUT) | OTC | FUN | SI | Onshore | Guru; Kiran | IBM | Yes | CapEx | Global | IT - External | 0h | 40h | 40h | 2017-05-29 | 2017-09-29 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073469 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Functional Specification (FSD) | OTC | FUN | SI | Onshore | Guru; Kiran | IBM | Yes | CapEx | Global | IT - External | 0h | 10h | 10h | 2017-05-29 | 2017-09-08 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073470 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Guru; Kiran | IBM | Yes | CapEx | Localization | IT - External | 0h | 55h | 55h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | -5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073471 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Guru; Kiran | IBM | Yes | CapEx | Localization | IT - External | 0h | 10h | 10h | 2017-09-05 | 2017-09-15 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 10 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073472 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Dvn; Satya | IBM | Yes | CapEx | Localization | IT - External | 49h | 0h | 49h | 2017-08-07 | 2017-08-23 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 4 | 20 | 0 | 0 | 0 | 0
1073473 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Dvn; Satya | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-07-31 | 2017-08-04 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073474 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing WRICEFs (Design/Build) | DEV | DEV | SI | Offshore | Dvn; Satya | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-01-11 | 2017-11-03 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -88 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073475 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | SI | Offshore | Dvn; Satya | IBM | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-08-28 | 2017-09-14 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 35 | 30 | 0
1073476 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | SI | Offshore | Dvn; Satya | IBM | Yes | CapEx | Localization | IT - External | 88h | 57h | 145h | 2017-08-07 | 2017-09-15 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 32 | 16 | 20 | 0 | 0 | 0
1073477 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy1 (Design/Build) | DEV | DEV | SI | Offshore | Dvn; Satya | IBM | Yes | CapEx | Localization | IT - External | 60h | 0h | 60h | 2017-07-13 | 2017-07-28 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 15 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073478 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Dvn; Satya | IBM | Yes | CapEx | Localization | IT - External | 0h | 145h | 145h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073479 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | SI | Offshore | Dvn; Satya | IBM | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073480 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Dvn; Satya | IBM | Yes | CapEx | Localization | IT - External | 0h | 115h | 115h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073481 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | SI | Offshore | Dvn; Satya | IBM | Yes | CapEx | Localization | IT - External | 476h | 25h | 501h | 2017-02-13 | 2017-10-20 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 36 | 35 | 18 | 25 | 36 | 45 | 45 | 45 | 36 | 40 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 15 | 0
1073482 | No | No | Yes | SDF | SDF Localisation | 04-Test | Communication Plan (Test) | CM | CM | SI | Onshore | Brown; Genevieve | Other | Yes | OpEx | Localization | IT - External | 175.75h | 0h | 175.75h | 2017-07-17 | 2017-08-25 | Yes |  |  | DELIV-CM-106.Communication Plan | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 33 | 21 | 30 | 31.25 | 27.5 | 0 | 0 | 0 | 0
1073483 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Communication Plan (Cutover/Go-live) - Deploy1 | CM | CM | SI | Onshore | Brown; Genevieve | Other | Yes | OpEx | Localization | IT - External | 81h | 50h | 131h | 2017-08-28 | 2017-09-29 | Yes |  |  | DELIV-CM-106.Communication Plan | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 27 | 27 | 0
1073484 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | Communication plan execution and monitoring | CM | CM | SI | Onshore | Brown; Genevieve | Other | Yes | OpEx | Localization | IT - External | 0h | 225h | 225h | 2017-10-02 | 2017-12-01 | Yes |  |  | ACT-CM.Communication plan execution and monitoring | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073485 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Communication Plan (Preparation) | CM | CM | SI | Onshore | Brown; Genevieve | Other | Yes | OpEx | Localization | IT - External | 29.75h | 0h | 29.75h | 2017-03-28 | 2017-04-07 | Yes |  |  | DELIV-CM-106.Communication Plan | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 19.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073486 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Communication Plan (Analyze) | CM | CM | SI | Onshore | Brown; Genevieve | Other | Yes | OpEx | Localization | IT - External | 171.75h | 0h | 171.75h | 2017-04-10 | 2017-06-02 | Yes |  |  | DELIV-CM-106.Communication Plan | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.5 | 16 | 18.5 | 2 | 30.25 | 27.5 | 21.5 | 29.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073487 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Communication Plan (Design/Build) | CM | CM | SI | Onshore | Brown; Genevieve | Other | Yes | OpEx | Localization | IT - External | 91.75h | 0h | 91.75h | 2017-06-05 | 2017-06-30 | Yes |  |  | DELIV-CM-106.Communication Plan | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.75 | 28 | 19 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073488 | No | No | Yes | SDF | SDF Localisation | 04-Test | Performance Test Scripts | TAI | TAI | SI | Onshore | Medina; Fernando | Accenture | Yes | CapEx | Localization | IT - External | 117h | 160h | 277h | 2017-08-07 | 2017-09-29 | Yes |  |  | DELIV-TST-302.Performance Test Scripts | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 27 | 0 | 0 | 0
1073489 | No | No | Yes | SDF | SDF Localisation | 04-Test | Transition Plan Execution & Monitoring (Test) | CM | CM | SI | Onshore | Elliot; Scott | Other | Yes | OpEx | Localization | IT - External | 192h | 40h | 232h | 2017-07-17 | 2017-09-29 | Yes |  |  | ACT-CM.Transition Plan Execution & Monitoring | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 40 | 40 | 32 | 40 | 0
1073490 | No | No | Yes | SDF | SDF Localisation | 99-Global | Role Mapping (Test) | CM | CM | SI | Onshore | Elliot; Scott | Other | Yes | OpEx | Localization | IT - External | 24h | 76h | 100h | 2017-07-17 | 2017-09-29 | Yes |  |  | DELIV-CM-218.Role Mapping | Future Task | 2017-05-29 | 2017-06-23 | 1 | Role Mapping | 1000 D1-1800 MultiPhases-1810 Role Mapping | 35 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073491 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Enhancement (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Biswas; Kapil | IBM | Yes | CapEx | Localization | IT - External | 0h | 220h | 220h | 2017-09-05 | 2017-10-13 | Yes |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073492 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Form (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Biswas; Kapil | IBM | Yes | CapEx | Localization | IT - External | 132h | 44h | 176h | 2017-08-14 | 2017-09-05 | Yes |  |  | DELIV-FUN-204.Functional Specification - Form | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 0 | 0 | 0
1073493 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Form (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Shanmugam; Raja | IBM | Yes | CapEx | Localization | IT - External | 132h | 44h | 176h | 2017-08-14 | 2017-09-12 | Yes |  |  | DELIV-FUN-204.Functional Specification - Form | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 0 | 0 | 0
1073494 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Enhancement (RTR) - Deploy2 | RTR | FUN | SI | Onshore | Shanmugam; Raja | IBM | Yes | CapEx | Localization | IT - External | 0h | 220h | 220h | 2017-09-05 | 2017-10-13 | Yes |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073495 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Dobriyal; Raveesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073496 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Dobriyal; Raveesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-08-07 | 2017-08-25 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073497 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | SI | Offshore | Dobriyal; Raveesh | IBM | Yes | CapEx | Localization | IT - External | 8h | 12h | 20h | 2016-12-28 | 2017-08-07 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073498 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy1 (Design/Build) | DEV | DEV | SI | Offshore | Dobriyal; Raveesh | IBM | Yes | CapEx | Localization | IT - External | 306h | 0h | 306h | 2017-06-05 | 2017-07-28 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 36 | 45 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073499 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | SI | Offshore | Dobriyal; Raveesh | IBM | Yes | CapEx | Localization | IT - External | 235h | 64h | 299h | 2017-07-10 | 2017-09-15 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 37 | 36 | 36 | 36 | 45 | 0 | 0 | 0
1073500 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | SI | Offshore | Dobriyal; Raveesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2017-08-28 | 2017-09-29 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073501 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | SI | Offshore | Saran; Chitranjan | IBM | Yes | CapEx | Localization | IT - External | 0h | 35h | 35h | 2017-08-28 | 2017-09-29 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073502 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | SI | Offshore | Saran; Chitranjan | IBM | Yes | CapEx | Localization | IT - External | 346h | 0h | 346h | 2017-07-17 | 2017-09-15 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 27 | 31 | 27 | 36 | 45 | 45 | 0
1073503 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | SI | Offshore | Saran; Chitranjan | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073504 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | SI | Offshore | Saran; Chitranjan | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2016-12-28 | 2017-10-31 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073505 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing WRICEFs (Design/Build) | DEV | DEV | SI | Offshore | Saran; Chitranjan | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-01-11 | 2017-11-03 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -88 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073506 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Saran; Chitranjan | IBM | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073507 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Saran; Chitranjan | IBM | Yes | CapEx | Localization | IT - External | 0h | 135h | 135h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073508 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Saran; Chitranjan | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-08-07 | 2017-08-25 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073509 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Saran; Chitranjan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073510 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy1 (Design/Build) | DEV | DEV | SI | Offshore | Saran; Chitranjan | IBM | Yes | CapEx | Localization | IT - External | 216h | 0h | 216h | 2017-06-09 | 2017-07-14 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 45 | 36 | 36 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073511 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Iyappan; Balasubramanian | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073512 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Iyappan; Balasubramanian | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-08-07 | 2017-08-25 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073513 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Iyappan; Balasubramanian | IBM | Yes | CapEx | Localization | IT - External | 0h | 135h | 135h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073514 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Iyappan; Balasubramanian | IBM | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2017-10-09 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073515 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | SI | Offshore | Iyappan; Balasubramanian | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073516 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | SI | Offshore | Iyappan; Balasubramanian | IBM | Yes | CapEx | Localization | IT - External | 435h | 0h | 435h | 2017-07-03 | 2017-09-15 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 36 | 40 | 45 | 27 | 45 | 36 | 36 | 45 | 45 | 45 | 0
1073517 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | SI | Offshore | Iyappan; Balasubramanian | IBM | Yes | CapEx | Localization | IT - External | 0h | 35h | 35h | 2017-08-28 | 2017-09-28 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073518 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing WRICEFs (Design/Build) | DEV | DEV | SI | Offshore | Iyappan; Balasubramanian | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-01-11 | 2017-11-03 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -88 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073519 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | SI | Offshore | Iyappan; Balasubramanian | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2016-12-28 | 2017-10-31 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073520 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy1 (Design/Build) | DEV | DEV | SI | Offshore | Iyappan; Balasubramanian | IBM | Yes | CapEx | Localization | IT - External | 195h | 0h | 195h | 2017-06-05 | 2017-07-17 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 36 | 10 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073521 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (RTR) - Deploy1 | LOG | FUN | SI | Offshore | Kumar; Arun | IBM | Yes | CapEx | Localization | IT - External | 225h | 0h | 225h | 2017-07-03 | 2017-08-04 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | -14 | 72.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073522 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 configuration (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Kumar; Arun | IBM | Yes | CapEx | Localization | IT - External | 207h | 0h | 207h | 2017-08-14 | 2017-09-15 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 36 | 45 | 45 | 45 | 0
1073523 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Support Mock1 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Kumar; Arun | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-08-21 | 2017-09-01 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-09-25 | 2017-10-06 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -25 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073524 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Kumar; Arun | IBM | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-08-14 | 2017-08-18 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073525 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Kumar; Arun | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-08-07 | 2017-08-11 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 4.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073526 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Support (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Kumar; Arun | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073527 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Kumar; Arun | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-07-17 | 2017-08-11 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0
1073528 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Kumar; Arun | IBM | Yes | CapEx | Localization | IT - External | 0h | 75h | 75h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073529 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Kumar; Arun | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073530 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Kumar; Arun | IBM | Yes | CapEx | Localization | IT - External | 0h | 75h | 75h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073531 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Kumar; Arun | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073532 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy2 | DEV | DEV | SI | Offshore | Dhanik; Piyush | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-10-09 | 2017-10-09 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073533 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing WRICEFs (Design/Build) | DEV | DEV | SI | Offshore | Dhanik; Piyush | IBM | Yes | CapEx | Localization | IT - External | 105h | 65h | 170h | 2017-02-13 | 2017-11-03 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -88 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073534 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | SI | Offshore | Dhanik; Piyush | IBM | Yes | CapEx | Localization | IT - External | 336.7h | 34h | 370.7h | 2017-02-13 | 2017-10-11 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 27 | 7.2 | 31 | 41 | 40.5 | 23 | 0 | 0 | 20 | 0 | 12 | 9 | 9 | 8 | 0 | 0 | 5 | 0 | 5 | 27 | 27
1073535 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | SI | Offshore | Dhanik; Piyush | IBM | Yes | CapEx | Localization | IT - External | 0h | 35h | 35h | 2017-08-28 | 2017-09-29 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073536 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy1 (Design/Build) | DEV | DEV | SI | Offshore | Dhanik; Piyush | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073537 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | SI | Offshore | Dhanik; Piyush | IBM | Yes | CapEx | Localization | IT - External | 270h | 4h | 274h | 2017-07-21 | 2017-09-25 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 37 | 45 | 36 | 22 | 36 | 31 | 18 | 18
1073538 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | SI | Offshore | Dhanik; Piyush | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073539 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Dhanik; Piyush | IBM | Yes | CapEx | Localization | IT - External | 0h | 120h | 120h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073540 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Dhanik; Piyush | IBM | Yes | CapEx | Localization | IT - External | 0h | 125h | 125h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073541 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Dhanik; Piyush | IBM | Yes | CapEx | Localization | IT - External | 9h | 21h | 30h | 2017-09-06 | 2017-09-26 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0
1073542 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Dhanik; Piyush | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073543 | No | No | Yes | SDF | SDF Interim State Project | 02-Analyze | Analyze | DEV | DEV | SI | Offshore | Dhanik; Piyush | IBM | Yes |  |  | IT - External | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | Yes |  |  |  |  | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073544 | No | Yes | No | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | SI | Offshore | Nandy; Debanjali | IBM | Yes | CapEx | Localization | IT - External | 70h | 0h | 70h | 2017-02-13 | 2017-05-30 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 18 | 0 | 1 | 1 | 22 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073545 | No | Yes | No | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing WRICEFs (Design/Build) | DEV | DEV | SI | Offshore | Nandy; Debanjali | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-11 | 2017-01-11 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -88 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073546 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-PDDs | OTC | FUN | SI | Offshore | Gattani; Praveen | IBM | Yes | CapEx | Global | IT - External | 126h | 0h | 126h | 2017-05-02 | 2017-05-19 | Yes |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073547 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-Fit-Gap-Global | OTC | FUN | SI | Offshore | Gattani; Praveen | IBM | Yes | CapEx | Global | IT - External | 50h | 0h | 50h | 2017-03-13 | 2017-03-31 | Yes |  |  | WP-FUN.Gap Definition | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073548 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-RTM-Global Trade-OTC | OTC | FUN | SI | Offshore | Gattani; Praveen | IBM | Yes | CapEx | Global | IT - External | 50h | 0h | 50h | 2017-04-03 | 2017-04-21 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073549 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-Global Trade scope / Solution validation-OTC | OTC | FUN | SI | Offshore | Gattani; Praveen | IBM | Yes | CapEx | Global | IT - External | 10h | 0h | 10h | 2017-04-24 | 2017-04-28 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073550 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-Gap Resolution-Global | OTC | FUN | SI | Offshore | Gattani; Praveen | IBM | Yes | CapEx | Global | IT - External | 20h | 0h | 20h | 2017-03-20 | 2017-03-24 | Yes |  |  | WP-FUN.Gap Definition | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073551 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | PDD-FS Trade Promotion Planning - TPM-OTC | OTC | FUN | SI | Offshore | Gattani; Praveen | IBM | Yes | CapEx | Global | IT - External | 30h | 0h | 30h | 2017-04-03 | 2017-04-21 | Yes |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073552 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | PDD-FS Trade Promotion Execution - TPM-OTC | OTC | FUN | SI | Offshore | Gattani; Praveen | IBM | Yes | CapEx | Global | IT - External | 35h | 0h | 35h | 2017-03-27 | 2017-04-07 | Yes |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073553 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | PDD-FS Settlements & Claim Reconcilation - TPM-OTC | OTC | FUN | SI | Offshore | Gattani; Praveen | IBM | Yes | CapEx | Global | IT - External | 45h | 0h | 45h | 2017-03-27 | 2017-04-28 | Yes |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073554 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | PDD-FS Trade Master Data - TPM-OTC | OTC | FUN | SI | Offshore | Gattani; Praveen | IBM | Yes | CapEx | Global | IT - External | 30h | 0h | 30h | 2017-04-03 | 2017-04-21 | Yes |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073555 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Baseline configuration - OTC | OTC | FUN | SI | Offshore | Gattani; Praveen | IBM | Yes | CapEx | Global | IT - External | 90h | 0h | 90h | 2017-05-22 | 2017-06-02 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-06-26 | 2017-07-14 | 0 | NA Others | 99000-99100-99130 NA others | -30 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073556 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Cycle1 Configuration | OTC | FUN | SI | Offshore | Gattani; Praveen | IBM | Yes | CapEx | Global | IT - External | 125h | 30h | 155h | 2017-06-05 | 2017-10-20 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 0 | NA Others | 99000-99100-99130 NA others | -15 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 10 | 20 | 25 | 0 | 15 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073557 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-SIT Test Scenarios/Scripts | OTC | FUN | SI | Offshore | Gattani; Praveen | IBM | Yes | CapEx | Global | IT - External | 76h | 154h | 230h | 2017-07-10 | 2017-11-03 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 0 | NA Others | 99000-99100-99130 NA others | -25 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 20 | 16 | 20 | 0 | 0 | 0 | 0
1073558 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Cycle2 Configuration | OTC | FUN | SI | Offshore | Gattani; Praveen | IBM | Yes | CapEx | Global | IT - External | 44h | 60h | 104h | 2017-07-10 | 2017-10-06 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 0 | NA Others | 99000-99100-99130 NA others | -20 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 4 | 15 | 0 | 0 | 0
1073559 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Functional Specification (FSD) | OTC | FUN | SI | Offshore | Gattani; Praveen | IBM | Yes | CapEx | Global | IT - External | 246h | 110h | 356h | 2017-06-05 | 2017-10-20 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | 5 | 85.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 25 | 15 | 4 | 20 | 0 | 20 | 25 | 25 | 20 | 20 | 12 | 30 | 0 | 0 | 0
1073560 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Execute FUT | OTC | FUN | SI | Offshore | Gattani; Praveen | IBM | Yes | CapEx | Global | IT - External | 30h | 60h | 90h | 2017-06-12 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-08-18 | 0 | NA Others | 99000-99100-99130 NA others | -30 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073561 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Shukla; Keyur | IBM | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-09-25 | 2017-09-29 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073562 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Shukla; Keyur | IBM | Yes | CapEx | Localization | IT - External | 0h | 100h | 100h | 2017-10-02 | 2017-11-06 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073563 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Shukla; Keyur | IBM | Yes | CapEx | Localization | IT - External | 0h | 65h | 65h | 2017-09-05 | 2017-10-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073564 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Shukla; Keyur | IBM | Yes | CapEx | Localization | IT - External | 0h | 125h | 125h | 2017-09-25 | 2017-10-30 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073565 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Shukla; Keyur | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-09-05 | 2017-10-02 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 15 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073566 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Shukla; Keyur | IBM | Yes | CapEx | Localization | IT - External | 0h | 65h | 65h | 2017-08-28 | 2017-09-25 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073567 | No | Yes | No | SDF | SDF Localisation | 04-Test | Mock2 - Prepare (LOG) - Deploy1 | PTM | FUN | SI | Offshore | Patil; Pralhad | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073568 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Execute FUT (LOG) - Deploy2 | PTM | FUN | SI | Offshore | Patil; Pralhad | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-18 | 2017-08-18 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | -8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073569 | No | Yes | No | SDF | SDF Localisation | 04-Test | Mock2 - Support (LOG) - Deploy1 | PTM | FUN | SI | Offshore | Patil; Pralhad | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073570 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Chougule; Vinay | IBM | Yes | CapEx | Localization | IT - External | 0h | 10h | 10h | 2017-09-25 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073571 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Chougule; Vinay | IBM | Yes | CapEx | Localization | IT - External | 43h | 17h | 60h | 2017-07-26 | 2017-08-09 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073572 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Chougule; Vinay | IBM | Yes | CapEx | Localization | IT - External | 1h | 59h | 60h | 2017-08-10 | 2017-08-30 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 17.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
1073573 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Chougule; Vinay | IBM | Yes | CapEx | Localization | IT - External | 0h | 55h | 55h | 2017-08-28 | 2017-09-15 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073574 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Chougule; Vinay | IBM | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-07-03 | 2017-07-14 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | 5 | 29.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073575 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Chougule; Vinay | IBM | Yes | CapEx | Localization | IT - External | 97h | 0h | 97h | 2017-07-17 | 2017-07-28 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073576 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Chougule; Vinay | IBM | Yes | CapEx | Localization | IT - External | 0h | 41h | 41h | 2017-08-28 | 2017-09-08 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073577 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Chougule; Vinay | IBM | Yes | CapEx | Localization | IT - External | 119h | 0h | 119h | 2017-08-07 | 2017-08-24 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 30 | 40 | 0 | 0 | 0 | 0
1073578 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Chougule; Vinay | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-09-05 | 2017-09-22 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 15 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073579 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Chougule; Vinay | IBM | Yes | CapEx | Localization | IT - External | 0h | 129h | 129h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073580 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Chougule; Vinay | IBM | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073581 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Singh; Menam | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073582 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Singh; Menam | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-08-07 | 2017-08-25 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073583 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | SI | Offshore | Singh; Menam | IBM | Yes | CapEx | Localization | IT - External | 0h | 175h | 175h | 2017-07-31 | 2017-08-31 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073584 | No | No | Yes | SDF | SDF Localisation | 04-Test | SEC Break/Fix SIT2 - SEC Deploy2 | SEC | SEC | Saputo | Onshore | Sidhu; Steven | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-10-10 | 2017-10-27 | Yes |  |  |  | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073585 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF Build/Support (SEC) - Deploy1 | SEC | SEC | Saputo | Onshore | Sidhu; Steven | Saputo | Yes | CapEx | Localization | IT - Internal | 46h | 0h | 46h | 2017-07-17 | 2017-07-21 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-05 | 2017-06-23 | 1 | Security Build | 1000 D1-1300 B-1335 Security Build | 20 | 86.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073586 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | Ansari; MuhammadAkber | Saputo | Yes | CapEx | Localization | IT - Internal | 10h | 80h | 90h | 2017-08-28 | 2017-09-11 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | -5 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0
1073587 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover Prepare - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | Ansari; MuhammadAkber | Saputo | Yes | OpEx | Localization | IT - Internal | 10h | 30h | 40h | 2017-08-28 | 2017-09-11 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -15 | -8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0
1073588 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT 1-Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Ansari; MuhammadAkber | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 30h | 30h | 2017-09-18 | 2017-10-06 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073589 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT 2-Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Ansari; MuhammadAkber | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 30h | 30h | 2017-10-10 | 2017-10-27 | Yes |  |  |  | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073590 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover Prepare - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Ansari; MuhammadAkber | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 80h | 80h | 2018-02-19 | 2018-03-02 | Yes |  |  |  | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -95 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073591 | No | No | Yes | SDF | SDF Localisation | 04-Test | Regression Testing - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Ansari; MuhammadAkber | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 30h | 30h | 2017-11-06 | 2017-11-24 | Yes |  |  |  | Future Task | 2017-11-06 | 2017-11-24 | 2 | D2 Regression (in QE2) | 20000 D2-21000 T-21054 D2 Regression (in QE2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073592 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Ansari; MuhammadAkber | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 120h | 120h | 2017-12-04 | 2017-12-22 | Yes |  |  |  | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | -25 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073593 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover Suport - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Ansari; MuhammadAkber | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 240h | 240h | 2018-01-08 | 2018-02-16 | Yes |  |  |  | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073594 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | Hypercare-Provide end User Support - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Ansari; MuhammadAkber | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 320h | 320h | 2018-02-05 | 2018-03-30 | Yes |  |  |  | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073595 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT 2-Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | Ansari; MuhammadAkber | Saputo | Yes | OpEx | Localization | IT - Internal | 45h | 0h | 45h | 2017-08-21 | 2017-09-01 | Yes |  |  |  | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 5 | 6.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 5 | 0 | 0 | 0
1073596 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover Suport - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | Ansari; MuhammadAkber | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 40h | 40h | 2017-09-18 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073597 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | Hypercare-Provide end User Support - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | Ansari; MuhammadAkber | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 360h | 360h | 2017-10-02 | 2017-12-01 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073598 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | FUT - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | Ansari; MuhammadAkber | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 20h | 20h | 2017-09-05 | 2017-09-15 | Yes |  |  |  | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 35 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073599 | No | No | Yes | SDF | SDF Localisation | 99-Global | Project Support | SEC | SEC | SI | Offshore | DeGuzman; Patricia | Accenture | Yes | CapEx | Localization | IT - External | 54h | 126h | 180h | 2017-08-21 | 2017-09-26 | Yes |  |  |  | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 18 | 0 | 0 | 0
1073600 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Baroni; Adriano | Accenture | Yes | CapEx | Localization | IT - External | 30h | 0h | 30h | 2017-07-31 | 2017-08-23 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 10 | 5 | 0 | 0 | 0 | 0
1073601 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Baroni; Adriano | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-07-31 | 2017-09-11 | Yes |  |  | ACT-MDG.Mock Load | Complete | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 10.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 5 | 5 | 8 | 4 | 3 | 0
1073602 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Baroni; Adriano | Accenture | Yes | CapEx | Localization | IT - External | 50.5h | 0h | 50.5h | 2017-07-31 | 2017-09-15 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 5 | 7.5 | 7 | 11 | 5 | 0
1073603 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Baroni; Adriano | Accenture | Yes | CapEx | Localization | IT - External | 56h | 0h | 56h | 2017-07-31 | 2017-09-15 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 5 | 12 | 7 | 7 | 10 | 0
1073604 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Baroni; Adriano | Accenture | Yes | CapEx | Localization | IT - External | 5h | 10h | 15h | 2017-09-11 | 2017-09-26 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0
1073605 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Baroni; Adriano | Accenture | Yes | CapEx | Localization | IT - External | 4h | 11h | 15h | 2017-09-12 | 2017-09-28 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
1073606 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Baroni; Adriano | Accenture | Yes | CapEx | Localization | IT - External | 5h | 10h | 15h | 2017-09-11 | 2017-09-26 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0
1073607 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Baroni; Adriano | Accenture | Yes | CapEx | Localization | IT - External | 8h | 11h | 19h | 2017-09-12 | 2017-09-28 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0
1073608 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy1 - HC - (Accenture) - DC | MDG | DC | SI | Onshore | Baroni; Adriano | Accenture | Yes | CapEx | Localization | IT - External | 0h | 1h | 1h | 2017-10-02 | 2017-10-06 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -21.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073609 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Onshore | Baroni; Adriano | Accenture | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-08-07 | 2017-08-11 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-07-31 | 2017-08-11 | 2 | QE2 Mock Prep | 20000 D2-20100 B-20110 QE2 Mock Prep | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0
1073610 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Baroni; Adriano | Accenture | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-08-07 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 3.5 | 1.5 | 5 | 0 | 0
1073611 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Baroni; Adriano | Accenture | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-08-07 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 3.5 | 1.5 | 5 | 0 | 0
1073612 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Baroni; Adriano | Accenture | Yes | CapEx | Localization | IT - External | 16.5h | 0h | 16.5h | 2017-08-07 | 2017-08-30 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 14.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 3.5 | 3 | 0 | 0 | 0
1073613 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Onshore | Baroni; Adriano | Accenture | Yes | CapEx | Localization | IT - External | 0h | 55h | 55h | 2017-09-25 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073614 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Baroni; Adriano | Accenture | Yes | CapEx | Localization | IT - External | 0h | 65h | 65h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073615 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Baroni; Adriano | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073616 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Baroni; Adriano | Accenture | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-09-25 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073617 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Baroni; Adriano | Accenture | Yes | CapEx | Localization | IT - External | 0h | 55h | 55h | 2017-10-30 | 2017-12-07 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 0 | 18.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073618 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Baroni; Adriano | Accenture | Yes | CapEx | Localization | IT - External | 0h | 65h | 65h | 2017-10-30 | 2017-12-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073619 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Baroni; Adriano | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -4.88 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073620 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Baroni; Adriano | Accenture | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-11-03 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -50 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073621 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Baroni; Adriano | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-22 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073622 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Baroni; Adriano | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073623 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Baroni; Adriano | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073624 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Baroni; Adriano | Accenture | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073625 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy2 - HC - (Accenture) - DC | MDG | DC | SI | Onshore | Baroni; Adriano | Accenture | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2018-02-05 | 2018-03-07 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | -17.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073626 | No | No | Yes | SDF | SDF Localisation | 04-Test | Performance Test Scripts | TAI | TAI | SI | Onshore | Kolathur; Gopinath | Accenture | Yes | CapEx | Localization | IT - External | 104h | 200h | 304h | 2017-08-09 | 2017-09-29 | Yes |  |  | DELIV-TST-302.Performance Test Scripts | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 40 | 40 | 0 | 0 | 0 | 0
1073627 | No | Yes | No | SDF | SDF Localisation | 99-Global | Deliver Training to End Users | CM | CM | SI | Onshore | Candy; Paul | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | Yes |  |  | ACT-CM.Deliver Training to End Users | Future Task | 2017-07-31 | 2017-09-22 | 1 | End User Training | 1000 D1-1800 MultiPhases-1850 End User Training | 45 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073628 | No | Yes | No | SDF | SDF Localisation | 99-Global | Training Materials-Traininng Data (exercise book) (Design/Build) | CM | CM | SI | Onshore | Candy; Paul | IBM | Yes | OpEx | Localization | IT - External | 2h | 0h | 2h | 2017-07-24 | 2017-07-25 | Yes |  |  | DELIV-CM-401.Training Materials | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 20 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073629 | No | Yes | No | SDF | SDF Localisation | 99-Global | Create Training Data in trg environment | CM | CM | SI | Onshore | Candy; Paul | IBM | Yes | OpEx | Localization | IT - External | 23h | 0h | 23h | 2017-06-14 | 2017-08-11 | Yes |  |  | DELIV-CM-402.Training Schedule and Logistics | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 12 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 3 | 8 | 1 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
1073630 | No | Yes | No | SDF | SDF Localisation | 99-Global | Onboard DTC | CM | CM | SI | Onshore | Candy; Paul | IBM | Yes | OpEx | Localization | IT - External | 5.5h | 0h | 5.5h | 2017-04-18 | 2017-08-10 | Yes |  |  | ACT-CM.Management | Future Task | 2017-06-26 | 2017-07-28 | 1 | Training Schedule | 1000 D1-1800 MultiPhases-1820 Training Schedule | -65 | 9.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0
1073631 | No | Yes | No | SDF | SDF Localisation | 99-Global | Training Materials-Work Instructions/Job aids (Design/Build) | CM | CM | SI | Onshore | Candy; Paul | IBM | Yes | OpEx | Localization | IT - External | 279.5h | 0h | 279.5h | 2017-06-12 | 2017-08-11 | Yes |  |  | DELIV-CM-451.Work Instructions | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 10 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 42 | 0 | 33 | 36 | 35 | 34 | 33 | 27.5 | 0 | 0 | 0 | 0 | 0 | 0
1073632 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Patil; Sanjay | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-21 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073633 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Patil; Sanjay | IBM | Yes | CapEx | Localization | IT - External | 84h | 0h | 84h | 2017-07-31 | 2017-09-08 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 20 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 20 | 0 | 16 | 0 | 25 | 0 | 0
1073634 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Patil; Sanjay | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2017-07-07 | 2017-08-11 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-19 | 2017-06-30 | 1 | Cycle 2 Config | 1000 D1-1300 B-1318 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073635 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Patil; Sanjay | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2017-07-07 | 2017-08-11 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073636 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Patil; Sanjay | IBM | Yes | CapEx | Localization | IT - External | 24h | 36h | 60h | 2017-09-04 | 2017-09-21 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 5 | 33.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 20 | 0
1073637 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Patil; Sanjay | IBM | Yes | CapEx | Localization | IT - External | 60h | 0h | 60h | 2017-07-31 | 2017-08-11 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 5 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0
1073638 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Patil; Sanjay | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-08-28 | 2017-09-01 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0
1073639 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Patil; Sanjay | IBM | Yes | CapEx | Localization | IT - External | 51h | 0h | 51h | 2017-08-14 | 2017-08-24 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 4.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 24 | 0 | 0 | 0 | 0
1073640 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Patil; Sanjay | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073641 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 configuration (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Patil; Sanjay | IBM | Yes | CapEx | Localization | IT - External | 0h | 10h | 10h | 2017-08-11 | 2017-08-18 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073642 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Report (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Patil; Sanjay | IBM | Yes | CapEx | Localization | IT - External | 22h | 0h | 22h | 2017-08-14 | 2017-08-18 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 55 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0
1073643 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Patil; Sanjay | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-10-13 | 2017-10-13 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073644 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Patil; Sanjay | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073645 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Support Mock1 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Patil; Sanjay | IBM | Yes | CapEx | Localization | IT - External | 0h | 85h | 85h | 2017-08-25 | 2017-09-15 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-09-25 | 2017-10-06 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -25 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073646 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Patil; Sanjay | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-10-09 | 2017-10-09 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073647 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Patil; Sanjay | IBM | Yes | CapEx | Localization | IT - External | 66h | 0h | 66h | 2017-08-28 | 2017-09-15 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | -8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 20 | 16 | 0
1073648 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Patil; Sanjay | IBM | Yes | CapEx | Localization | IT - External | 0h | 260h | 260h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073649 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Patil; Sanjay | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-01 | 2017-09-01 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 10 | 16.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073650 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | ILOG012-DEV FUT-INT-STO interface | LOG | FUN | SI | Offshore | Patil; Sanjay | IBM | Yes | CapEx | Localization | IT - External | 77h | 0h | 77h | 2017-06-23 | 2017-07-27 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-08-18 | 0 | NA Others | 99000-99100-99130 NA others | -15.88 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 20 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073651 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Cycle1 Configuration | OTC | FUN | SI | Offshore | Munagala; Praveen | IBM | Yes | CapEx | Global | IT - External | 210h | 0h | 210h | 2017-06-05 | 2017-07-28 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 0 | NA Others | 99000-99100-99130 NA others | -15 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 45 | 0 | 0 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073652 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Cycle2 Configuration | OTC | FUN | SI | Offshore | Munagala; Praveen | IBM | Yes | CapEx | Global | IT - External | 153h | 0h | 153h | 2017-06-29 | 2017-08-11 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 0 | NA Others | 99000-99100-99130 NA others | -20 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 45 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0
1073653 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-SIT Test Scenarios/Scripts | OTC | FUN | SI | Offshore | Munagala; Praveen | IBM | Yes | CapEx | Global | IT - External | 117h | 90h | 207h | 2017-08-14 | 2017-11-03 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 0 | NA Others | 99000-99100-99130 NA others | -25 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 36 | 45 | 0 | 0 | 0
1073654 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Functional Specification (FSD) | OTC | FUN | SI | Offshore | Munagala; Praveen | IBM | Yes | CapEx | Global | IT - External | 65h | 30h | 95h | 2017-06-05 | 2017-09-29 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | 5 | 85.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0
1073655 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Execute FUT | OTC | FUN | SI | Offshore | Munagala; Praveen | IBM | Yes | CapEx | Global | IT - External | 10h | 270h | 280h | 2017-06-05 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-08-18 | 0 | NA Others | 99000-99100-99130 NA others | -30 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073656 | No | No | Yes | SDF | Trade (in SDF) | 03-Design/Build | Trade-Baseline configuration - OTC | OTC | FUN | SI | Offshore | Munagala; Praveen | IBM | Yes | CapEx | Global | IT - External | 56h | 0h | 56h | 2017-05-18 | 2017-06-16 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-06-26 | 2017-07-14 | 0 | NA Others | 99000-99100-99130 NA others | -30 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 10 | 12 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073657 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-PDDs | OTC | FUN | SI | Offshore | Munagala; Praveen | IBM | Yes | CapEx | Global | IT - External | 142h | 0h | 142h | 2017-05-02 | 2017-06-01 | Yes |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 45 | 14 | 35 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073658 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-RTM-Global Trade-OTC | OTC | FUN | SI | Offshore | Munagala; Praveen | IBM | Yes | CapEx | Global | IT - External | 10h | 0h | 10h | 2017-04-24 | 2017-04-28 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073659 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-Fit-Gap-Global | OTC | FUN | SI | Offshore | Munagala; Praveen | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-17 | Yes |  |  | WP-FUN.Gap Definition | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073660 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | PDD-RT Trade Promotion Planning - TPM-OTC | OTC | FUN | SI | Offshore | Munagala; Praveen | IBM | Yes | CapEx | Global | IT - External | 20h | 0h | 20h | 2017-04-24 | 2017-04-28 | Yes |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073661 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | PDD-RT Trade Promotion Execution - TPM-OTC | OTC | FUN | SI | Offshore | Munagala; Praveen | IBM | Yes | CapEx | Global | IT - External | 15h | 0h | 15h | 2017-04-24 | 2017-04-28 | Yes |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073662 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | PDD-RT Settlements & Claim Reconcilation - TPM-OTC | OTC | FUN | SI | Offshore | Munagala; Praveen | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-04-10 | 2017-04-18 | Yes |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073663 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | PDD-RT Trade Master Data - TPM-OTC | OTC | FUN | SI | Offshore | Munagala; Praveen | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-04-24 | 2017-04-28 | Yes |  |  | DELIV-FUN-110.PDDs | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073664 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-Gap Resolution-Global | OTC | FUN | SI | Offshore | Munagala; Praveen | IBM | Yes | CapEx | Global | IT - External | 12h | 0h | 12h | 2017-04-24 | 2017-05-05 | Yes |  |  | WP-FUN.Gap Definition | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073665 | No | No | Yes | SDF | Trade (in SDF) | 02-Analyze | Trade-Global Trade scope / Solution validation-OTC | OTC | FUN | SI | Offshore | Munagala; Praveen | IBM | Yes | CapEx | Global | IT - External | 0h | 0h | 0h | 2017-04-17 | 2017-04-21 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073666 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy2 - HC - (Accenture) - DC | MDG | DC | SI | Offshore | Alvarez; Ronald | Accenture | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2018-02-05 | 2018-03-02 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | -17.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073667 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Alvarez; Ronald | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-10-30 | 2017-12-07 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 0 | 18.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073668 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Alvarez; Ronald | Accenture | Yes | CapEx | Localization | IT - External | 0h | 62h | 62h | 2017-10-30 | 2017-12-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073669 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Alvarez; Ronald | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -4.88 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073670 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Alvarez; Ronald | Accenture | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -50 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073671 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Alvarez; Ronald | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-22 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073672 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Alvarez; Ronald | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073673 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Alvarez; Ronald | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073674 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Alvarez; Ronald | Accenture | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073675 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy2 (Accenture) - DC | MDG | DC | SI | Offshore | Alvarez; Ronald | Accenture | Yes | CapEx | Localization | IT - External | 261h | 0h | 261h | 2017-07-03 | 2017-09-08 | Yes |  |  | ACT-MDG.Build ETL programs | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 36 | 0 | 0
1073676 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Alvarez; Ronald | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-09-22 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073677 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Alvarez; Ronald | Accenture | Yes | CapEx | Localization | IT - External | 57h | 11h | 68h | 2017-09-13 | 2017-10-02 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 35
1073678 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Alvarez; Ronald | Accenture | Yes | CapEx | Localization | IT - External | 0h | 53h | 53h | 2017-09-22 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073679 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Alvarez; Ronald | Accenture | Yes | CapEx | Localization | IT - External | 10h | 90h | 100h | 2017-09-18 | 2017-11-02 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
1073680 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Alvarez; Ronald | Accenture | Yes | CapEx | Localization | IT - External | 74h | 0h | 74h | 2017-08-07 | 2017-09-01 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 20 | 39 | 0 | 0 | 0
1073681 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Alvarez; Ronald | Accenture | Yes | CapEx | Localization | IT - External | 35h | 0h | 35h | 2017-08-07 | 2017-08-18 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 20 | 0 | 0 | 0 | 0 | 0
1073682 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Offshore | Alvarez; Ronald | Accenture | Yes | CapEx | Localization | IT - External | 46h | 0h | 46h | 2017-08-07 | 2017-09-13 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 14.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 9 | 23 | 0
1073683 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Alvarez; Ronald | Accenture | Yes | CapEx | Localization | IT - External | 48h | 0h | 48h | 2017-08-07 | 2017-08-30 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-07-31 | 2017-08-11 | 2 | QE2 Mock Prep | 20000 D2-20100 B-20110 QE2 Mock Prep | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 16 | 15 | 2 | 0 | 0 | 0
1073684 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Deshmukh; Sandip | IBM | Yes | CapEx | Localization | IT - External | 0h | 10h | 10h | 2017-09-11 | 2017-09-15 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073685 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Deshmukh; Sandip | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-09-05 | 2017-09-29 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 15 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073686 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Deshmukh; Sandip | IBM | Yes | CapEx | Localization | IT - External | 0h | 51h | 51h | 2017-08-28 | 2017-09-29 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073687 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Deshmukh; Sandip | IBM | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-07-24 | 2017-08-04 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073688 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Deshmukh; Sandip | IBM | Yes | CapEx | Localization | IT - External | 79h | 11h | 90h | 2017-08-07 | 2017-08-23 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 39 | 0 | 0 | 0 | 0 | 0
1073689 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Deshmukh; Sandip | IBM | Yes | CapEx | Localization | IT - External | 0h | 16h | 16h | 2017-06-05 | 2017-08-31 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 10 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073690 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Deshmukh; Sandip | IBM | Yes | CapEx | Localization | IT - External | 0h | 69h | 69h | 2017-08-28 | 2017-09-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073691 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Deshmukh; Sandip | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-06-05 | 2017-07-14 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | -15 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073692 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Deshmukh; Sandip | IBM | Yes | CapEx | Localization | IT - External | 0h | 52h | 52h | 2017-08-15 | 2017-09-01 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 17.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073693 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Deshmukh; Sandip | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-07-21 | 2017-08-11 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073694 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Deshmukh; Sandip | IBM | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-07-20 | 2017-08-02 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | 5 | 29.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073695 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Deshmukh; Sandip | IBM | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-09-05 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073696 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Deshmukh; Sandip | IBM | Yes | CapEx | Localization | IT - External | 0h | 125h | 125h | 2017-09-25 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073697 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Deshmukh; Sandip | IBM | Yes | CapEx | Localization | IT - External | 0h | 125h | 125h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073698 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Rai; Kaushal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-18 | 2017-09-22 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 15 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073699 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Rai; Kaushal | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-05-29 | 2017-06-02 | Yes |  |  | ACT-FUN.Management | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073700 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Shukla; Anant | IBM | Yes | CapEx | Localization | IT - External | 106h | 0h | 106h | 2017-05-22 | 2017-06-30 | Yes |  |  | ACT-FUN.Management | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 4 | 31 | 0 | 20 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073701 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Shukla; Anant | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-09-05 | 2017-09-15 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 15 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073702 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Shukla; Anant | IBM | Yes | CapEx | Localization | IT - External | 0h | 125h | 125h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073703 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Shukla; Anant | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-05 | 2017-09-15 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073704 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Shukla; Anant | IBM | Yes | CapEx | Localization | IT - External | 34h | 0h | 34h | 2017-07-24 | 2017-08-24 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | 5 | 29.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 10 | 20 | 0 | 0 | 0 | 0
1073705 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Shukla; Anant | IBM | Yes | CapEx | Localization | IT - External | 36h | 24h | 60h | 2017-08-07 | 2017-08-23 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 17.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 16 | 0 | 0 | 0 | 0 | 0
1073706 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Shukla; Anant | IBM | Yes | CapEx | Localization | IT - External | 10h | 30h | 40h | 2017-08-21 | 2017-09-01 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0
1073707 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Shukla; Anant | IBM | Yes | CapEx | Localization | IT - External | 49h | 0h | 49h | 2017-06-05 | 2017-07-21 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 10 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073708 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Shukla; Anant | IBM | Yes | CapEx | Localization | IT - External | 42h | 0h | 42h | 2017-06-05 | 2017-07-16 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | -15 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073709 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Shukla; Anant | IBM | Yes | CapEx | Localization | IT - External | 96h | 0h | 96h | 2017-07-24 | 2017-08-04 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073710 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Shukla; Anant | IBM | Yes | CapEx | Localization | IT - External | 64h | 26h | 90h | 2017-08-07 | 2017-08-25 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 24 | 10 | 0 | 0 | 0 | 0
1073711 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Shukla; Anant | IBM | Yes | CapEx | Localization | IT - External | 0h | 94h | 94h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073712 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Shukla; Anant | IBM | Yes | CapEx | Localization | IT - External | 0h | 100h | 100h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073713 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (PTP) - Deploy2 | PTP | FUN | SI | Onshore | Anstey; Stephen | IBM | Yes | CapEx | Localization | IT - External | 0h | 45h | 45h | 2017-08-28 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073714 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Anstey; Stephen | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-08-07 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073715 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTP) - Deploy2 | PTP | FUN | SI | Onshore | Anstey; Stephen | IBM | Yes | CapEx | Localization | IT - External | 0h | 45h | 45h | 2017-09-11 | 2017-10-13 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 20 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073716 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Anstey; Stephen | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073717 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTP) - Deploy1 | PTP | FUN | SI | Onshore | Anstey; Stephen | IBM | Yes | CapEx | Localization | IT - External | 28.5h | 11.5h | 40h | 2017-08-07 | 2017-09-28 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 17.5 | 0 | 0
1073718 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTP) - Deploy2 | PTP | FUN | SI | Onshore | Anstey; Stephen | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073719 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTP) - Deploy2 | PTP | FUN | SI | Onshore | Anstey; Stephen | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073720 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTP) - Deploy2 | PTP | FUN | SI | Onshore | Anstey; Stephen | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073721 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | MCP Mini config and masterdata for US and Canada | PTP | FUN | SI | Onshore | Anstey; Stephen | IBM | Yes | CapEx | Localization | IT - External | 28.5h | 41.5h | 70h | 2017-02-06 | 2017-10-19 | Yes |  |  | ACT-FUN.Configuration | Future Task | NA | NA | 0 | NA Others | 99000-99100-99130 NA others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 17.5 | 0 | 0
1073722 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Onshore | Kim; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-01 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-07-31 | 2017-08-11 | 2 | QE2 Mock Prep | 20000 D2-20100 B-20110 QE2 Mock Prep | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073723 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Kim; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 160h | 0h | 160h | 2017-07-31 | 2017-08-25 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0
1073724 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Kim; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2017-09-05 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0
1073725 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Kim; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 100h | 100h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073726 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Kim; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 65h | 65h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073727 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Kim; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073728 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | Kim; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 40h | 14h | 54h | 2017-08-28 | 2017-09-22 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 14.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0
1073729 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Onshore | Kim; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 40h | 30h | 70h | 2017-09-11 | 2017-10-05 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0
1073730 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Kim; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-18 | 2017-08-25 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073731 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Mock Load - Deploy1 - DC | MDG | DC | SI | Onshore | Kim; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-28 | 2017-07-28 | Yes |  |  | ACT-MDG.Mock Load | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073732 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Mock1 Preparation - Deploy1 - CG - DC | MDG | DC | SI | Onshore | Kim; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-28 | 2017-07-28 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073733 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Mock1 Validation - Deploy1 - CG- DC | MDG | DC | SI | Onshore | Kim; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-28 | 2017-07-28 | Yes |  |  | ACT-MDG.Mock Validation | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073734 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) - Deploy1 - DC | MDG | DC | SI | Onshore | Kim; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-22 | 2017-06-22 | Yes |  |  | DELIV-MDG-206.Functional Specification -Conversion | Complete | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | -20 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073735 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Onshore | Kim; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-21 | 2017-07-21 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073736 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Onshore | Kim; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-21 | 2017-07-21 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 30 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073737 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Onshore | Kim; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-21 | 2017-07-21 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073738 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy2 (Accenture) - DC | MDG | DC | SI | Onshore | Kim; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 160h | 0h | 160h | 2017-07-03 | 2017-07-28 | Yes |  |  | ACT-MDG.Build ETL programs | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073739 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Kim; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 55h | 55h | 2017-10-30 | 2017-12-07 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 0 | 18.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073740 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Kim; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 65h | 65h | 2017-10-30 | 2017-12-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073741 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Kim; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -4.88 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073742 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Kim; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073743 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Kim; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073744 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Kim; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073745 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Kim; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-11-03 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -50 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073746 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | Kim; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-22 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073747 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy2 - HC - (Accenture) - DC | MDG | DC | SI | Onshore | Kim; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2018-02-05 | 2018-03-02 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | -17.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073748 | No | No | Yes | SDF | SDF Localisation | 99-Global | Cutover planners | CM | CM | SI | Onshore | Sulzer; Brian | Other | Yes | CapEx | Localization | IT - External | 224h | 336h | 560h | 2017-07-24 | 2017-10-19 | Yes |  |  |  | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 40 | 40 | 56 | 48 | 0 | 0
1073749 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Scenarios/Scripts (Test) - Deploy2 | Test | Test | SI | Offshore | Wadwekar; Sarang | IBM | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-09-05 | 2017-09-15 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-11-24 | 2 | SIT 1 & 2 Prep | 20000 D2-21000 T-21036 SIT 1 & 2 Prep | -9 | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073750 | No | No | Yes | SDF | SDF Localisation | 04-Test | Manage SIT2 (Test) - Deploy2 | Test | Test | SI | Offshore | Wadwekar; Sarang | IBM | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-10-02 | 2017-10-20 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-10-20 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073751 | No | No | Yes | SDF | SDF Localisation | 04-Test | Manage SIT1 (Test) - Deploy2 | Test | Test | SI | Offshore | Wadwekar; Sarang | IBM | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-09-11 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-11-24 | 2 | TBD | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | -5 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073752 | No | No | Yes | SDF | SDF Localisation | 04-Test | Manage Regression (Test) - Deploy2 | Test | Test | SI | Offshore | Wadwekar; Sarang | IBM | Yes | CapEx | Localization | IT - External | 0h | 115h | 115h | 2017-11-06 | 2017-11-24 | Yes |  |  | ACT-Test.Management | Future Task | 2017-11-06 | 2017-11-24 | 2 | Q? Regression | 20000 D2-21000 T-21054 D2 Regression (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073753 | No | No | Yes | SDF | SDF Localisation | 04-Test | Regression Test Scenarios/Scripts (Test) - Deploy2 | Test | Test | SI | Offshore | Wadwekar; Sarang | IBM | Yes | CapEx | Localization | IT - External | 0h | 160h | 160h | 2017-09-05 | 2017-11-03 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-11-24 | 2 | QE2 Regression | 20000 D2-21000 T-21052 Regression Prep | -9 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073754 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Test preparation (Test) - Deploy1 | Test | Test | SI | Offshore | Wadwekar; Sarang | IBM | Yes | CapEx | Global | IT - External | 33h | 0h | 33h | 2017-07-04 | 2017-07-14 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Complete | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073755 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Scenarios/Scripts (Test) - Deploy1 | Test | Test | SI | Offshore | Wadwekar; Sarang | IBM | Yes | CapEx | Global | IT - External | 9h | 0h | 9h | 2017-07-04 | 2017-07-14 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Complete | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | -5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073756 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Regression Test Scenarios/Scripts (Test) - Deploy1 | Test | Test | SI | Offshore | Wadwekar; Sarang | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-07-04 | 2017-07-14 | Yes |  |  | DELIV-TST-308.Regression Test Scenarios/Scripts | Complete | 2017-06-26 | 2017-07-14 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | -10 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073757 | No | No | Yes | SDF | SDF Localisation | 04-Test | Manage SIT (Test) - Deploy1 | Test | Test | SI | Offshore | Wadwekar; Sarang | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | Yes |  |  | ACT-Test.Management | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073758 | No | No | Yes | SDF | SDF Localisation | 04-Test | Regression Test Scenarios/Scripts (Test) - Deploy1 | Test | Test | SI | Offshore | Wadwekar; Sarang | IBM | Yes | CapEx | Localization | IT - External | 261h | 0h | 261h | 2017-07-17 | 2017-09-01 | Yes |  |  | DELIV-TST-308.Regression Test Scenarios/Scripts | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | -15 | 9.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 36 | 45 | 45 | 36 | 36 | 27 | 0 | 0 | 0
1073759 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Scenarios/Scripts (Test) - Deploy1 | Test | Test | SI | Offshore | Wadwekar; Sarang | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | 15 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073760 | No | No | Yes | SDF | SDF Localisation | 04-Test | UAT Test Scenarios/Test Cases/Test Scripts (Test) - Deploy1 | Test | Test | SI | Offshore | Wadwekar; Sarang | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | DELIV-FUN-408.UAT Test Scenarios/Test Cases/Test Scripts | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073761 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Manage UAT (Test) - Deploy1 | Test | Test | SI | Offshore | Wadwekar; Sarang | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | Yes |  |  | ACT-Test.Management | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073762 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Test preparation (Test) - Deploy1 | Test | Test | SI | Offshore | Burra; Prasanthi | IBM | Yes | CapEx | Global | IT - External | 108h | 0h | 108h | 2017-06-12 | 2017-07-14 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Complete | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 22.5 | 18 | 22.5 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073763 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Scenarios/Scripts (Test) - Deploy1 | Test | Test | SI | Offshore | Burra; Prasanthi | IBM | Yes | CapEx | Global | IT - External | 63h | 0h | 63h | 2017-06-26 | 2017-07-14 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Complete | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | -5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 22.5 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073764 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Regression Test Scenarios/Scripts (Test) - Deploy1 | Test | Test | SI | Offshore | Burra; Prasanthi | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-06-12 | 2017-06-23 | Yes |  |  | DELIV-TST-308.Regression Test Scenarios/Scripts | Complete | 2017-06-26 | 2017-07-14 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | -10 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073765 | No | No | Yes | SDF | SDF Localisation | 04-Test | UAT Test Scenarios/Test Cases/Test Scripts (Test) - Deploy1 | Test | Test | SI | Offshore | Burra; Prasanthi | IBM | Yes | CapEx | Localization | IT - External | 183.5h | 0h | 183.5h | 2017-07-17 | 2017-09-15 | Yes |  |  | DELIV-FUN-408.UAT Test Scenarios/Test Cases/Test Scripts | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 0 | 0 | 0 | 8 | 28 | 35 | 45 | 45 | 0
1073766 | No | No | Yes | SDF | SDF Localisation | 04-Test | Regression Test Scenarios/Scripts (Test) - Deploy2 | Test | Test | SI | Offshore | Burra; Prasanthi | IBM | Yes | CapEx | Localization | IT - External | 0h | 660h | 660h | 2017-09-05 | 2017-12-18 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-11-24 | 2 | QE2 Regression | 20000 D2-21000 T-21052 Regression Prep | -9 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073767 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Scenarios/Scripts (Test) - Deploy1 | Test | Test | SI | Offshore | Burra; Prasanthi | IBM | Yes | CapEx | Localization | IT - External | 185.5h | 0h | 185.5h | 2017-07-17 | 2017-09-01 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | 15 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 45 | 45 | 45 | 10 | 8 | 10 | 0 | 0 | 0
1073768 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Jain; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 8h | 8h | 2017-08-21 | 2017-09-15 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073769 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Jain; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 4h | 4h | 2017-08-28 | 2017-09-15 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073770 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Jain; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 4h | 4h | 2017-08-30 | 2017-09-15 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073771 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Umraode; Mayank | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-06-19 | 2017-07-07 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | -5 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073772 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Umraode; Mayank | IBM | Yes | CapEx | Localization | IT - External | 0h | 5h | 5h | 2017-06-12 | 2017-07-07 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 11 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073773 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Umraode; Mayank | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-08-28 | 2017-09-15 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073774 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Interface (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Umraode; Mayank | IBM | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-09-15 | 2017-09-29 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 15 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073775 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Umraode; Mayank | IBM | Yes | CapEx | Localization | IT - External | 50h | 0h | 50h | 2017-07-24 | 2017-07-28 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073776 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Umraode; Mayank | IBM | Yes | CapEx | Localization | IT - External | 100h | 0h | 100h | 2017-08-07 | 2017-08-18 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 0 | 0 | 0 | 0
1073777 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Umraode; Mayank | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-06-26 | 2017-06-30 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 1 | FUT | 1000 D1-1300 B-1311 FUT | 20 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073778 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Umraode; Mayank | IBM | Yes | CapEx | Localization | IT - External | 50h | 0h | 50h | 2017-07-17 | 2017-07-21 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073779 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Umraode; Mayank | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2017-09-05 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073780 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Umraode; Mayank | IBM | Yes | CapEx | Localization | IT - External | 0h | 110h | 110h | 2017-09-25 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073781 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Umraode; Mayank | IBM | Yes | CapEx | Localization | IT - External | 55h | 0h | 55h | 2017-08-21 | 2017-09-01 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-06-26 | 2017-07-14 | 1 | SIT 1 & 2 Prep | 1000 D1-1300 B-1323 SIT 1 & 2 Prep | 33 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 45 | 0 | 0 | 0
1073782 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTP) - Deploy2 | PTP | FUN | SI | Offshore | Umraode; Mayank | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073783 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTP) - Deploy2 | PTP | FUN | SI | Offshore | Umraode; Mayank | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073784 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTP) - Deploy2 | PTP | FUN | SI | Offshore | Umraode; Mayank | IBM | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-09-18 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073785 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTP) - Deploy2 | PTP | FUN | SI | Offshore | Umraode; Mayank | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-10-10 | 2017-10-27 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073786 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTP) - Deploy2 | PTP | FUN | SI | Offshore | Umraode; Mayank | IBM | Yes | CapEx | Localization | IT - External | 45h | 15h | 60h | 2017-09-11 | 2017-09-18 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 20 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0
1073787 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTP) - Deploy1 | PTP | FUN | SI | Offshore | Umraode; Mayank | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-08-07 | 2017-08-25 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073788 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Khan; Jamsheed | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-04 | 2017-12-22 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073789 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Finalize Preliminary gaps (BPML, RTM, NFRs, RICEFWs DOMs) | OTC | FUN | SI | Onshore | Khan; Jamsheed | IBM | Yes | CapEx | Localization | IT - External | 72h | 0h | 72h | 2017-03-27 | 2017-04-12 | Yes |  |  | DELIV-RTM-001.Requirements Traceability Matrix (RTM) | Complete | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -25 | -13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 18 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073790 | No | No | Yes | SDF | SDF Localisation | 01-Preparation | Workshop Schedule (incl. review of DDDs) | OTC | FUN | SI | Onshore | Khan; Jamsheed | IBM | Yes | CapEx | Localization | IT - External | 60h | 0h | 60h | 2017-03-27 | 2017-04-14 | Yes |  |  | DELIV-FUN-101.Consolidated Workshop Schedule | Complete | 2017-04-03 | 2017-04-14 | 1 | Revise DDDs - Division review | 1000 D1-1100 PP-1110 Revise DDDs - Division review | -5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 26 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073791 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - OTC (AN) | OTC | FUN | SI | Onshore | Khan; Jamsheed | IBM | Yes | CapEx | Localization | IT - External | 287h | 0h | 287h | 2017-04-17 | 2017-07-14 | Yes |  |  | ACT-FUN.Management | Complete | NA | NA | 1 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 36 | 0 | 44 | 24 | 27 | 30 | 24 | 15 | 20 | 7 | 13 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073792 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | Configuration-Sales Order output conditions & ALE | OTC | FUN | SI | Onshore | Khan; Jamsheed | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-05-01 | 2017-05-05 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-05-19 | 0 | NA Others | 99000-99100-99130 NA others | -8 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073793 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Khan; Jamsheed | IBM | Yes | CapEx | Localization | IT - External | 7h | 0h | 7h | 2017-06-13 | 2017-06-16 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | -15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073794 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Khan; Jamsheed | IBM | Yes | CapEx | Localization | IT - External | 41h | 0h | 41h | 2017-06-19 | 2017-07-28 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-21 | 2017-09-01 | 2 | AT | 20000 D2-20100 B-20180 AT | -45 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 9 | 7 | 6 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073795 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT - OTC- Deploy2 | OTC | FUN | SI | Onshore | Khan; Jamsheed | IBM | Yes | CapEx | Localization | IT - External | 41h | 0h | 41h | 2017-06-05 | 2017-07-14 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 5 | 10 | 8 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073796 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Khan; Jamsheed | IBM | Yes | CapEx | Localization | IT - External | 89h | 0h | 89h | 2017-06-05 | 2017-07-28 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 12 | 7 | 13 | 19 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073797 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Khan; Jamsheed | IBM | Yes | CapEx | Localization | IT - External | 33h | 0h | 33h | 2017-05-08 | 2017-06-16 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-05-19 | 2 | Base Config | 1000 D1-1300 B-1314 Base Config | -5 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 15 | 2 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073798 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | IOTC010-DEV FUT-INT-Sales order interface | OTC | FUN | SI | Onshore | Khan; Jamsheed | IBM | Yes | CapEx | Localization | IT - External | 20h | 40h | 60h | 2017-07-20 | 2017-08-28 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-05-22 | 2017-07-07 | 0 | NA Others | 99000-99100-99130 NA others | 5 | 35.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 0 | 10 | 5 | 0 | 0 | 0 | 0
1073799 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Khan; Jamsheed | IBM | Yes | CapEx | Localization | IT - External | 33h | 0h | 33h | 2017-06-19 | 2017-08-24 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | -25 | 16.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 4 | 10 | 0 | 5 | 4 | 0 | 0 | 0 | 0
1073800 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | IOTC010-FSD-INT-Sales order interface | OTC | FUN | SI | Onshore | Khan; Jamsheed | IBM | Yes | CapEx | Localization | IT - External | 19h | 0h | 19h | 2017-01-23 | 2017-06-16 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-06-30 | 0 | NA Others | 99000-99100-99130 NA others | -90 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073801 | No | No | Yes | SDF | SDF Localisation | 99-Global | Management (Planning, reporting, CR, cross stream integration) - OTC-(Global) | OTC | FUN | SI | Onshore | Khan; Jamsheed | IBM | Yes | CapEx | Localization | IT - External | 143h | 1,320h | 1,463h | 2017-06-19 | 2018-03-30 | Yes |  |  | ACT-CM.Management | Future Task | NA | NA | 9 | Management | 90000 G-90100G-90110 Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 16 | 25 | 30 | 29 | 30 | 0 | 0 | 0 | 0
1073802 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (OTC) - Deploy2 | OTC | FUN | SI | Onshore | Khan; Jamsheed | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-10 | 2017-07-10 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073803 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Gaikwad; Pradeep | IBM | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073804 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - PTM | PTM | FUN | SI | Offshore | Gaikwad; Pradeep | IBM | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2017-05-10 | 2017-05-12 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Complete | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073805 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Gaikwad; Pradeep | IBM | Yes | CapEx | Localization | IT - External | 90h | 129h | 219h | 2017-08-07 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 40 | 0 | 0 | 0 | 0 | 0
1073806 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Gaikwad; Pradeep | IBM | Yes | CapEx | Localization | IT - External | 140h | 0h | 140h | 2017-07-17 | 2017-08-04 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 40 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073807 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Gaikwad; Pradeep | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-07-21 | 2017-08-11 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073808 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Gaikwad; Pradeep | IBM | Yes | CapEx | Localization | IT - External | 30h | 30h | 60h | 2017-08-21 | 2017-08-31 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 17.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0
1073809 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Support (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Gaikwad; Pradeep | IBM | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-09-05 | 2017-09-15 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -14.88 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073810 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Gaikwad; Pradeep | IBM | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-08-28 | 2017-09-15 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073811 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (PTM) - Deploy2 | PTM | FUN | SI | Offshore | Gaikwad; Pradeep | IBM | Yes | CapEx | Localization | IT - External | 0h | 56h | 56h | 2017-09-05 | 2017-09-22 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 15 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073812 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (PTM) - Deploy1 | PTM | FUN | SI | Offshore | Gaikwad; Pradeep | IBM | Yes | CapEx | Localization | IT - External | 179h | 0h | 179h | 2017-05-22 | 2017-07-12 | Yes |  |  | ACT-FUN.Management | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 18 | 17 | 0 | 0 | 27 | 45 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073813 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy1 - DC | MDG | DC | SI | Offshore | Rosal; Gielany | Accenture | Yes | CapEx | Localization | IT - External | 79h | 0h | 79h | 2017-06-26 | 2017-07-07 | Yes |  |  | ACT-MDG.Build ETL programs | Complete | 2017-05-08 | 2017-06-09 | 1 | Build and adjust conversion programs | 1000 D1-1300 B-1322 Build and adjust conversion programs | 15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073814 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Data Migration development - Deploy1 - DC | MDG | DC | SI | Offshore | Rosal; Gielany | Accenture | Yes | CapEx | Localization | IT - External | 85h | 0h | 85h | 2017-05-29 | 2017-06-23 | Yes |  |  | ACT-MDG.Data Construction | Complete | 2017-05-08 | 2017-06-09 | 1 | Data Construction | 1000 D1-1300 B-1320 Data Construction | 15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073815 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy1 - HC - (Accenture) - DC | MDG | DC | SI | Offshore | Rosal; Gielany | Accenture | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -21.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073816 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Rosal; Gielany | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-21 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073817 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Rosal; Gielany | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-14 | 2017-07-21 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 30 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073818 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Rosal; Gielany | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-14 | 2017-07-21 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073819 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Rosal; Gielany | Accenture | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073820 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Rosal; Gielany | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073821 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Rosal; Gielany | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073822 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Rosal; Gielany | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-22 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073823 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Rosal; Gielany | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-10-30 | 2017-12-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073824 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Rosal; Gielany | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-10-30 | 2017-12-07 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 0 | 18.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073825 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Rosal; Gielany | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -4.88 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073826 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Rosal; Gielany | Accenture | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -50 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073827 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Rosal; Gielany | Accenture | Yes | CapEx | Localization | IT - External | 36h | 14h | 50h | 2017-09-11 | 2017-09-26 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0
1073828 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Rosal; Gielany | Accenture | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073829 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Rosal; Gielany | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-07-10 | 2017-07-14 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073830 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Rosal; Gielany | Accenture | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-07-17 | 2017-07-21 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 15 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073831 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Rosal; Gielany | Accenture | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-07-24 | 2017-08-04 | Yes |  |  | ACT-MDG.Mock Load | Complete | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 10.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073832 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Rosal; Gielany | Accenture | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073833 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Rosal; Gielany | Accenture | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-09-15 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073834 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Rosal; Gielany | Accenture | Yes | CapEx | Localization | IT - External | 117h | 0h | 117h | 2017-08-22 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 36 | 45 | 0 | 0
1073835 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Rosal; Gielany | Accenture | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-08-07 | 2017-08-20 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0
1073836 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Villanueva; Carl | Accenture | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-09-05 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Load | Complete | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 10.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0
1073837 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Villanueva; Carl | Accenture | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2017-08-21 | 2017-09-01 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 36 | 0 | 0 | 0
1073838 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Villanueva; Carl | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-05 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073839 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Villanueva; Carl | Accenture | Yes | CapEx | Localization | IT - External | 36h | 20h | 56h | 2017-09-11 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0
1073840 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Villanueva; Carl | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-07-31 | 2017-08-04 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 15 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073841 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Villanueva; Carl | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-07-24 | 2017-07-28 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073842 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Villanueva; Carl | Accenture | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073843 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Villanueva; Carl | Accenture | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073844 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Villanueva; Carl | Accenture | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073845 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Villanueva; Carl | Accenture | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -50 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073846 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Villanueva; Carl | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-10-30 | 2017-12-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073847 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Villanueva; Carl | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -4.88 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073848 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Villanueva; Carl | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-10-30 | 2017-12-07 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 0 | 18.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073849 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Villanueva; Carl | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-22 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073850 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Villanueva; Carl | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073851 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Villanueva; Carl | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073852 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Villanueva; Carl | Accenture | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073853 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Villanueva; Carl | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-08-14 | 2017-08-18 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0
1073854 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Villanueva; Carl | Accenture | Yes | CapEx | Localization | IT - External | 81h | 0h | 81h | 2017-07-10 | 2017-07-21 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 30 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073855 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Villanueva; Carl | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-08-07 | 2017-08-11 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0
1073856 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy1 - HC - (Accenture) - DC | MDG | DC | SI | Offshore | Villanueva; Carl | Accenture | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -21.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073857 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Data Migration development - Deploy1 - DC | MDG | DC | SI | Offshore | Villanueva; Carl | Accenture | Yes | CapEx | Localization | IT - External | 180h | 0h | 180h | 2017-05-29 | 2017-07-02 | Yes |  |  | ACT-MDG.Data Construction | Complete | 2017-05-08 | 2017-06-09 | 1 | Data Construction | 1000 D1-1300 B-1320 Data Construction | 15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 50 | 51 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073858 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy1 - DC | MDG | DC | SI | Offshore | Villanueva; Carl | Accenture | Yes | CapEx | Localization | IT - External | 41h | 0h | 41h | 2017-06-27 | 2017-07-07 | Yes |  |  | ACT-MDG.Build ETL programs | Complete | 2017-05-08 | 2017-06-09 | 1 | Build and adjust conversion programs | 1000 D1-1300 B-1322 Build and adjust conversion programs | 15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073859 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy1 - DC | MDG | DC | SI | Offshore | Mendoza; Jeslyn | Accenture | Yes | CapEx | Localization | IT - External | 53h | 0h | 53h | 2017-06-26 | 2017-06-30 | Yes |  |  | ACT-MDG.Build ETL programs | Complete | 2017-05-08 | 2017-06-09 | 1 | Build and adjust conversion programs | 1000 D1-1300 B-1322 Build and adjust conversion programs | 15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073860 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Data Migration development - Deploy1 - DC | MDG | DC | SI | Offshore | Mendoza; Jeslyn | Accenture | Yes | CapEx | Localization | IT - External | 208.5h | 0h | 208.5h | 2017-05-29 | 2017-07-14 | Yes |  |  | ACT-MDG.Data Construction | Complete | 2017-05-08 | 2017-06-09 | 1 | Data Construction | 1000 D1-1300 B-1320 Data Construction | 15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 51 | 0 | 0 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073861 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy1 - HC - (Accenture) - DC | MDG | DC | SI | Offshore | Mendoza; Jeslyn | Accenture | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -21.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073862 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Mendoza; Jeslyn | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-01 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073863 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Mendoza; Jeslyn | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-19 | 2017-07-10 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 30 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073864 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Mendoza; Jeslyn | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-21 | 2017-07-28 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073865 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Mendoza; Jeslyn | Accenture | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073866 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Mendoza; Jeslyn | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073867 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Mendoza; Jeslyn | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-22 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073868 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Mendoza; Jeslyn | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073869 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Mendoza; Jeslyn | Accenture | Yes | CapEx | Localization | IT - External | 0h | 100h | 100h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -4.88 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073870 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Mendoza; Jeslyn | Accenture | Yes | CapEx | Localization | IT - External | 0h | 115h | 115h | 2017-10-30 | 2017-12-07 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 0 | 18.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073871 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Mendoza; Jeslyn | Accenture | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -50 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073872 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Mendoza; Jeslyn | Accenture | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073873 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Mendoza; Jeslyn | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-21 | 2017-07-28 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 15 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073874 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy1 - D&B (Accenture) - DC | MDG | DC | SI | Offshore | Mendoza; Jeslyn | Accenture | Yes | CapEx | Localization | IT - External | 58.5h | 0h | 58.5h | 2017-07-10 | 2017-07-20 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-05-08 | 2017-06-02 | 1 | MOCK 1A Prep | 1000 D1-1300 B-1324 MOCK 1A Prep | 25 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073875 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Mendoza; Jeslyn | Accenture | Yes | CapEx | Localization | IT - External | 45h | 10h | 55h | 2017-09-12 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0
1073876 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Mendoza; Jeslyn | Accenture | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073877 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Mendoza; Jeslyn | Accenture | Yes | CapEx | Localization | IT - External | 45h | 30h | 75h | 2017-09-04 | 2017-09-29 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0
1073878 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Mendoza; Jeslyn | Accenture | Yes | CapEx | Localization | IT - External | 126h | 0h | 126h | 2017-08-14 | 2017-09-01 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 36 | 45 | 0 | 0 | 0
1073879 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Mendoza; Jeslyn | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-08-08 | 2017-08-13 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0
1073880 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy1 - CG - (Accenture) - DC | MDG | DC | SI | Offshore | Mendoza; Jeslyn | Accenture | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-07-24 | 2017-08-06 | Yes |  |  | ACT-MDG.Mock Load | Complete | 2017-08-07 | 2017-08-25 | 1 | QE3 Dry Run for D1 Scope | 1000 D1-1400 T-1450 QE3 Dry Run for D1 Scope | -10 | 10.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073881 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Build ETL programs - Deploy2 (Accenture) - DC | MDG | DC | SI | Onshore | DeGuzman; Sheena | Accenture | Yes | CapEx | Localization | IT - External | 225h | 0h | 225h | 2017-07-03 | 2017-08-04 | Yes |  |  | ACT-MDG.Build ETL programs | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073882 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | DeGuzman; Sheena | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-09-04 | 2017-09-08 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0
1073883 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Onshore | DeGuzman; Sheena | Accenture | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-08-21 | 2017-09-01 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-07-31 | 2017-08-11 | 2 | QE2 Mock Prep | 20000 D2-20100 B-20110 QE2 Mock Prep | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0
1073884 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Execute - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | DeGuzman; Sheena | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073885 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Preparation - Deploy2 - D&B (Accenture) - DC | MDG | DC | SI | Onshore | DeGuzman; Sheena | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073886 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | DeGuzman; Sheena | Accenture | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-08-07 | 2017-08-18 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0
1073887 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Mock1 - Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | DeGuzman; Sheena | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-09-11 | 2017-09-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-08-14 | 2017-09-01 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -10 | 14.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0
1073888 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2Validation - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | DeGuzman; Sheena | Accenture | Yes | CapEx | Localization | IT - External | 0h | 65h | 65h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073889 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Break/Fix - Deploy2 - HC - (Accenture) - DC | MDG | DC | SI | Onshore | DeGuzman; Sheena | Accenture | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2018-02-05 | 2018-03-02 | Yes |  |  | ACT-MDG.Execute Break/Fix | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | -17.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073890 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | DeGuzman; Sheena | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-22 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073891 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | DeGuzman; Sheena | Accenture | Yes | CapEx | Localization | IT - External | 0h | 105h | 105h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -50 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073892 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | DeGuzman; Sheena | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073893 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | DeGuzman; Sheena | Accenture | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073894 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Manage Defect - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | DeGuzman; Sheena | Accenture | Yes | CapEx | Localization | IT - External | 0h | 90h | 90h | 2017-12-27 | 2018-02-02 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2018-01-15 | 2018-02-02 | 2 | D2 PRD Data Load | 20000 D2-22400 CG-22420 D2 PRD Data Load | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073895 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Validate - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | DeGuzman; Sheena | Accenture | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-11-06 | 2017-12-22 | Yes |  |  | ACT-MDG.Mock Validation | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -4.88 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073896 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Execute - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | DeGuzman; Sheena | Accenture | Yes | CapEx | Localization | IT - External | 0h | 65h | 65h | 2017-10-30 | 2017-12-15 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-11-13 | 2017-12-01 | 2 | D2 / D3 Dry Run in QE3 | 20000 D2-21000 T-21150 D2 / D3 Dry Run in QE3 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073897 | No | No | Yes | SDF | SDF Localisation | 04-Test | Dry Run - Prepare - Deploy2 - CG - (Accenture) - DC | MDG | DC | SI | Onshore | DeGuzman; Sheena | Accenture | Yes | CapEx | Localization | IT - External | 0h | 55h | 55h | 2017-10-30 | 2017-12-07 | Yes |  |  | ACT-MDG.Mock Preparation | Future Task | 2017-10-30 | 2017-11-10 | 2 | QE3 Dry Run Prevalidation | 20000 D2-21000 T-21140 QE3 Dry Run Prevalidation | 0 | 18.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073898 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2- Manage Defect - Deploy2- D&B (Accenture) - DC | MDG | DC | SI | Onshore | DeGuzman; Sheena | Accenture | Yes | CapEx | Localization | IT - External | 0h | 100h | 100h | 2017-09-15 | 2017-11-03 | Yes |  |  | ACT-MDG.Mock Load | Future Task | 2017-09-11 | 2017-10-27 | 2 | D2 MOCK 2 in QE1 (Require QE3 Refresh) | 20000 D2-21000 T-21100 D2 MOCK 2 in QE1 (Require QE3 Refresh) | -29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073899 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Kumar; Sameer | IBM | Yes | CapEx | Localization | IT - External | 0h | 61h | 61h | 2017-09-18 | 2017-10-13 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073900 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Kumar; Sameer | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-25 | 2017-10-13 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073901 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Kumar; Sameer | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-10-16 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073902 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Kumar; Sameer | IBM | Yes | CapEx | Localization | IT - External | 0h | 59h | 59h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073903 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kumar; Sameer | IBM | Yes | CapEx | Localization | IT - External | 0h | 4h | 4h | 2017-08-30 | 2017-09-15 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073904 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kumar; Sameer | IBM | Yes | CapEx | Localization | IT - External | 0h | 4h | 4h | 2017-08-28 | 2017-09-15 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073905 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kumar; Sameer | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | -5 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073906 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cut Over - Prepare (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kumar; Sameer | IBM | Yes | CapEx | Localization | IT - External | 0h | 15h | 15h | 2017-09-05 | 2017-09-22 | Yes |  |  | ACT-FUN.Cutover activities | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -9 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073907 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Enhancement (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Kumar; Sameer | IBM | Yes | CapEx | Localization | IT - External | 0h | 4h | 4h | 2017-09-05 | 2017-09-15 | Yes |  |  | DELIV-FUN-203.Functional Specification - Enhancement | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073908 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Kumar; Sameer | IBM | Yes | CapEx | Localization | IT - External | 0h | 76h | 76h | 2017-09-05 | 2017-09-18 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073909 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (RTR) - Deploy2 | RTR | FUN | SI | Offshore | Kumar; Sameer | IBM | Yes | CapEx | Localization | IT - External | 0h | 6h | 6h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073910 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Functional Break/Fix (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kumar; Sameer | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073911 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kumar; Sameer | IBM | Yes | CapEx | Localization | IT - External | 42h | 0h | 42h | 2017-08-07 | 2017-08-24 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 9.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 0
1073912 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kumar; Sameer | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-07-17 | 2017-07-27 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 15 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073913 | No | No | Yes | SDF | SDF Localisation | 04-Test | Regression - Run Tests (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kumar; Sameer | IBM | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-08-07 | 2017-08-18 | Yes |  |  | ACT-FUN.Execute Regression Test | Complete | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 9.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 40 | 0 | 0 | 0 | 0 | 0
1073914 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | WPB Recordings (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kumar; Sameer | IBM | Yes | CapEx | Localization | IT - External | 55h | 0h | 55h | 2017-07-07 | 2017-08-04 | Yes |  |  | DELIV-FUN-403.WPB Recordings | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073915 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (RTR) - Deploy1 | RTR | FUN | SI | Offshore | Kumar; Sameer | IBM | Yes | CapEx | Localization | IT - External | 41h | 0h | 41h | 2017-06-12 | 2017-06-23 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | -14 | 72.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073916 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Kickoff - RTR | RTR | FUN | SI | Offshore | Kumar; Sameer | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-04-24 | 2017-04-28 | Yes |  |  | ACT-FUN.Requirements/Process Design Workshops | Future Task | 2017-04-17 | 2017-04-28 | 1 | Work-shops | 1000 D1-1200 A-1210 Work-shops | -9.88 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073917 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF Build/Support (SEC) - Deploy1 | SEC | SEC | SI | Offshore | Quinto; Christian | Accenture | Yes | CapEx | Localization | IT - External | 162h | 0h | 162h | 2017-07-31 | 2017-08-24 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-05 | 2017-06-23 | 1 | Security Build | 1000 D1-1300 B-1335 Security Build | 20 | 86.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 36 | 36 | 0 | 0 | 0 | 0
1073918 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Configuration (BI) - Deploy1 | BI | BI | SI | Onshore | Kante; Sai | IBM | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2017-08-07 | 2017-09-01 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-06-19 | 2017-06-30 | 1 | Cycle 2 Config | 1000 D1-1300 B-1318 Cycle 2 Config | 30 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 20 | 0 | 0 | 0
1073919 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Configuration (BI) - Deploy2 | BI | BI | SI | Onshore | Kante; Sai | IBM | Yes | CapEx | Localization | IT - External | 135h | 0h | 135h | 2017-08-14 | 2017-09-15 | Yes |  |  | ACT-FUN.Configuration | Complete | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 16 | 24 | 27 | 24 | 0
1073920 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (BI) - Deploy2 | BI | BI | SI | Onshore | Kante; Sai | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-08-07 | 2017-08-25 | Yes |  |  | ACT-FUN.Execute FUT | Complete | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 24 | 0 | 0 | 0 | 0
1073921 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT-Open text- C/G-Deploy 1 | BI | BI | SI | Onshore | Kante; Sai | IBM | Yes | CapEx | Localization | IT - External | 28h | 20h | 48h | 2017-09-05 | 2017-09-22 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -10 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 20 | 0
1073922 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) (BI) - Deploy2 | BI | BI | SI | Onshore | Kante; Sai | IBM | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-09-05 | 2017-09-15 | Yes |  |  | DELIV-FUN-220.Solution Design Document (SDD) | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073923 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | WPB Recordings (BI) - Deploy2 | BI | BI | SI | Onshore | Kante; Sai | IBM | Yes | CapEx | Localization | IT - External | 0h | 10h | 10h | 2017-09-05 | 2017-09-15 | Yes |  |  | DELIV-FUN-403.WPB Recordings | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073924 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (BI) - Deploy2 | BI | BI | SI | Onshore | Kante; Sai | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-08-07 | 2017-08-11 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0
1073925 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Run Tests - MDG - MM - Saputo- Deploy1 - DM | MDG | DM | Saputo | Onshore | ElHadjMoussa; Nadir | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-28 | 2017-08-28 | Yes |  |  |  | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073926 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test-Train the Trainer (TTT)-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | ElHadjMoussa; Nadir | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-28 | 2017-07-28 | Yes |  |  |  | Future Task | 2017-07-17 | 2017-07-28 | 1 | Train the trainer | 1000 D1-1800 MultiPhases-1840 Train the trainer | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073927 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | C/G-Business Cutover Plan-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | ElHadjMoussa; Nadir | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-09-18 | 2017-09-18 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073928 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B-Dual Maintenance Training-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | ElHadjMoussa; Nadir | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-09-04 | 2017-09-04 | Yes |  |  |  | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 70 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073929 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B-Training: Concept Slides Final Review-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | ElHadjMoussa; Nadir | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-04 | 2017-08-04 | Yes |  |  |  | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 35 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073930 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B-Training: Job Aids Review-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | ElHadjMoussa; Nadir | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-04 | 2017-08-04 | Yes |  |  |  | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 35 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073931 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test - Material Master - Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | ElHadjMoussa; Nadir | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | -15 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073932 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B-Training: Work Instructions Review-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | ElHadjMoussa; Nadir | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-04 | 2017-08-04 | Yes |  |  |  | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 35 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073933 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HYP-Smoke Test Execution-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | ElHadjMoussa; Nadir | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073934 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HYP-End User Support-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | ElHadjMoussa; Nadir | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073935 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HYP-Dual Maintenance Execution-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | ElHadjMoussa; Nadir | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-10-02 | 2017-10-02 | Yes |  |  |  | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073936 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Support - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | ElHadjMoussa; Nadir | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-08-21 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-05-29 | 2017-07-28 | 1 | Training Material Localization | 1000 D1-1800 MultiPhases-1860 Training Material Localization | 60 | 48.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073937 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover Prepare - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | ElHadjMoussa; Nadir | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 30h | 30h | 2017-08-30 | 2017-09-19 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -15 | -8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073938 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | ElHadjMoussa; Nadir | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 80h | 80h | 2017-08-25 | 2017-09-15 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | -5 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073939 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | Hypercare-Provide end User Support - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | ElHadjMoussa; Nadir | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 360h | 360h | 2017-10-02 | 2017-12-01 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073940 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Cutover Suport - Deploy1 - Saputo - DM | MDG | DM | Saputo | Onshore | ElHadjMoussa; Nadir | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 60h | 60h | 2017-09-11 | 2017-09-29 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-09-29 | 1 | CG | 1000 D1-1500 CG: UAT and Regression-1515 CG | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073941 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | Hypercare-Provide end User Support - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | ElHadjMoussa; Nadir | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 320h | 320h | 2018-02-05 | 2018-03-30 | Yes |  |  |  | Future Task | 2018-02-05 | 2018-03-30 | 2 | D2 Hypercare | 20000 D2-23000 H-23010 D2 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073942 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | UAT - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | ElHadjMoussa; Nadir | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 120h | 120h | 2017-12-04 | 2017-12-22 | Yes |  |  |  | Future Task | 2017-12-04 | 2017-12-22 | 2 | D2/D3 UAT in QE3 | 20000 D2-22000 CG: UAT and Regression-22030 D2/D3 UAT in QE3 | -25 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073943 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT 2-Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | ElHadjMoussa; Nadir | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 30h | 30h | 2017-10-10 | 2017-10-27 | Yes |  |  |  | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073944 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT 1-Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | ElHadjMoussa; Nadir | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 30h | 30h | 2017-09-18 | 2017-10-06 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073945 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Preparation - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | ElHadjMoussa; Nadir | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 30h | 30h | 2017-08-21 | 2017-09-08 | Yes |  |  |  | Future Task | 2017-08-21 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 0 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073946 | No | No | Yes | SDF | SDF Localisation | 99-Global | Training Support - Deploy2 - Saputo - DM | MDG | DM | Saputo | Onshore | ElHadjMoussa; Nadir | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 140h | 140h | 2017-12-18 | 2018-02-02 | Yes |  |  |  | Future Task | 2017-09-18 | 2017-11-03 | 2 | Training Material Localization | 20000 D2-29000 MultiPhases-29040 Training Material Localization | 55 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073947 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test-RT Execution - Montreal-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | ElHadjMoussa; Nadir | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | Yes |  |  |  | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 Regression | 1000 D1-1400 T-1410 QE2 Regression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073948 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test-'Smoke'' Test Planning and Scheduling-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | ElHadjMoussa; Nadir | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | Yes |  |  |  | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073949 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test-'Smoke'' Test Planning and Scheduling-VM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | ElHadjMoussa; Nadir | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-14 | 2017-08-14 | Yes |  |  |  | Future Task | 2017-07-17 | 2017-08-25 | 1 | TBD | 99000-99100-99110 TBD | 20 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073950 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test-Defect Workarounds/OPLs-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | ElHadjMoussa; Nadir | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-11 | 2017-08-11 | Yes |  |  |  | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073951 | No | No | Yes | SDF | SDF Localisation | 04-Test | Test-Defect Management-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | ElHadjMoussa; Nadir | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-04 | 2017-08-04 | Yes |  |  |  | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073952 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | D&B-Dual Maintenance Design and Documentation-MM-Saputo - Deploy1 - DM | MDG | DM | Saputo | Onshore | ElHadjMoussa; Nadir | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-08-04 | 2017-08-04 | Yes |  |  |  | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073953 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Bansal; Divya | IBM | Yes | CapEx | Localization | IT - External | 0h | 180h | 180h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073954 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Bansal; Divya | IBM | Yes | CapEx | Localization | IT - External | 0h | 135h | 135h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073955 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | SI | Offshore | Bansal; Divya | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073956 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | SI | Offshore | Bansal; Divya | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2016-12-28 | 2017-10-31 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073957 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | SI | Offshore | Bansal; Divya | IBM | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-07-31 | 2017-09-15 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0
1073958 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing WRICEFs (Design/Build) | DEV | DEV | SI | Offshore | Bansal; Divya | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-01-11 | 2017-11-03 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -88 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073959 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | SI | Offshore | Bansal; Divya | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-08-28 | 2017-09-29 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073960 | No | No | Yes | SDF | SDF Interim State Project | 03-Design/Build | SDF Interim State Project (Desing/Build) | DEV | DEV | SI | Offshore | Singh; Vipul | IBM | Yes | CapEx | Localization | IT - External | 0h | 50h | 50h | 2016-12-28 | 2017-10-31 | Yes |  |  | DELIV-DEV-202.Technical Specification - Interface | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -98 | 99.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073961 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | DEV Break/Fix UAT (DEV) - Deploy1 (CG) | DEV | DEV | SI | Offshore | Singh; Vipul | IBM | Yes | CapEx | Localization | IT - External | 0h | 35h | 35h | 2017-08-28 | 2017-09-29 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073962 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy2(Design/Build) | DEV | DEV | SI | Offshore | Singh; Vipul | IBM | Yes | CapEx | Localization | IT - External | 235h | 0h | 235h | 2017-08-01 | 2017-09-15 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-06-12 | 2017-09-01 | 2 | DEV | 20000 D2-20100 B-20160 DEV | 5 | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 28 | 36 | 36 | 36 | 45 | 45 | 0
1073963 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SDF-Localisation (DEV) - Deploy1 (Design/Build) | DEV | DEV | SI | Offshore | Singh; Vipul | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | Yes |  |  | TBD-Tobedefine.Tbd | Complete | 2017-05-15 | 2017-06-23 | 1 | DEV | 1000 D1-1300 B-1313 DEV | 10 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073964 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | DEV Break/Fix (DEV) - Deploy1 (HYP) | DEV | DEV | SI | Offshore | Singh; Vipul | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-10-02 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073965 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Singh; Vipul | IBM | Yes | CapEx | Localization | IT - External | 0h | 165h | 165h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073966 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix - Deploy2 - (Test) | DEV | DEV | SI | Offshore | Singh; Vipul | IBM | Yes | CapEx | Localization | IT - External | 0h | 135h | 135h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073967 | No | No | Yes | SDF | Commodities Pricing (in SDF) | 03-Design/Build | Commodity Pricing WRICEFs (Design/Build) | DEV | DEV | SI | Offshore | Singh; Vipul | IBM | Yes | CapEx | Localization | IT - External | 487h | 50h | 537h | 2017-02-13 | 2017-11-03 | Yes |  |  | To delete-To delete.To delete | Future Task | 2017-05-15 | 2017-06-23 | 0 | NA Others | 99000-99100-99130 NA others | -88 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 36 | 45 | 18 | 18 | 36 | 36 | 37 | 45 | 45 | 45 | 45 | 45 | 9 | 0 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0
1073968 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT1-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Singh; Vipul | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-DEV.Execute Break/Fix | Complete | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073969 | No | No | Yes | SDF | SDF Localisation | 04-Test | SIT2-Execute Break/Fix (DEV) - Deploy1 (Test) | DEV | DEV | SI | Offshore | Singh; Vipul | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-08-07 | 2017-08-25 | Yes |  |  | ACT-DEV.Execute Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073970 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Kaushik; Ankit | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073971 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Kaushik; Ankit | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-26 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073972 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Mock1 - Support (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Kaushik; Ankit | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT-FUN.Mock Support | Complete | 2017-06-19 | 2017-07-07 | 1 | QE2 MOCK 1A for D1 Scope | 1000 D1-1300 B-1326 QE2 MOCK 1A for D1 Scope | 5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073973 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Kaushik; Ankit | IBM | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-05-15 | 2017-05-26 | Yes |  |  | ACT-FUN.Configuration | Complete | 2017-05-08 | 2017-05-19 | 1 | Base Config | 1000 D1-1300 B-1314 Base Config | 5 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073974 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Solution Design Document (SDD) (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Kaushik; Ankit | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-08 | 2017-05-18 | Yes |  |  | DELIV-FUN-220.Solution Design Document (SDD) | Future Task | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073975 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Kaushik; Ankit | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-19 | 2017-06-19 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-19 | 2017-06-30 | 1 | Cycle 2 Config | 1000 D1-1300 B-1318 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073976 | No | Yes | No | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Kaushik; Ankit | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-05-29 | 2017-06-02 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073977 | No | No | Yes | SDF | SDF Localisation | 06-Hypercare | HC - Provide end User Support (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Dhyani; Subhash | IBM | Yes | CapEx | Localization | IT - External | 0h | 260h | 260h | 2017-10-02 | 2017-10-27 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-02 | 2017-12-01 | 1 | D1 Hypercare | 1000 D1-1700 H-1710 D1 Hypercare | 0 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073978 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Execute UAT (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Dhyani; Subhash | IBM | Yes | CapEx | Localization | IT - External | 0h | 120h | 120h | 2017-08-28 | 2017-09-15 | Yes |  |  | ACT-FUN.Execute UAT | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073979 | No | No | Yes | SDF | SDF Localisation | 05-Cutover/Go-live | Functional Break/Fix UAT (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Dhyani; Subhash | IBM | Yes | CapEx | Localization | IT - External | 0h | 60h | 60h | 2017-08-28 | 2017-09-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-28 | 2017-09-15 | 1 | QE3 UAT for D1 | 1000 D1-1500 CG: UAT and Regression-1511 QE3 UAT for D1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073980 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Dhyani; Subhash | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-10-09 | 2017-10-09 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073981 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Support Mock1 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Dhyani; Subhash | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-09-04 | 2017-09-08 | Yes |  |  | ACT-FUN.Mock Support | Future Task | 2017-09-25 | 2017-10-06 | 2 | D2-MOCK 1B (in QE2) | 20000 D2-20100 B-20130 D2-MOCK 1B (in QE2) | -25 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0
1073982 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Dhyani; Subhash | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073983 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Dhyani; Subhash | IBM | Yes | CapEx | Localization | IT - External | 0h | 40h | 40h | 2017-09-18 | 2017-09-29 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073984 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Dhyani; Subhash | IBM | Yes | CapEx | Localization | IT - External | 95h | 0h | 95h | 2017-08-28 | 2017-09-15 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | -8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 45 | 0
1073985 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Dhyani; Subhash | IBM | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-06-30 | 2017-08-18 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-29 | 2017-06-09 | 1 | Cycle 1 Config | 1000 D1-1300 B-1316 Cycle 1 Config | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073986 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Dhyani; Subhash | IBM | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-06-30 | 2017-08-25 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-19 | 2017-06-30 | 1 | Cycle 2 Config | 1000 D1-1300 B-1318 Cycle 2 Config | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073987 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (FSD) (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Dhyani; Subhash | IBM | Yes | CapEx | Localization | IT - External | 45h | 53h | 98h | 2017-07-03 | 2017-08-02 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-06-30 | 1 | FSDs | 1000 D1-1300 B-1331 FSDs | 20 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073988 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Validate (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Dhyani; Subhash | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-07-17 | 2017-07-21 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073989 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Support (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Dhyani; Subhash | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073990 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Dhyani; Subhash | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-08-07 | 2017-08-07 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 0 | 4.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073991 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT2 (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Dhyani; Subhash | IBM | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-08-14 | 2017-08-18 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-08-07 | 2017-08-25 | 1 | QE2 SIT2 | 1000 D1-1400 T-1411 QE2 SIT2 | 5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0
1073992 | No | No | Yes | SDF | SDF Localisation | 04-Test | Mock2 - Prepare (LOG) - Deploy1 | LOG | FUN | SI | Offshore | Dhyani; Subhash | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | Yes |  |  | ACT-FUN.Mock Support | Complete | NA | NA | 1 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073993 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 configuration (LOG) - Deploy2 | LOG | FUN | SI | Offshore | Dhyani; Subhash | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-08-21 | 2017-08-24 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | 25 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0
1073994 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Bhardwaj; Smriti | IBM | Yes | CapEx | Localization | IT - External | 0h | 45h | 45h | 2017-10-10 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073995 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Bhardwaj; Smriti | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-18 | 2017-09-18 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073996 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (OTC) - Deploy1 | OTC | FUN | SI | Offshore | Bhardwaj; Smriti | IBM | Yes | CapEx | Localization | IT - External | 189h | 95h | 284h | 2017-08-07 | 2017-11-03 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 46 | 48 | 45 | 0 | 0 | 0
1073997 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification - Report (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Bhardwaj; Smriti | IBM | Yes | CapEx | Localization | IT - External | 0h | 120h | 120h | 2017-09-05 | 2017-11-03 | Yes |  |  | DELIV-FUN-201.Functional Specification - Report | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073998 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 configuration (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Bhardwaj; Smriti | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-10-02 | 2017-10-20 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073999 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (OTC) - Deploy1 | OTC | FUN | SI | Offshore | Bhardwaj; Smriti | IBM | Yes | CapEx | Localization | IT - External | 50h | 65h | 115h | 2017-07-31 | 2017-10-06 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1074000 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Bhardwaj; Smriti | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-11 | 2017-09-11 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | -5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1074001 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 configuration (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Bhardwaj; Smriti | IBM | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-09-18 | 2017-10-06 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1074002 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Bhardwaj; Smriti | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-09-05 | 2017-10-27 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | -20 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1074003 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Bhardwaj; Smriti | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-09 | 2017-06-09 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | -15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1074004 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Bhardwaj; Smriti | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-19 | 2017-06-19 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | -25 | 16.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1074005 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Bhardwaj; Smriti | IBM | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2017-05-08 | 2017-07-28 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-05-19 | 2 | Base Config | 1000 D1-1300 B-1314 Base Config | -5 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1074006 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Log Gaps - OTC | OTC | FUN | SI | Offshore | Bhardwaj; Smriti | IBM | Yes | CapEx | Localization | IT - External | 10h | 10h | 20h | 2017-05-08 | 2017-09-15 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -15 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1074007 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Verma; Poonam | IBM | Yes | CapEx | Localization | IT - External | 162h | 0h | 162h | 2017-05-01 | 2017-06-15 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-05-08 | 2017-05-19 | 2 | Base Config | 1000 D1-1300 B-1314 Base Config | -5 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 35 | 40 | 0 | 30 | 17 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1074008 | No | No | Yes | SDF | SDF Localisation | 02-Analyze | Log Gaps - OTC | OTC | FUN | SI | Offshore | Verma; Poonam | IBM | Yes | CapEx | Localization | IT - External | 93h | 25h | 118h | 2017-05-08 | 2017-09-29 | Yes |  |  | WP-FUN.Fit/Gap Workshop Note | Future Task | 2017-05-01 | 2017-05-05 | 1 | GAPs | 1000 D1-1200 A-1211GAPs | -15 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 45 | 15 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1074009 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Baseline configuration (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Verma; Poonam | IBM | Yes | CapEx | Localization | IT - External | 0h | 30h | 30h | 2017-09-11 | 2017-09-22 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | -20 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1074010 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 configuration (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Verma; Poonam | IBM | Yes | CapEx | Localization | IT - External | 0h | 20h | 20h | 2017-10-02 | 2017-10-06 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1074011 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Verma; Poonam | IBM | Yes | CapEx | Localization | IT - External | 0h | 80h | 80h | 2017-10-02 | 2017-10-20 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | 2017-07-17 | 2017-09-29 | 2 | FUT | 20000 D2-20100 B-20170 FUT | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1074012 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 configuration (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Verma; Poonam | IBM | Yes | CapEx | Localization | IT - External | 0h | 25h | 25h | 2017-10-02 | 2017-10-13 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1074013 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Verma; Poonam | IBM | Yes | CapEx | Localization | IT - External | 39h | 0h | 39h | 2017-07-10 | 2017-08-11 | Yes |  |  | DELIV-FUN-202.Functional Specification - Interface | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 9 | 5 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0
1074014 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Verma; Poonam | IBM | Yes | CapEx | Localization | IT - External | 29h | 80h | 109h | 2017-08-28 | 2017-11-03 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-14 | 2017-09-01 | 2 | SIT 1 & 2 Prep | 20000 D2-20100 B-20140 SIT 1 & 2 Prep | 10 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 14 | 0 | 0
1074015 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (OTC) - Deploy1 | OTC | FUN | SI | Offshore | Verma; Poonam | IBM | Yes | CapEx | Localization | IT - External | 194h | 0h | 194h | 2017-07-17 | 2017-09-08 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 37 | 50 | 10 | 24 | 14 | 10 | 14 | 0 | 0
1074016 | No | No | Yes | SDF | SDF Localisation | 04-Test | Functional Break/Fix SIT1 (OTC) - Deploy1 | OTC | FUN | SI | Offshore | Verma; Poonam | IBM | Yes | CapEx | Localization | IT - External | 110h | 0h | 110h | 2017-07-17 | 2017-09-08 | Yes |  |  | ACT-FUN.Functional Break/Fix | Future Task | 2017-07-17 | 2017-08-04 | 1 | QE2 SIT1 | 1000 D1-1400 T-1409 QE2 SIT1 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 8 | 0 | 25 | 12 | 22 | 20 | 17 | 0 | 0
1074017 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle1 Configuration (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Verma; Poonam | IBM | Yes | CapEx | Localization | IT - External | 7h | 0h | 7h | 2017-06-12 | 2017-06-14 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-06-26 | 2017-07-14 | 2 | Cycle 1 Config | 20000 D2-20100 B-20189 Cycle 1 Config | -15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1074018 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Cycle2 Configuration (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Verma; Poonam | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-07-03 | 2017-07-04 | Yes |  |  | ACT-FUN.Configuration | Future Task | 2017-07-24 | 2017-08-11 | 2 | Cycle 2 Config | 20000 D2-20100 B-20190 Cycle 2 Config | -25 | 16.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1074019 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Functional Specification (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Verma; Poonam | IBM | Yes | CapEx | Localization | IT - External | 59h | 0h | 59h | 2017-06-05 | 2017-06-30 | Yes |  |  | TBD-Tobedefine.Tbd | Future Task | 2017-05-29 | 2017-09-01 | 2 | FSD | 20000 D2-20100 B-20150 FSD | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 18 | 19 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1074020 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | Execute FUT - OTC- Deploy2 | OTC | FUN | SI | Offshore | Verma; Poonam | IBM | Yes | CapEx | Localization | IT - External | 96.5h | 0h | 96.5h | 2017-06-05 | 2017-07-14 | Yes |  |  | ACT-FUN.Execute FUT | Future Task | NA | NA | 2 | TBD | 99000-99100-99110 TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 8 | 20 | 31 | 4 | 26.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1074021 | No | No | Yes | SDF | SDF Localisation | 03-Design/Build | SIT Test Scenarios/Scripts (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Verma; Poonam | IBM | Yes | CapEx | Localization | IT - External | 40.5h | 0h | 40.5h | 2017-07-04 | 2017-07-14 | Yes |  |  | DELIV-TST-301.SIT Test Scenarios/Scripts | Future Task | 2017-08-21 | 2017-09-01 | 2 | AT | 20000 D2-20100 B-20180 AT | -45 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 8.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1074022 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT1 (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Verma; Poonam | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-09-18 | 2017-09-18 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-09-18 | 2017-10-06 | 2 | D2 SIT 1 (in QE2) | 20000 D2-21000 T-21040 D2 SIT 1 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1074023 | No | No | Yes | SDF | SDF Localisation | 04-Test | Execute SIT2 (OTC) - Deploy2 | OTC | FUN | SI | Offshore | Verma; Poonam | IBM | Yes | CapEx | Localization | IT - External | 0h | 70h | 70h | 2017-10-23 | 2017-11-03 | Yes |  |  | ACT-FUN.Execute SIT | Future Task | 2017-10-09 | 2017-10-27 | 2 | D2 SIT 2 (in QE2) | 20000 D2-21000 T-21050 D2 SIT 2 (in QE2) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Worksheet_Data
_Milestone | _Min_Start1 | _Max_Finish1 | 2017-09-25 | 2017-10-02 | 2017-10-09 | 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | 2017-12-04 | 2017-12-11 | 2017-12-18 | 2017-12-25
Activity 21 | 2017-04-17 | 2017-04-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 22 | 2017-05-01 | 2017-05-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 23 | 2017-05-08 | 2017-06-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 24 | 2017-05-08 | 2017-06-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 25 | 2017-05-08 | 2017-06-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 26 | 2017-06-05 | 2017-06-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 27 | 2017-05-29 | 2017-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 28 | 2017-08-07 | 2017-08-25 | 11 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 29 | 2017-09-18 | 2017-09-30 | 555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
Activity 30 | 2017-10-02 | 2017-12-01 | 0 | 551 | 551 | 551 | 555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 31 | 2017-07-31 | 2017-08-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 32 | 2017-08-14 | 2017-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 33 | 2017-05-29 | 2017-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 34 | 2017-09-11 | 2017-11-27 | 798.7 | 789.9 | 724.9 | 706 | 688 | 568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 35 | 2017-10-30 | 2017-11-10 | 0 | 0 | 0 | 0 | 0 | 280 | 324 | 324 | 324 | 324 | 325 | 70 | 70 | 0
Activity 36 | 2017-11-13 | 2017-12-01 | 15 | 15 | 5 | 0 | 0 | 192 | 842 | 1066 | 1053 | 1080 | 1066 | 1092 | 862 | 88
Activity 37 | 2018-01-15 | 2018-02-02 | 10 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1366
Activity 38 | 2018-02-05 | 2018-03-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 39 | 0 | 0 | 157 | 157 | 148 | 157 | 157 | 153 | 157 | 157 | 157 | 160.6 | 166 | 146.4 | 144 | 104.4
Activity 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Pivot_Table
Data
_Milestone | Min of_Start1 | Max of _Finish1 | 25/09/2017 | 02/10/2017 | 09/10/2017 | 16/10/2017 | 23/10/2017 | 30/10/2017 | 06/11/2017 | 13/11/2017 | 20/11/2017 | 27/11/2017 | 04/12/2017 | 11/12/2017 | 18/12/2017 | 25/12/2017
Activity 21 | 2017-04-17 | 2017-04-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 22 | 2017-05-01 | 2017-05-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 23 | 2017-05-08 | 2017-06-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 24 | 2017-05-08 | 2017-06-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 25 | 2017-05-08 | 2017-06-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 26 | 2017-06-05 | 2017-06-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 27 | 2017-05-29 | 2017-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 28 | 2017-08-07 | 2017-08-25 | 11 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 29 | 2017-09-18 | 2017-09-30 | 555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 30 | 2017-10-02 | 2017-12-01 | 0 | 551 | 551 | 551 | 555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 31 | 2017-07-31 | 2017-08-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 32 | 2017-08-14 | 2017-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 33 | 2017-05-29 | 2017-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 34 | 2017-09-11 | 2017-11-27 | 798.7 | 789.9 | 724.9 | 706 | 688 | 568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 35 | 2017-10-30 | 2017-11-10 | 0 | 0 | 0 | 0 | 0 | 280 | 324 | 324 | 324 | 324 | 325 | 70 | 70 | 0
Activity 36 | 2017-11-13 | 2017-12-01 | 15 | 15 | 5 | 0 | 0 | 192 | 842 | 1066 | 1053 | 1080 | 1066 | 1092 | 862 | 88
Activity 37 | 2018-01-15 | 2018-02-02 | 10 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1366
Activity 38 | 2018-02-05 | 2018-03-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 39 | 0 | 0 | 157 | 157 | 148 | 157 | 157 | 153 | 157 | 157 | 157 | 160.6 | 166 | 146.4 | 144 | 104.4
Activity 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Planned work (3) (hidden)
Less than 30h / week
(empty) | No | More than 60h / week
MDG
Planned hours

## Extrait du WEB
Appliquer une mise en forme conditionnelle à des données dans un rapport de tableau croisé dynamique
Utilisez un format conditionnel pour vous aider à explorer et analyser des données, à détecter des problèmes critiques et à identifier des modèles et des tendances. La mise en forme conditionnelle vous aide à répondre à des questions spécifiques concernant vos données. Il convient de comprendre certaines différences importantes lorsque vous utilisez la mise en forme conditionnelle dans un rapport de tableau croisé dynamique :
Si vous changez la disposition du rapport de tableau croisé dynamique en filtrant, masquant les niveaux, réduisant et développant les niveaux ou en déplaçant un champ, la mise en forme conditionnelle est préservée tant que les champs des données sous-jacentes ne sont pas supprimés.
L’étendue de la mise en forme conditionnelle des champs de la zone Valeurs peut être basée sur la hiérarchie des données et est déterminée par tous les enfants visibles (le niveau inférieur suivant dans la hiérarchie) d’un parent (le niveau supérieur suivant dans la hiérarchie) sur les lignes pour une ou plusieurs colonnes, ou sur les colonnes pour une ou plusieurs lignes.
REMARQUE : Dans la hiérarchie des données, les enfants n’héritent pas de la mise en forme conditionnelle du parent et vice-versa.
L’étendue de la mise en forme conditionnelle des champs de la zone Valeurs peut être définie de trois manières : par sélection, par champ correspondant et par champ de valeur.
Pour plus d’informations, voir Appliquer une mise en forme conditionnelle.

## DPCache_Weekly Work hrs at 20-0 (hidden)
Unique No | Inactive | Time Capture Required: | Projet | Sub-Project | Phase | Resource | Name | Stream | Sub-stream | Saputo/SI | Sourcing | Resource2 | Source_Organization | Total | Capex/Opex | Global / Localization | Resource Category | Actual Work Hrs | Remaining Work Hrs | Work Hrs | Start | FinisH | _Deliverable | 04/09/2017 | 11/09/2017 | 18/09/2017 | 25/09/2017 | 02/10/2017 | 09/10/2017 | 16/10/2017 | 23/10/2017 | 30/10/2017 | 06/11/2017 | 13/11/2017 | 20/11/2017 | 27/11/2017 | 04/12/2017 | 11/12/2017 | 18/12/2017 | 25/12/2017 | 01/01/2018 | 08/01/2018 | 15/01/2018 | 22/01/2018 | 29/01/2018 | 05/02/2018 | 12/02/2018 | 19/02/2018 | 26/02/2018 | 05/03/2018 | 12/03/2018 | 19/03/2018 | 26/03/2018 | 02/04/2018 | 09/04/2018 | 16/04/2018 | 23/04/2018 | 30/04/2018 | 07/05/2018 | 14/05/2018 | 21/05/2018 | 28/05/2018
1049107 | No | No | Argentina | Argentina | 03-Design/Build | Hebert; Dany | Complete Stakeholder Assessment in preparation for 1st communication cascade (2 VP's) | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | OpEx | Localization | IT - Internal | 0 | 0 | 0 | 2016-09-25 | 2016-09-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049108 | No | No | Argentina | Argentina | 03-Design/Build | Hebert; Dany | Validate deck for CM training for managers | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | OpEx | Localization | IT - Internal | 0 | 0 | 0 | 2016-06-15 | 2016-06-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049109 | No | No | Argentina | Argentina | 03-Design/Build | Hebert; Dany | Collect Employee List to Be Role Mapped | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | OpEx | Localization | IT - Internal | 0 | 0 | 0 | 2016-05-02 | 2016-05-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049110 | No | No | Argentina | Argentina | 03-Design/Build | Hebert; Dany | Prepare Role Mapping Onboarding Deck | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | OpEx | Localization | IT - Internal | 0 | 0 | 0 | 2016-05-02 | 2016-05-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049111 | No | No | Argentina | Argentina | 03-Design/Build | Hebert; Dany | Validate Kick-Off Deck | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | OpEx | Localization | IT - Internal | 0 | 0 | 0 | 2016-05-09 | 2016-05-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049112 | No | No | Argentina | Argentina | 03-Design/Build | Hebert; Dany | Validate Deck on Role Catalogue Change Control Process | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | OpEx | Localization | IT - Internal | 0 | 0 | 0 | 2016-05-09 | 2016-05-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049113 | No | No | Argentina | Argentina | 03-Design/Build | Hebert; Dany | Align Functional team on Roles Catalog Change control process | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | OpEx | Localization | IT - Internal | 0 | 0 | 0 | 2016-06-10 | 2016-06-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049114 | No | No | Argentina | Argentina | 03-Design/Build | Hebert; Dany | Validate RM Status Report | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | OpEx | Localization | IT - Internal | 0 | 0 | 0 | 2016-05-30 | 2016-05-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049115 | No | No | Argentina | Argentina | 03-Design/Build | Hebert; Dany | Develop RMS Training for the Business | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | OpEx | Localization | IT - Internal | 0 | 0 | 0 | 2016-05-16 | 2016-05-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049116 | No | No | Argentina | Argentina | 03-Design/Build | Hebert; Dany | Review first draft of VR plan with Fernando and Determine approach to cascade | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | OpEx | Localization | IT - Internal | 0 | 0 | 0 | 2016-06-03 | 2016-06-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049117 | No | No | Argentina | Argentina | 03-Design/Build | Hebert; Dany | Validate presentation | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | OpEx | Localization | IT - Internal | 0 | 0 | 0 | 2016-09-25 | 2016-09-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049118 | No | No | Argentina | Argentina | 03-Design/Build | Hebert; Dany | Validate Key Users On boarding deck | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | OpEx | Localization | IT - Internal | 0 | 0 | 0 | 2016-09-25 | 2016-09-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049119 | No | No | Argentina | Argentina | 06-Hypercare | Hebert; Dany | Argentina Production Support-CM | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | OpEx | Localization | IT - Internal | 0 | 0 | 0 | 2017-03-20 | 2017-03-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049120 | No | No | Argentina | Argentina | 01-Preparation | Hebert; Dany | Argentina Project - Sharepoint Access - | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | CapEx | Localization | IT - Internal | 0 | 0 | 0 | 2015-12-01 | 2015-12-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049121 | Yes | Yes | Argentina | Argentina | 01-Preparation | Vasudevan; Ramesh | Argentina Project - Sharepoint Access - | PTP | FUN | SI | Onshore | Vasudevan; Ramesh | SAP | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2015-12-01 | 2015-12-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049122 | Yes | No | Argentina | Argentina | 01-Preparation | Surneni; Parandama | Argentina Project - Sharepoint Access - | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2015-12-01 | 2015-12-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049123 | Yes | No | Argentina | Argentina | 04-Test | Surneni; Parandama | SIT 2 - PTM - Break/Fix | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 59 | 0 | 59 | 2016-11-14 | 2016-12-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049124 | Yes | No | Argentina | Argentina | 04-Test | Surneni; Parandama | SIT 1 - Break/Fix | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-09-12 | 2016-09-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049125 | Yes | No | Argentina | Argentina | 04-Test | Surneni; Parandama | SIT 2 - Prep | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 72 | 0 | 72 | 2016-10-17 | 2016-11-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049126 | Yes | No | Argentina | Argentina | 02-Analyze | Surneni; Parandama | PTM - Identfy Changes in GD for Localization ARG | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-02-29 | 2016-02-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049127 | Yes | No | Argentina | Argentina | 03-Design/Build | Surneni; Parandama | ARG : DB - Functional Specifications and UT - PTM | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 52 | 0 | 52 | 2016-05-24 | 2016-08-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049128 | Yes | No | Argentina | Argentina | 03-Design/Build | Surneni; Parandama | ARG : DB - SDD - PTM | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 88 | 0 | 88 | 2016-05-16 | 2016-06-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049129 | Yes | No | Argentina | Argentina | 10-PCR | Surneni; Parandama | CR-Defect 6666 and Production Incident for currency for AR03 | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | OpEx | Localization | IT - External | 60 | 0 | 60 | 2017-05-12 | 2017-06-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049130 | Yes | No | Argentina | Argentina | 04-Test | Surneni; Parandama | Mock2 - Prepare | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | OpEx | Localization | IT - External | 58 | 0 | 58 | 2016-10-05 | 2016-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049131 | Yes | No | Argentina | Argentina | 04-Test | Surneni; Parandama | Mock2 - Support | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-03 | 2016-10-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049132 | Yes | No | Argentina | Argentina | 03-Design/Build | Surneni; Parandama | Solution Design Document (SDD) | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 14 | 0 | 14 | 2016-08-17 | 2016-09-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049133 | Yes | No | Argentina | Argentina | 04-Test | Surneni; Parandama | SIT 1 - Run Tests | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 48 | 0 | 48 | 2016-09-12 | 2016-09-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049134 | Yes | No | Argentina | Argentina | 04-Test | Surneni; Parandama | Prep PRD for performance testing | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 12 | 0 | 12 | 2016-10-31 | 2016-11-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049135 | Yes | No | Argentina | Argentina | 03-Design/Build | Surneni; Parandama | Functional Specification (FSD) | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 12 | 0 | 12 | 2016-08-11 | 2016-08-26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049136 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Surneni; Parandama | Transition to Hypercare - PTM | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 35 | 0 | 35 | 2017-01-30 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049137 | Yes | No | Argentina | Argentina | 04-Test | Surneni; Parandama | SIT 2 - PTM - Run Tests | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 63 | 0 | 63 | 2016-11-07 | 2016-11-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049138 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Surneni; Parandama | Dry Run - Prepare | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 6 | 0 | 6 | 2016-11-14 | 2016-11-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049139 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Surneni; Parandama | Dry Run - Support | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 10 | 0 | 10 | 2016-12-12 | 2016-12-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049140 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Surneni; Parandama | Dry Run - Validate | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 18 | 0 | 18 | 2016-11-21 | 2016-12-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049141 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Surneni; Parandama | UAT - Break/Fix and document work around | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 76 | 0 | 76 | 2016-12-12 | 2017-01-26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049142 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Surneni; Parandama | Cut Over - Prepare | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049143 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Surneni; Parandama | Cut Over - Support | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 57 | 0 | 57 | 2016-12-19 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049144 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Surneni; Parandama | Cut Over - Validate | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 106 | 0 | 106 | 2016-12-19 | 2017-01-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049145 | Yes | No | Argentina | Argentina | 06-Hypercare | Surneni; Parandama | HC - Provide end User Support - PTM | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | OpEx | Localization | IT - External | 80 | 0 | 80 | 2017-02-06 | 2017-02-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049146 | Yes | No | Argentina | Argentina | 06-Hypercare | Surneni; Parandama | HC - Manage Defects | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 24 | 0 | 24 | 2017-02-06 | 2017-02-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049147 | Yes | No | Argentina | Argentina | 06-Hypercare | Surneni; Parandama | HC - Break/Fix - PTM | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 112 | 0 | 112 | 2017-02-13 | 2017-03-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049148 | No | Yes | Argentina | Argentina | 01-Preparation | Palmer; Josh | Argentina Project - Sharepoint Access - | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2015-12-01 | 2015-12-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049149 | No | Yes | Argentina | Argentina | 04-Test | Palmer; Josh | Prep PRD for performance testing | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-11 | 2016-10-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049150 | No | Yes | Argentina | Argentina | 06-Hypercare | Palmer; Josh | HC - Break/Fix | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 121 | 0 | 121 | 2017-02-20 | 2017-04-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049151 | No | Yes | Argentina | Argentina | 04-Test | Palmer; Josh | Mock1 - Prepare | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | OpEx | Localization | IT - External | 42 | 0 | 42 | 2016-08-22 | 2016-09-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049152 | No | Yes | Argentina | Argentina | 04-Test | Palmer; Josh | SIT 1 - Break/Fix | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 324.5 | 0 | 324.5 | 2016-09-06 | 2016-10-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049153 | No | Yes | Argentina | Argentina | 04-Test | Palmer; Josh | Mock1 - Support | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | OpEx | Localization | IT - External | 5 | 0 | 5 | 2016-08-29 | 2016-09-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049154 | No | Yes | Argentina | Argentina | 04-Test | Palmer; Josh | Mock2 - Validate | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | OpEx | Localization | IT - External | 2 | 0 | 2 | 2016-10-17 | 2016-10-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049155 | No | Yes | Argentina | Argentina | 04-Test | Palmer; Josh | SIT 2 - Prep | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-10 | 2016-10-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049156 | No | Yes | Argentina | Argentina | 04-Test | Palmer; Josh | LOG - SIT 2 - Run Tests | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 27 | 0 | 27 | 2016-11-05 | 2016-11-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049157 | No | Yes | Argentina | Argentina | 04-Test | Palmer; Josh | LOG - SIT 2 - Manage Defects | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 5 | 0 | 5 | 2016-11-21 | 2016-12-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049158 | No | Yes | Argentina | Argentina | 04-Test | Palmer; Josh | LOG - SIT 2 - Break/Fix | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 301 | 0 | 301 | 2016-10-31 | 2016-12-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049159 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Palmer; Josh | Dry Run - Prepare | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-11-07 | 2016-11-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049160 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Palmer; Josh | Dry Run - Support | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 6 | 0 | 6 | 2016-12-07 | 2016-12-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049161 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Palmer; Josh | Dry Run - Validate | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-11-07 | 2016-11-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049162 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Palmer; Josh | UAT - Break/Fix and document work around | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 408 | 0 | 408 | 2016-12-05 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049163 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Palmer; Josh | Cut Over - Prepare | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049164 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Palmer; Josh | Cut Over - Support | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 21 | 0 | 21 | 2016-12-20 | 2017-02-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049165 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Palmer; Josh | Cut Over - Validate | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-19 | 2016-12-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049166 | No | Yes | Argentina | Argentina | 06-Hypercare | Palmer; Josh | HC - Provide end User Support | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | OpEx | Localization | IT - External | 116 | 0 | 116 | 2017-02-06 | 2017-02-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049167 | No | Yes | Argentina | Argentina | 04-Test | Palmer; Josh | Mock2 - Prepare | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2016-09-03 | 2016-09-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049168 | No | Yes | Argentina | Argentina | 04-Test | Palmer; Josh | Mock2 - Support | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-07 | 2016-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049169 | No | Yes | Argentina | Argentina | 01-Preparation | Palmer; Josh | LOG Prepare Arg - GD integration | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 15 | 0 | 15 | 2016-02-24 | 2016-02-26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049170 | No | Yes | Argentina | Argentina | 04-Test | Palmer; Josh | SIT 1 - Manage Defects | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 5 | 0 | 5 | 2016-10-11 | 2016-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049171 | No | Yes | Argentina | Argentina | 04-Test | Palmer; Josh | SIT 1 - Run Tests | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 2 | 0 | 2 | 2016-10-15 | 2016-10-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049172 | No | Yes | Argentina | Argentina | 02-Analyze | Palmer; Josh | LOG - Identify changes in GD for Localization ARG | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 173 | 0 | 173 | 2016-02-29 | 2016-04-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049173 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Palmer; Josh | Transition to Hypercare - LOG | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-28 | 2016-12-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049174 | No | Yes | Argentina | Argentina | 03-Design/Build | Palmer; Josh | ARG : DB - Functional Specifications and UT - LOG | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-05-02 | 2016-05-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049175 | No | Yes | Argentina | Argentina | 03-Design/Build | Palmer; Josh | ARG : DB - SDD - LOG | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-05-02 | 2016-05-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049176 | No | Yes | Argentina | Argentina | 06-Hypercare | Palmer; Josh | Argentina Production Support-LOG | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | OpEx | Localization | IT - External | 82 | 0 | 82 | 2017-03-06 | 2017-06-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049177 | No | Yes | Argentina | Argentina | 03-Design/Build | Canimo; Roland | ARG : DB - SDD - LOG | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-05-02 | 2016-05-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049178 | No | Yes | Argentina | Argentina | 03-Design/Build | Canimo; Roland | ARG : DB - Functional Specifications and UT - LOG | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 44 | 0 | 44 | 2016-05-30 | 2016-06-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049179 | No | Yes | Argentina | Argentina | 04-Test | Canimo; Roland | Mock2 - Prepare | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | OpEx | Localization | IT - External | 16 | 0 | 16 | 2016-10-03 | 2016-10-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049180 | No | Yes | Argentina | Argentina | 04-Test | Canimo; Roland | Mock1 - Support | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2016-07-15 | 2016-07-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049181 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Canimo; Roland | Transition to Hypercare - LOG | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 124 | 0 | 124 | 2017-01-23 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049182 | No | Yes | Argentina | Argentina | 02-Analyze | Canimo; Roland | LOG - Identify changes in GD for Localization ARG | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 132 | 0 | 132 | 2016-03-07 | 2016-04-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049183 | No | Yes | Argentina | Argentina | 04-Test | Canimo; Roland | SIT 1 - Run Tests | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-09-05 | 2016-09-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049184 | No | Yes | Argentina | Argentina | 04-Test | Canimo; Roland | SIT 1 - Manage Defects | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-09-06 | 2016-09-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049185 | No | Yes | Argentina | Argentina | 04-Test | Canimo; Roland | Mock2 - Support | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | OpEx | Localization | IT - External | 87 | 0 | 87 | 2016-10-07 | 2016-11-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049186 | No | Yes | Argentina | Argentina | 04-Test | Canimo; Roland | LOG - SIT 2 - Manage Defects | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-24 | 2016-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049187 | No | Yes | Argentina | Argentina | 01-Preparation | Canimo; Roland | LOG Prepare Arg - GD integration | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 44 | 0 | 44 | 2016-02-22 | 2016-02-26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049188 | No | Yes | Argentina | Argentina | 06-Hypercare | Canimo; Roland | HC - Provide end User Support | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | OpEx | Localization | IT - External | 116 | 0 | 116 | 2017-02-06 | 2017-02-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049189 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Canimo; Roland | Cut Over - Validate | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-19 | 2016-12-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049190 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Canimo; Roland | Cut Over - Prepare | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049191 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Canimo; Roland | Cut Over - Support | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-19 | 2016-12-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049192 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Canimo; Roland | Dry Run - Validate | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-11-07 | 2016-11-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049193 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Canimo; Roland | UAT - Break/Fix and document work around | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 326 | 0 | 326 | 2016-12-05 | 2017-01-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049194 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Canimo; Roland | Dry Run - Support | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-11-15 | 2016-11-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049195 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Canimo; Roland | Dry Run - Prepare | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 60 | 0 | 60 | 2016-11-07 | 2016-11-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049196 | No | Yes | Argentina | Argentina | 04-Test | Canimo; Roland | LOG - SIT 2 - Break/Fix | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 94 | 0 | 94 | 2016-10-31 | 2016-12-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049197 | No | Yes | Argentina | Argentina | 04-Test | Canimo; Roland | LOG - SIT 2 - Run Tests | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 105 | 0 | 105 | 2016-11-14 | 2016-11-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049198 | No | Yes | Argentina | Argentina | 04-Test | Canimo; Roland | SIT 2 - Prep | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-10 | 2016-10-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049199 | No | Yes | Argentina | Argentina | 04-Test | Canimo; Roland | Mock2 - Validate | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-17 | 2016-10-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049200 | No | Yes | Argentina | Argentina | 04-Test | Canimo; Roland | SIT 1 - Break/Fix | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 275 | 0 | 275 | 2016-09-12 | 2016-10-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049201 | No | Yes | Argentina | Argentina | 03-Design/Build | Canimo; Roland | ARG KT visit | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 15 | 0 | 15 | 2016-08-15 | 2016-08-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049202 | No | Yes | Argentina | Argentina | 04-Test | Canimo; Roland | Mock1 - Prepare | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2016-07-11 | 2016-07-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049203 | No | Yes | Argentina | Argentina | 06-Hypercare | Canimo; Roland | HC - Break/Fix | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 56 | 0 | 56 | 2017-02-06 | 2017-02-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049204 | No | Yes | Argentina | Argentina | 04-Test | Canimo; Roland | Prep PRD for performance testing | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-11 | 2016-10-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049205 | No | Yes | Argentina | Argentina | 01-Preparation | Canimo; Roland | Argentina Project - Sharepoint Access - | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2015-12-01 | 2015-12-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049206 | No | Yes | Argentina | Argentina | 06-Hypercare | Aragon; Marvin | Argentina Production Support-SEC | SEC | SEC | SI | Offshore | Aragon; Marvin | Accenture | Yes | OpEx | Localization | IT - External | 99 | 0 | 99 | 2017-03-06 | 2017-07-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049207 | No | Yes | Argentina | Argentina | 06-Hypercare | SerranoMartinez; Efren | Argentina Production Support-LOG | LOG | FUN | SI | Onshore | SerranoMartinez; Efren | IBM | Yes | OpEx | Localization | IT - External | 688 | 0 | 688 | 2017-03-06 | 2017-07-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049208 | No | Yes | Argentina | Argentina | 06-Hypercare | Barreto; Bruno | Argentina Production Support-OTC | OTC | FUN | Saputo | Onshore | Barreto; Bruno | Saputo | Yes | OpEx | Localization | IT - Internal | 123.2 | 0 | 123.2 | 2017-03-06 | 2017-07-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049209 | Yes | No | Argentina | Argentina | 06-Hypercare | Thorat; Yogini | Argentina Production Support-PTM | PTM | FUN | SI | Onshore | Thorat; Yogini | IBM | Yes | OpEx | Localization | IT - External | 292 | 0 | 292 | 2017-03-13 | 2017-06-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049210 | No | Yes | Argentina | Argentina | 06-Hypercare | Gomare; Shankar | Argentina Production Support-DEV | DEV | DEV | Saputo | Onshore | Gomare; Shankar | Saputo | Yes | OpEx | Localization | IT - Internal | 6 | 0 | 6 | 2017-05-29 | 2017-06-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049211 | No | Yes | Argentina | Argentina |  | Gomare; Shankar | Knowledge_Transfer_AMS - DEV | DEV | DEV | Saputo | Onshore | Gomare; Shankar | Saputo | Yes | OpEx | Global | IT - Internal | 8 | 0 | 8 | 2017-05-23 | 2017-05-26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049212 | No | Yes | Argentina | Argentina |  | Gupta; Debapriya | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Gupta; Debapriya | IBM | Yes | OpEx | Global | IT - External | 0 | 0 | 0 | 2017-05-23 | 2017-05-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049213 | No | Yes | Argentina | Argentina | 06-Hypercare | Gupta; Debapriya | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | Gupta; Debapriya | IBM | Yes | OpEx | Localization | IT - External | 128.5 | 0 | 128.5 | 2017-02-27 | 2017-07-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049214 | No | Yes | Argentina | Argentina | 06-Hypercare | Gupta; Debapriya | ARG tax redesign- DEV | DEV | DEV | SI | Offshore | Gupta; Debapriya | IBM | Yes | OpEx | Localization | IT - External | 60 | 60 | 120 | 2017-08-02 | 2017-09-22 |  | 15 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049215 | No | Yes | Argentina | Argentina | 06-Hypercare | Salunke; Sachin | Argentina Production Support-PMO | OTC | FUN | SI | Offshore | Salunke; Sachin | IBM | Yes | OpEx | Localization | IT - External | 216 | 0 | 216 | 2017-03-20 | 2017-05-26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049216 | No | Yes | Argentina | Argentina | 06-Hypercare | Salunke; Sachin | Argentina Production Support-OTC | OTC | FUN | SI | Offshore | Salunke; Sachin | IBM | Yes | OpEx | Localization | IT - External | 324 | 0 | 324 | 2017-03-13 | 2017-07-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049217 | Yes | No | Argentina | Argentina | 04-Test | Moore; Laura | SIT 2 - PTM - Run Tests | PTP | FUN | SI | Onshore | Moore; Laura | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-17 | 2016-10-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049218 | Yes | No | Argentina | Argentina | 04-Test | Moore; Laura | SIT 2 - PTM - Break/Fix | PTP | FUN | SI | Onshore | Moore; Laura | IBM | Yes | CapEx | Localization | IT - External | 159 | 0 | 159 | 2016-11-14 | 2016-12-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049219 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Moore; Laura | UAT - Break/Fix and document work around | PTP | FUN | SI | Onshore | Moore; Laura | IBM | Yes | CapEx | Localization | IT - External | 142 | 0 | 142 | 2016-12-28 | 2017-01-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049220 | Yes | No | Argentina | Argentina | 06-Hypercare | Moore; Laura | HC - Provide end User Support - PTM | PTP | FUN | SI | Onshore | Moore; Laura | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2017-01-23 | 2017-01-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049221 | Yes | No | Argentina | Argentina | 06-Hypercare | Moore; Laura | HC - Break/Fix - PTM | PTP | FUN | SI | Onshore | Moore; Laura | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049222 | Yes | No | Argentina | Argentina | 04-Test | Moore; Laura | SIT 2 - PTP - Break/Fix | PTP | FUN | SI | Onshore | Moore; Laura | IBM | Yes | CapEx | Localization | IT - External | 88 | 0 | 88 | 2016-11-18 | 2016-12-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049223 | Yes | No | Argentina | Argentina | 04-Test | Moore; Laura | SIT 2 - PTP - Run Tests | PTP | FUN | SI | Onshore | Moore; Laura | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-24 | 2016-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049224 | No | Yes | Argentina | Argentina | 03-Design/Build | Medina; Julio Victor | Code, Tech spec. and FUT support | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 2 | 0 | 2 | 2016-08-15 | 2016-10-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049225 | No | Yes | Argentina | Argentina | 04-Test | Medina; Julio Victor | Project Management and Planning for SEC | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 225 | 0 | 225 | 2016-09-26 | 2016-11-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049226 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Medina; Julio Victor | UAT Defect Resolution | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 217 | 0 | 217 | 2016-12-19 | 2017-01-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049227 | No | Yes | Argentina | Argentina | 03-Design/Build | Medina; Julio Victor | Composite Role Design | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 0 | 0 | 0 | 2016-09-19 | 2016-09-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049228 | No | Yes | Argentina | Argentina | 03-Design/Build | Medina; Julio Victor | SoD Analysis and Remediation | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 8 | 0 | 8 | 2016-09-30 | 2016-10-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049229 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Medina; Julio Victor | GRC AC - Cutover planning and Exucution | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 55 | 0 | 55 | 2016-10-19 | 2016-12-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049230 | No | Yes | Argentina | Argentina | 06-Hypercare | Medina; Julio Victor | GRC AC - Hypercare | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 40 | 0 | 40 | 2017-02-13 | 2017-02-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049231 | No | Yes | Argentina | Argentina | 06-Hypercare | Medina; Julio Victor | Argentina Production Support-SEC | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | OpEx | Localization | IT - Internal | 104 | 0 | 104 | 2017-05-29 | 2017-06-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049232 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Medina; Julio Victor | Management (Cutover/Go-live) | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 87 | 0 | 87 | 2016-11-14 | 2017-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049233 | No | Yes | Argentina | Argentina | 06-Hypercare | Medina; Julio Victor | Management (Hypercare) | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 58 | 0 | 58 | 2017-02-06 | 2017-02-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049234 | No | Yes | Argentina | Argentina | 04-Test | Medina; Julio Victor | SoD Analysis and Remediation | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 23 | 0 | 23 | 2016-11-07 | 2016-11-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049235 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Medina; Julio Victor | SoD Analysis and Remediation | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 32 | 0 | 32 | 2016-12-05 | 2016-12-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049236 | No | Yes | Argentina | Argentina | 03-Design/Build | Medina; Julio Victor | Security Design Workshops | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 46 | 0 | 46 | 2016-09-13 | 2016-10-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049237 | No | Yes | Argentina | Argentina | 04-Test | Medina; Julio Victor | Security Role FUT | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 0 | 0 | 0 | 2016-09-19 | 2016-09-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049238 | No | Yes | Argentina | Argentina | 04-Test | Medina; Julio Victor | SIT 2 Defect Resolution | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 0 | 0 | 0 | 2016-10-22 | 2016-10-22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049239 | No | Yes | Argentina | Argentina | 04-Test | Medina; Julio Victor | GRC AC - SIT Execution | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 109 | 0 | 109 | 2016-10-24 | 2016-12-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049240 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Medina; Julio Victor | Cutover Planning and Execution | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 82 | 0 | 82 | 2016-10-19 | 2017-02-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049241 | No | Yes | Argentina | Argentina | 03-Design/Build | Medina; Julio Victor | SAP GRC AC - Design | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 25 | 0 | 25 | 2016-09-13 | 2016-10-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049242 | No | Yes | Argentina | Argentina | 04-Test | Bancoro; Evencio | SIT 1 - Run Tests | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 129 | 0 | 129 | 2016-09-06 | 2016-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049243 | No | Yes | Argentina | Argentina | 04-Test | Bancoro; Evencio | LOG - SIT 2 - Break/Fix | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 149 | 0 | 149 | 2016-10-24 | 2016-12-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049244 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Bancoro; Evencio | UAT - Manage Defects | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 29 | 0 | 29 | 2016-12-05 | 2017-01-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049245 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Bancoro; Evencio | Dry Run - Validate | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 0 | 0 | 0 | 2016-11-07 | 2016-11-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049246 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Bancoro; Evencio | UAT - Break/Fix and document work around | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 111 | 0 | 111 | 2016-12-05 | 2017-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049247 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Bancoro; Evencio | Cut Over - Validate | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 150 | 0 | 150 | 2016-12-19 | 2017-02-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049248 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Bancoro; Evencio | Transition to Hypercare - LOG | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 10 | 0 | 10 | 2017-01-30 | 2017-02-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049249 | No | Yes | Argentina | Argentina | 04-Test | Bancoro; Evencio | Updates concepts decks | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | OpEx | Localization | IT - Internal | 23 | 0 | 23 | 2016-09-19 | 2016-09-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049250 | No | Yes | Argentina | Argentina | 04-Test | Bancoro; Evencio | SIT 1 - Break/Fix | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 55 | 0 | 55 | 2016-10-11 | 2016-10-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049251 | No | Yes | Argentina | Argentina | 06-Hypercare | Bancoro; Evencio | Argentina Production Support-LOG | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | OpEx | Localization | IT - Internal | 354 | 0 | 354 | 2017-03-07 | 2017-06-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049252 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Bancoro; Evencio | UAT - Run Tests | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 25 | 0 | 25 | 2016-12-06 | 2017-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049253 | No | Yes | Argentina | Argentina | 06-Hypercare | Bancoro; Evencio | HC - Provide end User Support | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | OpEx | Localization | IT - Internal | 244 | 0 | 244 | 2016-12-01 | 2017-03-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049254 | No | Yes | Argentina | Argentina | 04-Test | Singh; Kuldeep | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Localization | IT - External | 40 | 0 | 40 | 2016-09-19 | 2016-09-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049255 | No | Yes | Argentina | Argentina | 06-Hypercare | Singh; Kuldeep | Hypercare Support - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049256 | No | Yes | Argentina | Argentina | 04-Test | Singh; Kuldeep | Test - MDSS Project Management - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Localization | IT - External | 72 | 0 | 72 | 2016-10-24 | 2016-11-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049257 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Singh; Kuldeep | MDSS Project Management (Cutover/Go-live) - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Localization | IT - External | 156 | 0 | 156 | 2016-12-12 | 2017-02-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049258 | No | Yes | Argentina | Argentina | 06-Hypercare | Singh; Kuldeep | MDSS Project Management (Hypercare) - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2017-01-30 | 2017-01-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049259 | No | Yes | Argentina | Argentina | 04-Test | Singh; Kuldeep | Mock1 Closure - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-09-11 | 2016-09-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049260 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Singh; Kuldeep | Cutover Closure Memo - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2017-01-20 | 2017-01-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049261 | No | Yes | Argentina | Argentina | 03-Design/Build | Singh; Kuldeep | ARG : DB - Conduct Mock 0 Load in DEV - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Localization | IT - External | 80 | 0 | 80 | 2016-05-30 | 2016-06-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049262 | No | Yes | Argentina | Argentina | 03-Design/Build | Singh; Kuldeep | ARG : DB - WP Obtain the Data Verification Signoff sheet - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-06-13 | 2016-06-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049263 | No | Yes | Argentina | Argentina | 03-Design/Build | Singh; Kuldeep | ARG : DB - Conduct Mock 1 Load in QA - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Localization | IT - External | 152 | 0 | 152 | 2016-06-27 | 2016-07-22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049264 | No | Yes | Argentina | Argentina | 03-Design/Build | Singh; Kuldeep | ARG : DB - MDG 333 Mock Closure Memo - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Localization | IT - External | 296 | 0 | 296 | 2016-07-25 | 2016-09-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049265 | No | Yes | Argentina | Argentina | 04-Test | Singh; Kuldeep | Mock2 Closure Memo - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Localization | IT - External | 8 | 0 | 8 | 2016-10-31 | 2016-11-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049266 | No | Yes | Argentina | Argentina | 04-Test | Kovacevich; Vladimir | SIT 1 - Break/Fix | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 87 | 0 | 87 | 2016-09-12 | 2016-11-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049267 | No | Yes | Argentina | Argentina | 03-Design/Build | Kovacevich; Vladimir | ARG KT visit | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-08-08 | 2016-08-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049268 | No | Yes | Argentina | Argentina | 04-Test | Kovacevich; Vladimir | OTC - SIT 2 - Run Tests | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-24 | 2016-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049269 | No | Yes | Argentina | Argentina | 06-Hypercare | Kovacevich; Vladimir | HC - Break/Fix | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 104 | 0 | 104 | 2017-02-06 | 2017-03-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049270 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Kovacevich; Vladimir | Transition to Hypercare - OTC | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 102 | 0 | 102 | 2017-01-23 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049271 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Kovacevich; Vladimir | UAT - Run Tests | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 32 | 0 | 32 | 2016-12-27 | 2016-12-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049272 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Kovacevich; Vladimir | UAT - Break/Fix and document work around | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 225 | 0 | 225 | 2016-12-05 | 2017-01-22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049273 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Kovacevich; Vladimir | Dry Run - Prepare | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-11-07 | 2016-11-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049274 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Kovacevich; Vladimir | Dry Run - Support | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-11-14 | 2016-11-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049275 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Kovacevich; Vladimir | Dry Run - Validate | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-11-28 | 2016-11-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049276 | No | Yes | Argentina | Argentina | 04-Test | Kovacevich; Vladimir | OTC - SIT 2 - Break/Fix | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 44 | 0 | 44 | 2016-12-19 | 2016-12-22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049277 | No | Yes | Argentina | Argentina | 04-Test | Kovacevich; Vladimir | SIT 1 - Run Tests | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 4 | 0 | 4 | 2016-10-10 | 2016-10-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049278 | Yes | No | Argentina | Argentina | 06-Hypercare | Nguyen; Tri | HC - Break/Fix - RTR | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049279 | Yes | No | Argentina | Argentina | 06-Hypercare | Nguyen; Tri | HC - Provide end User Support - RTR | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2017-01-02 | 2017-01-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049280 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Nguyen; Tri | UAT - Break/Fix and document work around | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049281 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Nguyen; Tri | Cut Over - Prepare | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049282 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Nguyen; Tri | Cut Over - Support | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-19 | 2016-12-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049283 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Nguyen; Tri | Cut Over - Validate | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-19 | 2016-12-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049284 | Yes | No | Argentina | Argentina | 04-Test | Nguyen; Tri | SIT 2 - RTR - Run Tests | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 123 | 0 | 123 | 2016-10-31 | 2016-12-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049285 | Yes | No | Argentina | Argentina | 04-Test | Nguyen; Tri | SIT 2 - RTR - Manage Defects | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-24 | 2016-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049286 | Yes | No | Argentina | Argentina | 04-Test | Nguyen; Tri | SIT 2 - RTR - Break/Fix | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 44 | 0 | 44 | 2016-11-14 | 2016-11-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049287 | Yes | No | Argentina | Argentina | 04-Test | Nguyen; Tri | Updates concepts decks | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-11 | 2016-10-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049288 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Nguyen; Tri | Dry Run - Validate | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-11-14 | 2016-11-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049289 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Nguyen; Tri | UAT - Run Tests | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049290 | Yes | No | Argentina | Argentina | 04-Test | Nguyen; Tri | SIT 1 - Break/Fix | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-09-05 | 2016-09-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049291 | Yes | No | Argentina | Argentina | 04-Test | Nguyen; Tri | Mock2 - Validate | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-11 | 2016-10-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049292 | Yes | No | Argentina | Argentina | 04-Test | Nguyen; Tri | SIT 2 - RTR - Prep | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 48 | 0 | 48 | 2016-10-13 | 2016-10-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049293 | Yes | No | Argentina | Argentina | 03-Design/Build | Nguyen; Tri | Unit testing Configuration Documentation | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 36 | 0 | 36 | 2016-09-06 | 2016-09-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049294 | Yes | No | Argentina | Argentina | 03-Design/Build | Nguyen; Tri | Configuration | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-07-18 | 2016-07-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049295 | Yes | No | Argentina | Argentina | 03-Design/Build | Nguyen; Tri | Solution Design Document (SDD) | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 44 | 0 | 44 | 2016-08-15 | 2016-08-26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049296 | Yes | No | Argentina | Argentina | 04-Test | Nguyen; Tri | SIT 1 - Run Tests | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 129 | 0 | 129 | 2016-09-12 | 2016-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049297 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Reed; Rodney | Interim reporting (400hours) | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-12 | 2016-12-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049298 | Yes | No | Argentina | Argentina | 04-Test | Reed; Rodney | SIT 2 - RTR - Prep | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 15 | 0 | 15 | 2016-10-24 | 2016-11-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049299 | Yes | No | Argentina | Argentina | 04-Test | Reed; Rodney | Mock2 - Validate | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-11 | 2016-11-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049300 | Yes | No | Argentina | Argentina | 04-Test | Reed; Rodney | SIT 1 - Break/Fix | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-09-05 | 2016-09-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049301 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Reed; Rodney | Transition to Hypercare | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 40 | 0 | 40 | 2017-01-23 | 2017-02-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049302 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Reed; Rodney | UAT - Run Tests | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 8 | 0 | 8 | 2016-12-12 | 2016-12-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049303 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Reed; Rodney | Dry Run - Validate | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 10 | 0 | 10 | 2016-12-05 | 2016-12-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049304 | Yes | No | Argentina | Argentina | 04-Test | Reed; Rodney | Updates concepts decks | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-11 | 2016-11-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049305 | Yes | No | Argentina | Argentina | 04-Test | Reed; Rodney | SIT 2 - RTR - Break/Fix | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 31 | 0 | 31 | 2016-10-31 | 2016-12-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049306 | Yes | No | Argentina | Argentina | 04-Test | Reed; Rodney | SIT 2 - RTR - Manage Defects | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-24 | 2016-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049307 | Yes | No | Argentina | Argentina | 04-Test | Reed; Rodney | SIT 2 - RTR - Run Tests | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 44 | 0 | 44 | 2016-11-07 | 2016-12-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049308 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Reed; Rodney | Cut Over - Validate | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-19 | 2016-12-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049309 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Reed; Rodney | Cut Over - Support | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 84 | 0 | 84 | 2017-01-09 | 2017-01-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049310 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Reed; Rodney | Cut Over - Prepare | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 15 | 0 | 15 | 2016-12-12 | 2016-12-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049311 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Reed; Rodney | UAT - Break/Fix and document work around | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 44 | 0 | 44 | 2017-01-16 | 2017-01-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049312 | Yes | No | Argentina | Argentina | 06-Hypercare | Reed; Rodney | HC - Provide end User Support - RTR | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | OpEx | Localization | IT - External | 106 | 0 | 106 | 2017-02-27 | 2017-03-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049313 | Yes | No | Argentina | Argentina | 06-Hypercare | Reed; Rodney | HC - Manage Defects | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-27 | 2017-02-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049314 | Yes | No | Argentina | Argentina | 06-Hypercare | Reed; Rodney | HC - Break/Fix - RTR | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 132 | 0 | 132 | 2017-02-06 | 2017-02-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049315 | Yes | No | Argentina | Argentina | 04-Test | Kothari; Sanjay | SIT 1 - Run Tests | OTC | FUN | SI | Onshore | Kothari; Sanjay | IBM | Yes | CapEx | Localization | IT - External | 15 | 0 | 15 | 2016-09-19 | 2016-09-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049316 | Yes | No | Argentina | Argentina | 04-Test | Kothari; Sanjay | SIT 1 - Break/Fix | OTC | FUN | SI | Onshore | Kothari; Sanjay | IBM | Yes | CapEx | Localization | IT - External | 172 | 0 | 172 | 2016-09-12 | 2016-12-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049317 | Yes | No | Argentina | Argentina | 04-Test | Kothari; Sanjay | Management (Planning, reporting, CR, cross stream integration) | OTC | FUN | SI | Onshore | Kothari; Sanjay | IBM | Yes | CapEx | Localization | IT - External | 42 | 0 | 42 | 2016-09-06 | 2016-11-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049318 | Yes | No | Argentina | Argentina | 03-Design/Build | Kothari; Sanjay | ARG KT visit | OTC | FUN | SI | Onshore | Kothari; Sanjay | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-08-08 | 2016-08-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049319 | Yes | No | Argentina | Argentina | 04-Test | Bill; Grey | Mock2 - Support | LOG | FUN | SI | Onshore | Bill; Grey | IBM | Yes | OpEx | Localization | IT - External | 40 | 0 | 40 | 2016-10-07 | 2016-11-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049320 | Yes | No | Argentina | Argentina | 04-Test | Bill; Grey | Mock1 - Support | LOG | FUN | SI | Onshore | Bill; Grey | IBM | Yes | OpEx | Localization | IT - External | 1.5 | 0 | 1.5 | 2016-08-15 | 2016-08-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049321 | Yes | No | Argentina | Argentina | 04-Test | Bill; Grey | SIT 1 - Run Tests | LOG | FUN | SI | Onshore | Bill; Grey | IBM | Yes | CapEx | Localization | IT - External | 193 | 0 | 193 | 2016-09-06 | 2016-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049322 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Power; Kat | Dry Run - Support | PTP | FUN | SI | Onshore | Power; Kat | IBM | Yes | CapEx | Localization | IT - External | 66 | 0 | 66 | 2016-11-28 | 2016-12-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049323 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Power; Kat | Dry Run - Validate | PTP | FUN | SI | Onshore | Power; Kat | IBM | Yes | CapEx | Localization | IT - External | 45 | 0 | 45 | 2016-11-14 | 2016-12-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049324 | Yes | No | Argentina | Argentina | 04-Test | Power; Kat | Management (Planning, reporting, CR, cross stream integration) | PTP | FUN | SI | Onshore | Power; Kat | IBM | Yes | CapEx | Localization | IT - External | 144 | 0 | 144 | 2016-09-06 | 2016-09-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049325 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Power; Kat | Cut Over - Support | PTP | FUN | SI | Onshore | Power; Kat | IBM | Yes | CapEx | Localization | IT - External | 16.5 | 0 | 16.5 | 2016-12-19 | 2016-12-22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049326 | Yes | No | Argentina | Argentina | 04-Test | Power; Kat | Mock2 - Validate | PTP | FUN | SI | Onshore | Power; Kat | IBM | Yes | OpEx | Localization | IT - External | 1 | 0 | 1 | 2016-11-07 | 2016-11-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049327 | Yes | No | Argentina | Argentina | 04-Test | Power; Kat | Mock2 - Support | PTP | FUN | SI | Onshore | Power; Kat | IBM | Yes | OpEx | Localization | IT - External | 61.5 | 0 | 61.5 | 2016-10-18 | 2016-11-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049328 | Yes | No | Argentina | Argentina | 06-Hypercare | Gupta; Ajay | HC - Manage Defects | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-27 | 2017-02-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049329 | Yes | No | Argentina | Argentina | 06-Hypercare | Gupta; Ajay | HC - Break/Fix - RTR | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049330 | Yes | No | Argentina | Argentina | 06-Hypercare | Gupta; Ajay | HC - Provide end User Support - RTR | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2017-01-02 | 2017-01-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049331 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Gupta; Ajay | Cut Over - Prepare | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 4 | 0 | 4 | 2016-12-13 | 2016-12-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049332 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Gupta; Ajay | Cut Over - Support | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 16 | 0 | 16 | 2016-12-19 | 2017-01-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049333 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Gupta; Ajay | Cut Over - Validate | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 6 | 0 | 6 | 2016-12-19 | 2016-12-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049334 | Yes | No | Argentina | Argentina | 04-Test | Gupta; Ajay | SIT 2 - RTR - Break/Fix | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 28 | 0 | 28 | 2016-11-08 | 2016-12-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049335 | Yes | No | Argentina | Argentina | 04-Test | Gupta; Ajay | Updates concepts decks | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | OpEx | Localization | IT - External | 10 | 0 | 10 | 2016-10-11 | 2016-11-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049336 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Gupta; Ajay | UAT - Break/Fix and document work around | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 28 | 0 | 28 | 2016-12-12 | 2017-01-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049337 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Gupta; Ajay | UAT - Run Tests | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 32 | 0 | 32 | 2016-12-19 | 2016-12-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049338 | Yes | No | Argentina | Argentina | 04-Test | Gupta; Ajay | SIT 1 - Run Tests | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 2 | 0 | 2 | 2016-10-05 | 2016-10-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049339 | Yes | No | Argentina | Argentina | 04-Test | Gupta; Ajay | SIT 1 - Break/Fix | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 22 | 0 | 22 | 2016-10-03 | 2016-10-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049340 | Yes | No | Argentina | Argentina | 04-Test | Gupta; Ajay | SIT 2 - RTR - Prep | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 42 | 0 | 42 | 2016-10-11 | 2016-11-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049341 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Gupta; Ajay | Interim reporting (400hours) | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-12 | 2016-12-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049342 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Singh; Pankaj | Transition to Hypercare | PTP | FUN | SI | Onshore | Singh; Pankaj | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2017-01-23 | 2017-01-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049343 | Yes | No | Argentina | Argentina | 04-Test | Singh; Pankaj | SIT 2 - PTP - Break/Fix | PTP | FUN | SI | Onshore | Singh; Pankaj | Accenture | Yes | CapEx | Localization | IT - External | 40 | 0 | 40 | 2016-11-28 | 2016-12-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049344 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Singh; Pankaj | Dry Run - Prepare | PTP | FUN | SI | Onshore | Singh; Pankaj | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-31 | 2016-10-31 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049345 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Singh; Pankaj | Dry Run - Support | PTP | FUN | SI | Onshore | Singh; Pankaj | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-11-14 | 2016-11-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049346 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Singh; Pankaj | Dry Run - Validate | PTP | FUN | SI | Onshore | Singh; Pankaj | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-11-14 | 2016-11-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049347 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Singh; Pankaj | UAT - Break/Fix and document work around | PTP | FUN | SI | Onshore | Singh; Pankaj | Accenture | Yes | CapEx | Localization | IT - External | 152 | 0 | 152 | 2016-12-05 | 2017-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049348 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Singh; Pankaj | Cut Over - Support | PTP | FUN | SI | Onshore | Singh; Pankaj | Accenture | Yes | CapEx | Localization | IT - External | 40 | 0 | 40 | 2016-12-19 | 2017-01-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049349 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Singh; Pankaj | Cut Over - Validate | PTP | FUN | SI | Onshore | Singh; Pankaj | Accenture | Yes | CapEx | Localization | IT - External | 16 | 0 | 16 | 2016-12-29 | 2016-12-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049350 | Yes | No | Argentina | Argentina | 06-Hypercare | Singh; Pankaj | HC - Provide end User Support | PTP | FUN | SI | Onshore | Singh; Pankaj | Accenture | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049351 | Yes | No | Argentina | Argentina | 06-Hypercare | Singh; Pankaj | HC - Break/Fix | PTP | FUN | SI | Onshore | Singh; Pankaj | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049352 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Mauro; JuanPablo | UAT - Break/Fix and document work around | LOG | FUN | SI | Onshore | Mauro; JuanPablo | IBM | Yes | CapEx | Localization | IT - External | 88 | 0 | 88 | 2017-01-16 | 2017-01-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049353 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Mauro; JuanPablo | Cut Over - Support | LOG | FUN | SI | Onshore | Mauro; JuanPablo | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-19 | 2016-12-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049354 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Mauro; JuanPablo | Cut Over - Validate | LOG | FUN | SI | Onshore | Mauro; JuanPablo | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-19 | 2016-12-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049355 | Yes | No | Argentina | Argentina | 06-Hypercare | Mauro; JuanPablo | HC - Provide end User Support | LOG | FUN | SI | Onshore | Mauro; JuanPablo | IBM | Yes | OpEx | Localization | IT - External | 227 | 0 | 227 | 2017-02-06 | 2017-03-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049356 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Mauro; JuanPablo | UAT - Run Tests | LOG | FUN | SI | Onshore | Mauro; JuanPablo | IBM | Yes | CapEx | Localization | IT - External | 140 | 0 | 140 | 2016-12-05 | 2016-12-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049357 | Yes | No | Argentina | Argentina | 06-Hypercare | Mauro; JuanPablo | HC - Break/Fix | LOG | FUN | SI | Onshore | Mauro; JuanPablo | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049358 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Mauro; JuanPablo | Transition to Hypercare - LOG | LOG | FUN | SI | Onshore | Mauro; JuanPablo | IBM | Yes | CapEx | Localization | IT - External | 44 | 0 | 44 | 2017-01-30 | 2017-02-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049359 | Yes | No | Argentina | Argentina | 04-Test | Mauro; JuanPablo | LOG - SIT 2 - Break/Fix | LOG | FUN | SI | Onshore | Mauro; JuanPablo | IBM | Yes | CapEx | Localization | IT - External | 41 | 0 | 41 | 2016-11-29 | 2016-12-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049360 | Yes | No | Argentina | Argentina | 06-Hypercare | Mauro; JuanPablo | Argentina Production Support-LOG | LOG | FUN | SI | Onshore | Mauro; JuanPablo | IBM | Yes | OpEx | Localization | IT - External | 80 | 0 | 80 | 2017-03-13 | 2017-03-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049361 | Yes | No | Argentina | Argentina | 04-Test | Sniezyk; Sebastian | LOG - SIT 2 - Break/Fix | LOG | FUN | SI | Onshore | Sniezyk; Sebastian | IBM | Yes | CapEx | Localization | IT - External | 75 | 0 | 75 | 2016-11-21 | 2016-12-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049362 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Sniezyk; Sebastian | UAT - Run Tests | LOG | FUN | SI | Onshore | Sniezyk; Sebastian | IBM | Yes | CapEx | Localization | IT - External | 181 | 0 | 181 | 2016-12-05 | 2017-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049363 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Sniezyk; Sebastian | UAT - Break/Fix and document work around | LOG | FUN | SI | Onshore | Sniezyk; Sebastian | IBM | Yes | CapEx | Localization | IT - External | 80 | 0 | 80 | 2016-12-27 | 2017-01-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049364 | Yes | No | Argentina | Argentina | 06-Hypercare | Sniezyk; Sebastian | HC - Break/Fix | LOG | FUN | SI | Onshore | Sniezyk; Sebastian | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049365 | Yes | No | Argentina | Argentina | 06-Hypercare | Sniezyk; Sebastian | HC - Provide end User Support | LOG | FUN | SI | Onshore | Sniezyk; Sebastian | IBM | Yes | OpEx | Localization | IT - External | 187 | 0 | 187 | 2017-02-06 | 2017-03-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049366 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Sniezyk; Sebastian | Transition to Hypercare - LOG | LOG | FUN | SI | Onshore | Sniezyk; Sebastian | IBM | Yes | CapEx | Localization | IT - External | 44 | 0 | 44 | 2017-01-30 | 2017-02-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049367 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Sniezyk; Sebastian | Cut Over - Support | LOG | FUN | SI | Onshore | Sniezyk; Sebastian | IBM | Yes | CapEx | Localization | IT - External | 88 | 0 | 88 | 2017-01-16 | 2017-01-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049368 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Sniezyk; Sebastian | Cut Over - Validate | LOG | FUN | SI | Onshore | Sniezyk; Sebastian | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-19 | 2016-12-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049369 | Yes | No | Argentina | Argentina | 06-Hypercare | Sniezyk; Sebastian | Argentina Production Support-LOG | LOG | FUN | SI | Onshore | Sniezyk; Sebastian | IBM | Yes | OpEx | Localization | IT - External | 799 | 0 | 799 | 2017-03-06 | 2017-07-31 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049370 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Esteves; Euler | Transition to Hypercare - OTC | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 40 | 0 | 40 | 2017-01-30 | 2017-02-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049371 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Esteves; Euler | UAT - Run Tests | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 80 | 0 | 80 | 2016-12-05 | 2016-12-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049372 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Esteves; Euler | Cut Over - Support | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 231.98 | 0 | 231.98 | 2016-12-19 | 2017-01-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049373 | No | Yes | Argentina | Argentina | 06-Hypercare | Esteves; Euler | HC - Provide end User Support | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | OpEx | Localization | IT - Internal | 80 | 0 | 80 | 2017-02-06 | 2017-02-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049374 | No | Yes | Argentina | Argentina | 06-Hypercare | Esteves; Euler | Argentina Production Support-OTC | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | OpEx | Localization | IT - Internal | 75 | 0 | 75 | 2017-03-06 | 2017-05-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049375 | No | Yes | Argentina | Argentina | 10-PCR | Esteves; Euler | Argentina new cheese line-OTC | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 0 | 0 | 0 | 2017-05-03 | 2017-05-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049376 | Yes | No | Argentina | Argentina | 03-Design/Build | Igwenazor; Stella | GRC AC - Build & UT | SEC | SEC | SI |  | Igwenazor; Stella | Other | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-09-07 | 2016-09-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049377 | Yes | No | Argentina | Argentina | 04-Test | Igwenazor; Stella | FUT Support Roles | SEC | SEC | SI |  | Igwenazor; Stella | Other | Yes | CapEx | Localization | IT - External | 10 | 0 | 10 | 2016-10-31 | 2016-11-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049378 | Yes | No | Argentina | Argentina | 04-Test | Igwenazor; Stella | GRC AC - SIT Execution | SEC | SEC | SI |  | Igwenazor; Stella | Other | Yes | CapEx | Localization | IT - External | 74 | 0 | 74 | 2016-10-31 | 2016-11-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049379 | Yes | No | Argentina | Argentina | 04-Test | Igwenazor; Stella | PCR - 209 - HR Administrator Derived role for Canada - Security | SEC | SEC | SI |  | Igwenazor; Stella | Other | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-18 | 2016-12-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049380 | Yes | No | Argentina | Argentina | 04-Test | Igwenazor; Stella | SIT 2 Defect Resolution | SEC | SEC | SI |  | Igwenazor; Stella | Other | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-22 | 2016-10-22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049381 | Yes | No | Argentina | Argentina | 06-Hypercare | Igwenazor; Stella | Hypercare/support | SEC | SEC | SI |  | Igwenazor; Stella | Other | Yes | OpEx | Localization | IT - External | 280 | 0 | 280 | 2017-02-06 | 2017-03-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049382 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Igwenazor; Stella | UAT Defect Resolution | SEC | SEC | SI |  | Igwenazor; Stella | Other | Yes | CapEx | Localization | IT - External | 309 | 0 | 309 | 2016-12-05 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049383 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Igwenazor; Stella | GRC AC - Cutover planning and Exucution | SEC | SEC | SI |  | Igwenazor; Stella | Other | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-18 | 2016-10-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049384 | No | Yes | Argentina | Argentina | 06-Hypercare | Pal; Gaurav | Hypercare/support | SEC | SEC | SI | Onshore | Pal; Gaurav | Accenture | Yes | OpEx | Localization | IT - External | 163 | 0 | 163 | 2017-02-13 | 2017-03-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049385 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Pal; Gaurav | Transition to Hypercare - CG | SEC | SEC | SI | Onshore | Pal; Gaurav | Accenture | Yes | CapEx | Localization | IT - External | 56 | 0 | 56 | 2017-01-23 | 2017-01-31 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049386 | No | Yes | Argentina | Argentina | 06-Hypercare | Pal; Gaurav | Support Hypercare - SEC | SEC | SEC | SI | Onshore | Pal; Gaurav | Accenture | Yes | CapEx | Localization | IT - External | 97 | 0 | 97 | 2017-02-01 | 2017-02-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049387 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Iozzo; Tony | Transition to Hypercare - LOG | LOG | FUN | SI | Onshore | Iozzo; Tony | IBM | Yes | CapEx | Localization | IT - External | 81 | 0 | 81 | 2017-01-23 | 2017-02-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049388 | Yes | No | Argentina | Argentina | 06-Hypercare | Iozzo; Tony | HC - Provide end User Support | LOG | FUN | SI | Onshore | Iozzo; Tony | IBM | Yes | OpEx | Localization | IT - External | 114 | 0 | 114 | 2017-02-06 | 2017-03-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049389 | Yes | No | Argentina | Argentina | 06-Hypercare | Iozzo; Tony | HC - Break/Fix | LOG | FUN | SI | Onshore | Iozzo; Tony | IBM | Yes | CapEx | Localization | IT - External | 127 | 0 | 127 | 2017-02-06 | 2017-03-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049390 | Yes | No | Argentina | Argentina | 06-Hypercare | DeBonis; Claudia | Argentina Production Support-PMO | PMO | PMO | SI | Onshore | DeBonis; Claudia | IBM | Yes | OpEx | Localization | IT - External | 49 | 0 | 49 | 2017-03-06 | 2017-03-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049391 | Yes | No | Argentina | Argentina |  | DeBonis; Claudia | Perform project Planning and Control | PMO | PMO | SI | Onshore | DeBonis; Claudia | IBM | Yes | CapEx | Localization | IT - External | 981 | 0 | 981 | 2016-09-26 | 2017-03-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049392 | No | Yes | Argentina | Argentina | 04-Test | Ragothaman; Ramkumar | Mock2 - Validate | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-31 | 2016-10-31 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049393 | No | Yes | Argentina | Argentina | 04-Test | Ragothaman; Ramkumar | SIT 2 - Manage Defects | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 51 | 0 | 51 | 2016-10-24 | 2016-11-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049394 | No | Yes | Argentina | Argentina | 04-Test | Ragothaman; Ramkumar | SIT 2 - PTP - Break/Fix | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 212 | 0 | 212 | 2016-10-26 | 2016-12-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049395 | No | Yes | Argentina | Argentina | 04-Test | Ragothaman; Ramkumar | Updates concepts decks | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-03 | 2016-10-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049396 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Ragothaman; Ramkumar | Transition to Hypercare | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 76 | 0 | 76 | 2017-01-23 | 2017-02-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049397 | No | Yes | Argentina | Argentina | 04-Test | Ragothaman; Ramkumar | Management (Planning, reporting, CR, cross stream integration) | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-09-06 | 2016-09-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049398 | No | Yes | Argentina | Argentina | 04-Test | Ragothaman; Ramkumar | Mock2 - Support | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-18 | 2016-10-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049399 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Ragothaman; Ramkumar | Cut Over - Support | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-19 | 2017-01-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049400 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Ragothaman; Ramkumar | Cut Over - Validate | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-19 | 2017-01-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049401 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Ragothaman; Ramkumar | UAT - Manage Defects | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 40 | 0 | 40 | 2016-12-07 | 2016-12-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049402 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Ragothaman; Ramkumar | UAT - Break/Fix and document work around | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 155 | 0 | 155 | 2016-12-05 | 2017-01-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049403 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Ragothaman; Ramkumar | Cut Over - Prepare | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-12 | 2016-12-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049404 | No | Yes | Argentina | Argentina | 06-Hypercare | Ragothaman; Ramkumar | HC - Provide end User Support | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | OpEx | Localization | IT - External | 88 | 0 | 88 | 2017-02-06 | 2017-02-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049405 | No | Yes | Argentina | Argentina | 06-Hypercare | Ragothaman; Ramkumar | HC - Manage Defects | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049406 | No | Yes | Argentina | Argentina | 06-Hypercare | Ragothaman; Ramkumar | HC - Break/Fix | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 8 | 0 | 8 | 2017-02-06 | 2017-02-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049407 | No | Yes | Argentina | Argentina | 04-Test | Ragothaman; Ramkumar | SIT 2 - Prep | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 78 | 0 | 78 | 2016-10-11 | 2016-10-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049408 | No | Yes | Argentina | Argentina | 04-Test | Ragothaman; Ramkumar | SIT 1 - Break/Fix | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 68 | 0 | 68 | 2016-09-06 | 2016-11-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049409 | No | Yes | Argentina | Argentina | 04-Test | Ragothaman; Ramkumar | SIT 1 - Run Tests | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 204 | 0 | 204 | 2016-09-12 | 2016-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049410 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Ragothaman; Ramkumar | Dry Run - Validate | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-11-14 | 2016-11-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049411 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Ragothaman; Ramkumar | Dry Run - Support | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-11-14 | 2016-11-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049412 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Ragothaman; Ramkumar | Dry Run - Prepare | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-31 | 2016-10-31 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049413 | Yes | No | Argentina | Argentina | 04-Test | Das; Biplab | Work Instructions - Exercices DATA (technical writer + Dele) | CM | CM | SI | Offshore | Das; Biplab | IBM | Yes | OpEx | Localization | IT - External | 171 | 0 | 171 | 2016-09-19 | 2016-10-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049414 | Yes | No | Argentina | Argentina | 04-Test | Sehgal; Arjun | Work Instructions - Exercices DATA (technical writer + Dele) | CM | CM | SI | Onshore | Sehgal; Arjun | IBM | Yes | OpEx | Localization | IT - External | 622 | 0 | 622 | 2016-10-03 | 2017-01-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049415 | Yes | No | Argentina | Argentina | 04-Test | Sehgal; Arjun | Manage SIT1 Prep (data, transports) | CM | CM | SI | Onshore | Sehgal; Arjun | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-08-29 | 2016-09-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049416 | Yes | No | Argentina | Argentina | 04-Test | Sehgal; Arjun | Manage SIT1 Execution | CM | CM | SI | Onshore | Sehgal; Arjun | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-09-19 | 2016-09-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049417 | No | Yes | Argentina | Argentina | 06-Hypercare | Nunez; Lawrence | Argentina Production Support-TAI | TAI | TAI | SI | Offshore | Nunez; Lawrence | Accenture | Yes | OpEx | Localization | IT - External | 710.5 | 0 | 710.5 | 2017-03-06 | 2017-07-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049418 | No | Yes | Argentina | Argentina | 06-Hypercare | Nunez; Lawrence | Support Hypercare | TAI | TAI | SI | Offshore | Nunez; Lawrence | Accenture | Yes | CapEx | Localization | IT - External | 162 | 0 | 162 | 2017-02-08 | 2017-03-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049419 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Nunez; Lawrence | Execute Cutover Steps | TAI | TAI | SI | Offshore | Nunez; Lawrence | Accenture | Yes | CapEx | Localization | IT - External | 252 | 0 | 252 | 2016-12-19 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049420 | Yes | No | Argentina | Argentina | 04-Test | Van-Kessel; Brian | Communication plan execution and monitoring | CM | CM | SI |  | Van-Kessel; Brian | Other | Yes | OpEx | Localization | IT - External | 543.5 | 0 | 543.5 | 2016-09-06 | 2016-12-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049421 | Yes | No | Argentina | Argentina | 06-Hypercare | Van-Kessel; Brian | Value Realization Monitoring | CM | CM | SI |  | Van-Kessel; Brian | Other | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049422 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Van-Kessel; Brian | Communication plan execution and monitoring | CM | CM | SI |  | Van-Kessel; Brian | Other | Yes | OpEx | Localization | IT - External | 323 | 0 | 323 | 2016-12-12 | 2017-02-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049423 | Yes | No | Argentina | Argentina | 06-Hypercare | Van-Kessel; Brian | Communication plan execution and monitoring | CM | CM | SI |  | Van-Kessel; Brian | Other | Yes | OpEx | Localization | IT - External | 134.5 | 0 | 134.5 | 2017-02-13 | 2017-03-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049424 | Yes | No | Argentina | Argentina | 04-Test | Mierski; Pawel | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | SI | Onshore | Mierski; Pawel | SAP | Yes | CapEx | Localization | IT - External | 80 | 0 | 80 | 2016-09-12 | 2016-09-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049425 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Valin; Eric | Cut Over - Support | RTR | FUN | Saputo | Onshore | Valin; Eric | Saputo | Yes | CapEx | Localization | IT - Internal | 16 | 0 | 16 | 2016-12-19 | 2017-02-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049426 | No | Yes | Argentina | Argentina | 06-Hypercare | Valin; Eric | HC - Provide end User Support - RTR | RTR | FUN | Saputo | Onshore | Valin; Eric | Saputo | Yes | OpEx | Localization | IT - Internal | 93 | 0 | 93 | 2017-01-02 | 2017-03-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049427 | No | Yes | Argentina | Argentina | 10-PCR | Valin; Eric | Argentina new cheese line-RTR | RTR | FUN | Saputo | Onshore | Valin; Eric | Saputo | Yes | CapEx | Localization | IT - Internal | 2 | 0 | 2 | 2017-04-25 | 2017-04-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049428 | No | Yes | Argentina | Argentina | 06-Hypercare | Valin; Eric | Argentina Production Support-RTR | RTR | FUN | Saputo | Onshore | Valin; Eric | Saputo | Yes | OpEx | Localization | IT - Internal | 249 | 0 | 249 | 2017-03-22 | 2017-07-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049429 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Kritika; Jain | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Kritika; Jain | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049430 | Yes | No | Argentina | Argentina | 06-Hypercare | Kritika; Jain | Development (Hypercare) | DEV | DEV | SI | Offshore | Kritika; Jain | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2017-01-23 | 2017-01-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049431 | Yes | No | Argentina | Argentina | 03-Design/Build | Kritika; Jain | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | Kritika; Jain | IBM | Yes | CapEx | Localization | IT - External | 45 | 0 | 45 | 2016-08-12 | 2016-08-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049432 | Yes | No | Argentina | Argentina | 03-Design/Build | Kritika; Jain | ARG : DB - Technical Specifications | DEV | DEV | SI | Offshore | Kritika; Jain | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-04-13 | 2016-04-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049433 | Yes | No | Argentina | Argentina | 03-Design/Build | Kritika; Jain | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Kritika; Jain | IBM | Yes | CapEx | Localization | IT - External | 76.5 | 0 | 76.5 | 2016-09-06 | 2016-09-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049434 | Yes | No | Argentina | Argentina | 04-Test | Kritika; Jain | Development | DEV | DEV | SI | Offshore | Kritika; Jain | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-08-22 | 2016-08-22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049435 | Yes | No | Argentina | Argentina | 04-Test | Kritika; Jain | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Kritika; Jain | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-24 | 2016-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049436 | No | Yes | Argentina | Argentina | 03-Design/Build | Valentino; Kevin | ARG : DB - Conduct Mock 0 Load in DEV - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 126 | 0 | 126 | 2016-06-06 | 2016-06-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049437 | No | Yes | Argentina | Argentina | 03-Design/Build | Valentino; Kevin | ARG : DB - Conduct Mock 1 Load in QA - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 437 | 0 | 437 | 2016-06-27 | 2016-09-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049438 | No | Yes | Argentina | Argentina | 06-Hypercare | Valentino; Kevin | Hypercare Support - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | OpEx | Localization | IT - External | 45 | 0 | 45 | 2017-02-06 | 2017-02-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049439 | No | Yes | Argentina | Argentina | 04-Test | Valentino; Kevin | M1 - Execute loads - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-09-05 | 2016-09-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049440 | No | Yes | Argentina | Argentina | 04-Test | Valentino; Kevin | SIT1 - Defect Fix - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 208.5 | 0 | 208.5 | 2016-09-12 | 2016-10-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049441 | No | Yes | Argentina | Argentina | 04-Test | Valentino; Kevin | M2 - Execute pre validation - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 36 | 0 | 36 | 2016-10-10 | 2016-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049442 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Valentino; Kevin | Execute pre validation - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | OpEx | Localization | IT - External | 135 | 0 | 135 | 2016-12-19 | 2017-01-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049443 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Valentino; Kevin | Execute Cutover - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | OpEx | Localization | IT - External | 78 | 0 | 78 | 2016-12-19 | 2017-02-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049444 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Valentino; Kevin | Execute loads/ reports - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | OpEx | Localization | IT - External | 4.5 | 0 | 4.5 | 2016-12-12 | 2017-02-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049445 | No | Yes | Argentina | Argentina | 04-Test | Valentino; Kevin | SIT2 - Defect Fix - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 55.5 | 0 | 55.5 | 2016-11-07 | 2016-12-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049446 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Valentino; Kevin | Dry Run - Execute pre validation - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 190 | 0 | 190 | 2016-11-07 | 2016-12-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049447 | No | Yes | Argentina | Argentina | 04-Test | Valentino; Kevin | M2 - Execute loads/reports - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 126 | 0 | 126 | 2016-10-17 | 2016-11-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049448 | No | Yes | Argentina | Argentina | 04-Test | Valentino; Kevin | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 45 | 0 | 45 | 2016-09-05 | 2016-09-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049449 | No | Yes | Argentina | Argentina | 03-Design/Build | Valentino; Kevin | ARG : DB - Technical Specifications - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-04-13 | 2016-04-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049450 | Yes | No | Argentina | Argentina | 03-Design/Build | Diwa; Karissa | ARG : DB - Conduct Mock 0 Load in DEV - DC | MDG | DC | SI | Offshore | Diwa; Karissa | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-05-25 | 2016-05-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049451 | No | Yes | Argentina | Argentina | 03-Design/Build | Mali; Harshal | ARG : DB - Functional Specifications and UT- OTC | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 216 | 0 | 216 | 2016-05-16 | 2016-06-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049452 | No | Yes | Argentina | Argentina | 03-Design/Build | Mali; Harshal | ARG : DB - SDD - OTC | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-04-25 | 2016-04-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049453 | No | Yes | Argentina | Argentina | 04-Test | Mali; Harshal | SIT 1 - Run Tests | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-08-29 | 2016-08-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049454 | No | Yes | Argentina | Argentina | 04-Test | Mali; Harshal | OTC - SIT 2 - Run Tests | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 5 | 0 | 5 | 2016-10-24 | 2016-10-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049455 | No | Yes | Argentina | Argentina | 03-Design/Build | Mali; Harshal | ARG KT visit | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-08-08 | 2016-08-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049456 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Mali; Harshal | UAT - Break/Fix and document work around | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 165 | 0 | 165 | 2016-12-05 | 2017-01-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049457 | No | Yes | Argentina | Argentina | 06-Hypercare | Mali; Harshal | HC - Provide end User Support | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049458 | No | Yes | Argentina | Argentina | 06-Hypercare | Mali; Harshal | HC - Break/Fix | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049459 | Yes | No | Argentina | Argentina | 03-Design/Build | Alviar; Maricar | ARG : DB - Conduct Mock 0 Load in DEV - DC | MDG | DC | SI | Offshore | Alviar; Maricar | Accenture | Yes | CapEx | Localization | IT - External | 62.5 | 0 | 62.5 | 2016-05-30 | 2016-06-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049460 | Yes | Yes | Argentina | Argentina | 03-Design/Build | Mangiliman; Maricar | ARG : DB - Conduct Mock 0 Load in DEV - DC | MDG | DC | SI | Offshore | Mangiliman; Maricar | Accenture | Yes | CapEx | Localization | IT - External | 72 | 0 | 72 | 2016-06-01 | 2016-06-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049461 | Yes | Yes | Argentina | Argentina | 05-Cutover/Go-live | Mangiliman; Maricar | Execute loads/ reports - DC | MDG | DC | SI | Offshore | Mangiliman; Maricar | Accenture | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049462 | Yes | Yes | Argentina | Argentina | 04-Test | Mangiliman; Maricar | M2 - Execute loads/reports - DC | MDG | DC | SI | Offshore | Mangiliman; Maricar | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-10 | 2016-10-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049463 | Yes | Yes | Argentina | Argentina | 05-Cutover/Go-live | Mangiliman; Maricar | Dry Run - Execute pre validation - DC | MDG | DC | SI | Offshore | Mangiliman; Maricar | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-24 | 2016-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049464 | Yes | Yes | Argentina | Argentina | 05-Cutover/Go-live | Mangiliman; Maricar | Dry Run - Execute Loads/Reports - DC | MDG | DC | SI | Offshore | Mangiliman; Maricar | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-11-28 | 2016-11-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049465 | Yes | Yes | Argentina | Argentina | 05-Cutover/Go-live | Mangiliman; Maricar | Execute pre validation - DC | MDG | DC | SI | Offshore | Mangiliman; Maricar | Accenture | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049466 | Yes | Yes | Argentina | Argentina | 05-Cutover/Go-live | Mangiliman; Maricar | Dry Run - Data verification Signoff sheets - DC | MDG | DC | SI | Offshore | Mangiliman; Maricar | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-11-29 | 2016-11-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049467 | Yes | Yes | Argentina | Argentina | 04-Test | Mangiliman; Maricar | SIT2 - Defect Fix - DC | MDG | DC | SI | Offshore | Mangiliman; Maricar | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-24 | 2016-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049468 | Yes | Yes | Argentina | Argentina | 05-Cutover/Go-live | Mangiliman; Maricar | Execute Cutover - DC | MDG | DC | SI | Offshore | Mangiliman; Maricar | Accenture | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-19 | 2016-12-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049469 | Yes | Yes | Argentina | Argentina | 05-Cutover/Go-live | Mangiliman; Maricar | UAT Prep - DC | MDG | DC | SI | Offshore | Mangiliman; Maricar | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-11-14 | 2016-11-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049470 | Yes | Yes | Argentina | Argentina | 04-Test | Mangiliman; Maricar | M2 - Execute pre validation - DC | MDG | DC | SI | Offshore | Mangiliman; Maricar | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-10 | 2016-10-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049471 | Yes | Yes | Argentina | Argentina | 04-Test | Mangiliman; Maricar | SIT1 - Defect Fix - DC | MDG | DC | SI | Offshore | Mangiliman; Maricar | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-09-05 | 2016-09-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049472 | Yes | Yes | Argentina | Argentina | 04-Test | Mangiliman; Maricar | Training Prep - DC | MDG | DC | SI | Offshore | Mangiliman; Maricar | Accenture | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2016-11-14 | 2016-11-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049473 | Yes | Yes | Argentina | Argentina | 06-Hypercare | Mangiliman; Maricar | Hypercare Support - DC | MDG | DC | SI | Offshore | Mangiliman; Maricar | Accenture | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049474 | Yes | No | Argentina | Argentina | 03-Design/Build | Manalac; Edgar | ARG : DB - Conduct Mock 0 Load in DEV - DC | MDG | DC | SI | Offshore | Manalac; Edgar | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-05-25 | 2016-05-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049475 | Yes | Yes | Argentina | Argentina | 04-Test | Doppalapudi; Nagaraju | Development | DEV | DEV | SI | Offshore | Doppalapudi; Nagaraju | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-08-22 | 2016-08-22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049476 | Yes | Yes | Argentina | Argentina | 03-Design/Build | Doppalapudi; Nagaraju | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Doppalapudi; Nagaraju | IBM | Yes | CapEx | Localization | IT - External | 12.5 | 0 | 12.5 | 2016-08-22 | 2016-08-26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049477 | Yes | Yes | Argentina | Argentina | 04-Test | Doppalapudi; Nagaraju | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Doppalapudi; Nagaraju | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-24 | 2016-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049478 | Yes | Yes | Argentina | Argentina | 05-Cutover/Go-live | Doppalapudi; Nagaraju | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Doppalapudi; Nagaraju | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049479 | No | Yes | Argentina | Argentina | 06-Hypercare | Therien; Stephane | Argentina Production Support-RTR | RTR | FUN | Saputo | Onshore | Therien; Stephane | Saputo | Yes | OpEx | Localization | IT - Internal | 580 | 0 | 580 | 2017-03-20 | 2017-06-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049480 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Therien; Stephane | Cut Over - Support | RTR | FUN | Saputo | Onshore | Therien; Stephane | Saputo | Yes | CapEx | Localization | IT - Internal | 80 | 0 | 80 | 2017-01-23 | 2017-02-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049481 | No | Yes | Argentina | Argentina | 06-Hypercare | Therien; Stephane | HC - Provide end User Support - RTR | RTR | FUN | Saputo | Onshore | Therien; Stephane | Saputo | Yes | OpEx | Localization | IT - Internal | 200 | 0 | 200 | 2017-02-06 | 2017-03-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049482 | No | Yes | Argentina | Argentina | 06-Hypercare | Esquerro; Alejandro | HC - Break/Fix | LOG | FUN | SI | Onshore | Esquerro; Alejandro | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049483 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Esquerro; Alejandro | Transition to Hypercare - LOG | LOG | FUN | SI | Onshore | Esquerro; Alejandro | IBM | Yes | CapEx | Localization | IT - External | 55 | 0 | 55 | 2017-01-30 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049484 | No | Yes | Argentina | Argentina | 06-Hypercare | Esquerro; Alejandro | Argentina Production Support-LOG | LOG | FUN | SI | Onshore | Esquerro; Alejandro | IBM | Yes | OpEx | Localization | IT - External | 622 | 0 | 622 | 2017-03-06 | 2017-06-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049485 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Esquerro; Alejandro | UAT - Break/Fix and document work around | LOG | FUN | SI | Onshore | Esquerro; Alejandro | IBM | Yes | CapEx | Localization | IT - External | 129 | 0 | 129 | 2017-01-09 | 2017-01-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049486 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Esquerro; Alejandro | Cut Over - Support | LOG | FUN | SI | Onshore | Esquerro; Alejandro | IBM | Yes | CapEx | Localization | IT - External | 60 | 0 | 60 | 2016-12-19 | 2017-02-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049487 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Esquerro; Alejandro | Cut Over - Validate | LOG | FUN | SI | Onshore | Esquerro; Alejandro | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-19 | 2016-12-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049488 | No | Yes | Argentina | Argentina | 06-Hypercare | Esquerro; Alejandro | HC - Provide end User Support | LOG | FUN | SI | Onshore | Esquerro; Alejandro | IBM | Yes | OpEx | Localization | IT - External | 165 | 0 | 165 | 2017-02-13 | 2017-03-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049489 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Esquerro; Alejandro | UAT - Run Tests | LOG | FUN | SI | Onshore | Esquerro; Alejandro | IBM | Yes | CapEx | Localization | IT - External | 43 | 0 | 43 | 2017-01-02 | 2017-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049490 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Esquerro; Alejandro | UAT - Manage Defects | LOG | FUN | SI | Onshore | Esquerro; Alejandro | IBM | Yes | CapEx | Localization | IT - External | 44 | 0 | 44 | 2016-12-26 | 2016-12-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049491 | No | Yes | Argentina | Argentina | 01-Preparation | Esquerro; Alejandro | Argentina Project - Sharepoint Access - | LOG | FUN | SI | Onshore | Esquerro; Alejandro | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2015-12-01 | 2015-12-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049492 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Gabra; Rania | Onboarding | CM | CM | Saputo | Onshore | Gabra; Rania | Saputo | Yes | OpEx | Localization | IT - Internal | 45 | 0 | 45 | 2017-01-09 | 2017-01-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049493 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Gabra; Rania | Communication plan execution and monitoring | CM | CM | Saputo | Onshore | Gabra; Rania | Saputo | Yes | OpEx | Localization | IT - Internal | 142.75 | 0 | 142.75 | 2017-01-16 | 2017-02-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049494 | No | Yes | Argentina | Argentina | 06-Hypercare | Gabra; Rania | Communication plan execution and monitoring | CM | CM | Saputo | Onshore | Gabra; Rania | Saputo | Yes | OpEx | Localization | IT - Internal | 144.5 | 0 | 144.5 | 2017-02-06 | 2017-03-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049495 | No | Yes | Argentina | Argentina | 06-Hypercare | Gabra; Rania | Value Realization Monitoring | CM | CM | Saputo | Onshore | Gabra; Rania | Saputo | Yes | OpEx | Localization | IT - Internal | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049496 | No | Yes | Argentina | Argentina | 06-Hypercare | Gabra; Rania | Argentina Production Support-CM | CM | CM | Saputo | Onshore | Gabra; Rania | Saputo | Yes | OpEx | Localization | IT - Internal | 23.7 | 0 | 23.7 | 2017-03-27 | 2017-06-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049497 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Narayanan; Arun | Transition to Hypercare - PTM | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 123 | 0 | 123 | 2017-01-30 | 2017-02-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049498 | No | Yes | Argentina | Argentina | 06-Hypercare | Narayanan; Arun | HC - Break/Fix - PTM | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 178 | 0 | 178 | 2017-02-06 | 2017-03-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049499 | No | Yes | Argentina | Argentina | 06-Hypercare | Narayanan; Arun | HC - Manage Defects | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049500 | No | Yes | Argentina | Argentina | 06-Hypercare | Narayanan; Arun | HC - Provide end User Support - PTM | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | OpEx | Localization | IT - External | 44 | 0 | 44 | 2017-01-23 | 2017-02-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049501 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Narayanan; Arun | Cut Over - Support | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 44 | 0 | 44 | 2017-01-16 | 2017-01-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049502 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Narayanan; Arun | Cut Over - Validate | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 88 | 0 | 88 | 2016-12-19 | 2017-01-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049503 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Narayanan; Arun | Cut Over - Prepare | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 15 | 0 | 15 | 2016-12-12 | 2016-12-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049504 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Narayanan; Arun | UAT - Manage Defects | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 84 | 0 | 84 | 2016-12-05 | 2016-12-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049505 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Narayanan; Arun | Dry Run - Validate | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 7 | 0 | 7 | 2016-12-12 | 2016-12-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049506 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Narayanan; Arun | Dry Run - Support | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 17 | 0 | 17 | 2016-12-12 | 2016-12-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049507 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Narayanan; Arun | Dry Run - Prepare | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-11-07 | 2016-11-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049508 | No | Yes | Argentina | Argentina | 04-Test | Narayanan; Arun | SIT 2 - PTM - Run Tests | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 76 | 0 | 76 | 2016-10-24 | 2016-11-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049509 | No | Yes | Argentina | Argentina | 04-Test | Narayanan; Arun | SIT 2 - PTM - Manage Defects | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 123 | 0 | 123 | 2016-10-31 | 2016-12-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049510 | No | Yes | Argentina | Argentina | 03-Design/Build | Narayanan; Arun | Functional Specification (FSD) | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 71 | 0 | 71 | 2016-08-01 | 2016-08-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049511 | No | Yes | Argentina | Argentina | 04-Test | Narayanan; Arun | SIT 1 - Run Tests | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 132 | 0 | 132 | 2016-09-12 | 2016-09-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049512 | No | Yes | Argentina | Argentina | 04-Test | Narayanan; Arun | SIT 1 - Manage Defects | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-09-26 | 2016-09-26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049513 | No | Yes | Argentina | Argentina | 04-Test | Narayanan; Arun | SIT 2 - Prep | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 80 | 0 | 80 | 2016-10-11 | 2016-11-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049514 | No | Yes | Argentina | Argentina | 04-Test | Narayanan; Arun | SIT 1 - Break/Fix | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-09-12 | 2016-09-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049515 | No | Yes | Argentina | Argentina | 04-Test | Narayanan; Arun | SIT 2 - PTM - Break/Fix | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 55 | 0 | 55 | 2016-11-21 | 2017-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049516 | No | Yes | Argentina | Argentina | 04-Test | Kingbo; David | Project SAP Environment Support | TAI | TAI | SI | Onshore | Kingbo; David | Accenture | Yes | CapEx | Localization | IT - External | 45 | 0 | 45 | 2016-10-24 | 2016-11-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049517 | No | Yes | Argentina | Argentina | 04-Test | Kingbo; David | Batch Execution Implementation | TAI | TAI | SI | Onshore | Kingbo; David | Accenture | Yes | CapEx | Localization | IT - External | 47 | 0 | 47 | 2016-10-24 | 2016-11-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049518 | No | Yes | Argentina | Argentina | 03-Design/Build | Kingbo; David | Contribute to Cutover Planning | TAI | TAI | SI | Onshore | Kingbo; David | Accenture | Yes | CapEx | Localization | IT - External | 118.48 | 0 | 118.48 | 2016-09-06 | 2016-10-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049519 | No | Yes | Argentina | Argentina | 04-Test | Kingbo; David | Maintain Existing Deliverables as needed | TAI | TAI | SI | Onshore | Kingbo; David | Accenture | Yes | CapEx | Localization | IT - External | 85.35 | 0 | 85.35 | 2016-09-06 | 2016-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049520 | No | Yes | Argentina | Argentina | 04-Test | Kingbo; David | TEST - Technical Architecture and Infrastructure (gen) | TAI | TAI | SI | Onshore | Kingbo; David | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-09-01 | 2016-09-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049521 | Yes | No | Argentina | Argentina | 06-Hypercare | Westerveld; Bruce | Argentina Production Support-PTM |  | Missing Stream | Saputo | Onshore | Westerveld; Bruce | Saputo | Yes | OpEx | Localization | Business | 0 | 0 | 0 | 2017-03-06 | 2017-03-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049522 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Westerveld; Bruce | Management (Cutover/Go-live) |  | Missing Stream | Saputo | Onshore | Westerveld; Bruce | Saputo | Yes | CapEx | Localization | Business | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049523 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Westerveld; Bruce | UAT - Break/Fix and document work around |  | Missing Stream | Saputo | Onshore | Westerveld; Bruce | Saputo | Yes | CapEx | Localization | Business | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049524 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Habib; Mustafa | UAT - Run Tests | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049525 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Habib; Mustafa | UAT - Manage Defects | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049526 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Habib; Mustafa | UAT - Break/Fix and document work around | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049527 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Habib; Mustafa | Cut Over - Validate | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 41 | 0 | 41 | 2017-01-10 | 2017-02-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049528 | No | Yes | Argentina | Argentina | 06-Hypercare | Habib; Mustafa | HC - Provide end User Support - PTM | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | OpEx | Localization | IT - Internal | 56 | 0 | 56 | 2017-01-23 | 2017-07-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049529 | No | Yes | Argentina | Argentina | 06-Hypercare | Habib; Mustafa | HC - Manage Defects | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 33 | 0 | 33 | 2017-02-06 | 2017-03-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049530 | No | Yes | Argentina | Argentina | 06-Hypercare | Habib; Mustafa | HC - Break/Fix - PTM | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049531 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Habib; Mustafa | Management (Cutover/Go-live) | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 47 | 0 | 47 | 2017-01-04 | 2017-01-26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049532 | No | Yes | Argentina | Argentina | 06-Hypercare | Habib; Mustafa | Argentina Production Support-PTM | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | OpEx | Localization | IT - Internal | 10.5 | 0 | 10.5 | 2017-04-12 | 2017-04-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049533 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Habib; Mustafa | Cut Over - Support | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0 | 0 | 0 | 2016-12-05 | 2017-01-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049534 | No | Yes | Argentina | Argentina | 06-Hypercare | Habib; Mustafa | HC - Provide end User Support | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | OpEx | Localization | IT - Internal | 64 | 0 | 64 | 2017-02-06 | 2017-03-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049535 | No | Yes | Argentina | Argentina | 06-Hypercare | Hasan; Niyazul | HC - Provide end User Support | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049536 | No | Yes | Argentina | Argentina | 06-Hypercare | Hasan; Niyazul | HC - Break/Fix | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049537 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Hasan; Niyazul | UAT - Break/Fix and document work around | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 115 | 0 | 115 | 2016-12-12 | 2017-01-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049538 | No | Yes | Argentina | Argentina | 04-Test | Hasan; Niyazul | SIT 1 - Run Tests | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 72 | 0 | 72 | 2016-09-12 | 2016-09-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049539 | No | Yes | Argentina | Argentina | 03-Design/Build | Sferlazza; Vincent | Solution Design Document (SDD) - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0 | 0 | 0 | 2016-08-15 | 2016-08-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049540 | No | Yes | Argentina | Argentina | 04-Test | Sferlazza; Vincent | SIT 1 - Run Tests (Saputo) - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0 | 0 | 0 | 2016-09-06 | 2016-09-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049541 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Litvin; Darrell | Interim reporting (400hours) | RTR | FUN | SI | Onshore | Litvin; Darrell | SAP | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-12 | 2016-12-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049542 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Litvin; Darrell | Transition to Hypercare | RTR | FUN | SI | Onshore | Litvin; Darrell | SAP | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2017-01-23 | 2017-01-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049543 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Litvin; Darrell | Dry Run - Validate | RTR | FUN | SI | Onshore | Litvin; Darrell | SAP | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-11-14 | 2016-11-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049544 | Yes | No | Argentina | Argentina | 04-Test | Litvin; Darrell | Updates concepts decks | RTR | FUN | SI | Onshore | Litvin; Darrell | SAP | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-11 | 2016-10-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049545 | Yes | No | Argentina | Argentina | 04-Test | Litvin; Darrell | SIT 2 - RTR - Prep | RTR | FUN | SI | Onshore | Litvin; Darrell | SAP | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-11 | 2016-10-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049546 | Yes | No | Argentina | Argentina | 06-Hypercare | Myers; Vincent | HC - Provide end User Support | LOG | FUN | SI | Onshore | Myers; Vincent | IBM | Yes | OpEx | Localization | IT - External | 84 | 0 | 84 | 2017-02-13 | 2017-02-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049547 | Yes | No | Argentina | Argentina | 06-Hypercare | Martin; Katy | HC - Provide end User Support | LOG | FUN | SI | Onshore | Martin; Katy | IBM | Yes | OpEx | Localization | IT - External | 124 | 0 | 124 | 2017-02-13 | 2017-02-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049548 | No | Yes | Argentina | Argentina | 06-Hypercare | Trivedi; Mohit | Development (Hypercare) | DEV | DEV | SI | Offshore | Trivedi; Mohit | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2017-01-23 | 2017-01-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049549 | No | Yes | Argentina | Argentina |  | Trivedi; Mohit | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Trivedi; Mohit | IBM | Yes | OpEx | Global | IT - External | 0 | 0 | 0 | 2017-05-23 | 2017-05-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049550 | No | Yes | Argentina | Argentina | 06-Hypercare | Trivedi; Mohit | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | Trivedi; Mohit | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-27 | 2017-02-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049551 | Yes | No | Argentina | Argentina | 04-Test | Docot; William | Mock2 - Prepare | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 21 | 0 | 21 | 2016-10-17 | 2016-10-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049552 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Docot; William | Interim reporting (400hours) | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 44 | 0 | 44 | 2017-01-23 | 2017-01-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049553 | Yes | No | Argentina | Argentina | 04-Test | Docot; William | SIT 1 - Run Tests | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 52 | 0 | 52 | 2016-09-12 | 2016-10-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049554 | Yes | No | Argentina | Argentina | 04-Test | Docot; William | Prep PRD for performance testing | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 2 | 0 | 2 | 2016-11-04 | 2016-11-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049555 | Yes | No | Argentina | Argentina | 04-Test | Docot; William | SIT 2 - RTR - Prep | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 18 | 0 | 18 | 2016-10-12 | 2016-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049556 | Yes | No | Argentina | Argentina | 04-Test | Docot; William | Mock2 - Validate | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-11 | 2016-10-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049557 | Yes | No | Argentina | Argentina | 06-Hypercare | Docot; William | CR-GL Upload Program | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | OpEx | Localization | IT - External | 64 | 0 | 64 | 2017-04-10 | 2017-05-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049558 | Yes | No | Argentina | Argentina | 06-Hypercare | Docot; William | Argentina Production Support-RTR | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | OpEx | Localization | IT - External | 18 | 0 | 18 | 2017-04-10 | 2017-04-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049559 | Yes | No | Argentina | Argentina | 04-Test | Docot; William | SIT 1 - Break/Fix | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 95 | 0 | 95 | 2016-09-12 | 2016-10-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049560 | Yes | No | Argentina | Argentina | 04-Test | Docot; William | Mock1 - Validate | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | OpEx | Localization | IT - External | 23 | 0 | 23 | 2016-09-06 | 2016-09-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049561 | Yes | No | Argentina | Argentina | 04-Test | Docot; William | SIT 2 - RTR - Run Tests | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-24 | 2016-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049562 | Yes | No | Argentina | Argentina | 04-Test | Docot; William | SIT 2 - RTR - Manage Defects | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 62 | 0 | 62 | 2016-10-24 | 2016-12-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049563 | Yes | No | Argentina | Argentina | 04-Test | Docot; William | Updates concepts decks | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | OpEx | Localization | IT - External | 10 | 0 | 10 | 2016-10-11 | 2016-12-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049564 | Yes | No | Argentina | Argentina | 04-Test | Docot; William | SIT 2 - RTR - Break/Fix | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 60 | 0 | 60 | 2016-11-04 | 2016-12-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049565 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Docot; William | UAT - Run Tests | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049566 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Docot; William | UAT - Break/Fix and document work around | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 80 | 0 | 80 | 2016-12-05 | 2017-01-22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049567 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Docot; William | Dry Run - Validate | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 24 | 0 | 24 | 2016-12-05 | 2016-12-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049568 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Docot; William | Dry Run - Prepare | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 11 | 0 | 11 | 2016-11-10 | 2016-12-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049569 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Docot; William | Dry Run - Support | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 8 | 0 | 8 | 2016-11-21 | 2016-11-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049570 | Yes | No | Argentina | Argentina | 06-Hypercare | Docot; William | HC - Manage Defects | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 12 | 0 | 12 | 2017-02-27 | 2017-03-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049571 | Yes | No | Argentina | Argentina | 06-Hypercare | Docot; William | HC - Break/Fix - RTR | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 114 | 0 | 114 | 2017-02-06 | 2017-03-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049572 | Yes | No | Argentina | Argentina | 06-Hypercare | Docot; William | HC - Provide end User Support - RTR | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | OpEx | Localization | IT - External | 24 | 0 | 24 | 2017-02-28 | 2017-03-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049573 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Docot; William | Cut Over - Support | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 43 | 0 | 43 | 2017-01-03 | 2017-01-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049574 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Docot; William | Cut Over - Validate | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-19 | 2016-12-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049575 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Docot; William | Cut Over - Prepare | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 23 | 0 | 23 | 2016-12-12 | 2016-12-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049576 | Yes | No | Argentina | Argentina | 04-Test | Docot; William | Mock1 - Support | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2016-07-15 | 2016-07-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049577 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Gilbert; Marc | Development (Cutover/Go-live) | DEV | DEV | SI | Onshore | Gilbert; Marc | IBM | Yes | CapEx | Localization | IT - External | 44 | 0 | 44 | 2017-01-30 | 2017-02-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049578 | Yes | No | Argentina | Argentina | 06-Hypercare | Gilbert; Marc | Development (Hypercare) | DEV | DEV | SI | Onshore | Gilbert; Marc | IBM | Yes | OpEx | Localization | IT - External | 275 | 0 | 275 | 2017-02-06 | 2017-03-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049579 | Yes | No | Argentina | Argentina | 04-Test | Gilbert; Marc | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Onshore | Gilbert; Marc | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-24 | 2016-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049580 | Yes | No | Argentina | Argentina | 03-Design/Build | Gilbert; Marc | Code, Tech spec. and FUT support | DEV | DEV | SI | Onshore | Gilbert; Marc | IBM | Yes | CapEx | Localization | IT - External | 36 | 0 | 36 | 2016-09-06 | 2016-09-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049581 | Yes | No | Argentina | Argentina | 04-Test | Gilbert; Marc | Development | DEV | DEV | SI | Onshore | Gilbert; Marc | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-08-22 | 2016-08-22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049582 | Yes | No | Argentina | Argentina |  | Gilbert; Marc | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Onshore | Gilbert; Marc | IBM | Yes | OpEx | Global | IT - External | 0 | 0 | 0 | 2017-05-23 | 2017-05-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049583 | Yes | No | Argentina | Argentina | 06-Hypercare | Gilbert; Marc | Argentina Production Support-DEV | DEV | DEV | SI | Onshore | Gilbert; Marc | IBM | Yes | OpEx | Localization | IT - External | 485 | 0 | 485 | 2017-03-06 | 2017-05-31 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049584 | Yes | No | Argentina | Argentina | 04-Test | Faiz; Abdelhadi | Development | DEV | DEV | SI | Onshore | Faiz; Abdelhadi | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-08-22 | 2016-08-22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049585 | Yes | No | Argentina | Argentina | 03-Design/Build | Faiz; Abdelhadi | Code, Tech spec. and FUT support | DEV | DEV | SI | Onshore | Faiz; Abdelhadi | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-08-15 | 2016-08-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049586 | Yes | No | Argentina | Argentina | 04-Test | Faiz; Abdelhadi | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Onshore | Faiz; Abdelhadi | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-24 | 2016-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049587 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Faiz; Abdelhadi | Development (Cutover/Go-live) | DEV | DEV | SI | Onshore | Faiz; Abdelhadi | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049588 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Nguyen; Tony | Development (Cutover/Go-live) | DEV | DEV | SI | Onshore | Nguyen; Tony | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049589 | Yes | No | Argentina | Argentina | 04-Test | Nguyen; Tony | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Onshore | Nguyen; Tony | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-24 | 2016-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049590 | Yes | No | Argentina | Argentina | 03-Design/Build | Nguyen; Tony | Code, Tech spec. and FUT support | DEV | DEV | SI | Onshore | Nguyen; Tony | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-08-15 | 2016-08-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049591 | Yes | No | Argentina | Argentina | 04-Test | Nguyen; Tony | Development | DEV | DEV | SI | Onshore | Nguyen; Tony | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-08-22 | 2016-08-22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049592 | Yes | No | Argentina | Argentina | 04-Test | Nera; Noel | TEST - Master Data Migration and Governance (Gen) (SI) - DM | MDG | DM | SI | Onshore | Nera; Noel | SAP | Yes | CapEx | Localization | IT - External | 32 | 0 | 32 | 2016-09-06 | 2016-09-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049593 | Yes | No | Argentina | Argentina | 04-Test | Nera; Noel | SIT1 - Execution (SI) - DM | MDG | DM | SI | Onshore | Nera; Noel | SAP | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-09-12 | 2016-09-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049594 | Yes | No | Argentina | Argentina | 03-Design/Build | Nera; Noel | ARG : DB - Conduct Mock 1 Load in QA (SAP) - DM | MDG | DM | SI | Onshore | Nera; Noel | SAP | Yes | CapEx | Localization | IT - External | 80 | 0 | 80 | 2016-08-22 | 2016-09-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049595 | Yes | No | Argentina | Argentina | 04-Test | Nera; Noel | SIT2 - Execution (SI) - DM | MDG | DM | SI | Onshore | Nera; Noel | SAP | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-24 | 2016-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049596 | Yes | No | Argentina | Argentina | 04-Test | Teixeira; Adilson | SIT 2 - Prep | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-17 | 2016-10-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049597 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Teixeira; Adilson | UAT - Run Tests | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 132 | 0 | 132 | 2016-12-12 | 2017-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049598 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Teixeira; Adilson | Dry Run - Validate | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-11-28 | 2016-11-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049599 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Teixeira; Adilson | Cut Over - Prepare | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049600 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Teixeira; Adilson | Cut Over - Support | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 132 | 0 | 132 | 2017-01-09 | 2017-01-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049601 | Yes | No | Argentina | Argentina | 04-Test | Teixeira; Adilson | OTC - SIT 2 - Run Tests | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 233 | 0 | 233 | 2016-10-24 | 2016-12-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049602 | Yes | No | Argentina | Argentina | 04-Test | Teixeira; Adilson | SIT 1 - Break/Fix | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 44 | 0 | 44 | 2016-10-17 | 2016-10-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049603 | Yes | No | Argentina | Argentina | 04-Test | Teixeira; Adilson | OTC - SIT 2 - Break/Fix | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 130 | 0 | 130 | 2016-11-07 | 2016-12-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049604 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Teixeira; Adilson | Dry Run - Prepare | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-11-07 | 2016-11-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049605 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Teixeira; Adilson | Dry Run - Support | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 4 | 0 | 4 | 2016-11-21 | 2016-11-22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049606 | Yes | No | Argentina | Argentina | 06-Hypercare | Teixeira; Adilson | HC - Manage Defects | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049607 | Yes | No | Argentina | Argentina | 06-Hypercare | Teixeira; Adilson | HC - Provide end User Support | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | OpEx | Localization | IT - External | 158 | 0 | 158 | 2017-02-06 | 2017-03-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049608 | Yes | No | Argentina | Argentina | 06-Hypercare | Teixeira; Adilson | HC - Break/Fix | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 60 | 0 | 60 | 2017-02-20 | 2017-02-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049609 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Teixeira; Adilson | Cut Over - Validate | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-19 | 2016-12-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049610 | Yes | No | Argentina | Argentina | 04-Test | Teixeira; Adilson | SIT 1 - Run Tests | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 98.4 | 0 | 98.4 | 2016-09-14 | 2016-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049611 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Teixeira; Adilson | Transition to Hypercare - OTC | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 78 | 0 | 78 | 2017-01-30 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049612 | No | Yes | Argentina | Argentina | 06-Hypercare | Lawson; Ted | Argentina Production Support-PMO | PMO | PMO | Saputo | Onshore | Lawson; Ted | Saputo | Yes | OpEx | Localization | Business | 0 | 0 | 0 | 2017-03-06 | 2017-03-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049613 | Yes | No | Argentina | Argentina | 06-Hypercare | Sulyman; Ola | Argentina Production Support-PTM | PTM | FUN | SI | Onshore | Sulyman; Ola | IBM | Yes | OpEx | Localization | IT - External | 240 | 0 | 240 | 2017-03-27 | 2017-06-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049614 | Yes | No | Argentina | Argentina | 06-Hypercare | Sulyman; Ola | HC - Provide end User Support - PTM | PTM | FUN | SI | Onshore | Sulyman; Ola | IBM | Yes | OpEx | Localization | IT - External | 44 | 0 | 44 | 2017-02-06 | 2017-02-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049615 | Yes | No | Argentina | Argentina | 06-Hypercare | Sulyman; Ola | HC - Break/Fix - PTM | PTM | FUN | SI | Onshore | Sulyman; Ola | IBM | Yes | CapEx | Localization | IT - External | 132 | 0 | 132 | 2017-02-13 | 2017-03-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049616 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Sulyman; Ola | Transition to Hypercare - PTM | PTM | FUN | SI | Onshore | Sulyman; Ola | IBM | Yes | CapEx | Localization | IT - External | 88 | 0 | 88 | 2017-01-23 | 2017-02-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049617 | No | Yes | Argentina | Argentina | 06-Hypercare | Parulekar; Manisha | HC - Provide end User Support - PTM | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2017-01-23 | 2017-01-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049618 | No | Yes | Argentina | Argentina | 06-Hypercare | Parulekar; Manisha | HC - Break/Fix - PTM | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049619 | No | Yes | Argentina | Argentina | 04-Test | Garapati; Sri | OTC - SIT 2 - Break/Fix | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 422 | 0 | 422 | 2016-11-21 | 2017-01-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049620 | No | Yes | Argentina | Argentina | 04-Test | Garapati; Sri | SIT 1 - Break/Fix | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 10 | 0 | 10 | 2016-10-03 | 2016-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049621 | No | Yes | Argentina | Argentina | 04-Test | Garapati; Sri | OTC - SIT 2 - Run Tests | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 153 | 0 | 153 | 2016-10-31 | 2016-11-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049622 | No | Yes | Argentina | Argentina | 04-Test | Garapati; Sri | OTC - SIT 2 - Manage Defects | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 9 | 0 | 9 | 2016-11-14 | 2016-11-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049623 | No | Yes | Argentina | Argentina | 03-Design/Build | Garapati; Sri | ARG KT visit | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-08-08 | 2016-08-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049624 | No | Yes | Argentina | Argentina | 04-Test | Garapati; Sri | SIT 2 - Prep | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 88 | 0 | 88 | 2016-10-17 | 2016-10-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049625 | No | Yes | Argentina | Argentina | 03-Design/Build | Garapati; Sri | Unit testing Configuration Documentation | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-08-08 | 2016-08-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049626 | No | Yes | Argentina | Argentina | 06-Hypercare | Garapati; Sri | HC - Break/Fix | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 9 | 0 | 9 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049627 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Garapati; Sri | Transition to Hypercare - OTC | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 60 | 0 | 60 | 2017-01-30 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049628 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Garapati; Sri | Cut Over - Support | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049629 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Garapati; Sri | Cut Over - Validate | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-19 | 2016-12-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049630 | No | Yes | Argentina | Argentina | 04-Test | Garapati; Sri | SIT 1 - Run Tests | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 75 | 0 | 75 | 2016-10-03 | 2016-10-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049631 | No | Yes | Argentina | Argentina | 04-Test | Garapati; Sri | SIT 1 - Manage Defects | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 10 | 0 | 10 | 2016-10-03 | 2016-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049632 | Yes | Yes | Argentina | Argentina | 04-Test | Tewari; Apoorva | Development | DEV | DEV | SI | Offshore | Tewari; Apoorva | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-08-22 | 2016-08-22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049633 | Yes | Yes | Argentina | Argentina | 03-Design/Build | Tewari; Apoorva | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Tewari; Apoorva | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-08-15 | 2016-08-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049634 | Yes | Yes | Argentina | Argentina | 04-Test | Tewari; Apoorva | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Tewari; Apoorva | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-24 | 2016-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049635 | Yes | Yes | Argentina | Argentina | 05-Cutover/Go-live | Tewari; Apoorva | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Tewari; Apoorva | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049636 | Yes | No | Argentina | Argentina | 04-Test | Frame; Susanne | Training Materials - Concept slides & Exercices book | CM | CM | SI | Onshore | Frame; Susanne | IBM | Yes | OpEx | Localization | IT - External | 412 | 0 | 412 | 2016-09-26 | 2016-12-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049637 | Yes | No | Argentina | Argentina | 04-Test | Harten; Ian | Work Instructions - Exercices DATA (technical writer + Dele) | CM | CM | SI | Onshore | Harten; Ian | IBM | Yes | OpEx | Localization | IT - External | 721 | 0 | 721 | 2016-09-19 | 2017-01-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049638 | Yes | Yes | Argentina | Argentina | 04-Test | Cousley; Fabian | SIT2 - Execution (SI) - DM | MDG | DM | SI | Onshore | Cousley; Fabian | SAP | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-24 | 2016-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049639 | Yes | Yes | Argentina | Argentina | 03-Design/Build | Cousley; Fabian | ARG : DB - Conduct Mock 1 Load in QA (SAP) - DM | MDG | DM | SI | Onshore | Cousley; Fabian | SAP | Yes | CapEx | Localization | IT - External | 32 | 0 | 32 | 2016-06-22 | 2016-09-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049640 | Yes | Yes | Argentina | Argentina | 04-Test | Cousley; Fabian | SIT1 - Execution (SI) - DM | MDG | DM | SI | Onshore | Cousley; Fabian | SAP | Yes | CapEx | Localization | IT - External | 40 | 0 | 40 | 2016-09-26 | 2016-09-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049641 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Sorino; Irezar | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Sorino; Irezar | Accenture | Yes | CapEx | Localization | IT - External | 387 | 0 | 387 | 2016-12-05 | 2017-02-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049642 | Yes | No | Argentina | Argentina | 06-Hypercare | Sorino; Irezar | Development (Hypercare) | DEV | DEV | SI | Offshore | Sorino; Irezar | Accenture | Yes | OpEx | Localization | IT - External | 35 | 0 | 35 | 2017-02-06 | 2017-02-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049643 | Yes | No | Argentina | Argentina | 04-Test | Sorino; Irezar | Development | DEV | DEV | SI | Offshore | Sorino; Irezar | Accenture | Yes | CapEx | Localization | IT - External | 333 | 0 | 333 | 2016-10-10 | 2016-12-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049644 | Yes | No | Argentina | Argentina | 06-Hypercare | Sorino; Irezar | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | Sorino; Irezar | Accenture | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-27 | 2017-02-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049645 | Yes | No | Argentina | Argentina | 04-Test | Sorino; Irezar | SIT1 - Defect Fix - DEV | DEV | DEV | SI | Offshore | Sorino; Irezar | Accenture | Yes | CapEx | Localization | IT - External | 20 | 0 | 20 | 2016-09-26 | 2016-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049646 | Yes | No | Argentina | Argentina | 04-Test | Sorino; Irezar | SIT1 - Manage Defect - DEV | DEV | DEV | SI | Offshore | Sorino; Irezar | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-09-12 | 2016-09-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049647 | Yes | No | Argentina | Argentina | 04-Test | Sorino; Irezar | TEST - Master Data Migration and Governance (Gen) - DEV | DEV | DEV | SI | Offshore | Sorino; Irezar | Accenture | Yes | CapEx | Localization | IT - External | 16 | 0 | 16 | 2016-10-03 | 2016-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049648 | Yes | No | Argentina | Argentina | 04-Test | Josephson; Jacob | TEST - Master Data Migration and Governance (Gen) (SI) - DM | MDG | DM | SI | Onshore | Josephson; Jacob | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-09-05 | 2016-09-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049649 | Yes | No | Argentina | Argentina | 06-Hypercare | Josephson; Jacob | Hypercare Support (Accenture) - DM | MDG | DM | SI | Onshore | Josephson; Jacob | Accenture | Yes | CapEx | Localization | IT - External | 156 | 0 | 156 | 2017-02-06 | 2017-02-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049650 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Josephson; Jacob | Recordings Customer/Work Instructions (Accenture) - DM | MDG | DM | SI | Onshore | Josephson; Jacob | Accenture | Yes | OpEx | Localization | IT - External | 72 | 0 | 72 | 2017-01-18 | 2017-02-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049651 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Josephson; Jacob | Recordings Vendor/Work Instructions (Accenture) - DM | MDG | DM | SI | Onshore | Josephson; Jacob | Accenture | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049652 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Josephson; Jacob | Execute Cutover (Accenture) - DM | MDG | DM | SI | Onshore | Josephson; Jacob | Accenture | Yes | CapEx | Localization | IT - External | 144 | 0 | 144 | 2016-12-19 | 2017-01-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049653 | Yes | No | Argentina | Argentina | 04-Test | Josephson; Jacob | SIT1 - Defect Fix (Accenture) - DM | MDG | DM | SI | Onshore | Josephson; Jacob | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-09-05 | 2016-09-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049654 | Yes | No | Argentina | Argentina | 04-Test | Josephson; Jacob | SIT 2 - Prep (Accenture) - DM | MDG | DM | SI | Onshore | Josephson; Jacob | Accenture | Yes | CapEx | Localization | IT - External | 40 | 0 | 40 | 2016-10-24 | 2016-10-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049655 | Yes | No | Argentina | Argentina | 04-Test | Josephson; Jacob | SIT2 - Execution (SI) - DM | MDG | DM | SI | Onshore | Josephson; Jacob | Accenture | Yes | CapEx | Localization | IT - External | 40 | 0 | 40 | 2016-11-28 | 2016-12-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049656 | Yes | No | Argentina | Argentina | 04-Test | Josephson; Jacob | SIT2 - Manage Defect (Accenture) - DM | MDG | DM | SI | Onshore | Josephson; Jacob | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-24 | 2016-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049657 | Yes | No | Argentina | Argentina | 04-Test | Josephson; Jacob | SIT2 - Defect Fix (Accenture) - DM | MDG | DM | SI | Onshore | Josephson; Jacob | Accenture | Yes | CapEx | Localization | IT - External | 104 | 0 | 104 | 2016-11-21 | 2016-12-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049658 | No | Yes | Argentina | Argentina | 04-Test | Thayyil; Shajariya | TEST - Technical Architecture and Infrastructure (gen) | TAI | TAI | SI | Onshore | Thayyil; Shajariya | Accenture | Yes | CapEx | Localization | IT - External | 132 | 0 | 132 | 2016-09-26 | 2016-10-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049659 | No | Yes | Argentina | Argentina | 04-Test | Thayyil; Shajariya | TEST - Master Data Migration and Governance (Gen) - TAI | TAI | TAI | SI | Onshore | Thayyil; Shajariya | Accenture | Yes | CapEx | Localization | IT - External | 36 | 0 | 36 | 2016-09-06 | 2016-09-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049660 | No | Yes | Argentina | Argentina | 04-Test | Policarpio; Raphael | Development | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 62.5 | 0 | 62.5 | 2016-10-24 | 2016-11-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049661 | No | Yes | Argentina | Argentina | 04-Test | Policarpio; Raphael | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 0 | 0 | 0 | 2016-10-24 | 2016-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049662 | No | Yes | Argentina | Argentina |  | Policarpio; Raphael | Knowledge_Transfer_AMS - DEV | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | OpEx | Global | IT - Internal | 1.5 | 0 | 1.5 | 2017-05-29 | 2017-05-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049663 | No | Yes | Argentina | Argentina | 06-Hypercare | Policarpio; Raphael | Argentina Production Support-DEV | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | OpEx | Localization | IT - Internal | 28.5 | 0 | 28.5 | 2017-03-27 | 2017-07-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049664 | No | Yes | Argentina | Argentina | 06-Hypercare | Policarpio; Raphael | Development (Hypercare) | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | OpEx | Localization | IT - Internal | 7.5 | 0 | 7.5 | 2017-02-07 | 2017-02-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049665 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Policarpio; Raphael | Development (Cutover/Go-live) | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 61.5 | 0 | 61.5 | 2017-01-04 | 2017-01-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049666 | No | Yes | Argentina | Argentina | 03-Design/Build | Policarpio; Raphael | Code, Tech spec. and FUT support | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 0 | 0 | 0 | 2016-08-15 | 2016-08-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049667 | No | Yes | Argentina | Argentina | 04-Test | Policarpio; Raphael | Management (Planning, reporting, team organization) | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 66.5 | 0 | 66.5 | 2016-10-06 | 2016-10-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049668 | Yes | No | Argentina | Argentina | 04-Test | Minarro; Javier | SIT 1 - Break/Fix | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 48 | 0 | 48 | 2016-10-10 | 2016-10-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049669 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Minarro; Javier | Transition to Hypercare | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 44 | 0 | 44 | 2017-01-30 | 2017-02-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049670 | Yes | No | Argentina | Argentina | 03-Design/Build | Minarro; Javier | Unit testing Configuration Documentation | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 34 | 0 | 34 | 2016-08-22 | 2016-09-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049671 | Yes | No | Argentina | Argentina | 04-Test | Minarro; Javier | SIT 2 - RTR - Prep | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 22 | 0 | 22 | 2016-10-17 | 2016-11-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049672 | Yes | No | Argentina | Argentina | 03-Design/Build | Minarro; Javier | ARG KT visit | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 34 | 0 | 34 | 2016-08-15 | 2016-08-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049673 | Yes | No | Argentina | Argentina | 04-Test | Minarro; Javier | SIT 1 - Run Tests | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 172 | 0 | 172 | 2016-09-10 | 2016-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049674 | Yes | No | Argentina | Argentina | 03-Design/Build | Minarro; Javier | ARG : DB - Functional Specifications and UT- RTR | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 430 | 0 | 430 | 2016-05-30 | 2016-08-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049675 | Yes | No | Argentina | Argentina | 03-Design/Build | Minarro; Javier | ARG : DB - SDD - RTR | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 26 | 0 | 26 | 2016-07-11 | 2016-07-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049676 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Minarro; Javier | Interim reporting (400hours) | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-12 | 2016-12-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049677 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Minarro; Javier | Cut Over - Prepare | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049678 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Minarro; Javier | UAT - Break/Fix and document work around | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 166 | 0 | 166 | 2016-12-19 | 2017-01-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049679 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Minarro; Javier | Cut Over - Support | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 1 | 0 | 1 | 2016-12-22 | 2016-12-22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049680 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Minarro; Javier | Cut Over - Validate | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 20 | 0 | 20 | 2017-01-16 | 2017-01-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049681 | Yes | No | Argentina | Argentina | 06-Hypercare | Minarro; Javier | HC - Manage Defects | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-27 | 2017-02-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049682 | Yes | No | Argentina | Argentina | 06-Hypercare | Minarro; Javier | HC - Provide end User Support - RTR | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | OpEx | Localization | IT - External | 228 | 0 | 228 | 2017-02-06 | 2017-03-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049683 | Yes | No | Argentina | Argentina | 06-Hypercare | Minarro; Javier | HC - Break/Fix - RTR | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 19 | 0 | 19 | 2017-02-06 | 2017-02-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049684 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Minarro; Javier | UAT - Run Tests | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 121 | 0 | 121 | 2016-12-05 | 2016-12-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049685 | Yes | No | Argentina | Argentina | 04-Test | Minarro; Javier | SIT 2 - RTR - Break/Fix | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 38 | 0 | 38 | 2016-10-31 | 2016-12-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049686 | Yes | No | Argentina | Argentina | 04-Test | Minarro; Javier | SIT 2 - RTR - Manage Defects | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 62 | 0 | 62 | 2016-11-11 | 2016-12-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049687 | Yes | No | Argentina | Argentina | 04-Test | Minarro; Javier | SIT 2 - RTR - Run Tests | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 86 | 0 | 86 | 2016-10-31 | 2016-11-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049688 | Yes | No | Argentina | Argentina | 01-Preparation | Minarro; Javier | Argentina Project - Sharepoint Access - | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2015-12-01 | 2015-12-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049689 | No | Yes | Argentina | Argentina | 06-Hypercare | Shukla; Yogesh | Development (Hypercare) | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | OpEx | Localization | IT - External | 180 | 0 | 180 | 2017-02-06 | 2017-03-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049690 | No | Yes | Argentina | Argentina | 04-Test | Shukla; Yogesh | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-24 | 2016-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049691 | No | Yes | Argentina | Argentina | 06-Hypercare | Shukla; Yogesh | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | OpEx | Localization | IT - External | 194.5 | 0 | 194.5 | 2017-03-06 | 2017-06-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049692 | No | Yes | Argentina | Argentina | 03-Design/Build | Shukla; Yogesh | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | CapEx | Localization | IT - External | 102 | 0 | 102 | 2016-08-22 | 2016-10-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049693 | No | Yes | Argentina | Argentina | 04-Test | Shukla; Yogesh | Development | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | CapEx | Localization | IT - External | 201 | 0 | 201 | 2016-09-21 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049694 | No | Yes | Argentina | Argentina |  | Shukla; Yogesh | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | OpEx | Global | IT - External | 5 | 0 | 5 | 2017-05-23 | 2017-06-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049695 | No | Yes | Argentina | Argentina | 03-Design/Build | Shukla; Yogesh | ARG : DB - Technical Specifications | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-04-13 | 2016-04-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049696 | No | Yes | Argentina | Argentina | 03-Design/Build | Shukla; Yogesh | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-05-09 | 2016-05-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049697 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Soufi; Sammy | Transition to Hypercare - LOG | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 184 | 0 | 184 | 2016-12-28 | 2017-02-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049698 | No | Yes | Argentina | Argentina | 06-Hypercare | Soufi; Sammy | HC - Provide end User Support | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | OpEx | Localization | IT - External | 88 | 0 | 88 | 2017-02-06 | 2017-02-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049699 | No | Yes | Argentina | Argentina | 06-Hypercare | Soufi; Sammy | HC - Break/Fix | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049700 | No | Yes | Argentina | Argentina | 04-Test | Soufi; Sammy | Manage SIT1 Prep (data, transports) | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 92 | 0 | 92 | 2016-08-29 | 2016-09-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049701 | No | Yes | Argentina | Argentina | 04-Test | Soufi; Sammy | Manage SIT1 Execution | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 40.88 | 0 | 40.88 | 2016-10-11 | 2016-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049702 | No | Yes | Argentina | Argentina | 04-Test | Soufi; Sammy | Manage SIT1 Execution local (ARG) | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 35 | 0 | 35 | 2016-10-04 | 2016-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049703 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Soufi; Sammy | Manage UAT Execution | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049704 | No | Yes | Argentina | Argentina | 04-Test | Soufi; Sammy | Manage SIT2 Execution local (ARG) | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 54 | 0 | 54 | 2016-11-14 | 2016-11-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049705 | No | Yes | Argentina | Argentina | 04-Test | Soufi; Sammy | Manage SIT2 Prep (data, transports) | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 44 | 0 | 44 | 2016-10-24 | 2016-10-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049706 | No | Yes | Argentina | Argentina | 04-Test | Soufi; Sammy | Manage SIT2 Execution | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 203 | 0 | 203 | 2016-10-31 | 2016-12-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049707 | No | Yes | Argentina | Argentina | 04-Test | Goel; Ronika | Work Instructions - Exercices DATA (technical writer + Dele) | CM | CM | SI | Onshore | Goel; Ronika | IBM | Yes | OpEx | Localization | IT - External | 859 | 0 | 859 | 2016-09-19 | 2017-02-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049708 | Yes | No | Argentina | Argentina | 04-Test | Rudrurkar; Vijay | Work Instructions - Exercices DATA (technical writer + Dele) | CM | CM | SI | Offshore | Rudrurkar; Vijay | IBM | Yes | OpEx | Localization | IT - External | 306 | 0 | 306 | 2016-09-19 | 2016-11-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049709 | No | Yes | Argentina | Argentina | 04-Test | Ombisi; Mercy | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 0 | 0 | 0 | 2016-09-05 | 2016-09-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049710 | No | Yes | Argentina | Argentina | 04-Test | Ombisi; Mercy | SIT1 - Execution - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 248 | 0 | 248 | 2016-09-12 | 2016-10-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049711 | No | Yes | Argentina | Argentina | 06-Hypercare | Ombisi; Mercy | Argentina Production Support-MDG-DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | OpEx | Localization | IT - Internal | 10 | 0 | 10 | 2017-03-20 | 2017-03-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049712 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Ombisi; Mercy | Execute pre validation - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | OpEx | Localization | IT - Internal | 44 | 0 | 44 | 2016-12-19 | 2017-01-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049713 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Ombisi; Mercy | Execute loads/ reports - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | OpEx | Localization | IT - Internal | 46 | 0 | 46 | 2016-12-12 | 2017-02-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049714 | No | Yes | Argentina | Argentina | 04-Test | Ombisi; Mercy | SIT2 - Execution - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 45 | 0 | 45 | 2016-10-24 | 2016-10-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049715 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Ombisi; Mercy | Cut Over - Support - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 89 | 0 | 89 | 2017-01-02 | 2017-01-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049716 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Gamez; Valerie | Transition to Hypercare - OTC | OTC | FUN | SI | Onshore | Gamez; Valerie | SAP | Yes | CapEx | Localization | IT - External | 120 | 0 | 120 | 2017-01-02 | 2017-01-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049717 | No | Yes | Argentina | Argentina | 06-Hypercare | Chan; Jonathan | Argentina Production Support-MDG-DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2017-03-20 | 2017-03-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049718 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Chan; Jonathan | Execute loads/ reports - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | OpEx | Localization | IT - External | 90 | 0 | 90 | 2016-12-12 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049719 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Chan; Jonathan | Dry Run - Execute pre validation - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 192 | 0 | 192 | 2016-11-14 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049720 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Chan; Jonathan | Execute pre validation - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | OpEx | Localization | IT - External | 269 | 0 | 269 | 2016-12-05 | 2017-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049721 | No | Yes | Argentina | Argentina | 04-Test | Chan; Jonathan | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 369 | 0 | 369 | 2016-09-19 | 2016-11-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049722 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Battles; Shanell | Recordings Customer/Work Instructions (Saputo) - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 0 | 0 | 0 | 2016-12-12 | 2016-12-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049723 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Battles; Shanell | Recordings Vendor/Work Instructions (Saputo) - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049724 | No | Yes | Argentina | Argentina | 06-Hypercare | Battles; Shanell | Hypercare Support (Saputo) - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 160 | 0 | 160 | 2017-02-06 | 2017-03-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049725 | No | Yes | Argentina | Argentina | 06-Hypercare | Battles; Shanell | Argentina Production Support-MDG-(Saputo - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 167 | 0 | 167 | 2017-03-20 | 2017-04-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049726 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Battles; Shanell | Cutover - Dual Maintenance Argentina Customer (Saputo) - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 36 | 0 | 36 | 2017-01-03 | 2017-01-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049727 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Battles; Shanell | Cutover - Dual Maintenance Argentina Vendor (Saputo) - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 92 | 0 | 92 | 2017-01-03 | 2017-02-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049728 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Battles; Shanell | Cutover - Dual Maintenance Argentina Materials (Saputo) - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 56 | 0 | 56 | 2017-01-16 | 2017-02-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049729 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Battles; Shanell | Cutover - Dual Maintenance Argentina Finance (Saputo) - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 0 | 0 | 0 | 2016-12-27 | 2016-12-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049730 | Yes | No | Argentina | Argentina | 04-Test | Dodds; Elaine | LOG - SIT 2 - Break/Fix | OTC | FUN | SI | Onshore | Dodds; Elaine | IBM | Yes | CapEx | Localization | IT - External | 88 | 0 | 88 | 2016-11-21 | 2016-12-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049731 | Yes | No | Argentina | Argentina | 06-Hypercare | Dodds; Elaine | HC - Provide end User Support | OTC | FUN | SI | Onshore | Dodds; Elaine | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-01 | 2016-12-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049732 | Yes | No | Argentina | Argentina | 06-Hypercare | Dodds; Elaine | HC - Break/Fix | OTC | FUN | SI | Onshore | Dodds; Elaine | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049733 | No | Yes | Argentina | Argentina | 06-Hypercare | Segarra; Josefina | Argentina Production Support-MDG-DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | OpEx | Localization | IT - Internal | 0 | 0 | 0 | 2017-03-20 | 2017-03-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049734 | No | Yes | Argentina | Argentina | 06-Hypercare | Lentz; Jared | Argentina Production Support-MDG-DG | MDG | DG | Saputo | Onshore | Lentz; Jared | Saputo | Yes | OpEx | Localization | IT - Internal | 15 | 0 | 15 | 2017-03-20 | 2017-06-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049735 | No | Yes | Argentina | Argentina | 04-Test | Lentz; Jared | Data quality - DG | MDG | DG | Saputo | Onshore | Lentz; Jared | Saputo | Yes | OpEx | Localization | IT - Internal | 108 | 0 | 108 | 2016-11-14 | 2016-12-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049736 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Lentz; Jared | Data quality (Cutover/Go-live) - DG | MDG | DG | Saputo | Onshore | Lentz; Jared | Saputo | Yes | OpEx | Localization | IT - Internal | 322 | 0 | 322 | 2016-12-05 | 2017-02-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049737 | No | Yes | Argentina | Argentina | 06-Hypercare | Lentz; Jared | Data quality (Hypercare) - DG | MDG | DG | Saputo | Onshore | Lentz; Jared | Saputo | Yes | OpEx | Localization | IT - Internal | 101.4 | 0 | 101.4 | 2017-02-06 | 2017-03-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049738 | Yes | No | Argentina | Argentina |  | Ghoshbiswas; Veena | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Ghoshbiswas; Veena | IBM | Yes | OpEx | Global | IT - External | 0 | 0 | 0 | 2017-05-23 | 2017-05-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049739 | Yes | No | Argentina | Argentina | 06-Hypercare | Ghoshbiswas; Veena | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | Ghoshbiswas; Veena | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-27 | 2017-02-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049740 | Yes | No | Argentina | Argentina | 06-Hypercare | Ghoshbiswas; Veena | Development (Hypercare) | DEV | DEV | SI | Offshore | Ghoshbiswas; Veena | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2017-01-23 | 2017-03-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049741 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Gireesh; Mangeshi | Execute loads/ reports (Accenture) - DM | MDG | DM | SI | Onshore | Gireesh; Mangeshi | Accenture | Yes | CapEx | Localization | IT - External | 168 | 0 | 168 | 2016-12-29 | 2017-01-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049742 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Gireesh; Mangeshi | Dry Run - Execute pre validation (Accenture) - DM | MDG | DM | SI | Onshore | Gireesh; Mangeshi | Accenture | Yes | CapEx | Localization | IT - External | 40 | 0 | 40 | 2016-12-05 | 2016-12-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049743 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Gireesh; Mangeshi | Dry Run - Execute Loads/Reports (Accenture) - DM | MDG | DM | SI | Onshore | Gireesh; Mangeshi | Accenture | Yes | CapEx | Localization | IT - External | 40 | 0 | 40 | 2016-11-28 | 2016-12-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049744 | Yes | No | Argentina | Argentina | 04-Test | Gireesh; Mangeshi | SIT2 - Execution (SI) - DM | MDG | DM | SI | Onshore | Gireesh; Mangeshi | Accenture | Yes | CapEx | Localization | IT - External | 120 | 0 | 120 | 2016-11-21 | 2016-12-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049745 | Yes | No | Argentina | Argentina | 04-Test | Gireesh; Mangeshi | SIT1 - Execution (SI) - DM | MDG | DM | SI | Onshore | Gireesh; Mangeshi | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-09-11 | 2016-09-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049746 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Gireesh; Mangeshi | Cutover - Dual Maintenance Argentina Finance (Accenture) - DM | MDG | DM | SI | Onshore | Gireesh; Mangeshi | Accenture | Yes | CapEx | Localization | IT - External | 40 | 0 | 40 | 2016-12-28 | 2017-02-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049747 | Yes | No | Argentina | Argentina | 06-Hypercare | Gireesh; Mangeshi | Hypercare Support (Accenture) - DM | MDG | DM | SI | Onshore | Gireesh; Mangeshi | Accenture | Yes | CapEx | Localization | IT - External | 112 | 0 | 112 | 2017-02-06 | 2017-02-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049748 | No | Yes | Argentina | Argentina | 04-Test | Kaji; Varun | SIT1 - Execution (SI) - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-09-11 | 2016-09-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049749 | No | Yes | Argentina | Argentina | 04-Test | Kaji; Varun | SIT2 - Execution (SI) - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 144 | 0 | 144 | 2016-11-21 | 2016-12-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049750 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Kaji; Varun | Cutover - Dual Maintenance Argentina Materials (Accenture) - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 120 | 0 | 120 | 2016-12-19 | 2017-01-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049751 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Kaji; Varun | Cutover - Dual Maintenance Argentina Finance (Accenture) - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-27 | 2016-12-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049752 | Yes | No | Argentina | Argentina | 06-Hypercare | McDonough; Alan | Argentina Production Support-LOG | LOG | FUN | SI | Onshore | McDonough; Alan | SAP | Yes | OpEx | Localization | IT - External | 120 | 0 | 120 | 2017-03-06 | 2017-03-31 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049753 | Yes | No | Argentina | Argentina | 04-Test | McDonough; Alan | LOG - SIT 2 - Break/Fix | LOG | FUN | SI | Onshore | McDonough; Alan | SAP | Yes | CapEx | Localization | IT - External | 136 | 0 | 136 | 2016-11-15 | 2016-12-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049754 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | McDonough; Alan | Dry Run - Support | LOG | FUN | SI | Onshore | McDonough; Alan | SAP | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-11-15 | 2016-11-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049755 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | McDonough; Alan | UAT - Break/Fix and document work around | LOG | FUN | SI | Onshore | McDonough; Alan | SAP | Yes | CapEx | Localization | IT - External | 160 | 0 | 160 | 2016-12-19 | 2017-01-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049756 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | McDonough; Alan | Cut Over - Support | LOG | FUN | SI | Onshore | McDonough; Alan | SAP | Yes | CapEx | Localization | IT - External | 98 | 0 | 98 | 2016-12-19 | 2017-02-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049757 | Yes | No | Argentina | Argentina | 06-Hypercare | McDonough; Alan | HC - Break/Fix | LOG | FUN | SI | Onshore | McDonough; Alan | SAP | Yes | CapEx | Localization | IT - External | 156 | 0 | 156 | 2017-02-06 | 2017-03-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049758 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | McDonough; Alan | Transition to Hypercare - LOG | LOG | FUN | SI | Onshore | McDonough; Alan | SAP | Yes | CapEx | Localization | IT - External | 40 | 0 | 40 | 2017-01-23 | 2017-01-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049759 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Haraida; Ricardo | Execute Cutover Steps | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-19 | 2016-12-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049760 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Haraida; Ricardo | Cut Over - Support | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049761 | Yes | No | Argentina | Argentina | 06-Hypercare | Haraida; Ricardo | HC - Manage Defects | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049762 | Yes | No | Argentina | Argentina | 06-Hypercare | Haraida; Ricardo | HC - Break/Fix | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049763 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Haraida; Ricardo | UAT - Prepare | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 115 | 0 | 115 | 2016-11-14 | 2016-12-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049764 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Haraida; Ricardo | UAT - Run Tests | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049765 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Haraida; Ricardo | UAT - Break/Fix and document work around | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049766 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Haraida; Ricardo | UAT - Manage Defects | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-11-21 | 2016-11-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049767 | Yes | No | Argentina | Argentina | 06-Hypercare | Haraida; Ricardo | HC - Provide end User Support | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049768 | No | Yes | Argentina | Argentina | 06-Hypercare | Imperial; Jhannica | Argentina Production Support-TAI | TAI | TAI | SI | Offshore | Imperial; Jhannica | Accenture | Yes | OpEx | Localization | IT - External | 751.5 | 0 | 751.5 | 2017-03-06 | 2017-08-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049769 | No | Yes | Argentina | Argentina | 06-Hypercare | Imperial; Jhannica | Support Hypercare | TAI | TAI | SI | Offshore | Imperial; Jhannica | Accenture | Yes | CapEx | Localization | IT - External | 180 | 0 | 180 | 2017-02-06 | 2017-03-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049770 | No | Yes | Argentina | Argentina |  | Prasad; Suresh | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | OpEx | Global | IT - External | 1 | 0 | 1 | 2017-06-01 | 2017-06-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049771 | No | Yes | Argentina | Argentina | 06-Hypercare | Prasad; Suresh | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | OpEx | Localization | IT - External | 93 | 0 | 93 | 2017-03-22 | 2017-05-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049772 | No | Yes | Argentina | Argentina | 03-Design/Build | Prasad; Suresh | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | CapEx | Localization | IT - External | 108.25 | 0 | 108.25 | 2016-09-19 | 2016-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049773 | No | Yes | Argentina | Argentina | 04-Test | Prasad; Suresh | Development | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | CapEx | Localization | IT - External | 93 | 0 | 93 | 2016-09-05 | 2016-11-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049774 | No | Yes | Argentina | Argentina | 06-Hypercare | Prasad; Suresh | Development (Hypercare) | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | OpEx | Localization | IT - External | 27 | 0 | 27 | 2017-02-06 | 2017-02-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049775 | No | Yes | Argentina | Argentina | 04-Test | Prasad; Suresh | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-24 | 2016-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049776 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Prasad; Suresh | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | CapEx | Localization | IT - External | 123 | 0 | 123 | 2016-12-24 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049777 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Gupta; Shubham | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Gupta; Shubham | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049778 | Yes | No | Argentina | Argentina | 04-Test | Gupta; Shubham | Development | DEV | DEV | SI | Offshore | Gupta; Shubham | IBM | Yes | CapEx | Localization | IT - External | 41 | 0 | 41 | 2016-09-28 | 2016-10-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049779 | Yes | No | Argentina | Argentina | 04-Test | Gupta; Shubham | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Gupta; Shubham | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-24 | 2016-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049780 | Yes | No | Argentina | Argentina | 03-Design/Build | Gupta; Shubham | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Gupta; Shubham | IBM | Yes | CapEx | Localization | IT - External | 92 | 0 | 92 | 2016-08-22 | 2016-10-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049781 | Yes | No | Argentina | Argentina | 03-Design/Build | Gupta; Shubham | ARG : DB - Technical Specifications | DEV | DEV | SI | Offshore | Gupta; Shubham | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-04-13 | 2016-04-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049782 | Yes | No | Argentina | Argentina | 03-Design/Build | Gupta; Shubham | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | Gupta; Shubham | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-05-09 | 2016-05-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049783 | Yes | No | Argentina | Argentina | 04-Test | Arya; Kapil | TEST - Technical Architecture and Infrastructure (gen) | TAI | TAI | SI | Onshore | Arya; Kapil | Accenture | Yes | CapEx | Localization | IT - External | 88 | 0 | 88 | 2016-09-01 | 2016-09-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049784 | Yes | No | Argentina | Argentina | 04-Test | Arya; Kapil | Performance testing and refresh | TAI | TAI | SI | Onshore | Arya; Kapil | Accenture | Yes | CapEx | Localization | IT - External | 152 | 0 | 152 | 2016-09-19 | 2016-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049785 | Yes | No | Argentina | Argentina | 04-Test | Arya; Kapil | Test disaster recovery | TAI | TAI | SI | Onshore | Arya; Kapil | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-02 | 2016-12-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049786 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Jaffery; Ikram | GRC AC - Cutover planning and Exucution | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-18 | 2016-10-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049787 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Jaffery; Ikram | UAT Defect Resolution | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 261 | 0 | 261 | 2016-12-05 | 2017-01-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049788 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Jaffery; Ikram | Cutover Planning and Execution | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-03 | 2016-10-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049789 | Yes | No | Argentina | Argentina | 03-Design/Build | Jaffery; Ikram | Composite Role Build | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-09-19 | 2016-09-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049790 | Yes | No | Argentina | Argentina | 03-Design/Build | Jaffery; Ikram | Derived Role Build | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 32 | 0 | 32 | 2016-10-17 | 2016-10-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049791 | Yes | No | Argentina | Argentina | 03-Design/Build | Jaffery; Ikram | Master Role Build and UT | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-09-12 | 2016-09-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049792 | Yes | No | Argentina | Argentina | 03-Design/Build | Jaffery; Ikram | Support Role Build and UT | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 24 | 0 | 24 | 2016-09-26 | 2016-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049793 | Yes | No | Argentina | Argentina | 04-Test | Jaffery; Ikram | FUT Support Roles | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-17 | 2016-10-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049794 | Yes | No | Argentina | Argentina | 04-Test | Jaffery; Ikram | Security Role FUT | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 20 | 0 | 20 | 2016-10-21 | 2016-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049795 | Yes | No | Argentina | Argentina | 04-Test | Jaffery; Ikram | SIT 1 Defect Resolution | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 8 | 0 | 8 | 2016-10-24 | 2016-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049796 | Yes | No | Argentina | Argentina | 04-Test | Jaffery; Ikram | SIT 2 Defect Resolution | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 258 | 0 | 258 | 2016-10-25 | 2016-12-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049797 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Jaffery; Ikram | GRC AC - UAT Execution | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049798 | Yes | No | Argentina | Argentina | 06-Hypercare | Jaffery; Ikram | Hypercare/support | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-01 | 2017-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049799 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Olvida; Julio | SoD Analysis and Remediation | SEC | SEC | SI | Offshore | Olvida; Julio | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049800 | No | Yes | Argentina | Argentina | 04-Test | Olvida; Julio | SoD Analysis and Remediation | SEC | SEC | SI | Offshore | Olvida; Julio | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-11-07 | 2016-11-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049801 | No | Yes | Argentina | Argentina | 04-Test | Olvida; Julio | GRC AC - SIT Execution | SEC | SEC | SI | Offshore | Olvida; Julio | Accenture | Yes | CapEx | Localization | IT - External | 74 | 0 | 74 | 2016-11-02 | 2016-11-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049802 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Olvida; Julio | GRC AC - UAT Execution | SEC | SEC | SI | Offshore | Olvida; Julio | Accenture | Yes | CapEx | Localization | IT - External | 65 | 0 | 65 | 2016-12-05 | 2017-01-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049803 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Olvida; Julio | GRC AC - Cutover planning and Exucution | SEC | SEC | SI | Offshore | Olvida; Julio | Accenture | Yes | CapEx | Localization | IT - External | 178 | 0 | 178 | 2016-10-19 | 2017-01-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049804 | No | Yes | Argentina | Argentina | 06-Hypercare | Olvida; Julio | GRC AC - Hypercare | SEC | SEC | SI | Offshore | Olvida; Julio | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049805 | No | Yes | Argentina | Argentina | 03-Design/Build | Olvida; Julio | GRC AC - Build & UT | SEC | SEC | SI | Offshore | Olvida; Julio | Accenture | Yes | CapEx | Localization | IT - External | 45 | 0 | 45 | 2016-10-17 | 2016-10-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049806 | No | Yes | Argentina | Argentina | 03-Design/Build | Olvida; Julio | GRC AC - SIT Prep | SEC | SEC | SI | Offshore | Olvida; Julio | Accenture | Yes | CapEx | Localization | IT - External | 82 | 0 | 82 | 2016-10-13 | 2016-11-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049807 | No | Yes | Argentina | Argentina | 03-Design/Build | Olvida; Julio | SoD Analysis and Remediation | SEC | SEC | SI | Offshore | Olvida; Julio | Accenture | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-09-30 | 2016-09-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049808 | No | Yes | Argentina | Argentina | 04-Test | Olvida; Julio | SIT 2 Defect Resolution | SEC | SEC | SI | Offshore | Olvida; Julio | Accenture | Yes | CapEx | Localization | IT - External | 30 | 0 | 30 | 2016-10-22 | 2016-12-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049809 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Olvida; Julio | Cutover Planning and Execution | SEC | SEC | SI | Offshore | Olvida; Julio | Accenture | Yes | CapEx | Localization | IT - External | 101 | 0 | 101 | 2016-12-12 | 2016-12-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049810 | Yes | No | Argentina | Argentina | 06-Hypercare | Jayasim; Franklin | Hypercare/support | SEC | SEC | SI | Onshore | Jayasim; Franklin | IBM | Yes | OpEx | Localization | IT - External | 53 | 0 | 53 | 2017-02-07 | 2017-02-26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049811 | Yes | No | Argentina | Argentina | 04-Test | Jayasim; Franklin | FUT Support Roles | SEC | SEC | SI | Onshore | Jayasim; Franklin | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-17 | 2016-10-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049812 | Yes | No | Argentina | Argentina | 04-Test | Jayasim; Franklin | SIT 2 Defect Resolution | SEC | SEC | SI | Onshore | Jayasim; Franklin | IBM | Yes | CapEx | Localization | IT - External | 16 | 0 | 16 | 2016-10-22 | 2016-11-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049813 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Jayasim; Franklin | UAT Defect Resolution | SEC | SEC | SI | Onshore | Jayasim; Franklin | IBM | Yes | CapEx | Localization | IT - External | 273 | 0 | 273 | 2016-12-05 | 2017-01-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049814 | Yes | No | Argentina | Argentina | 03-Design/Build | Jayasim; Franklin | SoD Analysis and Remediation | SEC | SEC | SI | Onshore | Jayasim; Franklin | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-09-30 | 2016-09-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049815 | Yes | No | Argentina | Argentina | 04-Test | Jayasim; Franklin | GRC AC - SIT Execution | SEC | SEC | SI | Onshore | Jayasim; Franklin | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-24 | 2016-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049816 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Jayasim; Franklin | GRC AC - Cutover planning and Exucution | SEC | SEC | SI | Onshore | Jayasim; Franklin | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-18 | 2016-10-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049817 | Yes | No | Argentina | Argentina | 06-Hypercare | Jayasim; Franklin | GRC AC - Hypercare | SEC | SEC | SI | Onshore | Jayasim; Franklin | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049818 | Yes | No | Argentina | Argentina | 04-Test | Jayasim; Franklin | SoD Analysis and Remediation | SEC | SEC | SI | Onshore | Jayasim; Franklin | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-11-07 | 2016-11-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049819 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Jayasim; Franklin | SoD Analysis and Remediation | SEC | SEC | SI | Onshore | Jayasim; Franklin | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049820 | Yes | No | Argentina | Argentina | 06-Hypercare | Kumar; Bijendra | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | Kumar; Bijendra | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-27 | 2017-02-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049821 | Yes | No | Argentina | Argentina | 06-Hypercare | Kumar; Bijendra | Development (Hypercare) | DEV | DEV | SI | Offshore | Kumar; Bijendra | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2017-01-23 | 2017-01-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049822 | No | Yes | Argentina | Argentina |  | Round; Andrew | Perform project Planning and Control | PMO | PMO | SI | Onshore | Round; Andrew | IBM | Yes | CapEx | Localization | IT - External | 26 | 0 | 26 | 2016-03-14 | 2017-01-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049823 | No | Yes | Argentina | Argentina | 04-Test | Melville; Steven | Management (Planning, reporting, CR, cross stream integration) | PTP | FUN | SI | Onshore | Melville; Steven | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-09-06 | 2016-09-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049824 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Martel; Kelly | Interim reporting (400hours) | RTR | FUN | SI | Onshore | Martel; Kelly | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-12 | 2016-12-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049825 | Yes | No | Argentina | Argentina | 04-Test | Martel; Kelly | SIT 2 - RTR - Prep | RTR | FUN | SI | Onshore | Martel; Kelly | IBM | Yes | CapEx | Localization | IT - External | 20 | 0 | 20 | 2016-10-24 | 2016-10-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049826 | Yes | No | Argentina | Argentina | 04-Test | Martel; Kelly | SIT 2 - RTR - Run Tests | RTR | FUN | SI | Onshore | Martel; Kelly | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-24 | 2016-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049827 | Yes | No | Argentina | Argentina | 04-Test | Martel; Kelly | SIT 2 - RTR - Manage Defects | RTR | FUN | SI | Onshore | Martel; Kelly | IBM | Yes | CapEx | Localization | IT - External | 34 | 0 | 34 | 2016-11-07 | 2016-11-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049828 | Yes | No | Argentina | Argentina | 04-Test | Martel; Kelly | SIT 2 - RTR - Break/Fix | RTR | FUN | SI | Onshore | Martel; Kelly | IBM | Yes | CapEx | Localization | IT - External | 99.25 | 0 | 99.25 | 2016-11-14 | 2016-12-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049829 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Martel; Kelly | UAT - Run Tests | RTR | FUN | SI | Onshore | Martel; Kelly | IBM | Yes | CapEx | Localization | IT - External | 44 | 0 | 44 | 2016-12-05 | 2016-12-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049830 | Yes | No | Argentina | Argentina | 06-Hypercare | Martel; Kelly | HC - Provide end User Support - RTR | RTR | FUN | SI | Onshore | Martel; Kelly | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2017-01-02 | 2017-01-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049831 | Yes | No | Argentina | Argentina | 06-Hypercare | Martel; Kelly | HC - Break/Fix - RTR | RTR | FUN | SI | Onshore | Martel; Kelly | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049832 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Martel; Kelly | Cut Over - Validate | RTR | FUN | SI | Onshore | Martel; Kelly | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-19 | 2016-12-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049833 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Martel; Kelly | Cut Over - Support | RTR | FUN | SI | Onshore | Martel; Kelly | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-19 | 2016-12-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049834 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Martel; Kelly | UAT - Break/Fix and document work around | RTR | FUN | SI | Onshore | Martel; Kelly | IBM | Yes | CapEx | Localization | IT - External | 39 | 0 | 39 | 2016-12-05 | 2016-12-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049835 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Martel; Kelly | Cut Over - Prepare | RTR | FUN | SI | Onshore | Martel; Kelly | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049836 | Yes | No | Argentina | Argentina | 04-Test | Davis; Sharlie | SIT 1 - Run Tests | LOG | FUN | SI | Onshore | Davis; Sharlie | IBM | Yes | CapEx | Localization | IT - External | 250.85 | 0 | 250.85 | 2016-09-06 | 2016-10-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049837 | Yes | No | Argentina | Argentina | 04-Test | Kim; Tae | LOG - SIT 2 - Manage Defects | OTC | FUN | SI | Onshore | Kim; Tae | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-24 | 2016-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049838 | Yes | No | Argentina | Argentina | 04-Test | Kim; Tae | LOG - SIT 2 - Break/Fix | OTC | FUN | SI | Onshore | Kim; Tae | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-24 | 2016-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049839 | Yes | No | Argentina | Argentina | 04-Test | Kim; Tae | OTC - SIT 2 - Manage Defects | OTC | FUN | SI | Onshore | Kim; Tae | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-24 | 2016-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049840 | Yes | No | Argentina | Argentina | 04-Test | Kim; Tae | OTC - SIT 2 - Break/Fix | OTC | FUN | SI | Onshore | Kim; Tae | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-24 | 2016-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049841 | Yes | No | Argentina | Argentina | 03-Design/Build | Kim; Tae | ARG KT visit | OTC | FUN | SI | Onshore | Kim; Tae | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-08-08 | 2016-08-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049842 | Yes | No | Argentina | Argentina | 04-Test | Adams; Andre | Work Instructions - Exercices DATA (technical writer + Dele) | CM | CM | SI | Onshore | Adams; Andre | IBM | Yes | OpEx | Localization | IT - External | 311 | 0 | 311 | 2016-10-24 | 2016-12-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049843 | Yes | No | Argentina | Argentina | 04-Test | Ganguly; Arunima | Work Instructions - Exercices DATA (technical writer + Dele) | CM | CM | SI | Offshore | Ganguly; Arunima | IBM | Yes | OpEx | Localization | IT - External | 234 | 0 | 234 | 2016-11-01 | 2016-12-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049844 | No | Yes | Argentina | Argentina |  | Morgan; Wilishia | 05-Release 1.3 | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | OpEx | Localization | IT - External | 72 | 0 | 72 | 2017-02-27 | 2017-03-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049845 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Morgan; Wilishia | Transition to Hypercare - LOG | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 45 | 0 | 45 | 2017-01-30 | 2017-02-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049846 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Morgan; Wilishia | Dry Run - Prepare | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-11-07 | 2016-11-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049847 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Morgan; Wilishia | Dry Run - Support | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-11-15 | 2016-11-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049848 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Morgan; Wilishia | Dry Run - Validate | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-11-07 | 2016-11-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049849 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Morgan; Wilishia | UAT - Break/Fix and document work around | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 17 | 0 | 17 | 2017-01-19 | 2017-01-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049850 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Morgan; Wilishia | Cut Over - Prepare | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049851 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Morgan; Wilishia | Cut Over - Support | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 186 | 0 | 186 | 2016-12-19 | 2017-01-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049852 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Morgan; Wilishia | Cut Over - Validate | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 44 | 0 | 44 | 2016-12-19 | 2017-01-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049853 | No | Yes | Argentina | Argentina | 06-Hypercare | Morgan; Wilishia | HC - Provide end User Support | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | OpEx | Localization | IT - External | 84 | 0 | 84 | 2017-02-20 | 2017-02-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049854 | No | Yes | Argentina | Argentina | 06-Hypercare | Morgan; Wilishia | HC - Break/Fix | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 126 | 0 | 126 | 2017-02-06 | 2017-02-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049855 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Morgan; Wilishia | UAT - Manage Defects | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049856 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Morgan; Wilishia | UAT - Run Tests | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049857 | No | Yes | Argentina | Argentina | 06-Hypercare | Morgan; Wilishia | Argentina Production Support-LOG | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | OpEx | Localization | IT - External | 208 | 0 | 208 | 2017-03-13 | 2017-04-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049858 | Yes | No | Argentina | Argentina | 04-Test | Ko; Mark-Kevin | Performance testing and refresh | TAI | TAI | SI | Offshore | Ko; Mark-Kevin | Accenture | Yes | CapEx | Localization | IT - External | 376 | 0 | 376 | 2016-10-17 | 2016-12-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049859 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Ko; Mark-Kevin | Performance testing write-off | TAI | TAI | SI | Offshore | Ko; Mark-Kevin | Accenture | Yes | CapEx | Localization | IT - External | 45 | 0 | 45 | 2016-12-12 | 2016-12-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049860 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Remane; Rajan | Transition to Hypercare - PTM | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2017-01-09 | 2017-01-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049861 | No | Yes | Argentina | Argentina | 06-Hypercare | Remane; Rajan | HC - Break/Fix - PTM | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 90 | 0 | 90 | 2017-02-13 | 2017-02-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049862 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Remane; Rajan | Dry Run - Support | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-11-14 | 2016-11-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049863 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Remane; Rajan | Cut Over - Support | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 135 | 0 | 135 | 2016-12-23 | 2017-01-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049864 | No | Yes | Argentina | Argentina | 06-Hypercare | Remane; Rajan | Argentina Production Support-PTM | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2017-03-06 | 2017-03-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049865 | Yes | No | Argentina | Argentina | 04-Test | Manoharan; Anandan | SIT 2 - PTP - Break/Fix | PTP | FUN | SI | Offshore | Manoharan; Anandan | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-24 | 2016-10-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049866 | Yes | No | Argentina | Argentina | 04-Test | Manoharan; Anandan | SIT 1 - Break/Fix | PTP | FUN | SI | Offshore | Manoharan; Anandan | IBM | Yes | CapEx | Localization | IT - External | 5 | 0 | 5 | 2016-09-12 | 2016-09-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049867 | Yes | No | Argentina | Argentina | 04-Test | Manoharan; Anandan | SIT 2 - Prep | PTP | FUN | SI | Offshore | Manoharan; Anandan | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-10-10 | 2016-10-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049868 | Yes | No | Argentina | Argentina | 06-Hypercare | Manoharan; Anandan | HC - Break/Fix | PTP | FUN | SI | Offshore | Manoharan; Anandan | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049869 | Yes | No | Argentina | Argentina | 06-Hypercare | Manoharan; Anandan | HC - Provide end User Support | PTP | FUN | SI | Offshore | Manoharan; Anandan | IBM | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049870 | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Manoharan; Anandan | UAT - Break/Fix and document work around | PTP | FUN | SI | Offshore | Manoharan; Anandan | IBM | Yes | CapEx | Localization | IT - External | 0 | 0 | 0 | 2016-12-05 | 2016-12-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049871 | No | Yes | Argentina | Argentina | 01-Preparation | Doucet; Caroline | Argentina Project - Sharepoint Access - | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | CapEx | Localization | IT - Internal | 0 | 0 | 0 | 2015-12-01 | 2015-12-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049872 | No | Yes | Argentina | Argentina | 06-Hypercare | Doucet; Caroline | Deliver Training to End Users | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | OpEx | Localization | IT - Internal | 0 | 0 | 0 | 2017-02-06 | 2017-02-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049873 | No | Yes | Argentina | Argentina | 06-Hypercare | Doucet; Caroline | Argentina Production Support-CM | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | OpEx | Localization | IT - Internal | 0 | 0 | 0 | 2017-03-20 | 2017-03-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049874 | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Doucet; Caroline | Deliver Training to End Users | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | OpEx | Localization | IT - Internal | 0 | 0 | 0 | 2016-12-19 | 2016-12-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049875 | No | Yes | Argentina | Argentina | 04-Test | Doucet; Caroline | Training Materials - Concept slides & Exercices book | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | OpEx | Localization | IT - Internal | 956 | 0 | 956 | 2016-09-06 | 2017-02-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049876 | No | Yes | Argentina | Argentina | 03-Design/Build | Doucet; Caroline | Identify materials needing localization | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | OpEx | Localization | IT - Internal | 16 | 0 | 16 | 2016-07-28 | 2016-07-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049877 | No | Yes | Argentina | Argentina | 03-Design/Build | Baque; Jim | Composite Role Build | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Localization | IT - External | 24 | 0 | 24 | 2016-10-14 | 2016-10-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049878 | No | Yes | Argentina | Argentina | 03-Design/Build | Baque; Jim | Derived Role Build | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Localization | IT - External | 7 | 0 | 7 | 2016-10-18 | 2016-10-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049879 | No | Yes | Argentina | Argentina | 06-Hypercare | Baque; Jim | Argentina Production Support-SEC | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | OpEx | Localization | IT - External | 0 | 0 | 0 | 2017-03-06 | 2017-03-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0