## Weekly Actual hrs at 17-09-2017 (hidden)
Unique No | Generic | Inactive | Time Capture Required: | Projet | Sub-Project | Phase | Name | Stream | Sub-stream | Saputo/SI | Sourcing | Resource | Source_Organization | Total | Capex/Opex | Global / Localization | Resource Category | Actual Work Hrs | Remaining Work Hrs | Work Hrs | Start | Finish | User Logon Account: | PP (Power Point report:) | _SAP_DMS_(Resource) | _Deliverable | _Task_Status | _POP_Start | _POP_Finish | _Deployment | _POP_Milestone | _POP_With code | _Var_POP_Start1 | _Var_POP_Finish1 | 2016-12-26 | 2017-01-02 | 2017-01-09 | 2017-01-16 | 2017-01-23 | 2017-01-30 | 2017-02-06 | 2017-02-13 | 2017-02-20 | 2017-02-27 | 2017-03-06 | 2017-03-13 | 2017-03-20 | 2017-03-27 | 2017-04-03 | 2017-04-10 | 2017-04-17 | 2017-04-24 | 2017-05-01 | 2017-05-08 | 2017-05-15 | 2017-05-22 | 2017-05-29 | 2017-06-05 | 2017-06-12 | 2017-06-19 | 2017-06-26 | 2017-07-03 | 2017-07-10 | 2017-07-17 | 2017-07-24 | 2017-07-31 | 2017-08-07 | 2017-08-14 | 2017-08-21 | 2017-08-28 | 2017-09-04 | 2017-09-11 | 2017-09-18
1049107 | No | No | No | Argentina | Argentina | 03-Design/Build | Complete Stakeholder Assessment in preparation for 1st communication cascade (2 VP's) | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049108 | No | No | No | Argentina | Argentina | 03-Design/Build | Validate deck for CM training for managers | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-06-15 | 2016-06-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049109 | No | No | No | Argentina | Argentina | 03-Design/Build | Collect Employee List to Be Role Mapped | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049110 | No | No | No | Argentina | Argentina | 03-Design/Build | Prepare Role Mapping Onboarding Deck | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049111 | No | No | No | Argentina | Argentina | 03-Design/Build | Validate Kick-Off Deck | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-09 | 2016-05-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049112 | No | No | No | Argentina | Argentina | 03-Design/Build | Validate Deck on Role Catalogue Change Control Process | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-09 | 2016-05-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049113 | No | No | No | Argentina | Argentina | 03-Design/Build | Align Functional team on Roles Catalog Change control process | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-06-10 | 2016-06-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049114 | No | No | No | Argentina | Argentina | 03-Design/Build | Validate RM Status Report | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049115 | No | No | No | Argentina | Argentina | 03-Design/Build | Develop RMS Training for the Business | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-16 | 2016-05-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049116 | No | No | No | Argentina | Argentina | 03-Design/Build | Review first draft of VR plan with Fernando and Determine approach to cascade | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-06-03 | 2016-06-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049117 | No | No | No | Argentina | Argentina | 03-Design/Build | Validate presentation | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049118 | No | No | No | Argentina | Argentina | 03-Design/Build | Validate Key Users On boarding deck | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049119 | No | No | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-CM | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049120 | No | No | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049121 | No | Yes | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PTP | FUN | SI | Onshore | Vasudevan; Ramesh | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049122 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049123 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - PTM - Break/Fix | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 59h | 0h | 59h | 2016-11-14 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049124 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049125 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - Prep | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 72h | 0h | 72h | 2016-10-17 | 2016-11-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049126 | No | Yes | No | Argentina | Argentina | 02-Analyze | PTM - Identfy Changes in GD for Localization ARG | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-02-29 | 2016-02-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049127 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - PTM | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 52h | 0h | 52h | 2016-05-24 | 2016-08-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049128 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - PTM | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2016-05-16 | 2016-06-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049129 | No | Yes | No | Argentina | Argentina | 10-PCR | CR-Defect 6666 and Production Incident for currency for AR03 | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | OpEx | Localization | IT - External | 60h | 0h | 60h | 2017-05-12 | 2017-06-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 10 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049130 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | OpEx | Localization | IT - External | 58h | 0h | 58h | 2016-10-05 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049131 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Support | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-03 | 2016-10-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049132 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Solution Design Document (SDD) | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 14h | 0h | 14h | 2016-08-17 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049133 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 48h | 0h | 48h | 2016-09-12 | 2016-09-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049134 | No | Yes | No | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2016-10-31 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049135 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Functional Specification (FSD) | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2016-08-11 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049136 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - PTM | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 35h | 0h | 35h | 2017-01-30 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049137 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - PTM - Run Tests | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 63h | 0h | 63h | 2016-11-07 | 2016-11-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049138 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2016-11-14 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049139 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-12-12 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049140 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2016-11-21 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049141 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 76h | 0h | 76h | 2016-12-12 | 2017-01-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 14 | 19 | 20 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049142 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049143 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 57h | 0h | 57h | 2016-12-19 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049144 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 106h | 0h | 106h | 2016-12-19 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 20 | 0 | 36 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049145 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | OpEx | Localization | IT - External | 80h | 0h | 80h | 2017-02-06 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049146 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2017-02-06 | 2017-02-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049147 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 112h | 0h | 112h | 2017-02-13 | 2017-03-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 35 | 44 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049148 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049149 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049150 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 121h | 0h | 121h | 2017-02-20 | 2017-04-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 9 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049151 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Prepare | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | OpEx | Localization | IT - External | 42h | 0h | 42h | 2016-08-22 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049152 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 324.5h | 0h | 324.5h | 2016-09-06 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049153 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Support | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | OpEx | Localization | IT - External | 5h | 0h | 5h | 2016-08-29 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049154 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | OpEx | Localization | IT - External | 2h | 0h | 2h | 2016-10-17 | 2016-10-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049155 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - Prep | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049156 | No | No | Yes | Argentina | Argentina | 04-Test | LOG - SIT 2 - Run Tests | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2016-11-05 | 2016-11-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049157 | No | No | Yes | Argentina | Argentina | 04-Test | LOG - SIT 2 - Manage Defects | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-11-21 | 2016-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049158 | No | No | Yes | Argentina | Argentina | 04-Test | LOG - SIT 2 - Break/Fix | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 301h | 0h | 301h | 2016-10-31 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049159 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049160 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2016-12-07 | 2016-12-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049161 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049162 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 408h | 0h | 408h | 2016-12-05 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 16 | 50 | 51 | 49 | 70 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049163 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049164 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 21h | 0h | 21h | 2016-12-20 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049165 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049166 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | OpEx | Localization | IT - External | 116h | 0h | 116h | 2017-02-06 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049167 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-03 | 2016-09-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049168 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-07 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049169 | No | No | Yes | Argentina | Argentina | 01-Preparation | LOG Prepare Arg - GD integration | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2016-02-24 | 2016-02-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049170 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Manage Defects | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-10-11 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049171 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2016-10-15 | 2016-10-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049172 | No | No | Yes | Argentina | Argentina | 02-Analyze | LOG - Identify changes in GD for Localization ARG | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 173h | 0h | 173h | 2016-02-29 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049173 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-28 | 2016-12-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049174 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - LOG | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049175 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - LOG | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049176 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-LOG | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | OpEx | Localization | IT - External | 82h | 0h | 82h | 2017-03-06 | 2017-06-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 6 | 3 | 10 | 9 | 10 | 8 | 6 | 7.5 | 7.5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049177 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - LOG | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049178 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - LOG | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-05-30 | 2016-06-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049179 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | OpEx | Localization | IT - External | 16h | 0h | 16h | 2016-10-03 | 2016-10-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049180 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Support | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-15 | 2016-07-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049181 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 124h | 0h | 124h | 2017-01-23 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049182 | No | No | Yes | Argentina | Argentina | 02-Analyze | LOG - Identify changes in GD for Localization ARG | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 132h | 0h | 132h | 2016-03-07 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049183 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049184 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Manage Defects | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-06 | 2016-09-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049185 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | OpEx | Localization | IT - External | 87h | 0h | 87h | 2016-10-07 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049186 | No | No | Yes | Argentina | Argentina | 04-Test | LOG - SIT 2 - Manage Defects | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049187 | No | No | Yes | Argentina | Argentina | 01-Preparation | LOG Prepare Arg - GD integration | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-02-22 | 2016-02-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049188 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | OpEx | Localization | IT - External | 116h | 0h | 116h | 2017-02-06 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049189 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049190 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049191 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049192 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049193 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 326h | 0h | 326h | 2016-12-05 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 31 | 53 | 53 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049194 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-15 | 2016-11-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049195 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 60h | 0h | 60h | 2016-11-07 | 2016-11-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049196 | No | No | Yes | Argentina | Argentina | 04-Test | LOG - SIT 2 - Break/Fix | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 94h | 0h | 94h | 2016-10-31 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049197 | No | No | Yes | Argentina | Argentina | 04-Test | LOG - SIT 2 - Run Tests | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 105h | 0h | 105h | 2016-11-14 | 2016-11-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049198 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - Prep | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049199 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-17 | 2016-10-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049200 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 275h | 0h | 275h | 2016-09-12 | 2016-10-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049201 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG KT visit | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2016-08-15 | 2016-08-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049202 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Prepare | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-11 | 2016-07-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049203 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 56h | 0h | 56h | 2017-02-06 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049204 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049205 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049206 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Redesing - Escalation | RTR | FUN | SI | Onshore | Roloff; Patrick | SAP | Yes | OpEx | Localization | IT - External | 0h | 42h | 42h | 2017-09-01 | 2017-09-11 | Yes |  | DMS |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049207 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-SEC | SEC | SEC | SI | Offshore | Aragon; Marvin | Accenture | Yes | OpEx | Localization | IT - External | 99h | 0h | 99h | 2017-03-06 | 2017-07-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049208 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-LOG | LOG | FUN | SI | Onshore | SerranoMartinez; Efren | IBM | Yes | OpEx | Localization | IT - External | 688h | 0h | 688h | 2017-03-06 | 2017-07-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 45 | 44 | 44 | 45 | 45 | 45 | 46 | 54 | 51 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049209 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-OTC | OTC | FUN | Saputo | Onshore | Barreto; Bruno | Saputo | Yes | OpEx | Localization | IT - Internal | 123.2h | 0h | 123.2h | 2017-03-06 | 2017-07-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 23.2 | 16 | 0 | 0 | 18.37 | 29.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049210 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | SI | Onshore | Thorat; Yogini | IBM | Yes | OpEx | Localization | IT - External | 292h | 0h | 292h | 2017-03-13 | 2017-06-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 17.5 | 22.5 | 22.5 | 22.5 | 22.5 | 13.5 | 0 | 22.5 | 22.5 | 18 | 22.5 | 22.5 | 22.5 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049211 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | Saputo | Onshore | Gomare; Shankar | Saputo | Yes | OpEx | Localization | IT - Internal | 6h | 0h | 6h | 2017-05-29 | 2017-06-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049212 | No | No | Yes | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | Saputo | Onshore | Gomare; Shankar | Saputo | Yes | OpEx | Global | IT - Internal | 8h | 0h | 8h | 2017-05-23 | 2017-05-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049213 | No | No | Yes | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Gupta; Debapriya | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049214 | No | No | Yes | Argentina | Argentina | 06-Hypercare | ARG tax redesign- DEV | DEV | DEV | SI | Offshore | Gupta; Debapriya | IBM | Yes | OpEx | Localization | IT - External | 85h | 35h | 120h | 2017-08-02 | 2017-09-14 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 9 | 10 | 21 | 20 | 5 | 0 | 0
1049215 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | Gupta; Debapriya | IBM | Yes | OpEx | Localization | IT - External | 128.5h | 0h | 128.5h | 2017-02-27 | 2017-07-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 44 | 29.5 | 3 | 7 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049216 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PMO | OTC | FUN | SI | Offshore | Salunke; Sachin | IBM | Yes | OpEx | Localization | IT - External | 216h | 0h | 216h | 2017-03-20 | 2017-05-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 18 | 22.5 | 22.5 | 22.5 | 22.5 | 18 | 22.5 | 22.5 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049217 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-OTC | OTC | FUN | SI | Offshore | Salunke; Sachin | IBM | Yes | OpEx | Localization | IT - External | 324h | 0h | 324h | 2017-03-13 | 2017-07-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 18 | 22.5 | 22.5 | 22.5 | 22.5 | 18 | 22.5 | 22.5 | 22.5 | 22.5 | 22.5 | 22.5 | 0 | 18 | 0 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049218 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - PTM - Run Tests | PTP | FUN | SI | Onshore | Moore; Laura | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-17 | 2016-10-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049219 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - PTM - Break/Fix | PTP | FUN | SI | Onshore | Moore; Laura | IBM | Yes | CapEx | Localization | IT - External | 159h | 0h | 159h | 2016-11-14 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049220 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTP | FUN | SI | Onshore | Moore; Laura | IBM | Yes | CapEx | Localization | IT - External | 142h | 0h | 142h | 2016-12-28 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 27 | 27 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049221 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTP | FUN | SI | Onshore | Moore; Laura | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049222 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTP | FUN | SI | Onshore | Moore; Laura | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049223 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - PTP - Break/Fix | PTP | FUN | SI | Onshore | Moore; Laura | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2016-11-18 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049224 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - PTP - Run Tests | PTP | FUN | SI | Onshore | Moore; Laura | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049225 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 2h | 0h | 2h | 2016-08-15 | 2016-10-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049226 | No | No | Yes | Argentina | Argentina | 04-Test | Project Management and Planning for SEC | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 225h | 0h | 225h | 2016-09-26 | 2016-11-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049227 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT Defect Resolution | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 217h | 0h | 217h | 2016-12-19 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 32 | 0 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049228 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Composite Role Design | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-09-19 | 2016-09-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049229 | No | No | Yes | Argentina | Argentina | 03-Design/Build | SoD Analysis and Remediation | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 8h | 0h | 8h | 2016-09-30 | 2016-10-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049230 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | GRC AC - Cutover planning and Exucution | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 55h | 0h | 55h | 2016-10-19 | 2016-12-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049231 | No | No | Yes | Argentina | Argentina | 06-Hypercare | GRC AC - Hypercare | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 40h | 0h | 40h | 2017-02-13 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049232 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-SEC | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | OpEx | Localization | IT - Internal | 104h | 0h | 104h | 2017-05-29 | 2017-06-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049233 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Management (Cutover/Go-live) | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 87h | 0h | 87h | 2016-11-14 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049234 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Management (Hypercare) | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 58h | 0h | 58h | 2017-02-06 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049235 | No | No | Yes | Argentina | Argentina | 04-Test | SoD Analysis and Remediation | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 23h | 0h | 23h | 2016-11-07 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049236 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | SoD Analysis and Remediation | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 32h | 0h | 32h | 2016-12-05 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049237 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Security Design Workshops | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 46h | 0h | 46h | 2016-09-13 | 2016-10-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049238 | No | No | Yes | Argentina | Argentina | 04-Test | Security Role FUT | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-09-19 | 2016-09-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049239 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 Defect Resolution | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-10-22 | 2016-10-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049240 | No | No | Yes | Argentina | Argentina | 04-Test | GRC AC - SIT Execution | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 109h | 0h | 109h | 2016-10-24 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049241 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cutover Planning and Execution | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 82h | 0h | 82h | 2016-10-19 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049242 | No | No | Yes | Argentina | Argentina | 03-Design/Build | SAP GRC AC - Design | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 25h | 0h | 25h | 2016-09-13 | 2016-10-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049243 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 129h | 0h | 129h | 2016-09-06 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049244 | No | No | Yes | Argentina | Argentina | 04-Test | LOG - SIT 2 - Break/Fix | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 149h | 0h | 149h | 2016-10-24 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049245 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Manage Defects | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 29h | 0h | 29h | 2016-12-05 | 2017-01-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049246 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049247 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 111h | 0h | 111h | 2016-12-05 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 21 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049248 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 150h | 0h | 150h | 2016-12-19 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049249 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 10h | 0h | 10h | 2017-01-30 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049250 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | OpEx | Localization | IT - Internal | 23h | 0h | 23h | 2016-09-19 | 2016-09-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049251 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 55h | 0h | 55h | 2016-10-11 | 2016-10-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049252 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-LOG | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | OpEx | Localization | IT - Internal | 354h | 0h | 354h | 2017-03-07 | 2017-06-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 40 | 35 | 23 | 12 | 18 | 40 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049253 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 25h | 0h | 25h | 2016-12-06 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049254 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | OpEx | Localization | IT - Internal | 244h | 0h | 244h | 2016-12-01 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 80 | 52 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049255 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-09-19 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049256 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Hypercare Support - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049257 | No | No | Yes | Argentina | Argentina | 04-Test | Test - MDSS Project Management - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Localization | IT - External | 72h | 0h | 72h | 2016-10-24 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049258 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | MDSS Project Management (Cutover/Go-live) - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Localization | IT - External | 156h | 0h | 156h | 2016-12-12 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 16 | 40 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049259 | No | No | Yes | Argentina | Argentina | 06-Hypercare | MDSS Project Management (Hypercare) - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049260 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 Closure - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-11 | 2016-09-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049261 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cutover Closure Memo - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-20 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049262 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 0 Load in DEV - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2016-05-30 | 2016-06-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049263 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - WP Obtain the Data Verification Signoff sheet - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-06-13 | 2016-06-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049264 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 1 Load in QA - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Localization | IT - External | 152h | 0h | 152h | 2016-06-27 | 2016-07-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049265 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - MDG 333 Mock Closure Memo - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Localization | IT - External | 296h | 0h | 296h | 2016-07-25 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049266 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 Closure Memo - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2016-10-31 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049267 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 87h | 0h | 87h | 2016-09-12 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049268 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG KT visit | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049269 | No | No | Yes | Argentina | Argentina | 04-Test | OTC - SIT 2 - Run Tests | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049270 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 104h | 0h | 104h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 22 | 24 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049271 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - OTC | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 102h | 0h | 102h | 2017-01-23 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049272 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2016-12-27 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049273 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 225h | 0h | 225h | 2016-12-05 | 2017-01-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 44 | 44 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049274 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049275 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049276 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-28 | 2016-11-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049277 | No | No | Yes | Argentina | Argentina | 04-Test | OTC - SIT 2 - Break/Fix | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-12-19 | 2016-12-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049278 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2016-10-10 | 2016-10-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049279 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - RTR | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049280 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - RTR | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049281 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049282 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049283 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049284 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049285 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Run Tests | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 123h | 0h | 123h | 2016-10-31 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049286 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Manage Defects | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049287 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Break/Fix | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-11-14 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049288 | No | Yes | No | Argentina | Argentina | 04-Test | Updates concepts decks | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049289 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049290 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049291 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049292 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Validate | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049293 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Prep | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 48h | 0h | 48h | 2016-10-13 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049294 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Unit testing Configuration Documentation | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2016-09-06 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049295 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Configuration | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-18 | 2016-07-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049296 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Solution Design Document (SDD) | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-08-15 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049297 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | RTR | FUN | SI | Onshore | Nguyen; Tri | IBM | Yes | CapEx | Localization | IT - External | 129h | 0h | 129h | 2016-09-12 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049298 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049299 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Prep | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2016-10-24 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049300 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Validate | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049301 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049302 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-01-23 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049303 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2016-12-12 | 2016-12-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049304 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-12-05 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049305 | No | Yes | No | Argentina | Argentina | 04-Test | Updates concepts decks | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-11-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049306 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Break/Fix | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 31h | 0h | 31h | 2016-10-31 | 2016-12-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049307 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Manage Defects | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049308 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Run Tests | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-11-07 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049309 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049310 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 84h | 0h | 84h | 2017-01-09 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 44 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049311 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2016-12-12 | 2016-12-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049312 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-01-16 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049313 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - RTR | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | OpEx | Localization | IT - External | 106h | 0h | 106h | 2017-02-27 | 2017-03-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049314 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049315 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - RTR | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 132h | 0h | 132h | 2017-02-06 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049316 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | OTC | FUN | SI | Onshore | Kothari; Sanjay | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2016-09-19 | 2016-09-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049317 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | OTC | FUN | SI | Onshore | Kothari; Sanjay | IBM | Yes | CapEx | Localization | IT - External | 172h | 0h | 172h | 2016-09-12 | 2016-12-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049318 | No | Yes | No | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | OTC | FUN | SI | Onshore | Kothari; Sanjay | IBM | Yes | CapEx | Localization | IT - External | 42h | 0h | 42h | 2016-09-06 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049319 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG KT visit | OTC | FUN | SI | Onshore | Kothari; Sanjay | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049320 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Support | LOG | FUN | SI | Onshore | Bill; Grey | IBM | Yes | OpEx | Localization | IT - External | 40h | 0h | 40h | 2016-10-07 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049321 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Support | LOG | FUN | SI | Onshore | Bill; Grey | IBM | Yes | OpEx | Localization | IT - External | 1.5h | 0h | 1.5h | 2016-08-15 | 2016-08-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049322 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | LOG | FUN | SI | Onshore | Bill; Grey | IBM | Yes | CapEx | Localization | IT - External | 193h | 0h | 193h | 2016-09-06 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049323 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | PTP | FUN | SI | Onshore | Power; Kat | IBM | Yes | CapEx | Localization | IT - External | 66h | 0h | 66h | 2016-11-28 | 2016-12-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049324 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | PTP | FUN | SI | Onshore | Power; Kat | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-11-14 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049325 | No | Yes | No | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTP | FUN | SI | Onshore | Power; Kat | IBM | Yes | CapEx | Localization | IT - External | 144h | 0h | 144h | 2016-09-06 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049326 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTP | FUN | SI | Onshore | Power; Kat | IBM | Yes | CapEx | Localization | IT - External | 16.5h | 0h | 16.5h | 2016-12-19 | 2016-12-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049327 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Validate | PTP | FUN | SI | Onshore | Power; Kat | IBM | Yes | OpEx | Localization | IT - External | 1h | 0h | 1h | 2016-11-07 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049328 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Support | PTP | FUN | SI | Onshore | Power; Kat | IBM | Yes | OpEx | Localization | IT - External | 61.5h | 0h | 61.5h | 2016-10-18 | 2016-11-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049329 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049330 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - RTR | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049331 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - RTR | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049332 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2016-12-13 | 2016-12-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049333 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2016-12-19 | 2017-01-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049334 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2016-12-19 | 2016-12-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049335 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Break/Fix | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2016-11-08 | 2016-12-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049336 | No | Yes | No | Argentina | Argentina | 04-Test | Updates concepts decks | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | OpEx | Localization | IT - External | 10h | 0h | 10h | 2016-10-11 | 2016-11-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049337 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2016-12-12 | 2017-01-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049338 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2016-12-19 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049339 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2016-10-05 | 2016-10-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049340 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 22h | 0h | 22h | 2016-10-03 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049341 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Prep | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 42h | 0h | 42h | 2016-10-11 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049342 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049343 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | PTP | FUN | SI | Onshore | Singh; Pankaj | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049344 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - PTP - Break/Fix | PTP | FUN | SI | Onshore | Singh; Pankaj | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-11-28 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049345 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | PTP | FUN | SI | Onshore | Singh; Pankaj | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049346 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | PTP | FUN | SI | Onshore | Singh; Pankaj | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049347 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | PTP | FUN | SI | Onshore | Singh; Pankaj | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049348 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTP | FUN | SI | Onshore | Singh; Pankaj | Accenture | Yes | CapEx | Localization | IT - External | 152h | 0h | 152h | 2016-12-05 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049349 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTP | FUN | SI | Onshore | Singh; Pankaj | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-12-19 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049350 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTP | FUN | SI | Onshore | Singh; Pankaj | Accenture | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2016-12-29 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049351 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | PTP | FUN | SI | Onshore | Singh; Pankaj | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049352 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | PTP | FUN | SI | Onshore | Singh; Pankaj | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049353 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | LOG | FUN | SI | Onshore | Mauro; JuanPablo | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2017-01-16 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049354 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | LOG | FUN | SI | Onshore | Mauro; JuanPablo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049355 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | LOG | FUN | SI | Onshore | Mauro; JuanPablo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049356 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | SI | Onshore | Mauro; JuanPablo | IBM | Yes | OpEx | Localization | IT - External | 227h | 0h | 227h | 2017-02-06 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 49 | 50 | 29 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049357 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | LOG | FUN | SI | Onshore | Mauro; JuanPablo | IBM | Yes | CapEx | Localization | IT - External | 140h | 0h | 140h | 2016-12-05 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049358 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | LOG | FUN | SI | Onshore | Mauro; JuanPablo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049359 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | SI | Onshore | Mauro; JuanPablo | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-01-30 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049360 | No | Yes | No | Argentina | Argentina | 04-Test | LOG - SIT 2 - Break/Fix | LOG | FUN | SI | Onshore | Mauro; JuanPablo | IBM | Yes | CapEx | Localization | IT - External | 41h | 0h | 41h | 2016-11-29 | 2016-12-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049361 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-LOG | LOG | FUN | SI | Onshore | Mauro; JuanPablo | IBM | Yes | OpEx | Localization | IT - External | 80h | 0h | 80h | 2017-03-13 | 2017-03-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049362 | No | Yes | No | Argentina | Argentina | 04-Test | LOG - SIT 2 - Break/Fix | LOG | FUN | SI | Onshore | Sniezyk; Sebastian | IBM | Yes | CapEx | Localization | IT - External | 75h | 0h | 75h | 2016-11-21 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049363 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | LOG | FUN | SI | Onshore | Sniezyk; Sebastian | IBM | Yes | CapEx | Localization | IT - External | 181h | 0h | 181h | 2016-12-05 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049364 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | LOG | FUN | SI | Onshore | Sniezyk; Sebastian | IBM | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2016-12-27 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 36 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049365 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | LOG | FUN | SI | Onshore | Sniezyk; Sebastian | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049366 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | SI | Onshore | Sniezyk; Sebastian | IBM | Yes | OpEx | Localization | IT - External | 187h | 0h | 187h | 2017-02-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 56.3 | 47.7 | 27 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049367 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | SI | Onshore | Sniezyk; Sebastian | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-01-30 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049368 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | LOG | FUN | SI | Onshore | Sniezyk; Sebastian | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2017-01-16 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049369 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | LOG | FUN | SI | Onshore | Sniezyk; Sebastian | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049370 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-LOG | LOG | FUN | SI | Onshore | Sniezyk; Sebastian | IBM | Yes | OpEx | Localization | IT - External | 799h | 0h | 799h | 2017-03-06 | 2017-07-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 44 | 43 | 0 | 44 | 31 | 44 | 44 | 41 | 44 | 44 | 42 | 44 | 44 | 44 | 42 | 40 | 40 | 30 | 29 | 15 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049371 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - OTC | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 40h | 0h | 40h | 2017-01-30 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049372 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 80h | 0h | 80h | 2016-12-05 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049373 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 231.98h | 0h | 231.98h | 2016-12-19 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 32 | 39.98 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049374 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | OpEx | Localization | IT - Internal | 80h | 0h | 80h | 2017-02-06 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049375 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-OTC | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | OpEx | Localization | IT - Internal | 75h | 0h | 75h | 2017-03-06 | 2017-05-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 3 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049376 | No | No | Yes | Argentina | Argentina | 10-PCR | Argentina new cheese line-OTC | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-05-03 | 2017-05-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049377 | No | Yes | No | Argentina | Argentina | 03-Design/Build | GRC AC - Build & UT | SEC | SEC | SI |  | Igwenazor; Stella | Other | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-07 | 2016-09-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049378 | No | Yes | No | Argentina | Argentina | 04-Test | FUT Support Roles | SEC | SEC | SI |  | Igwenazor; Stella | Other | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-10-31 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049379 | No | Yes | No | Argentina | Argentina | 04-Test | GRC AC - SIT Execution | SEC | SEC | SI |  | Igwenazor; Stella | Other | Yes | CapEx | Localization | IT - External | 74h | 0h | 74h | 2016-10-31 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049380 | No | Yes | No | Argentina | Argentina | 04-Test | PCR - 209 - HR Administrator Derived role for Canada - Security | SEC | SEC | SI |  | Igwenazor; Stella | Other | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-18 | 2016-12-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049381 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 Defect Resolution | SEC | SEC | SI |  | Igwenazor; Stella | Other | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-22 | 2016-10-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049382 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Hypercare/support | SEC | SEC | SI |  | Igwenazor; Stella | Other | Yes | OpEx | Localization | IT - External | 280h | 0h | 280h | 2017-02-06 | 2017-03-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 55 | 46 | 40 | 43 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049383 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT Defect Resolution | SEC | SEC | SI |  | Igwenazor; Stella | Other | Yes | CapEx | Localization | IT - External | 309h | 0h | 309h | 2016-12-05 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 3 | 29 | 40 | 40 | 40 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049384 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | GRC AC - Cutover planning and Exucution | SEC | SEC | SI |  | Igwenazor; Stella | Other | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-18 | 2016-10-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049385 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Hypercare/support | SEC | SEC | SI | Onshore | Pal; Gaurav | Accenture | Yes | OpEx | Localization | IT - External | 163h | 0h | 163h | 2017-02-13 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 35 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049386 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - CG | SEC | SEC | SI | Onshore | Pal; Gaurav | Accenture | Yes | CapEx | Localization | IT - External | 56h | 0h | 56h | 2017-01-23 | 2017-01-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049387 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Support Hypercare - SEC | SEC | SEC | SI | Onshore | Pal; Gaurav | Accenture | Yes | CapEx | Localization | IT - External | 97h | 0h | 97h | 2017-02-01 | 2017-02-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049388 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | SI | Onshore | Iozzo; Tony | IBM | Yes | CapEx | Localization | IT - External | 81h | 0h | 81h | 2017-01-23 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049389 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | SI | Onshore | Iozzo; Tony | IBM | Yes | OpEx | Localization | IT - External | 114h | 0h | 114h | 2017-02-06 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 9 | 28 | 23 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049390 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | LOG | FUN | SI | Onshore | Iozzo; Tony | IBM | Yes | CapEx | Localization | IT - External | 127h | 0h | 127h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 39 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049391 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PMO | PMO | PMO | SI | Onshore | DeBonis; Claudia | IBM | Yes | OpEx | Localization | IT - External | 49h | 0h | 49h | 2017-03-06 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049392 | No | Yes | No | Argentina | Argentina |  | Perform project Planning and Control | PMO | PMO | SI | Onshore | DeBonis; Claudia | IBM | Yes | CapEx | Localization | IT - External | 981h | 0h | 981h | 2016-09-26 | 2017-03-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 44 | 44 | 44 | 44 | 44 | 44 | 60 | 64 | 84 | 60 | 0 | 44 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049393 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049394 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - Manage Defects | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 51h | 0h | 51h | 2016-10-24 | 2016-11-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049395 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTP - Break/Fix | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 212h | 0h | 212h | 2016-10-26 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049396 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-03 | 2016-10-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049397 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 76h | 0h | 76h | 2017-01-23 | 2017-02-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049398 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-06 | 2016-09-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049399 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-18 | 2016-10-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049400 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049401 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049402 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Manage Defects | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-12-07 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049403 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 155h | 0h | 155h | 2016-12-05 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 26 | 44 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049404 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049405 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | OpEx | Localization | IT - External | 88h | 0h | 88h | 2017-02-06 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049406 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049407 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-02-06 | 2017-02-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049408 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - Prep | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 78h | 0h | 78h | 2016-10-11 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049409 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 68h | 0h | 68h | 2016-09-06 | 2016-11-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049410 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 204h | 0h | 204h | 2016-09-12 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049411 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049412 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049413 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049414 | No | Yes | No | Argentina | Argentina | 04-Test | Work Instructions - Exercices DATA (technical writer + Dele) | CM | CM | SI | Offshore | Das; Biplab | IBM | Yes | OpEx | Localization | IT - External | 171h | 0h | 171h | 2016-09-19 | 2016-10-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049415 | No | Yes | No | Argentina | Argentina | 04-Test | Work Instructions - Exercices DATA (technical writer + Dele) | CM | CM | SI | Onshore | Sehgal; Arjun | IBM | Yes | OpEx | Localization | IT - External | 622h | 0h | 622h | 2016-10-03 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 27 | 27 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049416 | No | Yes | No | Argentina | Argentina | 04-Test | Manage SIT1 Prep (data, transports) | CM | CM | SI | Onshore | Sehgal; Arjun | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-29 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049417 | No | Yes | No | Argentina | Argentina | 04-Test | Manage SIT1 Execution | CM | CM | SI | Onshore | Sehgal; Arjun | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-19 | 2016-09-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049418 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-TAI | TAI | TAI | SI | Offshore | Nunez; Lawrence | Accenture | Yes | OpEx | Localization | IT - External | 710.5h | 0h | 710.5h | 2017-03-06 | 2017-07-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 45 | 36 | 36 | 36 | 27 | 45 | 45 | 27 | 45 | 45 | 45 | 18 | 45 | 45 | 45 | 45 | 18 | 26.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049419 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Support Hypercare | TAI | TAI | SI | Offshore | Nunez; Lawrence | Accenture | Yes | CapEx | Localization | IT - External | 162h | 0h | 162h | 2017-02-08 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049420 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover Steps | TAI | TAI | SI | Offshore | Nunez; Lawrence | Accenture | Yes | CapEx | Localization | IT - External | 252h | 0h | 252h | 2016-12-19 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 27 | 45 | 22.5 | 22.5 | 36 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049421 | No | Yes | No | Argentina | Argentina | 04-Test | Communication plan execution and monitoring | CM | CM | SI |  | Van-Kessel; Brian | Other | Yes | OpEx | Localization | IT - External | 543.5h | 0h | 543.5h | 2016-09-06 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049422 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Value Realization Monitoring | CM | CM | SI |  | Van-Kessel; Brian | Other | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049423 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Communication plan execution and monitoring | CM | CM | SI |  | Van-Kessel; Brian | Other | Yes | OpEx | Localization | IT - External | 323h | 0h | 323h | 2016-12-12 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 24 | 24 | 40 | 40 | 34 | 40 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049424 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Communication plan execution and monitoring | CM | CM | SI |  | Van-Kessel; Brian | Other | Yes | OpEx | Localization | IT - External | 134.5h | 0h | 134.5h | 2017-02-13 | 2017-03-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 34.5 | 0 | 38 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049425 | No | Yes | No | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | SI | Onshore | Mierski; Pawel | SAP | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2016-09-12 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049426 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | RTR | FUN | Saputo | Onshore | Valin; Eric | Saputo | Yes | CapEx | Localization | IT - Internal | 16h | 0h | 16h | 2016-12-19 | 2017-02-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049427 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - RTR | RTR | FUN | Saputo | Onshore | Valin; Eric | Saputo | Yes | OpEx | Localization | IT - Internal | 93h | 0h | 93h | 2017-01-02 | 2017-03-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 40 | 5 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049428 | No | No | Yes | Argentina | Argentina | 10-PCR | Argentina new cheese line-RTR | RTR | FUN | Saputo | Onshore | Valin; Eric | Saputo | Yes | CapEx | Localization | IT - Internal | 2h | 0h | 2h | 2017-04-25 | 2017-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049429 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-RTR | RTR | FUN | Saputo | Onshore | Valin; Eric | Saputo | Yes | OpEx | Localization | IT - Internal | 249h | 0h | 249h | 2017-03-22 | 2017-07-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 10 | 10 | 24 | 0 | 0 | 32 | 0 | 40 | 0 | 1 | 10 | 40 | 8 | 0 | 32 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049430 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Kritika; Jain | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049431 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | SI | Offshore | Kritika; Jain | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049432 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | Kritika; Jain | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-08-12 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049433 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Offshore | Kritika; Jain | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-13 | 2016-04-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049434 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Kritika; Jain | IBM | Yes | CapEx | Localization | IT - External | 76.5h | 0h | 76.5h | 2016-09-06 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049435 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Kritika; Jain | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049436 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Kritika; Jain | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049437 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 0 Load in DEV - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 126h | 0h | 126h | 2016-06-06 | 2016-06-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049438 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 1 Load in QA - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 437h | 0h | 437h | 2016-06-27 | 2016-09-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049439 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Hypercare Support - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | OpEx | Localization | IT - External | 45h | 0h | 45h | 2017-02-06 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049440 | No | No | Yes | Argentina | Argentina | 04-Test | M1 - Execute loads - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049441 | No | No | Yes | Argentina | Argentina | 04-Test | SIT1 - Defect Fix - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 208.5h | 0h | 208.5h | 2016-09-12 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049442 | No | No | Yes | Argentina | Argentina | 04-Test | M2 - Execute pre validation - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2016-10-10 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049443 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute pre validation - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | OpEx | Localization | IT - External | 135h | 0h | 135h | 2016-12-19 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 27 | 36 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049444 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | OpEx | Localization | IT - External | 78h | 0h | 78h | 2016-12-19 | 2017-02-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049445 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute loads/ reports - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | OpEx | Localization | IT - External | 4.5h | 0h | 4.5h | 2016-12-12 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049446 | No | No | Yes | Argentina | Argentina | 04-Test | SIT2 - Defect Fix - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 55.5h | 0h | 55.5h | 2016-11-07 | 2016-12-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049447 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute pre validation - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 190h | 0h | 190h | 2016-11-07 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049448 | No | No | Yes | Argentina | Argentina | 04-Test | M2 - Execute loads/reports - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 126h | 0h | 126h | 2016-10-17 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049449 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-09-05 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049450 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-13 | 2016-04-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049451 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 0 Load in DEV - DC | MDG | DC | SI | Offshore | Diwa; Karissa | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-25 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049452 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- OTC | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 216h | 0h | 216h | 2016-05-16 | 2016-06-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049453 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - OTC | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049454 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-29 | 2016-08-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049455 | No | No | Yes | Argentina | Argentina | 04-Test | OTC - SIT 2 - Run Tests | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-10-24 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049456 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG KT visit | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049457 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 165h | 0h | 165h | 2016-12-05 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049458 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049459 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049460 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 0 Load in DEV - DC | MDG | DC | SI | Offshore | Alviar; Maricar | Accenture | Yes | CapEx | Localization | IT - External | 62.5h | 0h | 62.5h | 2016-05-30 | 2016-06-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049461 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 0 Load in DEV - DC | MDG | DC | SI | Offshore | Mangiliman; Maricar | Accenture | Yes | CapEx | Localization | IT - External | 72h | 0h | 72h | 2016-06-01 | 2016-06-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049462 | No | Yes | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute loads/ reports - DC | MDG | DC | SI | Offshore | Mangiliman; Maricar | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049463 | No | Yes | Yes | Argentina | Argentina | 04-Test | M2 - Execute loads/reports - DC | MDG | DC | SI | Offshore | Mangiliman; Maricar | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049464 | No | Yes | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute pre validation - DC | MDG | DC | SI | Offshore | Mangiliman; Maricar | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049465 | No | Yes | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute Loads/Reports - DC | MDG | DC | SI | Offshore | Mangiliman; Maricar | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-28 | 2016-11-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049466 | No | Yes | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute pre validation - DC | MDG | DC | SI | Offshore | Mangiliman; Maricar | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049467 | No | Yes | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Data verification Signoff sheets - DC | MDG | DC | SI | Offshore | Mangiliman; Maricar | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-29 | 2016-11-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049468 | No | Yes | Yes | Argentina | Argentina | 04-Test | SIT2 - Defect Fix - DC | MDG | DC | SI | Offshore | Mangiliman; Maricar | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049469 | No | Yes | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover - DC | MDG | DC | SI | Offshore | Mangiliman; Maricar | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049470 | No | Yes | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT Prep - DC | MDG | DC | SI | Offshore | Mangiliman; Maricar | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049471 | No | Yes | Yes | Argentina | Argentina | 04-Test | M2 - Execute pre validation - DC | MDG | DC | SI | Offshore | Mangiliman; Maricar | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049472 | No | Yes | Yes | Argentina | Argentina | 04-Test | SIT1 - Defect Fix - DC | MDG | DC | SI | Offshore | Mangiliman; Maricar | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049473 | No | Yes | Yes | Argentina | Argentina | 04-Test | Training Prep - DC | MDG | DC | SI | Offshore | Mangiliman; Maricar | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049474 | No | Yes | Yes | Argentina | Argentina | 06-Hypercare | Hypercare Support - DC | MDG | DC | SI | Offshore | Mangiliman; Maricar | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049475 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 0 Load in DEV - DC | MDG | DC | SI | Offshore | Manalac; Edgar | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-25 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049476 | No | Yes | Yes | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Doppalapudi; Nagaraju | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049477 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Doppalapudi; Nagaraju | IBM | Yes | CapEx | Localization | IT - External | 12.5h | 0h | 12.5h | 2016-08-22 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049478 | No | Yes | Yes | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Doppalapudi; Nagaraju | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049479 | No | Yes | Yes | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Doppalapudi; Nagaraju | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049480 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-RTR | RTR | FUN | Saputo | Onshore | Therien; Stephane | Saputo | Yes | OpEx | Localization | IT - Internal | 580h | 0h | 580h | 2017-03-20 | 2017-06-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 36 | 40 | 40 | 49 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049481 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | RTR | FUN | Saputo | Onshore | Therien; Stephane | Saputo | Yes | CapEx | Localization | IT - Internal | 80h | 0h | 80h | 2017-01-23 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049482 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - RTR | RTR | FUN | Saputo | Onshore | Therien; Stephane | Saputo | Yes | OpEx | Localization | IT - Internal | 200h | 0h | 200h | 2017-02-06 | 2017-03-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049483 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | LOG | FUN | SI | Onshore | Esquerro; Alejandro | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049484 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | SI | Onshore | Esquerro; Alejandro | IBM | Yes | CapEx | Localization | IT - External | 55h | 0h | 55h | 2017-01-30 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049485 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-LOG | LOG | FUN | SI | Onshore | Esquerro; Alejandro | IBM | Yes | OpEx | Localization | IT - External | 622h | 0h | 622h | 2017-03-06 | 2017-06-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 44 | 35 | 44 | 0 | 0 | 44 | 44 | 35 | 44 | 44 | 36 | 44 | 36 | 40 | 40 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049486 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | LOG | FUN | SI | Onshore | Esquerro; Alejandro | IBM | Yes | CapEx | Localization | IT - External | 129h | 0h | 129h | 2017-01-09 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 43 | 42 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049487 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | LOG | FUN | SI | Onshore | Esquerro; Alejandro | IBM | Yes | CapEx | Localization | IT - External | 60h | 0h | 60h | 2016-12-19 | 2017-02-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049488 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | LOG | FUN | SI | Onshore | Esquerro; Alejandro | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049489 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | SI | Onshore | Esquerro; Alejandro | IBM | Yes | OpEx | Localization | IT - External | 165h | 0h | 165h | 2017-02-13 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 50 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049490 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | LOG | FUN | SI | Onshore | Esquerro; Alejandro | IBM | Yes | CapEx | Localization | IT - External | 43h | 0h | 43h | 2017-01-02 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049491 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Manage Defects | LOG | FUN | SI | Onshore | Esquerro; Alejandro | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-12-26 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049492 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | LOG | FUN | SI | Onshore | Esquerro; Alejandro | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049493 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Onboarding | CM | CM | Saputo | Onshore | Gabra; Rania | Saputo | Yes | OpEx | Localization | IT - Internal | 45h | 0h | 45h | 2017-01-09 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049494 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Communication plan execution and monitoring | CM | CM | Saputo | Onshore | Gabra; Rania | Saputo | Yes | OpEx | Localization | IT - Internal | 142.75h | 0h | 142.75h | 2017-01-16 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 47 | 44.25 | 51.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049495 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Communication plan execution and monitoring | CM | CM | Saputo | Onshore | Gabra; Rania | Saputo | Yes | OpEx | Localization | IT - Internal | 144.5h | 0h | 144.5h | 2017-02-06 | 2017-03-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50.5 | 43.5 | 7 | 25.5 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049496 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Value Realization Monitoring | CM | CM | Saputo | Onshore | Gabra; Rania | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049497 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-CM | CM | CM | Saputo | Onshore | Gabra; Rania | Saputo | Yes | OpEx | Localization | IT - Internal | 23.7h | 0h | 23.7h | 2017-03-27 | 2017-06-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0.9 | 1.8 | 3 | 6 | 3 | 2 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049498 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - PTM | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 123h | 0h | 123h | 2017-01-30 | 2017-02-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049499 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 178h | 0h | 178h | 2017-02-06 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 84 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049500 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049501 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | OpEx | Localization | IT - External | 44h | 0h | 44h | 2017-01-23 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049502 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-01-16 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049503 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2016-12-19 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049504 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2016-12-12 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049505 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Manage Defects | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 84h | 0h | 84h | 2016-12-05 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049506 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 7h | 0h | 7h | 2016-12-12 | 2016-12-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049507 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 17h | 0h | 17h | 2016-12-12 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049508 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049509 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTM - Run Tests | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 76h | 0h | 76h | 2016-10-24 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049510 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTM - Manage Defects | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 123h | 0h | 123h | 2016-10-31 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049511 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Functional Specification (FSD) | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 71h | 0h | 71h | 2016-08-01 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049512 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 132h | 0h | 132h | 2016-09-12 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049513 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Manage Defects | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-26 | 2016-09-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049514 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - Prep | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2016-10-11 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049515 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049516 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTM - Break/Fix | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 55h | 0h | 55h | 2016-11-21 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049517 | No | Yes | No | Argentina | Argentina | 04-Test | Project SAP Environment Support | TAI | TAI | SI | Onshore | Kingbo; David | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-10-24 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049518 | No | Yes | No | Argentina | Argentina | 04-Test | Batch Execution Implementation | TAI | TAI | SI | Onshore | Kingbo; David | Accenture | Yes | CapEx | Localization | IT - External | 47h | 0h | 47h | 2016-10-24 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049519 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Contribute to Cutover Planning | TAI | TAI | SI | Onshore | Kingbo; David | Accenture | Yes | CapEx | Localization | IT - External | 118.48h | 0h | 118.48h | 2016-09-06 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049520 | No | Yes | No | Argentina | Argentina | 04-Test | Maintain Existing Deliverables as needed | TAI | TAI | SI | Onshore | Kingbo; David | Accenture | Yes | CapEx | Localization | IT - External | 85.35h | 0h | 85.35h | 2016-09-06 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049521 | No | Yes | No | Argentina | Argentina | 04-Test | TEST - Technical Architecture and Infrastructure (gen) | TAI | TAI | SI | Onshore | Kingbo; David | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-01 | 2016-09-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049522 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM |  | Missing Stream | Saputo | Onshore | Westerveld; Bruce | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049523 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Management (Cutover/Go-live) |  | Missing Stream | Saputo | Onshore | Westerveld; Bruce | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049524 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around |  | Missing Stream | Saputo | Onshore | Westerveld; Bruce | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049525 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049526 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Manage Defects | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049527 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049528 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 41h | 0h | 41h | 2017-01-10 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 1 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049529 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | OpEx | Localization | IT - Internal | 56h | 0h | 56h | 2017-01-23 | 2017-07-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 2 | 6 | 0 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049530 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 33h | 0h | 33h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049531 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049532 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Management (Cutover/Go-live) | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 47h | 0h | 47h | 2017-01-04 | 2017-01-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 24 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049533 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | OpEx | Localization | IT - Internal | 10.5h | 0h | 10.5h | 2017-04-12 | 2017-04-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049534 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-12-05 | 2017-01-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049535 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | OpEx | Localization | IT - Internal | 64h | 0h | 64h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049536 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049537 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049538 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 115h | 0h | 115h | 2016-12-12 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 30 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049539 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 72h | 0h | 72h | 2016-09-12 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049540 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Solution Design Document (SDD) - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049541 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests (Saputo) - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-09-06 | 2016-09-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049542 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | SI | Onshore | Litvin; Darrell | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049543 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | RTR | FUN | SI | Onshore | Litvin; Darrell | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049544 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | RTR | FUN | SI | Onshore | Litvin; Darrell | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049545 | No | Yes | No | Argentina | Argentina | 04-Test | Updates concepts decks | RTR | FUN | SI | Onshore | Litvin; Darrell | SAP | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049546 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Prep | RTR | FUN | SI | Onshore | Litvin; Darrell | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049547 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | SI | Onshore | Myers; Vincent | IBM | Yes | OpEx | Localization | IT - External | 84h | 0h | 84h | 2017-02-13 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049548 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | SI | Onshore | Martin; Katy | IBM | Yes | OpEx | Localization | IT - External | 124h | 0h | 124h | 2017-02-13 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049549 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | SI | Offshore | Trivedi; Mohit | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049550 | No | No | Yes | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Trivedi; Mohit | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049551 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | Trivedi; Mohit | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049552 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Prepare | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 21h | 0h | 21h | 2016-10-17 | 2016-10-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049553 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-01-23 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049554 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 52h | 0h | 52h | 2016-09-12 | 2016-10-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049555 | No | Yes | No | Argentina | Argentina | 04-Test | Prep PRD for performance testing | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2016-11-04 | 2016-11-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049556 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Prep | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2016-10-12 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049557 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Validate | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049558 | No | Yes | No | Argentina | Argentina | 06-Hypercare | CR-GL Upload Program | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | OpEx | Localization | IT - External | 64h | 0h | 64h | 2017-04-10 | 2017-05-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 25 | 19 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049559 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-RTR | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | OpEx | Localization | IT - External | 18h | 0h | 18h | 2017-04-10 | 2017-04-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049560 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 95h | 0h | 95h | 2016-09-12 | 2016-10-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049561 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Validate | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | OpEx | Localization | IT - External | 23h | 0h | 23h | 2016-09-06 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049562 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Run Tests | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049563 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Manage Defects | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 62h | 0h | 62h | 2016-10-24 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049564 | No | Yes | No | Argentina | Argentina | 04-Test | Updates concepts decks | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | OpEx | Localization | IT - External | 10h | 0h | 10h | 2016-10-11 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049565 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Break/Fix | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 60h | 0h | 60h | 2016-11-04 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049566 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049567 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2016-12-05 | 2017-01-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 16 | 20 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049568 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2016-12-05 | 2016-12-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049569 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 11h | 0h | 11h | 2016-11-10 | 2016-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049570 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2016-11-21 | 2016-11-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049571 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2017-02-27 | 2017-03-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049572 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - RTR | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 114h | 0h | 114h | 2017-02-06 | 2017-03-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 8 | 35 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049573 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - RTR | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | OpEx | Localization | IT - External | 24h | 0h | 24h | 2017-02-28 | 2017-03-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049574 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 43h | 0h | 43h | 2017-01-03 | 2017-01-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 19 | 20 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049575 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049576 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 23h | 0h | 23h | 2016-12-12 | 2016-12-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049577 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Support | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-15 | 2016-07-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049578 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Onshore | Gilbert; Marc | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-01-30 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049579 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | SI | Onshore | Gilbert; Marc | IBM | Yes | OpEx | Localization | IT - External | 275h | 0h | 275h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 72 | 72 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049580 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Onshore | Gilbert; Marc | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049581 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Onshore | Gilbert; Marc | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2016-09-06 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049582 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Onshore | Gilbert; Marc | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049583 | No | Yes | No | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Onshore | Gilbert; Marc | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049584 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | SI | Onshore | Gilbert; Marc | IBM | Yes | OpEx | Localization | IT - External | 485h | 0h | 485h | 2017-03-06 | 2017-05-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 26 | 39 | 40 | 44 | 36 | 44 | 44 | 44 | 44 | 44 | 36 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049585 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Onshore | Faiz; Abdelhadi | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049586 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Onshore | Faiz; Abdelhadi | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049587 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Onshore | Faiz; Abdelhadi | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049588 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Onshore | Faiz; Abdelhadi | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049589 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Onshore | Nguyen; Tony | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049590 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Onshore | Nguyen; Tony | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049591 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Onshore | Nguyen; Tony | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049592 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Onshore | Nguyen; Tony | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049593 | No | Yes | No | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) (SI) - DM | MDG | DM | SI | Onshore | Nera; Noel | SAP | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2016-09-06 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049594 | No | Yes | No | Argentina | Argentina | 04-Test | SIT1 - Execution (SI) - DM | MDG | DM | SI | Onshore | Nera; Noel | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-12 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049595 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 1 Load in QA (SAP) - DM | MDG | DM | SI | Onshore | Nera; Noel | SAP | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2016-08-22 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049596 | No | Yes | No | Argentina | Argentina | 04-Test | SIT2 - Execution (SI) - DM | MDG | DM | SI | Onshore | Nera; Noel | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049597 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - Prep | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-17 | 2016-10-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049598 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 132h | 0h | 132h | 2016-12-12 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049599 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-28 | 2016-11-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049600 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049601 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 132h | 0h | 132h | 2017-01-09 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049602 | No | Yes | No | Argentina | Argentina | 04-Test | OTC - SIT 2 - Run Tests | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 233h | 0h | 233h | 2016-10-24 | 2016-12-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049603 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-10-17 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049604 | No | Yes | No | Argentina | Argentina | 04-Test | OTC - SIT 2 - Break/Fix | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 130h | 0h | 130h | 2016-11-07 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049605 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049606 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2016-11-21 | 2016-11-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049607 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049608 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | OpEx | Localization | IT - External | 158h | 0h | 158h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 51 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049609 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 60h | 0h | 60h | 2017-02-20 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049610 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049611 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 98.4h | 0h | 98.4h | 2016-09-14 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049612 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - OTC | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 78h | 0h | 78h | 2017-01-30 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049613 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PMO | PMO | PMO | Saputo | Onshore | Lawson; Ted | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049614 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | SI | Onshore | Sulyman; Ola | IBM | Yes | OpEx | Localization | IT - External | 240h | 0h | 240h | 2017-03-27 | 2017-06-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 44 | 44 | 44 | 44 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049615 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTM | FUN | SI | Onshore | Sulyman; Ola | IBM | Yes | OpEx | Localization | IT - External | 44h | 0h | 44h | 2017-02-06 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049616 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | SI | Onshore | Sulyman; Ola | IBM | Yes | CapEx | Localization | IT - External | 132h | 0h | 132h | 2017-02-13 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049617 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - PTM | PTM | FUN | SI | Onshore | Sulyman; Ola | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2017-01-23 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049618 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049619 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049620 | No | No | Yes | Argentina | Argentina | 04-Test | OTC - SIT 2 - Break/Fix | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 422h | 0h | 422h | 2016-11-21 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 36 | 36 | 44 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049621 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-10-03 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049622 | No | No | Yes | Argentina | Argentina | 04-Test | OTC - SIT 2 - Run Tests | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 153h | 0h | 153h | 2016-10-31 | 2016-11-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049623 | No | No | Yes | Argentina | Argentina | 04-Test | OTC - SIT 2 - Manage Defects | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2016-11-14 | 2016-11-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049624 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG KT visit | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049625 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - Prep | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2016-10-17 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049626 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Unit testing Configuration Documentation | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049627 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049628 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - OTC | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 60h | 0h | 60h | 2017-01-30 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049629 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049630 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049631 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 75h | 0h | 75h | 2016-10-03 | 2016-10-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049632 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Manage Defects | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-10-03 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049633 | No | Yes | Yes | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Tewari; Apoorva | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049634 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Tewari; Apoorva | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049635 | No | Yes | Yes | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Tewari; Apoorva | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049636 | No | Yes | Yes | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Tewari; Apoorva | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049637 | No | Yes | No | Argentina | Argentina | 04-Test | Training Materials - Concept slides & Exercices book | CM | CM | SI | Onshore | Frame; Susanne | IBM | Yes | OpEx | Localization | IT - External | 412h | 0h | 412h | 2016-09-26 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049638 | No | Yes | No | Argentina | Argentina | 04-Test | Work Instructions - Exercices DATA (technical writer + Dele) | CM | CM | SI | Onshore | Harten; Ian | IBM | Yes | OpEx | Localization | IT - External | 721h | 0h | 721h | 2016-09-19 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049639 | No | Yes | Yes | Argentina | Argentina | 04-Test | SIT2 - Execution (SI) - DM | MDG | DM | SI | Onshore | Cousley; Fabian | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049640 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 1 Load in QA (SAP) - DM | MDG | DM | SI | Onshore | Cousley; Fabian | SAP | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2016-06-22 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049641 | No | Yes | Yes | Argentina | Argentina | 04-Test | SIT1 - Execution (SI) - DM | MDG | DM | SI | Onshore | Cousley; Fabian | SAP | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-09-26 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049642 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Sorino; Irezar | Accenture | Yes | CapEx | Localization | IT - External | 387h | 0h | 387h | 2016-12-05 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 27 | 45 | 45 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049643 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | SI | Offshore | Sorino; Irezar | Accenture | Yes | OpEx | Localization | IT - External | 35h | 0h | 35h | 2017-02-06 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049644 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Sorino; Irezar | Accenture | Yes | CapEx | Localization | IT - External | 333h | 0h | 333h | 2016-10-10 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049645 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | Sorino; Irezar | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049646 | No | Yes | No | Argentina | Argentina | 04-Test | SIT1 - Defect Fix - DEV | DEV | DEV | SI | Offshore | Sorino; Irezar | Accenture | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2016-09-26 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049647 | No | Yes | No | Argentina | Argentina | 04-Test | SIT1 - Manage Defect - DEV | DEV | DEV | SI | Offshore | Sorino; Irezar | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049648 | No | Yes | No | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DEV | DEV | DEV | SI | Offshore | Sorino; Irezar | Accenture | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2016-10-03 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049649 | No | Yes | No | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) (SI) - DM | MDG | DM | SI | Onshore | Josephson; Jacob | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049650 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Hypercare Support (Accenture) - DM | MDG | DM | SI | Onshore | Josephson; Jacob | Accenture | Yes | CapEx | Localization | IT - External | 156h | 0h | 156h | 2017-02-06 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 57 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049651 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Recordings Customer/Work Instructions (Accenture) - DM | MDG | DM | SI | Onshore | Josephson; Jacob | Accenture | Yes | OpEx | Localization | IT - External | 72h | 0h | 72h | 2017-01-18 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049652 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Recordings Vendor/Work Instructions (Accenture) - DM | MDG | DM | SI | Onshore | Josephson; Jacob | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049653 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover (Accenture) - DM | MDG | DM | SI | Onshore | Josephson; Jacob | Accenture | Yes | CapEx | Localization | IT - External | 144h | 0h | 144h | 2016-12-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 32 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049654 | No | Yes | No | Argentina | Argentina | 04-Test | SIT1 - Defect Fix (Accenture) - DM | MDG | DM | SI | Onshore | Josephson; Jacob | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049655 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - Prep (Accenture) - DM | MDG | DM | SI | Onshore | Josephson; Jacob | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-10-24 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049656 | No | Yes | No | Argentina | Argentina | 04-Test | SIT2 - Execution (SI) - DM | MDG | DM | SI | Onshore | Josephson; Jacob | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-11-28 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049657 | No | Yes | No | Argentina | Argentina | 04-Test | SIT2 - Manage Defect (Accenture) - DM | MDG | DM | SI | Onshore | Josephson; Jacob | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049658 | No | Yes | No | Argentina | Argentina | 04-Test | SIT2 - Defect Fix (Accenture) - DM | MDG | DM | SI | Onshore | Josephson; Jacob | Accenture | Yes | CapEx | Localization | IT - External | 104h | 0h | 104h | 2016-11-21 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049659 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Technical Architecture and Infrastructure (gen) | TAI | TAI | SI | Onshore | Thayyil; Shajariya | Accenture | Yes | CapEx | Localization | IT - External | 132h | 0h | 132h | 2016-09-26 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049660 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - TAI | TAI | TAI | SI | Onshore | Thayyil; Shajariya | Accenture | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2016-09-06 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049661 | No | No | Yes | Argentina | Argentina | 04-Test | Development | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 62.5h | 0h | 62.5h | 2016-10-24 | 2016-11-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049662 | No | No | Yes | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049663 | No | No | Yes | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | OpEx | Global | IT - Internal | 1.5h | 0h | 1.5h | 2017-05-29 | 2017-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049664 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | OpEx | Localization | IT - Internal | 28.5h | 0h | 28.5h | 2017-03-27 | 2017-07-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5 | 1 | 0.5 | 0.5 | 1 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 4.5 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049665 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | OpEx | Localization | IT - Internal | 7.5h | 0h | 7.5h | 2017-02-07 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049666 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 61.5h | 0h | 61.5h | 2017-01-04 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 17.5 | 24 | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049667 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049668 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, team organization) | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 66.5h | 0h | 66.5h | 2016-10-06 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049669 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 48h | 0h | 48h | 2016-10-10 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049670 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-01-30 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049671 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Unit testing Configuration Documentation | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 34h | 0h | 34h | 2016-08-22 | 2016-09-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049672 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Prep | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 22h | 0h | 22h | 2016-10-17 | 2016-11-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049673 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG KT visit | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 34h | 0h | 34h | 2016-08-15 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049674 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 172h | 0h | 172h | 2016-09-10 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049675 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- RTR | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 430h | 0h | 430h | 2016-05-30 | 2016-08-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049676 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - RTR | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 26h | 0h | 26h | 2016-07-11 | 2016-07-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049677 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-12 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049678 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049679 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 166h | 0h | 166h | 2016-12-19 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 44 | 44 | 24 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049680 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2016-12-22 | 2016-12-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049681 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-01-16 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049682 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049683 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - RTR | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | OpEx | Localization | IT - External | 228h | 0h | 228h | 2017-02-06 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 46 | 57 | 29 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049684 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - RTR | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 19h | 0h | 19h | 2017-02-06 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049685 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 121h | 0h | 121h | 2016-12-05 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049686 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Break/Fix | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 38h | 0h | 38h | 2016-10-31 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049687 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Manage Defects | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 62h | 0h | 62h | 2016-11-11 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049688 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Run Tests | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 86h | 0h | 86h | 2016-10-31 | 2016-11-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049689 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | RTR | FUN | SI | Onshore | Minarro; Javier | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049690 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | OpEx | Localization | IT - External | 180h | 0h | 180h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 52 | 47 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049691 | No | No | Yes | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049692 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | OpEx | Localization | IT - External | 194.5h | 0h | 194.5h | 2017-03-06 | 2017-06-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 34 | 8 | 0 | 0 | 27 | 9 | 0 | 36 | 22.5 | 0 | 0 | 0 | 11 | 28 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049693 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | CapEx | Localization | IT - External | 102h | 0h | 102h | 2016-08-22 | 2016-10-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049694 | No | No | Yes | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | CapEx | Localization | IT - External | 201h | 0h | 201h | 2016-09-21 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 2 | 16 | 3 | 10 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049695 | No | No | Yes | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | OpEx | Global | IT - External | 5h | 0h | 5h | 2017-05-23 | 2017-06-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049696 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-13 | 2016-04-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049697 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-09 | 2016-05-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049698 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 184h | 0h | 184h | 2016-12-28 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 26 | 26 | 44 | 0 | 0 | 44 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049699 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | OpEx | Localization | IT - External | 88h | 0h | 88h | 2017-02-06 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049700 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049701 | No | No | Yes | Argentina | Argentina | 04-Test | Manage SIT1 Prep (data, transports) | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 92h | 0h | 92h | 2016-08-29 | 2016-09-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049702 | No | No | Yes | Argentina | Argentina | 04-Test | Manage SIT1 Execution | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 40.88h | 0h | 40.88h | 2016-10-11 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049703 | No | No | Yes | Argentina | Argentina | 04-Test | Manage SIT1 Execution local (ARG) | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 35h | 0h | 35h | 2016-10-04 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049704 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Manage UAT Execution | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049705 | No | No | Yes | Argentina | Argentina | 04-Test | Manage SIT2 Execution local (ARG) | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 54h | 0h | 54h | 2016-11-14 | 2016-11-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049706 | No | No | Yes | Argentina | Argentina | 04-Test | Manage SIT2 Prep (data, transports) | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-10-24 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049707 | No | No | Yes | Argentina | Argentina | 04-Test | Manage SIT2 Execution | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 203h | 0h | 203h | 2016-10-31 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049708 | No | No | Yes | Argentina | Argentina | 04-Test | Work Instructions - Exercices DATA (technical writer + Dele) | CM | CM | SI | Onshore | Goel; Ronika | IBM | Yes | OpEx | Localization | IT - External | 859h | 0h | 859h | 2016-09-19 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 45 | 27 | 36 | 45 | 36 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049709 | No | Yes | No | Argentina | Argentina | 04-Test | Work Instructions - Exercices DATA (technical writer + Dele) | CM | CM | SI | Offshore | Rudrurkar; Vijay | IBM | Yes | OpEx | Localization | IT - External | 306h | 0h | 306h | 2016-09-19 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049710 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049711 | No | No | Yes | Argentina | Argentina | 04-Test | SIT1 - Execution - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 248h | 0h | 248h | 2016-09-12 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049712 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-MDG-DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | OpEx | Localization | IT - Internal | 10h | 0h | 10h | 2017-03-20 | 2017-03-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049713 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute pre validation - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | OpEx | Localization | IT - Internal | 44h | 0h | 44h | 2016-12-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049714 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute loads/ reports - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | OpEx | Localization | IT - Internal | 46h | 0h | 46h | 2016-12-12 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049715 | No | No | Yes | Argentina | Argentina | 04-Test | SIT2 - Execution - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 45h | 0h | 45h | 2016-10-24 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049716 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 89h | 0h | 89h | 2017-01-02 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 44 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049717 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - OTC | OTC | FUN | SI | Onshore | Gamez; Valerie | SAP | Yes | CapEx | Localization | IT - External | 120h | 0h | 120h | 2017-01-02 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 40 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049718 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-MDG-DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049719 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute loads/ reports - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | OpEx | Localization | IT - External | 90h | 0h | 90h | 2016-12-12 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049720 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute pre validation - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 192h | 0h | 192h | 2016-11-14 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049721 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute pre validation - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | OpEx | Localization | IT - External | 269h | 0h | 269h | 2016-12-05 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049722 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 369h | 0h | 369h | 2016-09-19 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049723 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Recordings Customer/Work Instructions (Saputo) - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049724 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Recordings Vendor/Work Instructions (Saputo) - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049725 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Hypercare Support (Saputo) - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 160h | 0h | 160h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049726 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-MDG-(Saputo - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 167h | 0h | 167h | 2017-03-20 | 2017-04-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 20 | 20 | 31 | 26 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049727 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cutover - Dual Maintenance Argentina Customer (Saputo) - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 36h | 0h | 36h | 2017-01-03 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 16 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049728 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cutover - Dual Maintenance Argentina Vendor (Saputo) - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 92h | 0h | 92h | 2017-01-03 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 16 | 20 | 16 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049729 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cutover - Dual Maintenance Argentina Materials (Saputo) - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 56h | 0h | 56h | 2017-01-16 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 16 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049730 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cutover - Dual Maintenance Argentina Finance (Saputo) - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-12-27 | 2016-12-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049731 | No | Yes | No | Argentina | Argentina | 04-Test | LOG - SIT 2 - Break/Fix | OTC | FUN | SI | Onshore | Dodds; Elaine | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2016-11-21 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049732 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | OTC | FUN | SI | Onshore | Dodds; Elaine | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-01 | 2016-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049733 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | OTC | FUN | SI | Onshore | Dodds; Elaine | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049734 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-MDG-DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049735 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-MDG-DG | MDG | DG | Saputo | Onshore | Lentz; Jared | Saputo | Yes | OpEx | Localization | IT - Internal | 15h | 0h | 15h | 2017-03-20 | 2017-06-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049736 | No | No | Yes | Argentina | Argentina | 04-Test | Data quality - DG | MDG | DG | Saputo | Onshore | Lentz; Jared | Saputo | Yes | OpEx | Localization | IT - Internal | 108h | 0h | 108h | 2016-11-14 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049737 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Data quality (Cutover/Go-live) - DG | MDG | DG | Saputo | Onshore | Lentz; Jared | Saputo | Yes | OpEx | Localization | IT - Internal | 322h | 0h | 322h | 2016-12-05 | 2017-02-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 24 | 40 | 40 | 40 | 40 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049738 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Data quality (Hypercare) - DG | MDG | DG | Saputo | Onshore | Lentz; Jared | Saputo | Yes | OpEx | Localization | IT - Internal | 101.4h | 0h | 101.4h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 31.4 | 25 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049739 | No | Yes | No | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Ghoshbiswas; Veena | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049740 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | Ghoshbiswas; Veena | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049741 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | SI | Offshore | Ghoshbiswas; Veena | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049742 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Execute loads/ reports (Accenture) - DM | MDG | DM | SI | Onshore | Gireesh; Mangeshi | Accenture | Yes | CapEx | Localization | IT - External | 168h | 0h | 168h | 2016-12-29 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 16 | 32 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049743 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute pre validation (Accenture) - DM | MDG | DM | SI | Onshore | Gireesh; Mangeshi | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-12-05 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049744 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute Loads/Reports (Accenture) - DM | MDG | DM | SI | Onshore | Gireesh; Mangeshi | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-11-28 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049745 | No | Yes | No | Argentina | Argentina | 04-Test | SIT2 - Execution (SI) - DM | MDG | DM | SI | Onshore | Gireesh; Mangeshi | Accenture | Yes | CapEx | Localization | IT - External | 120h | 0h | 120h | 2016-11-21 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049746 | No | Yes | No | Argentina | Argentina | 04-Test | SIT1 - Execution (SI) - DM | MDG | DM | SI | Onshore | Gireesh; Mangeshi | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-11 | 2016-09-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049747 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cutover - Dual Maintenance Argentina Finance (Accenture) - DM | MDG | DM | SI | Onshore | Gireesh; Mangeshi | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-12-28 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049748 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Hypercare Support (Accenture) - DM | MDG | DM | SI | Onshore | Gireesh; Mangeshi | Accenture | Yes | CapEx | Localization | IT - External | 112h | 0h | 112h | 2017-02-06 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049749 | No | Yes | No | Argentina | Argentina | 04-Test | SIT1 - Execution (SI) - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-11 | 2016-09-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049750 | No | Yes | No | Argentina | Argentina | 04-Test | SIT2 - Execution (SI) - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 144h | 0h | 144h | 2016-11-21 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049751 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cutover - Dual Maintenance Argentina Materials (Accenture) - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 120h | 0h | 120h | 2016-12-19 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 16 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049752 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cutover - Dual Maintenance Argentina Finance (Accenture) - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-27 | 2016-12-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049753 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-LOG | LOG | FUN | SI | Onshore | McDonough; Alan | SAP | Yes | OpEx | Localization | IT - External | 120h | 0h | 120h | 2017-03-06 | 2017-03-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049754 | No | Yes | No | Argentina | Argentina | 04-Test | LOG - SIT 2 - Break/Fix | LOG | FUN | SI | Onshore | McDonough; Alan | SAP | Yes | CapEx | Localization | IT - External | 136h | 0h | 136h | 2016-11-15 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049755 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | LOG | FUN | SI | Onshore | McDonough; Alan | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-15 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049756 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | LOG | FUN | SI | Onshore | McDonough; Alan | SAP | Yes | CapEx | Localization | IT - External | 160h | 0h | 160h | 2016-12-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049757 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | LOG | FUN | SI | Onshore | McDonough; Alan | SAP | Yes | CapEx | Localization | IT - External | 98h | 0h | 98h | 2016-12-19 | 2017-02-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049758 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | LOG | FUN | SI | Onshore | McDonough; Alan | SAP | Yes | CapEx | Localization | IT - External | 156h | 0h | 156h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 64 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049759 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | SI | Onshore | McDonough; Alan | SAP | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-01-23 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049760 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover Steps | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049761 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049762 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049763 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049764 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Prepare | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 115h | 0h | 115h | 2016-11-14 | 2016-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049765 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049766 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049767 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Manage Defects | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-21 | 2016-11-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049768 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049769 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-TAI | TAI | TAI | SI | Offshore | Imperial; Jhannica | Accenture | Yes | OpEx | Localization | IT - External | 751.5h | 0h | 751.5h | 2017-03-06 | 2017-08-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 36 | 27 | 36 | 45 | 0 | 45 | 45 | 45 | 45 | 36 | 36 | 45 | 45 | 22.5 | 22.5 | 0 | 18 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049770 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Support Hypercare | TAI | TAI | SI | Offshore | Imperial; Jhannica | Accenture | Yes | CapEx | Localization | IT - External | 180h | 0h | 180h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049771 | No | No | Yes | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | OpEx | Global | IT - External | 1h | 0h | 1h | 2017-06-01 | 2017-06-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049772 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | OpEx | Localization | IT - External | 93h | 0h | 93h | 2017-03-22 | 2017-05-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 19 | 0 | 0 | 0 | 0 | 0 | 36 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049773 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | CapEx | Localization | IT - External | 108.25h | 0h | 108.25h | 2016-09-19 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049774 | No | No | Yes | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | CapEx | Localization | IT - External | 93h | 0h | 93h | 2016-09-05 | 2016-11-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049775 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | OpEx | Localization | IT - External | 27h | 0h | 27h | 2017-02-06 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049776 | No | No | Yes | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049777 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | CapEx | Localization | IT - External | 123h | 0h | 123h | 2016-12-24 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 9 | 20 | 16 | 15 | 17 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049778 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Gupta; Shubham | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049779 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Gupta; Shubham | IBM | Yes | CapEx | Localization | IT - External | 41h | 0h | 41h | 2016-09-28 | 2016-10-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049780 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Gupta; Shubham | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049781 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Gupta; Shubham | IBM | Yes | CapEx | Localization | IT - External | 92h | 0h | 92h | 2016-08-22 | 2016-10-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049782 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Offshore | Gupta; Shubham | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-13 | 2016-04-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049783 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | Gupta; Shubham | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-09 | 2016-05-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049784 | No | Yes | No | Argentina | Argentina | 04-Test | TEST - Technical Architecture and Infrastructure (gen) | TAI | TAI | SI | Onshore | Arya; Kapil | Accenture | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2016-09-01 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049785 | No | Yes | No | Argentina | Argentina | 04-Test | Performance testing and refresh | TAI | TAI | SI | Onshore | Arya; Kapil | Accenture | Yes | CapEx | Localization | IT - External | 152h | 0h | 152h | 2016-09-19 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049786 | No | Yes | No | Argentina | Argentina | 04-Test | Test disaster recovery | TAI | TAI | SI | Onshore | Arya; Kapil | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-02 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049787 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | GRC AC - Cutover planning and Exucution | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-18 | 2016-10-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049788 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT Defect Resolution | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 261h | 0h | 261h | 2016-12-05 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 16 | 32 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049789 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cutover Planning and Execution | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-03 | 2016-10-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049790 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Composite Role Build | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-19 | 2016-09-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049791 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Derived Role Build | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2016-10-17 | 2016-10-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049792 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Master Role Build and UT | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049793 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Support Role Build and UT | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2016-09-26 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049794 | No | Yes | No | Argentina | Argentina | 04-Test | FUT Support Roles | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-17 | 2016-10-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049795 | No | Yes | No | Argentina | Argentina | 04-Test | Security Role FUT | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2016-10-21 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049796 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 Defect Resolution | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049797 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 Defect Resolution | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 258h | 0h | 258h | 2016-10-25 | 2016-12-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049798 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | GRC AC - UAT Execution | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049799 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Hypercare/support | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-01 | 2017-02-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049800 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | SoD Analysis and Remediation | SEC | SEC | SI | Offshore | Olvida; Julio | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049801 | No | No | Yes | Argentina | Argentina | 04-Test | SoD Analysis and Remediation | SEC | SEC | SI | Offshore | Olvida; Julio | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049802 | No | No | Yes | Argentina | Argentina | 04-Test | GRC AC - SIT Execution | SEC | SEC | SI | Offshore | Olvida; Julio | Accenture | Yes | CapEx | Localization | IT - External | 74h | 0h | 74h | 2016-11-02 | 2016-11-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049803 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | GRC AC - UAT Execution | SEC | SEC | SI | Offshore | Olvida; Julio | Accenture | Yes | CapEx | Localization | IT - External | 65h | 0h | 65h | 2016-12-05 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049804 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | GRC AC - Cutover planning and Exucution | SEC | SEC | SI | Offshore | Olvida; Julio | Accenture | Yes | CapEx | Localization | IT - External | 178h | 0h | 178h | 2016-10-19 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049805 | No | No | Yes | Argentina | Argentina | 06-Hypercare | GRC AC - Hypercare | SEC | SEC | SI | Offshore | Olvida; Julio | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049806 | No | No | Yes | Argentina | Argentina | 03-Design/Build | GRC AC - Build & UT | SEC | SEC | SI | Offshore | Olvida; Julio | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-10-17 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049807 | No | No | Yes | Argentina | Argentina | 03-Design/Build | GRC AC - SIT Prep | SEC | SEC | SI | Offshore | Olvida; Julio | Accenture | Yes | CapEx | Localization | IT - External | 82h | 0h | 82h | 2016-10-13 | 2016-11-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049808 | No | No | Yes | Argentina | Argentina | 03-Design/Build | SoD Analysis and Remediation | SEC | SEC | SI | Offshore | Olvida; Julio | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-30 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049809 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 Defect Resolution | SEC | SEC | SI | Offshore | Olvida; Julio | Accenture | Yes | CapEx | Localization | IT - External | 30h | 0h | 30h | 2016-10-22 | 2016-12-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049810 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cutover Planning and Execution | SEC | SEC | SI | Offshore | Olvida; Julio | Accenture | Yes | CapEx | Localization | IT - External | 101h | 0h | 101h | 2016-12-12 | 2016-12-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049811 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Hypercare/support | SEC | SEC | SI | Onshore | Jayasim; Franklin | IBM | Yes | OpEx | Localization | IT - External | 53h | 0h | 53h | 2017-02-07 | 2017-02-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049812 | No | Yes | No | Argentina | Argentina | 04-Test | FUT Support Roles | SEC | SEC | SI | Onshore | Jayasim; Franklin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-17 | 2016-10-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049813 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 Defect Resolution | SEC | SEC | SI | Onshore | Jayasim; Franklin | IBM | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2016-10-22 | 2016-11-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049814 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT Defect Resolution | SEC | SEC | SI | Onshore | Jayasim; Franklin | IBM | Yes | CapEx | Localization | IT - External | 273h | 0h | 273h | 2016-12-05 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 27 | 44 | 40 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049815 | No | Yes | No | Argentina | Argentina | 03-Design/Build | SoD Analysis and Remediation | SEC | SEC | SI | Onshore | Jayasim; Franklin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-30 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049816 | No | Yes | No | Argentina | Argentina | 04-Test | GRC AC - SIT Execution | SEC | SEC | SI | Onshore | Jayasim; Franklin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049817 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | GRC AC - Cutover planning and Exucution | SEC | SEC | SI | Onshore | Jayasim; Franklin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-18 | 2016-10-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049818 | No | Yes | No | Argentina | Argentina | 06-Hypercare | GRC AC - Hypercare | SEC | SEC | SI | Onshore | Jayasim; Franklin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049819 | No | Yes | No | Argentina | Argentina | 04-Test | SoD Analysis and Remediation | SEC | SEC | SI | Onshore | Jayasim; Franklin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049820 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | SoD Analysis and Remediation | SEC | SEC | SI | Onshore | Jayasim; Franklin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049821 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | Kumar; Bijendra | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049822 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | SI | Offshore | Kumar; Bijendra | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049823 | No | Yes | No | Argentina | Argentina |  | Perform project Planning and Control | PMO | PMO | SI | Onshore | Round; Andrew | IBM | Yes | CapEx | Localization | IT - External | 26h | 0h | 26h | 2016-03-14 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049824 | No | Yes | No | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTP | FUN | SI | Onshore | Melville; Steven | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-06 | 2016-09-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049825 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | SI | Onshore | Martel; Kelly | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049826 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Prep | RTR | FUN | SI | Onshore | Martel; Kelly | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2016-10-24 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049827 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Run Tests | RTR | FUN | SI | Onshore | Martel; Kelly | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049828 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Manage Defects | RTR | FUN | SI | Onshore | Martel; Kelly | IBM | Yes | CapEx | Localization | IT - External | 34h | 0h | 34h | 2016-11-07 | 2016-11-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049829 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Break/Fix | RTR | FUN | SI | Onshore | Martel; Kelly | IBM | Yes | CapEx | Localization | IT - External | 99.25h | 0h | 99.25h | 2016-11-14 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049830 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | RTR | FUN | SI | Onshore | Martel; Kelly | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-12-05 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049831 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - RTR | RTR | FUN | SI | Onshore | Martel; Kelly | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049832 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - RTR | RTR | FUN | SI | Onshore | Martel; Kelly | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049833 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | RTR | FUN | SI | Onshore | Martel; Kelly | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049834 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | RTR | FUN | SI | Onshore | Martel; Kelly | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049835 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | RTR | FUN | SI | Onshore | Martel; Kelly | IBM | Yes | CapEx | Localization | IT - External | 39h | 0h | 39h | 2016-12-05 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049836 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | RTR | FUN | SI | Onshore | Martel; Kelly | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049837 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | LOG | FUN | SI | Onshore | Davis; Sharlie | IBM | Yes | CapEx | Localization | IT - External | 250.85h | 0h | 250.85h | 2016-09-06 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049838 | No | Yes | No | Argentina | Argentina | 04-Test | LOG - SIT 2 - Manage Defects | OTC | FUN | SI | Onshore | Kim; Tae | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049839 | No | Yes | No | Argentina | Argentina | 04-Test | LOG - SIT 2 - Break/Fix | OTC | FUN | SI | Onshore | Kim; Tae | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049840 | No | Yes | No | Argentina | Argentina | 04-Test | OTC - SIT 2 - Manage Defects | OTC | FUN | SI | Onshore | Kim; Tae | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049841 | No | Yes | No | Argentina | Argentina | 04-Test | OTC - SIT 2 - Break/Fix | OTC | FUN | SI | Onshore | Kim; Tae | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049842 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG KT visit | OTC | FUN | SI | Onshore | Kim; Tae | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049843 | No | Yes | No | Argentina | Argentina | 04-Test | Work Instructions - Exercices DATA (technical writer + Dele) | CM | CM | SI | Onshore | Adams; Andre | IBM | Yes | OpEx | Localization | IT - External | 311h | 0h | 311h | 2016-10-24 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049844 | No | Yes | No | Argentina | Argentina | 04-Test | Work Instructions - Exercices DATA (technical writer + Dele) | CM | CM | SI | Offshore | Ganguly; Arunima | IBM | Yes | OpEx | Localization | IT - External | 234h | 0h | 234h | 2016-11-01 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049845 | No | No | Yes | Argentina | Argentina |  | 05-Release 1.3 | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | OpEx | Localization | IT - External | 72h | 0h | 72h | 2017-02-27 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049846 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-01-30 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049847 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049848 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-15 | 2016-11-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049849 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049850 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 17h | 0h | 17h | 2017-01-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049851 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049852 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 186h | 0h | 186h | 2016-12-19 | 2017-01-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 27 | 44 | 44 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049853 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-12-19 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049854 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | OpEx | Localization | IT - External | 84h | 0h | 84h | 2017-02-20 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049855 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 126h | 0h | 126h | 2017-02-06 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049856 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Manage Defects | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049857 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049858 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-LOG | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | OpEx | Localization | IT - External | 208h | 0h | 208h | 2017-03-13 | 2017-04-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 17 | 16 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049859 | No | Yes | No | Argentina | Argentina | 04-Test | Performance testing and refresh | TAI | TAI | SI | Offshore | Ko; Mark-Kevin | Accenture | Yes | CapEx | Localization | IT - External | 376h | 0h | 376h | 2016-10-17 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049860 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Performance testing write-off | TAI | TAI | SI | Offshore | Ko; Mark-Kevin | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-12-12 | 2016-12-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049861 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - PTM | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049862 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-02-13 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049863 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049864 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 135h | 0h | 135h | 2016-12-23 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 18 | 27 | 18 | 27 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049865 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049866 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - PTP - Break/Fix | PTP | FUN | SI | Offshore | Manoharan; Anandan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049867 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | PTP | FUN | SI | Offshore | Manoharan; Anandan | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-09-12 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049868 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - Prep | PTP | FUN | SI | Offshore | Manoharan; Anandan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049869 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | PTP | FUN | SI | Offshore | Manoharan; Anandan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049870 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | PTP | FUN | SI | Offshore | Manoharan; Anandan | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049871 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTP | FUN | SI | Offshore | Manoharan; Anandan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049872 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049873 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Deliver Training to End Users | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049874 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-CM | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049875 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Deliver Training to End Users | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049876 | No | No | Yes | Argentina | Argentina | 04-Test | Training Materials - Concept slides & Exercices book | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | OpEx | Localization | IT - Internal | 956h | 0h | 956h | 2016-09-06 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 32 | 32 | 41 | 32 | 40 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049877 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Identify materials needing localization | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | OpEx | Localization | IT - Internal | 16h | 0h | 16h | 2016-07-28 | 2016-07-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049878 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Composite Role Build | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2016-10-14 | 2016-10-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049879 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Derived Role Build | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Localization | IT - External | 7h | 0h | 7h | 2016-10-18 | 2016-10-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049880 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-SEC | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049881 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Security Role Design (Business Users) | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-06-20 | 2016-06-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049882 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Security Role Build & Unit Test (Business Users) | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-06-20 | 2016-06-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049883 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Hypercare/support | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-01 | 2017-02-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049884 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | GRC AC - UAT Execution | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049885 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT Defect Resolution | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2017-01-05 | 2017-01-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049886 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 Defect Resolution | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-07 | 2016-09-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049887 | No | No | Yes | Argentina | Argentina | 04-Test | FUT Support Roles | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Localization | IT - External | 51h | 0h | 51h | 2016-10-17 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049888 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Master Role Build and UT | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Localization | IT - External | 31h | 0h | 31h | 2016-09-16 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049889 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Support Role Build and UT | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-19 | 2016-09-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049890 | No | No | Yes | Argentina | Argentina | 04-Test | Security Role FUT | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-19 | 2016-09-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049891 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 Defect Resolution | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Localization | IT - External | 7.6h | 0h | 7.6h | 2016-10-22 | 2016-12-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049892 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | GRC AC - Cutover planning and Exucution | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-18 | 2016-10-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049893 | No | No | Yes | Argentina | Argentina | 03-Design/Build | SoD Analysis Prior to SIT - Roles | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-18 | 2016-09-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049894 | No | No | Yes | Argentina | Argentina | 03-Design/Build | SoD Remediation Prior to SIT - Roles | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-21 | 2016-07-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049895 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Support SIT 1 & Defect Resolution | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-28 | 2016-07-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049896 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Technical Architecture and Infrastructure (gen) | TAI | TAI | Saputo | Onshore | Tengler; David | Saputo | Yes | CapEx | Localization | IT - Internal | 16h | 0h | 16h | 2016-09-06 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049897 | No | No | Yes | Argentina | Argentina | 04-Test | Management | TAI | TAI | Saputo | Onshore | Tengler; David | Saputo | Yes | CapEx | Localization | IT - Internal | 490.6h | 0h | 490.6h | 2016-08-02 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049898 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-TAI | TAI | TAI | Saputo | Onshore | Tengler; David | Saputo | Yes | OpEx | Localization | IT - Internal | 130h | 0h | 130h | 2017-03-20 | 2017-05-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 0 | 40 | 20 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049899 | No | No | Yes | Argentina | Argentina | 04-Test | Development | DEV | DEV | Saputo | Onshore | Boisvert; Claude MIS | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049900 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | Saputo | Onshore | Boisvert; Claude MIS | Saputo | Yes | OpEx | Localization | IT - Internal | 86.5h | 0h | 86.5h | 2017-06-26 | 2017-07-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 31 | 27.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049901 | No | No | Yes | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | Saputo | Onshore | Boisvert; Claude MIS | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049902 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | Saputo | Onshore | Boisvert; Claude MIS | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049903 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | Saputo | Onshore | Boisvert; Claude MIS | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-12-09 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049904 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-TAI | TAI | TAI | Saputo | Onshore | Shindadkar; Amol | Saputo | Yes | OpEx | Localization | IT - Internal | 215h | 0h | 215h | 2017-03-27 | 2017-06-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 16 | 20 | 20 | 8 | 20 | 20 | 16 | 15 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049905 | No | No | Yes | Argentina | Argentina | 04-Test | Management | TAI | TAI | Saputo | Onshore | Shindadkar; Amol | Saputo | Yes | CapEx | Localization | IT - Internal | 40h | 0h | 40h | 2016-08-02 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049906 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Hypercare/support | SEC | SEC | SI | Offshore | Bobiles; CharmaineAnn | Accenture | Yes | OpEx | Localization | IT - External | 207h | 0h | 207h | 2017-02-01 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 45 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049907 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-SEC | SEC | SEC | SI | Offshore | Bobiles; CharmaineAnn | Accenture | Yes | OpEx | Localization | IT - External | 575h | 0h | 575h | 2017-03-06 | 2017-07-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 13 | 28 | 32 | 39 | 27 | 27 | 16 | 10 | 23 | 7 | 47 | 36 | 54 | 45 | 0 | 36 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049908 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Balchandani; Roma | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049909 | No | Yes | Yes | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Balchandani; Roma | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049910 | No | Yes | Yes | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Balchandani; Roma | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049911 | No | Yes | Yes | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Balchandani; Roma | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049912 | No | Yes | No | Argentina | Argentina | 04-Test | Work Instructions - Exercices DATA (technical writer + Dele) | CM | CM | SI | Offshore | Lakshmi; Gita | IBM | Yes | OpEx | Localization | IT - External | 369h | 0h | 369h | 2016-10-03 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049913 | No | No | Yes | Argentina | Argentina | 10-PCR | CR-Defect 6666 and Production Incident for currency for AR03 | BI | BI | SI | Onshore | Tata; SreeRama | IBM | Yes | OpEx | Localization | IT - External | 49h | 0h | 49h | 2017-05-12 | 2017-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 7 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049914 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Agarwal; Sunil | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049915 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Agarwal; Sunil | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049916 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Agarwal; Sunil | IBM | Yes | CapEx | Localization | IT - External | 126h | 0h | 126h | 2016-09-06 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049917 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Agarwal; Sunil | IBM | Yes | CapEx | Localization | IT - External | 115h | 0h | 115h | 2016-09-06 | 2016-10-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049918 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | PTM | FUN | Saputo | Onshore | Montgomery; David | Saputo | Yes | CapEx | Localization | IT - Internal | 120h | 0h | 120h | 2016-12-05 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049919 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTM | FUN | Saputo | Onshore | Montgomery; David | Saputo | Yes | CapEx | Localization | IT - Internal | 120h | 0h | 120h | 2016-12-28 | 2017-01-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 24 | 24 | 40 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049920 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTM | FUN | Saputo | Onshore | Montgomery; David | Saputo | Yes | CapEx | Localization | IT - Internal | 48h | 0h | 48h | 2017-01-16 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 40 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049921 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTM | FUN | Saputo | Onshore | Montgomery; David | Saputo | Yes | OpEx | Localization | IT - Internal | 16h | 0h | 16h | 2017-02-08 | 2017-02-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049922 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | Saputo | Onshore | Montgomery; David | Saputo | Yes | CapEx | Localization | IT - Internal | 16h | 0h | 16h | 2017-02-06 | 2017-02-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049923 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTP | PTM | FUN | Saputo | Onshore | Montgomery; David | Saputo | Yes | OpEx | Localization | IT - Internal | 40h | 0h | 40h | 2017-03-13 | 2017-03-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049924 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | Saputo | Onshore | Montgomery; David | Saputo | Yes | OpEx | Localization | IT - Internal | 342h | 0h | 342h | 2017-03-27 | 2017-06-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 40 | 0 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049925 | No | Yes | No | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTP | FUN | SI | Onshore | Neurath; Julian | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-06 | 2016-09-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049926 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | CapEx | Localization | IT - Internal | 37.5h | 0h | 37.5h | 2016-09-26 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049927 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | OpEx | Localization | IT - Internal | 369h | 0h | 369h | 2017-03-06 | 2017-07-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 29 | 0 | 16.5 | 41 | 31 | 40 | 43.5 | 43 | 40 | 25 | 0 | 0 | 0 | 1 | 2 | 5 | 0 | 2 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049928 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | OpEx | Localization | IT - Internal | 62h | 0h | 62h | 2016-10-11 | 2016-11-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049929 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | OpEx | Localization | IT - Internal | 33h | 0h | 33h | 2016-09-12 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049930 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | OpEx | Localization | IT - Internal | 24h | 0h | 24h | 2016-10-21 | 2016-11-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049931 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | CapEx | Localization | IT - Internal | 74h | 0h | 74h | 2016-09-12 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049932 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | CapEx | Localization | IT - Internal | 19h | 0h | 19h | 2016-10-24 | 2016-11-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049933 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | CapEx | Localization | IT - Internal | 126h | 0h | 126h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 26 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049934 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | CapEx | Localization | IT - Internal | 7h | 0h | 7h | 2016-12-12 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049935 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | CapEx | Localization | IT - Internal | 15h | 0h | 15h | 2016-12-12 | 2016-12-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049936 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | CapEx | Localization | IT - Internal | 91h | 0h | 91h | 2016-12-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 22.5 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049937 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - PTM | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | CapEx | Localization | IT - Internal | 89h | 0h | 89h | 2017-01-23 | 2017-02-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049938 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | OpEx | Localization | IT - Internal | 70.5h | 0h | 70.5h | 2017-02-16 | 2017-02-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 54.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049939 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | CapEx | Localization | IT - Internal | 79.5h | 0h | 79.5h | 2016-12-20 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 22.5 | 30 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049940 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | CapEx | Localization | IT - Internal | 82h | 0h | 82h | 2016-11-14 | 2016-12-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049941 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | OpEx | Localization | IT - Internal | 36h | 0h | 36h | 2016-10-03 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049942 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTM - Run Tests | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | CapEx | Localization | IT - Internal | 60.5h | 0h | 60.5h | 2016-11-07 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049943 | No | Yes | No | Argentina | Argentina | 04-Test | OTC - SIT 2 - Break/Fix | RTR | FUN | SI | Onshore | Gimenez; Pamela | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049944 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | RTR | FUN | SI | Onshore | Gimenez; Pamela | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-29 | 2016-08-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049945 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | RTR | FUN | SI | Onshore | Gimenez; Pamela | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049946 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | SI | Onshore | Gimenez; Pamela | IBM | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2016-12-19 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049947 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | RTR | FUN | SI | Onshore | Gimenez; Pamela | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-01-30 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049948 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | RTR | FUN | SI | Onshore | Gimenez; Pamela | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-12-12 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049949 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | RTR | FUN | SI | Onshore | Gimenez; Pamela | IBM | Yes | CapEx | Localization | IT - External | 159h | 0h | 159h | 2016-12-05 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 44 | 27 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049950 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - RTR | RTR | FUN | SI | Onshore | Gimenez; Pamela | IBM | Yes | OpEx | Localization | IT - External | 340h | 0h | 340h | 2017-01-02 | 2017-03-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 49 | 49 | 55 | 33 | 55 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049951 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - RTR | RTR | FUN | SI | Onshore | Gimenez; Pamela | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049952 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-RTR | RTR | FUN | SI | Onshore | Gimenez; Pamela | IBM | Yes | OpEx | Localization | IT - External | 899h | 0h | 899h | 2017-03-20 | 2017-08-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 44 | 44 | 36 | 44 | 44 | 41 | 44 | 44 | 40 | 44 | 44 | 40 | 39 | 44 | 44 | 44 | 44 | 44 | 44 | 35 | 44 | 0 | 0 | 0 | 0 | 0
1049953 | No | Yes | Yes | Argentina | Argentina | 04-Test | Cutover Plan | PMO | PMO | SI | Onshore | Singh; Govind | IBM | Yes | CapEx | Localization | IT - External | 387h | 0h | 387h | 2016-08-08 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049954 | No | Yes | No | Argentina | Argentina | 04-Test | Work Instructions - Exercices DATA (technical writer + Dele) | CM | CM | SI | Offshore | Mathur; Shruti | IBM | Yes | OpEx | Localization | IT - External | 819h | 0h | 819h | 2016-09-19 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 45 | 45 | 27 | 45 | 36 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049955 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | OpEx | Localization | Business | 36h | 0h | 36h | 2016-09-22 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049956 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Validate | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | OpEx | Localization | Business | 25h | 0h | 25h | 2016-08-15 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049957 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | CapEx | Localization | Business | 40h | 0h | 40h | 2017-01-30 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049958 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | OpEx | Localization | Business | 29h | 0h | 29h | 2016-10-17 | 2016-11-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049959 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | OpEx | Localization | Business | 122h | 0h | 122h | 2016-10-07 | 2016-11-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049960 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | CapEx | Localization | Business | 32h | 0h | 32h | 2016-12-19 | 2016-12-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049961 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-LOG | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | OpEx | Localization | Business | 165h | 0h | 165h | 2017-03-20 | 2017-07-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 32 | 16 | 16 | 12 | 11 | 10 | 10 | 8 | 2 | 0 | 0 | 6 | 5 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049962 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Support | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | OpEx | Localization | Business | 21h | 0h | 21h | 2016-08-08 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049963 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG KT visit | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-08-14 | 2016-08-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049964 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | CapEx | Localization | Business | 163h | 0h | 163h | 2016-09-05 | 2016-10-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049965 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | OpEx | Localization | Business | 151h | 0h | 151h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049966 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | CapEx | Localization | Business | 152h | 0h | 152h | 2017-01-02 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 32 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049967 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049968 | No | No | Yes | Argentina | Argentina | 04-Test | LOG - SIT 2 - Run Tests | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | CapEx | Localization | Business | 29h | 0h | 29h | 2016-11-07 | 2016-11-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049969 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | CapEx | Localization | IT - Internal | 80h | 0h | 80h | 2017-01-09 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049970 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, team organization) | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-09-06 | 2016-09-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049971 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | OpEx | Localization | IT - Internal | 80h | 0h | 80h | 2017-02-20 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049972 | No | No | Yes | Argentina | Argentina | 04-Test | Development | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049973 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049974 | No | No | Yes | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049975 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Management | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049976 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 1 Load in QA (Accenture) - DM | MDG | DM | SI | Offshore | Cruz; Rommel | Accenture | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2016-06-27 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049977 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 1 Load in QA (Accenture) - DM | MDG | DM | SI | Offshore | Shah; Sanjay | Accenture | Yes | CapEx | Localization | IT - External | 148h | 0h | 148h | 2016-08-11 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049978 | No | Yes | No | Argentina | Argentina | 04-Test | SIT2 - Defect Fix (Accenture) - DM | MDG | DM | SI | Offshore | Shah; Sanjay | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049979 | No | Yes | No | Argentina | Argentina | 04-Test | SIT1 - Manage Defect (Accenture) - DM | MDG | DM | SI | Offshore | Shah; Sanjay | Accenture | Yes | CapEx | Localization | IT - External | 23h | 0h | 23h | 2016-09-12 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049980 | No | Yes | No | Argentina | Argentina | 04-Test | SIT1 - Defect Fix (Accenture) - DM | MDG | DM | SI | Offshore | Shah; Sanjay | Accenture | Yes | CapEx | Localization | IT - External | 148h | 0h | 148h | 2016-09-12 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049981 | No | Yes | No | Argentina | Argentina | 04-Test | SIT2 - Manage Defect (Accenture) - DM | MDG | DM | SI | Offshore | Shah; Sanjay | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049982 | No | Yes | No | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) (SI) - DM | MDG | DM | SI | Offshore | Shah; Sanjay | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-09-05 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049983 | No | Yes | No | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) (SI) - DM | MDG | DM | SI | Offshore | Cruz; Marc | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049984 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 1 Load in QA (Accenture) - DM | MDG | DM | SI | Offshore | Cruz; Marc | Accenture | Yes | CapEx | Localization | IT - External | 142h | 0h | 142h | 2016-06-27 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049985 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | ARG - Manage and execute communications | CM | CM | SI | Onshore | Shilpa; Patel | IBM | Yes | OpEx | Localization | IT - External | 99.6h | 0h | 99.6h | 2016-08-01 | 2016-09-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049986 | No | Yes | No | Argentina | Argentina | 04-Test | Performance testing and refresh | TAI | TAI | SI | Offshore | Formantes; Murphy | Accenture | Yes | CapEx | Localization | IT - External | 384h | 0h | 384h | 2016-10-24 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049987 | No | Yes | No | Argentina | Argentina | 04-Test | TEST - Technical Architecture and Infrastructure (gen) | TAI | TAI | SI | Offshore | Formantes; Murphy | Accenture | Yes | CapEx | Localization | IT - External | 180h | 0h | 180h | 2016-09-26 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049988 | No | Yes | No | Argentina | Argentina | 04-Test | TEST - Technical Architecture and Infrastructure (gen) | TAI | TAI | SI | Offshore | Nabayra; Ronald | Accenture | Yes | CapEx | Localization | IT - External | 180h | 0h | 180h | 2016-10-03 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049989 | No | Yes | No | Argentina | Argentina | 04-Test | Performance testing and refresh | TAI | TAI | SI | Offshore | Nabayra; Ronald | Accenture | Yes | CapEx | Localization | IT - External | 250h | 0h | 250h | 2016-10-24 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049990 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Performance testing write-off | TAI | TAI | SI | Offshore | Nabayra; Ronald | Accenture | Yes | CapEx | Localization | IT - External | 108h | 0h | 108h | 2016-12-12 | 2016-12-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049991 | No | Yes | No | Argentina | Argentina | 04-Test | TEST - Technical Architecture and Infrastructure (gen) | TAI | TAI | SI | Offshore | Espino; Mark | Accenture | Yes | CapEx | Localization | IT - External | 63h | 0h | 63h | 2016-10-05 | 2016-10-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049992 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Management (Hypercare) | CM | CM | Saputo | Onshore | Lochner; Andrea | Saputo | Yes | OpEx | Localization | IT - Internal | 40h | 0h | 40h | 2017-02-06 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049993 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Management (Cutover/Go-live) | CM | CM | Saputo | Onshore | Lochner; Andrea | Saputo | Yes | OpEx | Localization | IT - Internal | 270h | 0h | 270h | 2016-12-12 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 32 | 43 | 0 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049994 | No | No | Yes | Argentina | Argentina | 04-Test | Management | CM | CM | Saputo | Onshore | Lochner; Andrea | Saputo | Yes | OpEx | Localization | IT - Internal | 243h | 0h | 243h | 2016-10-03 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049995 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 1 Load in QA - DC | SEC | SEC | SI | Onshore | Kumar; Sathish | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-06-22 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049996 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | SEC | SEC | SI | Onshore | Kumar; Sathish | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049997 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT Defect Resolution | SEC | SEC | SI | Onshore | Kumar; Sathish | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049998 | No | Yes | No | Argentina | Argentina | 03-Design/Build | GRC AC - Build & UT | SEC | SEC | SI | Onshore | Kumar; Sathish | Accenture | Yes | CapEx | Localization | IT - External | 100h | 0h | 100h | 2016-09-12 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049999 | No | Yes | No | Argentina | Argentina | 03-Design/Build | SAP GRC PC - Build | SEC | SEC | SI | Onshore | Kumar; Sathish | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-04 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050000 | No | Yes | No | Argentina | Argentina | 03-Design/Build | SAP GRC PC - Design | SEC | SEC | SI | Onshore | Kumar; Sathish | Accenture | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2016-10-31 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050001 | No | Yes | No | Argentina | Argentina | 03-Design/Build | SAP GRC PC - UT | SEC | SEC | SI | Onshore | Kumar; Sathish | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-04 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050002 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | GRC AC - Cutover planning and Exucution | SEC | SEC | SI | Onshore | Kumar; Sathish | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-10-18 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050003 | No | Yes | No | Argentina | Argentina | 03-Design/Build | SAP GRC AC - Design | SEC | SEC | SI | Onshore | Kumar; Sathish | Accenture | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2016-09-12 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050004 | No | Yes | No | Argentina | Argentina | 03-Design/Build | SAP GRC PC - Analyze - SAP GRC PC Post Installation Steps | SEC | SEC | SI | Onshore | Kumar; Sathish | Accenture | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2016-10-31 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050005 | No | Yes | No | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Onshore | Silverman; Joshua | SAP | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050006 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | SI | Onshore | Silverman; Joshua | SAP | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050007 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Manage Hypercare | PMO | PMO | SI | Onshore | Paquay; Dominique | IBM | Yes | CapEx | Localization | IT - External | 284h | 0h | 284h | 2017-02-13 | 2017-03-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 84 | 60 | 0 | 0 | 36 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050008 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PMO | PMO | SI | Onshore | Paquay; Dominique | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050009 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | PMO | PMO | SI | Onshore | Paquay; Dominique | IBM | Yes | CapEx | Localization | IT - External | 84h | 0h | 84h | 2017-02-06 | 2017-02-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050010 | No | Yes | No | Argentina | Argentina | 04-Test | Cutover Plan | PMO | PMO | SI | Onshore | Paquay; Dominique | IBM | Yes | CapEx | Localization | IT - External | 488h | 0h | 488h | 2016-10-05 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050011 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Manage Dry Run Cut Over activities | PMO | PMO | SI | Onshore | Paquay; Dominique | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-12-12 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050012 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Manage PROD Cut Over activities | PMO | PMO | SI | Onshore | Paquay; Dominique | IBM | Yes | CapEx | Localization | IT - External | 337h | 0h | 337h | 2016-12-19 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 44 | 44 | 44 | 44 | 44 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050013 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Support Role Build and UT | SEC | SEC | SI | Onshore | Kothapalli; Omni | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-19 | 2016-09-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050014 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-SEC | SEC | SEC | SI | Onshore | Kothapalli; Omni | Accenture | Yes | OpEx | Localization | IT - External | 56h | 0h | 56h | 2017-03-13 | 2017-03-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050015 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 Defect Resolution | SEC | SEC | SI | Onshore | Kothapalli; Omni | Accenture | Yes | CapEx | Localization | IT - External | 126h | 0h | 126h | 2016-11-07 | 2016-12-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050016 | No | No | Yes | Argentina | Argentina | 04-Test | FUT Support Roles | SEC | SEC | SI | Onshore | Kothapalli; Omni | Accenture | Yes | CapEx | Localization | IT - External | 69h | 0h | 69h | 2016-10-31 | 2016-11-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050017 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | GRC AC - Cutover planning and Exucution | SEC | SEC | SI | Onshore | Kothapalli; Omni | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-18 | 2016-10-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050018 | No | No | Yes | Argentina | Argentina | 04-Test | PCR - 207 - Trade and Commission Rebate Role - Security | SEC | SEC | SI | Onshore | Kothapalli; Omni | Accenture | Yes | CapEx | Localization | IT - External | 13h | 0h | 13h | 2016-12-06 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050019 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Hypercare/support | SEC | SEC | SI | Onshore | Kothapalli; Omni | Accenture | Yes | OpEx | Localization | IT - External | 180h | 0h | 180h | 2017-02-06 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 48 | 40 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050020 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT Defect Resolution | SEC | SEC | SI | Onshore | Kothapalli; Omni | Accenture | Yes | CapEx | Localization | IT - External | 349h | 0h | 349h | 2016-12-05 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 32 | 40 | 40 | 40 | 40 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050021 | No | No | Yes | Argentina | Argentina | 04-Test | Work Instructions - Exercices DATA (technical writer + Dele) | CM | CM | SI | Offshore | Basak; Dipannita | IBM | Yes | OpEx | Localization | IT - External | 580h | 0h | 580h | 2016-11-07 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 45 | 45 | 45 | 45 | 18 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050022 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | LOG | FUN | SI | Onshore | Thippanna; Ashok | SAP | Yes | CapEx | Localization | IT - External | 176h | 0h | 176h | 2016-09-19 | 2016-12-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050023 | No | Yes | No | Argentina | Argentina | 04-Test | Prep PRD for performance testing | LOG | FUN | SI | Onshore | Thippanna; Ashok | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050024 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Validate | LOG | FUN | SI | Onshore | Thippanna; Ashok | SAP | Yes | OpEx | Localization | IT - External | 40h | 0h | 40h | 2016-10-31 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050025 | No | Yes | No | Argentina | Argentina | 04-Test | LOG - SIT 2 - Run Tests | LOG | FUN | SI | Onshore | Thippanna; Ashok | SAP | Yes | CapEx | Localization | IT - External | 128h | 0h | 128h | 2016-11-07 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050026 | No | Yes | No | Argentina | Argentina | 04-Test | LOG - SIT 2 - Manage Defects | LOG | FUN | SI | Onshore | Thippanna; Ashok | SAP | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2016-11-23 | 2016-11-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050027 | No | Yes | No | Argentina | Argentina | 04-Test | LOG - SIT 2 - Break/Fix | LOG | FUN | SI | Onshore | Thippanna; Ashok | SAP | Yes | CapEx | Localization | IT - External | 34h | 0h | 34h | 2016-11-21 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050028 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Prepare | LOG | FUN | SI | Onshore | Thippanna; Ashok | SAP | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-11 | 2016-07-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050029 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | LOG | FUN | SI | Onshore | Thippanna; Ashok | SAP | Yes | CapEx | Localization | IT - External | 172h | 0h | 172h | 2016-12-28 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 16 | 30 | 0 | 40 | 40 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050030 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | LOG | FUN | SI | Onshore | Thippanna; Ashok | SAP | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2016-12-05 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050031 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | LOG | FUN | SI | Onshore | Thippanna; Ashok | SAP | Yes | CapEx | Localization | IT - External | 64h | 0h | 64h | 2016-12-21 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050032 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | LOG | FUN | SI | Onshore | Thippanna; Ashok | SAP | Yes | CapEx | Localization | IT - External | 240h | 0h | 240h | 2017-02-06 | 2017-03-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050033 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | GRC AC - Cutover planning and Exucution | SEC | SEC | SI | Offshore | DeBlas; RahpRelly | Accenture | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2017-01-12 | 2017-01-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050034 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Hypercare/support | SEC | SEC | SI | Offshore | DeBlas; RahpRelly | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-01 | 2017-02-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050035 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 Defect Resolution | SEC | SEC | SI | Offshore | DeBlas; RahpRelly | Accenture | Yes | CapEx | Localization | IT - External | 60.25h | 0h | 60.25h | 2016-10-22 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050036 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT Defect Resolution | SEC | SEC | SI | Offshore | DeBlas; RahpRelly | Accenture | Yes | CapEx | Localization | IT - External | 38h | 0h | 38h | 2016-12-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 4 | 12.5 | 11 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050037 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Support Role Build and UT | SEC | SEC | SI | Offshore | DeBlas; RahpRelly | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-19 | 2016-09-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050038 | No | Yes | No | Argentina | Argentina | 04-Test | FUT Support Roles | SEC | SEC | SI | Offshore | DeBlas; RahpRelly | Accenture | Yes | CapEx | Localization | IT - External | 31.75h | 0h | 31.75h | 2016-10-17 | 2016-12-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050039 | No | Yes | No | Argentina | Argentina | 04-Test | Security Role FUT | SEC | SEC | SI | Offshore | DeBlas; RahpRelly | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-19 | 2016-09-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050040 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 Defect Resolution | SEC | SEC | SI | Offshore | DeBlas; RahpRelly | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-07 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050041 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Composite Role Build | SEC | SEC | SI | Offshore | DeBlas; RahpRelly | Accenture | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-09-19 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050042 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Derived Role Build | SEC | SEC | SI | Offshore | DeBlas; RahpRelly | Accenture | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2016-10-17 | 2016-10-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050043 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Master Role Build and UT | SEC | SEC | SI | Offshore | DeBlas; RahpRelly | Accenture | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-10-31 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050044 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Management (Hypercare) | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | CapEx | Localization | IT - External | 156h | 0h | 156h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 44 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050045 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Management (Cutover/Go-live) | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2017-01-23 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050046 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Redesing - Escalation | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | OpEx | Localization | IT - External | 32h | 0h | 32h | 2017-08-21 | 2017-08-25 | Yes |  | DMS |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0
1050047 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050048 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Break/Fix | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2016-12-01 | 2016-12-02 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050049 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 120h | 0h | 120h | 2016-12-05 | 2016-12-30 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050050 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2017-01-02 | 2017-01-13 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050051 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 48h | 0h | 48h | 2016-12-19 | 2017-01-18 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050052 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2017-01-17 | 2017-01-20 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050053 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - RTR | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | OpEx | Localization | IT - External | 209h | 0h | 209h | 2017-02-06 | 2017-03-24 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 30 | 23 | 20 | 56 | 2 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050054 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - RTR | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-02-06 | 2017-03-19 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050055 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-01-30 | 2017-02-03 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050056 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 91h | 0h | 91h | 2017-01-23 | 2017-04-09 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 4 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050057 | No | No | Yes | Argentina | Argentina | 06-Hypercare | DMS Argentina Production Support- RTR | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | OpEx | Localization | IT - External | 231h | 0h | 231h | 2017-03-27 | 2017-06-23 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 26 | 28 | 40 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050058 | No | No | Yes | Argentina | Argentina | 06-Hypercare | DMS Argentina Production Support- RTR | RTR | FUN | SI | Onshore | Strobel; Lars | SAP | Yes | OpEx | Localization | IT - External | 8h | 0h | 8h | 2017-04-18 | 2017-04-21 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050059 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | RTR | FUN | SI | Onshore | Strobel; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050060 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | RTR | FUN | SI | Onshore | Strobel; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050061 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - RTR | RTR | FUN | SI | Onshore | Strobel; Lars | SAP | Yes | OpEx | Localization | IT - External | 90h | 0h | 90h | 2017-02-13 | 2017-02-27 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 40 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050062 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - RTR | RTR | FUN | SI | Onshore | Strobel; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050063 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | RTR | FUN | SI | Onshore | Strobel; Lars | SAP | Yes | CapEx | Localization | IT - External | 96h | 0h | 96h | 2016-12-19 | 2017-01-23 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 24 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050064 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | RTR | FUN | SI | Onshore | Strobel; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050065 | No | No | Yes | Argentina | Argentina | 10-PCR | Argentina new cheese line-RTR | RTR | FUN | SI | Onshore | Strobel; Lars | SAP | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-04-25 | 2017-05-05 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050066 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | RTR | FUN | SI | Onshore | Strobel; Lars | SAP | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2017-01-23 | 2017-01-26 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050067 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Hypercare/support | SEC | SEC | SI | Offshore | Valencia; Jackie | Accenture | Yes | OpEx | Localization | IT - External | 240h | 0h | 240h | 2017-02-06 | 2017-03-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 42 | 36 | 27 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050068 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cutover Planning and Execution | SEC | SEC | SI | Offshore | Valencia; Jackie | Accenture | Yes | CapEx | Localization | IT - External | 261.5h | 0h | 261.5h | 2016-12-19 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 24 | 26 | 34 | 45 | 44.5 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050069 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | GRC AC - UAT Execution | SEC | SEC | SI | Offshore | Valencia; Jackie | Accenture | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-12-19 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050070 | No | No | Yes | Argentina | Argentina | 04-Test | GRC AC - SIT Execution | SEC | SEC | SI | Offshore | Valencia; Jackie | Accenture | Yes | CapEx | Localization | IT - External | 145h | 0h | 145h | 2016-11-07 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050071 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT Defect Resolution | SEC | SEC | SI | Offshore | Valencia; Jackie | Accenture | Yes | CapEx | Localization | IT - External | 16.5h | 0h | 16.5h | 2016-12-27 | 2017-01-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 3 | 8 | 2 | 0 | 0.5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050072 | No | No | Yes | Argentina | Argentina | 03-Design/Build | GRC AC - SIT Prep | SEC | SEC | SI | Offshore | Valencia; Jackie | Accenture | Yes | CapEx | Localization | IT - External | 305h | 0h | 305h | 2016-11-07 | 2017-04-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050073 | No | No | Yes | Argentina | Argentina | 04-Test | SoD Analysis and Remediation | SEC | SEC | SI | Offshore | Valencia; Jackie | Accenture | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2016-11-07 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050074 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Hypercare Support (Saputo) - DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | OpEx | Localization | IT - Internal | 134h | 0h | 134h | 2017-02-06 | 2017-02-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 38 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050075 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-MDG-(Saputo - DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | OpEx | Localization | IT - Internal | 343h | 0h | 343h | 2017-03-20 | 2017-06-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46.5 | 54.5 | 35.5 | 38.5 | 0 | 0 | 50.5 | 43.5 | 22.5 | 19 | 32.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050076 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Material Master Offline/Work Instructions (Saputo) - DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | OpEx | Localization | IT - Internal | 369.5h | 0h | 369.5h | 2016-11-14 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 29 | 31 | 32 | 44.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050077 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cutover - Dual Maintenance Argentina Materials (Saputo) - DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | OpEx | Localization | IT - Internal | 41h | 0h | 41h | 2017-01-13 | 2017-01-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050078 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Train-the-Trainer Materials (Saputo) - DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | OpEx | Localization | IT - Internal | 4h | 0h | 4h | 2017-01-11 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050079 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Hypercare Support - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050080 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | OpEx | Localization | IT - External | 45h | 0h | 45h | 2017-01-23 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050081 | No | Yes | No | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Onshore | Lu; Richard | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050082 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Onshore | Lu; Richard | Accenture | Yes | CapEx | Localization | IT - External | 180h | 0h | 180h | 2016-08-22 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050083 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Onshore | Lu; Richard | Accenture | Yes | CapEx | Localization | IT - External | 369h | 0h | 369h | 2016-12-05 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 27 | 45 | 45 | 36 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050084 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | SI | Onshore | Lu; Richard | Accenture | Yes | OpEx | Localization | IT - External | 171h | 0h | 171h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 36 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050085 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | PTP | FUN | SI | Onshore | Luna; Sandra | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050086 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - PTP - Run Tests | PTP | FUN | SI | Onshore | Luna; Sandra | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050087 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - PTP - Break/Fix | PTP | FUN | SI | Onshore | Luna; Sandra | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050088 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | PTP | FUN | SI | Onshore | Luna; Sandra | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050089 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | PTP | FUN | SI | Onshore | Luna; Sandra | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2016-11-29 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050090 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | PTP | FUN | SI | Onshore | Luna; Sandra | IBM | Yes | CapEx | Localization | IT - External | 198h | 0h | 198h | 2016-12-05 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 18 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050091 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTP | FUN | SI | Onshore | Luna; Sandra | IBM | Yes | CapEx | Localization | IT - External | 124h | 0h | 124h | 2016-12-26 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 36 | 0 | 0 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050092 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTP | FUN | SI | Onshore | Luna; Sandra | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050093 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTP | FUN | SI | Onshore | Luna; Sandra | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050094 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | PTP | FUN | SI | Onshore | Luna; Sandra | IBM | Yes | OpEx | Localization | IT - External | 100h | 0h | 100h | 2017-02-13 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050095 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | PTP | FUN | SI | Onshore | Luna; Sandra | IBM | Yes | CapEx | Localization | IT - External | 74h | 0h | 74h | 2017-03-01 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050096 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | PTP | FUN | SI | Onshore | Luna; Sandra | IBM | Yes | CapEx | Localization | IT - External | 96h | 0h | 96h | 2017-01-30 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050097 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTP | PTP | FUN | SI | Onshore | Luna; Sandra | IBM | Yes | OpEx | Localization | IT - External | 36h | 0h | 36h | 2017-03-20 | 2017-03-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050098 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | PTP | FUN | SI | Onshore | Luna; Sandra | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050099 | No | No | Yes | Argentina | Argentina | 04-Test | LOG - SIT 2 - Break/Fix | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 168h | 0h | 168h | 2016-11-14 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050100 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-17 | 2016-10-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050101 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | OpEx | Localization | IT - External | 40h | 0h | 40h | 2016-11-14 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050102 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050103 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-11-15 | 2016-12-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050104 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-11-07 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050105 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050106 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 175h | 0h | 175h | 2017-01-02 | 2017-01-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 24 | 30 | 53 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050107 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 67h | 0h | 67h | 2017-01-02 | 2017-01-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 29 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050108 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | OpEx | Localization | IT - External | 54h | 0h | 54h | 2016-12-01 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050109 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 298h | 0h | 298h | 2017-02-06 | 2017-03-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 84 | 90 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050110 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 62h | 0h | 62h | 2017-01-30 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050111 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-LOG | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | OpEx | Localization | IT - External | 74h | 0h | 74h | 2017-03-06 | 2017-07-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050112 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-06 | 2017-02-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050113 | No | No | Yes | Argentina | Argentina | 04-Test | SIT2 Preparation | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 24h | 0h | 24h | 2016-10-11 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050114 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | OpEx | Localization | IT - Internal | 31h | 0h | 31h | 2016-10-10 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050115 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | OpEx | Localization | IT - Internal | 227h | 0h | 227h | 2017-03-20 | 2017-08-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 8 | 9 | 7 | 20 | 22 | 16 | 16 | 19 | 10 | 9 | 29 | 17 | 20 | 0 | 0 | 0 | 0 | 0 | 3 | 7 | 6 | 0 | 0 | 0 | 0 | 0
1050116 | No | No | Yes | Argentina | Argentina | 03-Design/Build | FMEA Participation | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | OpEx | Localization | IT - Internal | 2h | 0h | 2h | 2016-10-10 | 2016-10-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050117 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | OpEx | Localization | IT - Internal | 43h | 0h | 43h | 2016-10-03 | 2016-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050118 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTM - Run Tests | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 114h | 0h | 114h | 2016-11-01 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050119 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 58h | 0h | 58h | 2016-11-15 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050120 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 17h | 0h | 17h | 2017-01-02 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050121 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | OpEx | Localization | IT - Internal | 123h | 0h | 123h | 2017-02-06 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 38 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050122 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 60h | 0h | 60h | 2017-02-10 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 26 | 8 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050123 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - PTM | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 125h | 0h | 125h | 2017-01-23 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050124 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTM - Break/Fix | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 107h | 0h | 107h | 2016-12-19 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 38 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050125 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 30.5h | 0h | 30.5h | 2016-09-27 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050126 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 64.4h | 0h | 64.4h | 2016-09-26 | 2016-10-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050127 | No | Yes | No | Argentina | Argentina | 04-Test | Training Prep | MDG | To Define | SI | Onshore | Manlapaz; Carmel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050128 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute Loads/Reports (Accenture) | MDG | To Define | SI | Onshore | Manlapaz; Carmel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-28 | 2016-11-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050129 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover (Accenture) | MDG | To Define | SI | Onshore | Manlapaz; Carmel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050130 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Data verification Signoff sheets | MDG | To Define | SI | Onshore | Manlapaz; Carmel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-29 | 2016-11-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050131 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT Prep | MDG | To Define | SI | Onshore | Manlapaz; Carmel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050132 | No | Yes | No | Argentina | Argentina | 04-Test | SIT2 - Defect Fix (Accenture) | MDG | To Define | SI | Onshore | Manlapaz; Carmel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050133 | No | Yes | No | Argentina | Argentina | 04-Test | M1 - Execute loads | MDG | To Define | SI | Onshore | Manlapaz; Carmel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050134 | No | Yes | No | Argentina | Argentina | 04-Test | SIT1 - Defect Fix (Accenture) - DM | MDG | To Define | SI | Onshore | Manlapaz; Carmel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050135 | No | Yes | No | Argentina | Argentina | 04-Test | M2 - Execute pre validation | MDG | To Define | SI | Onshore | Manlapaz; Carmel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050136 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Execute loads/ reports | MDG | To Define | SI | Onshore | Manlapaz; Carmel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050137 | No | Yes | No | Argentina | Argentina | 04-Test | M2 - Execute loads/reports | MDG | To Define | SI | Onshore | Manlapaz; Carmel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050138 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Execute pre validation | MDG | To Define | SI | Onshore | Manlapaz; Carmel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050139 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Manage UAT Execution | Test | Test | Saputo | Onshore | Lee; Ryan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050140 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-Test | Test | Test | Saputo | Onshore | Lee; Ryan | Saputo | Yes | OpEx | Localization | IT - Internal | 5h | 0h | 5h | 2017-03-20 | 2017-03-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050141 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTM | FUN | Saputo | Onshore | Atkins; Aaon | Saputo | Yes | OpEx | Localization | IT - Internal | 4h | 0h | 4h | 2017-02-06 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050142 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | Saputo | Onshore | Atkins; Aaon | Saputo | Yes | OpEx | Localization | IT - Internal | 274h | 0h | 274h | 2017-03-21 | 2017-08-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 30 | 38 | 32 | 28 | 29 | 0 | 41 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050143 | No | Yes | No | Argentina | Argentina | 04-Test | Work Instructions - Exercices DATA (technical writer + Dele) | CM | CM | SI | Offshore | Dutta; Reenia | IBM | Yes | OpEx | Localization | IT - External | 897h | 0h | 897h | 2016-09-28 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 45 | 45 | 45 | 36 | 27 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050144 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050145 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-03 | 2016-10-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050146 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050147 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - PTM | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 81h | 0h | 81h | 2017-01-23 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050148 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 160h | 0h | 160h | 2017-02-13 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050149 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 31h | 0h | 31h | 2017-01-09 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 10 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050150 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050151 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Onshore | Liu; Changning | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050152 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Onshore | Liu; Changning | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050153 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Onshore | Liu; Changning | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-09-19 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050154 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Onshore | Liu; Changning | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050155 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-LOG | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | OpEx | Localization | IT - Internal | 224h | 0h | 224h | 2017-03-06 | 2017-04-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 68 | 40 | 20 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050156 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | OpEx | Localization | IT - Internal | 142h | 0h | 142h | 2017-02-03 | 2017-03-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 44 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050157 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | CapEx | Localization | IT - Internal | 109h | 0h | 109h | 2017-01-23 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050158 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050159 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | CapEx | Localization | IT - Internal | 210h | 0h | 210h | 2016-12-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 40 | 48 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050160 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Manage Defects | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | CapEx | Localization | IT - Internal | 43h | 0h | 43h | 2016-12-12 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050161 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050162 | No | No | Yes | Argentina | Argentina | 04-Test | LOG - SIT 2 - Break/Fix | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | CapEx | Localization | IT - Internal | 161h | 0h | 161h | 2016-11-21 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050163 | No | No | Yes | Argentina | Argentina | 10-PCR | Argentina new cheese line-LOG | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050164 | No | No | Yes | Argentina | Argentina |  | 03-Release 1.1 | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | OpEx | Localization | IT - Internal | 80h | 0h | 80h | 2017-02-06 | 2017-02-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050165 | No | No | Yes | Argentina | Argentina |  | 04-Release 1.2 | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050166 | No | No | Yes | Argentina | Argentina |  | 05-Release 1.3 | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-24 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050167 | No | No | Yes | Argentina | Argentina |  | 06-Release 1.4 | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-10 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050168 | No | No | Yes | Argentina | Argentina |  | 07-Release 1.5 | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-24 | 2017-03-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050169 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Bhowmick; Kallol | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050170 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Bhowmick; Kallol | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050171 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Bhowmick; Kallol | IBM | Yes | CapEx | Localization | IT - External | 81h | 0h | 81h | 2016-09-12 | 2016-09-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050172 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Bhowmick; Kallol | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050173 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | Bhowmick; Kallol | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-09 | 2016-05-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050174 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Offshore | Bhowmick; Kallol | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-13 | 2016-04-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050175 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | LOG | FUN | SI | Offshore | Chauhan; Rajesh | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050176 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | LOG | FUN | SI | Offshore | Chauhan; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050177 | No | Yes | No | Argentina | Argentina | 04-Test | Development | LOG | FUN | SI | Offshore | Chauhan; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 35h | 0h | 35h | 2016-09-06 | 2016-09-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050178 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | LOG | FUN | SI | Offshore | Chauhan; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050179 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Unit testing Configuration Documentation | LOG | FUN | SI | Offshore | Chauhan; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2016-08-22 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050180 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Configuration | LOG | FUN | SI | Offshore | Chauhan; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-08-15 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050181 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | LOG | FUN | SI | Offshore | Chauhan; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 212h | 0h | 212h | 2016-09-12 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050182 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Prepare | LOG | FUN | SI | Offshore | Chauhan; Rajesh | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-11 | 2016-07-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050183 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Support | LOG | FUN | SI | Offshore | Chauhan; Rajesh | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-15 | 2016-07-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050184 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | LOG | FUN | SI | Offshore | Chauhan; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050185 | No | Yes | No | Argentina | Argentina | 04-Test | Prep PRD for performance testing | LOG | FUN | SI | Offshore | Chauhan; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050186 | No | Yes | No | Argentina | Argentina | 04-Test | LOG - SIT 2 - Break/Fix | LOG | FUN | SI | Offshore | Chauhan; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050187 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | LOG | FUN | SI | Offshore | Chauhan; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-15 | 2016-11-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050188 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - Prep | LOG | FUN | SI | Offshore | Chauhan; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050189 | No | Yes | No | Argentina | Argentina | 04-Test | LOG - SIT 2 - Run Tests | LOG | FUN | SI | Offshore | Chauhan; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050190 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | LOG | FUN | SI | Offshore | Chauhan; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050191 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | LOG | FUN | SI | Offshore | Chauhan; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050192 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | LOG | FUN | SI | Offshore | Chauhan; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050193 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | LOG | FUN | SI | Offshore | Chauhan; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050194 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | SI | Offshore | Chauhan; Rajesh | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-01 | 2016-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050195 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Prepare | LOG | FUN | SI | Offshore | Chauhan; Rajesh | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-03 | 2016-09-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050196 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | LOG | FUN | SI | Offshore | Chauhan; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2016-10-11 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050197 | No | No | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - RTR | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2017-02-08 | 2017-03-15 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 4 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050198 | No | No | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - RTR | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050199 | No | No | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050200 | No | No | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050201 | No | No | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050202 | No | No | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050203 | No | No | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050204 | No | No | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2016-12-15 | 2016-12-15 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050205 | No | No | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Break/Fix | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-25 | 2016-10-25 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050206 | No | No | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Manage Defects | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050207 | No | No | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Run Tests | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050208 | No | No | No | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050209 | No | No | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050210 | No | No | No | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | CapEx | Localization | IT - External | 104h | 0h | 104h | 2016-09-05 | 2016-12-02 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050211 | No | No | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Prep | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050212 | No | No | No | Argentina | Argentina | 04-Test | Mock2 - Validate | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050213 | No | No | No | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050214 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover Steps | TAI | TAI | SI | Offshore | Lledo; Philip | Accenture | Yes | CapEx | Localization | IT - External | 82h | 0h | 82h | 2017-01-23 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050215 | No | No | Yes | Argentina | Argentina | 04-Test | Project SAP Environment Support | TAI | TAI | SI | Offshore | Lledo; Philip | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050216 | No | No | Yes | Argentina | Argentina | 04-Test | Performance testing and refresh | TAI | TAI | SI | Offshore | Lledo; Philip | Accenture | Yes | CapEx | Localization | IT - External | 19h | 0h | 19h | 2016-11-14 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050217 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Support Hypercare | TAI | TAI | SI | Offshore | Lledo; Philip | Accenture | Yes | CapEx | Localization | IT - External | 151h | 0h | 151h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 42 | 40 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050218 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Technical Architecture and Infrastructure (gen) | TAI | TAI | SI | Offshore | Lledo; Philip | Accenture | Yes | CapEx | Localization | IT - External | 52.5h | 0h | 52.5h | 2016-09-19 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050219 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-MDG-DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | OpEx | Localization | IT - Internal | 3h | 0h | 3h | 2017-04-26 | 2017-04-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050220 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 112h | 0h | 112h | 2016-10-03 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050221 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-OTC | OTC | FUN | SI | Onshore | Nieva; Ricardo | Accenture | Yes | OpEx | Localization | IT - External | 537h | 0h | 537h | 2017-03-06 | 2017-07-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 32 | 40 | 40 | 24 | 40 | 40 | 32 | 40 | 20 | 20 | 20 | 16 | 0 | 32 | 32 | 29 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050222 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | OTC | FUN | SI | Onshore | Nieva; Ricardo | Accenture | Yes | CapEx | Localization | IT - External | 102h | 0h | 102h | 2017-01-09 | 2017-01-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 20 | 40 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050223 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | OTC | FUN | SI | Onshore | Nieva; Ricardo | Accenture | Yes | OpEx | Localization | IT - External | 166h | 0h | 166h | 2017-02-06 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 46 | 0 | 28 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050224 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | OTC | FUN | SI | Onshore | Nieva; Ricardo | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050225 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - OTC | OTC | FUN | SI | Onshore | Nieva; Ricardo | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-01-30 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050226 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | OpEx | Localization | IT - External | 49.5h | 0h | 49.5h | 2017-01-23 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050227 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Hypercare Support - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050228 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | LOG | FUN | SI | Onshore | Steve; Leslie | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-12-19 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050229 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | LOG | FUN | SI | Onshore | Steve; Leslie | IBM | Yes | CapEx | Localization | IT - External | 131h | 0h | 131h | 2016-09-06 | 2016-10-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050230 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Support | LOG | FUN | SI | Onshore | Steve; Leslie | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-15 | 2016-07-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050231 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Manage Defects | LOG | FUN | SI | Onshore | Steve; Leslie | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-09-12 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050232 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Support | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050233 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-11 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050234 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 56h | 0h | 56h | 2016-09-12 | 2016-12-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050235 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-09-06 | 2016-10-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050236 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 70h | 0h | 70h | 2016-09-06 | 2016-10-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050237 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Manage Defects | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 19h | 0h | 19h | 2017-01-02 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050238 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 111h | 0h | 111h | 2016-12-12 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 12 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050239 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2016-12-27 | 2016-12-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050240 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2017-02-06 | 2017-02-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050241 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 135h | 0h | 135h | 2017-02-06 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 59 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050242 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - Prep | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2016-11-06 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050243 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - Manage Defects | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050244 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTP - Break/Fix | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 79h | 0h | 79h | 2016-11-14 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050245 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | OpEx | Localization | IT - External | 11h | 0h | 11h | 2016-09-19 | 2016-09-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050246 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-03 | 2016-10-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050247 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTP | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | OpEx | Localization | IT - External | 56h | 0h | 56h | 2017-04-10 | 2017-05-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050248 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 158h | 0h | 158h | 2017-01-09 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 20 | 30 | 44 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050249 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 14h | 0h | 14h | 2017-02-03 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050250 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | OpEx | Localization | IT - External | 67h | 0h | 67h | 2017-02-13 | 2017-03-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 11 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050251 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Manage Defects | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 7h | 0h | 7h | 2016-10-03 | 2016-10-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050252 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | OpEx | Localization | IT - External | 278h | 0h | 278h | 2017-03-06 | 2017-07-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 18 | 15 | 15 | 0 | 16 | 17 | 0 | 24 | 44 | 8 | 8 | 8 | 10 | 8 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050253 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2017-01-02 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050254 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Value Realization Monitoring | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050255 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Plan activities to create FMEA | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | OpEx | Localization | IT - Internal | 20h | 0h | 20h | 2016-08-15 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050256 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Create FMEA overview presentation | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | OpEx | Localization | IT - Internal | 20h | 0h | 20h | 2016-08-15 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050257 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Planning - FMEA | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | OpEx | Localization | IT - Internal | 80h | 0h | 80h | 2016-08-22 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050258 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | FMEA - Implementation | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | OpEx | Localization | IT - Internal | 107h | 0h | 107h | 2016-12-05 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050259 | No | Yes | No | Argentina | Argentina | 04-Test | FMEA - Development | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | OpEx | Localization | IT - Internal | 232h | 0h | 232h | 2016-09-12 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050260 | No | Yes | No | Argentina | Argentina | 04-Test | FMEA - Implementation | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | OpEx | Localization | IT - Internal | 240h | 0h | 240h | 2016-10-24 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050261 | No | Yes | No | Argentina | Argentina | 04-Test | FMEA - Sustainning | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-12-02 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050262 | No | Yes | No | Argentina | Argentina | 04-Test | FMEA - Planning | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | OpEx | Localization | IT - Internal | 32h | 0h | 32h | 2016-09-06 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050263 | No | Yes | No | Argentina | Argentina | 06-Hypercare | FMEA plan exectuion and Monitoring | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | OpEx | Localization | IT - Internal | 210h | 0h | 210h | 2017-02-06 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 85 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050264 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | FMEA plan exectuion and Monitoring | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | OpEx | Localization | IT - Internal | 288h | 0h | 288h | 2016-12-19 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 29 | 40 | 40 | 40 | 34 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050265 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | PTM | FUN | SI | Onshore | Arce; Hugo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050266 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | PTM | FUN | SI | Onshore | Arce; Hugo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050267 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTM | FUN | SI | Onshore | Arce; Hugo | IBM | Yes | CapEx | Localization | IT - External | 176h | 0h | 176h | 2016-12-26 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 44 | 0 | 44 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050268 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTM | FUN | SI | Onshore | Arce; Hugo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-06 | 2016-12-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050269 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | PTM | FUN | SI | Onshore | Arce; Hugo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050270 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | PTM | FUN | SI | Onshore | Arce; Hugo | IBM | Yes | CapEx | Localization | IT - External | 176h | 0h | 176h | 2016-12-05 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050271 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | PTM | FUN | SI | Onshore | Arce; Hugo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050272 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | SI | Onshore | Arce; Hugo | IBM | Yes | CapEx | Localization | IT - External | 115h | 0h | 115h | 2017-02-13 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050273 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | PTM | FUN | SI | Onshore | Arce; Hugo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050274 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTM | FUN | SI | Onshore | Arce; Hugo | IBM | Yes | OpEx | Localization | IT - External | 103h | 0h | 103h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050275 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - PTM | PTM | FUN | SI | Onshore | Arce; Hugo | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-01-30 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050276 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - PTM | PTM | FUN | SI | Onshore | Arce; Hugo | IBM | Yes | CapEx | Localization | IT - External | 148h | 0h | 148h | 2016-05-31 | 2016-08-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050277 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - PTM | PTM | FUN | SI | Onshore | Arce; Hugo | IBM | Yes | CapEx | Localization | IT - External | 162h | 0h | 162h | 2016-05-31 | 2016-08-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050278 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Support | PTM | FUN | SI | Onshore | Arce; Hugo | IBM | Yes | OpEx | Localization | IT - External | 15h | 0h | 15h | 2016-10-11 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050279 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Validate | PTM | FUN | SI | Onshore | Arce; Hugo | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050280 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - PTM - Run Tests | PTM | FUN | SI | Onshore | Arce; Hugo | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2016-11-07 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050281 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG KT visit | PTM | FUN | SI | Onshore | Arce; Hugo | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-08-15 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050282 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTM | FUN | SI | Onshore | Arce; Hugo | IBM | Yes | CapEx | Localization | IT - External | 108h | 0h | 108h | 2016-09-12 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050283 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTM | FUN | SI | Onshore | Arce; Hugo | IBM | Yes | OpEx | Localization | IT - External | 24h | 0h | 24h | 2016-09-12 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050284 | No | Yes | No | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTM | FUN | SI | Onshore | Arce; Hugo | IBM | Yes | CapEx | Localization | IT - External | 92h | 0h | 92h | 2016-11-02 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050285 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Support | PTM | FUN | SI | Onshore | Arce; Hugo | IBM | Yes | OpEx | Localization | IT - External | 24h | 0h | 24h | 2016-08-08 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050286 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Data collection templates (DCT) - Explain and collect | PTM | FUN | SI | Onshore | Arce; Hugo | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2016-08-08 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050287 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Validate | PTM | FUN | SI | Onshore | Arce; Hugo | IBM | Yes | OpEx | Localization | IT - External | 24h | 0h | 24h | 2016-08-29 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050288 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PTM | FUN | SI | Onshore | Arce; Hugo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050289 | No | No | Yes | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Bhat; Lavleen | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050290 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | SI | Offshore | Bhat; Lavleen | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050291 | No | Yes | Yes | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Ambekar; Shilpa | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050292 | No | Yes | Yes | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Ambekar; Shilpa | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050293 | No | Yes | Yes | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Ambekar; Shilpa | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050294 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Ambekar; Shilpa | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050295 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Onshore | Velez; Edwin | IBM | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2016-09-12 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050296 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Onshore | Velez; Edwin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050297 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Onshore | Velez; Edwin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050298 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Onshore | Velez; Edwin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050299 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Onshore | Velez; Edwin | IBM | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2016-07-11 | 2016-07-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050300 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Onshore | Velez; Edwin | IBM | Yes | CapEx | Localization | IT - External | 203h | 0h | 203h | 2016-07-04 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050301 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 56h | 0h | 56h | 2017-01-30 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050302 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050303 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 22h | 0h | 22h | 2016-12-19 | 2017-01-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050304 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050305 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Prep | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050306 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Run Tests | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050307 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Manage Defects | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050308 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Break/Fix | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-25 | 2016-10-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050309 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050310 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050311 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 328h | 0h | 328h | 2016-12-05 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 33 | 45 | 39 | 56 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050312 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - RTR | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 347h | 0h | 347h | 2017-02-06 | 2017-03-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 43 | 46 | 47 | 80 | 61 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050313 | No | Yes | Yes | Argentina | Argentina | 04-Test | Work Instructions - Exercices DATA (technical writer + Dele) | CM | CM | SI | Offshore | Banerjee; Roopkatha | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-06 | 2016-09-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050314 | No | Yes | No | Argentina | Argentina | 04-Test | Work Instructions - Exercices DATA (technical writer + Dele) | CM | CM | SI | Offshore | Kundu; Lakshmi | IBM | Yes | OpEx | Localization | IT - External | 859h | 0h | 859h | 2016-09-06 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 45 | 45 | 45 | 36 | 27 | 18 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050315 | No | Yes | No | Argentina | Argentina | 04-Test | Work Instructions - Exercices DATA (technical writer + Dele) | CM | CM | SI | Offshore | Roy; Moon | IBM | Yes | OpEx | Localization | IT - External | 513h | 0h | 513h | 2016-09-19 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050316 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Revil; Dianne | Accenture | Yes | CapEx | Localization | IT - External | 198h | 0h | 198h | 2017-01-16 | 2017-02-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 0 | 0 | 45 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050317 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | SI | Offshore | Revil; Dianne | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050318 | No | No | Yes | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Revil; Dianne | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050319 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | Revil; Dianne | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050320 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT Defect Resolution | SEC | SEC | SI | Onshore | Vanderveer; Monina | Accenture | Yes | CapEx | Localization | IT - External | 78h | 0h | 78h | 2016-12-15 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 14 | 22 | 26 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050321 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | GRC AC - Cutover planning and Exucution | SEC | SEC | SI | Onshore | Vanderveer; Monina | Accenture | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-10-18 | 2017-01-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050322 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Hypercare/support | SEC | SEC | SI | Onshore | Vanderveer; Monina | Accenture | Yes | OpEx | Localization | IT - External | 156h | 0h | 156h | 2017-02-06 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 1 | 40 | 40 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050323 | No | No | Yes | Argentina | Argentina | 04-Test | FUT Support Roles | SEC | SEC | SI | Onshore | Vanderveer; Monina | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-17 | 2016-10-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050324 | No | No | Yes | Argentina | Argentina | 04-Test | Project Management and Planning for SEC | SEC | SEC | SI | Onshore | Vanderveer; Monina | Accenture | Yes | CapEx | Localization | IT - External | 85h | 0h | 85h | 2016-09-26 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050325 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 Defect Resolution | SEC | SEC | SI | Onshore | Vanderveer; Monina | Accenture | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2016-10-22 | 2016-11-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050326 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Master Role Build and UT | SEC | SEC | SI | Onshore | Vanderveer; Monina | Accenture | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2016-09-26 | 2016-09-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050327 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Composite Role Build | SEC | SEC | SI | Onshore | Vanderveer; Monina | Accenture | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-10-11 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050328 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Security Design Workshops | SEC | SEC | SI | Onshore | Vanderveer; Monina | Accenture | Yes | CapEx | Localization | IT - External | 26h | 0h | 26h | 2016-09-27 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050329 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Support Role Build and UT | SEC | SEC | SI | Onshore | Vanderveer; Monina | Accenture | Yes | CapEx | Localization | IT - External | 56h | 0h | 56h | 2016-11-03 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050330 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cutover Planning and Execution | SEC | SEC | SI | Onshore | Vanderveer; Monina | Accenture | Yes | CapEx | Localization | IT - External | 358h | 0h | 358h | 2016-10-03 | 2017-03-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 14 | 22 | 22 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050331 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Support Role Design | SEC | SEC | SI | Onshore | Vanderveer; Monina | Accenture | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2016-09-29 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050332 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Composite Role Design | SEC | SEC | SI | Onshore | Vanderveer; Monina | Accenture | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2016-09-19 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050333 | No | No | Yes | Argentina | Argentina | 04-Test | Security Role FUT | SEC | SEC | SI | Onshore | Vanderveer; Monina | Accenture | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2016-09-19 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050334 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Management (Cutover/Go-live) | SEC | SEC | SI | Onshore | Vanderveer; Monina | Accenture | Yes | CapEx | Localization | IT - External | 48h | 0h | 48h | 2016-11-14 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050335 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Management (Hypercare) | SEC | SEC | SI | Onshore | Vanderveer; Monina | Accenture | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-02-06 | 2017-02-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050336 | No | Yes | Yes | Argentina | Argentina | 04-Test | Manage SIT2 Execution | Test | Test | SI | Onshore | Ganti; Chax | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050337 | No | Yes | Yes | Argentina | Argentina | 04-Test | Manage SIT2 Execution local (ARG) | Test | Test | SI | Onshore | Ganti; Chax | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050338 | No | Yes | Yes | Argentina | Argentina | 04-Test | Manage SIT1 Prep (data, transports) | Test | Test | SI | Onshore | Ganti; Chax | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2016-08-29 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050339 | No | Yes | Yes | Argentina | Argentina | 04-Test | Manage SIT1 Execution local (ARG) | Test | Test | SI | Onshore | Ganti; Chax | IBM | Yes | CapEx | Localization | IT - External | 120h | 0h | 120h | 2016-09-19 | 2016-10-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050340 | No | Yes | Yes | Argentina | Argentina | 04-Test | Manage SIT2 Prep (data, transports) | Test | Test | SI | Onshore | Ganti; Chax | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050341 | No | Yes | Yes | Argentina | Argentina | 04-Test | Manage SIT1 Execution | Test | Test | SI | Onshore | Ganti; Chax | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-10-03 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050342 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Verma; Mamta | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050343 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Verma; Mamta | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050344 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Verma; Mamta | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-09-26 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050345 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Verma; Mamta | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050346 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | Saputo | Onshore | Pavlovski; Victor | Saputo | Yes | CapEx | Localization | Business | 150h | 0h | 150h | 2017-02-13 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 64 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050347 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - PTM | PTM | FUN | Saputo | Onshore | Pavlovski; Victor | Saputo | Yes | CapEx | Localization | Business | 55h | 0h | 55h | 2017-01-09 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050348 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTM | FUN | Saputo | Onshore | Pavlovski; Victor | Saputo | Yes | CapEx | Localization | Business | 280h | 0h | 280h | 2016-12-06 | 2017-01-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 42 | 43 | 33 | 44 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050349 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTM | FUN | Saputo | Onshore | Pavlovski; Victor | Saputo | Yes | OpEx | Localization | Business | 172h | 0h | 172h | 2017-01-23 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 10 | 50 | 0 | 0 | 48 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050350 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | PTM | FUN | Saputo | Onshore | Pavlovski; Victor | Saputo | Yes | CapEx | Localization | Business | 10h | 0h | 10h | 2016-12-05 | 2016-12-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050351 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | PTM | FUN | Saputo | Onshore | Pavlovski; Victor | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-10-03 | 2016-10-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050352 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTM - Run Tests | PTM | FUN | Saputo | Onshore | Pavlovski; Victor | Saputo | Yes | CapEx | Localization | Business | 75.5h | 0h | 75.5h | 2016-10-24 | 2016-11-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050353 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTM | FUN | Saputo | Onshore | Pavlovski; Victor | Saputo | Yes | CapEx | Localization | Business | 8h | 0h | 8h | 2016-10-11 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050354 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | PTM | FUN | Saputo | Onshore | Pavlovski; Victor | Saputo | Yes | OpEx | Localization | Business | 33.5h | 0h | 33.5h | 2016-10-17 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050355 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | Saputo | Onshore | Pavlovski; Victor | Saputo | Yes | OpEx | Localization | Business | 160h | 0h | 160h | 2017-03-13 | 2017-08-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 18 | 21 | 12 | 0 | 12 | 28 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 10 | 8 | 6 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050356 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | PTM | FUN | Saputo | Onshore | Pavlovski; Victor | Saputo | Yes | OpEx | Localization | Business | 8h | 0h | 8h | 2016-10-11 | 2016-11-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050357 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTM | FUN | Saputo | Onshore | Pavlovski; Victor | Saputo | Yes | CapEx | Localization | Business | 80.5h | 0h | 80.5h | 2016-09-12 | 2016-09-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050358 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTM | FUN | Saputo | Onshore | Pavlovski; Victor | Saputo | Yes | OpEx | Localization | Business | 39h | 0h | 39h | 2016-09-12 | 2016-10-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050359 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | SI | Onshore | Kuhnmuench; Gretchen | Accenture | Yes | OpEx | Localization | IT - External | 266h | 0h | 266h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 84 | 52 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050360 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | SI | Onshore | Kuhnmuench; Gretchen | Accenture | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-01-30 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050361 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-LOG | LOG | FUN | SI | Onshore | Kuhnmuench; Gretchen | Accenture | Yes | OpEx | Localization | IT - External | 646h | 0h | 646h | 2017-03-06 | 2017-07-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 34 | 44 | 40 | 24 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 30 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050362 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | SI | Onshore | Laferrara; Melisa | Accenture | Yes | OpEx | Localization | IT - External | 592.5h | 0h | 592.5h | 2017-03-06 | 2017-07-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 32 | 40 | 40 | 24 | 0 | 0 | 32 | 40 | 40 | 32 | 40 | 36 | 32.5 | 21 | 31 | 38 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050363 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - PTM | PTM | FUN | SI | Onshore | Laferrara; Melisa | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-01-30 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050364 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTM | FUN | SI | Onshore | Laferrara; Melisa | Accenture | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2017-01-16 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050365 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTM | FUN | SI | Onshore | Laferrara; Melisa | Accenture | Yes | OpEx | Localization | IT - External | 90h | 0h | 90h | 2017-02-06 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050366 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | SI | Onshore | Laferrara; Melisa | Accenture | Yes | CapEx | Localization | IT - External | 79h | 0h | 79h | 2017-02-13 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 48 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050367 | No | Yes | Yes | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Taneja; Charushree | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050368 | No | Yes | Yes | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Taneja; Charushree | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050369 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Taneja; Charushree | IBM | Yes | CapEx | Localization | IT - External | 46h | 0h | 46h | 2016-08-22 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050370 | No | Yes | Yes | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Taneja; Charushree | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050371 | No | Yes | No | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTM | FUN | SI | Onshore | Dirndorfer; Johann | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-06 | 2016-09-06 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050372 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Manage Hypercare | Test | Test | SI | Onshore | Wolk; Rob | IBM | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-02-13 | 2017-02-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050373 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Manage UAT Execution | Test | Test | SI | Onshore | Wolk; Rob | IBM | Yes | CapEx | Localization | IT - External | 168h | 0h | 168h | 2016-12-05 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050374 | No | Yes | No | Argentina | Argentina | 04-Test | Manage SIT2 Execution | Test | Test | SI | Onshore | Wolk; Rob | IBM | Yes | CapEx | Localization | IT - External | 283h | 0h | 283h | 2016-10-24 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050375 | No | Yes | No | Argentina | Argentina | 04-Test | Manage SIT2 Execution local (ARG) | Test | Test | SI | Onshore | Wolk; Rob | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050376 | No | Yes | No | Argentina | Argentina | 04-Test | Manage SIT1 Execution | Test | Test | SI | Onshore | Wolk; Rob | IBM | Yes | CapEx | Localization | IT - External | 165h | 0h | 165h | 2016-09-21 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050377 | No | Yes | No | Argentina | Argentina | 04-Test | Manage SIT1 Execution local (ARG) | Test | Test | SI | Onshore | Wolk; Rob | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-19 | 2016-09-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050378 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Value Realization Monitoring | CM | CM | Saputo | Onshore | Goldstein; Evan | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050379 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Business Readiness Execution & Monitoring | CM | CM | Saputo | Onshore | Goldstein; Evan | Saputo | Yes | OpEx | Localization | IT - Internal | 20h | 0h | 20h | 2016-12-05 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050380 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Communication plan execution and monitoring | CM | CM | Saputo | Onshore | Goldstein; Evan | Saputo | Yes | OpEx | Localization | IT - Internal | 225h | 0h | 225h | 2016-12-19 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 21 | 24 | 40 | 40 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050381 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Communication plan execution and monitoring | CM | CM | Saputo | Onshore | Goldstein; Evan | Saputo | Yes | OpEx | Localization | IT - Internal | 138h | 0h | 138h | 2017-02-06 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 35 | 28 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050382 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-CM | CM | CM | Saputo | Onshore | Goldstein; Evan | Saputo | Yes | OpEx | Localization | IT - Internal | 63.42h | 0h | 63.42h | 2017-03-20 | 2017-07-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0.5 | 1 | 1 | 0 | 15 | 3 | 5.92 | 10 | 3 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050383 | No | No | Yes | Argentina | Argentina | 04-Test | Communication plan execution and monitoring | CM | CM | Saputo | Onshore | Goldstein; Evan | Saputo | Yes | OpEx | Localization | IT - Internal | 308.5h | 0h | 308.5h | 2016-09-26 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050384 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-LOG | LOG | FUN | SI | Onshore | DelValleLeal; JuanManuel | IBM | Yes | OpEx | Localization | IT - External | 64h | 0h | 64h | 2017-03-06 | 2017-03-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050385 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | LOG | FUN | SI | Onshore | DelValleLeal; JuanManuel | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2017-01-16 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050386 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT Prep - LOG | LOG | FUN | SI | Onshore | DelValleLeal; JuanManuel | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2016-11-29 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050387 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Manage Defects | LOG | FUN | SI | Onshore | DelValleLeal; JuanManuel | IBM | Yes | CapEx | Localization | IT - External | 42h | 0h | 42h | 2016-12-05 | 2016-12-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050388 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | LOG | FUN | SI | Onshore | DelValleLeal; JuanManuel | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050389 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | LOG | FUN | SI | Onshore | DelValleLeal; JuanManuel | IBM | Yes | CapEx | Localization | IT - External | 118h | 0h | 118h | 2016-12-09 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050390 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | SI | Onshore | DelValleLeal; JuanManuel | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-28 | 2016-12-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050391 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | SI | Onshore | DelValleLeal; JuanManuel | IBM | Yes | OpEx | Localization | IT - External | 48h | 0h | 48h | 2017-02-27 | 2017-03-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050392 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | LOG | FUN | SI | Onshore | DelValleLeal; JuanManuel | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-12-05 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050393 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | LOG | FUN | SI | Onshore | DelValleLeal; JuanManuel | IBM | Yes | CapEx | Localization | IT - External | 179h | 0h | 179h | 2017-02-06 | 2017-02-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 65 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050394 | No | Yes | No | Argentina | Argentina | 04-Test | LOG - SIT 2 - Break/Fix | LOG | FUN | SI | Onshore | DelValleLeal; JuanManuel | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050395 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | LOG | FUN | SI | Onshore | DelValleLeal; JuanManuel | IBM | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2017-01-03 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 36 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050396 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - OTC | OTC | FUN | SI | Onshore | Casanueva; Diego | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050397 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | OTC | FUN | SI | Onshore | Casanueva; Diego | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050398 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | OTC | FUN | SI | Onshore | Casanueva; Diego | IBM | Yes | CapEx | Localization | IT - External | 107h | 0h | 107h | 2016-12-26 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 44 | 31 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050399 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | OTC | FUN | SI | Onshore | Casanueva; Diego | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050400 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | OTC | FUN | SI | Onshore | Casanueva; Diego | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-12-19 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050401 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | OTC | FUN | SI | Onshore | Casanueva; Diego | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050402 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | OTC | FUN | SI | Onshore | Casanueva; Diego | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050403 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | OTC | FUN | SI | Onshore | Casanueva; Diego | IBM | Yes | CapEx | Localization | IT - External | 52h | 0h | 52h | 2016-12-05 | 2016-12-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050404 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Manage Defects | OTC | FUN | SI | Onshore | Casanueva; Diego | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2016-11-21 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050405 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Prepare | OTC | FUN | SI | Onshore | Casanueva; Diego | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-11-14 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050406 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | OTC | FUN | SI | Onshore | Casanueva; Diego | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050407 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050408 | No | No | Yes | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050409 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | OpEx | Localization | IT - Internal | 2h | 0h | 2h | 2017-02-07 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050410 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Onboarding | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | CapEx | Localization | IT - Internal | 73.75h | 0h | 73.75h | 2016-12-12 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050411 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | CapEx | Localization | IT - Internal | 27.5h | 0h | 27.5h | 2017-01-03 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 6 | 0 | 0 | 12.5 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050412 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT Defect Resolution | SEC | SEC | SI | Offshore | Santiago; Perzeus | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050413 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-SEC | SEC | SEC | SI | Offshore | Santiago; Perzeus | Accenture | Yes | OpEx | Localization | IT - External | 423h | 0h | 423h | 2017-03-27 | 2017-07-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 18 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 54 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050414 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | BI | BI | SI | Onshore | Chalasani; Rajiv | IBM | Yes | OpEx | Localization | IT - External | 36h | 0h | 36h | 2017-02-06 | 2017-02-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050415 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | PTP | FUN | SI | Onshore | Vergara; Roberto | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-01-30 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050416 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTP | FUN | SI | Onshore | Vergara; Roberto | Accenture | Yes | CapEx | Localization | IT - External | 56h | 0h | 56h | 2016-12-19 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 16 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050417 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | PTP | FUN | SI | Onshore | Vergara; Roberto | Accenture | Yes | OpEx | Localization | IT - External | 174h | 0h | 174h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 46 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050418 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Communication plan execution and monitoring | CM | CM | SI | Onshore | Fernandez; Ruth | IBM | Yes | OpEx | Localization | IT - External | 134h | 0h | 134h | 2016-12-19 | 2017-01-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 30 | 24 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050419 | No | Yes | No | Argentina | Argentina | 04-Test | Communication plan execution and monitoring | CM | CM | SI | Onshore | Fernandez; Ruth | IBM | Yes | OpEx | Localization | IT - External | 449h | 0h | 449h | 2016-09-06 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050420 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Value Realization Monitoring | CM | CM | SI | Onshore | Fernandez; Ruth | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050421 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG - Manage and execute communications | CM | CM | SI | Onshore | Fernandez; Ruth | IBM | Yes | OpEx | Localization | IT - External | 278h | 0h | 278h | 2016-06-08 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050422 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PMO | PMO | PMO | Saputo | Onshore | Steringa; Dan | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050423 | No | Yes | No | Argentina | Argentina | 04-Test | Cutover Plan | BI | BI | SI | Onshore | Tien; Thang | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2016-09-16 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050424 | No | Yes | No | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | CDP | CDP | SI | Onshore | McLaren; Leanne | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-06 | 2016-09-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050425 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Venkateswaran; Hema | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-09-05 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050426 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Venkateswaran; Hema | IBM | Yes | CapEx | Localization | IT - External | 81h | 0h | 81h | 2016-08-22 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050427 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Venkateswaran; Hema | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050428 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Venkateswaran; Hema | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050429 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Onshore | Negrete; Diego | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050430 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Onshore | Negrete; Diego | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-05-09 | 2016-08-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050431 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Onshore | Negrete; Diego | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-05-09 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050432 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Onshore | Negrete; Diego | IBM | Yes | CapEx | Localization | IT - External | 236h | 0h | 236h | 2016-08-16 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050433 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Onshore | Negrete; Diego | IBM | Yes | CapEx | Localization | IT - External | 63h | 0h | 63h | 2016-09-12 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050434 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Onshore | Negrete; Diego | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050435 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PMO | PMO | PMO | Saputo | Onshore | Kovacs; Robert | Saputo | Yes | OpEx | Localization | IT - Internal | 9h | 0h | 9h | 2017-03-28 | 2017-05-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050436 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | PMO | PMO | Saputo | Onshore | Kovacs; Robert | Saputo | Yes | CapEx | Localization | IT - Internal | 45h | 0h | 45h | 2016-12-12 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050437 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG KT visit | PMO | PMO | Saputo | Onshore | Kovacs; Robert | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050438 | No | Yes | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-TAI | TAI | TAI | Saputo | Onshore | Patel; Rupesh | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050439 | No | Yes | Yes | Argentina | Argentina | 04-Test | Management | TAI | TAI | Saputo | Onshore | Patel; Rupesh | Saputo | Yes | CapEx | Localization | IT - Internal | 405.5h | 0h | 405.5h | 2016-09-12 | 2016-11-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050440 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Manage Defects | RTR | FUN | Saputo | Onshore | Ethier; Patrice | Saputo | Yes | CapEx | Localization | IT - Internal | 4.5h | 0h | 4.5h | 2016-10-03 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050441 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Management (Cutover/Go-live) | RTR | FUN | Saputo | Onshore | Ethier; Patrice | Saputo | Yes | CapEx | Localization | IT - Internal | 350h | 0h | 350h | 2016-12-05 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 40 | 0 | 40 | 40 | 35 | 40 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050442 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Management (Hypercare) - RTR | RTR | FUN | Saputo | Onshore | Ethier; Patrice | Saputo | Yes | CapEx | Localization | IT - Internal | 194h | 0h | 194h | 2017-02-13 | 2017-03-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 35 | 30 | 35 | 30 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050443 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | RTR | FUN | Saputo | Onshore | Ethier; Patrice | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050444 | No | No | Yes | Argentina | Argentina | 10-PCR | Argentina new cheese line-RTR | RTR | FUN | Saputo | Onshore | Ethier; Patrice | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050445 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | Saputo | Onshore | Ethier; Patrice | Saputo | Yes | CapEx | Localization | IT - Internal | 1h | 0h | 1h | 2016-12-12 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050446 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | RTR | FUN | Saputo | Onshore | Ethier; Patrice | Saputo | Yes | CapEx | Localization | IT - Internal | 308.5h | 0h | 308.5h | 2016-08-29 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050447 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-RTR | RTR | FUN | Saputo | Onshore | Ethier; Patrice | Saputo | Yes | OpEx | Localization | IT - Internal | 281h | 0h | 281h | 2017-03-24 | 2017-07-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 29 | 24 | 20 | 22 | 0 | 0 | 25 | 30 | 20 | 25 | 25 | 20 | 20 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050448 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | RTR | FUN | Saputo | Onshore | Ethier; Patrice | Saputo | Yes | OpEx | Localization | IT - Internal | 6h | 0h | 6h | 2016-10-11 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050449 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | RTR | FUN | Saputo | Onshore | Ethier; Patrice | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050450 | No | Yes | Yes | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Anne; Vikram | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050451 | No | Yes | Yes | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Anne; Vikram | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050452 | No | Yes | Yes | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Anne; Vikram | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050453 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Anne; Vikram | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-08-22 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050454 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Management (Hypercare) - RTR | RTR | FUN | SI | Onshore | Holyk; Vic | IBM | Yes | CapEx | Localization | IT - External | 242h | 0h | 242h | 2017-02-06 | 2017-03-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 44 | 44 | 44 | 44 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050455 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Management (Cutover/Go-live) | RTR | FUN | SI | Onshore | Holyk; Vic | IBM | Yes | CapEx | Localization | IT - External | 259h | 0h | 259h | 2016-12-12 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 24 | 44 | 44 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050456 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Manage Defects | RTR | FUN | SI | Onshore | Holyk; Vic | IBM | Yes | CapEx | Localization | IT - External | 35h | 0h | 35h | 2016-10-03 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050457 | No | Yes | No | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | RTR | FUN | SI | Onshore | Holyk; Vic | IBM | Yes | CapEx | Localization | IT - External | 115h | 0h | 115h | 2016-09-06 | 2016-12-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050458 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | SI | Onshore | Holyk; Vic | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050459 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Roy; Pinaki | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050460 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Offshore | Roy; Pinaki | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-13 | 2016-04-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050461 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | Roy; Pinaki | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-09 | 2016-05-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050462 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Roy; Pinaki | IBM | Yes | CapEx | Localization | IT - External | 55h | 0h | 55h | 2016-08-29 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050463 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Roy; Pinaki | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050464 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Roy; Pinaki | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050465 | No | No | Yes | Argentina | Argentina | 04-Test | Role Mapping (ongoing) | CM | CM | SI | Onshore | Fischer; Gillian | IBM | Yes | OpEx | Localization | IT - External | 316h | 0h | 316h | 2016-09-05 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050466 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Role mapping - Ongoing | CM | CM | SI | Onshore | Fischer; Gillian | IBM | Yes | OpEx | Localization | IT - External | 626h | 0h | 626h | 2016-12-05 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 34 | 44 | 44 | 44 | 44 | 44 | 68 | 46 | 48 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050467 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Adress SOD Issues | CM | CM | SI | Onshore | Fischer; Gillian | IBM | Yes | OpEx | Localization | IT - External | 34h | 0h | 34h | 2016-07-18 | 2016-07-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050468 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Role mapping Workshops (incl. RMS Training) | CM | CM | SI | Onshore | Fischer; Gillian | IBM | Yes | OpEx | Localization | IT - External | 131h | 0h | 131h | 2016-05-30 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050469 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Prepare variance analysis tool | CM | CM | SI | Onshore | Fischer; Gillian | IBM | Yes | OpEx | Localization | IT - External | 99h | 0h | 99h | 2016-07-25 | 2016-09-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050470 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Evaluate variances between current and future tasks and responsibilities (old Roles vs new Roles) | CM | CM | SI | Onshore | Fischer; Gillian | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-06-27 | 2016-06-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050471 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Determine mitigation measures for each variances (in Meetings) (options: comm, training, transition) | CM | CM | SI | Onshore | Fischer; Gillian | IBM | Yes | OpEx | Localization | IT - External | 51h | 0h | 51h | 2016-08-29 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050472 | No | No | Yes | Argentina | Argentina | 04-Test | SOD report | CM | CM | SI | Onshore | Fischer; Gillian | IBM | Yes | OpEx | Localization | IT - External | 46h | 0h | 46h | 2016-10-17 | 2016-11-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050473 | No | No | Yes | Argentina | Argentina | 04-Test | Variances an Mitigation | CM | CM | SI | Onshore | Fischer; Gillian | IBM | Yes | OpEx | Localization | IT - External | 75h | 0h | 75h | 2016-10-03 | 2016-10-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050474 | No | No | Yes | Argentina | Argentina | 04-Test | Define Role Owners | CM | CM | SI | Onshore | Fischer; Gillian | IBM | Yes | OpEx | Localization | IT - External | 20h | 0h | 20h | 2016-09-26 | 2016-10-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050475 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Matta; Supriya | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050476 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Matta; Supriya | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050477 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Matta; Supriya | IBM | Yes | CapEx | Localization | IT - External | 50h | 0h | 50h | 2016-08-29 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050478 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | Matta; Supriya | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-09 | 2016-05-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050479 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Matta; Supriya | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050480 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Offshore | Matta; Supriya | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-13 | 2016-04-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050481 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Onshore | Morinigo; JulioCesar | IBM | Yes | CapEx | Localization | IT - External | 52h | 0h | 52h | 2016-05-09 | 2016-08-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050482 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Onshore | Morinigo; JulioCesar | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-05-09 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050483 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Onshore | Morinigo; JulioCesar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050484 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Onshore | Morinigo; JulioCesar | IBM | Yes | CapEx | Localization | IT - External | 300h | 0h | 300h | 2016-08-22 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050485 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Onshore | Morinigo; JulioCesar | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2016-10-03 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050486 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Onshore | Morinigo; JulioCesar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050487 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT Defect Resolution | DEV | DEV | SI | Onshore | Morinigo; JulioCesar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050488 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | D; Kavya | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050489 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | D; Kavya | IBM | Yes | CapEx | Localization | IT - External | 58h | 0h | 58h | 2016-09-28 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050490 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | D; Kavya | IBM | Yes | OpEx | Localization | IT - External | 33h | 0h | 33h | 2017-03-06 | 2017-03-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050491 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | D; Kavya | IBM | Yes | CapEx | Localization | IT - External | 39h | 0h | 39h | 2016-09-26 | 2016-10-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050492 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | D; Kavya | IBM | Yes | CapEx | Localization | IT - External | 57h | 0h | 57h | 2017-01-30 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050493 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Offshore | D; Kavya | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-13 | 2016-04-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050494 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | D; Kavya | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-09 | 2016-05-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050495 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | SI | Offshore | D; Kavya | IBM | Yes | OpEx | Localization | IT - External | 234.5h | 0h | 234.5h | 2017-02-06 | 2017-03-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 37 | 69 | 56.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050496 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Offshore | Bera; Ranjita | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-13 | 2016-04-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050497 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Bera; Ranjita | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050498 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | Bera; Ranjita | IBM | Yes | CapEx | Localization | IT - External | 72h | 0h | 72h | 2016-05-09 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050499 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Bera; Ranjita | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050500 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Bera; Ranjita | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050501 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Bera; Ranjita | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050502 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - PTM | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-01-30 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050503 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | OpEx | Localization | IT - External | 153h | 0h | 153h | 2017-02-06 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050504 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050505 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2017-02-27 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050506 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTM - Run Tests | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 48h | 0h | 48h | 2016-10-24 | 2016-11-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050507 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050508 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 98h | 0h | 98h | 2016-12-28 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 27 | 27 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050509 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | OpEx | Localization | IT - External | 59h | 0h | 59h | 2017-03-06 | 2017-05-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 10 | 26 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050510 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Manage Hypercare | PMO | PMO | SI | Onshore | Herda; Steve | IBM | Yes | CapEx | Localization | IT - External | 48h | 0h | 48h | 2017-02-13 | 2017-02-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050511 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Manage Dry Run Cut Over activities | PMO | PMO | SI | Onshore | Herda; Steve | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-12-12 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050512 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Manage PROD Cut Over activities | PMO | PMO | SI | Onshore | Herda; Steve | IBM | Yes | CapEx | Localization | IT - External | 415h | 0h | 415h | 2016-12-19 | 2017-02-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 36 | 44 | 44 | 44 | 44 | 75 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050513 | No | Yes | No | Argentina | Argentina | 04-Test | Cutover Plan | PMO | PMO | SI | Onshore | Herda; Steve | IBM | Yes | CapEx | Localization | IT - External | 431h | 0h | 431h | 2016-10-03 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050514 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Performance testing write-off | TAI | TAI | SI | Onshore | Strauss; Christopher | Accenture | Yes | CapEx | Localization | IT - External | 96h | 0h | 96h | 2016-12-12 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050515 | No | Yes | No | Argentina | Argentina | 04-Test | Performance testing and refresh | TAI | TAI | SI | Onshore | Strauss; Christopher | Accenture | Yes | CapEx | Localization | IT - External | 316h | 0h | 316h | 2016-10-17 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050516 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-BI | BI | BI | Saputo | Onshore | Chicoine; Luc | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050517 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-BI | BI | BI | Saputo | Onshore | Archambault; Louis | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050518 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Onshore | Suryadevara; Laxmi | IBM | Yes | CapEx | Localization | IT - External | 76h | 0h | 76h | 2016-09-12 | 2016-09-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050519 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Onshore | Suryadevara; Laxmi | IBM | Yes | CapEx | Localization | IT - External | 35h | 0h | 35h | 2016-09-06 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050520 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Onshore | Suryadevara; Laxmi | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050521 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Onshore | Suryadevara; Laxmi | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050522 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050523 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 152h | 0h | 152h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050524 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050525 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2016-12-26 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050526 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 48h | 0h | 48h | 2016-12-20 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050527 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-12-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050528 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Solution Design Document (SDD) | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050529 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 56h | 0h | 56h | 2016-09-21 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050530 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 200h | 0h | 200h | 2016-09-19 | 2016-12-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050531 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - PTM | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-01-30 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050532 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | OpEx | Localization | IT - External | 44h | 0h | 44h | 2017-03-27 | 2017-04-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050533 | No | No | Yes | Argentina | Argentina | 04-Test | Manage SIT1 Prep (data, transports) | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-09-19 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050534 | No | No | Yes | Argentina | Argentina | 04-Test | Manage SIT1 Execution | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-19 | 2016-09-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050535 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2017-01-16 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050536 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | OpEx | Localization | IT - External | 177h | 0h | 177h | 2017-02-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 52 | 13 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050537 | No | No | Yes | Argentina | Argentina | 10-PCR | Argentina new cheese line-PTM | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050538 | No | No | Yes | Argentina | Argentina | 04-Test | Work Instructions - Exercices DATA (technical writer + Dele) | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | OpEx | Localization | IT - External | 640h | 0h | 640h | 2016-09-27 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 17 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050539 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Composite Role Build | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-19 | 2016-09-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050540 | No | No | Yes | Argentina | Argentina | 04-Test | Security Role FUT | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 53h | 0h | 53h | 2016-10-17 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050541 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Support Role Build and UT | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-19 | 2016-09-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050542 | No | No | Yes | Argentina | Argentina | 04-Test | FUT Support Roles | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-17 | 2016-10-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050543 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Derived Role Build | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-19 | 2016-09-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050544 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Master Role Build and UT | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 81h | 0h | 81h | 2016-09-12 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050545 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 Defect Resolution | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 111.9h | 0h | 111.9h | 2016-10-22 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050546 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT Defect Resolution | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 265.75h | 0h | 265.75h | 2016-12-20 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 22.75 | 45 | 45 | 45 | 45 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050547 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Hypercare/support | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | OpEx | Localization | IT - External | 153h | 0h | 153h | 2017-02-06 | 2017-03-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 45 | 45 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050548 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | GRC AC - UAT Execution | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 46h | 0h | 46h | 2016-12-05 | 2017-03-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050549 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 Defect Resolution | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-09-07 | 2016-10-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050550 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Support SIT 1 & Defect Resolution | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-28 | 2016-07-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050551 | No | No | Yes | Argentina | Argentina | 03-Design/Build | SoD Remediation Prior to SIT - Roles | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-21 | 2016-07-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050552 | No | No | Yes | Argentina | Argentina | 03-Design/Build | SoD Analysis Prior to SIT - Roles | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-18 | 2016-09-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050553 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Security Role Build & Unit Test (Business Users) | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-06-20 | 2016-06-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050554 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Security Role Design (Business Users) | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-06-20 | 2016-06-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050555 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SAP Security Detailed Design | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-23 | 2016-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050556 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Security Profiles & Authorizations | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-06-13 | 2016-06-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050557 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Security Profiles & Authorizations | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-06-13 | 2016-06-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050558 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SAP Security Detailed Design | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-23 | 2016-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050559 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Security Role Design (Business Users) | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-06-20 | 2016-06-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050560 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Security Role Build & Unit Test (Business Users) | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2016-06-20 | 2016-08-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050561 | No | No | Yes | Argentina | Argentina | 03-Design/Build | SoD Analysis Prior to SIT - Roles | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-18 | 2016-09-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050562 | No | No | Yes | Argentina | Argentina | 03-Design/Build | SoD Remediation Prior to SIT - Roles | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-21 | 2016-07-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050563 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Support SIT 1 & Defect Resolution | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-28 | 2016-07-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050564 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | GRC AC - Cutover planning and Exucution | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-18 | 2016-10-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050565 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Hypercare/support | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | OpEx | Localization | IT - External | 180h | 0h | 180h | 2017-02-09 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 45 | 45 | 45 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050566 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | GRC AC - UAT Execution | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050567 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT Defect Resolution | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 85.5h | 0h | 85.5h | 2016-12-12 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 7.5 | 9.75 | 26.5 | 20.5 | 6.25 | 7.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050568 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Master Role Build and UT | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 19.5h | 0h | 19.5h | 2016-09-12 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050569 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Support Role Build and UT | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-09-19 | 2016-09-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050570 | No | No | Yes | Argentina | Argentina | 04-Test | Security Role FUT | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-19 | 2016-09-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050571 | No | No | Yes | Argentina | Argentina | 04-Test | FUT Support Roles | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 19.35h | 0h | 19.35h | 2016-11-04 | 2016-12-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050572 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 Defect Resolution | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 41.25h | 0h | 41.25h | 2016-09-07 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050573 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 Defect Resolution | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 89.2h | 0h | 89.2h | 2016-10-24 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050574 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Derived Role Build | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 3h | 0h | 3h | 2016-09-20 | 2016-09-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050575 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Composite Role Build | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 12.75h | 0h | 12.75h | 2016-09-22 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050576 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Acosta; Junel | Accenture | Yes | CapEx | Localization | IT - External | 297h | 0h | 297h | 2016-10-10 | 2016-11-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050577 | No | Yes | No | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Acosta; Junel | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050578 | No | Yes | No | Argentina | Argentina | 04-Test | SIT1 - Defect Fix - DEV | DEV | DEV | SI | Offshore | Acosta; Junel | Accenture | Yes | CapEx | Localization | IT - External | 156h | 0h | 156h | 2016-09-12 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050579 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | SI | Offshore | Acosta; Junel | Accenture | Yes | OpEx | Localization | IT - External | 117h | 0h | 117h | 2017-01-23 | 2017-05-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050580 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | Acosta; Junel | Accenture | Yes | OpEx | Localization | IT - External | 135h | 0h | 135h | 2017-02-27 | 2017-06-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050581 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Acosta; Junel | Accenture | Yes | CapEx | Localization | IT - External | 144h | 0h | 144h | 2016-12-05 | 2016-12-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050582 | No | Yes | No | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DEV | DEV | DEV | SI | Offshore | Acosta; Junel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-06 | 2016-09-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050583 | No | Yes | No | Argentina | Argentina | 04-Test | SIT2 - Defect Fix - DC | DEV | DEV | SI | Offshore | Acosta; Junel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050584 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 1 Load in QA (Accenture) - DM | MDG | DM | SI | Offshore | Cheruku; Shiva | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-06-22 | 2016-06-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050585 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - MDG 333 Mock Closure Memo (Accenture) - DM | MDG | DM | SI | Offshore | Cheruku; Shiva | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-11 | 2016-07-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050586 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 0 Load in DEV - DM | MDG | DM | SI | Offshore | Cheruku; Shiva | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-25 | 2016-05-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050587 | No | Yes | No | Argentina | Argentina | 04-Test | SIT2 - Defect Fix - DC | DEV | DEV | SI | Offshore | Calope; Mary | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050588 | No | Yes | No | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DEV | DEV | DEV | SI | Offshore | Calope; Mary | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-06 | 2016-09-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050589 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Calope; Mary | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050590 | No | Yes | No | Argentina | Argentina | 04-Test | SIT1 - Defect Fix - DEV | DEV | DEV | SI | Offshore | Calope; Mary | Accenture | Yes | CapEx | Localization | IT - External | 237h | 0h | 237h | 2016-09-05 | 2016-10-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050591 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Calope; Mary | Accenture | Yes | CapEx | Localization | IT - External | 237h | 0h | 237h | 2016-10-10 | 2016-11-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050592 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 161h | 0h | 161h | 2016-09-06 | 2016-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050593 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Support | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-15 | 2016-07-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050594 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Prepare | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | OpEx | Localization | IT - External | 15h | 0h | 15h | 2016-08-29 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050595 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050596 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 156h | 0h | 156h | 2017-02-13 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 52 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050597 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-01 | 2016-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050598 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050599 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-12-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050600 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 203h | 0h | 203h | 2016-12-19 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 27 | 44 | 44 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050601 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050602 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - Prep | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050603 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-17 | 2016-10-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050604 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-15 | 2016-11-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050605 | No | No | Yes | Argentina | Argentina | 04-Test | LOG - SIT 2 - Break/Fix | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 167h | 0h | 167h | 2016-11-14 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050606 | No | No | Yes | Argentina | Argentina | 04-Test | LOG - SIT 2 - Run Tests | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 52h | 0h | 52h | 2016-11-07 | 2016-11-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050607 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 60h | 0h | 60h | 2017-01-30 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050608 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-03 | 2016-09-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050609 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-LOG | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | OpEx | Localization | IT - External | 559h | 0h | 559h | 2017-03-06 | 2017-06-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 0 | 44 | 44 | 0 | 44 | 33 | 35 | 35 | 33 | 33 | 33 | 27 | 33 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050610 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | OpEx | Localization | IT - External | 40h | 0h | 40h | 2016-10-07 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050611 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 236h | 0h | 236h | 2016-10-11 | 2016-12-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050612 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | OpEx | Localization | IT - External | 25h | 0h | 25h | 2017-03-27 | 2017-03-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050613 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - PTM | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-01-30 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050614 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 108h | 0h | 108h | 2017-02-20 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050615 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 67h | 0h | 67h | 2016-12-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 12 | 15 | 20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050616 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 95h | 0h | 95h | 2016-11-14 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050617 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | OpEx | Localization | IT - External | 132h | 0h | 132h | 2017-02-06 | 2017-02-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050618 | No | Yes | No | Argentina | Argentina | 04-Test | Performance testing and refresh | TAI | TAI | SI | Offshore | Javier; Kristine | Accenture | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-11-28 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050619 | No | Yes | No | Argentina | Argentina | 04-Test | Project SAP Environment Support | TAI | TAI | SI | Offshore | Javier; Kristine | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050620 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover Steps | TAI | TAI | SI | Offshore | Javier; Kristine | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050621 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Support Hypercare | TAI | TAI | SI | Offshore | Javier; Kristine | Accenture | Yes | CapEx | Localization | IT - External | 135h | 0h | 135h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 9 | 36 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050622 | No | Yes | No | Argentina | Argentina | 04-Test | TEST - Technical Architecture and Infrastructure (gen) | TAI | TAI | SI | Offshore | Javier; Kristine | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-09-05 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050623 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 122h | 0h | 122h | 2016-09-12 | 2017-01-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050624 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Unit testing Configuration Documentation | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 13h | 0h | 13h | 2016-08-24 | 2016-08-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050625 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2016-12-12 | 2016-12-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050626 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 21h | 0h | 21h | 2016-12-16 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050627 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050628 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-02-20 | 2017-02-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050629 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-06 | 2016-09-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050630 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | OpEx | Localization | IT - External | 74h | 0h | 74h | 2016-10-03 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050631 | No | Yes | No | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Dongare; Pranouti | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050632 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Dongare; Pranouti | IBM | Yes | CapEx | Localization | IT - External | 54h | 0h | 54h | 2016-09-08 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050633 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Dongare; Pranouti | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050634 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Dongare; Pranouti | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050635 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | Dongare; Pranouti | IBM | Yes | OpEx | Localization | IT - External | 81h | 0h | 81h | 2017-02-27 | 2017-06-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 36 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050636 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | SI | Offshore | Dongare; Pranouti | IBM | Yes | OpEx | Localization | IT - External | 75h | 0h | 75h | 2017-01-23 | 2017-05-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 11 | 10 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050637 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Offshore | Dongare; Pranouti | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2016-05-03 | 2016-05-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050638 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | Dongare; Pranouti | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-09 | 2016-05-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050639 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | Ravi; Shankar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-09 | 2016-05-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050640 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Offshore | Ravi; Shankar | IBM | Yes | CapEx | Localization | IT - External | 13.5h | 0h | 13.5h | 2016-05-02 | 2016-05-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050641 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Ravi; Shankar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050642 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Ravi; Shankar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050643 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Ravi; Shankar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050644 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Ravi; Shankar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050645 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Offshore | Singh; Satyanarayan | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-05-02 | 2016-05-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050646 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | Singh; Satyanarayan | IBM | Yes | CapEx | Localization | IT - External | 89h | 0h | 89h | 2016-05-09 | 2016-05-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050647 | No | No | Yes | Argentina | Argentina | 04-Test | LOG - SIT 2 - Run Tests | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 53h | 0h | 53h | 2016-11-07 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050648 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 248h | 0h | 248h | 2017-02-06 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 60 | 60 | 44 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050649 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-01 | 2016-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050650 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 50h | 0h | 50h | 2016-09-12 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050651 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 109h | 0h | 109h | 2016-11-14 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050652 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-LOG | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | OpEx | Localization | IT - External | 44h | 0h | 44h | 2017-03-17 | 2017-05-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 20 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050653 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 199h | 0h | 199h | 2017-01-02 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 57 | 45 | 61 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050654 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2016-12-26 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050655 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-01-30 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050656 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Deliver Training to End Users | CM | CM | SI | Onshore | Faleyimu; Dele | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050657 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Deliver Training to End Users | CM | CM | SI | Onshore | Faleyimu; Dele | IBM | Yes | OpEx | Localization | IT - External | 71h | 0h | 71h | 2016-12-19 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050658 | No | Yes | No | Argentina | Argentina | 04-Test | Work Instructions - Exercices DATA (technical writer + Dele) | CM | CM | SI | Onshore | Faleyimu; Dele | IBM | Yes | OpEx | Localization | IT - External | 786h | 0h | 786h | 2016-09-26 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 36 | 44 | 44 | 44 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050659 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | SI | Offshore | Bh; Vamsi | IBM | Yes | OpEx | Localization | IT - External | 135h | 0h | 135h | 2017-02-06 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050660 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | Bh; Vamsi | IBM | Yes | CapEx | Localization | IT - External | 69h | 0h | 69h | 2016-05-09 | 2016-07-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050661 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Offshore | Bh; Vamsi | IBM | Yes | CapEx | Localization | IT - External | 35h | 0h | 35h | 2016-05-02 | 2016-05-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050662 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Bh; Vamsi | IBM | Yes | CapEx | Localization | IT - External | 387h | 0h | 387h | 2016-12-05 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 45 | 45 | 45 | 45 | 27 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050663 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Bh; Vamsi | IBM | Yes | CapEx | Localization | IT - External | 225h | 0h | 225h | 2016-08-22 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050664 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | Bh; Vamsi | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050665 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Bh; Vamsi | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050666 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Bh; Vamsi | IBM | Yes | CapEx | Localization | IT - External | 58h | 0h | 58h | 2016-08-22 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050667 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Arora; Maninder | IBM | Yes | CapEx | Localization | IT - External | 106h | 0h | 106h | 2016-08-22 | 2016-10-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050668 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Arora; Maninder | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050669 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Arora; Maninder | IBM | Yes | CapEx | Localization | IT - External | 31h | 0h | 31h | 2016-09-26 | 2016-10-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050670 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Arora; Maninder | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050671 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Offshore | Arora; Maninder | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-05-02 | 2016-05-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050672 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | Arora; Maninder | IBM | Yes | CapEx | Localization | IT - External | 144h | 0h | 144h | 2016-05-30 | 2016-06-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050673 | No | Yes | No | Argentina | Argentina | 04-Test | Business Readiness Execution & Monitoring - Survey/communication | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-18 | 2016-09-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050674 | No | Yes | No | Argentina | Argentina | 04-Test | Role Mapping (ongoing) | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 105h | 0h | 105h | 2016-09-12 | 2016-10-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050675 | No | Yes | No | Argentina | Argentina | 04-Test | Change Agents Network Execution and Monitoring | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 54h | 0h | 54h | 2016-09-06 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050676 | No | Yes | No | Argentina | Argentina | 04-Test | Transition Plan Execution & Monitoring | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 137h | 0h | 137h | 2016-09-12 | 2016-10-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050677 | No | Yes | No | Argentina | Argentina | 01-Preparation | ArG - Prepare for Localisation High Level Impact assessment | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 32h | 0h | 32h | 2016-02-29 | 2016-03-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050678 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : Identify all localization for the High Level Impact Assessment | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 64h | 0h | 64h | 2016-03-07 | 2016-03-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050679 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Walkthrough KU presentation with DCLs | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050680 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Establish Key User Requirements | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 16h | 0h | 16h | 2016-06-27 | 2016-06-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050681 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Walkthrough KU on-boarding deck with DCLs | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050682 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Package Changes and Impacts per Department | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 20h | 0h | 20h | 2016-05-16 | 2016-05-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050683 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Onboarding of Division Managers to Role Mapping | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 2h | 0h | 2h | 2016-06-06 | 2016-06-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050684 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Educate\Train DCL on Role mapping | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 5h | 0h | 5h | 2016-05-16 | 2016-05-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050685 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Role mapping Workshops (incl. RMS Training) | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 13h | 0h | 13h | 2016-06-16 | 2016-06-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050686 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Adress SOD Issues | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-18 | 2016-07-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050687 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Evaluate variances between current and future tasks and responsibilities (old Roles vs new Roles) | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 56h | 0h | 56h | 2016-06-27 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050688 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Review Changes and Impacts with Core Team | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 32h | 0h | 32h | 2016-05-24 | 2016-05-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050689 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Hold mitigation workshops | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 40h | 0h | 40h | 2016-05-09 | 2016-05-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050690 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Obtain approval on mitigation plans | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050691 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Build comm package (BU, Changes =benefits, nature of change, people, process, tool Impacts) | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 47h | 0h | 47h | 2016-05-16 | 2016-06-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050692 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Manage as uncovered (log, assess, mitigate, approve) - GTS | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 52h | 0h | 52h | 2016-06-06 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050693 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050694 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: LOG Determine Transition Activities From Completed High Level CI analysis | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-16 | 2016-05-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050695 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: LOG Determine Transition Activitie from Completed Detailed CI Analysis | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-04 | 2016-07-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050696 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: LOG Obtain Approval of the Transition Plan | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-18 | 2016-07-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050697 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTP Determine Transition Activities From Completed High Level CI analysis | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-16 | 2016-05-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050698 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTP Determine Transition Activitie from Completed Detailed CI Analysis | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-04 | 2016-07-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050699 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTP Obtain Approval of the Transition Plan | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-18 | 2016-07-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050700 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : Confirm Baseline measurement procedures | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 4h | 0h | 4h | 2016-06-13 | 2016-06-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050701 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: Establish timelines (planning workshops) | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-11 | 2016-07-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050702 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: Keep Applicable Benefits and KPI | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050703 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : Confirm benefit and KPI owners | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-16 | 2016-05-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050704 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : Obtain buy-in from owners on Value realization responsibilities | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050705 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Validate deck for CM training for managers | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 3h | 0h | 3h | 2016-06-15 | 2016-06-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050706 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Update FAQ and CA toolkit (on-going) | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-31 | 2016-05-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050707 | No | Yes | No | Argentina | Argentina | 03-Design/Build | CA weekly touchpoint/Pulse Check | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 14h | 0h | 14h | 2016-06-06 | 2016-06-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050708 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Debrief on Pulse Check | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 5h | 0h | 5h | 2016-06-06 | 2016-06-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050709 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Convert each mitigation measure into and executable action (Resp., end date, etc…) and log in the appropriate execution plan (Communication, Training or Transition) | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 202h | 0h | 202h | 2016-06-03 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050710 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Present transition activities to responsible managers (Timing will vary depending on start date of transition activities) | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050711 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Implement monitoring process (bi-weekly touchpoint with some managers?) | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-06 | 2016-09-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050712 | No | Yes | No | Argentina | Argentina | 03-Design/Build | On-going management of additional mitigation measures | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 35h | 0h | 35h | 2016-06-03 | 2016-06-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050713 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTP Identify Business Risks from the Change Impacts and briefly describe each risks | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 3.02h | 0h | 3.02h | 2016-03-29 | 2016-04-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050714 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTP Recommand and validate mitigation measures to address Business risks | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 2.73h | 0h | 2.73h | 2016-03-29 | 2016-04-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050715 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTP Incorporate measures into Execution Plans with Change Management team | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 2.73h | 0h | 2.73h | 2016-03-29 | 2016-04-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050716 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTP Log Business risks in PMO Log | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 2.73h | 0h | 2.73h | 2016-03-29 | 2016-04-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050717 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTP Report Project Risks to Project Managers | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 2.73h | 0h | 2.73h | 2016-03-29 | 2016-04-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050718 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: LOG Identify Business Risks from the Change Impacts and briefly describe each risks | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 3.02h | 0h | 3.02h | 2016-03-29 | 2016-04-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050719 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: LOG Recommand and validate mitigation measures to address Business risks | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 2.73h | 0h | 2.73h | 2016-03-29 | 2016-04-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050720 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: LOG Incorporate measures into Execution Plans with Change Management team | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 2.73h | 0h | 2.73h | 2016-03-29 | 2016-04-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050721 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: LOG Log Business risks in PMO Log | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 2.73h | 0h | 2.73h | 2016-03-29 | 2016-04-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050722 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: LOG Report Project Risks to Project Managers | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 2.73h | 0h | 2.73h | 2016-03-29 | 2016-04-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050723 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTP Start Mitigation Measures for High Impact Changes or Business Risks. (*leverage positive impacts when possible) | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 12h | 0h | 12h | 2016-03-28 | 2016-04-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050724 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTP Hold final CI WORKSHOP : Confirm High Level CI and complete\define Mitigation Measures | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 20h | 0h | 20h | 2016-04-25 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050725 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : PTP Validate Mitigation Measures with Managers | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-29 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050726 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : PTP Obtain Business lead Approval (Fernando Mayer) | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-29 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050727 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : LOG Review and Validate Changes AND Identify and Describe Impacts | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 20.5h | 0h | 20.5h | 2016-03-21 | 2016-04-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050728 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: LOG Insert line for new change | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 8h | 0h | 8h | 2016-03-21 | 2016-03-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050729 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: LOG Identify if there are Business risks and transfer info to Business Risk Log\Template. | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 3.25h | 0h | 3.25h | 2016-03-28 | 2016-04-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050730 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: LOG Start Mitigation Measures for High Impact Changes or Business Risks. (*leverage positive impacts when possible) | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 12.13h | 0h | 12.13h | 2016-03-28 | 2016-04-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050731 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: LOG Hold final CI WORKSHOP : Confirm High Level CI and complete\define Mitigation Measures | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 15h | 0h | 15h | 2016-04-25 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050732 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : LOG Validate Mitigation Measures with Managers | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-29 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050733 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : LOG Obtain Business lead Approval (Fernando Mayer) | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-29 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050734 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: LOG Educate/Train DCL on Role Mapping | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-10 | 2016-05-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050735 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: LOG Workshops : Evaluate Variances between current and future tasks and responsibilties (old Roles vs new roles) | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050736 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: LOG Determine mitigation measures for each variances (in meetings) | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050737 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : PTP Align Functional Team on Roles Catalog Change Control process | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-03-14 | 2016-03-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050738 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTP Divide Catalog by Process Area | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 10h | 0h | 10h | 2016-04-04 | 2016-04-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050739 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTP Educate/Train DCL on Role Mapping | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-10 | 2016-05-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050740 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTP Workshops : Evaluate Variances between current and future tasks and responsibilties (old Roles vs new roles) | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050741 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTP Determine mitigation measures for each variances (in meetings) | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050742 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : LOG Align Functional Team on Roles Catalog Change Control process | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-03-14 | 2016-03-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050743 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: LOG Divide Catalog by Process Area | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 10h | 0h | 10h | 2016-04-04 | 2016-04-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050744 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : PTP Review and Validate Changes AND Identify and Describe Impacts | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 21.5h | 0h | 21.5h | 2016-03-21 | 2016-04-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050745 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTP Insert line for new change | CM | CM | SI | Onshore | Azevedo; Daniel | Accenture | Yes | OpEx | Localization | IT - External | 3.25h | 0h | 3.25h | 2016-03-28 | 2016-04-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050746 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - LOG | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050747 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - LOG | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-05-02 | 2016-05-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050748 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 81h | 0h | 81h | 2017-01-23 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050749 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | OpEx | Localization | IT - External | 5h | 0h | 5h | 2016-09-19 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050750 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 238h | 0h | 238h | 2016-09-19 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050751 | No | No | Yes | Argentina | Argentina | 02-Analyze | LOG - Identify changes in GD for Localization ARG | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 22h | 0h | 22h | 2016-04-06 | 2016-04-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050752 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-LOG | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | OpEx | Localization | IT - External | 446h | 0h | 446h | 2017-03-06 | 2017-06-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 10 | 20 | 20 | 20 | 25 | 33 | 0 | 33 | 18 | 0 | 33 | 33 | 33 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050753 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2016-12-19 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050754 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 95h | 0h | 95h | 2016-09-06 | 2016-09-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050755 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 110h | 0h | 110h | 2017-02-13 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050756 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050757 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - Prep | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 33h | 0h | 33h | 2016-10-24 | 2016-11-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050758 | No | No | Yes | Argentina | Argentina | 04-Test | LOG - SIT 2 - Run Tests | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 108h | 0h | 108h | 2016-10-31 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050759 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | OpEx | Localization | IT - External | 70h | 0h | 70h | 2016-12-01 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050760 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SoD Analysis & Remediation - Role Level | SEC | SEC | SI | Onshore | Ebojoh; Omamerhi | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-04 | 2016-07-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050761 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | HR | HR | Saputo | Onshore | Centeno; Katya | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050762 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-HR | HR | HR | Saputo | Onshore | Centeno; Katya | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050763 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-29 | 2016-08-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050764 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 49h | 0h | 49h | 2016-11-21 | 2016-12-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050765 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG KT visit | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050766 | No | Yes | No | Argentina | Argentina | 04-Test | OTC - SIT 2 - Run Tests | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 39h | 0h | 39h | 2016-11-11 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050767 | No | Yes | No | Argentina | Argentina | 02-Analyze | OTC - Identify Changes in GD for Localization ARG | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 247h | 0h | 247h | 2016-03-07 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050768 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 147h | 0h | 147h | 2016-12-05 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 25 | 40 | 35 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050769 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050770 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050771 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- OTC | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050772 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - OTC | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050773 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTM | FUN | SI | Onshore | Gudipudi; Raghu | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-01-09 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050774 | No | Yes | No | Argentina | Argentina | 04-Test | Updates concepts decks | PTM | FUN | SI | Onshore | Gudipudi; Raghu | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-03 | 2016-10-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050775 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - PTP - Break/Fix | PTM | FUN | SI | Onshore | Gudipudi; Raghu | IBM | Yes | CapEx | Localization | IT - External | 175h | 0h | 175h | 2016-10-24 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050776 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - Manage Defects | PTM | FUN | SI | Onshore | Gudipudi; Raghu | IBM | Yes | CapEx | Localization | IT - External | 13h | 0h | 13h | 2016-11-14 | 2016-11-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050777 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Support | PTM | FUN | SI | Onshore | Gudipudi; Raghu | IBM | Yes | OpEx | Localization | IT - External | 103h | 0h | 103h | 2016-10-18 | 2016-12-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050778 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | PTM | FUN | SI | Onshore | Gudipudi; Raghu | IBM | Yes | CapEx | Localization | IT - External | 79h | 0h | 79h | 2017-01-30 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050779 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTM | FUN | SI | Onshore | Gudipudi; Raghu | IBM | Yes | OpEx | Localization | IT - External | 41h | 0h | 41h | 2016-09-12 | 2016-09-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050780 | No | Yes | No | Argentina | Argentina | 02-Analyze | PTP - Identify Changesin GD for Localization ARG | PTM | FUN | SI | Onshore | Gudipudi; Raghu | IBM | Yes | CapEx | Localization | IT - External | 43.5h | 0h | 43.5h | 2016-03-02 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050781 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - PTP | PTM | FUN | SI | Onshore | Gudipudi; Raghu | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050782 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- PTP | PTM | FUN | SI | Onshore | Gudipudi; Raghu | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-05-02 | 2016-05-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050783 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | PTM | FUN | SI | Onshore | Gudipudi; Raghu | IBM | Yes | CapEx | Localization | IT - External | 176h | 0h | 176h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 54 | 26 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050784 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - Prep | PTM | FUN | SI | Onshore | Gudipudi; Raghu | IBM | Yes | CapEx | Localization | IT - External | 76h | 0h | 76h | 2016-10-11 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050785 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | PTM | FUN | SI | Onshore | Gudipudi; Raghu | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050786 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTM | FUN | SI | Onshore | Gudipudi; Raghu | IBM | Yes | CapEx | Localization | IT - External | 60h | 0h | 60h | 2017-01-02 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 17 | 24 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050787 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Manage Defects | PTM | FUN | SI | Onshore | Gudipudi; Raghu | IBM | Yes | CapEx | Localization | IT - External | 58h | 0h | 58h | 2016-12-05 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050788 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTM | FUN | SI | Onshore | Gudipudi; Raghu | IBM | Yes | CapEx | Localization | IT - External | 66h | 0h | 66h | 2016-12-26 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 16 | 25 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050789 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Data collection templates (DCT) - Explain and collect | PTM | FUN | SI | Onshore | Gudipudi; Raghu | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-14 | 2016-08-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050790 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Prepare | PTM | FUN | SI | Onshore | Gudipudi; Raghu | IBM | Yes | OpEx | Localization | IT - External | 35h | 0h | 35h | 2016-08-15 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050791 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Support | PTM | FUN | SI | Onshore | Gudipudi; Raghu | IBM | Yes | OpEx | Localization | IT - External | 14h | 0h | 14h | 2016-08-08 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050792 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTM | FUN | SI | Onshore | Gudipudi; Raghu | IBM | Yes | CapEx | Localization | IT - External | 63h | 0h | 63h | 2016-09-05 | 2016-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050793 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Manage Defects | PTM | FUN | SI | Onshore | Gudipudi; Raghu | IBM | Yes | CapEx | Localization | IT - External | 17h | 0h | 17h | 2016-09-05 | 2016-09-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050794 | No | Yes | No | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTM | FUN | SI | Onshore | Gudipudi; Raghu | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-11 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050795 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | PTM | FUN | SI | Onshore | Gudipudi; Raghu | IBM | Yes | CapEx | Localization | IT - External | 30h | 0h | 30h | 2016-10-31 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050796 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | PTM | FUN | SI | Onshore | Gudipudi; Raghu | IBM | Yes | CapEx | Localization | IT - External | 40.85h | 0h | 40.85h | 2016-11-14 | 2016-11-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050797 | No | No | Yes | Argentina | Argentina | 04-Test | M2 - Execute pre validation - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-10 | 2016-10-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050798 | No | No | Yes | Argentina | Argentina | 04-Test | SIT1 - Defect Fix - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 207h | 0h | 207h | 2016-09-12 | 2016-10-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050799 | No | No | Yes | Argentina | Argentina | 04-Test | M1 - Execute loads - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050800 | No | No | Yes | Argentina | Argentina | 04-Test | SIT2 - Defect Fix - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 175h | 0h | 175h | 2016-10-31 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050801 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT Prep - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050802 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Data verification Signoff sheets - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-29 | 2016-11-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050803 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | OpEx | Localization | IT - External | 196h | 0h | 196h | 2016-12-19 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050804 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute loads/ reports - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | OpEx | Localization | IT - External | 88h | 0h | 88h | 2016-12-12 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050805 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute pre validation - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | OpEx | Localization | IT - External | 72h | 0h | 72h | 2016-12-12 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 27 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050806 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute pre validation - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-11-14 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050807 | No | No | Yes | Argentina | Argentina | 04-Test | M2 - Execute loads/reports - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 115h | 0h | 115h | 2016-10-17 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050808 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2016-09-05 | 2016-09-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050809 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Hypercare Support - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | OpEx | Localization | IT - External | 90h | 0h | 90h | 2017-02-06 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050810 | No | No | Yes | Argentina | Argentina | 04-Test | Training Prep - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050811 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 0 Load in DEV - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 114h | 0h | 114h | 2016-05-30 | 2016-06-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050812 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute Loads/Reports - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 50.5h | 0h | 50.5h | 2016-12-05 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050813 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 1 Load in QA - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 430h | 0h | 430h | 2016-06-27 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050814 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 1 Load in QA - DC | MDG | DC | SI | Offshore | Paniza; Rolly | Accenture | Yes | CapEx | Localization | IT - External | 444h | 0h | 444h | 2016-06-27 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050815 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 0 Load in DEV - DC | MDG | DC | SI | Offshore | Paniza; Rolly | Accenture | Yes | CapEx | Localization | IT - External | 84h | 0h | 84h | 2016-06-06 | 2016-06-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050816 | No | Yes | No | Argentina | Argentina | 04-Test | Training Prep - DC | MDG | DC | SI | Offshore | Paniza; Rolly | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050817 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Hypercare Support - DC | MDG | DC | SI | Offshore | Paniza; Rolly | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050818 | No | Yes | No | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | SI | Offshore | Paniza; Rolly | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050819 | No | Yes | No | Argentina | Argentina | 04-Test | M2 - Execute loads/reports - DC | MDG | DC | SI | Offshore | Paniza; Rolly | Accenture | Yes | CapEx | Localization | IT - External | 168.5h | 0h | 168.5h | 2016-10-17 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050820 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute pre validation - DC | MDG | DC | SI | Offshore | Paniza; Rolly | Accenture | Yes | CapEx | Localization | IT - External | 97h | 0h | 97h | 2016-11-14 | 2016-11-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050821 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Execute pre validation - DC | MDG | DC | SI | Offshore | Paniza; Rolly | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050822 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute Loads/Reports - DC | MDG | DC | SI | Offshore | Paniza; Rolly | Accenture | Yes | CapEx | Localization | IT - External | 99h | 0h | 99h | 2016-11-28 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050823 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Execute loads/ reports - DC | MDG | DC | SI | Offshore | Paniza; Rolly | Accenture | Yes | OpEx | Localization | IT - External | 49h | 0h | 49h | 2016-12-12 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050824 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover - DC | MDG | DC | SI | Offshore | Paniza; Rolly | Accenture | Yes | OpEx | Localization | IT - External | 152h | 0h | 152h | 2016-12-19 | 2017-01-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 36 | 45 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050825 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT Prep - DC | MDG | DC | SI | Offshore | Paniza; Rolly | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050826 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Data verification Signoff sheets - DC | MDG | DC | SI | Offshore | Paniza; Rolly | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-29 | 2016-11-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050827 | No | Yes | No | Argentina | Argentina | 04-Test | SIT2 - Defect Fix - DC | MDG | DC | SI | Offshore | Paniza; Rolly | Accenture | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2016-11-09 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050828 | No | Yes | No | Argentina | Argentina | 04-Test | M1 - Execute loads - DC | MDG | DC | SI | Offshore | Paniza; Rolly | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-09-05 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050829 | No | Yes | No | Argentina | Argentina | 04-Test | SIT1 - Defect Fix - DC | MDG | DC | SI | Offshore | Paniza; Rolly | Accenture | Yes | CapEx | Localization | IT - External | 180h | 0h | 180h | 2016-09-12 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050830 | No | Yes | No | Argentina | Argentina | 04-Test | M2 - Execute pre validation - DC | MDG | DC | SI | Offshore | Paniza; Rolly | Accenture | Yes | CapEx | Localization | IT - External | 64h | 0h | 64h | 2016-10-10 | 2016-10-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050831 | No | Yes | No | Argentina | Argentina | 04-Test | M2 - Execute pre validation - DC | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050832 | No | Yes | No | Argentina | Argentina | 04-Test | SIT1 - Defect Fix - DC | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | CapEx | Localization | IT - External | 171h | 0h | 171h | 2016-09-12 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050833 | No | Yes | No | Argentina | Argentina | 04-Test | M1 - Execute loads - DC | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050834 | No | Yes | No | Argentina | Argentina | 04-Test | SIT2 - Defect Fix - DC | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | CapEx | Localization | IT - External | 180h | 0h | 180h | 2016-11-02 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050835 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Data verification Signoff sheets - DC | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-29 | 2016-11-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050836 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT Prep - DC | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050837 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover - DC | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050838 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Execute loads/ reports - DC | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | OpEx | Localization | IT - External | 27h | 0h | 27h | 2016-12-05 | 2017-02-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050839 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Execute pre validation - DC | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050840 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute pre validation - DC | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050841 | No | Yes | No | Argentina | Argentina | 04-Test | M2 - Execute loads/reports - DC | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050842 | No | Yes | No | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | CapEx | Localization | IT - External | 99h | 0h | 99h | 2016-09-05 | 2016-10-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050843 | No | Yes | No | Argentina | Argentina | 04-Test | Training Prep - DC | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050844 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Hypercare Support - DC | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | OpEx | Localization | IT - External | 63h | 0h | 63h | 2017-02-22 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050845 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 0 Load in DEV - DC | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | CapEx | Localization | IT - External | 66h | 0h | 66h | 2016-05-30 | 2016-06-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050846 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 1 Load in QA - DC | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | CapEx | Localization | IT - External | 444h | 0h | 444h | 2016-06-27 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050847 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 1 Load in QA - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | CapEx | Localization | IT - External | 510h | 0h | 510h | 2016-06-27 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050848 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 0 Load in DEV - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | CapEx | Localization | IT - External | 81h | 0h | 81h | 2016-06-13 | 2016-06-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050849 | No | Yes | No | Argentina | Argentina | 04-Test | Training Prep - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050850 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Hypercare Support - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | OpEx | Localization | IT - External | 69h | 0h | 69h | 2017-02-06 | 2017-02-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050851 | No | Yes | No | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2016-09-05 | 2016-09-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050852 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute pre validation - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | CapEx | Localization | IT - External | 142h | 0h | 142h | 2016-11-07 | 2016-11-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050853 | No | Yes | No | Argentina | Argentina | 04-Test | M2 - Execute loads/reports - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | CapEx | Localization | IT - External | 121h | 0h | 121h | 2016-10-10 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050854 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute Loads/Reports - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | CapEx | Localization | IT - External | 47h | 0h | 47h | 2016-11-28 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050855 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Execute pre validation - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | OpEx | Localization | IT - External | 80h | 0h | 80h | 2016-12-12 | 2017-01-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050856 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Execute loads/ reports - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | OpEx | Localization | IT - External | 108h | 0h | 108h | 2016-12-27 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 27 | 36 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050857 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | OpEx | Localization | IT - External | 126h | 0h | 126h | 2016-12-19 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050858 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT Prep - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050859 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Data verification Signoff sheets - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-29 | 2016-11-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050860 | No | Yes | No | Argentina | Argentina | 04-Test | SIT2 - Defect Fix - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | CapEx | Localization | IT - External | 71h | 0h | 71h | 2016-10-25 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050861 | No | Yes | No | Argentina | Argentina | 04-Test | SIT1 - Defect Fix - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | CapEx | Localization | IT - External | 142h | 0h | 142h | 2016-09-19 | 2016-10-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050862 | No | Yes | No | Argentina | Argentina | 04-Test | M2 - Execute pre validation - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | CapEx | Localization | IT - External | 17h | 0h | 17h | 2016-10-10 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050863 | No | Yes | No | Argentina | Argentina | 04-Test | M1 - Execute pre validation - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-11 | 2016-09-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050864 | No | Yes | No | Argentina | Argentina | 04-Test | M1 - Execute loads - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050865 | No | No | Yes | Argentina | Argentina | 04-Test | M2 - Execute pre validation - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050866 | No | No | Yes | Argentina | Argentina | 04-Test | SIT1 - Defect Fix - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 225h | 0h | 225h | 2016-09-12 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050867 | No | No | Yes | Argentina | Argentina | 04-Test | M1 - Execute loads - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050868 | No | No | Yes | Argentina | Argentina | 04-Test | SIT2 - Defect Fix - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 63h | 0h | 63h | 2016-11-07 | 2016-11-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050869 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Data verification Signoff sheets - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-29 | 2016-11-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050870 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT Prep - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050871 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | OpEx | Localization | IT - External | 81h | 0h | 81h | 2016-12-19 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050872 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute pre validation - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | OpEx | Localization | IT - External | 56h | 0h | 56h | 2017-01-30 | 2017-02-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050873 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute loads/ reports - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | OpEx | Localization | IT - External | 124.5h | 0h | 124.5h | 2016-12-12 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050874 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute pre validation - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 104h | 0h | 104h | 2016-11-14 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050875 | No | No | Yes | Argentina | Argentina | 04-Test | M2 - Execute loads/reports - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 113.5h | 0h | 113.5h | 2016-10-10 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050876 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-09-05 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050877 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Hypercare Support - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | OpEx | Localization | IT - External | 83h | 0h | 83h | 2017-02-06 | 2017-03-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 18 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050878 | No | No | Yes | Argentina | Argentina | 04-Test | Training Prep - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050879 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 0 Load in DEV - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 108h | 0h | 108h | 2016-05-30 | 2016-06-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050880 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 1 Load in QA - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 427h | 0h | 427h | 2016-06-27 | 2016-09-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050881 | No | Yes | No | Argentina | Argentina | 04-Test | TEST - Technical Architecture and Infrastructure (gen) | Test | Test | SI | Offshore | Podder; Suman | IBM | Yes | CapEx | Localization | IT - External | 67.5h | 0h | 67.5h | 2016-09-05 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050882 | No | Yes | No | Argentina | Argentina | 04-Test | Support Non SAP environments | Test | Test | SI | Offshore | Podder; Suman | IBM | Yes | CapEx | Localization | IT - External | 121.5h | 0h | 121.5h | 2016-09-26 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050883 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Performance testing write-off | Test | Test | SI | Offshore | Podder; Suman | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050884 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover Steps | Test | Test | SI | Offshore | Podder; Suman | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050885 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Chourey; Vandana | IBM | Yes | CapEx | Localization | IT - External | 14h | 0h | 14h | 2016-09-22 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050886 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Chourey; Vandana | IBM | Yes | CapEx | Localization | IT - External | 101h | 0h | 101h | 2016-09-06 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050887 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Chourey; Vandana | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050888 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Offshore | Chourey; Vandana | IBM | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2016-05-02 | 2016-06-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050889 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | Chourey; Vandana | IBM | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2016-05-16 | 2016-06-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050890 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Chourey; Vandana | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050891 | No | No | Yes | Argentina | Argentina | 10-PCR | Argentina new cheese line-LOG | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050892 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | CapEx | Localization | IT - Internal | 425h | 0h | 425h | 2016-09-06 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050893 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-LOG | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | OpEx | Localization | IT - Internal | 230h | 0h | 230h | 2017-03-20 | 2017-06-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 8 | 40 | 30 | 32 | 0 | 0 | 15 | 20 | 0 | 0 | 10 | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050894 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Management (Hypercare) | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | CapEx | Localization | IT - Internal | 148h | 0h | 148h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 28 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050895 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Management (Cutover/Go-live) | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | CapEx | Localization | IT - Internal | 328h | 0h | 328h | 2016-12-05 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 24 | 24 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050896 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050897 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050898 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2016-12-26 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050899 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Break/Fix | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-25 | 2016-10-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050900 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-06 | 2016-09-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050901 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 241h | 0h | 241h | 2016-12-12 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 43 | 43 | 42 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050902 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050903 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-RTR | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | OpEx | Localization | IT - External | 66h | 0h | 66h | 2017-03-09 | 2017-06-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 10 | 8 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050904 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 14h | 0h | 14h | 2016-09-15 | 2016-11-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050905 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - RTR | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050906 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- RTR | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2016-05-03 | 2016-10-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050907 | No | No | Yes | Argentina | Argentina | 02-Analyze | RTR - Identify Changes in GD for Localization ARG | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-02-29 | 2016-02-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050908 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Unit testing Configuration Documentation | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 34h | 0h | 34h | 2016-09-06 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050909 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - LOG | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 17h | 0h | 17h | 2016-05-16 | 2016-06-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050910 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - LOG | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 41h | 0h | 41h | 2016-05-02 | 2016-05-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050911 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2017-01-30 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050912 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-01-09 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 30 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050913 | No | No | Yes | Argentina | Argentina | 02-Analyze | LOG - Identify changes in GD for Localization ARG | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2016-03-21 | 2016-04-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050914 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-LOG | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | OpEx | Localization | IT - External | 169.5h | 0h | 169.5h | 2017-03-06 | 2017-05-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 5 | 4 | 7 | 27 | 32.5 | 7 | 8 | 32 | 3 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050915 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 65h | 0h | 65h | 2016-11-14 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050916 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 100h | 0h | 100h | 2016-09-06 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050917 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | OpEx | Localization | IT - External | 20h | 0h | 20h | 2016-12-01 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050918 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 240h | 0h | 240h | 2017-02-06 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 60 | 60 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050919 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - Prep | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 3h | 0h | 3h | 2016-11-07 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050920 | No | No | Yes | Argentina | Argentina |  | 05-Release 1.3 | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-24 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050921 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 1 Load in QA - DC | MDG | DC | SI | Offshore | Crodua; Michelle | Accenture | Yes | CapEx | Localization | IT - External | 252h | 0h | 252h | 2016-06-27 | 2016-08-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050922 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 0 Load in DEV - DC | MDG | DC | SI | Offshore | Crodua; Michelle | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-25 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050923 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 0 Load in DEV - DC | MDG | DC | SI | Offshore | Perez; Lou | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-25 | 2016-05-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050924 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 1 Load in QA - DC | MDG | DC | SI | Offshore | Perez; Lou | Accenture | Yes | CapEx | Localization | IT - External | 375h | 0h | 375h | 2016-06-28 | 2016-08-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050925 | No | Yes | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute loads/ reports - DC | MDG | DC | SI | Offshore | Perez; Lou | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050926 | No | Yes | Yes | Argentina | Argentina | 04-Test | M2 - Execute loads/reports - DC | MDG | DC | SI | Offshore | Perez; Lou | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050927 | No | Yes | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute pre validation - DC | MDG | DC | SI | Offshore | Perez; Lou | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050928 | No | Yes | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute pre validation - DC | MDG | DC | SI | Offshore | Perez; Lou | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050929 | No | Yes | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover - DC | MDG | DC | SI | Offshore | Perez; Lou | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050930 | No | Yes | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT Prep - DC | MDG | DC | SI | Offshore | Perez; Lou | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050931 | No | Yes | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Data verification Signoff sheets - DC | MDG | DC | SI | Offshore | Perez; Lou | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-29 | 2016-11-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050932 | No | Yes | Yes | Argentina | Argentina | 04-Test | SIT2 - Defect Fix - DC | MDG | DC | SI | Offshore | Perez; Lou | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050933 | No | Yes | Yes | Argentina | Argentina | 04-Test | M1 - Execute loads - DC | MDG | DC | SI | Offshore | Perez; Lou | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050934 | No | Yes | Yes | Argentina | Argentina | 04-Test | SIT1 - Defect Fix - DC | MDG | DC | SI | Offshore | Perez; Lou | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050935 | No | Yes | Yes | Argentina | Argentina | 04-Test | M2 - Execute pre validation - DC | MDG | DC | SI | Offshore | Perez; Lou | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050936 | No | Yes | Yes | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | SI | Offshore | Perez; Lou | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050937 | No | Yes | Yes | Argentina | Argentina | 04-Test | Training Prep - DC | MDG | DC | SI | Offshore | Perez; Lou | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050938 | No | Yes | Yes | Argentina | Argentina | 06-Hypercare | Hypercare Support - DC | MDG | DC | SI | Offshore | Perez; Lou | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050939 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 0 Load in DEV - DC | MDG | DC | SI | Offshore | Unde; Paul | Accenture | Yes | CapEx | Localization | IT - External | 114h | 0h | 114h | 2016-05-30 | 2016-06-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050940 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 1 Load in QA - DC | MDG | DC | SI | Offshore | Unde; Paul | Accenture | Yes | CapEx | Localization | IT - External | 297h | 0h | 297h | 2016-06-27 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050941 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Jaju; Nikhar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050942 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | Jaju; Nikhar | IBM | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2016-05-09 | 2016-05-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050943 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Offshore | Jaju; Nikhar | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-05-02 | 2016-05-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050944 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Jaju; Nikhar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050945 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Jaju; Nikhar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050946 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Jaju; Nikhar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050947 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Offshore | Sharma; Namita | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-08-08 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050948 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Sharma; Namita | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050949 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | Sharma; Namita | IBM | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2016-05-09 | 2016-05-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050950 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Sharma; Namita | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050951 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - PTM | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050952 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-10-03 | 2016-10-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050953 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTM - Run Tests | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | CapEx | Localization | IT - Internal | 30h | 0h | 30h | 2016-11-07 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050954 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | CapEx | Localization | IT - Internal | 40h | 0h | 40h | 2016-11-14 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050955 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050956 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | CapEx | Localization | IT - Internal | 211.98h | 0h | 211.98h | 2017-01-04 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 39.98 | 0 | 48 | 58 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050957 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Management (Cutover/Go-live) | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | CapEx | Localization | IT - Internal | 192h | 0h | 192h | 2016-12-05 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 32 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050958 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | CapEx | Localization | IT - Internal | 362h | 0h | 362h | 2016-09-19 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050959 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | CapEx | Localization | IT - Internal | 89h | 0h | 89h | 2017-02-06 | 2017-02-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050960 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-10-03 | 2016-10-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050961 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050962 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050963 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Functional Specification (FSD) | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | CapEx | Localization | IT - Internal | 40h | 0h | 40h | 2016-08-08 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050964 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050965 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTP | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | OpEx | Localization | IT - Internal | 166h | 0h | 166h | 2017-03-27 | 2017-05-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 26 | 24 | 18 | 30 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050966 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Management (Hypercare) | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | CapEx | Localization | IT - Internal | 150h | 0h | 150h | 2017-02-13 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 40 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050967 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | CM | CM | SI | Onshore | Pinard; Patricia | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050968 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : Localize the Value realization Plan for Argentina | CM | CM | SI | Onshore | Pinard; Patricia | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-23 | 2016-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050969 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Build Argentina VR plan - First draft | CM | CM | SI | Onshore | Pinard; Patricia | IBM | Yes | OpEx | Localization | IT - External | 2.5h | 0h | 2.5h | 2016-05-16 | 2016-06-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050970 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Review first draft of VR plan with Fernando and Determine approach to cascade | CM | CM | SI | Onshore | Pinard; Patricia | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-06-03 | 2016-06-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050971 | No | No | Yes | Argentina | Argentina |  | Update ArG Project Charter | PMO | PMO | SI | Onshore | Ruggerio; Michael | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-03-14 | 2016-03-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050972 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-06 | 2016-09-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050973 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 78h | 0h | 78h | 2017-01-30 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050974 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Support | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050975 | No | No | Yes | Argentina | Argentina | 10-PCR | Argentina new cheese line-RTR | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 51.8h | 0h | 51.8h | 2017-04-17 | 2017-05-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 6.8 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050976 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Prepare | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050977 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Solution Design Document (SDD) | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050978 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050979 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Prep | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 7h | 0h | 7h | 2016-10-11 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050980 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2016-09-26 | 2016-11-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050981 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 28.9h | 0h | 28.9h | 2016-09-12 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050982 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050983 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Validate | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | OpEx | Localization | IT - External | 1.15h | 0h | 1.15h | 2016-08-22 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050984 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - RTR | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 7.6h | 0h | 7.6h | 2016-05-16 | 2016-05-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050985 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- RTR | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 38.85h | 0h | 38.85h | 2016-05-02 | 2016-05-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050986 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 107.75h | 0h | 107.75h | 2016-09-05 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050987 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0.65h | 0h | 0.65h | 2016-09-12 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050988 | No | No | Yes | Argentina | Argentina | 02-Analyze | RTR - Identify Changes in GD for Localization ARG | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-02-29 | 2016-02-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050989 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 17.9h | 0h | 17.9h | 2017-01-09 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 5.9 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050990 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050991 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Manage Defects | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2016-11-04 | 2016-11-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050992 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Break/Fix | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 30h | 0h | 30h | 2016-11-14 | 2016-11-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050993 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Run Tests | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050994 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 125h | 0h | 125h | 2016-12-05 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 40 | 0 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050995 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2016-12-05 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050996 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 19h | 0h | 19h | 2016-11-07 | 2016-11-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050997 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 19h | 0h | 19h | 2016-11-14 | 2016-11-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050998 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2016-11-18 | 2016-11-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050999 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-RTR | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | OpEx | Localization | IT - External | 20h | 0h | 20h | 2017-05-23 | 2017-05-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051000 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - RTR | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 211.8h | 0h | 211.8h | 2017-02-06 | 2017-03-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 34 | 33.8 | 37 | 20 | 62.5 | 6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051001 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051002 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 38h | 0h | 38h | 2017-01-23 | 2017-01-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051003 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051004 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - RTR | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | OpEx | Localization | IT - External | 79h | 0h | 79h | 2017-02-27 | 2017-03-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051005 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-12-19 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051006 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Training workshops | PTM | FUN | SI | Onshore | Ferrante; Alfredo | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-12 | 2016-05-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051007 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - CR | PTM | FUN | SI | Onshore | Ferrante; Alfredo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-10 | 2016-05-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051008 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Data Management | PTM | FUN | SI | Onshore | Ferrante; Alfredo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-10 | 2016-05-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051009 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Operational Procedures | PTM | FUN | SI | Onshore | Ferrante; Alfredo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-16 | 2016-05-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051010 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Non Functional | PTM | FUN | SI | Onshore | Ferrante; Alfredo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-09 | 2016-05-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051011 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PTM | FUN | SI | Onshore | Ferrante; Alfredo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051012 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - PTM | PTM | FUN | SI | Onshore | Ferrante; Alfredo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051013 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - PTM | PTM | FUN | SI | Onshore | Ferrante; Alfredo | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2016-05-02 | 2016-05-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051014 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - PTM Localisation Workshops | PTM | FUN | SI | Onshore | Ferrante; Alfredo | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2016-04-25 | 2016-04-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051015 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | LOG | FUN | SI | Onshore | Avila; Rafael | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051016 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | LOG | FUN | SI | Onshore | Avila; Rafael | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-06 | 2016-09-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051017 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | LOG | FUN | SI | Onshore | Avila; Rafael | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051018 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | LOG | FUN | SI | Onshore | Avila; Rafael | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051019 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | SI | Onshore | Avila; Rafael | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-28 | 2016-12-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051020 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Support | LOG | FUN | SI | Onshore | Avila; Rafael | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-15 | 2016-07-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051021 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Configuration | LOG | FUN | SI | Onshore | Avila; Rafael | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-14 | 2016-08-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051022 | No | Yes | No | Argentina | Argentina | 04-Test | LOG - SIT 2 - Run Tests | LOG | FUN | SI | Onshore | Avila; Rafael | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051023 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - Prep | LOG | FUN | SI | Onshore | Avila; Rafael | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051024 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | SI | Onshore | Avila; Rafael | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-01 | 2016-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051025 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | LOG | FUN | SI | Onshore | Avila; Rafael | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051026 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - LOG | LOG | FUN | SI | Onshore | Avila; Rafael | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2016-05-30 | 2016-06-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051027 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - LOG | LOG | FUN | SI | Onshore | Avila; Rafael | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051028 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG KT visit | LOG | FUN | SI | Onshore | Avila; Rafael | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-14 | 2016-08-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051029 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Unit testing Development Documentation (FUT) | LOG | FUN | SI | Onshore | Avila; Rafael | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-18 | 2016-07-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051030 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Functional Specification (FSD) | LOG | FUN | SI | Onshore | Avila; Rafael | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-18 | 2016-07-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051031 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | LOG | FUN | SI | Onshore | Avila; Rafael | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051032 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Lodha; Chetan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051033 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | Lodha; Chetan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-09 | 2016-05-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051034 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Offshore | Lodha; Chetan | IBM | Yes | CapEx | Localization | IT - External | 11h | 0h | 11h | 2016-05-09 | 2016-05-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051035 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Lodha; Chetan | IBM | Yes | CapEx | Localization | IT - External | 43.5h | 0h | 43.5h | 2016-09-12 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051036 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Lodha; Chetan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051037 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Lodha; Chetan | IBM | Yes | CapEx | Localization | IT - External | 57h | 0h | 57h | 2016-09-06 | 2016-09-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051038 | No | Yes | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | CM | CM | SI | Onshore | Koso; Melanie | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051039 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | Finalize Deck on Role Catalogue Change Control Process | CM | CM | SI | Onshore | Koso; Melanie | IBM | Yes | OpEx | Localization | IT - External | 10h | 0h | 10h | 2016-05-02 | 2016-05-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051040 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | Confirm Role Catalogue and Divide Catalogue by Process Area to be Sent to Managers | CM | CM | SI | Onshore | Koso; Melanie | IBM | Yes | OpEx | Localization | IT - External | 10h | 0h | 10h | 2016-05-02 | 2016-05-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051041 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | Review Process Role Description for clarity and divide by department | CM | CM | SI | Onshore | Koso; Melanie | IBM | Yes | OpEx | Localization | IT - External | 97h | 0h | 97h | 2016-05-09 | 2016-06-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051042 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | Validate Kick-Off Deck | CM | CM | SI | Onshore | Koso; Melanie | IBM | Yes | OpEx | Localization | IT - External | 25h | 0h | 25h | 2016-05-09 | 2016-05-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051043 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | Prepare Role Mapping Onboarding Deck | CM | CM | SI | Onshore | Koso; Melanie | IBM | Yes | OpEx | Localization | IT - External | 24h | 0h | 24h | 2016-05-02 | 2016-05-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051044 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | Educate\Train DCL on Role mapping | CM | CM | SI | Onshore | Koso; Melanie | IBM | Yes | OpEx | Localization | IT - External | 8h | 0h | 8h | 2016-05-16 | 2016-05-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051045 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | Develop RMS Training for the Business | CM | CM | SI | Onshore | Koso; Melanie | IBM | Yes | OpEx | Localization | IT - External | 38h | 0h | 38h | 2016-05-16 | 2016-06-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051046 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | Prepare variance analysis tool | CM | CM | SI | Onshore | Koso; Melanie | IBM | Yes | OpEx | Localization | IT - External | 35h | 0h | 35h | 2016-07-05 | 2016-07-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051047 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | Adress SOD Issues | CM | CM | SI | Onshore | Koso; Melanie | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-18 | 2016-07-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051048 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | Develop RM Status Report (including regular reporting from RMS) | CM | CM | SI | Onshore | Koso; Melanie | IBM | Yes | OpEx | Localization | IT - External | 26h | 0h | 26h | 2016-05-09 | 2016-05-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051049 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | Load End Users & Positions into RMS | CM | CM | SI | Onshore | Koso; Melanie | IBM | Yes | OpEx | Localization | IT - External | 44h | 0h | 44h | 2016-05-24 | 2016-06-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051050 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | Role mapping Workshops (incl. RMS Training) | CM | CM | SI | Onshore | Koso; Melanie | IBM | Yes | OpEx | Localization | IT - External | 56h | 0h | 56h | 2016-05-30 | 2016-06-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051051 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | Onboarding of Division Managers to Role Mapping | CM | CM | SI | Onshore | Koso; Melanie | IBM | Yes | OpEx | Localization | IT - External | 14h | 0h | 14h | 2016-05-18 | 2016-06-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051052 | No | Yes | Yes | Argentina | Argentina | 02-Analyze | Change Management Workstream - Planning - Analyze Phase | CM | CM | SI | Onshore | Koso; Melanie | IBM | Yes | OpEx | Localization | IT - External | 88h | 0h | 88h | 2016-05-23 | 2016-06-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051053 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | Detailled role description | CM | CM | SI | Onshore | Koso; Melanie | IBM | Yes | OpEx | Localization | IT - External | 20h | 0h | 20h | 2016-05-30 | 2016-06-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051054 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - PTP - Run Tests | PTP | FUN | SI | Onshore | Ruetz; Christoph | SAP | Yes | CapEx | Localization | IT - External | 51h | 0h | 51h | 2016-10-31 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051055 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - Manage Defects | PTP | FUN | SI | Onshore | Ruetz; Christoph | SAP | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2016-11-10 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051056 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - PTP - Break/Fix | PTP | FUN | SI | Onshore | Ruetz; Christoph | SAP | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2016-11-10 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051057 | No | Yes | No | Argentina | Argentina | 04-Test | Updates concepts decks | PTP | FUN | SI | Onshore | Ruetz; Christoph | SAP | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-03 | 2016-10-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051058 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | PTP | FUN | SI | Onshore | Ruetz; Christoph | SAP | Yes | CapEx | Localization | IT - External | 59h | 0h | 59h | 2017-02-13 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 18 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051059 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Manage Defects | PTP | FUN | SI | Onshore | Ruetz; Christoph | SAP | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-10-06 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051060 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTP | FUN | SI | Onshore | Ruetz; Christoph | SAP | Yes | CapEx | Localization | IT - External | 26h | 0h | 26h | 2016-10-03 | 2016-10-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051061 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | PTP | FUN | SI | Onshore | Ruetz; Christoph | SAP | Yes | CapEx | Localization | IT - External | 30h | 0h | 30h | 2016-10-06 | 2016-11-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051062 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTP | FUN | SI | Onshore | Ruetz; Christoph | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051063 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | PTP | FUN | SI | Onshore | Ruetz; Christoph | SAP | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-12-12 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051064 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | PTP | FUN | SI | Onshore | Ruetz; Christoph | SAP | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051065 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTP | FUN | SI | Onshore | Ruetz; Christoph | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051066 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTP | FUN | SI | Onshore | Ruetz; Christoph | SAP | Yes | CapEx | Localization | IT - External | 22h | 0h | 22h | 2017-01-10 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 8 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051067 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | PTP | FUN | SI | Onshore | Ruetz; Christoph | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051068 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | PTP | FUN | SI | Onshore | Ruetz; Christoph | SAP | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051069 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - Prep | PTP | FUN | SI | Onshore | Ruetz; Christoph | SAP | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2016-10-24 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051070 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | PTP | FUN | SI | Onshore | Ruetz; Christoph | SAP | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2017-02-06 | 2017-02-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051076 | No | Yes | Yes | Argentina | Argentina | 02-Analyze | PTP - Identify Changesin GD for Localization ARG | PTP | FUN | SI | Onshore | Armstrong; Craig | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-02-29 | 2016-02-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051077 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- PTP | PTP | FUN | SI | Onshore | Armstrong; Craig | Accenture | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2016-05-16 | 2016-05-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051078 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - PTP | PTP | FUN | SI | Onshore | Armstrong; Craig | Accenture | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2016-05-02 | 2016-05-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051079 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | Unit testing Configuration Documentation | PTP | FUN | SI | Onshore | Armstrong; Craig | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051080 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2016-12-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 17 | 9 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051081 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - RTR | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051082 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Break/Fix | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-25 | 2016-10-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051083 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-06 | 2016-09-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051084 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 130h | 0h | 130h | 2016-12-19 | 2017-01-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 23 | 29 | 36 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051085 | No | No | Yes | Argentina | Argentina | 02-Analyze | RTR - Identify Changes in GD for Localization ARG | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 64h | 0h | 64h | 2016-03-28 | 2016-04-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051086 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-09-05 | 2017-01-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051087 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - RTR | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2016-05-17 | 2016-05-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051088 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- RTR | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-05-16 | 2016-05-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051089 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Unit testing Configuration Documentation | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-08-22 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051090 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SoD Analysis & Remediation - Role Level | SEC | SEC | SI | Onshore | Khanna; Tara | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-04 | 2016-07-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051091 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SAP Security Detailed Design | SEC | SEC | SI | Onshore | Khanna; Tara | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-23 | 2016-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051092 | No | Yes | No | Argentina | Argentina | 04-Test | Project Management and Planning for SEC | SEC | SEC | SI | Onshore | Khanna; Tara | Accenture | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-09-26 | 2016-11-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051093 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Management (Hypercare) | SEC | SEC | SI | Onshore | Khanna; Tara | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051094 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Management (Cutover/Go-live) | SEC | SEC | SI | Onshore | Khanna; Tara | Accenture | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2017-01-11 | 2017-01-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051095 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PMO | PMO | SI | Onshore | Allard; Cynthia | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051096 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTP | FUN | SI | Onshore | Pethtel; Melanie | SAP | Yes | CapEx | Localization | IT - External | 120h | 0h | 120h | 2016-09-12 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051097 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | PTP | FUN | SI | Onshore | Pethtel; Melanie | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051098 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | PTP | FUN | SI | Onshore | Pethtel; Melanie | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051099 | No | No | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | CM | CM | Saputo | Onshore | Marcotte; Catherine | Saputo | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051100 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | Test | Test | Saputo | Onshore | Wong; Justin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051101 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Shinde; Amol | IBM | Yes | CapEx | Localization | IT - External | 171h | 0h | 171h | 2016-08-15 | 2016-10-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051102 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Shinde; Amol | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051103 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Shinde; Amol | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051104 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Shinde; Amol | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051105 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Offshore | Shinde; Amol | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-13 | 2016-04-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051106 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | Shinde; Amol | IBM | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2016-07-27 | 2016-07-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051107 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PMO | PMO | SI | Onshore | Letourneau; Benoit | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051108 | No | No | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - |  | Missing Stream | Saputo | Onshore | Maschio Verónica | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051109 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | Raina; Urvashi | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-09 | 2016-05-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051110 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Offshore | Raina; Urvashi | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-13 | 2016-04-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051111 | No | Yes | No | Argentina | Argentina | 04-Test | Management (Planning, reporting, team organization) | DEV | DEV | SI | Offshore | Raina; Urvashi | IBM | Yes | CapEx | Localization | IT - External | 58.5h | 0h | 58.5h | 2016-09-19 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051112 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Raina; Urvashi | IBM | Yes | CapEx | Localization | IT - External | 21h | 0h | 21h | 2016-12-05 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051113 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Raina; Urvashi | IBM | Yes | CapEx | Localization | IT - External | 41h | 0h | 41h | 2016-09-19 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051114 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Raina; Urvashi | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051115 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Raina; Urvashi | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051116 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | Singh; Virender | IBM | Yes | OpEx | Localization | IT - External | 143h | 0h | 143h | 2017-03-06 | 2017-06-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 16 | 0 | 0 | 0 | 0 | 2 | 18 | 0 | 36 | 36 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051117 | No | No | Yes | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Singh; Virender | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051118 | No | No | Yes | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Singh; Virender | IBM | Yes | CapEx | Localization | IT - External | 134h | 0h | 134h | 2016-09-14 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051119 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Singh; Virender | IBM | Yes | CapEx | Localization | IT - External | 58h | 0h | 58h | 2016-08-27 | 2016-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051120 | No | No | Yes | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Singh; Virender | IBM | Yes | OpEx | Global | IT - External | 9h | 0h | 9h | 2017-05-31 | 2017-06-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051121 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, team organization) | DEV | DEV | SI | Offshore | Singh; Virender | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-09-26 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051122 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Singh; Virender | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051123 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | SI | Offshore | Singh; Virender | IBM | Yes | OpEx | Localization | IT - External | 180h | 0h | 180h | 2017-02-06 | 2017-02-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 63 | 52 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051124 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | Singh; Virender | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-09 | 2016-05-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051125 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Offshore | Singh; Virender | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-05-23 | 2016-07-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051126 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | Subhedar; Adheesh | IBM | Yes | CapEx | Localization | IT - External | 64h | 0h | 64h | 2016-05-16 | 2016-06-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051127 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | Subhedar; Adheesh | IBM | Yes | OpEx | Localization | IT - External | 3h | 0h | 3h | 2017-02-27 | 2017-04-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051128 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | SI | Offshore | Subhedar; Adheesh | IBM | Yes | OpEx | Localization | IT - External | 42h | 0h | 42h | 2017-02-14 | 2017-02-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051129 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Subhedar; Adheesh | IBM | Yes | CapEx | Localization | IT - External | 126h | 0h | 126h | 2016-12-06 | 2017-01-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 27 | 30 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051130 | No | No | Yes | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Subhedar; Adheesh | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051131 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Subhedar; Adheesh | IBM | Yes | CapEx | Localization | IT - External | 137h | 0h | 137h | 2016-08-16 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051132 | No | No | Yes | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Subhedar; Adheesh | IBM | Yes | CapEx | Localization | IT - External | 165h | 0h | 165h | 2016-10-10 | 2016-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051133 | No | No | Yes | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Subhedar; Adheesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051134 | No | Yes | No | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) (SI) - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-09-19 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051135 | No | Yes | No | Argentina | Argentina | 04-Test | SIT2 - Manage Defect (Accenture) - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 35h | 0h | 35h | 2016-10-24 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051136 | No | Yes | No | Argentina | Argentina | 04-Test | SIT2 - Execution (SI) - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 117h | 0h | 117h | 2016-10-24 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051137 | No | Yes | No | Argentina | Argentina | 04-Test | SIT1 - Defect Fix (Accenture) - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 30h | 0h | 30h | 2016-09-26 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051138 | No | Yes | No | Argentina | Argentina | 04-Test | SIT1 - Execution (SI) - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 58h | 0h | 58h | 2016-09-26 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051139 | No | Yes | No | Argentina | Argentina | 04-Test | SIT1 - Manage Defect (Accenture) - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2016-09-26 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051140 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 Preparation (Accenture) - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 47h | 0h | 47h | 2016-10-05 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051141 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Execute pre validation (Accenture) - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 108h | 0h | 108h | 2016-12-19 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 16 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051142 | No | Yes | No | Argentina | Argentina | 04-Test | SIT2 - Defect Fix (Accenture) - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 102h | 0h | 102h | 2016-10-31 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051143 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Recordings Vendor/Work Instructions (Accenture) - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | OpEx | Localization | IT - External | 10h | 0h | 10h | 2017-01-13 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051144 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Recordings Customer/Work Instructions (Accenture) - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | OpEx | Localization | IT - External | 10h | 0h | 10h | 2017-01-18 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051145 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Hypercare Support (Accenture) - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 64h | 0h | 64h | 2017-02-06 | 2017-02-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 24 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051146 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 122h | 0h | 122h | 2016-09-06 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051147 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Manage Defects | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 144h | 0h | 144h | 2016-09-06 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051148 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Configuration | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-08-15 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051149 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 124h | 0h | 124h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 14 | 54 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051150 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 113h | 0h | 113h | 2016-12-12 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 11 | 22 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051151 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | OpEx | Localization | IT - External | 122h | 0h | 122h | 2017-02-06 | 2017-02-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051152 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Manage Defects | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2016-12-12 | 2016-12-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051153 | No | No | Yes | Argentina | Argentina | 04-Test | LOG - SIT 2 - Run Tests | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 132h | 0h | 132h | 2016-10-24 | 2016-12-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051154 | No | No | Yes | Argentina | Argentina | 04-Test | LOG - SIT 2 - Manage Defects | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 119h | 0h | 119h | 2016-10-24 | 2016-12-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051155 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Support | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | OpEx | Localization | IT - External | 17h | 0h | 17h | 2016-08-01 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051156 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2017-01-23 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051157 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - LOG | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 53.43h | 0h | 53.43h | 2016-05-09 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051158 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - LOG | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2016-05-09 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051159 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-LOG | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | OpEx | Localization | IT - External | 693.8h | 0h | 693.8h | 2017-03-06 | 2017-07-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 34 | 34 | 38 | 40 | 41 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 33.7 | 33.7 | 33.7 | 33.7 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051160 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | OpEx | Localization | IT - External | 45h | 0h | 45h | 2016-10-07 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051161 | No | No | Yes | Argentina | Argentina | 02-Analyze | LOG - Identify changes in GD for Localization ARG | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 78.5h | 0h | 78.5h | 2016-03-01 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051162 | No | No | Yes | Argentina | Argentina | 04-Test | SIT2 - Defect Fix - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 50.5h | 0h | 50.5h | 2016-11-22 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051163 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Data verification Signoff sheets - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-29 | 2016-11-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051164 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT Prep - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051165 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | OpEx | Localization | IT - External | 140h | 0h | 140h | 2016-12-19 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 45 | 5 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051166 | No | No | Yes | Argentina | Argentina | 04-Test | M1 - Execute pre validation - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-11 | 2016-09-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051167 | No | No | Yes | Argentina | Argentina | 04-Test | M1 - Execute loads - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051168 | No | No | Yes | Argentina | Argentina | 04-Test | M2 - Execute pre validation - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051169 | No | No | Yes | Argentina | Argentina | 04-Test | SIT1 - Defect Fix - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051170 | No | No | Yes | Argentina | Argentina | 04-Test | M2 - Execute loads/reports - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051171 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute pre validation - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | OpEx | Localization | IT - External | 36h | 0h | 36h | 2016-12-19 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051172 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute Loads/Reports - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-11-28 | 2016-12-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051173 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute pre validation - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 48h | 0h | 48h | 2016-11-16 | 2016-11-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051174 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute loads/ reports - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | OpEx | Localization | IT - External | 130.5h | 0h | 130.5h | 2016-12-12 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 27 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051175 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051176 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Hypercare Support - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | OpEx | Localization | IT - External | 87h | 0h | 87h | 2017-02-06 | 2017-02-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 18 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051177 | No | No | Yes | Argentina | Argentina | 04-Test | Training Prep - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051178 | No | No | Yes | Argentina | Argentina | 04-Test | Training Prep - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051179 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Hypercare Support - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | OpEx | Localization | IT - External | 45h | 0h | 45h | 2017-02-06 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051180 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-09-05 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051181 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute loads/ reports - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | OpEx | Localization | IT - External | 168.5h | 0h | 168.5h | 2016-12-12 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 27 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051182 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute pre validation - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051183 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute Loads/Reports - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 49h | 0h | 49h | 2016-11-28 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051184 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute pre validation - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051185 | No | No | Yes | Argentina | Argentina | 04-Test | M2 - Execute loads/reports - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 92h | 0h | 92h | 2016-10-17 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051186 | No | No | Yes | Argentina | Argentina | 04-Test | M2 - Execute pre validation - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051187 | No | No | Yes | Argentina | Argentina | 04-Test | M1 - Execute pre validation - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-11 | 2016-09-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051188 | No | No | Yes | Argentina | Argentina | 04-Test | M1 - Execute loads - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051189 | No | No | Yes | Argentina | Argentina | 04-Test | SIT1 - Defect Fix - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 165.5h | 0h | 165.5h | 2016-09-13 | 2016-10-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051190 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | OpEx | Localization | IT - External | 201h | 0h | 201h | 2017-01-02 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 45 | 0 | 45 | 55 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051191 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT Prep - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051192 | No | No | Yes | Argentina | Argentina | 04-Test | SIT2 - Defect Fix - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 201.5h | 0h | 201.5h | 2016-11-02 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051193 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Data verification Signoff sheets - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-29 | 2016-11-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051194 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - PTM | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051195 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - PTM | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051196 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | OpEx | Localization | IT - External | 84h | 0h | 84h | 2017-02-06 | 2017-02-17 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051197 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2017-02-20 | 2017-02-22 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051198 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051199 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051200 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051201 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTM - Break/Fix | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051202 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTM - Run Tests | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-17 | 2016-10-17 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051203 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051204 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051205 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - Prep | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051206 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051207 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-03 | 2016-10-03 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051208 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051209 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-06 | 2016-09-06 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051210 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051211 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - PTP | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2016-05-02 | 2016-05-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051212 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- PTP | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 11h | 0h | 11h | 2016-05-02 | 2016-05-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051213 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - PTPComplete PDDs | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-03-21 | 2016-03-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051214 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - PTP Finalize BPML | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051215 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - PTP Update RTM | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051216 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - PTP Localisation Output (Report, Interface, Enhancement, Form and Workflow list) | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051217 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - PTP Localisation Workshops | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-03-21 | 2016-03-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051218 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - PTP Create Process documentation in BWL/BPM | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-18 | 2016-04-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051219 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Training workshops | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | OpEx | Localization | IT - External | 2h | 0h | 2h | 2016-05-12 | 2016-05-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051220 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Operational Procedures | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-16 | 2016-05-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051221 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - CR | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 11h | 0h | 11h | 2016-05-10 | 2016-05-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051222 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Non Functional | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2016-05-10 | 2016-05-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051223 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Data Management | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 7h | 0h | 7h | 2016-05-10 | 2016-05-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051224 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG -LOG Create Process documentation in BWL/BPM | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-18 | 2016-04-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051225 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG -LOG Update Project Logs and BWL/BPM | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-18 | 2016-04-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051226 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG -LOG Fit Gap Workshops Notes | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-18 | 2016-04-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051227 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG -LOG Fit Gap Workshops decks | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-18 | 2016-04-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051228 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Support | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | OpEx | Localization | IT - External | 40h | 0h | 40h | 2016-10-07 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051229 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-LOG | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051230 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - LOG | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 429h | 0h | 429h | 2016-05-02 | 2016-08-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051231 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - LOG | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 85h | 0h | 85h | 2016-05-23 | 2016-06-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051232 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - LOG Finalize BPML | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051233 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - LOG Localization Workshop | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-03-21 | 2016-03-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051234 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - LOG Update RTM | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051235 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - LOG Complete PDDs | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-03-21 | 2016-03-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051236 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - LOG Localisation Output (Report, Interface, Enhancement, Form and Workflow list) | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051237 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 63h | 0h | 63h | 2017-02-20 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051238 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Support | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | OpEx | Localization | IT - External | 44h | 0h | 44h | 2016-08-08 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051239 | No | Yes | No | Argentina | Argentina | 04-Test | LOG - SIT 2 - Run Tests | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 159h | 0h | 159h | 2016-10-31 | 2016-11-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051240 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Validate | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-17 | 2016-10-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051241 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 96h | 0h | 96h | 2016-12-19 | 2017-01-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051242 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | OpEx | Localization | IT - External | 373h | 0h | 373h | 2016-12-01 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 44 | 0 | 59 | 0 | 52 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051243 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 60h | 0h | 60h | 2017-02-06 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051244 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG KT visit | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-08-15 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051245 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Data collection templates (DCT) - Explain and collect | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-08-22 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051246 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 256h | 0h | 256h | 2016-09-05 | 2016-10-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051247 | No | Yes | No | Argentina | Argentina | 01-Preparation | ArG GD Integrated sessions | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-02-19 | 2016-02-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051248 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Onshore | Goyal; Shinki | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-09 | 2016-05-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051249 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Onshore | Goyal; Shinki | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-05-02 | 2016-05-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051250 | No | No | Yes | Argentina | Argentina | 04-Test | Project SAP Environment Support | TAI | TAI | SI | Onshore | Barman; Tapan | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-11-07 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051251 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Performance testing write-off | TAI | TAI | SI | Onshore | Barman; Tapan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051252 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover Steps | TAI | TAI | SI | Onshore | Barman; Tapan | Accenture | Yes | CapEx | Localization | IT - External | 230h | 0h | 230h | 2016-12-27 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 24 | 40 | 32 | 38 | 40 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051253 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Support Hypercare | TAI | TAI | SI | Onshore | Barman; Tapan | Accenture | Yes | CapEx | Localization | IT - External | 200h | 0h | 200h | 2017-02-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 56 | 48 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051254 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Identify and procure local hardware | TAI | TAI | SI | Onshore | Barman; Tapan | Accenture | Yes | CapEx | Localization | IT - External | 112h | 0h | 112h | 2016-10-03 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051255 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Technical Architecture and Infrastructure (gen) | TAI | TAI | SI | Onshore | Barman; Tapan | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-09-12 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051256 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | Agrawal; Purvi | IBM | Yes | OpEx | Localization | IT - External | 87h | 0h | 87h | 2017-03-27 | 2017-05-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 18 | 36 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051257 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Agrawal; Purvi | IBM | Yes | CapEx | Localization | IT - External | 81h | 0h | 81h | 2016-08-29 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051258 | No | No | Yes | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Agrawal; Purvi | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051259 | No | No | Yes | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Agrawal; Purvi | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051260 | No | No | Yes | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Agrawal; Purvi | IBM | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2016-10-05 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051261 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Offshore | Agrawal; Purvi | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-05-02 | 2016-05-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051262 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | Agrawal; Purvi | IBM | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2016-05-09 | 2016-05-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051263 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | SI | Offshore | Agrawal; Purvi | IBM | Yes | OpEx | Localization | IT - External | 214h | 0h | 214h | 2017-02-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 68 | 39 | 32 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051264 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Agrawal; Purvi | IBM | Yes | CapEx | Localization | IT - External | 204h | 0h | 204h | 2016-12-10 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 45 | 54 | 33 | 27 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051265 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2016-11-11 | 2016-11-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051266 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 36.5h | 0h | 36.5h | 2016-11-21 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051267 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Unit testing Configuration Documentation | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 26h | 0h | 26h | 2016-08-10 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051268 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Solution Design Document (SDD) | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2016-08-22 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051269 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2016-09-19 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051270 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-02-20 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051271 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - Prep | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 85.5h | 0h | 85.5h | 2016-10-10 | 2016-10-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051272 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 22.5h | 0h | 22.5h | 2016-12-19 | 2016-12-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 12.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051273 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | OpEx | Localization | IT - External | 45h | 0h | 45h | 2017-02-20 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051274 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 138h | 0h | 138h | 2016-12-05 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 2 | 18 | 3 | 22.5 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051275 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 20.5h | 0h | 20.5h | 2016-12-12 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051276 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 125h | 0h | 125h | 2016-12-19 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 12.5 | 18 | 37 | 22.5 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051277 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-01-30 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051278 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTP | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051279 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 89.5h | 0h | 89.5h | 2016-10-03 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051280 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTP - Break/Fix | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 136h | 0h | 136h | 2016-11-02 | 2016-12-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051281 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTP - Break/Fix | PTP | FUN | SI | Offshore | Ragusante; Paul | Accenture | Yes | CapEx | Localization | IT - External | 207h | 0h | 207h | 2016-10-24 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051282 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | PTP | FUN | SI | Offshore | Ragusante; Paul | Accenture | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2016-10-10 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051283 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | PTP | FUN | SI | Offshore | Ragusante; Paul | Accenture | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-01-30 | 2017-01-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051284 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTP | FUN | SI | Offshore | Ragusante; Paul | Accenture | Yes | CapEx | Localization | IT - External | 180h | 0h | 180h | 2016-12-27 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 18 | 45 | 36 | 36 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051285 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | PTP | FUN | SI | Offshore | Ragusante; Paul | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-12-12 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051286 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | PTP | FUN | SI | Offshore | Ragusante; Paul | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051287 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTP | FUN | SI | Offshore | Ragusante; Paul | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051288 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | PTP | FUN | SI | Offshore | Ragusante; Paul | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051289 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTP | FUN | SI | Offshore | Ragusante; Paul | Accenture | Yes | CapEx | Localization | IT - External | 171h | 0h | 171h | 2016-09-12 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051290 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Solution Design Document (SDD) | PTP | FUN | SI | Offshore | Ragusante; Paul | Accenture | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051291 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Unit testing Configuration Documentation | PTP | FUN | SI | Offshore | Ragusante; Paul | Accenture | Yes | CapEx | Localization | IT - External | 51h | 0h | 51h | 2016-08-08 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051292 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | PTP | FUN | SI | Offshore | Ragusante; Paul | Accenture | Yes | CapEx | Localization | IT - External | 63h | 0h | 63h | 2016-11-28 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051293 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | PTP | FUN | SI | Offshore | Ragusante; Paul | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051294 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Break/Fix | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 39h | 0h | 39h | 2016-10-26 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051295 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051296 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Run Tests | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 96h | 0h | 96h | 2016-10-24 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051297 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Manage Defects | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 17h | 0h | 17h | 2016-10-24 | 2016-11-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051298 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2016-11-30 | 2016-12-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051299 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2016-11-30 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051300 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 11h | 0h | 11h | 2016-11-08 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051301 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 37h | 0h | 37h | 2016-12-12 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 4 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051302 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 150h | 0h | 150h | 2016-12-12 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 28 | 35 | 31 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051303 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 13h | 0h | 13h | 2017-02-27 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051304 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - RTR | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-02-06 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051305 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - RTR | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | OpEx | Localization | IT - External | 3h | 0h | 3h | 2017-02-28 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051306 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2016-12-14 | 2016-12-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051307 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2016-12-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051308 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2016-12-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 4 | 4 | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051309 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 64h | 0h | 64h | 2017-01-23 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051310 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - RTR | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 68h | 0h | 68h | 2016-05-30 | 2016-07-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051311 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Unit testing Configuration Documentation | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-08-31 | 2016-09-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051312 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Validate | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | OpEx | Localization | IT - External | 8h | 0h | 8h | 2016-08-29 | 2016-09-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051313 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Solution Design Document (SDD) | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 3.5h | 0h | 3.5h | 2016-08-15 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051314 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Configuration | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2016-08-08 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051315 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Prepare | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051316 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Support | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | OpEx | Localization | IT - External | 5h | 0h | 5h | 2016-08-08 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051317 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051318 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2016-09-12 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051319 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 19h | 0h | 19h | 2016-09-26 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051320 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Prep | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2016-10-11 | 2016-11-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051321 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | OpEx | Localization | IT - External | 7h | 0h | 7h | 2016-10-11 | 2016-11-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051322 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 48h | 0h | 48h | 2016-09-06 | 2016-11-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051323 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2016-09-13 | 2016-09-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051324 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 75h | 0h | 75h | 2016-09-06 | 2016-10-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051325 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051326 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Management (Hypercare) - RTR | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 64h | 0h | 64h | 2017-02-14 | 2017-03-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 14 | 6 | 15 | 8 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051327 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Unit testing Development Documentation (FUT) | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-18 | 2016-07-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051328 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Support | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051329 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 191.5h | 0h | 191.5h | 2016-09-06 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051330 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - Prep | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 14h | 0h | 14h | 2016-10-17 | 2016-10-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051331 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051332 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051333 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051334 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051335 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051336 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 49h | 0h | 49h | 2016-10-03 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051337 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-18 | 2016-10-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051338 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-10-18 | 2016-11-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051339 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-03 | 2016-10-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051340 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTP - Break/Fix | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2016-11-01 | 2016-11-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051341 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051342 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-MDG-DG | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | OpEx | Localization | IT - Internal | 31h | 0h | 31h | 2017-04-04 | 2017-06-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 4 | 6 | 5 | 3 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051343 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DG | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051344 | No | No | Yes | Argentina | Argentina | 06-Hypercare | MDSS Project Management (Hypercare) - DG | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | OpEx | Localization | IT - Internal | 11h | 0h | 11h | 2017-01-30 | 2017-02-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051345 | No | No | Yes | Argentina | Argentina | 06-Hypercare | MDSS Gouvernance Management (Hypercare) - DG | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | OpEx | Localization | IT - Internal | 44h | 0h | 44h | 2017-02-06 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 14 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051346 | No | No | Yes | Argentina | Argentina | 04-Test | Test - MDSS Gouvernance Management - DG | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | OpEx | Localization | IT - Internal | 170h | 0h | 170h | 2016-10-10 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051347 | No | No | Yes | Argentina | Argentina | 04-Test | Test - MDSS Project Management - DG | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | OpEx | Localization | IT - Internal | 86h | 0h | 86h | 2016-10-17 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051348 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | MDSS Project Management (Cutover/Go-live) - DG | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | CapEx | Localization | IT - Internal | 92h | 0h | 92h | 2016-10-10 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 14 | 0 | 11 | 4 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051349 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | MDSS Gouvernance Management (Cutover/Go-live) - DG | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | OpEx | Localization | IT - Internal | 16h | 0h | 16h | 2017-01-09 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 6 | 4 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051350 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Data quality (Hypercare) - DG | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | OpEx | Localization | IT - Internal | 7h | 0h | 7h | 2017-02-06 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051351 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Data Governance – Change Process (Hypercare) - DG | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | OpEx | Localization | IT - Internal | 15h | 0h | 15h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051352 | No | No | Yes | Argentina | Argentina | 04-Test | MDSS - Onboarding - DG | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-11-21 | 2016-11-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051353 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Data Governance – Change Process (Cutover/Go-live) - DG | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | OpEx | Localization | IT - Internal | 41h | 0h | 41h | 2016-12-05 | 2017-02-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 7 | 2 | 3 | 5 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051354 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Data quality (Cutover/Go-live) - DG | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | OpEx | Localization | IT - Internal | 30h | 0h | 30h | 2016-12-05 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 7 | 7 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051355 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Policies, Standards, Business Rules and Metrics (Cutover/Go-live) - DG | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | OpEx | Localization | IT - Internal | 107h | 0h | 107h | 2016-12-05 | 2017-01-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 26 | 16 | 14 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051356 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Policies, Standards, Business Rules and Metrics (Hypercare) - DG | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | OpEx | Localization | IT - Internal | 35h | 0h | 35h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 14 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051357 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - PTM Localisation Workshops | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-03-28 | 2016-04-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051358 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - PTM Complete PDDs | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-04-04 | 2016-04-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051359 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Training workshops | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-12 | 2016-05-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051360 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - CR | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-10 | 2016-05-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051361 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Data Management | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 201h | 0h | 201h | 2016-06-06 | 2016-08-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051362 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Non Functional | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-09 | 2016-05-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051363 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Operational Procedures | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-05-16 | 2016-05-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051364 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051365 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - PTP - Break/Fix | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2016-11-14 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051366 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - Manage Defects | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 19h | 0h | 19h | 2016-11-14 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051367 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - PTP - Run Tests | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 100h | 0h | 100h | 2016-10-31 | 2016-11-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051368 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Validate | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | OpEx | Localization | IT - External | 47h | 0h | 47h | 2016-10-31 | 2016-11-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051369 | No | Yes | No | Argentina | Argentina | 04-Test | Updates concepts decks | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-03 | 2016-10-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051370 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Support | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-18 | 2016-10-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051371 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | OpEx | Localization | IT - External | 78h | 0h | 78h | 2016-10-03 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051372 | No | Yes | No | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 17h | 0h | 17h | 2016-10-03 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051373 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- PTP | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 236h | 0h | 236h | 2016-05-02 | 2016-08-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051374 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - PTP | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 14h | 0h | 14h | 2016-05-02 | 2016-05-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051375 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2017-02-07 | 2017-02-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051376 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - PTP Localisation Workshops | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 14h | 0h | 14h | 2016-04-25 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051377 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTP | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | OpEx | Localization | IT - External | 124h | 0h | 124h | 2017-03-06 | 2017-03-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051378 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - PTM Localisation Output (Report, Interface, Enhancement, Form and Workflow list) | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2016-04-25 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051379 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - PTM Finalize BPML | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-04-25 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051380 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - PTM | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-05-02 | 2016-05-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051381 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - PTM | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-05-02 | 2016-05-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051382 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Manage Defects | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-12-19 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051383 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2016-12-27 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 36 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051384 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-12-12 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051385 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 132h | 0h | 132h | 2017-01-16 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051386 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-01-09 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051387 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | OpEx | Localization | IT - External | 63h | 0h | 63h | 2017-02-10 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051388 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-02-06 | 2017-02-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051389 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 79h | 0h | 79h | 2017-02-06 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051390 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - Prep | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-10-24 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051391 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 69h | 0h | 69h | 2016-09-19 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051392 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Support | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | OpEx | Localization | IT - External | 5h | 0h | 5h | 2016-08-08 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051393 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Validate | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | OpEx | Localization | IT - External | 4h | 0h | 4h | 2016-08-30 | 2016-08-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051394 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Data collection templates (DCT) - Explain and collect | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-08-15 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051395 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Configuration | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-08-30 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051396 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051397 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051398 | No | Yes | No | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-11 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051399 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG KT visit | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2016-08-15 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051400 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 54h | 0h | 54h | 2016-11-14 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051401 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-02-08 | 2017-02-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051402 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Technical Architecture and Infrastructure (gen) - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-01 | 2016-09-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051403 | No | No | Yes | Argentina | Argentina | 04-Test | M2 - Execute loads/reports - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 72h | 0h | 72h | 2016-10-24 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051404 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute pre validation - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | OpEx | Localization | IT - External | 204h | 0h | 204h | 2016-12-12 | 2017-01-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 9 | 45 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051405 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute Loads/Reports - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 49h | 0h | 49h | 2016-11-28 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051406 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute pre validation - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 149h | 0h | 149h | 2016-11-14 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051407 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute loads/ reports - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | OpEx | Localization | IT - External | 45h | 0h | 45h | 2016-12-16 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051408 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 0 Load in DEV - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 83h | 0h | 83h | 2016-05-30 | 2016-06-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051409 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 1 Load in QA - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 455h | 0h | 455h | 2016-06-27 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051410 | No | No | Yes | Argentina | Argentina | 04-Test | M1 - Execute pre validation - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-11 | 2016-09-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051411 | No | No | Yes | Argentina | Argentina | 04-Test | M1 - Execute loads - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051412 | No | No | Yes | Argentina | Argentina | 04-Test | M2 - Execute pre validation - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 66.5h | 0h | 66.5h | 2016-10-10 | 2016-10-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051413 | No | No | Yes | Argentina | Argentina | 04-Test | SIT1 - Defect Fix - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 177h | 0h | 177h | 2016-09-12 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051414 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Data verification Signoff sheets - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-29 | 2016-11-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051415 | No | No | Yes | Argentina | Argentina | 04-Test | SIT2 - Defect Fix - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2016-11-07 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051416 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | OpEx | Localization | IT - External | 99h | 0h | 99h | 2016-12-19 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051417 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT Prep - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051418 | No | No | Yes | Argentina | Argentina | 04-Test | Training Prep - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051419 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Hypercare Support - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | OpEx | Localization | IT - External | 85h | 0h | 85h | 2017-02-06 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051420 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051421 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2016-09-06 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051422 | No | No | Yes | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Tayal; Nidhi | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051423 | No | No | Yes | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Tayal; Nidhi | IBM | Yes | CapEx | Localization | IT - External | 200.5h | 0h | 200.5h | 2016-10-14 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051424 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Tayal; Nidhi | IBM | Yes | CapEx | Localization | IT - External | 41h | 0h | 41h | 2016-09-19 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051425 | No | No | Yes | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Tayal; Nidhi | IBM | Yes | OpEx | Global | IT - External | 5h | 0h | 5h | 2017-06-01 | 2017-06-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051426 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | Tayal; Nidhi | IBM | Yes | OpEx | Localization | IT - External | 156.5h | 0h | 156.5h | 2017-03-06 | 2017-06-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 2.5 | 6 | 2 | 10 | 0 | 11 | 3 | 0 | 0 | 36 | 23 | 1 | 10 | 1 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051427 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Tayal; Nidhi | IBM | Yes | CapEx | Localization | IT - External | 310h | 0h | 310h | 2016-12-19 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 45 | 54 | 45 | 49 | 36 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051428 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | Tayal; Nidhi | IBM | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2016-05-09 | 2016-05-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051429 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | SI | Offshore | Tayal; Nidhi | IBM | Yes | OpEx | Localization | IT - External | 264h | 0h | 264h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 72 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051430 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Offshore | Tayal; Nidhi | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-05-02 | 2016-05-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051431 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | SI | Offshore | Dipankar; Saha | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051432 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Dipankar; Saha | IBM | Yes | CapEx | Localization | IT - External | 13h | 0h | 13h | 2017-01-02 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 5 | 0 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051433 | No | Yes | No | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Dipankar; Saha | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051434 | No | Yes | No | Argentina | Argentina | 04-Test | Management (Planning, reporting, team organization) | DEV | DEV | SI | Offshore | Dipankar; Saha | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-06 | 2016-09-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051435 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | Dipankar; Saha | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051436 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Dipankar; Saha | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051437 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Guha; Arundhati | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051438 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Guha; Arundhati | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051439 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Guha; Arundhati | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051440 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Guha; Arundhati | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051441 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | Guha; Arundhati | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-09 | 2016-05-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051442 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Offshore | Guha; Arundhati | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-13 | 2016-04-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051443 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | SI | Offshore | Agarwal; Khushbu | IBM | Yes | OpEx | Localization | IT - External | 181h | 0h | 181h | 2017-02-06 | 2017-05-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 45 | 45 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051444 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Offshore | Agarwal; Khushbu | IBM | Yes | CapEx | Localization | IT - External | 178h | 0h | 178h | 2016-05-02 | 2016-08-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051445 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | Agarwal; Khushbu | IBM | Yes | CapEx | Localization | IT - External | 170.9h | 0h | 170.9h | 2016-05-09 | 2016-07-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051446 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Agarwal; Khushbu | IBM | Yes | CapEx | Localization | IT - External | 127h | 0h | 127h | 2016-12-05 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 4 | 10 | 0 | 0 | 6 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051447 | No | No | Yes | Argentina | Argentina | 06-Hypercare | ARG tax redesign- DEV | DEV | DEV | SI | Offshore | Agarwal; Khushbu | IBM | Yes | OpEx | Localization | IT - External | 16h | 40h | 56h | 2017-07-31 | 2017-09-22 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 6 | 7 | 0 | 0 | 0 | 0
1051448 | No | No | Yes | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Agarwal; Khushbu | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051449 | No | No | Yes | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Agarwal; Khushbu | IBM | Yes | CapEx | Localization | IT - External | 69h | 0h | 69h | 2016-09-12 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051450 | No | No | Yes | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Agarwal; Khushbu | IBM | Yes | OpEx | Global | IT - External | 11.3h | 0h | 11.3h | 2017-06-02 | 2017-06-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.3 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051451 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Agarwal; Khushbu | IBM | Yes | CapEx | Localization | IT - External | 129h | 0h | 129h | 2016-09-06 | 2016-09-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051452 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | Agarwal; Khushbu | IBM | Yes | OpEx | Localization | IT - External | 219.8h | 0h | 219.8h | 2017-03-06 | 2017-07-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 25 | 9 | 3 | 9 | 0 | 0 | 20 | 28.8 | 36 | 0 | 0 | 3 | 5 | 36 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051453 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | DEV | DEV | SI | Offshore | Agarwal; Khushbu | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051454 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | DEV | DEV | SI | Offshore | Agarwal; Khushbu | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051455 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Ghosh; Arindam | IBM | Yes | CapEx | Localization | IT - External | 60.5h | 0h | 60.5h | 2016-08-22 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051456 | No | Yes | No | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Ghosh; Arindam | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051457 | No | Yes | No | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Ghosh; Arindam | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051458 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | Ghosh; Arindam | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051459 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Ghosh; Arindam | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051460 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Ghosh; Arindam | IBM | Yes | CapEx | Localization | IT - External | 340h | 0h | 340h | 2016-12-05 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 45 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051461 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | SI | Offshore | Ghosh; Arindam | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051462 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Offshore | Ghosh; Arindam | IBM | Yes | CapEx | Localization | IT - External | 26.5h | 0h | 26.5h | 2016-05-09 | 2016-07-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051463 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | Ghosh; Arindam | IBM | Yes | CapEx | Localization | IT - External | 102h | 0h | 102h | 2016-05-09 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051464 | No | No | Yes | Argentina | Argentina | 10-PCR | Argentina new cheese line-MDG-(Saputo) - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051465 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Finance Offline/Work Instructions (Saputo) - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 5h | 0h | 5h | 2017-01-16 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051466 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Train-the-Trainer Customer (Saputo) - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 39h | 0h | 39h | 2016-11-14 | 2017-01-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051467 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Training - Concept Slide Finance - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 5h | 0h | 5h | 2016-12-15 | 2016-12-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051468 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Hypercare Support (Saputo) - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 15h | 0h | 15h | 2017-02-20 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051469 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT Execution Customer (Saputo) - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 31h | 0h | 31h | 2016-12-12 | 2017-01-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051470 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT Execution Vendor (Saputo) - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 31h | 0h | 31h | 2016-12-12 | 2017-01-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051471 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Train-the-Trainer Finance (Saputo) - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 40h | 0h | 40h | 2016-11-14 | 2016-12-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051472 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cutover - Dual Maintenance Argentina Finance (Saputo) - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 66h | 0h | 66h | 2016-12-27 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 6 | 40 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051473 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) (Saputo) - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 32h | 0h | 32h | 2016-09-06 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051474 | No | No | Yes | Argentina | Argentina | 06-Hypercare | MDSS Project Management (Hypercare) - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051475 | No | No | Yes | Argentina | Argentina | 06-Hypercare | MDSS Gouvernance Management (Hypercare) (Saputo) - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 25h | 0h | 25h | 2017-02-13 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051476 | No | No | Yes | Argentina | Argentina | 04-Test | Test - MDSS Gouvernance Management - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 149.45h | 0h | 149.45h | 2016-09-19 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051477 | No | No | Yes | Argentina | Argentina | 04-Test | Test - MDSS Project Management - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 131.75h | 0h | 131.75h | 2016-10-24 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051478 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT Prep - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051479 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-MDG-(Saputo - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 96h | 0h | 96h | 2017-03-20 | 2017-04-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051480 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051481 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | MDSS Gouvernance Management (Cutover/Go-live) (Saputo) - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 20h | 0h | 20h | 2017-01-09 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051482 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Train-the-Trainer Vendor (Saputo) - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 2h | 0h | 2h | 2017-01-23 | 2017-01-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051483 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | Kalra; Inderjeet | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-09 | 2016-05-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051484 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Offshore | Kalra; Inderjeet | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-13 | 2016-04-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051485 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Kalra; Inderjeet | IBM | Yes | CapEx | Localization | IT - External | 606h | 0h | 606h | 2016-12-08 | 2017-03-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 36 | 45 | 45 | 27 | 18 | 55 | 72 | 72 | 72 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051486 | No | No | Yes | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Kalra; Inderjeet | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051487 | No | No | Yes | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Kalra; Inderjeet | IBM | Yes | CapEx | Localization | IT - External | 142h | 0h | 142h | 2016-09-26 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051488 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | Kalra; Inderjeet | IBM | Yes | OpEx | Localization | IT - External | 161h | 0h | 161h | 2017-03-06 | 2017-07-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 12 | 9 | 12 | 12 | 10 | 13 | 8 | 8 | 9 | 7 | 8 | 8 | 8 | 8 | 3 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051489 | No | No | Yes | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Kalra; Inderjeet | IBM | Yes | OpEx | Global | IT - External | 4h | 0h | 4h | 2017-05-23 | 2017-07-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051490 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Kalra; Inderjeet | IBM | Yes | CapEx | Localization | IT - External | 72h | 0h | 72h | 2016-08-16 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051491 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Offshore | Prakash; Gaurav | IBM | Yes | CapEx | Localization | IT - External | 89h | 0h | 89h | 2016-08-18 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051492 | No | No | Yes | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Prakash; Gaurav | IBM | Yes | OpEx | Global | IT - External | 10h | 0h | 10h | 2017-05-31 | 2017-06-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051493 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | Prakash; Gaurav | IBM | Yes | OpEx | Localization | IT - External | 273h | 0h | 273h | 2017-03-06 | 2017-06-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 12 | 14 | 2 | 11 | 22 | 18 | 7 | 6 | 36 | 18 | 13 | 20 | 0 | 3 | 38 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051494 | No | No | Yes | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | Prakash; Gaurav | IBM | Yes | CapEx | Localization | IT - External | 65h | 0h | 65h | 2016-10-07 | 2016-12-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051495 | No | No | Yes | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Offshore | Prakash; Gaurav | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051496 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | Prakash; Gaurav | IBM | Yes | CapEx | Localization | IT - External | 266h | 0h | 266h | 2016-12-05 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 32 | 15 | 28 | 47 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051497 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Offshore | Prakash; Gaurav | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2016-05-02 | 2016-05-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051498 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Offshore | Prakash; Gaurav | IBM | Yes | CapEx | Localization | IT - External | 70h | 0h | 70h | 2016-06-20 | 2016-07-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051499 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | SI | Offshore | Prakash; Gaurav | IBM | Yes | OpEx | Localization | IT - External | 191.5h | 0h | 191.5h | 2017-02-06 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 58.5 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051500 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051501 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - OTC | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 53h | 0h | 53h | 2016-05-02 | 2016-06-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051502 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- OTC | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 20h | 0h | 20h | 2016-05-02 | 2016-05-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051503 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 19h | 0h | 19h | 2016-12-05 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051504 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 108h | 0h | 108h | 2016-12-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 15 | 15 | 23 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051505 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | OpEx | Localization | Business | 80.5h | 0h | 80.5h | 2016-10-31 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051506 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | OpEx | Localization | Business | 40.5h | 0h | 40.5h | 2016-10-11 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051507 | No | No | Yes | Argentina | Argentina | 02-Analyze | OTC - Identify Changes in GD for Localization ARG | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 105h | 0h | 105h | 2016-02-29 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051508 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | OpEx | Localization | Business | 20h | 0h | 20h | 2016-10-19 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051509 | No | No | Yes | Argentina | Argentina | 04-Test | OTC - SIT 2 - Run Tests | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 39h | 0h | 39h | 2016-10-31 | 2016-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051510 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG KT visit | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 21h | 0h | 21h | 2016-08-15 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051511 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-OTC | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | OpEx | Localization | Business | 68.5h | 0h | 68.5h | 2017-03-27 | 2017-07-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 4 | 5 | 5 | 5 | 10 | 5 | 8 | 0 | 0 | 0 | 2.5 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051512 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | OpEx | Localization | Business | 20h | 0h | 20h | 2017-02-20 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051513 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 10h | 0h | 10h | 2017-02-20 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051514 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Support | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | OpEx | Localization | Business | 32h | 0h | 32h | 2016-08-08 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051515 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | OpEx | Localization | Business | 52h | 0h | 52h | 2016-09-06 | 2016-10-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051516 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 29h | 0h | 29h | 2016-11-21 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051517 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 78h | 0h | 78h | 2016-09-06 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051518 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 348.5h | 0h | 348.5h | 2016-09-06 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051519 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG KT visit | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 12.5h | 0h | 12.5h | 2016-08-08 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051520 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | OpEx | Localization | Business | 9.5h | 0h | 9.5h | 2016-10-03 | 2016-11-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051521 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-OTC | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | OpEx | Localization | Business | 31.5h | 0h | 31.5h | 2017-03-06 | 2017-05-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 5 | 2.5 | 0 | 0 | 1 | 2 | 1 | 2 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051522 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-10-17 | 2016-10-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051523 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 15h | 0h | 15h | 2016-12-12 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051524 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 2.5h | 0h | 2.5h | 2016-12-05 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051525 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 10h | 0h | 10h | 2017-01-09 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051526 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 10h | 0h | 10h | 2016-12-19 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051527 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051528 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Management (Hypercare) | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 85h | 0h | 85h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 15 | 20 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051529 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Management (Cutover/Go-live) | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 257.5h | 0h | 257.5h | 2016-12-05 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 24 | 34 | 33 | 21.5 | 40 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051530 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051531 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-10-11 | 2016-11-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051532 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | OpEx | Localization | Business | 163h | 0h | 163h | 2017-03-20 | 2017-05-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2 | 5 | 0 | 45 | 22 | 45 | 10 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051533 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | CapEx | Localization | Business | 277h | 0h | 277h | 2016-09-06 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051534 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051535 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | OpEx | Localization | Business | 4h | 0h | 4h | 2016-10-11 | 2016-10-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051536 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | OpEx | Localization | Business | 4h | 0h | 4h | 2016-10-11 | 2016-11-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051537 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Management (Hypercare) - PTM | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | CapEx | Localization | Business | 236h | 0h | 236h | 2017-01-30 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 72 | 68 | 27 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051538 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - PTM | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051539 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Management (Cutover/Go-live) | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | CapEx | Localization | Business | 172h | 0h | 172h | 2016-12-12 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 27 | 0 | 45 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051540 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | CapEx | Localization | Business | 24h | 0h | 24h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051541 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | OpEx | Localization | Business | 13h | 0h | 13h | 2017-02-22 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051542 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | CapEx | Localization | Business | 44h | 0h | 44h | 2017-01-02 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051543 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | OpEx | Localization | Business | 15h | 0h | 15h | 2016-10-03 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051544 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTM - Run Tests | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | CapEx | Localization | Business | 9h | 0h | 9h | 2016-11-07 | 2016-11-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051545 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | CapEx | Localization | Business | 24h | 0h | 24h | 2016-12-05 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051546 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Management (Cutover/Go-live) | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051547 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-RTR | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | OpEx | Localization | Business | 175.45h | 0h | 175.45h | 2017-03-27 | 2017-06-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 8 | 12 | 10 | 15 | 14.25 | 20 | 24 | 20 | 12.2 | 8.9 | 11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051548 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | CapEx | Localization | Business | 5h | 0h | 5h | 2016-12-05 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051549 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | OpEx | Localization | Business | 5h | 0h | 5h | 2016-10-11 | 2016-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051550 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Management (Cutover/Go-live) | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | CapEx | Localization | Business | 265h | 0h | 265h | 2016-12-07 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 30 | 28 | 23 | 40 | 50 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051551 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Management (Hypercare) - RTR | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | CapEx | Localization | Business | 310.65h | 0h | 310.65h | 2017-02-06 | 2017-07-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 40 | 43.65 | 40 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051552 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Manage Defects | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051553 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- RTR | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | CapEx | Localization | Business | 36.8h | 0h | 36.8h | 2016-06-13 | 2016-07-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051554 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | CapEx | Localization | Business | 34h | 0h | 34h | 2016-12-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 10 | 7 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051555 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | CapEx | Localization | Business | 175.5h | 0h | 175.5h | 2016-09-12 | 2016-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051556 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051557 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051558 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051559 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-LOG | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | OpEx | Localization | Business | 125h | 0h | 125h | 2017-03-20 | 2017-05-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 15 | 40 | 10 | 5 | 5 | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051560 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051561 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Management (Hypercare) | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 212h | 0h | 212h | 2017-01-30 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 40 | 56 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051562 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Management (Cutover/Go-live) | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 260h | 0h | 260h | 2016-12-05 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 40 | 0 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051563 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Manage Defects | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 44h | 0h | 44h | 2016-09-06 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051564 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 243h | 0h | 243h | 2016-09-06 | 2016-11-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051565 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 40h | 0h | 40h | 2016-12-05 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051566 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-12-19 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051567 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 40h | 0h | 40h | 2016-12-19 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051568 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051569 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-09-19 | 2016-09-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051570 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051571 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - OTC | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 105h | 0h | 105h | 2017-01-30 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051572 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 179h | 0h | 179h | 2016-12-19 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 25 | 25 | 34 | 40 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051573 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- OTC | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 40h | 0h | 40h | 2016-05-02 | 2016-05-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051574 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - OTC | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051575 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | OpEx | Localization | Business | 51.5h | 0h | 51.5h | 2016-10-17 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051576 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 57.5h | 0h | 57.5h | 2016-12-05 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051577 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | OpEx | Localization | Business | 68h | 0h | 68h | 2016-10-04 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051578 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | OpEx | Localization | Business | 86h | 0h | 86h | 2017-02-13 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 20 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051579 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 50h | 0h | 50h | 2017-02-13 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051580 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-OTC | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | OpEx | Localization | Business | 23.75h | 0h | 23.75h | 2017-03-20 | 2017-06-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2.5 | 0 | 1 | 1.25 | 0 | 0.5 | 0.5 | 1.5 | 1.5 | 2.5 | 3 | 2 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051581 | No | No | Yes | Argentina | Argentina | 04-Test | OTC - SIT 2 - Run Tests | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 119h | 0h | 119h | 2016-10-24 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051582 | No | No | Yes | Argentina | Argentina | 02-Analyze | OTC - Identify Changes in GD for Localization ARG | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 124.2h | 0h | 124.2h | 2016-02-29 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051583 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 105h | 0h | 105h | 2016-09-06 | 2016-09-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051584 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG KT visit | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 11h | 0h | 11h | 2016-08-08 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051585 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051586 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Break/Fix | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-10-25 | 2016-10-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051587 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Run Tests | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051588 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051589 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 64h | 0h | 64h | 2016-12-19 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051590 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051591 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051592 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051593 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-RTR | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | OpEx | Localization | Business | 424h | 0h | 424h | 2017-03-20 | 2017-06-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 32 | 40 | 0 | 40 | 40 | 0 | 0 | 0 | 40 | 40 | 32 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051594 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - RTR | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051595 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - RTR | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | OpEx | Localization | Business | 280h | 0h | 280h | 2017-01-02 | 2017-03-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051596 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 80h | 0h | 80h | 2017-01-23 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051597 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051598 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051599 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 40h | 0h | 40h | 2017-01-04 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051600 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051601 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-09-26 | 2016-09-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051602 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 12.9h | 0h | 12.9h | 2016-09-12 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051603 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 32h | 0h | 32h | 2016-10-11 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051604 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Support | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051605 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Solution Design Document (SDD) | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051606 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Validate | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | OpEx | Localization | Business | 15h | 0h | 15h | 2016-08-29 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051607 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Prepare | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051608 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 8.9h | 0h | 8.9h | 2016-09-12 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051609 | No | No | Yes | Argentina | Argentina | 02-Analyze | RTR - Identify Changes in GD for Localization ARG | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 122.15h | 0h | 122.15h | 2016-02-29 | 2016-04-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051610 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- RTR | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 61.52h | 0h | 61.52h | 2016-05-09 | 2016-06-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051611 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - RTR | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 28.97h | 0h | 28.97h | 2016-05-02 | 2016-05-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051612 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051613 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051614 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051615 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051616 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 3h | 0h | 3h | 2016-10-20 | 2016-10-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051617 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 68h | 0h | 68h | 2016-09-06 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051618 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | OpEx | Localization | Business | 85h | 0h | 85h | 2016-09-06 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051619 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Functional Specification (FSD) | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 28.8h | 0h | 28.8h | 2016-08-08 | 2016-08-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051620 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Validate | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | OpEx | Localization | Business | 22h | 0h | 22h | 2016-08-15 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051621 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Data collection templates (DCT) - Explain and collect | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 8h | 0h | 8h | 2016-08-15 | 2016-08-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051622 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | OpEx | Localization | Business | 209h | 0h | 209h | 2017-03-21 | 2017-05-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 11 | 4 | 44 | 52 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051623 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | OpEx | Localization | Business | 30h | 0h | 30h | 2016-10-03 | 2016-10-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051624 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | OpEx | Localization | Business | 37h | 0h | 37h | 2016-10-10 | 2016-10-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051625 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - PTM | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 51.8h | 0h | 51.8h | 2016-05-09 | 2016-05-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051626 | No | No | Yes | Argentina | Argentina | 02-Analyze | PTM - Identfy Changes in GD for Localization ARG | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 89.42h | 0h | 89.42h | 2016-02-29 | 2016-04-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051627 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - PTM | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 28.47h | 0h | 28.47h | 2016-05-09 | 2016-07-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051628 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051629 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | OpEx | Localization | Business | 21h | 0h | 21h | 2016-10-03 | 2016-11-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051630 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTM - Run Tests | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 4h | 0h | 4h | 2016-10-26 | 2016-10-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051631 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 64h | 0h | 64h | 2016-12-19 | 2017-01-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 6 | 15 | 11 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051632 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | OpEx | Localization | Business | 181h | 0h | 181h | 2017-02-06 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 48 | 48 | 28 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051633 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 8h | 0h | 8h | 2017-02-06 | 2017-02-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051634 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Manage Defects | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-09-26 | 2016-09-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051635 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 41h | 0h | 41h | 2016-09-12 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051636 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - PTM | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 30h | 0h | 30h | 2017-01-30 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051637 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | OTC | FUN | Saputo | Onshore | Cook; Darrius | Saputo | Yes | CapEx | Localization | Business | 97.5h | 0h | 97.5h | 2016-09-12 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051638 | No | No | Yes | Argentina | Argentina | 02-Analyze | OTC - Identify Changes in GD for Localization ARG | OTC | FUN | Saputo | Onshore | Cook; Darrius | Saputo | Yes | CapEx | Localization | Business | 105h | 0h | 105h | 2016-02-29 | 2016-04-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051639 | No | No | Yes | Argentina | Argentina | 04-Test | OTC - SIT 2 - Run Tests | OTC | FUN | Saputo | Onshore | Cook; Darrius | Saputo | Yes | CapEx | Localization | Business | 20h | 0h | 20h | 2016-10-31 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051640 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-OTC | OTC | FUN | Saputo | Onshore | Cook; Darrius | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051641 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG KT visit | OTC | FUN | Saputo | Onshore | Cook; Darrius | Saputo | Yes | CapEx | Localization | Business | 5h | 0h | 5h | 2016-08-08 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051642 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | OTC | FUN | Saputo | Onshore | Cook; Darrius | Saputo | Yes | OpEx | Localization | Business | 25h | 0h | 25h | 2016-10-03 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051643 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | OTC | FUN | Saputo | Onshore | Cook; Darrius | Saputo | Yes | OpEx | Localization | Business | 25h | 0h | 25h | 2016-10-24 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051644 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | OTC | FUN | Saputo | Onshore | Cook; Darrius | Saputo | Yes | CapEx | Localization | Business | 56h | 0h | 56h | 2016-12-05 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 16 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051645 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | OTC | FUN | Saputo | Onshore | Cook; Darrius | Saputo | Yes | CapEx | Localization | Business | 121h | 0h | 121h | 2016-12-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 16 | 25 | 25 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051646 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- OTC | OTC | FUN | Saputo | Onshore | Cook; Darrius | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051647 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - OTC | OTC | FUN | Saputo | Onshore | Cook; Darrius | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051648 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | OTC | FUN | Saputo | Onshore | Cook; Darrius | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051649 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - OTC | OTC | FUN | Saputo | Onshore | Cook; Darrius | Saputo | Yes | CapEx | Localization | Business | 40h | 0h | 40h | 2017-01-30 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051650 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Solution Design Document (SDD) | OTC | FUN | Saputo | Onshore | Cook; Darrius | Saputo | Yes | CapEx | Localization | Business | 4h | 0h | 4h | 2016-08-22 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051651 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051652 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - OTC | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 37.15h | 0h | 37.15h | 2016-05-02 | 2016-06-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051653 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- OTC | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 22.13h | 0h | 22.13h | 2016-05-02 | 2016-06-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051654 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 120h | 0h | 120h | 2016-12-26 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051655 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051656 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-10-17 | 2016-10-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051657 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051658 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051659 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | OpEx | Localization | Business | 193h | 0h | 193h | 2016-10-10 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051660 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-OTC | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051661 | No | No | Yes | Argentina | Argentina | 04-Test | OTC - SIT 2 - Run Tests | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051662 | No | No | Yes | Argentina | Argentina | 02-Analyze | OTC - Identify Changes in GD for Localization ARG | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 139.9h | 0h | 139.9h | 2016-02-29 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051663 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 100h | 0h | 100h | 2016-09-12 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051664 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-11-21 | 2016-11-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051665 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG KT visit | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 15h | 0h | 15h | 2016-08-08 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051666 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051667 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - LOG | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 5.95h | 0h | 5.95h | 2016-05-02 | 2016-06-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051668 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - LOG | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 30.75h | 0h | 30.75h | 2016-05-02 | 2016-06-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051669 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 35h | 0h | 35h | 2017-01-30 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051670 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Validate | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | OpEx | Localization | Business | 17.5h | 0h | 17.5h | 2016-08-16 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051671 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | OpEx | Localization | Business | 62h | 0h | 62h | 2016-09-19 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051672 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 43h | 0h | 43h | 2016-12-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 7 | 0 | 14 | 14.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051673 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | OpEx | Localization | Business | 6h | 0h | 6h | 2016-10-17 | 2016-11-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051674 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-LOG | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | OpEx | Localization | Business | 136h | 0h | 136h | 2017-03-20 | 2017-06-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 8.5 | 10.5 | 10 | 9 | 0 | 9 | 9 | 9 | 8 | 10 | 14 | 9 | 10.5 | 10.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051675 | No | No | Yes | Argentina | Argentina | 04-Test | Argentina 3 PL Testing | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 5h | 0h | 5h | 2016-11-07 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051676 | No | No | Yes | Argentina | Argentina | 02-Analyze | LOG - Identify changes in GD for Localization ARG | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 64.75h | 0h | 64.75h | 2016-03-07 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051677 | No | No | Yes | Argentina | Argentina | 04-Test | LOG - SIT 2 - Run Tests | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 53h | 0h | 53h | 2016-10-27 | 2016-11-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051678 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 61.25h | 0h | 61.25h | 2016-12-12 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051679 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 119h | 0h | 119h | 2016-12-19 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 6 | 0 | 14 | 15.75 | 40 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051680 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 174h | 0h | 174h | 2016-09-06 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051681 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover 3 PL | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 45h | 0h | 45h | 2016-12-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 6 | 0 | 15 | 15.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051682 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | OpEx | Localization | Business | 237h | 0h | 237h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 73 | 45 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051683 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051684 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051685 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-11-11 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051686 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Validate | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | OpEx | Localization | Business | 4h | 0h | 4h | 2016-08-16 | 2016-08-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051687 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 188.5h | 0h | 188.5h | 2016-09-06 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051688 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051689 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051690 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051691 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 22h | 0h | 22h | 2016-12-28 | 2017-02-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051692 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 17h | 0h | 17h | 2016-12-20 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051693 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051694 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 3h | 0h | 3h | 2016-12-05 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051695 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051696 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-10-03 | 2016-10-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051697 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-10-18 | 2016-10-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051698 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051699 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTP - Run Tests | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051700 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTP | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | OpEx | Localization | Business | 11.5h | 0h | 11.5h | 2017-03-20 | 2017-05-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051701 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Management (Cutover/Go-live) | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 106h | 0h | 106h | 2016-12-05 | 2017-02-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 40 | 0 | 5 | 42 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051702 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Management (Hypercare) | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 39h | 0h | 39h | 2017-02-06 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 15 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051703 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 3h | 0h | 3h | 2016-10-03 | 2016-10-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051704 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | OpEx | Localization | Business | 3h | 0h | 3h | 2016-10-03 | 2016-10-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051705 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-12-05 | 2016-12-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051706 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051707 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 61.5h | 0h | 61.5h | 2017-01-02 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 34.5 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051708 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051709 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 8h | 0h | 8h | 2017-01-09 | 2017-01-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051710 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 68.5h | 0h | 68.5h | 2017-01-04 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 4.5 | 0 | 0 | 28 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051711 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - RTR | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | OpEx | Localization | Business | 237h | 0h | 237h | 2017-02-06 | 2017-03-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.62 | 41.53 | 41.53 | 41.53 | 41.53 | 33.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051712 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - RTR | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051713 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-RTR | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | OpEx | Localization | Business | 149h | 0h | 149h | 2017-03-20 | 2017-07-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 40 | 14 | 22 | 40 | 0 | 0 | 0 | 0 | 0 | 7 | 3 | 2 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051714 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051715 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | OpEx | Localization | Business | 5h | 0h | 5h | 2016-10-11 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051716 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 8h | 0h | 8h | 2016-11-08 | 2016-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051717 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 112h | 0h | 112h | 2016-12-05 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051718 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051719 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Run Tests | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 34h | 0h | 34h | 2016-11-07 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051720 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Break/Fix | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-10-25 | 2016-10-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051721 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Support | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-08-08 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051722 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Solution Design Document (SDD) | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 4.25h | 0h | 4.25h | 2016-08-15 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051723 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051724 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051725 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 16h | 0h | 16h | 2017-01-04 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 1 | 5 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051726 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - RTR | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 76.42h | 0h | 76.42h | 2016-05-09 | 2016-08-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051727 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- RTR | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 124.55h | 0h | 124.55h | 2016-05-09 | 2016-08-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051728 | No | No | Yes | Argentina | Argentina | 02-Analyze | RTR - Identify Changes in GD for Localization ARG | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 155.6h | 0h | 155.6h | 2016-02-29 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051729 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 27h | 0h | 27h | 2016-09-07 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051730 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 5h | 0h | 5h | 2017-01-30 | 2017-02-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051731 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 44h | 0h | 44h | 2016-10-03 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051732 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 32h | 0h | 32h | 2016-10-11 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051733 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PMO | PMO | SI | Onshore | Ingram; Dave | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051734 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PMO | PMO | SI | Onshore | Noel; Alain | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051735 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-06 | 2016-09-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051736 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 72h | 0h | 72h | 2016-09-22 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051737 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-RTR | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-09 | 2017-03-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051738 | No | No | Yes | Argentina | Argentina | 06-Hypercare | CR-GL Upload Program | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | OpEx | Localization | IT - External | 6h | 0h | 6h | 2017-05-01 | 2017-05-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051739 | No | No | Yes | Argentina | Argentina | 02-Analyze | RTR - Identify Changes in GD for Localization ARG | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 139.88h | 0h | 139.88h | 2016-02-29 | 2016-04-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051740 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- RTR | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 69h | 0h | 69h | 2016-06-07 | 2016-07-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051741 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - RTR | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051742 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 267h | 0h | 267h | 2016-12-12 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 43 | 34 | 35 | 40 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051743 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Unit testing Configuration Documentation | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 38h | 0h | 38h | 2016-08-29 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051744 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Break/Fix | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 135h | 0h | 135h | 2016-10-28 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051745 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 34h | 0h | 34h | 2016-12-16 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 2 | 11 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051746 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG KT visit | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051747 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-09-16 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051748 | No | No | Yes | Argentina | Argentina | 02-Analyze | OTC - Identify Changes in GD for Localization ARG | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 162.5h | 0h | 162.5h | 2016-02-29 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051749 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 102h | 0h | 102h | 2016-12-05 | 2017-01-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 10 | 15 | 14 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051750 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | OpEx | Localization | IT - External | 25h | 0h | 25h | 2017-02-20 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051751 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051752 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - OTC | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 38h | 0h | 38h | 2016-05-02 | 2016-05-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051753 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- OTC | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 29h | 0h | 29h | 2016-05-09 | 2016-06-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051754 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Break/Fix | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2016-10-31 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051755 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-RTR | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | OpEx | Localization | IT - External | 36h | 0h | 36h | 2017-03-31 | 2017-05-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 10 | 5 | 0 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051756 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - RTR | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051757 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 11h | 0h | 11h | 2016-12-06 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051758 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Unit testing Configuration Documentation | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 39h | 0h | 39h | 2016-08-22 | 2016-09-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051759 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 215h | 0h | 215h | 2016-12-12 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 45 | 44 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051760 | No | No | Yes | Argentina | Argentina | 02-Analyze | RTR - Identify Changes in GD for Localization ARG | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-02-29 | 2016-02-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051761 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- RTR | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 63h | 0h | 63h | 2016-05-30 | 2016-06-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051762 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - RTR | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 72h | 0h | 72h | 2016-05-09 | 2016-07-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051763 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 38h | 0h | 38h | 2016-09-15 | 2016-11-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051764 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2016-09-26 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051765 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-09-06 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051766 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 73h | 0h | 73h | 2016-09-26 | 2016-12-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051767 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- RTR | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-05-23 | 2016-05-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051768 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - RTR | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-05-16 | 2016-05-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051769 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 184h | 0h | 184h | 2016-12-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 40 | 32 | 32 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051770 | No | No | Yes | Argentina | Argentina | 02-Analyze | RTR - Identify Changes in GD for Localization ARG | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-03-28 | 2016-04-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051771 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Unit testing Configuration Documentation | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-22 | 2016-07-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051772 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-RTR | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-09 | 2017-03-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051773 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051774 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - RTR | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051775 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Break/Fix | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-25 | 2016-10-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051776 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - PTM | PTM | FUN | SI | Offshore | Lande; Kiran | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-02 | 2016-05-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051777 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - PTM | PTM | FUN | SI | Offshore | Lande; Kiran | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-05-23 | 2016-05-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051778 | No | Yes | No | Argentina | Argentina | 02-Analyze | PTM - Identfy Changes in GD for Localization ARG | PTM | FUN | SI | Offshore | Lande; Kiran | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-02-29 | 2016-02-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051779 | No | No | Yes | Argentina | Argentina |  | 05-Release 1.3 | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-24 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051780 | No | No | Yes | Argentina | Argentina | 02-Analyze | LOG - Identify changes in GD for Localization ARG | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2016-02-29 | 2016-04-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051781 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2017-01-09 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051782 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 98h | 0h | 98h | 2017-01-09 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 25 | 30 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051783 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | OpEx | Localization | IT - External | 10h | 0h | 10h | 2016-09-12 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051784 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | OpEx | Localization | IT - External | 40h | 0h | 40h | 2016-10-07 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051785 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-LOG | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | OpEx | Localization | IT - External | 365h | 0h | 365h | 2017-03-06 | 2017-06-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 13.5 | 22.5 | 35 | 22.5 | 18 | 22.5 | 22.5 | 22.5 | 22.5 | 22.5 | 18 | 22.5 | 22.5 | 22.5 | 18 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051786 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Validate | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051787 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Support | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | OpEx | Localization | IT - External | 78h | 0h | 78h | 2016-08-01 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051788 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2017-01-23 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051789 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2016-10-03 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051790 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - LOG | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-05-02 | 2016-05-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051791 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - LOG | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-05-02 | 2016-05-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051792 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051793 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051794 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Prepare | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | OpEx | Localization | IT - External | 33h | 0h | 33h | 2016-08-16 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051795 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 197h | 0h | 197h | 2016-09-06 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051796 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | OpEx | Localization | IT - External | 20h | 0h | 20h | 2016-12-01 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051797 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - Prep | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-10-10 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051798 | No | No | Yes | Argentina | Argentina | 04-Test | LOG - SIT 2 - Run Tests | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 46h | 0h | 46h | 2016-11-07 | 2016-11-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051799 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Break/Fix | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-10-31 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051800 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Run Tests | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 176h | 0h | 176h | 2016-11-07 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051801 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Manage Defects | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051802 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 132h | 0h | 132h | 2016-12-12 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051803 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - RTR | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2017-03-01 | 2017-03-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051804 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051805 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 132h | 0h | 132h | 2016-12-05 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 44 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051806 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051807 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-01-16 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051808 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051809 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - RTR | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | OpEx | Localization | IT - External | 216h | 0h | 216h | 2017-02-06 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 55 | 55 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051810 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Configuration | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 60h | 0h | 60h | 2016-08-08 | 2016-09-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051811 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Solution Design Document (SDD) | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051812 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Unit testing Configuration Documentation | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-08-22 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051813 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Prep | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051814 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG KT visit | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-08-15 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051815 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - RTR Localization workshops | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 115h | 0h | 115h | 2016-03-14 | 2016-04-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051816 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - RTR Localisation Output (Report, Interface, Enhancement, Form and Workflow list) | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-04-04 | 2016-04-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051817 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - RTR Complete PDDs | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-04-18 | 2016-04-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051818 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - RTR Finalize BPML | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051819 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - RTR Update RTM | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-04-11 | 2016-04-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051820 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - RTR Fit Gap Workshops decks | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-18 | 2016-04-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051821 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - RTR Fit Gap Workshops Notes | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-18 | 2016-04-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051822 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - RTR Update Project Logs and BWL/BPM | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-18 | 2016-04-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051823 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - RTR Create Process documentation in BWL/BPM | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-04-25 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051824 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2016-12-26 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051825 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- RTR | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 261h | 0h | 261h | 2016-05-23 | 2016-08-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051826 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - RTR | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-05-02 | 2016-05-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051827 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 140h | 0h | 140h | 2016-09-12 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051828 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2016-10-24 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051829 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-01-30 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051830 | No | Yes | No | Argentina | Argentina | 01-Preparation | ArG Review and understanding PDD | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-01-25 | 2016-01-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051831 | No | Yes | No | Argentina | Argentina | 01-Preparation | ArG Prepare Localisation WS | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 179h | 0h | 179h | 2016-02-01 | 2016-03-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051832 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Operational Procedures | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-05-16 | 2016-05-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051833 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Non Functional | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-05-09 | 2016-05-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051834 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Solution Design Document (SDD) | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 106h | 0h | 106h | 2016-05-23 | 2016-07-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051835 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - CR | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-10 | 2016-05-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051836 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Training workshops | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-12 | 2016-05-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051837 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Data Management | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-10 | 2016-05-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051838 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051839 | No | Yes | No | Argentina | Argentina | 01-Preparation | ArG GD Integrated sessions | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 48h | 0h | 48h | 2016-02-22 | 2016-03-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051840 | No | Yes | No | Argentina | Argentina | 01-Preparation | ArG Global Process Overview | RTR | FUN | SI | Onshore | Graffigna; Oscar | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2016-02-15 | 2016-02-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051841 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-OTC | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | OpEx | Localization | IT - External | 5h | 0h | 5h | 2017-04-24 | 2017-04-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051842 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-06 | 2016-09-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051843 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 152h | 0h | 152h | 2016-09-12 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051844 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - RTR | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 23h | 0h | 23h | 2016-05-02 | 2016-05-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051845 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 137h | 0h | 137h | 2016-12-12 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 33 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051846 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- RTR | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 224h | 0h | 224h | 2016-05-09 | 2016-08-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051847 | No | No | Yes | Argentina | Argentina | 02-Analyze | RTR - Identify Changes in GD for Localization ARG | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 120h | 0h | 120h | 2016-02-29 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051848 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 31h | 0h | 31h | 2016-12-12 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051849 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Break/Fix | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 52h | 0h | 52h | 2016-11-07 | 2016-11-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051850 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | PTP | FUN | SI | Offshore | Zute; Sudeep | IBM | Yes | CapEx | Localization | IT - External | 11h | 0h | 11h | 2016-12-12 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051851 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | PTP | FUN | SI | Offshore | Zute; Sudeep | IBM | Yes | CapEx | Localization | IT - External | 21.5h | 0h | 21.5h | 2017-02-06 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051852 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | PTP | FUN | SI | Offshore | Zute; Sudeep | IBM | Yes | CapEx | Localization | IT - External | 382h | 0h | 382h | 2016-09-12 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 32 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051853 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | PTP | FUN | SI | Offshore | Zute; Sudeep | IBM | Yes | OpEx | Localization | IT - External | 1h | 0h | 1h | 2016-10-03 | 2016-10-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051854 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTP | FUN | SI | Offshore | Zute; Sudeep | IBM | Yes | CapEx | Localization | IT - External | 21h | 0h | 21h | 2016-10-10 | 2016-11-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051855 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTP | PTP | FUN | SI | Offshore | Zute; Sudeep | IBM | Yes | OpEx | Localization | IT - External | 52h | 0h | 52h | 2017-03-06 | 2017-05-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 7 | 13 | 1 | 2 | 4 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051856 | No | No | Yes | Argentina | Argentina | 02-Analyze | PTP - Identify Changesin GD for Localization ARG | PTP | FUN | SI | Offshore | Zute; Sudeep | IBM | Yes | CapEx | Localization | IT - External | 153h | 0h | 153h | 2016-03-14 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051857 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - PTP | PTP | FUN | SI | Offshore | Zute; Sudeep | IBM | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2016-05-10 | 2016-05-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051858 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- PTP | PTP | FUN | SI | Offshore | Zute; Sudeep | IBM | Yes | CapEx | Localization | IT - External | 22h | 0h | 22h | 2016-05-02 | 2016-05-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051859 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | OTC | FUN | Saputo | Onshore | Aikens; Curtis | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051860 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - OTC | OTC | FUN | Saputo | Onshore | Aikens; Curtis | Saputo | Yes | CapEx | Localization | Business | 20h | 0h | 20h | 2017-01-30 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051861 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | OTC | FUN | Saputo | Onshore | Aikens; Curtis | Saputo | Yes | CapEx | Localization | Business | 80h | 0h | 80h | 2016-12-05 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051862 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - OTC | OTC | FUN | Saputo | Onshore | Aikens; Curtis | Saputo | Yes | CapEx | Localization | Business | 57.75h | 0h | 57.75h | 2016-05-02 | 2016-06-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051863 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- OTC | OTC | FUN | Saputo | Onshore | Aikens; Curtis | Saputo | Yes | CapEx | Localization | Business | 32.5h | 0h | 32.5h | 2016-05-02 | 2016-05-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051864 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | OTC | FUN | Saputo | Onshore | Aikens; Curtis | Saputo | Yes | CapEx | Localization | Business | 111h | 0h | 111h | 2016-12-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 24 | 12 | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051865 | No | No | Yes | Argentina | Argentina | 02-Analyze | OTC - Identify Changes in GD for Localization ARG | OTC | FUN | Saputo | Onshore | Aikens; Curtis | Saputo | Yes | CapEx | Localization | Business | 112.5h | 0h | 112.5h | 2016-02-29 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051866 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | OTC | FUN | Saputo | Onshore | Aikens; Curtis | Saputo | Yes | OpEx | Localization | Business | 149h | 0h | 149h | 2016-10-24 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051867 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | OTC | FUN | Saputo | Onshore | Aikens; Curtis | Saputo | Yes | OpEx | Localization | Business | 91h | 0h | 91h | 2016-10-24 | 2016-11-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051868 | No | No | Yes | Argentina | Argentina | 04-Test | OTC - SIT 2 - Run Tests | OTC | FUN | Saputo | Onshore | Aikens; Curtis | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051869 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-OTC | OTC | FUN | Saputo | Onshore | Aikens; Curtis | Saputo | Yes | OpEx | Localization | Business | 121h | 0h | 121h | 2017-03-20 | 2017-05-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 40 | 40 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051870 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | OTC | FUN | Saputo | Onshore | Aikens; Curtis | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-08-29 | 2016-08-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051871 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | OTC | FUN | Saputo | Onshore | Aikens; Curtis | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-11-21 | 2016-11-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051872 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG KT visit | OTC | FUN | Saputo | Onshore | Aikens; Curtis | Saputo | Yes | CapEx | Localization | Business | 2h | 0h | 2h | 2016-08-18 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051873 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | OTC | FUN | Saputo | Onshore | Aikens; Curtis | Saputo | Yes | OpEx | Localization | Business | 236.5h | 0h | 236.5h | 2016-09-12 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051874 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Support | OTC | FUN | Saputo | Onshore | Aikens; Curtis | Saputo | Yes | OpEx | Localization | Business | 55h | 0h | 55h | 2016-08-08 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051875 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Validate | OTC | FUN | Saputo | Onshore | Aikens; Curtis | Saputo | Yes | OpEx | Localization | Business | 100h | 0h | 100h | 2016-08-15 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051876 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | RTR | FUN | SI | Onshore | Herrenknecht; Andreas | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051877 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Break/Fix | RTR | FUN | SI | Onshore | Herrenknecht; Andreas | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-25 | 2016-10-25 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051878 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Manage Defects | RTR | FUN | SI | Onshore | Herrenknecht; Andreas | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051879 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Run Tests | RTR | FUN | SI | Onshore | Herrenknecht; Andreas | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051880 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | RTR | FUN | SI | Onshore | Herrenknecht; Andreas | SAP | Yes | CapEx | Localization | IT - External | 56h | 0h | 56h | 2016-12-06 | 2017-01-06 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051881 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | RTR | FUN | SI | Onshore | Herrenknecht; Andreas | SAP | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-12-12 | 2016-12-18 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051882 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | RTR | FUN | SI | Onshore | Herrenknecht; Andreas | SAP | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-01-16 | 2017-01-20 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051883 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | RTR | FUN | SI | Onshore | Herrenknecht; Andreas | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051884 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | RTR | FUN | SI | Onshore | Herrenknecht; Andreas | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051885 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | RTR | FUN | SI | Onshore | Herrenknecht; Andreas | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051886 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - RTR | RTR | FUN | SI | Onshore | Herrenknecht; Andreas | SAP | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051887 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - RTR | RTR | FUN | SI | Onshore | Herrenknecht; Andreas | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051888 | No | No | Yes | Argentina | Argentina | 06-Hypercare | DMS Argentina Production Support- RTR | RTR | FUN | SI | Onshore | Herrenknecht; Andreas | SAP | Yes | OpEx | Localization | IT - External | 32h | 0h | 32h | 2017-04-03 | 2017-04-06 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051889 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | SI | Onshore | Herrenknecht; Andreas | SAP | Yes | CapEx | Localization | IT - External | 116h | 0h | 116h | 2017-01-16 | 2017-03-29 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 8 | 40 | 32 | 0 | 0 | 8 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051890 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Prep | RTR | FUN | SI | Onshore | Herrenknecht; Andreas | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051891 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | RTR | FUN | SI | Onshore | Herrenknecht; Andreas | SAP | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051892 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | RTR | FUN | SI | Onshore | Herrenknecht; Andreas | SAP | Yes | CapEx | Localization | IT - External | 82h | 0h | 82h | 2016-09-12 | 2016-11-18 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051893 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | RTR | FUN | SI | Onshore | Herrenknecht; Andreas | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051894 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | RTR | FUN | SI | Onshore | Herrenknecht; Andreas | SAP | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2017-01-23 | 2017-02-06 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051895 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | RTR | FUN | SI | Onshore | Bodfeld; Frank | SAP | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2017-01-30 | 2017-01-31 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051896 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | RTR | FUN | SI | Onshore | Bodfeld; Frank | SAP | Yes | CapEx | Localization | IT - External | 104h | 0h | 104h | 2016-09-12 | 2016-11-18 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051897 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | SI | Onshore | Bodfeld; Frank | SAP | Yes | CapEx | Localization | IT - External | 104h | 0h | 104h | 2016-12-19 | 2017-02-14 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 32 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051898 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - RTR | RTR | FUN | SI | Onshore | Bodfeld; Frank | SAP | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-02 | 2017-02-13 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051899 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | RTR | FUN | SI | Onshore | Bodfeld; Frank | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051900 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | RTR | FUN | SI | Onshore | Beiderhase; Thomas | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051901 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Management (Hypercare) - PTM | RTR | FUN | SI | Onshore | Beiderhase; Thomas | SAP | Yes | CapEx | Localization | IT - External | 64h | 0h | 64h | 2017-02-06 | 2017-02-17 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051902 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | SI | Onshore | Beiderhase; Thomas | SAP | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2016-12-20 | 2016-12-23 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051903 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Management (Hypercare) - RTR | RTR | FUN | SI | Onshore | Beiderhase; Thomas | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051904 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Management (Cutover/Go-live) | RTR | FUN | SI | Onshore | Beiderhase; Thomas | SAP | Yes | CapEx | Localization | IT - External | 120h | 0h | 120h | 2016-12-12 | 2017-02-01 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 12 | 16 | 40 | 8 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051905 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | RTR | FUN | SI | Onshore | Beiderhase; Thomas | SAP | Yes | CapEx | Localization | IT - External | 268h | 0h | 268h | 2016-09-12 | 2016-11-24 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051906 | No | Yes | No | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | RTR | FUN | SI | Onshore | Kranich; Oliver | SAP | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2016-09-13 | 2016-11-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051907 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Validate | RTR | FUN | SI | Onshore | Kranich; Oliver | SAP | Yes | OpEx | Localization | IT - External | 6h | 0h | 6h | 2016-08-29 | 2016-09-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051908 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Solution Design Document (SDD) | RTR | FUN | SI | Onshore | Kranich; Oliver | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051909 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Validate | RTR | FUN | SI | Onshore | Kranich; Oliver | SAP | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051910 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Prep | RTR | FUN | SI | Onshore | Kranich; Oliver | SAP | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2016-10-18 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051911 | No | Yes | No | Argentina | Argentina | 04-Test | Prep PRD for performance testing | RTR | FUN | SI | Onshore | Kranich; Oliver | SAP | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2016-10-25 | 2016-10-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051912 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Prepare | RTR | FUN | SI | Onshore | Kranich; Oliver | SAP | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051913 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Prepare | RTR | FUN | SI | Onshore | Kranich; Oliver | SAP | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2016-09-12 | 2016-09-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051914 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | SI | Onshore | Kranich; Oliver | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051915 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | RTR | FUN | SI | Onshore | Kranich; Oliver | SAP | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2016-09-14 | 2016-09-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051916 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | RTR | FUN | SI | Onshore | Kranich; Oliver | SAP | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2016-10-20 | 2016-10-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051917 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - RTR | RTR | FUN | SI | Onshore | Kranich; Oliver | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051918 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - RTR | RTR | FUN | SI | Onshore | Kranich; Oliver | SAP | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051919 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | RTR | FUN | SI | Onshore | Kranich; Oliver | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051920 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | RTR | FUN | SI | Onshore | Kranich; Oliver | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051921 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | RTR | FUN | SI | Onshore | Kranich; Oliver | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051922 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | RTR | FUN | SI | Onshore | Kranich; Oliver | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051923 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | RTR | FUN | SI | Onshore | Kranich; Oliver | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051924 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | RTR | FUN | SI | Onshore | Kranich; Oliver | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051925 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Run Tests | RTR | FUN | SI | Onshore | Kranich; Oliver | SAP | Yes | CapEx | Localization | IT - External | 70h | 0h | 70h | 2016-11-03 | 2016-11-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051926 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Manage Defects | RTR | FUN | SI | Onshore | Kranich; Oliver | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051927 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Break/Fix | RTR | FUN | SI | Onshore | Kranich; Oliver | SAP | Yes | CapEx | Localization | IT - External | 34h | 0h | 34h | 2016-11-14 | 2016-11-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051928 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | RTR | FUN | SI | Onshore | Kranich; Oliver | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051929 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PTM | FUN | SI | Onshore | Roth; Edgar | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051930 | No | Yes | No | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTM | FUN | SI | Onshore | Roth; Edgar | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051931 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTM | FUN | SI | Onshore | Roth; Edgar | SAP | Yes | OpEx | Localization | IT - External | 84h | 0h | 84h | 2017-02-03 | 2017-02-24 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 48 | 20 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051932 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - PTM | PTM | FUN | SI | Onshore | Roth; Edgar | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051933 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - RTR | PTM | FUN | SI | Onshore | Roth; Edgar | SAP | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-02 | 2017-02-07 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051934 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - PTM | PTM | FUN | SI | Onshore | Hagelauer; Harald | SAP | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2016-06-27 | 2016-06-30 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051935 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - PTM | PTM | FUN | SI | Onshore | Hagelauer; Harald | SAP | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2017-02-03 | 2017-02-16 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 12 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051936 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | SI | Onshore | Hagelauer; Harald | SAP | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-02-06 | 2017-03-23 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051937 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTM | FUN | SI | Onshore | Hagelauer; Harald | SAP | Yes | OpEx | Localization | IT - External | 88h | 0h | 88h | 2017-02-20 | 2017-03-03 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051938 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTM - Run Tests | PTM | FUN | SI | Onshore | Hagelauer; Harald | SAP | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2016-11-21 | 2016-12-02 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051939 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTM - Break/Fix | PTM | FUN | SI | Onshore | Hagelauer; Harald | SAP | Yes | CapEx | Localization | IT - External | 172h | 0h | 172h | 2016-10-24 | 2016-12-15 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051940 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | PTM | FUN | SI | Onshore | Hagelauer; Harald | SAP | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2016-12-12 | 2016-12-12 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051941 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | PTM | FUN | SI | Onshore | Hagelauer; Harald | SAP | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2016-12-05 | 2016-12-06 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051942 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTM | FUN | SI | Onshore | Hagelauer; Harald | SAP | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-01-23 | 2017-01-27 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051943 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTM | FUN | SI | Onshore | Hagelauer; Harald | SAP | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2016-12-09 | 2017-01-20 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 12 | 8 | 12 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051944 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | PTM | FUN | SI | Onshore | Hagelauer; Harald | SAP | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2016-12-12 | 2016-12-12 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051945 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTM | FUN | SI | Onshore | Hagelauer; Harald | SAP | Yes | CapEx | Localization | IT - External | 128h | 0h | 128h | 2016-09-05 | 2016-09-29 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051946 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTM | FUN | SI | Onshore | Hagelauer; Harald | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051947 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Functional Specification (FSD) | PTM | FUN | SI | Onshore | Hagelauer; Harald | SAP | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2016-08-09 | 2016-08-12 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051948 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | PTM | FUN | SI | Onshore | Hagelauer; Harald | SAP | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-03 | 2016-10-03 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051949 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTM | FUN | SI | Onshore | Hagelauer; Harald | SAP | Yes | OpEx | Localization | IT - External | 52h | 0h | 52h | 2016-10-03 | 2016-10-13 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051950 | No | No | Yes | Argentina | Argentina | 06-Hypercare | DMS Argentina Production Support - PTM | PTM | FUN | SI | Onshore | Hagelauer; Harald | SAP | Yes | OpEx | Localization | IT - External | 40h | 0h | 40h | 2017-04-10 | 2017-04-28 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051951 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - Prep | PTM | FUN | SI | Onshore | Hagelauer; Harald | SAP | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2016-10-31 | 2016-11-03 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051952 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PTM | FUN | SI | Onshore | Hagelauer; Harald | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051953 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051954 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - Prep | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 84h | 0h | 84h | 2016-10-10 | 2016-11-04 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051955 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | OpEx | Localization | IT - External | 38.5h | 0h | 38.5h | 2016-10-04 | 2016-10-21 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051956 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-03 | 2016-10-03 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051957 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 168h | 0h | 168h | 2016-09-05 | 2016-12-02 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051958 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2016-09-06 | 2016-09-16 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051959 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051960 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2016-12-12 | 2016-12-16 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051961 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 64h | 0h | 64h | 2016-12-19 | 2017-01-27 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 10 | 10 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051962 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 116h | 0h | 116h | 2016-12-05 | 2017-01-27 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 16 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051963 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051964 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051965 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTM - Break/Fix | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2016-11-21 | 2016-12-08 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051966 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTM - Run Tests | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 42h | 0h | 42h | 2016-11-07 | 2016-12-02 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051967 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | OpEx | Localization | IT - External | 80h | 0h | 80h | 2017-02-06 | 2017-02-24 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 36 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051968 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2017-02-06 | 2017-02-12 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051969 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - PTM | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-01-30 | 2017-02-06 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051970 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - PTM | PTM | FUN | SI | Onshore | Coll-Vinent; Javier | SAP | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2016-07-11 | 2016-07-29 | Yes |  | DMS |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051971 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | Saputo | Onshore | Durham; Cecil | Saputo | Yes | CapEx | Localization | Business | 20h | 0h | 20h | 2017-02-06 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051972 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTM | FUN | Saputo | Onshore | Durham; Cecil | Saputo | Yes | OpEx | Localization | Business | 20h | 0h | 20h | 2017-01-23 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051973 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTM | FUN | Saputo | Onshore | Durham; Cecil | Saputo | Yes | CapEx | Localization | Business | 110h | 0h | 110h | 2016-12-19 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051974 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTM - Run Tests | PTM | FUN | Saputo | Onshore | Durham; Cecil | Saputo | Yes | CapEx | Localization | Business | 20h | 0h | 20h | 2016-10-31 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051975 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | PTM | FUN | Saputo | Onshore | Durham; Cecil | Saputo | Yes | OpEx | Localization | Business | 10h | 0h | 10h | 2016-10-21 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051976 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | PTM | FUN | Saputo | Onshore | Durham; Cecil | Saputo | Yes | OpEx | Localization | Business | 15h | 0h | 15h | 2016-10-10 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051977 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | PTM | FUN | Saputo | Onshore | Durham; Cecil | Saputo | Yes | CapEx | Localization | Business | 10h | 0h | 10h | 2016-11-14 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051978 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTM | FUN | Saputo | Onshore | Durham; Cecil | Saputo | Yes | CapEx | Localization | Business | 10h | 0h | 10h | 2016-10-24 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051979 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Support | PTM | FUN | Saputo | Onshore | Durham; Cecil | Saputo | Yes | OpEx | Localization | Business | 15h | 0h | 15h | 2016-08-22 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051980 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTM | FUN | Saputo | Onshore | Durham; Cecil | Saputo | Yes | CapEx | Localization | Business | 39.75h | 0h | 39.75h | 2016-09-26 | 2016-10-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051981 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Validate | PTM | FUN | Saputo | Onshore | Durham; Cecil | Saputo | Yes | OpEx | Localization | Business | 46h | 0h | 46h | 2016-08-08 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051982 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Data collection templates (DCT) - Explain and collect | PTM | FUN | Saputo | Onshore | Durham; Cecil | Saputo | Yes | CapEx | Localization | Business | 42h | 0h | 42h | 2016-08-15 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051983 | No | No | Yes | Argentina | Argentina | 10-PCR | Argentina new cheese line-PTM | PTM | FUN | Saputo | Onshore | Durham; Cecil | Saputo | Yes | CapEx | Localization | Business | 2.5h | 0h | 2.5h | 2017-04-24 | 2017-04-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051984 | No | No | Yes | Argentina | Argentina | 02-Analyze | PTM - Identfy Changes in GD for Localization ARG | PTM | FUN | Saputo | Onshore | Durham; Cecil | Saputo | Yes | CapEx | Localization | Business | 100.6h | 0h | 100.6h | 2016-02-29 | 2016-04-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051985 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - PTM | PTM | FUN | Saputo | Onshore | Durham; Cecil | Saputo | Yes | CapEx | Localization | Business | 23.65h | 0h | 23.65h | 2016-05-09 | 2016-07-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051986 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - PTM | PTM | FUN | Saputo | Onshore | Durham; Cecil | Saputo | Yes | CapEx | Localization | Business | 81.95h | 0h | 81.95h | 2016-05-09 | 2016-06-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051987 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTM | FUN | Saputo | Onshore | Durham; Cecil | Saputo | Yes | OpEx | Localization | Business | 46.5h | 0h | 46.5h | 2016-09-12 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051988 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | Saputo | Onshore | Durham; Cecil | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051989 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | PTM | FUN | Saputo | Onshore | Durham; Cecil | Saputo | Yes | OpEx | Localization | Business | 10h | 0h | 10h | 2016-10-11 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051990 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PTM | FUN | Saputo | Onshore | Durham; Cecil | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051991 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Data collection templates (DCT) - Explain and collect | PTM | FUN | Saputo | Onshore | Durham; Cecil | Saputo | Yes | CapEx | Localization | Business | 15h | 0h | 15h | 2016-08-08 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051992 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PMO | PMO | SI | Onshore | Rahman; Maiko | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051993 | No | Yes | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | TAI | TAI | SI | Onshore | Lau; Kim | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051994 | No | Yes | Yes | Argentina | Argentina | 04-Test | TEST - Technical Architecture and Infrastructure (gen) | TAI | TAI | SI | Onshore | Lau; Kim | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-01 | 2016-09-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051995 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTP | FUN | SI | Onshore | Chandrakanthan; Muthukumar | Accenture | Yes | CapEx | Localization | IT - External | 58h | 0h | 58h | 2016-09-12 | 2016-09-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051996 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | PTP | FUN | SI | Onshore | Chandrakanthan; Muthukumar | Accenture | Yes | CapEx | Localization | IT - External | 84h | 0h | 84h | 2016-09-12 | 2016-11-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051997 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Solution Design Document (SDD) | PTP | FUN | SI | Onshore | Chandrakanthan; Muthukumar | Accenture | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2016-08-17 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051998 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Unit testing Configuration Documentation | PTP | FUN | SI | Onshore | Chandrakanthan; Muthukumar | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051999 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | PTP | FUN | SI | Onshore | Chandrakanthan; Muthukumar | Accenture | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2016-11-07 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052000 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | PTP | FUN | SI | Onshore | Chandrakanthan; Muthukumar | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052001 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | PTP | FUN | SI | Onshore | Chandrakanthan; Muthukumar | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-11-21 | 2016-11-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052002 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | PTP | FUN | SI | Onshore | Chandrakanthan; Muthukumar | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052003 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTP | FUN | SI | Onshore | Chandrakanthan; Muthukumar | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052004 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | PTP | FUN | SI | Onshore | Chandrakanthan; Muthukumar | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052005 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - Prep | PTP | FUN | SI | Onshore | Chandrakanthan; Muthukumar | Accenture | Yes | CapEx | Localization | IT - External | 72h | 0h | 72h | 2016-10-11 | 2016-10-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052006 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTP | FUN | SI | Onshore | Chandrakanthan; Muthukumar | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052007 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | PTP | FUN | SI | Onshore | Chandrakanthan; Muthukumar | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052008 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTP | FUN | SI | Onshore | Chandrakanthan; Muthukumar | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052009 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PTP | FUN | SI | Onshore | Chandrakanthan; Muthukumar | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052010 | No | Yes | No | Argentina | Argentina | 04-Test | Updates concepts decks | PTP | FUN | SI | Onshore | Chandrakanthan; Muthukumar | Accenture | Yes | OpEx | Localization | IT - External | 18h | 0h | 18h | 2016-10-03 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052011 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - PTP - Break/Fix | PTP | FUN | SI | Onshore | Chandrakanthan; Muthukumar | Accenture | Yes | CapEx | Localization | IT - External | 43h | 0h | 43h | 2016-10-31 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052012 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Support | PTP | FUN | SI | Onshore | Chandrakanthan; Muthukumar | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-18 | 2016-10-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052013 | No | Yes | No | Argentina | Argentina | 02-Analyze | PTP - Identify Changesin GD for Localization ARG | PTP | FUN | SI | Onshore | Chandrakanthan; Muthukumar | Accenture | Yes | CapEx | Localization | IT - External | 37h | 0h | 37h | 2016-02-29 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052014 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - PTP | PTP | FUN | SI | Onshore | Chandrakanthan; Muthukumar | Accenture | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2016-05-02 | 2016-05-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052015 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- PTP | PTP | FUN | SI | Onshore | Chandrakanthan; Muthukumar | Accenture | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2016-05-26 | 2016-05-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052016 | No | Yes | No | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTP | FUN | SI | Onshore | Chandrakanthan; Muthukumar | Accenture | Yes | CapEx | Localization | IT - External | 38h | 0h | 38h | 2016-10-03 | 2016-11-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052017 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PMO | PTP | FUN | SI | Onshore | Chandrakanthan; Muthukumar | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052018 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PMO | PMO | SI | Onshore | May; Charles | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052019 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- RTR | PMO | PMO | SI | Onshore | May; Charles | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052020 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - RTR | PMO | PMO | SI | Onshore | May; Charles | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052021 | No | Yes | No | Argentina | Argentina | 02-Analyze | RTR - Identify Changes in GD for Localization ARG | PMO | PMO | SI | Onshore | May; Charles | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2016-03-07 | 2016-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052022 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052023 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG - Manage and execute communications | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | OpEx | Localization | IT - Internal | 116h | 0h | 116h | 2016-05-02 | 2016-07-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052024 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTM Prepare Role Mapping Onboarding Deck | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052025 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTM Schedule and Prepare workshops (variances by process areas) | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-23 | 2016-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052026 | No | Yes | No | Argentina | Argentina | 02-Analyze | Arg: PTM Update Execution Plans (Comm, training, transition) | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052027 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: OTC Prepare Role Mapping Onboarding Deck | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052028 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: OTC Schedule and Prepare workshops (variances by process areas) | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-16 | 2016-05-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052029 | No | Yes | No | Argentina | Argentina | 02-Analyze | Arg: OTC Update Execution Plans (Comm, training, transition) | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052030 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: RTR Schedule and Prepare workshops (variances by process areas) | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-16 | 2016-05-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052031 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTP Schedule and Prepare workshops (variances by process areas) | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-16 | 2016-05-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052032 | No | Yes | No | Argentina | Argentina | 02-Analyze | Arg: RTR Update Execution Plans (Comm, training, transition) | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052033 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTP Prepare Role Mapping Onboarding Deck | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052034 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: RTR Prepare Role Mapping Onboarding Deck | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052035 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: LOG Schedule and Prepare workshops (variances by process areas) | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-16 | 2016-05-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052036 | No | Yes | No | Argentina | Argentina | 02-Analyze | Arg: PTP Update Execution Plans (Comm, training, transition) | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052037 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: LOG Prepare Role Mapping Onboarding Deck | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052038 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : PTM Package the change in a presentable form | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-06-06 | 2016-06-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052039 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : OTC Package the change in a presentable form | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-06-06 | 2016-06-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052040 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : RTR Package the change in a presentable form | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-06-06 | 2016-06-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052041 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : LOG Create Transition Plan presentation | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052042 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : RTR Create Transition Plan presentation | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052043 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : PTP Create Transition Plan presentation | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052044 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : OTC Create Transition Plan presentation | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052045 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: Localized Communication Plan | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052046 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : PTM Create Transition Plan presentation | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052047 | No | Yes | No | Argentina | Argentina | 02-Analyze | Arg: LOG Update Execution Plans (Comm, training, transition) | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052048 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : PTP Package the change in a presentable form | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-06-06 | 2016-06-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052049 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : LOG Package the change in a presentable form | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-06-06 | 2016-06-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052050 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: Prepare presentation to be used by DCL to get buy-in from Owners | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052051 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: Prepare decks for DCL meeting with managers | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-11 | 2016-04-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052052 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: Plan and Ajustment | CM | CM | Saputo | Onshore | Lemyre McCraw; Christina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052053 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PMO | PMO | Saputo | Onshore | Razavinia; Nayereh | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052054 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PMO | PMO | PMO | Saputo | Onshore | Razavinia; Nayereh | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-06 | 2017-03-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052055 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052056 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG - Manage and execute communications | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 70h | 0h | 70h | 2016-05-09 | 2016-06-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052057 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Translate presentation | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052058 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : Kick off meeting with Change Agents and DCL | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052059 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : Communicate to the Divisions | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 46h | 0h | 46h | 2016-05-02 | 2016-05-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052060 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: Plan and Ajustment | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052061 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : LOG Package the change in a presentable form | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-06-06 | 2016-06-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052062 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: Prepare presentation to be used by DCL to get buy-in from Owners | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052063 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : OTC Create Transition Plan presentation | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052064 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: Prepare decks for DCL meeting with managers | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 39h | 0h | 39h | 2016-04-11 | 2016-04-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052065 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: Localized Communication Plan | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052066 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : RTR Create Transition Plan presentation | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052067 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : PTM Create Transition Plan presentation | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052068 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : PTP Create Transition Plan presentation | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052069 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : LOG Create Transition Plan presentation | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052070 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : PTP Package the change in a presentable form | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-06-06 | 2016-06-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052071 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : RTR Package the change in a presentable form | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-06-06 | 2016-06-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052072 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : OTC Package the change in a presentable form | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-06-06 | 2016-06-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052073 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : PTM Package the change in a presentable form | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-06-06 | 2016-06-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052074 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: LOG Schedule and Prepare workshops (variances by process areas) | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-16 | 2016-05-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052075 | No | Yes | No | Argentina | Argentina | 02-Analyze | Arg: LOG Update Execution Plans (Comm, training, transition) | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052076 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: RTR Schedule and Prepare workshops (variances by process areas) | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-16 | 2016-05-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052077 | No | Yes | No | Argentina | Argentina | 02-Analyze | Arg: RTR Update Execution Plans (Comm, training, transition) | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052078 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTP Prepare Role Mapping Onboarding Deck | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052079 | No | Yes | No | Argentina | Argentina | 02-Analyze | Arg: PTP Update Execution Plans (Comm, training, transition) | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052080 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: LOG Prepare Role Mapping Onboarding Deck | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052081 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTP Schedule and Prepare workshops (variances by process areas) | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-16 | 2016-05-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052082 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: OTC Prepare Role Mapping Onboarding Deck | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052083 | No | Yes | No | Argentina | Argentina | 02-Analyze | Arg: OTC Update Execution Plans (Comm, training, transition) | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052084 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: RTR Prepare Role Mapping Onboarding Deck | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052085 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTM Schedule and Prepare workshops (variances by process areas) | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-23 | 2016-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052086 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTM Prepare Role Mapping Onboarding Deck | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052087 | No | Yes | No | Argentina | Argentina | 02-Analyze | Arg: PTM Update Execution Plans (Comm, training, transition) | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052088 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: OTC Schedule and Prepare workshops (variances by process areas) | CM | CM | Saputo | Onshore | Leblanc; Francoise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-16 | 2016-05-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052089 | No | No | Yes | Argentina | Argentina | 04-Test | LOG - SIT 2 - Run Tests | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 86h | 0h | 86h | 2016-10-31 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052090 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - Prep | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 72.4h | 0h | 72.4h | 2016-10-11 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052091 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2016-11-12 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052092 | No | No | Yes | Argentina | Argentina | 04-Test | LOG - SIT 2 - Break/Fix | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 50.8h | 0h | 50.8h | 2016-10-31 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052093 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-11-15 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052094 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 41.2h | 0h | 41.2h | 2016-12-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 11.2 | 5 | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052095 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 53h | 0h | 53h | 2016-12-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 16 | 5 | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052096 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | OpEx | Localization | IT - External | 99h | 0h | 99h | 2017-02-20 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052097 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 120h | 0h | 120h | 2016-12-05 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 8 | 34 | 14 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052098 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2016-11-15 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052099 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052100 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 109.8h | 0h | 109.8h | 2016-09-06 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052101 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 123.6h | 0h | 123.6h | 2016-09-06 | 2016-10-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052102 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Prepare | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | OpEx | Localization | IT - External | 42.1h | 0h | 42.1h | 2016-08-15 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052103 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-11-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052104 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 165.8h | 0h | 165.8h | 2017-02-06 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62.8 | 70 | 10 | 9 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052105 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG KT visit | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2016-08-15 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052106 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - LOG | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 4.53h | 0h | 4.53h | 2016-05-24 | 2016-06-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052107 | No | No | Yes | Argentina | Argentina | 02-Analyze | LOG - Identify changes in GD for Localization ARG | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 86.35h | 0h | 86.35h | 2016-02-29 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052108 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 98h | 0h | 98h | 2017-01-23 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052109 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Validate | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052110 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Support | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | OpEx | Localization | IT - External | 47.8h | 0h | 47.8h | 2016-08-01 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052111 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | OpEx | Localization | IT - External | 28.6h | 0h | 28.6h | 2016-09-12 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052112 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | OpEx | Localization | IT - External | 56.6h | 0h | 56.6h | 2016-10-07 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052113 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | OpEx | Localization | IT - External | 2.6h | 0h | 2.6h | 2016-10-17 | 2016-11-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052114 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - LOG | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 24.85h | 0h | 24.85h | 2016-05-02 | 2016-05-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052115 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | LOG | FUN | SI | Onshore | Alphonse; David | IBM | Yes | CapEx | Localization | IT - External | 84h | 0h | 84h | 2016-12-05 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052116 | No | Yes | No | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTP | FUN | SI | Onshore | Louay; Abuomar | SAP | Yes | CapEx | Localization | IT - External | 440h | 0h | 440h | 2016-09-07 | 2016-12-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052117 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTP | FUN | SI | Onshore | Louay; Abuomar | SAP | Yes | CapEx | Localization | IT - External | 82h | 0h | 82h | 2016-12-20 | 2017-01-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052118 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | PTP | FUN | SI | Onshore | Louay; Abuomar | SAP | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2016-12-12 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052119 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | PTP | FUN | SI | Onshore | Louay; Abuomar | SAP | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2017-01-24 | 2017-01-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052120 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- PTP | PTP | FUN | SI | Onshore | Louay; Abuomar | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052121 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - PTP | PTP | FUN | SI | Onshore | Louay; Abuomar | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052122 | No | Yes | No | Argentina | Argentina | 02-Analyze | PTP - Identify Changesin GD for Localization ARG | PTP | FUN | SI | Onshore | Louay; Abuomar | SAP | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2016-02-29 | 2016-03-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052123 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Landed Onshore | Tubati; Pavan | IBM | Yes | CapEx | Localization | IT - External | 276h | 0h | 276h | 2016-12-05 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 36 | 44 | 36 | 27 | 36 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052124 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | SI | Landed Onshore | Tubati; Pavan | IBM | Yes | OpEx | Localization | IT - External | 230h | 0h | 230h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 72 | 66 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052125 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Landed Onshore | Tubati; Pavan | IBM | Yes | CapEx | Localization | IT - External | 69h | 0h | 69h | 2016-05-09 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052126 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Landed Onshore | Tubati; Pavan | IBM | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-05-02 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052127 | No | No | Yes | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Landed Onshore | Tubati; Pavan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052128 | No | No | Yes | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Landed Onshore | Tubati; Pavan | IBM | Yes | CapEx | Localization | IT - External | 176h | 0h | 176h | 2016-09-06 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052129 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | SI | Landed Onshore | Tubati; Pavan | IBM | Yes | OpEx | Localization | IT - External | 363.5h | 0h | 363.5h | 2017-03-06 | 2017-07-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 22 | 22 | 22 | 22 | 17.5 | 17 | 17 | 17 | 16 | 17 | 22 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052130 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Landed Onshore | Tubati; Pavan | IBM | Yes | CapEx | Localization | IT - External | 62h | 0h | 62h | 2016-08-22 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052131 | No | No | Yes | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Landed Onshore | Tubati; Pavan | IBM | Yes | OpEx | Global | IT - External | 5h | 0h | 5h | 2017-05-29 | 2017-06-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052132 | No | Yes | Yes | Argentina | Argentina | 02-Analyze | PTP - Identify Changesin GD for Localization ARG | PTP | FUN | SI | Onshore | Sweetman; kelly | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-02-29 | 2016-02-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052133 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - PTP | PTP | FUN | SI | Onshore | Sweetman; kelly | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052134 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- PTP | PTP | FUN | SI | Onshore | Sweetman; kelly | SAP | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2016-05-16 | 2016-05-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052135 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PTM | FUN | Saputo | Onshore | Tenhagen; Chris | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052136 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | Saputo | Onshore | Tenhagen; Chris | Saputo | Yes | OpEx | Localization | Business | 80h | 0h | 80h | 2017-04-03 | 2017-04-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052137 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Data collection templates (DCT) - Explain and collect | PTM | FUN | Saputo | Onshore | Tenhagen; Chris | Saputo | Yes | CapEx | Localization | Business | 21.6h | 0h | 21.6h | 2016-08-09 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052138 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Validate | PTM | FUN | Saputo | Onshore | Tenhagen; Chris | Saputo | Yes | OpEx | Localization | Business | 22h | 0h | 22h | 2016-08-15 | 2016-09-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052139 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Functional Specification (FSD) | PTM | FUN | Saputo | Onshore | Tenhagen; Chris | Saputo | Yes | CapEx | Localization | Business | 10h | 0h | 10h | 2016-08-08 | 2016-08-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052140 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTM | FUN | Saputo | Onshore | Tenhagen; Chris | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052141 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTM | FUN | Saputo | Onshore | Tenhagen; Chris | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052142 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTM | FUN | Saputo | Onshore | Tenhagen; Chris | Saputo | Yes | CapEx | Localization | Business | 35h | 0h | 35h | 2016-09-12 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052143 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - PTM | PTM | FUN | Saputo | Onshore | Tenhagen; Chris | Saputo | Yes | CapEx | Localization | Business | 10h | 0h | 10h | 2016-07-18 | 2016-07-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052144 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 3h | 0h | 3h | 2017-01-09 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052145 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052146 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052147 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTP | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 45h | 0h | 45h | 2017-03-20 | 2017-06-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 2 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052148 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 3h | 0h | 3h | 2016-10-18 | 2016-11-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052149 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Management (Cutover/Go-live) | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 235.5h | 0h | 235.5h | 2016-12-12 | 2017-02-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 29 | 42.5 | 43 | 35 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052150 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 13h | 0h | 13h | 2017-01-23 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052151 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Management (Hypercare) | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 133h | 0h | 133h | 2017-02-06 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67.5 | 29 | 36.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052152 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052153 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 19h | 0h | 19h | 2016-12-19 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052154 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052155 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 26h | 0h | 26h | 2017-02-06 | 2017-02-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052156 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052157 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-11-14 | 2016-11-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052158 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 66.5h | 0h | 66.5h | 2016-11-21 | 2016-12-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052159 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 29h | 0h | 29h | 2016-11-07 | 2016-11-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052160 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Support | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 49h | 0h | 49h | 2016-08-08 | 2016-08-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052161 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Validate | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-08-16 | 2016-08-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052162 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-11-11 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052163 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Data collection templates (DCT) - Explain and collect | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-08-14 | 2016-08-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052164 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 339h | 0h | 339h | 2016-09-07 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052165 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTP | FUN | Saputo | Onshore | Desrochers; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 214.5h | 0h | 214.5h | 2016-09-12 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052166 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | LOG | FUN | Saputo | Onshore | Seabrook; Vern | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052167 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | EDI | EDI | Saputo | Onshore | Tanguay; Yves | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052168 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | EDI | EDI | Saputo | Onshore | Tanguay; Yves | Saputo | Yes | OpEx | Localization | IT - Internal | 2h | 0h | 2h | 2016-10-12 | 2016-10-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052169 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | EDI | EDI | Saputo | Onshore | Tanguay; Yves | Saputo | Yes | CapEx | Localization | IT - Internal | 17h | 0h | 17h | 2016-11-21 | 2016-12-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052170 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | EDI | EDI | Saputo | Onshore | Tanguay; Yves | Saputo | Yes | CapEx | Localization | IT - Internal | 31.5h | 0h | 31.5h | 2017-01-23 | 2017-02-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 21.5 | 3 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052171 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | EDI | EDI | Saputo | Onshore | Tanguay; Yves | Saputo | Yes | OpEx | Localization | IT - Internal | 13.75h | 0h | 13.75h | 2017-03-22 | 2017-05-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 3.5 | 1.25 | 1.25 | 0.75 | 1.25 | 1.25 | 1.75 | 1.25 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052172 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Develop EDI mappings and communication | EDI | EDI | Saputo | Onshore | Tanguay; Yves | Saputo | Yes | CapEx | Localization | IT - Internal | 31h | 0h | 31h | 2016-07-15 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052173 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | EDI | EDI | Saputo | Onshore | Tanguay; Yves | Saputo | Yes | OpEx | Localization | IT - Internal | 4.75h | 0h | 4.75h | 2017-02-06 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052174 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | Saputo | Onshore | Archambault; Yannick | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-12-28 | 2016-12-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052175 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Validate | LOG | FUN | Saputo | Onshore | Archambault; Yannick | Saputo | Yes | OpEx | Localization | IT - Internal | 74h | 0h | 74h | 2016-08-17 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052176 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | LOG | FUN | Saputo | Onshore | Archambault; Yannick | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052177 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | LOG | FUN | Saputo | Onshore | Archambault; Yannick | Saputo | Yes | CapEx | Localization | IT - Internal | 6h | 0h | 6h | 2016-12-05 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052178 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | LOG | FUN | Saputo | Onshore | Archambault; Yannick | Saputo | Yes | CapEx | Localization | IT - Internal | 59h | 0h | 59h | 2016-12-05 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052179 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | LOG | FUN | Saputo | Onshore | Archambault; Yannick | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052180 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | LOG | FUN | Saputo | Onshore | Archambault; Yannick | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052181 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | LOG | FUN | Saputo | Onshore | Archambault; Yannick | Saputo | Yes | CapEx | Localization | IT - Internal | 52h | 0h | 52h | 2016-12-12 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052182 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | LOG | FUN | Saputo | Onshore | Archambault; Yannick | Saputo | Yes | CapEx | Localization | IT - Internal | 180h | 0h | 180h | 2016-12-19 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 40 | 20 | 40 | 20 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052183 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | LOG | FUN | Saputo | Onshore | Archambault; Yannick | Saputo | Yes | CapEx | Localization | IT - Internal | 130h | 0h | 130h | 2016-12-19 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052184 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | Saputo | Onshore | Archambault; Yannick | Saputo | Yes | OpEx | Localization | IT - Internal | 78h | 0h | 78h | 2016-12-01 | 2017-02-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052185 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | LOG | FUN | Saputo | Onshore | Archambault; Yannick | Saputo | Yes | CapEx | Localization | IT - Internal | 60h | 0h | 60h | 2017-02-06 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052186 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-LOG | LOG | FUN | Saputo | Onshore | Archambault; Yannick | Saputo | Yes | OpEx | Localization | IT - Internal | 41h | 0h | 41h | 2017-03-20 | 2017-06-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 6 | 4 | 2 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 6.5 | 6 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052187 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | LOG | FUN | Saputo | Onshore | Archambault; Yannick | Saputo | Yes | OpEx | Localization | IT - Internal | 70h | 0h | 70h | 2016-10-17 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052188 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | LOG | FUN | Saputo | Onshore | Archambault; Yannick | Saputo | Yes | OpEx | Localization | IT - Internal | 96h | 0h | 96h | 2016-11-07 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052189 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Manage Defects | LOG | FUN | Saputo | Onshore | Archambault; Yannick | Saputo | Yes | CapEx | Localization | IT - Internal | 25h | 0h | 25h | 2016-09-06 | 2016-09-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052190 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | LOG | FUN | Saputo | Onshore | Archambault; Yannick | Saputo | Yes | OpEx | Localization | IT - Internal | 212h | 0h | 212h | 2016-09-06 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052191 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | LOG | FUN | Saputo | Onshore | Archambault; Yannick | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052192 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Support | LOG | FUN | Saputo | Onshore | Archambault; Yannick | Saputo | Yes | OpEx | Localization | IT - Internal | 30h | 0h | 30h | 2016-08-15 | 2016-09-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052193 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | LOG | FUN | Saputo | Onshore | Archambault; Yannick | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052194 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | LOG | FUN | Saputo | Onshore | Archambault; Yannick | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052195 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Management (Cutover/Go-live) | OTC | FUN | Saputo | Onshore | Larose; Line | Saputo | Yes | CapEx | Localization | IT - Internal | 377h | 0h | 377h | 2016-11-07 | 2017-01-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 32 | 32 | 40 | 40 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052196 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Management (Hypercare) | OTC | FUN | Saputo | Onshore | Larose; Line | Saputo | Yes | CapEx | Localization | IT - Internal | 113h | 0h | 113h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 28 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052197 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | OTC | FUN | Saputo | Onshore | Larose; Line | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052198 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | OTC | FUN | Saputo | Onshore | Larose; Line | Saputo | Yes | CapEx | Localization | IT - Internal | 275h | 0h | 275h | 2016-09-06 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052199 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | OTC | FUN | Saputo | Onshore | Larose; Line | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-11-21 | 2016-11-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052200 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | OTC | FUN | Saputo | Onshore | Larose; Line | Saputo | Yes | CapEx | Localization | IT - Internal | 10h | 0h | 10h | 2016-09-06 | 2016-09-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052201 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Support | OTC | FUN | Saputo | Onshore | Larose; Line | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052202 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG KT visit | OTC | FUN | Saputo | Onshore | Larose; Line | Saputo | Yes | CapEx | Localization | IT - Internal | 41h | 0h | 41h | 2016-08-08 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052203 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-OTC | OTC | FUN | Saputo | Onshore | Larose; Line | Saputo | Yes | OpEx | Localization | IT - Internal | 175h | 0h | 175h | 2017-03-20 | 2017-07-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 30 | 18 | 0 | 6 | 12 | 5 | 0 | 18 | 16 | 20 | 5 | 4 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052204 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | OTC | FUN | Saputo | Onshore | Larose; Line | Saputo | Yes | CapEx | Localization | IT - Internal | 102h | 0h | 102h | 2016-12-05 | 2016-12-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052205 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | OTC | FUN | Saputo | Onshore | Larose; Line | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-10-17 | 2016-10-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052206 | No | No | Yes | Argentina | Argentina | 04-Test | OTC - SIT 2 - Run Tests | OTC | FUN | Saputo | Onshore | Larose; Line | Saputo | Yes | CapEx | Localization | IT - Internal | 40h | 0h | 40h | 2016-10-24 | 2016-11-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052207 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | OTC | FUN | Saputo | Onshore | Larose; Line | Saputo | Yes | OpEx | Localization | IT - Internal | 16h | 0h | 16h | 2016-09-12 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052208 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | OTC | FUN | Saputo | Onshore | Larose; Line | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052209 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | OTC | FUN | Saputo | Onshore | Larose; Line | Saputo | Yes | CapEx | Localization | IT - Internal | 8h | 0h | 8h | 2016-12-05 | 2016-12-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052210 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | OTC | FUN | Saputo | Onshore | Larose; Line | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052211 | No | No | Yes | Argentina | Argentina | 10-PCR | Argentina new cheese line-OTC | OTC | FUN | Saputo | Onshore | Larose; Line | Saputo | Yes | CapEx | Localization | IT - Internal | 2h | 0h | 2h | 2017-05-03 | 2017-05-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052212 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-OTC | EDI | EDI | Saputo | Onshore | Szilbereisz; Norman | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052213 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | EDI | EDI | Saputo | Onshore | Szilbereisz; Norman | Saputo | Yes | CapEx | Localization | IT - Internal | 36h | 0h | 36h | 2017-01-11 | 2017-01-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 11 | 17 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052214 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG KT visit | EDI | EDI | Saputo | Onshore | Szilbereisz; Norman | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052215 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | EDI | EDI | Saputo | Onshore | Szilbereisz; Norman | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-11-21 | 2016-11-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052216 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | EDI | EDI | Saputo | Onshore | Szilbereisz; Norman | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052217 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | EDI | EDI | Saputo | Onshore | Szilbereisz; Norman | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052218 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Develop EDI mappings and communication | EDI | EDI | Saputo | Onshore | Szilbereisz; Norman | Saputo | Yes | CapEx | Localization | IT - Internal | 8h | 0h | 8h | 2016-09-12 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052219 | No | No | Yes | Argentina | Argentina |  | Perform project Planning and Control | EDI | EDI | Saputo | Onshore | Szilbereisz; Norman | Saputo | Yes | CapEx | Localization | IT - Internal | 843h | 0h | 843h | 2016-03-14 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052220 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG KT visit | Non ERP | Non ERP | Saputo | Onshore | Fournier; Guylaine | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052221 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | Non ERP | Non ERP | Saputo | Onshore | Beland; Yves | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052222 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | BI | BI | Saputo | Onshore | Arcuri; Rosalie | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052223 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | BI | BI | Saputo | Onshore | Arcuri; Rosalie | Saputo | Yes | CapEx | Localization | IT - Internal | 37h | 0h | 37h | 2017-01-17 | 2017-01-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 9.5 | 17.5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052224 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-BI | BI | BI | Saputo | Onshore | Arcuri; Rosalie | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052225 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | PCR 212 Interim Daily Operational KPI’s report | BI | BI | Saputo | Onshore | Arcuri; Rosalie | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052226 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | PCR 212 Interim Daily Operational KPI’s report | BI | BI | Saputo | Onshore | McCubbin; Andrew | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052227 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | BI | BI | Saputo | Onshore | McCubbin; Andrew | Saputo | Yes | CapEx | Localization | IT - Internal | 3.5h | 0h | 3.5h | 2017-01-20 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052228 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- RTR | BI | BI | Saputo | Onshore | Dupont; Normand | Saputo | Yes | CapEx | Localization | IT - Internal | 37h | 0h | 37h | 2016-06-13 | 2016-07-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052229 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-BI | BI | BI | Saputo | Onshore | Dupont; Normand | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052230 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | BI | BI | Saputo | Onshore | Dupont; Normand | Saputo | Yes | CapEx | Localization | IT - Internal | 15h | 0h | 15h | 2017-02-03 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052231 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | BI | BI | Saputo | Onshore | Dupont; Normand | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052232 | No | No | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | Saputo | Onshore | Boisvert; Claude | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052233 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | Saputo | Onshore | Tremblay; Denis | Saputo | Yes | OpEx | Localization | IT - Internal | 14.5h | 0h | 14.5h | 2017-03-20 | 2017-03-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052234 | No | No | Yes | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | Saputo | Onshore | Tremblay; Denis | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052235 | No | No | Yes | Argentina | Argentina | 04-Test | Development | DEV | DEV | Saputo | Onshore | Tremblay; Denis | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-08-22 | 2016-11-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052236 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | Saputo | Onshore | Tremblay; Denis | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052237 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | Saputo | Onshore | Tremblay; Denis | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052238 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-MDG-DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | OpEx | Localization | IT - Internal | 69h | 0h | 69h | 2017-05-03 | 2017-08-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 48 | 2 | 0 | 4 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
1052239 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | Saputo | Onshore | Nunez; Augusto | Saputo | Yes | CapEx | Localization | IT - Internal | 113h | 0h | 113h | 2016-09-19 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052240 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Hypercare/support | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-01 | 2017-02-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052241 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-SEC | MDG | DC | Saputo | Onshore | Perron; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052242 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Management (Hypercare) - PTM | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052243 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - PTM | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Localization | IT - Internal | 4h | 0h | 4h | 2016-06-27 | 2016-06-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052244 | No | No | Yes | Argentina | Argentina | 04-Test | Cutover Plan | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Localization | IT - Internal | 33h | 0h | 33h | 2016-08-08 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052245 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Localization | IT - Internal | 10h | 0h | 10h | 2016-11-14 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052246 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-10-03 | 2016-10-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052247 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTM - Run Tests | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Localization | IT - Internal | 30h | 0h | 30h | 2016-11-07 | 2016-11-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052248 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | OpEx | Localization | IT - Internal | 20h | 0h | 20h | 2016-10-17 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052249 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Localization | IT - Internal | 85h | 0h | 85h | 2016-12-26 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 24 | 30 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052250 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052251 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052252 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Management (Cutover/Go-live) | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Localization | IT - Internal | 217h | 0h | 217h | 2016-12-19 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 12 | 14 | 14 | 44 | 45 | 77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052253 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052254 | No | No | Yes | Argentina | Argentina | 10-PCR | Argentina new cheese line-PTM | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052255 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Functional Specification (FSD) | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Localization | IT - Internal | 8h | 0h | 8h | 2016-08-08 | 2016-08-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052256 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Localization | IT - Internal | 188h | 0h | 188h | 2016-09-06 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052257 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Localization | IT - Internal | 23h | 0h | 23h | 2016-09-06 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052258 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Localization | IT - Internal | 80h | 0h | 80h | 2016-12-12 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052259 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Validate | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | OpEx | Localization | IT - Internal | 17h | 0h | 17h | 2016-08-22 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052260 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | CapEx | Localization | IT - Internal | 21h | 0h | 21h | 2016-10-11 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052261 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | OpEx | Localization | IT - Internal | 4h | 0h | 4h | 2016-09-12 | 2016-09-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052262 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052263 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | PTM | FUN | Saputo | Onshore | Magnan; Gaby | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-10-03 | 2016-10-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052264 | No | No | Yes | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | Saputo | Onshore | Ho; Lien-Chi | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052265 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | Saputo | Onshore | Ho; Lien-Chi | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052266 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | Saputo | Onshore | Ho; Lien-Chi | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052267 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | OpEx | Localization | IT - Internal | 573.5h | 0h | 573.5h | 2017-03-06 | 2017-07-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 40 | 39 | 39.75 | 40 | 16.75 | 21 | 23 | 20 | 35.5 | 35.5 | 28.5 | 49 | 42.5 | 41.5 | 31 | 38.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052268 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-10-03 | 2016-10-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052269 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | OpEx | Localization | IT - Internal | 3h | 0h | 3h | 2016-09-12 | 2016-09-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052270 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052271 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | CapEx | Localization | IT - Internal | 28h | 0h | 28h | 2016-10-11 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052272 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | CapEx | Localization | IT - Internal | 48.83h | 0h | 48.83h | 2016-09-06 | 2016-09-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052273 | No | No | Yes | Argentina | Argentina | 10-PCR | Argentina new cheese line-PTM | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | CapEx | Localization | IT - Internal | 9h | 0h | 9h | 2017-04-18 | 2017-04-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052274 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | CapEx | Localization | IT - Internal | 40.25h | 0h | 40.25h | 2016-12-19 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052275 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | CapEx | Localization | IT - Internal | 1h | 0h | 1h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052276 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | CapEx | Localization | IT - Internal | 207.25h | 0h | 207.25h | 2016-12-19 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 28.5 | 37.5 | 27.5 | 35 | 37.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052277 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | OpEx | Localization | IT - Internal | 218h | 0h | 218h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 62 | 65 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052278 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTM - Run Tests | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | CapEx | Localization | IT - Internal | 68.75h | 0h | 68.75h | 2016-11-07 | 2016-11-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052279 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | OpEx | Localization | IT - Internal | 167.5h | 0h | 167.5h | 2016-10-17 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052280 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | CapEx | Localization | IT - Internal | 75.83h | 0h | 75.83h | 2016-12-05 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052281 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - PTM | PTM | FUN | Saputo | Onshore | Blaires; Nelson | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052282 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) (Saputo) - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052283 | No | No | Yes | Argentina | Argentina | 10-PCR | Argentina new cheese line-MDG-(Saputo) - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 2h | 0h | 2h | 2017-04-17 | 2017-04-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052284 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) (Saputo) - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-09-06 | 2016-09-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052285 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cutover - Dual Maintenance Argentina Materials (Saputo) - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 130h | 0h | 130h | 2017-01-09 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 38 | 47 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052286 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Hypercare Support (Saputo) - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 128h | 0h | 128h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 24 | 26 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052287 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Train-the-Trainer Materials (Saputo) - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 32h | 0h | 32h | 2016-12-15 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 24 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052288 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Material Master Offline/Work Instructions (Saputo) - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 97h | 0h | 97h | 2016-11-14 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052289 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-MDG-(Saputo - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 36h | 0h | 36h | 2017-03-20 | 2017-04-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 10 | 4 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052290 | No | No | Yes | Argentina | Argentina | 04-Test | SIT1 - Execution (Saputo) - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-09-11 | 2016-09-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052291 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Legacy Data Extraction (Saputo) - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 101h | 0h | 101h | 2016-05-02 | 2016-06-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052292 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Manage and Execute Legacy development - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 6h | 0h | 6h | 2016-05-26 | 2016-05-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052293 | No | No | Yes | Argentina | Argentina | 04-Test | SIT2 - Execution (Saputo) - DM | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052294 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | MDG | DM | Saputo | Onshore | Leboeuf; Martin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052295 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-CM | CM | CM | Saputo | Onshore | Bogan; Alina | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052296 | No | No | Yes | Argentina | Argentina | 04-Test | Work Instructions - Exercices DATA (technical writer + Dele) | CM | CM | Saputo | Onshore | Bogan; Alina | Saputo | Yes | OpEx | Localization | IT - Internal | 738.5h | 0h | 738.5h | 2016-09-19 | 2017-02-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 24 | 14 | 37.5 | 38.5 | 36 | 38 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052297 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | RTR | FUN | Saputo | Onshore | Amrine; Dave | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052298 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | RTR | FUN | Saputo | Onshore | Amrine; Dave | Saputo | Yes | CapEx | Localization | IT - Internal | 50h | 0h | 50h | 2016-10-10 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052299 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | RTR | FUN | Saputo | Onshore | Amrine; Dave | Saputo | Yes | CapEx | Localization | IT - Internal | 48h | 0h | 48h | 2017-01-30 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052300 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | RTR | FUN | Saputo | Onshore | Amrine; Dave | Saputo | Yes | OpEx | Localization | IT - Internal | 50h | 0h | 50h | 2016-10-11 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052301 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | Saputo | Onshore | Amrine; Dave | Saputo | Yes | CapEx | Localization | IT - Internal | 22h | 0h | 22h | 2017-01-04 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052302 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | RTR | FUN | Saputo | Onshore | Amrine; Dave | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052303 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | RTR | FUN | Saputo | Onshore | Amrine; Dave | Saputo | Yes | CapEx | Localization | IT - Internal | 25h | 0h | 25h | 2016-09-26 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052304 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | RTR | FUN | Saputo | Onshore | Amrine; Dave | Saputo | Yes | CapEx | Localization | IT - Internal | 120h | 0h | 120h | 2016-09-06 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052305 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Support | RTR | FUN | Saputo | Onshore | Amrine; Dave | Saputo | Yes | OpEx | Localization | IT - Internal | 120h | 0h | 120h | 2016-08-10 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052306 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - RTR | RTR | FUN | Saputo | Onshore | Amrine; Dave | Saputo | Yes | CapEx | Localization | IT - Internal | 220h | 0h | 220h | 2017-02-06 | 2017-03-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052307 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-RTR | RTR | FUN | Saputo | Onshore | Amrine; Dave | Saputo | Yes | OpEx | Localization | IT - Internal | 324h | 0h | 324h | 2017-03-20 | 2017-07-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 8 | 40 | 32 | 40 | 40 | 25 | 20 | 10 | 8 | 18 | 15 | 9 | 0 | 12 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052308 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | RTR | FUN | Saputo | Onshore | Amrine; Dave | Saputo | Yes | CapEx | Localization | IT - Internal | 104h | 0h | 104h | 2016-12-05 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 12 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052309 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Break/Fix | RTR | FUN | Saputo | Onshore | Amrine; Dave | Saputo | Yes | CapEx | Localization | IT - Internal | 22h | 0h | 22h | 2016-11-07 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052310 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Prep | RTR | FUN | Saputo | Onshore | Amrine; Dave | Saputo | Yes | CapEx | Localization | IT - Internal | 40h | 0h | 40h | 2016-10-17 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052311 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | RTR | FUN | Saputo | Onshore | Amrine; Dave | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052312 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | RTR | FUN | Saputo | Onshore | Amrine; Dave | Saputo | Yes | CapEx | Localization | IT - Internal | 37h | 0h | 37h | 2016-11-28 | 2016-12-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052313 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | RTR | FUN | Saputo | Onshore | Amrine; Dave | Saputo | Yes | CapEx | Localization | IT - Internal | 45h | 0h | 45h | 2016-11-07 | 2016-11-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052314 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052315 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-MDG-DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | OpEx | Localization | IT - Internal | 40h | 0h | 40h | 2017-04-03 | 2017-04-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052316 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | Saputo | Onshore | Wright; Susan | Saputo | Yes | CapEx | Localization | IT - Internal | 268h | 0h | 268h | 2016-09-06 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052317 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PMO | PMO | Saputo | Onshore | Iñiguez Manuel | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052318 | No | No | Yes | Argentina | Argentina |  | IT Application Management & Support | PMO | PMO | Saputo | Onshore | Iñiguez Manuel | Saputo | Yes | OpEx | Localization | IT - Internal | 713.63h | 0h | 713.63h | 2016-08-01 | 2017-04-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 3 | 14 | 8 | 6 | 12 | 43 | 40 | 60.5 | 43.5 | 40 | 0 | 42 | 18 | 40 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052319 | No | No | Yes | Argentina | Argentina |  | IT Application Management & Support | PMO | PMO | Saputo | Onshore | Leal Fernando | Saputo | Yes | OpEx | Localization | IT - Internal | 1,042.5h | 0h | 1,042.5h | 2016-08-01 | 2017-05-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 31 | 23.5 | 32 | 37 | 0 | 0 | 40 | 40 | 40 | 40 | 31 | 40 | 40 | 42.5 | 31.5 | 33.5 | 47 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052320 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PMO | PMO | Saputo | Onshore | Leal Fernando | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052321 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | PTP | FUN | Saputo | Onshore | Karch-Hahn; Denise | Saputo | Yes | OpEx | Localization | IT - Internal | 1h | 0h | 1h | 2016-11-09 | 2016-11-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052322 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTP - Run Tests | PTP | FUN | Saputo | Onshore | Karch-Hahn; Denise | Saputo | Yes | CapEx | Localization | IT - Internal | 4h | 0h | 4h | 2016-10-24 | 2016-11-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052323 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | PTP | FUN | Saputo | Onshore | Karch-Hahn; Denise | Saputo | Yes | OpEx | Localization | IT - Internal | 171.5h | 0h | 171.5h | 2016-10-03 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052324 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PTP | FUN | Saputo | Onshore | Karch-Hahn; Denise | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052325 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | PTP | FUN | Saputo | Onshore | Karch-Hahn; Denise | Saputo | Yes | CapEx | Localization | IT - Internal | 85.5h | 0h | 85.5h | 2017-01-30 | 2017-02-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.5 | 0 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052326 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | PTP | FUN | Saputo | Onshore | Karch-Hahn; Denise | Saputo | Yes | OpEx | Localization | IT - Internal | 22h | 0h | 22h | 2016-10-18 | 2016-11-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052327 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTP | FUN | Saputo | Onshore | Karch-Hahn; Denise | Saputo | Yes | OpEx | Localization | IT - Internal | 5h | 0h | 5h | 2016-10-03 | 2016-10-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052328 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTP | PTP | FUN | Saputo | Onshore | Karch-Hahn; Denise | Saputo | Yes | OpEx | Localization | IT - Internal | 90h | 0h | 90h | 2017-03-06 | 2017-03-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052329 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTP | FUN | Saputo | Onshore | Karch-Hahn; Denise | Saputo | Yes | CapEx | Localization | IT - Internal | 72h | 0h | 72h | 2016-12-19 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052330 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTP | FUN | Saputo | Onshore | Karch-Hahn; Denise | Saputo | Yes | CapEx | Localization | IT - Internal | 107h | 0h | 107h | 2016-09-07 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052331 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | PTP | FUN | Saputo | Onshore | Karch-Hahn; Denise | Saputo | Yes | CapEx | Localization | IT - Internal | 4h | 0h | 4h | 2016-09-12 | 2016-09-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052332 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTP | FUN | Saputo | Onshore | Karch-Hahn; Denise | Saputo | Yes | CapEx | Localization | IT - Internal | 67.5h | 0h | 67.5h | 2016-09-06 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052333 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Data collection templates (DCT) - Explain and collect | PTP | FUN | Saputo | Onshore | Karch-Hahn; Denise | Saputo | Yes | CapEx | Localization | IT - Internal | 14h | 0h | 14h | 2016-08-15 | 2016-08-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052334 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTP | FUN | Saputo | Onshore | Karch-Hahn; Denise | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-11-11 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052335 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Validate | PTP | FUN | Saputo | Onshore | Karch-Hahn; Denise | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-08-16 | 2016-08-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052336 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | PTP | FUN | Saputo | Onshore | Karch-Hahn; Denise | Saputo | Yes | CapEx | Localization | IT - Internal | 21h | 0h | 21h | 2016-11-14 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052337 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | PTP | FUN | Saputo | Onshore | Karch-Hahn; Denise | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052338 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | PTP | FUN | Saputo | Onshore | Karch-Hahn; Denise | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052339 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | PTP | FUN | Saputo | Onshore | Karch-Hahn; Denise | Saputo | Yes | OpEx | Localization | IT - Internal | 110h | 0h | 110h | 2017-02-20 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052340 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | PTP | FUN | Saputo | Onshore | Karch-Hahn; Denise | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052341 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTP | FUN | Saputo | Onshore | Karch-Hahn; Denise | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052342 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTP | FUN | Saputo | Onshore | Karch-Hahn; Denise | Saputo | Yes | CapEx | Localization | IT - Internal | 147.5h | 0h | 147.5h | 2016-12-27 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 12 | 0 | 45 | 45 | 45.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052343 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | PTP | FUN | Saputo | Onshore | Karch-Hahn; Denise | Saputo | Yes | CapEx | Localization | IT - Internal | 45h | 0h | 45h | 2016-12-12 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052344 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTP | FUN | Saputo | Onshore | Karch-Hahn; Denise | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052345 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Data collection templates (DCT) - Explain and collect | PTM | FUN | Saputo | Onshore | Olcott; Lisa | Saputo | Yes | CapEx | Localization | IT - Internal | 8h | 0h | 8h | 2016-08-08 | 2016-08-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052346 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Functional Specification (FSD) | PTM | FUN | Saputo | Onshore | Olcott; Lisa | Saputo | Yes | CapEx | Localization | IT - Internal | 16h | 0h | 16h | 2016-08-08 | 2016-08-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052347 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Validate | PTM | FUN | Saputo | Onshore | Olcott; Lisa | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-08-03 | 2016-08-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052348 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PTM | FUN | Saputo | Onshore | Olcott; Lisa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052349 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - PTM | PTM | FUN | Saputo | Onshore | Olcott; Lisa | Saputo | Yes | CapEx | Localization | IT - Internal | 20h | 0h | 20h | 2016-07-11 | 2016-08-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052350 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) (Saputo) - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052351 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Recordings Customer/Work Instructions (Saputo) - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | OpEx | Localization | IT - Internal | 35h | 0h | 35h | 2016-12-12 | 2017-01-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052352 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Recordings Vendor/Work Instructions (Saputo) - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | OpEx | Localization | IT - Internal | 30h | 0h | 30h | 2016-12-05 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052353 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Hypercare Support (Saputo) - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | OpEx | Localization | IT - Internal | 104h | 0h | 104h | 2017-02-06 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 40 | 15 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052354 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Offline Process Customer - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | OpEx | Localization | IT - Internal | 36h | 0h | 36h | 2016-12-19 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052355 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Offline Process Vendor - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | OpEx | Localization | IT - Internal | 66h | 0h | 66h | 2016-11-14 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052356 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cutover - Dual Maintenance Argentina Customer (Saputo) - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | OpEx | Localization | IT - Internal | 104h | 0h | 104h | 2016-12-19 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 8 | 15 | 24 | 28 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052357 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cutover - Dual Maintenance Argentina Vendor (Saputo) - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | OpEx | Localization | IT - Internal | 99h | 0h | 99h | 2016-12-21 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 8 | 15 | 21 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052358 | No | No | Yes | Argentina | Argentina | 04-Test | SIT2 - Defect Fix (Saputo) - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | OpEx | Localization | IT - Internal | 15h | 0h | 15h | 2016-11-28 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052359 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-MDG-(Saputo - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | OpEx | Localization | IT - Internal | 89h | 0h | 89h | 2017-03-20 | 2017-05-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 10 | 5 | 5 | 5 | 5 | 10 | 10 | 10 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052360 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 Preparation (Saputo) - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | OpEx | Localization | IT - Internal | 45h | 0h | 45h | 2016-10-11 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052361 | No | No | Yes | Argentina | Argentina | 04-Test | SIT1 - Manage Defect (Saputo) - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | OpEx | Localization | IT - Internal | 37.6h | 0h | 37.6h | 2016-09-12 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052362 | No | No | Yes | Argentina | Argentina | 04-Test | SIT1 - Execution (Saputo) - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | OpEx | Localization | IT - Internal | 42.6h | 0h | 42.6h | 2016-09-26 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052363 | No | No | Yes | Argentina | Argentina | 04-Test | SIT1 - Defect Fix (Saputo) - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | OpEx | Localization | IT - Internal | 41.6h | 0h | 41.6h | 2016-09-12 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052364 | No | No | Yes | Argentina | Argentina | 04-Test | SIT2 - Manage Defect (Saputo) - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | OpEx | Localization | IT - Internal | 15h | 0h | 15h | 2016-11-14 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052365 | No | No | Yes | Argentina | Argentina | 04-Test | SIT2 - Execution (Saputo) - DM | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | OpEx | Localization | IT - Internal | 80h | 0h | 80h | 2016-10-31 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052366 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | MDG | DM | Saputo | Onshore | Masole; Marie | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052367 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Functional Specification (FSD) | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-09-12 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052368 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 30.2h | 0h | 30.2h | 2016-09-19 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052369 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052370 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | OpEx | Localization | IT - External | 22h | 0h | 22h | 2016-10-11 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052371 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | OpEx | Localization | IT - External | 21h | 0h | 21h | 2016-10-03 | 2016-10-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052372 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - PTM | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 57h | 0h | 57h | 2016-05-09 | 2016-05-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052373 | No | No | Yes | Argentina | Argentina | 02-Analyze | PTM - Identfy Changes in GD for Localization ARG | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 81h | 0h | 81h | 2016-03-28 | 2016-04-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052374 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - PTM | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 19h | 0h | 19h | 2016-05-09 | 2016-05-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052375 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052376 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTM - Break/Fix | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 72.4h | 0h | 72.4h | 2016-11-14 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 8.4 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052377 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - Prep | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 50.2h | 0h | 50.2h | 2016-10-11 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052378 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - PTM | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 81h | 0h | 81h | 2017-01-23 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052379 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 23h | 0h | 23h | 2016-11-30 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052380 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 65h | 0h | 65h | 2016-12-12 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 11.2 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052381 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 47.4h | 0h | 47.4h | 2016-12-21 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 18 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052382 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 12.4h | 0h | 12.4h | 2016-12-12 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052383 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 34.6h | 0h | 34.6h | 2016-12-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052384 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTM - Run Tests | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-11-14 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052385 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 18.8h | 0h | 18.8h | 2016-11-07 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052386 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2016-12-01 | 2016-12-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052387 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | OpEx | Localization | IT - External | 114h | 0h | 114h | 2017-02-06 | 2017-02-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052388 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 76h | 0h | 76h | 2017-02-13 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 18 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052389 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | PTM | FUN | SI | Onshore | Manuel; Isaac | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052390 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | SEC | SEC | Saputo | Onshore | Sharma; Kush | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-13 | 2016-04-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052391 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-SEC | SEC | SEC | Saputo | Onshore | Sharma; Kush | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052392 | No | Yes | No | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | SI | Onshore | Escobedo; Andre | Accenture | Yes | CapEx | Localization | IT - External | 112h | 0h | 112h | 2016-09-06 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052393 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute pre validation - DC | MDG | DC | SI | Onshore | Escobedo; Andre | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052394 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Execute pre validation - DC | MDG | DC | SI | Onshore | Escobedo; Andre | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052395 | No | Yes | No | Argentina | Argentina | 04-Test | M2 -Support the data construction - DC | MDG | DC | SI | Onshore | Escobedo; Andre | Accenture | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2016-09-12 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052396 | No | Yes | No | Argentina | Argentina | 04-Test | M2 - Execute pre validation - DC | MDG | DC | SI | Onshore | Escobedo; Andre | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052397 | No | Yes | No | Argentina | Argentina | 04-Test | M1 - Execute pre validation - DC | MDG | DC | SI | Onshore | Escobedo; Andre | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-11 | 2016-09-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052398 | No | Yes | No | Argentina | Argentina | 04-Test | M1 -Support the data construction - DC | MDG | DC | SI | Onshore | Escobedo; Andre | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-11 | 2016-09-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052399 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - WP Obtain the Data Verification Signoff sheet - DC | MDG | DC | SI | Onshore | Escobedo; Andre | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-06-13 | 2016-06-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052400 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 1 Load in QA - DC | MDG | DC | SI | Onshore | Escobedo; Andre | Accenture | Yes | CapEx | Localization | IT - External | 400.5h | 0h | 400.5h | 2016-06-27 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052401 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 0 Load in DEV - DC | MDG | DC | SI | Onshore | Escobedo; Andre | Accenture | Yes | CapEx | Localization | IT - External | 144h | 0h | 144h | 2016-05-30 | 2016-06-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052402 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | RTR | FUN | SI | Onshore | OGorman; Jessica | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2016-11-14 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052403 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | RTR | FUN | SI | Onshore | OGorman; Jessica | IBM | Yes | CapEx | Localization | IT - External | 63h | 0h | 63h | 2016-12-05 | 2016-12-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052404 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | RTR | FUN | SI | Onshore | OGorman; Jessica | IBM | Yes | CapEx | Localization | IT - External | 31h | 0h | 31h | 2016-12-05 | 2016-12-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052405 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | RTR | FUN | SI | Onshore | OGorman; Jessica | IBM | Yes | CapEx | Localization | IT - External | 127h | 0h | 127h | 2016-12-20 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 24 | 44 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052406 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | RTR | FUN | SI | Onshore | OGorman; Jessica | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052407 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - RTR | RTR | FUN | SI | Onshore | OGorman; Jessica | IBM | Yes | OpEx | Localization | IT - External | 8h | 0h | 8h | 2017-03-07 | 2017-03-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052408 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - RTR | RTR | FUN | SI | Onshore | OGorman; Jessica | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052409 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - PTM | PTM | FUN | SI | Onshore | Boesl; Robert | SAP | Yes | CapEx | Localization | IT - External | 68h | 0h | 68h | 2016-06-27 | 2016-09-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052410 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | SI | Onshore | Boesl; Robert | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052411 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTM | FUN | SI | Onshore | Boesl; Robert | SAP | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052412 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | PTM | FUN | SI | Onshore | Boesl; Robert | SAP | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-12-06 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052413 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | PTM | FUN | SI | Onshore | Boesl; Robert | SAP | Yes | CapEx | Localization | IT - External | 76h | 0h | 76h | 2016-11-08 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052414 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - PTM - Run Tests | PTM | FUN | SI | Onshore | Boesl; Robert | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-17 | 2016-10-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052415 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - PTM - Break/Fix | PTM | FUN | SI | Onshore | Boesl; Robert | SAP | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052416 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | PTM | FUN | SI | Onshore | Boesl; Robert | SAP | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2016-12-15 | 2016-12-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052417 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTM | FUN | SI | Onshore | Boesl; Robert | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052418 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTM | FUN | SI | Onshore | Boesl; Robert | SAP | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-12-05 | 2016-12-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052419 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - Prep | PTM | FUN | SI | Onshore | Boesl; Robert | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052420 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTM | FUN | SI | Onshore | Boesl; Robert | SAP | Yes | OpEx | Localization | IT - External | 32h | 0h | 32h | 2016-10-03 | 2016-10-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052421 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Support | PTM | FUN | SI | Onshore | Boesl; Robert | SAP | Yes | OpEx | Localization | IT - External | 44h | 0h | 44h | 2016-10-11 | 2016-11-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052422 | No | Yes | No | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTM | FUN | SI | Onshore | Boesl; Robert | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052423 | No | Yes | No | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTM | FUN | SI | Onshore | Boesl; Robert | SAP | Yes | CapEx | Localization | IT - External | 64h | 0h | 64h | 2016-09-13 | 2016-09-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052424 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Landed Onshore | Chauhan; Sidharth | IBM | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2016-06-20 | 2016-07-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052425 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Landed Onshore | Chauhan; Sidharth | IBM | Yes | CapEx | Localization | IT - External | 19h | 0h | 19h | 2016-06-06 | 2016-06-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052426 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, team organization) | DEV | DEV | SI | Landed Onshore | Chauhan; Sidharth | IBM | Yes | CapEx | Localization | IT - External | 102h | 0h | 102h | 2016-09-19 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052427 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Landed Onshore | Chauhan; Sidharth | IBM | Yes | CapEx | Localization | IT - External | 147h | 0h | 147h | 2016-12-05 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 8 | 15 | 9 | 9 | 9 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052428 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | SI | Landed Onshore | Chauhan; Sidharth | IBM | Yes | OpEx | Localization | IT - External | 194h | 0h | 194h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 47 | 47 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052429 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Management | DEV | DEV | SI | Landed Onshore | Chauhan; Sidharth | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052430 | No | No | Yes | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Landed Onshore | Chauhan; Sidharth | IBM | Yes | OpEx | Global | IT - External | 4h | 0h | 4h | 2017-05-29 | 2017-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052431 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Landed Onshore | Chauhan; Sidharth | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-08-22 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052432 | No | No | Yes | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Landed Onshore | Chauhan; Sidharth | IBM | Yes | CapEx | Localization | IT - External | 54h | 0h | 54h | 2016-10-24 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052433 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | SI | Landed Onshore | Chauhan; Sidharth | IBM | Yes | OpEx | Localization | IT - External | 16h | 0h | 16h | 2017-03-06 | 2017-04-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052434 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Configuration | DEV | DEV | SI | Landed Onshore | Chauhan; Sidharth | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-14 | 2016-08-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052435 | No | No | Yes | Argentina | Argentina |  | Manage Infrastructure Design and Deployment | PMO | PMO | Saputo | Onshore | Volcy; Carl-Henry | Saputo | Yes | CapEx | Localization | IT - Internal | 441h | 0h | 441h | 2016-05-30 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 20 | 20 | 20 | 20 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052436 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PMO | PMO | PMO | Saputo | Onshore | Volcy; Carl-Henry | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052437 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PMO | PMO | Saputo | Onshore | Volcy; Carl-Henry | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052438 | No | No | Yes | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | Saputo | Onshore | Costa; Jorge Luis | Saputo | Yes | OpEx | Global | IT - Internal | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052439 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | Saputo | Onshore | Costa; Jorge Luis | Saputo | Yes | OpEx | Localization | IT - Internal | 56h | 0h | 56h | 2017-05-15 | 2017-05-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052440 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | Saputo | Onshore | Costa; Jorge Luis | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052441 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Localization | IT - External | 101.5h | 0h | 101.5h | 2017-01-30 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.5 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052442 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2016-10-10 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052443 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2016-12-12 | 2017-04-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052444 | No | Yes | No | Argentina | Argentina | 02-Analyze | RTR - Identify Changes in GD for Localization ARG | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Localization | IT - External | 77.5h | 0h | 77.5h | 2016-02-29 | 2016-04-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052445 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- RTR | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Localization | IT - External | 70.5h | 0h | 70.5h | 2016-05-03 | 2016-07-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052446 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - RTR | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Localization | IT - External | 61.5h | 0h | 61.5h | 2016-05-02 | 2016-08-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052447 | No | Yes | No | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2016-09-07 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052448 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Localization | IT - External | 83h | 0h | 83h | 2016-09-06 | 2016-11-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052449 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Manage Defects | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Localization | IT - External | 94h | 0h | 94h | 2016-09-05 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052450 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Support | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052451 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Validate | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | OpEx | Localization | IT - External | 1h | 0h | 1h | 2016-08-25 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052452 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Unit testing Configuration Documentation | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-08-22 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052453 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Configuration | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Localization | IT - External | 44.5h | 0h | 44.5h | 2016-08-08 | 2016-09-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052454 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Solution Design Document (SDD) | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-08-15 | 2016-08-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052455 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Prepare | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | OpEx | Localization | IT - External | 1h | 0h | 1h | 2016-08-08 | 2016-08-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052456 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Support | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Localization | IT - External | 13h | 0h | 13h | 2016-09-26 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052457 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Validate | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | OpEx | Localization | IT - External | 9h | 0h | 9h | 2016-10-11 | 2016-11-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052458 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Prep | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Localization | IT - External | 29h | 0h | 29h | 2016-10-11 | 2016-10-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052459 | No | Yes | No | Argentina | Argentina | 04-Test | Prep PRD for performance testing | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052460 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Prepare | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2016-09-12 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052461 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052462 | No | Yes | No | Argentina | Argentina | 04-Test | Updates concepts decks | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | OpEx | Localization | IT - External | 11h | 0h | 11h | 2016-10-24 | 2016-11-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052463 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Localization | IT - External | 3h | 0h | 3h | 2016-11-14 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052464 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Localization | IT - External | 3h | 0h | 3h | 2016-11-14 | 2016-12-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052465 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Localization | IT - External | 91h | 0h | 91h | 2016-12-05 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 35 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052466 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Manage Defects | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2016-10-24 | 2016-11-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052467 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Run Tests | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2016-11-10 | 2016-11-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052468 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Break/Fix | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Localization | IT - External | 104h | 0h | 104h | 2016-10-25 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052469 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Localization | IT - External | 242h | 0h | 242h | 2016-12-05 | 2017-02-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 44 | 22 | 48 | 44 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052470 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052471 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052472 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052473 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - RTR | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Localization | IT - External | 169h | 0h | 169h | 2017-02-13 | 2017-03-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 22 | 44 | 32 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052474 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - RTR | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | OpEx | Localization | IT - External | 52h | 0h | 52h | 2017-02-13 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052475 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | RTR | FUN | SI | Onshore | Moss; James | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052476 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | OTC | FUN | SI | Onshore | Lastman; Samantha | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052477 | No | Yes | No | Argentina | Argentina | 02-Analyze | OTC - Identify Changes in GD for Localization ARG | OTC | FUN | SI | Onshore | Lastman; Samantha | IBM | Yes | CapEx | Localization | IT - External | 79.9h | 0h | 79.9h | 2016-02-29 | 2016-04-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052478 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | OTC | FUN | SI | Onshore | Lastman; Samantha | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-29 | 2016-08-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052479 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | OTC | FUN | SI | Onshore | Lastman; Samantha | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-29 | 2016-08-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052480 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG KT visit | OTC | FUN | SI | Onshore | Lastman; Samantha | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2016-08-08 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052481 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Support | OTC | FUN | SI | Onshore | Lastman; Samantha | IBM | Yes | OpEx | Localization | IT - External | 30h | 0h | 30h | 2016-08-08 | 2016-08-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052482 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Solution Design Document (SDD) | OTC | FUN | SI | Onshore | Lastman; Samantha | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2016-08-15 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052483 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- OTC | OTC | FUN | SI | Onshore | Lastman; Samantha | IBM | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-05-02 | 2016-05-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052484 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - OTC | OTC | FUN | SI | Onshore | Lastman; Samantha | IBM | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2016-05-30 | 2016-06-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052485 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Unit testing Configuration Documentation | PTM | FUN | SI | Onshore | Boersma; Andy | IBM | Yes | CapEx | Localization | IT - External | 81h | 0h | 81h | 2016-08-08 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052486 | No | Yes | No | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTM | FUN | SI | Onshore | Boersma; Andy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052487 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTM | FUN | SI | Onshore | Boersma; Andy | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-09-19 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052488 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Support | PTM | FUN | SI | Onshore | Boersma; Andy | IBM | Yes | OpEx | Localization | IT - External | 7h | 0h | 7h | 2016-10-11 | 2016-11-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052489 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTM | FUN | SI | Onshore | Boersma; Andy | IBM | Yes | OpEx | Localization | IT - External | 66h | 0h | 66h | 2016-10-03 | 2016-10-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052490 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - PTM - Run Tests | PTM | FUN | SI | Onshore | Boersma; Andy | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2016-11-01 | 2016-11-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052491 | No | Yes | No | Argentina | Argentina | 02-Analyze | PTM - Identfy Changes in GD for Localization ARG | PTM | FUN | SI | Onshore | Boersma; Andy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-02-29 | 2016-02-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052492 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | PTM | FUN | SI | Onshore | Boersma; Andy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052493 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - Prep | PTM | FUN | SI | Onshore | Boersma; Andy | IBM | Yes | CapEx | Localization | IT - External | 47h | 0h | 47h | 2016-10-17 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052494 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - PTM - Break/Fix | PTM | FUN | SI | Onshore | Boersma; Andy | IBM | Yes | CapEx | Localization | IT - External | 218h | 0h | 218h | 2016-11-01 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052495 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | PTM | FUN | SI | Onshore | Boersma; Andy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052496 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTM | FUN | SI | Onshore | Boersma; Andy | IBM | Yes | CapEx | Localization | IT - External | 182h | 0h | 182h | 2016-12-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 35 | 43 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052497 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | PTM | FUN | SI | Onshore | Boersma; Andy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052498 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTM | FUN | SI | Onshore | Boersma; Andy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-06 | 2016-12-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052499 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTM | FUN | SI | Onshore | Boersma; Andy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052500 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | PTM | FUN | SI | Onshore | Boersma; Andy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052501 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | PTM | FUN | SI | Onshore | Boersma; Andy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052502 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTM | FUN | SI | Onshore | Boersma; Andy | IBM | Yes | OpEx | Localization | IT - External | 44h | 0h | 44h | 2017-01-23 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052503 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | PTM | FUN | SI | Onshore | Boersma; Andy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052504 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | SI | Onshore | Boersma; Andy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052505 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - PTM | PTM | FUN | SI | Onshore | Boersma; Andy | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2016-06-27 | 2016-06-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052506 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - PTM | PTM | FUN | SI | Onshore | Boersma; Andy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-02 | 2016-05-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052507 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - PTM | PTM | FUN | SI | Onshore | Boersma; Andy | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-01-23 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052508 | No | Yes | No | Argentina | Argentina | 01-Preparation | ArG Finalize and Deploy Localization Questionaire | PMO | PMO | SI | Onshore | Carabajal; Alan | IBM | Yes | CapEx | Localization | IT - External | 84h | 0h | 84h | 2016-01-04 | 2016-02-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052509 | No | Yes | No | Argentina | Argentina | 01-Preparation | ArG Review and understanding PDD | PMO | PMO | SI | Onshore | Carabajal; Alan | IBM | Yes | CapEx | Localization | IT - External | 46.25h | 0h | 46.25h | 2016-01-18 | 2016-01-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052510 | No | Yes | No | Argentina | Argentina | 01-Preparation | ArG Update / Confirm BPML & RTM | PMO | PMO | SI | Onshore | Carabajal; Alan | IBM | Yes | CapEx | Localization | IT - External | 26h | 0h | 26h | 2016-02-01 | 2016-02-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052511 | No | Yes | No | Argentina | Argentina | 01-Preparation | ArG Prepare Localisation WS | PMO | PMO | SI | Onshore | Carabajal; Alan | IBM | Yes | CapEx | Localization | IT - External | 67h | 0h | 67h | 2016-01-18 | 2016-03-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052512 | No | Yes | No | Argentina | Argentina | 01-Preparation | ArG Finalize WS Schedule and Invites | PMO | PMO | SI | Onshore | Carabajal; Alan | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2016-01-12 | 2016-01-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052513 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PMO | PMO | SI | Onshore | Carabajal; Alan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052514 | No | Yes | No | Argentina | Argentina | 01-Preparation | ArG GD Integrated sessions | PMO | PMO | SI | Onshore | Carabajal; Alan | IBM | Yes | CapEx | Localization | IT - External | 89h | 0h | 89h | 2016-02-22 | 2016-03-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052515 | No | Yes | No | Argentina | Argentina |  | Participate in ArG Localisation workshops | PMO | PMO | SI | Onshore | Carabajal; Alan | IBM | Yes | CapEx | Localization | IT - External | 50h | 0h | 50h | 2016-03-14 | 2016-04-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052516 | No | Yes | No | Argentina | Argentina |  | Update ArG Project Charter | PMO | PMO | SI | Onshore | Carabajal; Alan | IBM | Yes | CapEx | Localization | IT - External | 23h | 0h | 23h | 2016-03-14 | 2016-05-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052517 | No | Yes | No | Argentina | Argentina |  | Validate ArG Localisation Gap Log | PMO | PMO | SI | Onshore | Carabajal; Alan | IBM | Yes | CapEx | Localization | IT - External | 62h | 0h | 62h | 2016-03-14 | 2016-04-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052518 | No | Yes | No | Argentina | Argentina |  | Manage and Design Argentina deployment | PMO | PMO | SI | Onshore | Carabajal; Alan | IBM | Yes | CapEx | Localization | IT - External | 134h | 0h | 134h | 2016-03-14 | 2016-05-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052519 | No | Yes | No | Argentina | Argentina | 01-Preparation | ArG Global Process Overview | PMO | PMO | SI | Onshore | Carabajal; Alan | IBM | Yes | CapEx | Localization | IT - External | 22h | 0h | 22h | 2016-02-15 | 2016-02-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052520 | No | Yes | No | Argentina | Argentina | 01-Preparation | ArG Project A/L/D phase Planning | PMO | PMO | SI | Onshore | Carabajal; Alan | IBM | Yes | CapEx | Localization | IT - External | 52.75h | 0h | 52.75h | 2016-01-18 | 2016-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052521 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PMO | PMO | SI | Onshore | Pietrantoni; Luana | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052522 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Support | LOG | FUN | SI | Onshore | Gera; Tanvi | IBM | Yes | OpEx | Localization | IT - External | 31.4h | 0h | 31.4h | 2016-08-02 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052523 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | SI | Onshore | Gera; Tanvi | IBM | Yes | CapEx | Localization | IT - External | 86h | 0h | 86h | 2017-01-23 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052524 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - LOG | LOG | FUN | SI | Onshore | Gera; Tanvi | IBM | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2016-05-02 | 2016-05-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052525 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - LOG | LOG | FUN | SI | Onshore | Gera; Tanvi | IBM | Yes | CapEx | Localization | IT - External | 35.2h | 0h | 35.2h | 2016-05-09 | 2016-05-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052526 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Prepare | LOG | FUN | SI | Onshore | Gera; Tanvi | IBM | Yes | OpEx | Localization | IT - External | 18h | 0h | 18h | 2016-09-19 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052527 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Support | LOG | FUN | SI | Onshore | Gera; Tanvi | IBM | Yes | OpEx | Localization | IT - External | 43h | 0h | 43h | 2016-10-07 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052528 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | LOG | FUN | SI | Onshore | Gera; Tanvi | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052529 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Manage Defects | LOG | FUN | SI | Onshore | Gera; Tanvi | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-09-06 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052530 | No | Yes | No | Argentina | Argentina | 02-Analyze | LOG - Identify changes in GD for Localization ARG | LOG | FUN | SI | Onshore | Gera; Tanvi | IBM | Yes | CapEx | Localization | IT - External | 42.4h | 0h | 42.4h | 2016-02-29 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052531 | No | Yes | No | Argentina | Argentina | 04-Test | Prep PRD for performance testing | LOG | FUN | SI | Onshore | Gera; Tanvi | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052532 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | LOG | FUN | SI | Onshore | Gera; Tanvi | IBM | Yes | CapEx | Localization | IT - External | 60h | 0h | 60h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052533 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Unit testing Configuration Documentation | LOG | FUN | SI | Onshore | Gera; Tanvi | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2016-08-22 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052534 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Prepare | LOG | FUN | SI | Onshore | Gera; Tanvi | IBM | Yes | OpEx | Localization | IT - External | 16h | 0h | 16h | 2016-08-22 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052535 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | LOG | FUN | SI | Onshore | Gera; Tanvi | IBM | Yes | CapEx | Localization | IT - External | 200.2h | 0h | 200.2h | 2016-09-19 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052536 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | LOG | FUN | SI | Onshore | Gera; Tanvi | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-01-16 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052537 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | LOG | FUN | SI | Onshore | Gera; Tanvi | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-12-12 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052538 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | LOG | FUN | SI | Onshore | Gera; Tanvi | IBM | Yes | CapEx | Localization | IT - External | 120h | 0h | 120h | 2016-12-12 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 14 | 44 | 30 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052539 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | LOG | FUN | SI | Onshore | Gera; Tanvi | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052540 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | LOG | FUN | SI | Onshore | Gera; Tanvi | IBM | Yes | CapEx | Localization | IT - External | 29h | 0h | 29h | 2017-01-09 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 14 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052541 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | SI | Onshore | Gera; Tanvi | IBM | Yes | OpEx | Localization | IT - External | 97h | 0h | 97h | 2017-02-06 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 24 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052542 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | LOG | FUN | SI | Onshore | Gera; Tanvi | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-15 | 2016-11-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052543 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | LOG | FUN | SI | Onshore | Gera; Tanvi | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052544 | No | Yes | No | Argentina | Argentina | 04-Test | LOG - SIT 2 - Manage Defects | LOG | FUN | SI | Onshore | Gera; Tanvi | IBM | Yes | CapEx | Localization | IT - External | 42h | 0h | 42h | 2016-11-07 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052545 | No | Yes | No | Argentina | Argentina | 04-Test | LOG - SIT 2 - Break/Fix | LOG | FUN | SI | Onshore | Gera; Tanvi | IBM | Yes | CapEx | Localization | IT - External | 167h | 0h | 167h | 2016-10-31 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052546 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - Prep | LOG | FUN | SI | Onshore | Gera; Tanvi | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2016-10-24 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052547 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Validate | LOG | FUN | SI | Onshore | Gera; Tanvi | IBM | Yes | OpEx | Localization | IT - External | 15h | 0h | 15h | 2016-10-17 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052548 | No | Yes | No | Argentina | Argentina | 04-Test | LOG - SIT 2 - Run Tests | LOG | FUN | SI | Onshore | Gera; Tanvi | IBM | Yes | CapEx | Localization | IT - External | 34.6h | 0h | 34.6h | 2016-11-07 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052549 | No | No | Yes | Argentina | Argentina | 04-Test | Performance testing and refresh | TAI | TAI | SI | Landed Onshore | Deluao; Nathan | Accenture | Yes | CapEx | Localization | IT - External | 23h | 0h | 23h | 2016-11-28 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052550 | No | No | Yes | Argentina | Argentina | 04-Test | Project SAP Environment Support | TAI | TAI | SI | Landed Onshore | Deluao; Nathan | Accenture | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2016-10-24 | 2016-11-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052551 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-TAI | TAI | TAI | SI | Landed Onshore | Deluao; Nathan | Accenture | Yes | OpEx | Localization | IT - External | 566h | 0h | 566h | 2017-03-06 | 2017-07-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 18 | 36 | 36 | 45 | 18 | 23 | 45 | 36 | 0 | 40 | 32 | 40 | 40 | 40 | 24 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052552 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover Steps | TAI | TAI | SI | Landed Onshore | Deluao; Nathan | Accenture | Yes | CapEx | Localization | IT - External | 84h | 0h | 84h | 2016-12-27 | 2017-02-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 45 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052553 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Technical Architecture and Infrastructure (gen) | TAI | TAI | SI | Landed Onshore | Deluao; Nathan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-01 | 2016-09-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052554 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Support Hypercare | TAI | TAI | SI | Landed Onshore | Deluao; Nathan | Accenture | Yes | CapEx | Localization | IT - External | 145h | 0h | 145h | 2017-02-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052555 | No | Yes | No | Argentina | Argentina | 04-Test | TEST - Technical Architecture and Infrastructure (gen) | TAI | TAI | SI | Offshore | Bohol; Earl Hanzel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-01 | 2016-09-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052556 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 Preparation (Accenture) - DM | MDG | DM | SI | Onshore | Ingalls; Lindsey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-05 | 2016-10-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052557 | No | Yes | No | Argentina | Argentina | 04-Test | SIT1 - Defect Fix (Accenture) - DM | MDG | DM | SI | Onshore | Ingalls; Lindsey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052558 | No | Yes | No | Argentina | Argentina | 04-Test | SIT1 - Manage Defect (Accenture) - DM | MDG | DM | SI | Onshore | Ingalls; Lindsey | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-10-03 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052559 | No | Yes | No | Argentina | Argentina | 04-Test | SIT1 - Execution (SI) - DM | MDG | DM | SI | Onshore | Ingalls; Lindsey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-11 | 2016-09-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052560 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover (Accenture) - DM | MDG | DM | SI | Onshore | Ingalls; Lindsey | Accenture | Yes | CapEx | Localization | IT - External | 144h | 0h | 144h | 2016-12-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 32 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052561 | No | Yes | No | Argentina | Argentina | 04-Test | SIT2 - Execution (SI) - DM | MDG | DM | SI | Onshore | Ingalls; Lindsey | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-11-14 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052562 | No | Yes | No | Argentina | Argentina | 04-Test | SIT2 - Manage Defect (Accenture) - DM | MDG | DM | SI | Onshore | Ingalls; Lindsey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052563 | No | Yes | No | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) (SI) - DM | MDG | DM | SI | Onshore | Ingalls; Lindsey | Accenture | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2016-09-06 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052564 | No | Yes | No | Argentina | Argentina | 04-Test | SIT2 - Defect Fix (Accenture) - DM | MDG | DM | SI | Onshore | Ingalls; Lindsey | Accenture | Yes | CapEx | Localization | IT - External | 120h | 0h | 120h | 2016-11-28 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052565 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - Prep (Accenture) - DM | MDG | DM | SI | Onshore | Ingalls; Lindsey | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052566 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | MDSS Gouvernance Management (Cutover/Go-live) - DM | MDG | DM | SI | Onshore | Ingalls; Lindsey | Accenture | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2017-01-09 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052567 | No | Yes | No | Argentina | Argentina | 06-Hypercare | MDSS Gouvernance Management (Hypercare) (Accenture) - DM | MDG | DM | SI | Onshore | Ingalls; Lindsey | Accenture | Yes | CapEx | Localization | IT - External | 60h | 0h | 60h | 2017-02-06 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052568 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | PTP | FUN | SI | Onshore | Ho; Michele | IBM | Yes | CapEx | Localization | IT - External | 161h | 0h | 161h | 2016-11-01 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052569 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | PTP | FUN | SI | Onshore | Ho; Michele | IBM | Yes | CapEx | Localization | IT - External | 86h | 0h | 86h | 2016-11-21 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052570 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | PTP | FUN | SI | Onshore | Ho; Michele | IBM | Yes | CapEx | Localization | IT - External | 42h | 0h | 42h | 2016-12-12 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052571 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTP | FUN | SI | Onshore | Ho; Michele | IBM | Yes | CapEx | Localization | IT - External | 229h | 0h | 229h | 2016-12-19 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 24 | 44 | 44 | 39 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052572 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTP | FUN | SI | Onshore | Ho; Michele | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052573 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | PTP | FUN | SI | Onshore | Ho; Michele | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052574 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Technical Architecture and Infrastructure (gen) | TAI | TAI | SI | Landed Onshore | Roel; Luis | Accenture | Yes | CapEx | Localization | IT - External | 152h | 0h | 152h | 2016-09-26 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052575 | No | No | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PMO | PMO | Saputo | Onshore | Daitchman; Lorne | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052576 | No | No | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - |  | Missing Stream | Saputo | Onshore | Skertchly; Mario | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052577 | No | No | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PMO | PMO | Saputo | Onshore | Chausse; Bertrand | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052578 | No | No | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PMO | PMO | Saputo | Onshore | Burdisso Walter | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052579 | No | No | No | Argentina | Argentina |  | IT Application Management & Support | PMO | PMO | Saputo | Onshore | Burdisso Walter | Saputo | Yes | OpEx | Localization | IT - Internal | 30h | 0h | 30h | 2016-08-01 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052580 | No | Yes | No | Argentina | Argentina | 01-Preparation | ArG Project A/L/D phase Planning | PMO | PMO | Saputo | Onshore | Montoya; Jose | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-01-18 | 2016-01-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052581 | No | Yes | No | Argentina | Argentina |  | Manage and Design Argentina deployment | PMO | PMO | Saputo | Onshore | Montoya; Jose | Saputo | Yes | CapEx | Localization | IT - Internal | 90h | 0h | 90h | 2016-03-14 | 2016-04-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052582 | No | Yes | No | Argentina | Argentina |  | Validate ArG Localisation Gap Log | PMO | PMO | Saputo | Onshore | Montoya; Jose | Saputo | Yes | CapEx | Localization | IT - Internal | 12h | 0h | 12h | 2016-03-15 | 2016-04-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052583 | No | Yes | No | Argentina | Argentina |  | Update ArG Project Charter | PMO | PMO | Saputo | Onshore | Montoya; Jose | Saputo | Yes | CapEx | Localization | IT - Internal | 4h | 0h | 4h | 2016-03-15 | 2016-04-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052584 | No | Yes | No | Argentina | Argentina |  | Participate in ArG Localisation workshops | PMO | PMO | Saputo | Onshore | Montoya; Jose | Saputo | Yes | CapEx | Localization | IT - Internal | 40h | 0h | 40h | 2016-03-15 | 2016-04-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052585 | No | Yes | No | Argentina | Argentina |  | Perform project Planning and Control | PMO | PMO | Saputo | Onshore | Montoya; Jose | Saputo | Yes | CapEx | Localization | IT - Internal | 6h | 0h | 6h | 2016-03-14 | 2016-04-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052586 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PMO | PMO | PMO | Saputo | Onshore | Montoya; Jose | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052587 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PMO | PMO | Saputo | Onshore | Montoya; Jose | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052588 | No | Yes | No | Argentina | Argentina |  | Manage Argentina Preparation phase | PMO | PMO | Saputo | Onshore | Montoya; Jose | Saputo | Yes | CapEx | Localization | IT - Internal | 220h | 0h | 220h | 2016-02-01 | 2016-03-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052589 | No | Yes | No | Argentina | Argentina | 01-Preparation | ArG Drafted Localization Questionnaire | PMO | PMO | Saputo | Onshore | Montoya; Jose | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-15 | 2015-12-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052590 | No | Yes | No | Argentina | Argentina | 01-Preparation | ArG Drafted WS schedule | PMO | PMO | Saputo | Onshore | Montoya; Jose | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-16 | 2015-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052591 | No | Yes | No | Argentina | Argentina | 01-Preparation | ArG Submit DAC's | PMO | PMO | Saputo | Onshore | Montoya; Jose | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-01-08 | 2016-01-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052592 | No | Yes | No | Argentina | Argentina | 01-Preparation | ArG LBPL Assist Site Visit for Core FUN and Core SI (Dec 14 -Dec18) | PMO | PMO | Saputo | Onshore | Montoya; Jose | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-14 | 2015-12-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052593 | No | Yes | No | Argentina | Argentina | 01-Preparation | ArG Update / Confirm BPML & RTM | PMO | PMO | Saputo | Onshore | Montoya; Jose | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-02-01 | 2016-02-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052594 | No | Yes | No | Argentina | Argentina | 01-Preparation | ArG Deliverables approval & Signoff monitoring (Feb 8 - March 4th) | PMO | PMO | Saputo | Onshore | Montoya; Jose | Saputo | Yes | CapEx | Localization | IT - Internal | 20h | 0h | 20h | 2016-02-29 | 2016-03-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052595 | No | Yes | No | Argentina | Argentina | 01-Preparation | ArG Project Charter | PMO | PMO | Saputo | Onshore | Montoya; Jose | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-01-08 | 2016-01-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052596 | No | Yes | No | Argentina | Argentina | 01-Preparation | ArG Deliver the Argentina PP detailed planning (Nov 30 - Dec 4th) | PMO | PMO | Saputo | Onshore | Montoya; Jose | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-04 | 2015-12-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052597 | No | Yes | No | Argentina | Argentina | 01-Preparation | ArG Prepare Localization Budget (dec 14-Jan 15) | PMO | PMO | Saputo | Onshore | Montoya; Jose | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-01-15 | 2016-01-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052598 | No | Yes | No | Argentina | Argentina | 01-Preparation | ArG Finalize WS Schedule and Invites | PMO | PMO | Saputo | Onshore | Montoya; Jose | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-01-11 | 2016-01-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052599 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - PTM | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | CapEx | Localization | IT - External | 68h | 0h | 68h | 2017-01-23 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052600 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052601 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | CapEx | Localization | IT - External | 61h | 0h | 61h | 2017-02-15 | 2017-03-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 44 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052602 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-12-20 | 2017-01-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052603 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | OpEx | Localization | IT - External | 83h | 0h | 83h | 2017-02-06 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052604 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | CapEx | Localization | IT - External | 24.5h | 0h | 24.5h | 2016-11-14 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052605 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | CapEx | Localization | IT - External | 57h | 0h | 57h | 2016-11-07 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052606 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - PTM - Run Tests | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | CapEx | Localization | IT - External | 33h | 0h | 33h | 2016-10-31 | 2016-11-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052607 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | CapEx | Localization | IT - External | 38h | 0h | 38h | 2016-12-05 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052608 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | CapEx | Localization | IT - External | 135h | 0h | 135h | 2016-12-05 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 32 | 2 | 13 | 17 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052609 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | CapEx | Localization | IT - External | 43h | 0h | 43h | 2016-11-16 | 2016-12-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052610 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | CapEx | Localization | IT - External | 70h | 0h | 70h | 2016-12-05 | 2017-01-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 3 | 40 | 12 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052611 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | OpEx | Localization | IT - External | 59h | 0h | 59h | 2017-03-06 | 2017-03-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 17 | 13 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052612 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Support | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | OpEx | Localization | IT - External | 79h | 0h | 79h | 2016-10-11 | 2016-11-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052613 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052614 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - PTM - Break/Fix | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | CapEx | Localization | IT - External | 7h | 0h | 7h | 2016-11-02 | 2016-12-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052615 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - Prep | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | CapEx | Localization | IT - External | 7h | 0h | 7h | 2016-10-11 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052616 | No | Yes | No | Argentina | Argentina | 02-Analyze | PTM - Identfy Changes in GD for Localization ARG | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | CapEx | Localization | IT - External | 26h | 0h | 26h | 2016-03-10 | 2016-04-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052617 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - PTM | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | CapEx | Localization | IT - External | 89h | 0h | 89h | 2016-05-09 | 2016-08-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052618 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - PTM | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | CapEx | Localization | IT - External | 59h | 0h | 59h | 2016-05-16 | 2016-06-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052619 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | CapEx | Localization | IT - External | 11h | 0h | 11h | 2016-09-12 | 2016-09-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052620 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | OpEx | Localization | IT - External | 154h | 0h | 154h | 2016-09-12 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052621 | No | Yes | No | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | CapEx | Localization | IT - External | 34h | 0h | 34h | 2016-10-11 | 2016-11-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052622 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Validate | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | OpEx | Localization | IT - External | 20h | 0h | 20h | 2016-08-03 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052623 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Support | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | OpEx | Localization | IT - External | 36h | 0h | 36h | 2016-08-08 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052624 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Solution Design Document (SDD) | PTM | FUN | SI | Onshore | Villamizar; Daniel | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-01 | 2016-08-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052625 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 232h | 0h | 232h | 2016-09-06 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052626 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute loads/ reports - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | OpEx | Localization | IT - External | 32h | 0h | 32h | 2016-12-12 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052627 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | OpEx | Localization | IT - External | 40h | 0h | 40h | 2016-12-19 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052628 | No | No | Yes | Argentina | Argentina | 04-Test | M1 -Support the data construction - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-11 | 2016-09-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052629 | No | No | Yes | Argentina | Argentina | 04-Test | M2 -Support the data construction - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2016-09-12 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052630 | No | No | Yes | Argentina | Argentina | 04-Test | M2 - Execute pre validation - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2016-10-11 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052631 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute pre validation - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 216h | 0h | 216h | 2016-11-07 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052632 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute pre validation - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | OpEx | Localization | IT - External | 82h | 0h | 82h | 2016-12-30 | 2017-01-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 8 | 32 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052633 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 1 Load in QA - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 334h | 0h | 334h | 2016-06-27 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052634 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute Loads/Reports - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 48h | 0h | 48h | 2016-12-05 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052635 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - WP Obtain the Data Verification Signoff sheet - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 50h | 0h | 50h | 2016-07-04 | 2016-07-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052636 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 0 Load in DEV - DC | MDG | DC | SI | Onshore | Chanicharo; Hemali | Accenture | Yes | CapEx | Localization | IT - External | 84h | 0h | 84h | 2016-05-30 | 2016-06-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052637 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - PTM - Break/Fix | BI | BI | SI | Offshore | Roychowdhury; Rajibendra | IBM | Yes | CapEx | Localization | IT - External | 167h | 0h | 167h | 2016-11-14 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 27 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052638 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - PTM - Run Tests | BI | BI | SI | Offshore | Roychowdhury; Rajibendra | IBM | Yes | CapEx | Localization | IT - External | 85h | 0h | 85h | 2016-11-14 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052639 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | BI | BI | SI | Offshore | Roychowdhury; Rajibendra | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052640 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | BI | BI | SI | Offshore | Roychowdhury; Rajibendra | IBM | Yes | CapEx | Localization | IT - External | 30h | 0h | 30h | 2016-08-29 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052641 | No | Yes | No | Argentina | Argentina | 04-Test | Development | BI | BI | SI | Offshore | Roychowdhury; Rajibendra | IBM | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2016-09-05 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052642 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Run Tests | BI | BI | SI | Offshore | Roychowdhury; Rajibendra | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052643 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Break/Fix | BI | BI | SI | Offshore | Roychowdhury; Rajibendra | IBM | Yes | CapEx | Localization | IT - External | 198h | 0h | 198h | 2016-10-25 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 18 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052644 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | BI | BI | SI | Offshore | Roychowdhury; Rajibendra | IBM | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2016-12-12 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052645 | No | Yes | No | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | BI | BI | SI | Offshore | Roychowdhury; Rajibendra | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052646 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | BI | BI | SI | Offshore | Roychowdhury; Rajibendra | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-03 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052647 | No | Yes | No | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | RTR | FUN | SI | Onshore | Lindemann; Ryan | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-29 | 2016-10-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052648 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - RTR | RTR | FUN | SI | Onshore | Lindemann; Ryan | SAP | Yes | CapEx | Localization | IT - External | 14h | 0h | 14h | 2016-05-02 | 2016-05-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052649 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- RTR | RTR | FUN | SI | Onshore | Lindemann; Ryan | SAP | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2016-05-23 | 2016-05-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052650 | No | Yes | No | Argentina | Argentina | 02-Analyze | RTR - Identify Changes in GD for Localization ARG | RTR | FUN | SI | Onshore | Lindemann; Ryan | SAP | Yes | CapEx | Localization | IT - External | 44.5h | 0h | 44.5h | 2016-03-01 | 2016-04-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052651 | No | No | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - |  | Missing Stream | Saputo | Onshore | Zuliani Pablo | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052652 | No | No | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - |  | Missing Stream | Saputo | Onshore | Morel Maria Soledad | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052653 | No | No | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - |  | Missing Stream | Saputo | Onshore | Orchese Fernando | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052654 | No | No | No | Argentina | Argentina | 04-Test | Mock1 - Validate |  | Missing Stream | Saputo | Onshore | Orchese Fernando | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052655 | No | No | No | Argentina | Argentina | 03-Design/Build | Solution Design Document (SDD) |  | Missing Stream | Saputo | Onshore | Orchese Fernando | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052656 | No | No | No | Argentina | Argentina | 04-Test | Mock1 - Support |  | Missing Stream | Saputo | Onshore | Orchese Fernando | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052657 | No | No | No | Argentina | Argentina | 04-Test | Mock2 - Support |  | Missing Stream | Saputo | Onshore | Orchese Fernando | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-09-26 | 2016-09-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052658 | No | No | No | Argentina | Argentina | 04-Test | Mock2 - Validate |  | Missing Stream | Saputo | Onshore | Orchese Fernando | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052659 | No | No | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate |  | Missing Stream | Saputo | Onshore | Orchese Fernando | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052660 | No | No | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Manage Defect |  | Missing Stream | Saputo | Onshore | Orchese Fernando | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-06 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052661 | No | No | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support |  | Missing Stream | Saputo | Onshore | Orchese Fernando | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052662 | No | No | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | Non ERP | Non ERP | Saputo | Onshore | Traverso Fabián | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052663 | No | No | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - |  | Missing Stream | Saputo | Onshore | Altamirano Facundo | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052664 | No | No | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - |  | Missing Stream | Saputo | Onshore | Coria Sergio | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052665 | No | No | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - |  | Missing Stream | Saputo | Onshore | Meyer Fernando | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052666 | No | No | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - |  | Missing Stream | Saputo | Onshore | Paredes Hernán | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052667 | No | No | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | CM | CM | Saputo | Onshore | Strauch Gabriela | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052668 | No | No | No | Argentina | Argentina | 03-Design/Build | Establish Key User Requirements | CM | CM | Saputo | Onshore | Strauch Gabriela | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-06-27 | 2016-06-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052669 | No | No | No | Argentina | Argentina | 03-Design/Build | Walkthrough KU presentation with DCLs | CM | CM | Saputo | Onshore | Strauch Gabriela | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052670 | No | No | No | Argentina | Argentina | 03-Design/Build | Meet with manager to request assignment of KU | CM | CM | Saputo | Onshore | Strauch Gabriela | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052671 | No | No | No | Argentina | Argentina | 03-Design/Build | Hold mitigation workshops | CM | CM | Saputo | Onshore | Strauch Gabriela | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-09 | 2016-05-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052672 | No | No | No | Argentina | Argentina | 03-Design/Build | On board Key Users | CM | CM | Saputo | Onshore | Strauch Gabriela | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-09-30 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052673 | No | No | No | Argentina | Argentina | 03-Design/Build | Walkthrough KU on-boarding deck with DCLs | CM | CM | Saputo | Onshore | Strauch Gabriela | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052674 | No | No | No | Argentina | Argentina | 03-Design/Build | Review Process Role Description for clarity and divide by department | CM | CM | Saputo | Onshore | Strauch Gabriela | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-09 | 2016-05-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052675 | No | No | No | Argentina | Argentina | 03-Design/Build | Review Changes and Impacts with Core Team | CM | CM | Saputo | Onshore | Strauch Gabriela | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-24 | 2016-05-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052676 | No | No | No | Argentina | Argentina | 03-Design/Build | Package Changes and Impacts per Department | CM | CM | Saputo | Onshore | Strauch Gabriela | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-12 | 2016-05-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052677 | No | No | No | Argentina | Argentina | 03-Design/Build | Educate\Train DCL on Role mapping | CM | CM | Saputo | Onshore | Strauch Gabriela | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-12 | 2016-05-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052678 | No | No | No | Argentina | Argentina | 03-Design/Build | Onboarding of Division Managers to Role Mapping | CM | CM | Saputo | Onshore | Strauch Gabriela | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-18 | 2016-05-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052679 | No | No | No | Argentina | Argentina | 03-Design/Build | Build Change Agents feedback tool | CM | CM | Saputo | Onshore | Strauch Gabriela | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-16 | 2016-05-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052680 | No | No | No | Argentina | Argentina | 03-Design/Build | On-going management of additional mitigation measures | CM | CM | Saputo | Onshore | Strauch Gabriela | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052681 | No | No | No | Argentina | Argentina | 03-Design/Build | Implement monitoring process (bi-weekly touchpoint with some managers?) | CM | CM | Saputo | Onshore | Strauch Gabriela | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-09-06 | 2016-09-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052682 | No | No | No | Argentina | Argentina | 03-Design/Build | Present transition activities to responsible managers (Timing will vary depending on start date of transition activities) | CM | CM | Saputo | Onshore | Strauch Gabriela | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052683 | No | No | No | Argentina | Argentina | 03-Design/Build | Convert each mitigation measure into and executable action (Resp., end date, etc…) and log in the appropriate execution plan (Communication, Training or Transition) | CM | CM | Saputo | Onshore | Strauch Gabriela | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-06-01 | 2016-06-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052684 | No | No | No | Argentina | Argentina | 03-Design/Build | Debrief on Pulse Check | CM | CM | Saputo | Onshore | Strauch Gabriela | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-16 | 2016-05-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052685 | No | No | No | Argentina | Argentina | 03-Design/Build | CA weekly touchpoint/Pulse Check | CM | CM | Saputo | Onshore | Strauch Gabriela | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052686 | No | No | No | Argentina | Argentina | 03-Design/Build | Update FAQ and CA toolkit (on-going) | CM | CM | Saputo | Onshore | Strauch Gabriela | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-31 | 2016-05-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052687 | No | No | No | Argentina | Argentina | 03-Design/Build | Determine mitigation measures for each variances (in Meetings) (options: comm, training, transition) | CM | CM | Saputo | Onshore | Strauch Gabriela | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-08-28 | 2016-08-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052688 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- RTR | RTR | FUN | SI | Offshore | Paradkar; Parag | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-07-11 | 2016-07-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052689 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - RTR | RTR | FUN | SI | Offshore | Paradkar; Parag | IBM | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2016-05-25 | 2016-05-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052690 | No | Yes | No | Argentina | Argentina | 02-Analyze | RTR - Identify Changes in GD for Localization ARG | RTR | FUN | SI | Offshore | Paradkar; Parag | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2016-04-25 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052691 | No | No | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - |  | Missing Stream | Saputo | Onshore | Russo Fernanda | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052692 | No | No | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | CM | CM | Saputo | Onshore | Calvo Laura | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052693 | No | No | No | Argentina | Argentina | 03-Design/Build | Build Change Agents feedback tool | CM | CM | Saputo | Onshore | Calvo Laura | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-16 | 2016-05-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052694 | No | No | No | Argentina | Argentina | 03-Design/Build | Determine mitigation measures for each variances (in Meetings) (options: comm, training, transition) | CM | CM | Saputo | Onshore | Calvo Laura | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-08-28 | 2016-08-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052695 | No | No | No | Argentina | Argentina | 03-Design/Build | Educate\Train DCL on Role mapping | CM | CM | Saputo | Onshore | Calvo Laura | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-12 | 2016-05-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052696 | No | No | No | Argentina | Argentina | 03-Design/Build | Onboarding of Division Managers to Role Mapping | CM | CM | Saputo | Onshore | Calvo Laura | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-18 | 2016-05-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052697 | No | No | No | Argentina | Argentina | 03-Design/Build | Package Changes and Impacts per Department | CM | CM | Saputo | Onshore | Calvo Laura | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-12 | 2016-05-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052698 | No | No | No | Argentina | Argentina | 03-Design/Build | Review Changes and Impacts with Core Team | CM | CM | Saputo | Onshore | Calvo Laura | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-24 | 2016-05-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052699 | No | No | No | Argentina | Argentina | 03-Design/Build | Review Process Role Description for clarity and divide by department | CM | CM | Saputo | Onshore | Calvo Laura | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-09 | 2016-05-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052700 | No | No | No | Argentina | Argentina | 03-Design/Build | On board Key Users | CM | CM | Saputo | Onshore | Calvo Laura | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-09-30 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052701 | No | No | No | Argentina | Argentina | 03-Design/Build | Walkthrough KU on-boarding deck with DCLs | CM | CM | Saputo | Onshore | Calvo Laura | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052702 | No | No | No | Argentina | Argentina | 03-Design/Build | Hold mitigation workshops | CM | CM | Saputo | Onshore | Calvo Laura | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-09 | 2016-05-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052703 | No | No | No | Argentina | Argentina | 03-Design/Build | Walkthrough KU presentation with DCLs | CM | CM | Saputo | Onshore | Calvo Laura | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052704 | No | No | No | Argentina | Argentina | 03-Design/Build | Meet with manager to request assignment of KU | CM | CM | Saputo | Onshore | Calvo Laura | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052705 | No | No | No | Argentina | Argentina | 03-Design/Build | Establish Key User Requirements | CM | CM | Saputo | Onshore | Calvo Laura | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-06-27 | 2016-06-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052706 | No | No | No | Argentina | Argentina | 03-Design/Build | CA weekly touchpoint/Pulse Check | CM | CM | Saputo | Onshore | Calvo Laura | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052707 | No | No | No | Argentina | Argentina | 03-Design/Build | Debrief on Pulse Check | CM | CM | Saputo | Onshore | Calvo Laura | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-16 | 2016-05-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052708 | No | No | No | Argentina | Argentina | 03-Design/Build | Convert each mitigation measure into and executable action (Resp., end date, etc…) and log in the appropriate execution plan (Communication, Training or Transition) | CM | CM | Saputo | Onshore | Calvo Laura | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-06-01 | 2016-06-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052709 | No | No | No | Argentina | Argentina | 03-Design/Build | Update FAQ and CA toolkit (on-going) | CM | CM | Saputo | Onshore | Calvo Laura | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-31 | 2016-05-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052710 | No | No | No | Argentina | Argentina | 03-Design/Build | Present transition activities to responsible managers (Timing will vary depending on start date of transition activities) | CM | CM | Saputo | Onshore | Calvo Laura | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052711 | No | No | No | Argentina | Argentina | 03-Design/Build | Implement monitoring process (bi-weekly touchpoint with some managers?) | CM | CM | Saputo | Onshore | Calvo Laura | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-09-06 | 2016-09-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052712 | No | No | No | Argentina | Argentina | 03-Design/Build | On-going management of additional mitigation measures | CM | CM | Saputo | Onshore | Calvo Laura | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052713 | No | No | No | Argentina | Argentina | 03-Design/Build | On-going management of additional mitigation measures | CM | CM | Saputo | Onshore | Floriani Martin | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052714 | No | No | No | Argentina | Argentina | 03-Design/Build | Implement monitoring process (bi-weekly touchpoint with some managers?) | CM | CM | Saputo | Onshore | Floriani Martin | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-09-06 | 2016-09-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052715 | No | No | No | Argentina | Argentina | 03-Design/Build | Present transition activities to responsible managers (Timing will vary depending on start date of transition activities) | CM | CM | Saputo | Onshore | Floriani Martin | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052716 | No | No | No | Argentina | Argentina | 03-Design/Build | Convert each mitigation measure into and executable action (Resp., end date, etc…) and log in the appropriate execution plan (Communication, Training or Transition) | CM | CM | Saputo | Onshore | Floriani Martin | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-06-01 | 2016-06-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052717 | No | No | No | Argentina | Argentina | 03-Design/Build | Debrief on Pulse Check | CM | CM | Saputo | Onshore | Floriani Martin | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-16 | 2016-05-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052718 | No | No | No | Argentina | Argentina | 03-Design/Build | CA weekly touchpoint/Pulse Check | CM | CM | Saputo | Onshore | Floriani Martin | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052719 | No | No | No | Argentina | Argentina | 03-Design/Build | Update FAQ and CA toolkit (on-going) | CM | CM | Saputo | Onshore | Floriani Martin | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-31 | 2016-05-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052720 | No | No | No | Argentina | Argentina | 03-Design/Build | Meet with manager to request assignment of KU | CM | CM | Saputo | Onshore | Floriani Martin | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052721 | No | No | No | Argentina | Argentina | 03-Design/Build | Walkthrough KU presentation with DCLs | CM | CM | Saputo | Onshore | Floriani Martin | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052722 | No | No | No | Argentina | Argentina | 03-Design/Build | Establish Key User Requirements | CM | CM | Saputo | Onshore | Floriani Martin | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-06-27 | 2016-06-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052723 | No | No | No | Argentina | Argentina | 03-Design/Build | Hold mitigation workshops | CM | CM | Saputo | Onshore | Floriani Martin | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-09 | 2016-05-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052724 | No | No | No | Argentina | Argentina | 03-Design/Build | Walkthrough KU on-boarding deck with DCLs | CM | CM | Saputo | Onshore | Floriani Martin | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052725 | No | No | No | Argentina | Argentina | 03-Design/Build | On board Key Users | CM | CM | Saputo | Onshore | Floriani Martin | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-09-30 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052726 | No | No | No | Argentina | Argentina | 03-Design/Build | Review Process Role Description for clarity and divide by department | CM | CM | Saputo | Onshore | Floriani Martin | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-09 | 2016-05-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052727 | No | No | No | Argentina | Argentina | 03-Design/Build | Educate\Train DCL on Role mapping | CM | CM | Saputo | Onshore | Floriani Martin | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-12 | 2016-05-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052728 | No | No | No | Argentina | Argentina | 03-Design/Build | Review Changes and Impacts with Core Team | CM | CM | Saputo | Onshore | Floriani Martin | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-24 | 2016-05-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052729 | No | No | No | Argentina | Argentina | 03-Design/Build | Package Changes and Impacts per Department | CM | CM | Saputo | Onshore | Floriani Martin | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-12 | 2016-05-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052730 | No | No | No | Argentina | Argentina | 03-Design/Build | Onboarding of Division Managers to Role Mapping | CM | CM | Saputo | Onshore | Floriani Martin | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-18 | 2016-05-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052731 | No | No | No | Argentina | Argentina | 03-Design/Build | Determine mitigation measures for each variances (in Meetings) (options: comm, training, transition) | CM | CM | Saputo | Onshore | Floriani Martin | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-08-28 | 2016-08-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052732 | No | No | No | Argentina | Argentina | 03-Design/Build | Build Change Agents feedback tool | CM | CM | Saputo | Onshore | Floriani Martin | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-05-16 | 2016-05-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052733 | No | No | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | CM | CM | Saputo | Onshore | Floriani Martin | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052734 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052735 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Update FAQ and CA toolkit (on-going) | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-31 | 2016-05-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052736 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Adress SOD Issues | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-07-18 | 2016-07-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052737 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Evaluate variances between current and future tasks and responsibilities (old Roles vs new Roles) | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-06-27 | 2016-06-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052738 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Educate\Train DCL on Role mapping | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-12 | 2016-05-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052739 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Onboarding of Division Managers to Role Mapping | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-18 | 2016-05-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052740 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Role mapping Workshops (incl. RMS Training) | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052741 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Validate RM Status Report | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 2h | 0h | 2h | 2016-05-30 | 2016-06-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052742 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Review Changes and Impacts with Core Team | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 21h | 0h | 21h | 2016-05-24 | 2016-06-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052743 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Obtain approval on mitigation plans | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 3h | 0h | 3h | 2016-05-30 | 2016-06-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052744 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Manage as uncovered (log, assess, mitigate, approve) - GTS | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 10h | 0h | 10h | 2016-05-30 | 2016-06-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052745 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Build comm package (BU, Changes =benefits, nature of change, people, process, tool Impacts) | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 30h | 0h | 30h | 2016-05-16 | 2016-06-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052746 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Package Changes and Impacts per Department | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 16h | 0h | 16h | 2016-05-24 | 2016-05-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052747 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Hold mitigation workshops | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 20h | 0h | 20h | 2016-05-09 | 2016-05-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052748 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Establish Key User Requirements | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-06-27 | 2016-06-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052749 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Prepare Key Users On boarding deck | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-07-25 | 2016-07-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052750 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Walkthrough KU on-boarding deck with DCLs | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052751 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Prepare Presentation for managers who will assign | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-06-10 | 2016-06-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052752 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Walkthrough KU presentation with DCLs | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052753 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Complete Stakeholder Assessment in preparation for 1st communication cascade (2 VP's) | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052754 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Build Change Agents feedback tool | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-16 | 2016-05-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052755 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Debrief on Pulse Check | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-16 | 2016-05-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052756 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Convert each mitigation measure into and executable action (Resp., end date, etc…) and log in the appropriate execution plan (Communication, Training or Transition) | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-06-01 | 2016-06-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052757 | No | Yes | No | Argentina | Argentina | 03-Design/Build | CA weekly touchpoint/Pulse Check | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052758 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Present transition activities to responsible managers (Timing will vary depending on start date of transition activities) | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052759 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Implement monitoring process (bi-weekly touchpoint with some managers?) | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-09-06 | 2016-09-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052760 | No | Yes | No | Argentina | Argentina | 03-Design/Build | On-going management of additional mitigation measures | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052761 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Validate deck for CM training for managers | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-06-15 | 2016-06-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052762 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Prepare deck for CM training for managers | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-06-06 | 2016-06-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052763 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG Onboarding of 4DCL on CM (Approach, Deliverables, Roles and Team) | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-03-07 | 2016-03-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052764 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTM Identify Business Risks from the Change Impacts and briefly describe each risks | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052765 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTM Recommand and validate mitigation measures to address Business risks | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052766 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTM Incorporate measures into Execution Plans with Change Management team | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052767 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTM Log Business risks in PMO Log | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052768 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTM Report Project Risks to Project Managers | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052769 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG Prepare Kickoff session | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052770 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : Conduct Interviews with Management and DCL | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-01-15 | 2016-01-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052771 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : Summarize and Share with CM Core | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-01-15 | 2016-01-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052772 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : Transfer Global Design CI to the 4 DCL | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-03-08 | 2016-03-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052773 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : PTM Review and Validate Changes AND Identify and Describe Impacts | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052774 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTM Insert line for new change | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052775 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTM Identify if there are Business risks and transfer info to Business Risk Log\Template. | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052776 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTM Start Mitigation Measures for High Impact Changes or Business Risks. (*leverage positive impacts when possible) | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052777 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTM Hold final CI WORKSHOP : Confirm High Level CI and complete\define Mitigation Measures | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052778 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : PTM Validate Mitigation Measures with Managers | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-29 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052779 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : PTM Obtain Business lead Approval (Fernando Mayer) | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-29 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052780 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTM Educate/Train DCL on Role Mapping | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-10 | 2016-05-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052781 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTM Workshops : Evaluate Variances between current and future tasks and responsibilties (old Roles vs new roles) | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052782 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTM Determine mitigation measures for each variances (in meetings) | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052783 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : PTM Align Functional Team on Roles Catalog Change Control process | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052784 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTM Divide Catalog by Process Area | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052785 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : Confirm benefit and KPI owners | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-16 | 2016-05-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052786 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: Keep Applicable Benefits and KPI | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052787 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : Obtain buy-in from owners on Value realization responsibilities | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052788 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : Confirm Baseline measurement procedures | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-06-13 | 2016-06-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052789 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: Establish timelines (planning workshops) | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-07-11 | 2016-07-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052790 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : Kick off meeting with Change Agents and DCL | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052791 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : Align on CA criteria and requirements with DCL (location & groups) | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052792 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTM Determine Transition Activities From Completed High Level CI analysis | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-16 | 2016-05-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052793 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTM Determine Transition Activitie from Completed Detailed CI Analysis | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-07-04 | 2016-07-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052794 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTM Obtain Approval of the Transition Plan | CM | CM | Saputo | Onshore | Guay; Philippe | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-07-18 | 2016-07-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052795 | No | No | Yes | Argentina | Argentina | 04-Test | Manage SIT2 Execution | Test | Test | Saputo | Onshore | Bensoussan; Tanya | Saputo | Yes | CapEx | Localization | IT - Internal | 170h | 0h | 170h | 2016-10-24 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052796 | No | No | Yes | Argentina | Argentina | 04-Test | Manage SIT2 Execution local (ARG) | Test | Test | Saputo | Onshore | Bensoussan; Tanya | Saputo | Yes | CapEx | Localization | IT - Internal | 30h | 0h | 30h | 2016-10-24 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052797 | No | No | Yes | Argentina | Argentina | 04-Test | Manage SIT2 Prep (data, transports) | Test | Test | Saputo | Onshore | Bensoussan; Tanya | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052798 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Manage UAT Execution | Test | Test | Saputo | Onshore | Bensoussan; Tanya | Saputo | Yes | CapEx | Localization | IT - Internal | 248h | 0h | 248h | 2016-12-05 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 24 | 24 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052799 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | Test | Test | Saputo | Onshore | Bensoussan; Tanya | Saputo | Yes | CapEx | Localization | IT - Internal | 64h | 0h | 64h | 2017-01-23 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052800 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-Test | Test | Test | Saputo | Onshore | Bensoussan; Tanya | Saputo | Yes | OpEx | Localization | IT - Internal | 70h | 0h | 70h | 2017-03-20 | 2017-05-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052801 | No | No | Yes | Argentina | Argentina | 04-Test | Manage SIT1 Execution | Test | Test | Saputo | Onshore | Bensoussan; Tanya | Saputo | Yes | CapEx | Localization | IT - Internal | 89h | 0h | 89h | 2016-09-19 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052802 | No | No | Yes | Argentina | Argentina | 04-Test | Manage SIT1 Execution local (ARG) | Test | Test | Saputo | Onshore | Bensoussan; Tanya | Saputo | Yes | CapEx | Localization | IT - Internal | 9.5h | 0h | 9.5h | 2016-10-11 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052803 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | Test | Test | Saputo | Onshore | Bensoussan; Tanya | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052804 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - PTM | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2016-05-02 | 2016-05-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052805 | No | No | Yes | Argentina | Argentina | 02-Analyze | PTM - Identfy Changes in GD for Localization ARG | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-02-29 | 2016-02-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052806 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - PTM | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052807 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-06 | 2016-09-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052808 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Support | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052809 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Solution Design Document (SDD) | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 39h | 0h | 39h | 2016-08-01 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052810 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052811 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052812 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052813 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Configuration | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 29h | 0h | 29h | 2016-09-26 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052814 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTM | FUN | SI | Offshore | Priyanka; Mishra | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-01-04 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052815 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2016-09-19 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052816 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-03 | 2016-09-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052817 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - LOG | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052818 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - LOG | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052819 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-01-30 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052820 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-LOG | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | OpEx | Localization | IT - External | 180h | 0h | 180h | 2017-04-11 | 2017-06-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 45 | 45 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052821 | No | No | Yes | Argentina | Argentina | 02-Analyze | LOG - Identify changes in GD for Localization ARG | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-02-29 | 2016-02-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052822 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052823 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - Prep | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2016-11-07 | 2016-11-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052824 | No | No | Yes | Argentina | Argentina | 04-Test | LOG - SIT 2 - Run Tests | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 108h | 0h | 108h | 2016-11-07 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052825 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | OpEx | Localization | IT - External | 135h | 0h | 135h | 2016-12-01 | 2017-06-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052826 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-09-12 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052827 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Unit testing Configuration Documentation | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2016-08-22 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052828 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 216h | 0h | 216h | 2017-02-13 | 2017-05-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052829 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | LOG | FUN | SI | Offshore | Sudheer; Yadav | IBM | Yes | CapEx | Localization | IT - External | 3h | 0h | 3h | 2016-11-07 | 2016-11-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052830 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Unit testing Configuration Documentation | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052831 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Support | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | OpEx | Localization | IT - External | 8h | 0h | 8h | 2016-08-08 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052832 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052833 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - Prep | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2016-11-04 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052834 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052835 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTP - Break/Fix | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | CapEx | Localization | IT - External | 82h | 0h | 82h | 2016-11-14 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052836 | No | No | Yes | Argentina | Argentina | 02-Analyze | PTP - Identify Changesin GD for Localization ARG | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | CapEx | Localization | IT - External | 151h | 0h | 151h | 2016-03-28 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052837 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- PTP | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-05-02 | 2016-05-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052838 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - PTP | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052839 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | PTM | FUN | SI | Offshore | Amol; Shahane | IBM | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2017-01-23 | 2017-01-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052840 | No | No | Yes | Argentina | Argentina | 04-Test | Defect management | PMO | PMO | SI | Offshore | Manish; Desai | IBM | Yes | CapEx | Localization | IT - External | 19h | 0h | 19h | 2016-09-06 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052841 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, team organization) | PMO | PMO | SI | Offshore | Manish; Desai | IBM | Yes | CapEx | Localization | IT - External | 48h | 0h | 48h | 2016-09-06 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052842 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Management | PMO | PMO | SI | Offshore | Manish; Desai | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2016-08-22 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052843 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | PMO | PMO | SI | Offshore | Manish; Desai | IBM | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2016-12-05 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052844 | No | No | Yes | Argentina | Argentina | 04-Test | Development | PMO | PMO | SI | Offshore | Manish; Desai | IBM | Yes | CapEx | Localization | IT - External | 135h | 0h | 135h | 2016-10-17 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052845 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 189h | 0h | 189h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 54 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052846 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2016-09-06 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052847 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | OpEx | Localization | IT - External | 20h | 0h | 20h | 2016-12-01 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052848 | No | No | Yes | Argentina | Argentina | 04-Test | LOG - SIT 2 - Run Tests | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 63h | 0h | 63h | 2016-10-31 | 2016-11-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052849 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - Prep | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-10-10 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052850 | No | No | Yes | Argentina | Argentina | 02-Analyze | LOG - Identify changes in GD for Localization ARG | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-03-07 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052851 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-LOG | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | OpEx | Localization | IT - External | 41h | 0h | 41h | 2017-03-20 | 2017-05-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 4 | 2 | 3 | 2 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052852 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2017-01-30 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052853 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - LOG | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 13h | 0h | 13h | 2017-03-20 | 2017-03-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052854 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - LOG | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-05-02 | 2016-05-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052855 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | LOG | FUN | SI | Onshore | Suraj; Lote | IBM | Yes | CapEx | Localization | IT - External | 176h | 0h | 176h | 2016-09-12 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052856 | No | Yes | No | Argentina | Argentina | 04-Test | Project SAP Environment Support | TAI | TAI | SI | Offshore | Catoy; John | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-11-07 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052857 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover Steps | TAI | TAI | SI | Offshore | Catoy; John | Accenture | Yes | CapEx | Localization | IT - External | 135h | 0h | 135h | 2017-01-16 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052858 | No | Yes | No | Argentina | Argentina | 04-Test | Performance testing and refresh | TAI | TAI | SI | Offshore | Catoy; John | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-19 | 2016-09-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052859 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Support Hypercare | TAI | TAI | SI | Offshore | Catoy; John | Accenture | Yes | CapEx | Localization | IT - External | 171h | 0h | 171h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 36 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052860 | No | Yes | No | Argentina | Argentina | 04-Test | TEST - Technical Architecture and Infrastructure (gen) | TAI | TAI | SI | Offshore | Catoy; John | Accenture | Yes | CapEx | Localization | IT - External | 108h | 0h | 108h | 2016-09-05 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052861 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PMO | PMO | PMO | Saputo | Onshore | Bensoussan; Orly | Saputo | Yes | OpEx | Localization | IT - Internal | 8h | 0h | 8h | 2017-04-13 | 2017-04-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052862 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PMO | PMO | Saputo | Onshore | Bensoussan; Orly | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052863 | No | No | Yes | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | HEDA; NAND | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052864 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Management | DEV | DEV | SI | Offshore | HEDA; NAND | IBM | Yes | CapEx | Localization | IT - External | 49h | 0h | 49h | 2016-08-15 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052865 | No | No | Yes | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Offshore | HEDA; NAND | IBM | Yes | CapEx | Localization | IT - External | 78h | 0h | 78h | 2016-10-24 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052866 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | HEDA; NAND | IBM | Yes | OpEx | Localization | IT - External | 158h | 0h | 158h | 2017-02-27 | 2017-06-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 8 | 10 | 8 | 6 | 10 | 10 | 10 | 8 | 10 | 10 | 10 | 10 | 8 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052867 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Offshore | HEDA; NAND | IBM | Yes | CapEx | Localization | IT - External | 182h | 0h | 182h | 2016-12-05 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 20 | 16 | 20 | 20 | 16 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052868 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, team organization) | DEV | DEV | SI | Offshore | HEDA; NAND | IBM | Yes | CapEx | Localization | IT - External | 82h | 0h | 82h | 2016-09-06 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052869 | No | No | Yes | Argentina | Argentina | 04-Test | Defect management | DEV | DEV | SI | Offshore | HEDA; NAND | IBM | Yes | CapEx | Localization | IT - External | 86h | 0h | 86h | 2016-09-06 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052870 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | SI | Offshore | HEDA; NAND | IBM | Yes | OpEx | Localization | IT - External | 79h | 0h | 79h | 2017-02-06 | 2017-06-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 25 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052871 | No | Yes | No | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | SI | Onshore | Arora; Mandeep | Accenture | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2016-09-06 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052872 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Execute pre validation - DC | MDG | DC | SI | Onshore | Arora; Mandeep | Accenture | Yes | OpEx | Localization | IT - External | 167h | 0h | 167h | 2016-12-12 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 24 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052873 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute pre validation - DC | MDG | DC | SI | Onshore | Arora; Mandeep | Accenture | Yes | CapEx | Localization | IT - External | 305.5h | 0h | 305.5h | 2016-10-24 | 2016-12-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052874 | No | Yes | No | Argentina | Argentina | 04-Test | M2 -Support the data construction - DC | MDG | DC | SI | Onshore | Arora; Mandeep | Accenture | Yes | CapEx | Localization | IT - External | 215h | 0h | 215h | 2016-09-12 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052875 | No | Yes | No | Argentina | Argentina | 04-Test | M2 - Execute pre validation - DC | MDG | DC | SI | Onshore | Arora; Mandeep | Accenture | Yes | CapEx | Localization | IT - External | 47h | 0h | 47h | 2016-10-11 | 2016-10-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052876 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 0 Load in DEV - DC | MDG | DC | SI | Onshore | Arora; Mandeep | Accenture | Yes | CapEx | Localization | IT - External | 113h | 0h | 113h | 2016-05-30 | 2016-06-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052877 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - WP Obtain the Data Verification Signoff sheet - DC | MDG | DC | SI | Onshore | Arora; Mandeep | Accenture | Yes | CapEx | Localization | IT - External | 104h | 0h | 104h | 2016-06-27 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052878 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 1 Load in QA - DC | MDG | DC | SI | Onshore | Arora; Mandeep | Accenture | Yes | CapEx | Localization | IT - External | 102h | 0h | 102h | 2016-06-27 | 2016-07-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052879 | No | Yes | No | Argentina | Argentina | 04-Test | Performance testing and refresh | TAI | TAI | SI | Offshore | Zapata; Michael | Accenture | Yes | CapEx | Localization | IT - External | 69h | 0h | 69h | 2016-11-02 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052880 | No | Yes | No | Argentina | Argentina | 04-Test | Project SAP Environment Support | TAI | TAI | SI | Offshore | Zapata; Michael | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-11-07 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052881 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover Steps | TAI | TAI | SI | Offshore | Zapata; Michael | Accenture | Yes | CapEx | Localization | IT - External | 54h | 0h | 54h | 2016-12-19 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 15 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052882 | No | Yes | No | Argentina | Argentina | 04-Test | TEST - Technical Architecture and Infrastructure (gen) | TAI | TAI | SI | Offshore | Zapata; Michael | Accenture | Yes | CapEx | Localization | IT - External | 22.5h | 0h | 22.5h | 2016-09-05 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052883 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Support Hypercare | TAI | TAI | SI | Offshore | Zapata; Michael | Accenture | Yes | CapEx | Localization | IT - External | 180h | 0h | 180h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 45 | 45 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052884 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 Closure - DC | MDG | DC | Saputo | Onshore | Mayhall; Delano | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-09-11 | 2016-09-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052885 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-MDG-DC | MDG | DC | Saputo | Onshore | Mayhall; Delano | Saputo | Yes | OpEx | Localization | IT - Internal | 10h | 0h | 10h | 2017-05-08 | 2017-05-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052886 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 Closure Memo - DC | MDG | DC | Saputo | Onshore | Mayhall; Delano | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052887 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cutover Closure Memo - DC | MDG | DC | Saputo | Onshore | Mayhall; Delano | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-20 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052888 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | Saputo | Onshore | Mayhall; Delano | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052889 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Hypercare Support - DC | MDG | DC | Saputo | Onshore | Mayhall; Delano | Saputo | Yes | OpEx | Localization | IT - Internal | 17h | 0h | 17h | 2017-02-06 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052890 | No | No | Yes | Argentina | Argentina | 04-Test | Test - MDSS Project Management - DC | MDG | DC | Saputo | Onshore | Mayhall; Delano | Saputo | Yes | CapEx | Localization | IT - Internal | 169h | 0h | 169h | 2016-09-12 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052891 | No | No | Yes | Argentina | Argentina | 06-Hypercare | MDSS Project Management (Hypercare) - DC | MDG | DC | Saputo | Onshore | Mayhall; Delano | Saputo | Yes | OpEx | Localization | IT - Internal | 14.5h | 0h | 14.5h | 2017-02-06 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052892 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | MDG | DC | Saputo | Onshore | Mayhall; Delano | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052893 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052894 | No | No | Yes | Argentina | Argentina | 02-Analyze | PTM - Identfy Changes in GD for Localization ARG | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-02-29 | 2016-02-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052895 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - PTM | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2016-06-06 | 2016-06-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052896 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - PTM | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-02 | 2016-05-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052897 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTM - Run Tests | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | CapEx | Localization | IT - External | 76h | 0h | 76h | 2016-11-07 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052898 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTM - Break/Fix | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | CapEx | Localization | IT - External | 178h | 0h | 178h | 2016-11-10 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052899 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | OpEx | Localization | IT - External | 56h | 0h | 56h | 2016-10-11 | 2016-11-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052900 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052901 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | OpEx | Localization | IT - External | 61h | 0h | 61h | 2016-09-12 | 2016-10-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052902 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - Prep | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | CapEx | Localization | IT - External | 33h | 0h | 33h | 2016-10-20 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052903 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Validate | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | OpEx | Localization | IT - External | 13h | 0h | 13h | 2016-08-15 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052904 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Functional Specification (FSD) | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2016-08-15 | 2016-08-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052905 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | CapEx | Localization | IT - External | 124h | 0h | 124h | 2016-09-06 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052906 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052907 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - PTM | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052908 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052909 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052910 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052911 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-11-28 | 2016-11-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052912 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052913 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-06 | 2016-12-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052914 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-01-30 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052915 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052916 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | CapEx | Localization | IT - External | 256h | 0h | 256h | 2016-12-12 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 36 | 44 | 44 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052917 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | PTM | FUN | SI | Onshore | Dave; Amarish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052918 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | ARG KT visit | OTC | FUN | SI | Onshore | Sudhanshu; Mathur | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052919 | No | Yes | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | OTC | FUN | SI | Onshore | Sudhanshu; Mathur | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052920 | No | No | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - |  | Missing Stream | Saputo | Onshore | Dummer; Kirk | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052921 | No | No | Yes | Argentina | Argentina | 02-Analyze | OTC - Identify Changes in GD for Localization ARG | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 35h | 0h | 35h | 2016-02-29 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052922 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - OTC | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 21.45h | 0h | 21.45h | 2016-05-02 | 2016-05-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052923 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- OTC | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 39.5h | 0h | 39.5h | 2016-05-02 | 2016-05-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052924 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-01-23 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052925 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - LOG | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 41.9h | 0h | 41.9h | 2016-05-02 | 2016-05-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052926 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - LOG | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 9.05h | 0h | 9.05h | 2016-05-02 | 2016-05-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052927 | No | No | Yes | Argentina | Argentina | 02-Analyze | LOG - Identify changes in GD for Localization ARG | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 40.35h | 0h | 40.35h | 2016-03-21 | 2016-04-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052928 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Manage Defects | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-06 | 2016-09-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052929 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | OpEx | Localization | IT - External | 128h | 0h | 128h | 2016-10-07 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052930 | No | No | Yes | Argentina | Argentina | 01-Preparation | LOG Prepare Arg - GD integration | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 7.5h | 0h | 7.5h | 2016-02-15 | 2016-02-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052931 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - Prep | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052932 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | OpEx | Localization | IT - External | 40h | 0h | 40h | 2016-10-17 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052933 | No | No | Yes | Argentina | Argentina | 04-Test | LOG - SIT 2 - Run Tests | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052934 | No | No | Yes | Argentina | Argentina | 04-Test | LOG - SIT 2 - Break/Fix | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052935 | No | No | Yes | Argentina | Argentina | 04-Test | LOG - SIT 2 - Manage Defects | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052936 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2016-11-07 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052937 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-11-21 | 2016-11-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052938 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | OpEx | Localization | IT - External | 132h | 0h | 132h | 2017-02-06 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052939 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052940 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 196h | 0h | 196h | 2016-12-19 | 2017-01-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 32 | 40 | 40 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052941 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052942 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-12-05 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052943 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052944 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG KT visit | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-08-15 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052945 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Prepare | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-11 | 2016-07-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052946 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 192h | 0h | 192h | 2016-09-06 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052947 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052948 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | LOG | FUN | SI | Onshore | Hayashiguchi; Michael | SAP | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2017-02-20 | 2017-03-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 24 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052949 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052950 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Change Agents Network Execution and Monitoring | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 83h | 0h | 83h | 2017-02-20 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052951 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Monitor Key users Network | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 63h | 0h | 63h | 2017-02-13 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052952 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Change Agents Network Execution and Monitoring | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 129h | 0h | 129h | 2016-12-05 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 25 | 16 | 25 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052953 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition Plan Execution & Monitoring | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 81h | 0h | 81h | 2016-12-05 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052954 | No | Yes | No | Argentina | Argentina | 04-Test | Role Mapping (ongoing) | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 199h | 0h | 199h | 2016-09-12 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052955 | No | Yes | No | Argentina | Argentina | 04-Test | Business Readiness Execution & Monitoring - Survey/communication | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 98h | 0h | 98h | 2016-09-19 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052956 | No | Yes | No | Argentina | Argentina | 04-Test | Transition Plan Execution & Monitoring | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 130h | 0h | 130h | 2016-09-12 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052957 | No | Yes | No | Argentina | Argentina | 04-Test | Change Agents Network Execution and Monitoring | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 43h | 0h | 43h | 2016-09-26 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052958 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Walkthrough KU presentation with DCLs | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052959 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Prepare Presentation for managers who will assign | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 155h | 0h | 155h | 2016-06-10 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052960 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Walkthrough KU on-boarding deck with DCLs | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052961 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Prepare Key Users On boarding deck | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 5h | 0h | 5h | 2016-07-25 | 2016-07-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052962 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Establish Key User Requirements | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 5h | 0h | 5h | 2016-07-25 | 2016-07-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052963 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Hold mitigation workshops | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 27h | 0h | 27h | 2016-05-09 | 2016-05-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052964 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Package Changes and Impacts per Department | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 13h | 0h | 13h | 2016-05-12 | 2016-05-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052965 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Build comm package (BU, Changes =benefits, nature of change, people, process, tool Impacts) | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 40h | 0h | 40h | 2016-05-16 | 2016-05-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052966 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Manage as uncovered (log, assess, mitigate, approve) - GTS | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 10h | 0h | 10h | 2016-05-30 | 2016-06-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052967 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Obtain approval on mitigation plans | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052968 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Review Changes and Impacts with Core Team | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 34h | 0h | 34h | 2016-05-24 | 2016-05-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052969 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Role mapping Workshops (incl. RMS Training) | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 41h | 0h | 41h | 2016-06-08 | 2016-06-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052970 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Onboarding of Division Managers to Role Mapping | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 4h | 0h | 4h | 2016-06-09 | 2016-06-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052971 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Educate\Train DCL on Role mapping | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-12 | 2016-05-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052972 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Evaluate variances between current and future tasks and responsibilities (old Roles vs new Roles) | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 47h | 0h | 47h | 2016-07-25 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052973 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Adress SOD Issues | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 5h | 0h | 5h | 2016-07-18 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052974 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Update FAQ and CA toolkit (on-going) | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 20h | 0h | 20h | 2016-05-31 | 2016-09-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052975 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-CM | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 89h | 0h | 89h | 2017-03-20 | 2017-06-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 12 | 0 | 9 | 8 | 11 | 15 | 3 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052976 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Prepare deck for CM training for managers | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 6h | 0h | 6h | 2016-06-06 | 2016-06-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052977 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Validate deck for CM training for managers | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-06-15 | 2016-06-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052978 | No | Yes | No | Argentina | Argentina | 03-Design/Build | On-going management of additional mitigation measures | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 42h | 0h | 42h | 2016-05-30 | 2016-06-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052979 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Implement monitoring process (bi-weekly touchpoint with some managers?) | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 2h | 0h | 2h | 2016-09-06 | 2016-09-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052980 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Present transition activities to responsible managers (Timing will vary depending on start date of transition activities) | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052981 | No | Yes | No | Argentina | Argentina | 03-Design/Build | CA weekly touchpoint/Pulse Check | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 12h | 0h | 12h | 2016-06-06 | 2016-07-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052982 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Convert each mitigation measure into and executable action (Resp., end date, etc…) and log in the appropriate execution plan (Communication, Training or Transition) | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 1h | 0h | 1h | 2016-06-01 | 2016-06-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052983 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Debrief on Pulse Check | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-16 | 2016-05-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052984 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: PTP Identify if there are Business risks and transfer info to Business Risk Log\Template. | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-03-15 | 2016-03-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052985 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : OCT Align Functional Team on Roles Catalog Change Control process | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 5h | 0h | 5h | 2016-03-14 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052986 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: OTC Divide Catalog by Process Area | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052987 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: OTC Workshops : Evaluate Variances between current and future tasks and responsibilties (old Roles vs new roles) | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052988 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: OTC Determine mitigation measures for each variances (in meetings) | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052989 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: OTC Educate/Train DCL on Role Mapping | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-10 | 2016-05-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052990 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: RTR Workshops : Evaluate Variances between current and future tasks and responsibilties (old Roles vs new roles) | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052991 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: RTR Determine mitigation measures for each variances (in meetings) | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052992 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : RTR Align Functional Team on Roles Catalog Change Control process | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052993 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: RTR Divide Catalog by Process Area | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052994 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: RTR Educate/Train DCL on Role Mapping | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-10 | 2016-05-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052995 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : OTC Review and Validate Changes AND Identify and Describe Impacts | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 19h | 0h | 19h | 2016-03-15 | 2016-04-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052996 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: OTC Insert line for new change | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 11.5h | 0h | 11.5h | 2016-03-16 | 2016-04-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052997 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: OTC Identify if there are Business risks and transfer info to Business Risk Log\Template. | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-03-16 | 2016-03-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052998 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: OTC Start Mitigation Measures for High Impact Changes or Business Risks. (*leverage positive impacts when possible) | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-03-16 | 2016-03-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052999 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: OTC Hold final CI WORKSHOP : Confirm High Level CI and complete\define Mitigation Measures | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 15h | 0h | 15h | 2016-04-25 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053000 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : OTC Validate Mitigation Measures with Managers | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-29 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053001 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : OTC Obtain Business lead Approval (Fernando Mayer) | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-29 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053002 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : RTR Review and Validate Changes AND Identify and Describe Impacts | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 24h | 0h | 24h | 2016-03-15 | 2016-04-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053003 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: RTR Insert line for new change | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 11.5h | 0h | 11.5h | 2016-03-16 | 2016-04-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053004 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: RTR Identify if there are Business risks and transfer info to Business Risk Log\Template. | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-03-16 | 2016-03-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053005 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: RTR Start Mitigation Measures for High Impact Changes or Business Risks. (*leverage positive impacts when possible) | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-03-16 | 2016-03-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053006 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: RTR Hold final CI WORKSHOP : Confirm High Level CI and complete\define Mitigation Measures | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 15h | 0h | 15h | 2016-04-25 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053007 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : RTR Validate Mitigation Measures with Managers | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-29 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053008 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : RTR Obtain Business lead Approval (Fernando Mayer) | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-29 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053009 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : Identify all localization for the High Level Impact Assessment | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 16h | 0h | 16h | 2016-03-07 | 2016-03-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053010 | No | Yes | No | Argentina | Argentina | 01-Preparation | ArG - Prepare for Localisation High Level Impact assessment | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 41h | 0h | 41h | 2016-02-29 | 2016-03-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053011 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: OTC Identify Business Risks from the Change Impacts and briefly describe each risks | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053012 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: OTC Recommand and validate mitigation measures to address Business risks | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 10h | 0h | 10h | 2016-04-18 | 2016-04-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053013 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: OTC Incorporate measures into Execution Plans with Change Management team | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-18 | 2016-04-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053014 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: OTC Log Business risks in PMO Log | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-18 | 2016-04-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053015 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: OTC Report Project Risks to Project Managers | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-18 | 2016-04-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053016 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: RTR Identify Business Risks from the Change Impacts and briefly describe each risks | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053017 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: RTR Recommand and validate mitigation measures to address Business risks | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 10h | 0h | 10h | 2016-04-18 | 2016-04-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053018 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: RTR Incorporate measures into Execution Plans with Change Management team | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-18 | 2016-04-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053019 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: RTR Log Business risks in PMO Log | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-18 | 2016-04-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053020 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: RTR Report Project Risks to Project Managers | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-04-18 | 2016-04-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053021 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: OTC Determine Transition Activities From Completed High Level CI analysis | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-16 | 2016-05-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053022 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: OTC Determine Transition Activitie from Completed Detailed CI Analysis | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 10h | 0h | 10h | 2016-07-04 | 2016-07-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053023 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: OTC Obtain Approval of the Transition Plan | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 20h | 0h | 20h | 2016-07-18 | 2016-07-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053024 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: Establish timelines (planning workshops) | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-07-11 | 2016-07-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053025 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: Keep Applicable Benefits and KPI | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 48h | 0h | 48h | 2016-05-02 | 2016-05-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053026 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : Confirm benefit and KPI owners | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-16 | 2016-05-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053027 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : Confirm Baseline measurement procedures | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 2h | 0h | 2h | 2016-06-13 | 2016-06-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053028 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG : Obtain buy-in from owners on Value realization responsibilities | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053029 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: RTR Determine Transition Activities From Completed High Level CI analysis | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-16 | 2016-05-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053030 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: RTR Determine Transition Activitie from Completed Detailed CI Analysis | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 10h | 0h | 10h | 2016-07-04 | 2016-07-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053031 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG: RTR Obtain Approval of the Transition Plan | CM | CM | Saputo | Onshore | Provost; Mira | Saputo | Yes | OpEx | Localization | IT - Internal | 20h | 0h | 20h | 2016-07-18 | 2016-07-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053032 | No | Yes | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | MDG | To Define | SI | Onshore | El Ouehabi; Hassan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053033 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Data collection templates (DCT) - Explain and collect | PTM | FUN | Saputo | Onshore | Leite; Alexandre | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053034 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | PTM | FUN | Saputo | Onshore | Leite; Alexandre | Saputo | Yes | OpEx | Localization | IT - Internal | 42.5h | 0h | 42.5h | 2016-10-11 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053035 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTM | FUN | Saputo | Onshore | Leite; Alexandre | Saputo | Yes | OpEx | Localization | IT - Internal | 104h | 0h | 104h | 2016-10-11 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053036 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTM | FUN | Saputo | Onshore | Leite; Alexandre | Saputo | Yes | CapEx | Localization | IT - Internal | 63.5h | 0h | 63.5h | 2016-11-18 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053037 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTM | FUN | Saputo | Onshore | Leite; Alexandre | Saputo | Yes | CapEx | Localization | IT - Internal | 61h | 0h | 61h | 2016-12-28 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 22.5 | 0 | 0 | 0 | 0 | 0 | 38.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053038 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTM | FUN | Saputo | Onshore | Leite; Alexandre | Saputo | Yes | CapEx | Localization | IT - Internal | 68.5h | 0h | 68.5h | 2016-09-26 | 2016-10-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053039 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | Saputo | Onshore | Leite; Alexandre | Saputo | Yes | OpEx | Localization | IT - Internal | 429h | 0h | 429h | 2017-03-06 | 2017-08-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 39.5 | 40.5 | 12.5 | 20 | 12 | 35 | 61.5 | 6 | 0 | 0 | 0 | 0 | 44 | 14.5 | 0 | 58 | 0 | 0 | 2 | 0 | 33.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053040 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | PTM | FUN | Saputo | Onshore | Leite; Alexandre | Saputo | Yes | OpEx | Localization | IT - Internal | 7.5h | 0h | 7.5h | 2016-10-10 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053041 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | PTM | FUN | Saputo | Onshore | Leite; Alexandre | Saputo | Yes | CapEx | Localization | IT - Internal | 43.5h | 0h | 43.5h | 2016-12-12 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053042 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTM - Run Tests | PTM | FUN | Saputo | Onshore | Leite; Alexandre | Saputo | Yes | CapEx | Localization | IT - Internal | 84h | 0h | 84h | 2016-11-02 | 2016-11-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053043 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | PTM | FUN | Saputo | Onshore | Leite; Alexandre | Saputo | Yes | OpEx | Localization | IT - Internal | 6.5h | 0h | 6.5h | 2016-11-25 | 2016-11-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053044 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTM | FUN | Saputo | Onshore | Leite; Alexandre | Saputo | Yes | CapEx | Localization | IT - Internal | 164h | 0h | 164h | 2016-12-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 35.5 | 45 | 39.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053045 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTM | FUN | Saputo | Onshore | Leite; Alexandre | Saputo | Yes | OpEx | Localization | IT - Internal | 118h | 0h | 118h | 2017-02-13 | 2017-02-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053046 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - PTM | PTM | FUN | Saputo | Onshore | Leite; Alexandre | Saputo | Yes | CapEx | Localization | IT - Internal | 81h | 0h | 81h | 2017-01-23 | 2017-02-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 38.5 | 42.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053047 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | Saputo | Onshore | Leite; Alexandre | Saputo | Yes | CapEx | Localization | IT - Internal | 61h | 0h | 61h | 2017-02-06 | 2017-03-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053048 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | TAI | TAI | SI | Onshore | Doherty; Sean | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053049 | No | Yes | No | Argentina | Argentina | 04-Test | TEST - Technical Architecture and Infrastructure (gen) | TAI | TAI | SI | Onshore | Doherty; Sean | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-01 | 2016-09-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053050 | No | Yes | No | Argentina | Argentina | 04-Test | Management | TAI | TAI | SI | Onshore | Doherty; Sean | Accenture | Yes | CapEx | Localization | IT - External | 374h | 0h | 374h | 2016-09-12 | 2016-11-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053051 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PMO | PMO | SI | Onshore | Minotti; Daniel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053052 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | SEC | SEC | SI | Onshore | Heaton; John | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053053 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | MDG | DC | SI | Onshore | Fonseca; Thiago | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053054 | No | Yes | No | Argentina | Argentina | 06-Hypercare | MDSS Project Management (Hypercare) - DC | MDG | DC | SI | Onshore | Fonseca; Thiago | Accenture | Yes | OpEx | Localization | IT - External | 25h | 0h | 25h | 2017-02-06 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053055 | No | Yes | No | Argentina | Argentina | 04-Test | Test - MDSS Project Management - DC | MDG | DC | SI | Onshore | Fonseca; Thiago | Accenture | Yes | CapEx | Localization | IT - External | 212h | 0h | 212h | 2016-10-10 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053056 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | MDSS Project Management (Cutover/Go-live) - DC | MDG | DC | SI | Onshore | Fonseca; Thiago | Accenture | Yes | CapEx | Localization | IT - External | 118h | 0h | 118h | 2017-01-03 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 32 | 20 | 20 | 10 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053057 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PTP | FUN | SI | Onshore | Lospied; Jerome | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053058 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | SEC | SEC | SI | Onshore | Vernon; Franck | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053059 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | GRC AC - Cutover planning and Exucution | SEC | SEC | SI | Onshore | Vernon; Franck | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-18 | 2016-10-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053060 | No | Yes | No | Argentina | Argentina | 04-Test | Project Management and Planning for SEC | SEC | SEC | SI | Onshore | Vernon; Franck | Accenture | Yes | CapEx | Localization | IT - External | 99h | 0h | 99h | 2016-10-03 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053061 | No | Yes | No | Argentina | Argentina | 04-Test | FUT Support Roles | SEC | SEC | SI | Onshore | Vernon; Franck | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-17 | 2016-10-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053062 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT Defect Resolution | SEC | SEC | SI | Onshore | Vernon; Franck | Accenture | Yes | CapEx | Localization | IT - External | 166h | 0h | 166h | 2016-12-12 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 16 | 32 | 24 | 30 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053063 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-SEC | SEC | SEC | SI | Onshore | Vernon; Franck | Accenture | Yes | OpEx | Localization | IT - External | 36h | 0h | 36h | 2017-03-27 | 2017-04-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053064 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Hypercare/support | SEC | SEC | SI | Onshore | Vernon; Franck | Accenture | Yes | OpEx | Localization | IT - External | 156h | 0h | 156h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 52 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053065 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Derived Role Build | SEC | SEC | SI | Onshore | Vernon; Franck | Accenture | Yes | CapEx | Localization | IT - External | 13h | 0h | 13h | 2016-10-03 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053066 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Support Role Build and UT | SEC | SEC | SI | Onshore | Vernon; Franck | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-19 | 2016-09-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053067 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Security Design Workshops | SEC | SEC | SI | Onshore | Vernon; Franck | Accenture | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-10-03 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053068 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Composite Role Design | SEC | SEC | SI | Onshore | Vernon; Franck | Accenture | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-10-03 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053069 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Composite Role Build | SEC | SEC | SI | Onshore | Vernon; Franck | Accenture | Yes | CapEx | Localization | IT - External | 13h | 0h | 13h | 2016-10-03 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053070 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Management (Hypercare) | SEC | SEC | SI | Onshore | Vernon; Franck | Accenture | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2017-02-06 | 2017-02-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053071 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Management (Cutover/Go-live) | SEC | SEC | SI | Onshore | Vernon; Franck | Accenture | Yes | CapEx | Localization | IT - External | 78h | 0h | 78h | 2016-12-05 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053072 | No | Yes | No | Argentina | Argentina | 04-Test | Security Role FUT | SEC | SEC | SI | Onshore | Vernon; Franck | Accenture | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2016-09-19 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053073 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 Defect Resolution | SEC | SEC | SI | Onshore | Vernon; Franck | Accenture | Yes | CapEx | Localization | IT - External | 195h | 0h | 195h | 2016-10-24 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053074 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cutover Planning and Execution | SEC | SEC | SI | Onshore | Vernon; Franck | Accenture | Yes | CapEx | Localization | IT - External | 150h | 0h | 150h | 2016-10-24 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 28 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053075 | No | No | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - |  | Missing Stream |  |  | Holzheimer; Donald |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053076 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | LOG | FUN | SI | Onshore | Bright; Brandon | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053077 | No | Yes | No | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | LOG | FUN | SI | Onshore | Bright; Brandon | IBM | Yes | CapEx | Localization | IT - External | 407h | 0h | 407h | 2016-09-06 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053078 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | LOG | FUN | SI | Onshore | Bright; Brandon | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2016-12-12 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053079 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | LOG | FUN | SI | Onshore | Bright; Brandon | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2016-11-07 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053080 | No | Yes | No | Argentina | Argentina | 04-Test | LOG - SIT 2 - Manage Defects | LOG | FUN | SI | Onshore | Bright; Brandon | IBM | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2016-11-14 | 2016-11-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053081 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | LOG | FUN | SI | Onshore | Bright; Brandon | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-12-05 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053082 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | LOG | FUN | SI | Onshore | Bright; Brandon | IBM | Yes | CapEx | Localization | IT - External | 30h | 0h | 30h | 2016-12-05 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053083 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Management (Cutover/Go-live) | LOG | FUN | SI | Onshore | Bright; Brandon | IBM | Yes | CapEx | Localization | IT - External | 284h | 0h | 284h | 2016-12-12 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 32 | 40 | 32 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053084 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Management (Hypercare) | LOG | FUN | SI | Onshore | Bright; Brandon | IBM | Yes | CapEx | Localization | IT - External | 223h | 0h | 223h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 56 | 70 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053085 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | PTP | FUN | SI | Onshore | Lazure; Stephane | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053086 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | PTP | FUN | SI | Onshore | Lazure; Stephane | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053087 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | PTP | FUN | SI | Onshore | Lazure; Stephane | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053088 | No | Yes | No | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTP | FUN | SI | Onshore | Lazure; Stephane | IBM | Yes | CapEx | Localization | IT - External | 364h | 0h | 364h | 2016-09-12 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053089 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Support | PTP | FUN | SI | Onshore | Lazure; Stephane | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053090 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PTP | FUN | SI | Onshore | Lazure; Stephane | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053091 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PTM | FUN | SI | Onshore | Novak; Steve | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053092 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTM | FUN | SI | Onshore | Novak; Steve | IBM | Yes | CapEx | Localization | IT - External | 242h | 0h | 242h | 2016-09-06 | 2016-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053093 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Management (Hypercare) - PTM | PTM | FUN | SI | Onshore | Novak; Steve | IBM | Yes | CapEx | Localization | IT - External | 141h | 0h | 141h | 2017-02-06 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 44 | 26 | 44 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053094 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Management (Cutover/Go-live) | PTM | FUN | SI | Onshore | Novak; Steve | IBM | Yes | CapEx | Localization | IT - External | 346h | 0h | 346h | 2016-12-12 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 35 | 44 | 44 | 44 | 44 | 44 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053095 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | SI | Onshore | Novak; Steve | IBM | Yes | CapEx | Localization | IT - External | 33h | 0h | 33h | 2017-02-07 | 2017-02-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053096 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | RTR | FUN | SI | Onshore | Bebjak; Ludo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053097 | No | Yes | No | Argentina | Argentina | 02-Analyze | RTR - Identify Changes in GD for Localization ARG | RTR | FUN | SI | Onshore | Bebjak; Ludo | IBM | Yes | CapEx | Localization | IT - External | 95.13h | 0h | 95.13h | 2016-02-29 | 2016-04-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053098 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053099 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Management (Hypercare) | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 119h | 0h | 119h | 2017-02-07 | 2017-03-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 36 | 33 | 27 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053100 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-09-06 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053101 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 73h | 0h | 73h | 2016-09-10 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053102 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Management (Cutover/Go-live) | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 288h | 0h | 288h | 2016-12-05 | 2017-01-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 31 | 52 | 41 | 54 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053103 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2016-12-19 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053104 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053105 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-02-06 | 2017-03-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053106 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 41h | 0h | 41h | 2017-02-06 | 2017-02-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053107 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 30h | 0h | 30h | 2016-12-05 | 2017-01-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053108 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 30h | 0h | 30h | 2016-12-05 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053109 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 11h | 0h | 11h | 2016-11-07 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053110 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2016-11-28 | 2016-12-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053111 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-11-14 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053112 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG KT visit | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2016-08-08 | 2016-08-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053113 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | OTC | FUN | SI | Onshore | Irene Salazar | IBM | Yes | CapEx | Localization | IT - External | 426h | 0h | 426h | 2016-09-06 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053114 | No | Yes | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PMO | PMO | SI | Onshore | Porter; Stephanie | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053115 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PMO | PMO | SI | Onshore | Von Fintel; Dieter | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053116 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, team organization) | PMO | PMO | SI | Onshore | Von Fintel; Dieter | IBM | Yes | CapEx | Localization | IT - External | 123h | 0h | 123h | 2016-09-06 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053117 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | PCR 212 Interim Daily Operational KPI’s report | PMO | PMO | SI | Onshore | Von Fintel; Dieter | IBM | Yes | CapEx | Localization | IT - External | 108h | 0h | 108h | 2016-12-05 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053118 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Management | PMO | PMO | SI | Onshore | Von Fintel; Dieter | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2016-08-15 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053119 | No | Yes | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PMO | PMO | SI | Onshore | Gilbert; Michael | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053120 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053121 | No | Yes | No | Argentina | Argentina | 04-Test | Updates concepts decks | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | OpEx | Localization | IT - External | 9h | 0h | 9h | 2016-10-03 | 2016-11-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053122 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - PTP - Break/Fix | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053123 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - Manage Defects | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-11-28 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053124 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Support | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-18 | 2016-10-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053125 | No | Yes | No | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Localization | IT - External | 51h | 0h | 51h | 2016-10-24 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053126 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - PTP | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2016-05-02 | 2016-05-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053127 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- PTP | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2016-05-23 | 2016-05-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053128 | No | Yes | No | Argentina | Argentina | 02-Analyze | PTP - Identify Changesin GD for Localization ARG | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Localization | IT - External | 60h | 0h | 60h | 2016-03-07 | 2016-04-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053129 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2016-12-12 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053130 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2016-12-26 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 16 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053131 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Solution Design Document (SDD) | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Localization | IT - External | 33h | 0h | 33h | 2016-08-08 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053132 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2016-09-26 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053133 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Manage Defects | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Localization | IT - External | 124h | 0h | 124h | 2016-09-06 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053134 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053135 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053136 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053137 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | OpEx | Localization | IT - External | 72h | 0h | 72h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 20 | 8 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053138 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2017-02-06 | 2017-02-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053139 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Localization | IT - External | 84h | 0h | 84h | 2016-12-19 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 16 | 16 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053140 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Localization | IT - External | 48h | 0h | 48h | 2017-02-13 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 8 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053141 | No | Yes | No | Argentina | Argentina | 01-Preparation | PTP Prepare ArG - GD integration | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-02-22 | 2016-02-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053142 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - Prep | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Localization | IT - External | 26h | 0h | 26h | 2016-10-11 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053143 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Manage Defects | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-12-05 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053144 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2016-12-05 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053145 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053146 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTP | FUN | SI | Onshore | Tran; Ted | Accenture | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2016-12-20 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 16 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053147 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 20h | 0h | 20h | 2017-01-09 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053148 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-12-19 | 2016-12-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053149 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 12h | 0h | 12h | 2016-12-12 | 2016-12-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053150 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 26h | 0h | 26h | 2016-12-05 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053151 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053152 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | OpEx | Localization | Business | 128h | 0h | 128h | 2017-02-06 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 48 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053153 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 10h | 0h | 10h | 2017-02-06 | 2017-02-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053154 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 10h | 0h | 10h | 2016-11-14 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053155 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 42h | 0h | 42h | 2016-12-26 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 32 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053156 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Support | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | OpEx | Localization | Business | 40h | 0h | 40h | 2016-08-08 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053157 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-11-11 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053158 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Validate | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | OpEx | Localization | Business | 40h | 0h | 40h | 2016-08-19 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053159 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 124h | 0h | 124h | 2016-09-12 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053160 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 64h | 0h | 64h | 2016-09-12 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053161 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 95h | 0h | 95h | 2016-09-12 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053162 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Data collection templates (DCT) - Explain and collect | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-08-14 | 2016-08-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053163 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTP | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | OpEx | Localization | Business | 2h | 0h | 2h | 2017-05-15 | 2017-05-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053164 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - PTP | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 11.02h | 0h | 11.02h | 2016-05-02 | 2016-05-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053165 | No | No | Yes | Argentina | Argentina | 02-Analyze | PTP - Identify Changesin GD for Localization ARG | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 37.65h | 0h | 37.65h | 2016-02-29 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053166 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | OpEx | Localization | Business | 15h | 0h | 15h | 2016-10-10 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053167 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-10-18 | 2016-10-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053168 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 20h | 0h | 20h | 2017-01-23 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053169 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- PTP | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 5.02h | 0h | 5.02h | 2016-05-02 | 2016-05-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053170 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTP - Run Tests | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 65h | 0h | 65h | 2016-10-31 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053171 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053172 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | OpEx | Localization | Business | 65h | 0h | 65h | 2016-10-03 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053173 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PTP | FUN | Saputo | Onshore | Machula; Michele | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053174 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053175 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | OpEx | Localization | Business | 32h | 0h | 32h | 2016-10-03 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053176 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | OpEx | Localization | Business | 1h | 0h | 1h | 2016-11-09 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053177 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | OpEx | Localization | Business | 28h | 0h | 28h | 2016-10-18 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053178 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTP - Run Tests | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Localization | Business | 42h | 0h | 42h | 2016-10-24 | 2016-11-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053179 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Localization | Business | 71h | 0h | 71h | 2017-01-30 | 2017-02-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053180 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | OpEx | Localization | Business | 14h | 0h | 14h | 2016-10-03 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053181 | No | No | Yes | Argentina | Argentina | 02-Analyze | PTP - Identify Changesin GD for Localization ARG | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-02-29 | 2016-02-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053182 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - PTP | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Localization | Business | 18h | 0h | 18h | 2016-05-02 | 2016-05-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053183 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- PTP | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Localization | Business | 6h | 0h | 6h | 2016-05-02 | 2016-05-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053184 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTP | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | OpEx | Localization | Business | 42h | 0h | 42h | 2017-03-20 | 2017-06-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 32 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053185 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Support | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | OpEx | Localization | Business | 11h | 0h | 11h | 2016-08-08 | 2016-08-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053186 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Data collection templates (DCT) - Explain and collect | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-08-14 | 2016-08-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053187 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Localization | Business | 47h | 0h | 47h | 2016-09-12 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053188 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Localization | Business | 107h | 0h | 107h | 2016-09-06 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053189 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Localization | Business | 40h | 0h | 40h | 2016-09-12 | 2016-10-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053190 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-11-11 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053191 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Validate | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | OpEx | Localization | Business | 26h | 0h | 26h | 2016-08-16 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053192 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Localization | Business | 73h | 0h | 73h | 2016-12-05 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053193 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Localization | Business | 40h | 0h | 40h | 2016-10-31 | 2016-12-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053194 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Localization | Business | 5h | 0h | 5h | 2017-02-06 | 2017-02-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053195 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | OpEx | Localization | Business | 166h | 0h | 166h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 54 | 68.5 | 35.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053196 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053197 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Localization | Business | 37h | 0h | 37h | 2016-12-20 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 2 | 6 | 14 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053198 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Localization | Business | 4h | 0h | 4h | 2016-12-12 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053199 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Localization | Business | 8h | 0h | 8h | 2017-01-04 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053200 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTP | FUN | Saputo | Onshore | Piencikowski; Joy | Saputo | Yes | CapEx | Localization | Business | 31h | 0h | 31h | 2016-12-28 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 3 | 5 | 17 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053201 | No | No | Yes | Argentina | Argentina | 04-Test | Project SAP Environment Support | TAI | TAI | SI | Onshore | Chea; SaySanne | Accenture | Yes | CapEx | Localization | IT - External | 35h | 0h | 35h | 2016-10-24 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053202 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover Steps | TAI | TAI | SI | Onshore | Chea; SaySanne | Accenture | Yes | CapEx | Localization | IT - External | 264h | 0h | 264h | 2016-12-26 | 2017-02-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 16 | 40 | 40 | 16 | 40 | 56 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053203 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Performance testing write-off | TAI | TAI | SI | Onshore | Chea; SaySanne | Accenture | Yes | CapEx | Localization | IT - External | 84h | 0h | 84h | 2016-12-12 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053204 | No | No | Yes | Argentina | Argentina | 04-Test | Performance testing and refresh | TAI | TAI | SI | Onshore | Chea; SaySanne | Accenture | Yes | CapEx | Localization | IT - External | 116h | 0h | 116h | 2016-10-31 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053205 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Support Hypercare | TAI | TAI | SI | Onshore | Chea; SaySanne | Accenture | Yes | CapEx | Localization | IT - External | 144h | 0h | 144h | 2017-02-13 | 2017-03-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 48 | 40 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053206 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Identify and procure local hardware | TAI | TAI | SI | Onshore | Chea; SaySanne | Accenture | Yes | CapEx | Localization | IT - External | 11h | 0h | 11h | 2016-09-05 | 2016-09-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053207 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Technical Architecture and Infrastructure (gen) | TAI | TAI | SI | Onshore | Chea; SaySanne | Accenture | Yes | CapEx | Localization | IT - External | 104h | 0h | 104h | 2016-10-03 | 2016-10-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053208 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | TAI | TAI | SI | Onshore | Chea; SaySanne | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053209 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PMO | PMO | Saputo | Onshore | Sabir; Kaoutar | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053210 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PMO | PMO | PMO | Saputo | Onshore | Sabir; Kaoutar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053211 | No | No | Yes | Argentina | Argentina | 04-Test | Communication plan execution and monitoring | PMO | PMO | Saputo | Onshore | Sabir; Kaoutar | Saputo | Yes | OpEx | Localization | IT - Internal | 10h | 0h | 10h | 2016-10-03 | 2016-10-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053212 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - OTC | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-02-20 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053213 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Manage Defects | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 42h | 0h | 42h | 2016-10-03 | 2016-10-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053214 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 22h | 0h | 22h | 2016-09-26 | 2016-10-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053215 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - Prep | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2016-10-24 | 2016-10-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053216 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Configuration | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2016-08-08 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053217 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG KT visit | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2016-08-08 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053218 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 166h | 0h | 166h | 2016-09-06 | 2016-10-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053219 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Unit testing Configuration Documentation | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 34h | 0h | 34h | 2016-08-08 | 2016-09-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053220 | No | No | Yes | Argentina | Argentina | 04-Test | OTC - SIT 2 - Run Tests | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2016-10-25 | 2016-11-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053221 | No | No | Yes | Argentina | Argentina | 04-Test | OTC - SIT 2 - Break/Fix | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 95h | 0h | 95h | 2016-10-31 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053222 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-11-14 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053223 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053224 | No | No | Yes | Argentina | Argentina | 04-Test | OTC - SIT 2 - Manage Defects | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 97h | 0h | 97h | 2016-10-25 | 2016-12-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053225 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2016-12-05 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053226 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 186h | 0h | 186h | 2016-12-05 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 20 | 44 | 36 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053227 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 62h | 0h | 62h | 2016-12-21 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053228 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Manage Defects | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 79h | 0h | 79h | 2016-12-05 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053229 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-28 | 2016-11-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053230 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2017-02-06 | 2017-02-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053231 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 87h | 0h | 87h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 44 | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053232 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053233 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053234 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - OTC | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053235 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- OTC | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2016-05-24 | 2016-06-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053236 | No | No | Yes | Argentina | Argentina | 02-Analyze | OTC - Identify Changes in GD for Localization ARG | OTC | FUN | SI | Onshore | Lanctot; Francois | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-02-29 | 2016-03-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053237 | No | No | Yes | Argentina | Argentina | 03-Design/Build | SoD Analysis Prior to SIT - Roles | SEC | SEC | SI | Landed Onshore | Manongsong; Melissa | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-18 | 2016-09-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053238 | No | No | Yes | Argentina | Argentina | 03-Design/Build | SoD Remediation Prior to SIT - Roles | SEC | SEC | SI | Landed Onshore | Manongsong; Melissa | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-21 | 2016-07-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053239 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | GRC AC - UAT Execution | SEC | SEC | SI | Landed Onshore | Manongsong; Melissa | Accenture | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2016-12-05 | 2017-04-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053240 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cutover Planning and Execution | SEC | SEC | SI | Landed Onshore | Manongsong; Melissa | Accenture | Yes | CapEx | Localization | IT - External | 190h | 0h | 190h | 2016-12-19 | 2017-03-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 16 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053241 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SAP Security Detailed Design | SEC | SEC | SI | Landed Onshore | Manongsong; Melissa | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-23 | 2016-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053242 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SoD Analysis & Remediation - Role Level | SEC | SEC | SI | Landed Onshore | Manongsong; Melissa | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-04 | 2016-07-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053243 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Security Profiles & Authorizations | SEC | SEC | SI | Landed Onshore | Manongsong; Melissa | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-06-13 | 2016-06-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053244 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | GRC AC - Cutover planning and Exucution | SEC | SEC | SI | Landed Onshore | Manongsong; Melissa | Accenture | Yes | CapEx | Localization | IT - External | 384.5h | 0h | 384.5h | 2016-10-18 | 2017-04-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 36.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053245 | No | No | Yes | Argentina | Argentina | 04-Test | GRC AC - SIT Execution | SEC | SEC | SI | Landed Onshore | Manongsong; Melissa | Accenture | Yes | CapEx | Localization | IT - External | 176h | 0h | 176h | 2016-10-24 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053246 | No | No | Yes | Argentina | Argentina | 06-Hypercare | GRC AC - Hypercare | SEC | SEC | SI | Landed Onshore | Manongsong; Melissa | Accenture | Yes | CapEx | Localization | IT - External | 160h | 0h | 160h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053247 | No | No | Yes | Argentina | Argentina | 03-Design/Build | GRC AC - Build & UT | SEC | SEC | SI | Landed Onshore | Manongsong; Melissa | Accenture | Yes | CapEx | Localization | IT - External | 95h | 0h | 95h | 2016-09-07 | 2016-09-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053248 | No | No | Yes | Argentina | Argentina | 03-Design/Build | GRC AC - SIT Prep | SEC | SEC | SI | Landed Onshore | Manongsong; Melissa | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-13 | 2016-10-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053249 | No | No | Yes | Argentina | Argentina | 03-Design/Build | SoD Analysis and Remediation | SEC | SEC | SI | Landed Onshore | Manongsong; Melissa | Accenture | Yes | CapEx | Localization | IT - External | 56h | 0h | 56h | 2016-09-30 | 2016-10-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053250 | No | No | Yes | Argentina | Argentina | 04-Test | SoD Analysis and Remediation | SEC | SEC | SI | Landed Onshore | Manongsong; Melissa | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053251 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT Defect Resolution | SEC | SEC | SI | Landed Onshore | Manongsong; Melissa | Accenture | Yes | CapEx | Localization | IT - External | 162h | 0h | 162h | 2016-12-19 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 16 | 10 | 24 | 40 | 24 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053252 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | SoD Analysis and Remediation | SEC | SEC | SI | Landed Onshore | Manongsong; Melissa | Accenture | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2016-12-05 | 2016-12-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053253 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Security Profiles & Authorizations | SEC | SEC | SI | Offshore | Maynes; Rosemarie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-06-13 | 2016-06-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053254 | No | Yes | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SAP Security Detailed Design | SEC | SEC | SI | Offshore | Maynes; Rosemarie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-23 | 2016-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053255 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT Defect Resolution | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 106.2h | 0h | 106.2h | 2016-12-12 | 2017-02-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 1.5 | 21.1 | 19.4 | 17.7 | 3 | 12.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053256 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Support SIT 1 & Defect Resolution | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-28 | 2016-07-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053257 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 Defect Resolution | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 1.5h | 0h | 1.5h | 2016-09-26 | 2016-09-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053258 | No | No | Yes | Argentina | Argentina | 04-Test | Project Management and Planning for SEC | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 108h | 0h | 108h | 2016-09-26 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053259 | No | No | Yes | Argentina | Argentina | 04-Test | PCR - 214 - Logistics Security/Role Change Request - Security | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2016-12-19 | 2016-12-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053260 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | GRC AC - Cutover planning and Exucution | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 0.75h | 0h | 0.75h | 2016-12-26 | 2017-02-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053261 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Management (Hypercare) | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053262 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Composite Role Build | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 4.5h | 0h | 4.5h | 2016-09-19 | 2016-10-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053263 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Derived Role Build | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 15.5h | 0h | 15.5h | 2016-09-19 | 2016-10-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053264 | No | No | Yes | Argentina | Argentina | 03-Design/Build | SoD Analysis Prior to SIT - Roles | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-18 | 2016-09-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053265 | No | No | Yes | Argentina | Argentina | 03-Design/Build | SoD Remediation Prior to SIT - Roles | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-21 | 2016-07-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053266 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Management (Cutover/Go-live) | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 73.25h | 0h | 73.25h | 2016-11-14 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053267 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Security Role Design (Business Users) | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-06-20 | 2016-07-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053268 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Security Role Build & Unit Test (Business Users) | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-06-20 | 2016-07-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053269 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Support Role Build and UT | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 10.5h | 0h | 10.5h | 2016-09-19 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053270 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Master Role Build and UT | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 17h | 0h | 17h | 2016-09-12 | 2016-10-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053271 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 Defect Resolution | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 30.5h | 0h | 30.5h | 2016-11-09 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053272 | No | No | Yes | Argentina | Argentina | 04-Test | FUT Support Roles | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2016-10-17 | 2016-11-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053273 | No | No | Yes | Argentina | Argentina | 04-Test | Security Role FUT | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 33.5h | 0h | 33.5h | 2016-09-28 | 2016-10-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053274 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cutover Planning and Execution | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 16.2h | 0h | 16.2h | 2016-11-28 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 1.5 | 2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053275 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Hypercare/support | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | OpEx | Localization | IT - External | 186h | 0h | 186h | 2017-02-07 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 36 | 27 | 36 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053276 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | GRC AC - UAT Execution | SEC | SEC | SI | Offshore | Manaog; Alfredo | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053277 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare (Accenture) - DM | MDG | DM | SI | Offshore | Quinones; Franz | Accenture | Yes | CapEx | Localization | IT - External | 53.5h | 0h | 53.5h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5 | 18.5 | 0 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053278 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) (SI) - DM | MDG | DM | SI | Offshore | Quinones; Franz | Accenture | Yes | CapEx | Localization | IT - External | 22.5h | 0h | 22.5h | 2016-09-05 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053279 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT Execution Customer (Accenture) - DM | MDG | DM | SI | Offshore | Quinones; Franz | Accenture | Yes | CapEx | Localization | IT - External | 31.5h | 0h | 31.5h | 2016-12-19 | 2016-12-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053280 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute loads/ reports (Accenture) - DM | MDG | DM | SI | Offshore | Quinones; Franz | Accenture | Yes | CapEx | Localization | IT - External | 81h | 0h | 81h | 2016-12-05 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 4.5 | 9 | 22.5 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053281 | No | No | Yes | Argentina | Argentina | 04-Test | SIT1 - Defect Fix (Accenture) - DM | MDG | DM | SI | Offshore | Quinones; Franz | Accenture | Yes | CapEx | Localization | IT - External | 118h | 0h | 118h | 2016-09-12 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053282 | No | No | Yes | Argentina | Argentina | 04-Test | SIT2 - Defect Fix (Accenture) - DM | MDG | DM | SI | Offshore | Quinones; Franz | Accenture | Yes | CapEx | Localization | IT - External | 121.5h | 0h | 121.5h | 2016-10-24 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053283 | No | Yes | No | Argentina | Argentina | 04-Test | SIT2 - Defect Fix - DC | MDG | DC | SI | Offshore | Agena; Cherry | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053284 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Data verification Signoff sheets - DC | MDG | DC | SI | Offshore | Agena; Cherry | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-29 | 2016-11-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053285 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT Prep - DC | MDG | DC | SI | Offshore | Agena; Cherry | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053286 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover - DC | MDG | DC | SI | Offshore | Agena; Cherry | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053287 | No | Yes | No | Argentina | Argentina | 04-Test | SIT1 - Defect Fix - DC | MDG | DC | SI | Offshore | Agena; Cherry | Accenture | Yes | CapEx | Localization | IT - External | 176h | 0h | 176h | 2016-09-12 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053288 | No | Yes | No | Argentina | Argentina | 04-Test | M2 - Execute pre validation - DC | MDG | DC | SI | Offshore | Agena; Cherry | Accenture | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2016-10-12 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053289 | No | Yes | No | Argentina | Argentina | 04-Test | M1 - Execute pre validation - DC | MDG | DC | SI | Offshore | Agena; Cherry | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-11 | 2016-09-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053290 | No | Yes | No | Argentina | Argentina | 04-Test | M1 - Execute loads - DC | MDG | DC | SI | Offshore | Agena; Cherry | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053291 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Execute loads/ reports - DC | MDG | DC | SI | Offshore | Agena; Cherry | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053292 | No | Yes | No | Argentina | Argentina | 04-Test | M2 - Execute loads/reports - DC | MDG | DC | SI | Offshore | Agena; Cherry | Accenture | Yes | CapEx | Localization | IT - External | 78h | 0h | 78h | 2016-10-12 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053293 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute pre validation - DC | MDG | DC | SI | Offshore | Agena; Cherry | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053294 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute Loads/Reports - DC | MDG | DC | SI | Offshore | Agena; Cherry | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-28 | 2016-11-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053295 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Execute pre validation - DC | MDG | DC | SI | Offshore | Agena; Cherry | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053296 | No | Yes | No | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | SI | Offshore | Agena; Cherry | Accenture | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2016-09-12 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053297 | No | Yes | No | Argentina | Argentina | 04-Test | Training Prep - DC | MDG | DC | SI | Offshore | Agena; Cherry | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053298 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Hypercare Support - DC | MDG | DC | SI | Offshore | Agena; Cherry | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053299 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 0 Load in DEV - DC | MDG | DC | SI | Offshore | Agena; Cherry | Accenture | Yes | CapEx | Localization | IT - External | 70h | 0h | 70h | 2016-06-01 | 2016-06-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053300 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 1 Load in QA - DC | MDG | DC | SI | Offshore | Agena; Cherry | Accenture | Yes | CapEx | Localization | IT - External | 429h | 0h | 429h | 2016-06-27 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053301 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - WP Obtain the Data Verification Signoff sheet - DC | MDG | DC | SI | Offshore | Agena; Cherry | Accenture | Yes | CapEx | Localization | IT - External | 41h | 0h | 41h | 2016-07-04 | 2016-07-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053302 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - WP Obtain the Data Verification Signoff sheet - DC | MDG | DC | SI | Landed Onshore | Lloren; Jerry | Accenture | Yes | CapEx | Localization | IT - External | 56h | 0h | 56h | 2016-07-11 | 2016-08-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053303 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 1 Load in QA - DC | MDG | DC | SI | Landed Onshore | Lloren; Jerry | Accenture | Yes | CapEx | Localization | IT - External | 322h | 0h | 322h | 2016-06-27 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053304 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 0 Load in DEV - DC | MDG | DC | SI | Landed Onshore | Lloren; Jerry | Accenture | Yes | CapEx | Localization | IT - External | 100h | 0h | 100h | 2016-05-30 | 2016-06-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053305 | No | Yes | No | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | SI | Landed Onshore | Lloren; Jerry | Accenture | Yes | CapEx | Localization | IT - External | 204h | 0h | 204h | 2016-09-26 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053306 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute pre validation - DC | MDG | DC | SI | Landed Onshore | Lloren; Jerry | Accenture | Yes | CapEx | Localization | IT - External | 204h | 0h | 204h | 2016-11-07 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053307 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Execute pre validation - DC | MDG | DC | SI | Landed Onshore | Lloren; Jerry | Accenture | Yes | OpEx | Localization | IT - External | 214h | 0h | 214h | 2016-12-12 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 24 | 32 | 40 | 20 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053308 | No | Yes | No | Argentina | Argentina | 04-Test | M1 - Execute pre validation - DC | MDG | DC | SI | Landed Onshore | Lloren; Jerry | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-11 | 2016-09-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053309 | No | Yes | No | Argentina | Argentina | 04-Test | M1 -Support the data construction - DC | MDG | DC | SI | Landed Onshore | Lloren; Jerry | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-11 | 2016-09-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053310 | No | Yes | No | Argentina | Argentina | 04-Test | M2 -Support the data construction - DC | MDG | DC | SI | Landed Onshore | Lloren; Jerry | Accenture | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2016-09-12 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053311 | No | Yes | No | Argentina | Argentina | 04-Test | M2 - Execute pre validation - DC | MDG | DC | SI | Landed Onshore | Lloren; Jerry | Accenture | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2016-10-10 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053312 | No | Yes | No | Argentina | Argentina | 04-Test | M2 - Execute pre validation - DC | MDG | DC | SI | Offshore | Cabasagan; Fretsie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053313 | No | Yes | No | Argentina | Argentina | 04-Test | SIT1 - Defect Fix - DC | MDG | DC | SI | Offshore | Cabasagan; Fretsie | Accenture | Yes | CapEx | Localization | IT - External | 171h | 0h | 171h | 2016-09-12 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053314 | No | Yes | No | Argentina | Argentina | 04-Test | M1 - Execute pre validation - DC | MDG | DC | SI | Offshore | Cabasagan; Fretsie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-11 | 2016-09-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053315 | No | Yes | No | Argentina | Argentina | 04-Test | M1 - Execute loads - DC | MDG | DC | SI | Offshore | Cabasagan; Fretsie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053316 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT Prep - DC | MDG | DC | SI | Offshore | Cabasagan; Fretsie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053317 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover - DC | MDG | DC | SI | Offshore | Cabasagan; Fretsie | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053318 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Data verification Signoff sheets - DC | MDG | DC | SI | Offshore | Cabasagan; Fretsie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-29 | 2016-11-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053319 | No | Yes | No | Argentina | Argentina | 04-Test | SIT2 - Defect Fix - DC | MDG | DC | SI | Offshore | Cabasagan; Fretsie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053320 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Execute loads/ reports - DC | MDG | DC | SI | Offshore | Cabasagan; Fretsie | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053321 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute Loads/Reports - DC | MDG | DC | SI | Offshore | Cabasagan; Fretsie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-28 | 2016-11-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053322 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Execute pre validation - DC | MDG | DC | SI | Offshore | Cabasagan; Fretsie | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053323 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute pre validation - DC | MDG | DC | SI | Offshore | Cabasagan; Fretsie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053324 | No | Yes | No | Argentina | Argentina | 04-Test | M2 - Execute loads/reports - DC | MDG | DC | SI | Offshore | Cabasagan; Fretsie | Accenture | Yes | CapEx | Localization | IT - External | 75h | 0h | 75h | 2016-10-17 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053325 | No | Yes | No | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | SI | Offshore | Cabasagan; Fretsie | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-09-05 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053326 | No | Yes | No | Argentina | Argentina | 04-Test | Training Prep - DC | MDG | DC | SI | Offshore | Cabasagan; Fretsie | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053327 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Hypercare Support - DC | MDG | DC | SI | Offshore | Cabasagan; Fretsie | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053328 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 1 Load in QA - DC | MDG | DC | SI | Offshore | Cabasagan; Fretsie | Accenture | Yes | CapEx | Localization | IT - External | 400.5h | 0h | 400.5h | 2016-06-27 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053329 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - WP Obtain the Data Verification Signoff sheet - DC | MDG | DC | SI | Offshore | Cabasagan; Fretsie | Accenture | Yes | CapEx | Localization | IT - External | 22.5h | 0h | 22.5h | 2016-06-13 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053330 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 0 Load in DEV - DC | MDG | DC | SI | Offshore | Cabasagan; Fretsie | Accenture | Yes | CapEx | Localization | IT - External | 108h | 0h | 108h | 2016-05-30 | 2016-06-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053331 | No | No | Yes | Argentina | Argentina | 02-Analyze | Arg: PTP Update Execution Plans (Comm, training, transition) | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053332 | No | No | Yes | Argentina | Argentina | 02-Analyze | Arg: LOG Update Execution Plans (Comm, training, transition) | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053333 | No | No | Yes | Argentina | Argentina | 02-Analyze | Arg: RTR Update Execution Plans (Comm, training, transition) | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053334 | No | No | Yes | Argentina | Argentina | 02-Analyze | Arg: OTC Update Execution Plans (Comm, training, transition) | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053335 | No | No | Yes | Argentina | Argentina | 02-Analyze | Arg: PTM Update Execution Plans (Comm, training, transition) | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-05-30 | 2016-05-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053336 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Identify materials needing localization | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 10h | 0h | 10h | 2016-07-25 | 2016-07-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053337 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Assign ARG team resources | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 24h | 0h | 24h | 2016-07-25 | 2016-08-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053338 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Educate ARG resources on localization task | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 35h | 0h | 35h | 2016-08-29 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053339 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Build ARG localization tracker | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 16h | 0h | 16h | 2016-08-01 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053340 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Generate draft PTPs | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 113h | 0h | 113h | 2016-07-06 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053341 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Resolve deduplications | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053342 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Generate Preliminary PTPs | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 15h | 0h | 15h | 2016-08-01 | 2016-08-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053343 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Obtain approval | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053344 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Make adjustments | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053345 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Generate Final PTPs | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 41h | 0h | 41h | 2016-08-01 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053346 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Preliminary Training Schedule | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 68h | 0h | 68h | 2016-07-25 | 2016-08-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053347 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Deliver Training to End Users | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 177h | 0h | 177h | 2016-12-19 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 12 | 0 | 10 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053348 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Manage Training Logisitics | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 107h | 0h | 107h | 2016-12-19 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 15 | 27 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053349 | No | No | Yes | Argentina | Argentina | 04-Test | Training Schedule and Logistics | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 347h | 0h | 347h | 2016-09-12 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053350 | No | No | Yes | Argentina | Argentina | 04-Test | Deliver Training to UAT Testers | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 124h | 0h | 124h | 2016-10-11 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053351 | No | No | Yes | Argentina | Argentina | 04-Test | Execute Train the Trainer | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 25h | 0h | 25h | 2016-10-17 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053352 | No | No | Yes | Argentina | Argentina | 04-Test | Training Materials - Concept slides & Exercices book | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 153h | 0h | 153h | 2016-09-12 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053353 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Manage Training Logisitics | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 120h | 0h | 120h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053354 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Deliver Training to End Users | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053355 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-CM | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053356 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | CM | CM | Saputo | Onshore | Carmel; Sylvain | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053357 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | DEV | DEV | SI | Landed Onshore | Iyer; Jagdeesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053358 | No | No | Yes | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Landed Onshore | Iyer; Jagdeesh | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053359 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | SI | Landed Onshore | Iyer; Jagdeesh | IBM | Yes | OpEx | Localization | IT - External | 117h | 0h | 117h | 2017-03-07 | 2017-06-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 26 | 0 | 0 | 24 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053360 | No | No | Yes | Argentina | Argentina | 04-Test | Development | DEV | DEV | SI | Landed Onshore | Iyer; Jagdeesh | IBM | Yes | CapEx | Localization | IT - External | 157.7h | 0h | 157.7h | 2016-09-06 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053361 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Code, Tech spec. and FUT support | DEV | DEV | SI | Landed Onshore | Iyer; Jagdeesh | IBM | Yes | CapEx | Localization | IT - External | 89.73h | 0h | 89.73h | 2016-08-22 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053362 | No | No | Yes | Argentina | Argentina | 04-Test | GD and ARG - SIT2 Support - Cancelled | DEV | DEV | SI | Landed Onshore | Iyer; Jagdeesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053363 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Development (Cutover/Go-live) | DEV | DEV | SI | Landed Onshore | Iyer; Jagdeesh | IBM | Yes | CapEx | Localization | IT - External | 254.5h | 0h | 254.5h | 2016-12-05 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 19 | 30 | 22 | 30 | 20 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053364 | No | No | Yes | Argentina | Argentina | 06-Hypercare | ARG tax redesign- DEV | DEV | DEV | SI | Landed Onshore | Iyer; Jagdeesh | IBM | Yes | OpEx | Localization | IT - External | 0h | 20h | 20h | 2017-07-31 | 2017-09-22 | Yes |  |  |  | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053365 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Complete DEV & UT1 | DEV | DEV | SI | Landed Onshore | Iyer; Jagdeesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-09 | 2016-05-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053366 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Technical Specifications | DEV | DEV | SI | Landed Onshore | Iyer; Jagdeesh | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-05-09 | 2016-05-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053367 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Development (Hypercare) | DEV | DEV | SI | Landed Onshore | Iyer; Jagdeesh | IBM | Yes | OpEx | Localization | IT - External | 137h | 0h | 137h | 2017-02-06 | 2017-02-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053368 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, team organization) | DEV | DEV | SI | Landed Onshore | Iyer; Jagdeesh | IBM | Yes | CapEx | Localization | IT - External | 14h | 0h | 14h | 2016-09-26 | 2016-09-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053369 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - RTR | DEV | DEV | SI | Landed Onshore | Iyer; Jagdeesh | IBM | Yes | CapEx | Localization | IT - External | 53h | 0h | 53h | 2017-02-20 | 2017-03-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053370 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PMO | PMO | SI | Offshore | Bhide; Chaitanya | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053371 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053372 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | OpEx | Localization | IT - External | 44h | 0h | 44h | 2016-10-03 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053373 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Support | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-18 | 2016-07-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053374 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 81h | 0h | 81h | 2017-01-23 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053375 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Validate | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053376 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - LOG | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053377 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - LOG | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053378 | No | No | Yes | Argentina | Argentina | 02-Analyze | LOG - Identify changes in GD for Localization ARG | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2016-03-03 | 2016-04-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053379 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053380 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | OpEx | Localization | IT - External | 40h | 0h | 40h | 2016-10-07 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053381 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 73h | 0h | 73h | 2016-10-12 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053382 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 17.5h | 0h | 17.5h | 2016-11-07 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053383 | No | No | Yes | Argentina | Argentina | 04-Test | LOG - SIT 2 - Break/Fix | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 189h | 0h | 189h | 2016-10-31 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053384 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-15 | 2016-11-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053385 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-17 | 2016-10-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053386 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - Prep | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 31h | 0h | 31h | 2016-10-10 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053387 | No | No | Yes | Argentina | Argentina | 04-Test | LOG - SIT 2 - Run Tests | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 264h | 0h | 264h | 2016-10-24 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053388 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 35h | 0h | 35h | 2017-01-09 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 18.5 | 16.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053389 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-12-05 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053390 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 270.5h | 0h | 270.5h | 2016-12-19 | 2017-01-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 36 | 42.5 | 44 | 44 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053391 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053392 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 41h | 0h | 41h | 2016-12-19 | 2017-01-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 15 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053393 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | OpEx | Localization | IT - External | 108h | 0h | 108h | 2017-02-06 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053394 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Prepare | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-11 | 2016-07-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053395 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 218.5h | 0h | 218.5h | 2016-09-05 | 2016-10-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053396 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053397 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 98h | 0h | 98h | 2017-02-21 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053398 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-LOG | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | OpEx | Localization | IT - External | 505h | 0h | 505h | 2017-03-06 | 2017-06-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 45 | 44 | 44 | 27 | 0 | 0 | 18 | 33 | 33 | 33 | 0 | 33 | 33 | 33 | 33 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053399 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | PCR 212 Interim Daily Operational KPI’s report | LOG | FUN | SI | Onshore | Makovik; Victor | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053400 | No | Yes | No | Argentina | Argentina | 02-Analyze | RTR - Identify Changes in GD for Localization ARG | RTR | FUN | SI | Onshore | Cheng; Katrina | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2016-02-29 | 2016-03-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053401 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - RTR | RTR | FUN | SI | Onshore | Cheng; Katrina | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053402 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- RTR | RTR | FUN | SI | Onshore | Cheng; Katrina | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053403 | No | Yes | No | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | RTR | FUN | SI | Onshore | Cheng; Katrina | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-29 | 2016-11-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053404 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Prepare | RTR | FUN | SI | Onshore | Cheng; Katrina | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053405 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Solution Design Document (SDD) | RTR | FUN | SI | Onshore | Cheng; Katrina | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053406 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Configuration | RTR | FUN | SI | Onshore | Cheng; Katrina | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2016-08-17 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053407 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Support | RTR | FUN | SI | Onshore | Cheng; Katrina | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053408 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Validate | RTR | FUN | SI | Onshore | Cheng; Katrina | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053409 | No | Yes | No | Argentina | Argentina | 01-Preparation | RTR Prepare ArG- GD Integration | RTR | FUN | SI | Onshore | Cheng; Katrina | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-02-15 | 2016-02-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053410 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | RTR | FUN | SI | Onshore | Cheng; Katrina | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053411 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053412 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - OTC | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Localization | IT - External | 96h | 0h | 96h | 2017-01-23 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053413 | No | No | Yes | Argentina | Argentina | 02-Analyze | OTC - Identify Changes in GD for Localization ARG | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Localization | IT - External | 105.42h | 0h | 105.42h | 2016-02-29 | 2016-04-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053414 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- OTC | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Localization | IT - External | 59h | 0h | 59h | 2016-05-02 | 2016-07-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053415 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - OTC | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2016-05-02 | 2016-05-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053416 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053417 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | OpEx | Localization | IT - External | 180h | 0h | 180h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 44 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053418 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053419 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053420 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-28 | 2016-11-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053421 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Manage Defects | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2016-12-12 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053422 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Localization | IT - External | 175h | 0h | 175h | 2016-12-12 | 2017-01-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 35 | 44 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053423 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-01-16 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053424 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053425 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-17 | 2016-10-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053426 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053427 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053428 | No | No | Yes | Argentina | Argentina | 04-Test | OTC - SIT 2 - Break/Fix | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Localization | IT - External | 143h | 0h | 143h | 2016-10-24 | 2016-12-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053429 | No | No | Yes | Argentina | Argentina | 04-Test | OTC - SIT 2 - Manage Defects | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Localization | IT - External | 85h | 0h | 85h | 2016-10-24 | 2016-11-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053430 | No | No | Yes | Argentina | Argentina | 04-Test | OTC - SIT 2 - Run Tests | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Localization | IT - External | 112h | 0h | 112h | 2016-10-24 | 2016-11-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053431 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG KT visit | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-08-15 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053432 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - Prep | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-17 | 2016-10-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053433 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Localization | IT - External | 116h | 0h | 116h | 2016-08-29 | 2016-10-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053434 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Manage Defects | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Localization | IT - External | 116h | 0h | 116h | 2016-09-06 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053435 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | OTC | FUN | SI | Onshore | Monette; Katy | IBM | Yes | CapEx | Localization | IT - External | 96h | 0h | 96h | 2016-08-29 | 2016-10-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053436 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTM - Break/Fix | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 62h | 0h | 62h | 2016-10-24 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053437 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - Prep | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 35h | 0h | 35h | 2016-10-17 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053438 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053439 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTM - Run Tests | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 85h | 0h | 85h | 2016-11-07 | 2016-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053440 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053441 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-03 | 2016-10-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053442 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - PTM | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 42h | 0h | 42h | 2016-05-09 | 2016-06-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053443 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT - PTM | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 49h | 0h | 49h | 2016-06-27 | 2016-07-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053444 | No | No | Yes | Argentina | Argentina | 02-Analyze | PTM - Identfy Changes in GD for Localization ARG | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 105h | 0h | 105h | 2016-02-29 | 2016-04-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053445 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 100h | 0h | 100h | 2016-09-12 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053446 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053447 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Functional Specification (FSD) | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 42h | 0h | 42h | 2016-08-03 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053448 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053449 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-02-06 | 2017-02-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053450 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - PTM | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 68h | 0h | 68h | 2017-02-11 | 2017-02-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053451 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - PTM | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | OpEx | Localization | IT - External | 204h | 0h | 204h | 2017-02-06 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 20 | 44 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053452 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - PTM | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 81h | 0h | 81h | 2017-01-30 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053453 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-11-07 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053454 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053455 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053456 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 49h | 0h | 49h | 2016-12-05 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053457 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 56h | 0h | 56h | 2016-12-12 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053458 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 218h | 0h | 218h | 2016-12-19 | 2017-01-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 36 | 44 | 24 | 40 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053459 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTM | FUN | SI | Onshore | Jagadeeswaran; Rajesh | IBM | Yes | CapEx | Localization | IT - External | 54h | 0h | 54h | 2017-01-09 | 2017-01-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 20 | 5 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053460 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | CM | CM | SI | Onshore | Yowell; Jeff | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053461 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053462 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 13h | 0h | 13h | 2016-12-29 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 2 | 4 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053463 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - RTR | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | OpEx | Localization | IT - External | 4h | 0h | 4h | 2017-02-27 | 2017-03-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053464 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 9.5h | 0h | 9.5h | 2017-02-27 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053465 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - RTR | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 164.5h | 0h | 164.5h | 2017-02-06 | 2017-03-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43.5 | 44 | 40 | 7 | 28 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053466 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 3h | 0h | 3h | 2016-11-14 | 2016-12-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053467 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2016-11-07 | 2016-12-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053468 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-12-07 | 2016-12-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053469 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 138.5h | 0h | 138.5h | 2016-12-06 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 23 | 27 | 11 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053470 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | OpEx | Localization | IT - External | 6h | 0h | 6h | 2016-10-11 | 2016-11-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053471 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Break/Fix | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 29h | 0h | 29h | 2016-10-31 | 2016-11-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053472 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Manage Defects | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2016-11-07 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053473 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Run Tests | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2016-11-02 | 2016-11-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053474 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 43.5h | 0h | 43.5h | 2016-12-13 | 2017-01-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 7 | 15 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053475 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Validate | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | OpEx | Localization | IT - External | 2h | 0h | 2h | 2016-08-22 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053476 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Support | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053477 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Solution Design Document (SDD) | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-15 | 2016-08-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053478 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Prepare | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053479 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 3h | 0h | 3h | 2016-10-11 | 2016-10-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053480 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 7h | 0h | 7h | 2016-09-26 | 2016-10-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053481 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-10-03 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053482 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | OpEx | Localization | IT - External | 1h | 0h | 1h | 2016-10-11 | 2016-10-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053483 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - RTR - Prep | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 14h | 0h | 14h | 2016-10-13 | 2016-11-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053484 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 64h | 0h | 64h | 2016-09-12 | 2016-10-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053485 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 47h | 0h | 47h | 2016-09-12 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053486 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - RTR | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 119h | 0h | 119h | 2016-05-04 | 2016-08-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053487 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 14h | 0h | 14h | 2017-01-23 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053488 | No | No | Yes | Argentina | Argentina | 02-Analyze | RTR - Identify Changes in GD for Localization ARG | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 98h | 0h | 98h | 2016-03-02 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053489 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- RTR | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 145h | 0h | 145h | 2016-05-04 | 2016-07-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053490 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | RTR | FUN | SI | Onshore | Heap; Kaitlyn | IBM | Yes | CapEx | Localization | IT - External | 46h | 0h | 46h | 2017-01-30 | 2017-02-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053491 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | OTC | FUN | SI | Onshore | Kane; Jeremy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053492 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | OTC | FUN | SI | Onshore | Kane; Jeremy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-29 | 2016-08-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053493 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- OTC | OTC | FUN | SI | Onshore | Kane; Jeremy | IBM | Yes | CapEx | Localization | IT - External | 28.63h | 0h | 28.63h | 2016-05-02 | 2016-06-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053494 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - OTC | OTC | FUN | SI | Onshore | Kane; Jeremy | IBM | Yes | CapEx | Localization | IT - External | 58.67h | 0h | 58.67h | 2016-05-02 | 2016-07-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053495 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - Prep | OTC | FUN | SI | Onshore | Kane; Jeremy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-17 | 2016-10-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053496 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | OTC | FUN | SI | Onshore | Kane; Jeremy | IBM | Yes | CapEx | Localization | IT - External | 371.6h | 0h | 371.6h | 2016-09-05 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053497 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Solution Design Document (SDD) | OTC | FUN | SI | Onshore | Kane; Jeremy | IBM | Yes | CapEx | Localization | IT - External | 68h | 0h | 68h | 2016-08-22 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053498 | No | No | Yes | Argentina | Argentina | 04-Test | OTC - SIT 2 - Break/Fix | OTC | FUN | SI | Onshore | Kane; Jeremy | IBM | Yes | CapEx | Localization | IT - External | 253.5h | 0h | 253.5h | 2016-10-24 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053499 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG KT visit | OTC | FUN | SI | Onshore | Kane; Jeremy | IBM | Yes | CapEx | Localization | IT - External | 8.8h | 0h | 8.8h | 2016-08-15 | 2016-08-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053500 | No | No | Yes | Argentina | Argentina | 04-Test | Argentina 3 PL Testing | OTC | FUN | SI | Onshore | Kane; Jeremy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053501 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | OTC | FUN | SI | Onshore | Kane; Jeremy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053502 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | OTC | FUN | SI | Onshore | Kane; Jeremy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-28 | 2016-11-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053503 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | OTC | FUN | SI | Onshore | Kane; Jeremy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053504 | No | No | Yes | Argentina | Argentina | 04-Test | OTC - SIT 2 - Run Tests | OTC | FUN | SI | Onshore | Kane; Jeremy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053505 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | OTC | FUN | SI | Onshore | Kane; Jeremy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053506 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | OTC | FUN | SI | Onshore | Kane; Jeremy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053507 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | OTC | FUN | SI | Onshore | Kane; Jeremy | IBM | Yes | CapEx | Localization | IT - External | 230.4h | 0h | 230.4h | 2016-12-05 | 2017-01-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 36.4 | 47.4 | 49.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053508 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | OTC | FUN | SI | Onshore | Kane; Jeremy | IBM | Yes | CapEx | Localization | IT - External | 10.4h | 0h | 10.4h | 2017-02-06 | 2017-02-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053509 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | OTC | FUN | SI | Onshore | Kane; Jeremy | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053510 | No | No | Yes | Argentina | Argentina | 02-Analyze | OTC - Identify Changes in GD for Localization ARG | OTC | FUN | SI | Onshore | Kane; Jeremy | IBM | Yes | CapEx | Localization | IT - External | 108.52h | 0h | 108.52h | 2016-02-29 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053511 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - |  | Missing Stream | SI | Onshore | OLeary; Christopher | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053512 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PMO | PMO | Saputo | Onshore | Martin; Jeff | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053513 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PMO | PMO | PMO | Saputo | Onshore | Martin; Jeff | Saputo | Yes | OpEx | Localization | Business | 151h | 0h | 151h | 2017-03-20 | 2017-04-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 40 | 40 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053514 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | MDG | To Define | Saputo | Onshore | Teeples; Maja | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053515 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | MDG | To Define | SI | Offshore | Rudra; Sekhar | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053516 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | SEC | SEC | SI | Onshore | Tran; Menard | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053517 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | SEC | SEC | SI | Onshore | Tran; Menard | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053518 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT Defect Resolution | SEC | SEC | SI | Onshore | Tran; Menard | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053519 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 Defect Resolution | SEC | SEC | SI | Onshore | Tran; Menard | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-22 | 2016-10-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053520 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Hypercare/support | SEC | SEC | SI | Onshore | Tran; Menard | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-01 | 2017-02-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053521 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | GRC AC - UAT Execution | SEC | SEC | SI | Onshore | Tran; Menard | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053522 | No | Yes | No | Argentina | Argentina | 04-Test | FUT Support Roles | SEC | SEC | SI | Onshore | Tran; Menard | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-17 | 2016-10-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053523 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Support Role Build and UT | SEC | SEC | SI | Onshore | Tran; Menard | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-19 | 2016-09-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053524 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Support Role Design | SEC | SEC | SI | Onshore | Tran; Menard | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-29 | 2016-09-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053525 | No | Yes | No | Argentina | Argentina | 04-Test | Security Role FUT | SEC | SEC | SI | Onshore | Tran; Menard | Accenture | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2016-09-28 | 2016-09-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053526 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Derived Role Build | SEC | SEC | SI | Onshore | Tran; Menard | Accenture | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-09-26 | 2016-09-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053527 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Master Role Build and UT | SEC | SEC | SI | Onshore | Tran; Menard | Accenture | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2016-09-12 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053528 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Security Design Workshops | SEC | SEC | SI | Onshore | Tran; Menard | Accenture | Yes | CapEx | Localization | IT - External | 22h | 0h | 22h | 2016-09-19 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053529 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Security Approach | SEC | SEC | SI | Onshore | Tran; Menard | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-18 | 2016-09-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053530 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Security Role Design (Business Users) | SEC | SEC | SI | Onshore | Tran; Menard | Accenture | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2016-07-05 | 2016-07-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053531 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Composite Role Build | SEC | SEC | SI | Onshore | Tran; Menard | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-19 | 2016-09-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053532 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Composite Role Design | SEC | SEC | SI | Onshore | Tran; Menard | Accenture | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2016-09-20 | 2016-09-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053533 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 Defect Resolution | SEC | SEC | SI | Onshore | Tran; Menard | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-07 | 2016-09-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053534 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Security Role Build & Unit Test (Business Users) | SEC | SEC | SI | Onshore | Tran; Menard | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-06-20 | 2016-06-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053535 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Support SIT 1 & Defect Resolution | SEC | SEC | SI | Onshore | Tran; Menard | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-28 | 2016-07-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053536 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Security Profiles & Authorizations | SEC | SEC | SI | Onshore | Tran; Menard | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-06-13 | 2016-06-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053537 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SoD Analysis & Remediation - Role Level | SEC | SEC | SI | Onshore | Tran; Menard | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-04 | 2016-07-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053538 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SAP Security Detailed Design | SEC | SEC | SI | Onshore | Tran; Menard | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-23 | 2016-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053539 | No | No | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | CDP | CDP | SI | Onshore | George; Steven | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053540 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053541 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | OpEx | Localization | IT - External | 11h | 0h | 11h | 2016-10-03 | 2016-11-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053542 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTP | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | OpEx | Localization | IT - External | 9h | 0h | 9h | 2017-03-06 | 2017-04-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053543 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 68h | 0h | 68h | 2017-01-30 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053544 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 111.8h | 0h | 111.8h | 2016-10-03 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053545 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | OpEx | Localization | IT - External | 8h | 0h | 8h | 2016-09-22 | 2016-09-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053546 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 98h | 0h | 98h | 2017-01-09 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 54 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053547 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 53h | 0h | 53h | 2017-01-16 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053548 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053549 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | OpEx | Localization | IT - External | 88h | 0h | 88h | 2017-02-06 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053550 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-02-06 | 2017-02-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053551 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 133h | 0h | 133h | 2017-02-06 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 24 | 44 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053552 | No | No | Yes | Argentina | Argentina | 02-Analyze | PTP - Identify Changesin GD for Localization ARG | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-02-29 | 2016-02-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053553 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- PTP | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-05-16 | 2016-05-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053554 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - PTP | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 3h | 0h | 3h | 2016-05-24 | 2016-05-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053555 | No | No | Yes | Argentina | Argentina | 01-Preparation | PTP Prepare ArG - GD integration | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 26.4h | 0h | 26.4h | 2016-02-22 | 2016-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053556 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2016-11-11 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053557 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2016-09-06 | 2016-10-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053558 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Manage Defects | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 140h | 0h | 140h | 2016-09-06 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053559 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | CapEx | Localization | IT - External | 72h | 0h | 72h | 2016-09-08 | 2016-11-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053560 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Prepare | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-14 | 2016-08-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053561 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Support | PTP | FUN | SI | Onshore | Huot; Sylvain | IBM | Yes | OpEx | Localization | IT - External | 56h | 0h | 56h | 2016-08-09 | 2016-08-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053562 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Unit testing Development Documentation (FUT) | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-18 | 2016-07-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053563 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053564 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 192h | 0h | 192h | 2016-12-26 | 2017-02-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 44 | 60 | 44 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053565 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-29 | 2016-09-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053566 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 148h | 0h | 148h | 2016-12-19 | 2017-01-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 44 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053567 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - OTC | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053568 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - OTC Localisation workshops | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 91h | 0h | 91h | 2016-03-21 | 2016-04-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053569 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - OTC Complete PDDs | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 48h | 0h | 48h | 2016-03-21 | 2016-04-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053570 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - OTC Update RTM | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053571 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - OTC Localisation Output (Report, Interface, Enhancement, Form and Workflow list) | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053572 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - OTC | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 228h | 0h | 228h | 2016-05-02 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053573 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- OTC | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 292h | 0h | 292h | 2016-05-09 | 2016-08-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053574 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | OpEx | Localization | IT - External | 78h | 0h | 78h | 2017-02-20 | 2017-03-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053575 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 107h | 0h | 107h | 2017-02-06 | 2017-02-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053576 | No | Yes | No | Argentina | Argentina | 04-Test | OTC - SIT 2 - Break/Fix | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2016-11-21 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053577 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Support | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-17 | 2016-10-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053578 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG KT visit | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2016-08-15 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053579 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-OTC | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | OpEx | Localization | IT - External | 171h | 0h | 171h | 2017-03-06 | 2017-04-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 44 | 52 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053580 | No | Yes | No | Argentina | Argentina | 04-Test | OTC - SIT 2 - Run Tests | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053581 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - OTC Finalize BPML | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-25 | 2016-04-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053582 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - OTC Create Process documentation in BWL/BPM | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 70h | 0h | 70h | 2016-04-20 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053583 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - OTC Update Project Logs and BWL/BPM | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-04-18 | 2016-04-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053584 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - OTC Fit Gap workshops Notes | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2016-04-18 | 2016-04-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053585 | No | Yes | No | Argentina | Argentina | 02-Analyze | ArG - OTC Fit Gap workshops decks | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2016-04-11 | 2016-04-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053586 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Unit testing Development Documentation (FUT) | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-18 | 2016-07-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053587 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Functional Specification (FSD) | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-07-18 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053588 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Configuration | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2016-09-02 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053589 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-29 | 2016-08-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053590 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - Prep | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-17 | 2016-10-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053591 | No | Yes | No | Argentina | Argentina | 01-Preparation | ArG Prepare Localisation WS | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-02-15 | 2016-02-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053592 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Data Management | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-10 | 2016-05-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053593 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Training workshops | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-12 | 2016-05-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053594 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Operational Procedures | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-05-16 | 2016-05-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053595 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - CR | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-10 | 2016-05-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053596 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Solution Design Document (SDD) | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2016-05-23 | 2016-06-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053597 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Non Functional | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-09 | 2016-05-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053598 | No | Yes | No | Argentina | Argentina | 01-Preparation | ArG GD Integrated sessions | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-02-22 | 2016-02-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053599 | No | Yes | No | Argentina | Argentina | 01-Preparation | ArG Global Process Overview | OTC | FUN | SI | Onshore | Rodriguez; Gimena | IBM | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-02-29 | 2016-03-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053600 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PMO | PMO | SI | Onshore | Aflalo; Michael | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053601 | No | No | Yes | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PMO | PMO | SI | Onshore | Kreuzer; Winfried | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053602 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053603 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Run Tests | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2016-10-25 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053604 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Manage Defects | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2016-10-24 | 2016-12-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053605 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Break/Fix | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | CapEx | Localization | IT - External | 52h | 0h | 52h | 2016-10-25 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053606 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | CapEx | Localization | IT - External | 58h | 0h | 58h | 2016-12-19 | 2017-01-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 25 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053607 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | CapEx | Localization | IT - External | 19h | 0h | 19h | 2016-11-10 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053608 | No | Yes | No | Argentina | Argentina | 04-Test | Updates concepts decks | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053609 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Validate | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | CapEx | Localization | IT - External | 17h | 0h | 17h | 2016-11-14 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053610 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | CapEx | Localization | IT - External | 37h | 0h | 37h | 2016-11-14 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053611 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Manage Defects | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053612 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support - RTR | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-02 | 2017-01-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053613 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - RTR | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053614 | No | Yes | No | Argentina | Argentina | 01-Preparation | RTR Prepare ArG- GD Integration | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-02-15 | 2016-02-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053615 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | CapEx | Localization | IT - External | 67h | 0h | 67h | 2016-12-19 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 5 | 10 | 3 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053616 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Validate | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2016-12-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053617 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2016-12-12 | 2016-12-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053618 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | CapEx | Localization | IT - External | 99h | 0h | 99h | 2016-12-05 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 7 | 27 | 22 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053619 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | CapEx | Localization | IT - External | 29h | 0h | 29h | 2016-09-05 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053620 | No | Yes | No | Argentina | Argentina | 02-Analyze | RTR - Identify Changes in GD for Localization ARG | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | CapEx | Localization | IT - External | 108.9h | 0h | 108.9h | 2016-02-29 | 2016-04-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053621 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | CapEx | Localization | IT - External | 46h | 0h | 46h | 2016-12-19 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 4 | 5 | 9 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053622 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - RTR | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | CapEx | Localization | IT - External | 93h | 0h | 93h | 2016-05-02 | 2016-07-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053623 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- RTR | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | CapEx | Localization | IT - External | 35h | 0h | 35h | 2016-05-02 | 2016-05-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053624 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | CapEx | Localization | IT - External | 111h | 0h | 111h | 2016-09-06 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053625 | No | Yes | No | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-09-06 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053626 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Prep | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | CapEx | Localization | IT - External | 37h | 0h | 37h | 2016-10-11 | 2016-11-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053627 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Validate | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | OpEx | Localization | IT - External | 1h | 0h | 1h | 2016-10-11 | 2016-11-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053628 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Prepare | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2016-09-12 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053629 | No | Yes | No | Argentina | Argentina | 04-Test | Mock2 - Support | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | CapEx | Localization | IT - External | 17h | 0h | 17h | 2016-09-26 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053630 | No | Yes | No | Argentina | Argentina | 04-Test | Prep PRD for performance testing | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053631 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Prepare | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | OpEx | Localization | IT - External | 20h | 0h | 20h | 2016-08-08 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053632 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Solution Design Document (SDD) | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2016-08-15 | 2016-08-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053633 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Configuration | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | CapEx | Localization | IT - External | 48.53h | 0h | 48.53h | 2016-08-08 | 2016-10-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053634 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Support | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | OpEx | Localization | IT - External | 9h | 0h | 9h | 2016-09-06 | 2016-09-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053635 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Unit testing Configuration Documentation | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2016-08-22 | 2016-08-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053636 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Validate | RTR | FUN | SI | Onshore | Morin; Nadia | IBM | Yes | OpEx | Localization | IT - External | 14h | 0h | 14h | 2016-08-22 | 2016-09-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053637 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Support | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | OpEx | Localization | IT - External | 91h | 0h | 91h | 2016-08-08 | 2016-08-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053638 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Validate | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | OpEx | Localization | IT - External | 6h | 0h | 6h | 2016-08-16 | 2016-08-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053639 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Data collection templates (DCT) - Explain and collect | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-14 | 2016-08-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053640 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 223.5h | 0h | 223.5h | 2016-09-12 | 2016-12-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053641 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-11 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053642 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Prepare | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 22h | 0h | 22h | 2016-11-10 | 2016-12-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053643 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Support | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 38h | 0h | 38h | 2016-12-05 | 2016-12-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053644 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-02-07 | 2017-02-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053645 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | OpEx | Localization | IT - External | 54h | 0h | 54h | 2017-02-06 | 2017-02-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053646 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 127h | 0h | 127h | 2016-12-20 | 2017-01-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 45 | 0 | 14 | 10 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053647 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Prepare | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2016-12-13 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053648 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 115h | 0h | 115h | 2016-12-20 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 45 | 31 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053649 | No | No | Yes | Argentina | Argentina | 04-Test | Updates concepts decks | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-03 | 2016-10-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053650 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | OpEx | Localization | IT - External | 56h | 0h | 56h | 2016-09-19 | 2016-10-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053651 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | OpEx | Localization | IT - External | 119h | 0h | 119h | 2016-10-18 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053652 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Validate | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | OpEx | Localization | IT - External | 2h | 0h | 2h | 2016-11-09 | 2016-11-17 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053653 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - PTP | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 13.35h | 0h | 13.35h | 2016-05-02 | 2016-05-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053654 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- PTP | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2016-05-04 | 2016-05-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053655 | No | No | Yes | Argentina | Argentina | 02-Analyze | PTP - Identify Changesin GD for Localization ARG | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | CapEx | Localization | IT - External | 26.6h | 0h | 26.6h | 2016-02-29 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053656 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | SI | Offshore | Keshari; Vinita | IBM | Yes | OpEx | Localization | IT - External | 54h | 0h | 54h | 2017-04-04 | 2017-05-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053657 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | SI | Offshore | Samant; Rupa | IBM | Yes | OpEx | Localization | IT - External | 220h | 0h | 220h | 2017-03-06 | 2017-07-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 21 | 30 | 45 | 45 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053658 | No | No | Yes | Argentina | Argentina | 02-Analyze | PTP - Identify Changesin GD for Localization ARG | PTM | FUN | SI | Offshore | Samant; Rupa | IBM | Yes | CapEx | Localization | IT - External | 54.1h | 0h | 54.1h | 2016-02-29 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053659 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- PTP | PTM | FUN | SI | Offshore | Samant; Rupa | IBM | Yes | CapEx | Localization | IT - External | 7.75h | 0h | 7.75h | 2016-05-02 | 2016-06-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053660 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - PTP | PTM | FUN | SI | Offshore | Samant; Rupa | IBM | Yes | CapEx | Localization | IT - External | 13.25h | 0h | 13.25h | 2016-05-02 | 2016-06-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053661 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - PTP - Break/Fix | PTM | FUN | SI | Offshore | Samant; Rupa | IBM | Yes | CapEx | Localization | IT - External | 42h | 0h | 42h | 2016-11-14 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053662 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | PTM | FUN | SI | Offshore | Samant; Rupa | IBM | Yes | CapEx | Localization | IT - External | 87h | 0h | 87h | 2017-01-09 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 15 | 40 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053663 | No | No | Yes | Argentina | Argentina | 06-Hypercare | CR321-Modify EPTP026 Report | PTM | FUN | SI | Offshore | Samant; Rupa | IBM | Yes | OpEx | Global | IT - External | 20h | 0h | 20h | 2017-06-19 | 2017-07-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053664 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | PTM | FUN | SI | Offshore | Samant; Rupa | IBM | Yes | CapEx | Localization | IT - External | 87h | 0h | 87h | 2016-12-12 | 2017-01-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 25 | 20 | 30 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053665 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | PTM | FUN | SI | Offshore | Samant; Rupa | IBM | Yes | CapEx | Localization | IT - External | 187h | 0h | 187h | 2017-02-06 | 2017-03-10 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 24 | 55 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053666 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 2 - Prep | PTM | FUN | SI | Offshore | Samant; Rupa | IBM | Yes | CapEx | Localization | IT - External | 73h | 0h | 73h | 2016-10-10 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053667 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | PTM | FUN | SI | Offshore | Samant; Rupa | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-09-12 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053668 | No | No | Yes | Argentina | Argentina | 04-Test | Prep PRD for performance testing | OTC | FUN | SI | Offshore | Pradhan; Gyan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-21 | 2016-11-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053669 | No | No | Yes | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | OTC | FUN | SI | Offshore | Pradhan; Gyan | IBM | Yes | CapEx | Localization | IT - External | 70h | 0h | 70h | 2016-09-12 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053670 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG KT visit | OTC | FUN | SI | Offshore | Pradhan; Gyan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-08 | 2016-08-08 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053671 | No | No | Yes | Argentina | Argentina | 04-Test | Mock1 - Support | OTC | FUN | SI | Offshore | Pradhan; Gyan | IBM | Yes | OpEx | Localization | IT - External | 5h | 0h | 5h | 2016-08-08 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053672 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Prepare | OTC | FUN | SI | Offshore | Pradhan; Gyan | IBM | Yes | OpEx | Localization | IT - External | 10h | 0h | 10h | 2016-09-12 | 2016-09-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053673 | No | No | Yes | Argentina | Argentina | 02-Analyze | OTC - Identify Changes in GD for Localization ARG | OTC | FUN | SI | Offshore | Pradhan; Gyan | IBM | Yes | CapEx | Localization | IT - External | 104h | 0h | 104h | 2016-03-02 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053674 | No | No | Yes | Argentina | Argentina | 04-Test | Mock2 - Support | OTC | FUN | SI | Offshore | Pradhan; Gyan | IBM | Yes | OpEx | Localization | IT - External | 4h | 0h | 4h | 2016-10-17 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053675 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | OTC | FUN | SI | Offshore | Pradhan; Gyan | IBM | Yes | CapEx | Localization | IT - External | 31h | 0h | 31h | 2016-12-05 | 2016-12-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053676 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | OTC | FUN | SI | Offshore | Pradhan; Gyan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053677 | No | No | Yes | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | OTC | FUN | SI | Offshore | Pradhan; Gyan | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053678 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- OTC | OTC | FUN | SI | Offshore | Pradhan; Gyan | IBM | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2016-05-02 | 2016-06-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053679 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - OTC | OTC | FUN | SI | Offshore | Pradhan; Gyan | IBM | Yes | CapEx | Localization | IT - External | 34h | 0h | 34h | 2016-05-02 | 2016-05-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053680 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix - RTR | RTR | FUN | SI | Offshore | Deshpande; Anuprita | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053681 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | RTR | FUN | SI | Offshore | Deshpande; Anuprita | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053682 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - RTR - Break/Fix | RTR | FUN | SI | Offshore | Deshpande; Anuprita | IBM | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2016-11-28 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053683 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Interim reporting (400hours) | RTR | FUN | SI | Offshore | Deshpande; Anuprita | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053684 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | RTR | FUN | SI | Offshore | Deshpande; Anuprita | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-06 | 2016-09-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053685 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | RTR | FUN | SI | Offshore | Deshpande; Anuprita | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-10-03 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053686 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Break/Fix | LOG | FUN | SI | Onshore | Mahoney; Stephen | IBM | Yes | CapEx | Localization | IT - External | 136h | 0h | 136h | 2016-09-12 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053687 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | SI | Onshore | Mahoney; Stephen | IBM | Yes | CapEx | Localization | IT - External | 58h | 0h | 58h | 2017-01-16 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053688 | No | Yes | No | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - LOG | LOG | FUN | SI | Onshore | Mahoney; Stephen | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053689 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-LOG | LOG | FUN | SI | Onshore | Mahoney; Stephen | IBM | Yes | OpEx | Localization | IT - External | 371h | 0h | 371h | 2017-03-13 | 2017-05-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 34 | 29 | 0 | 17 | 44 | 42 | 38 | 44 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053690 | No | Yes | No | Argentina | Argentina | 02-Analyze | LOG - Identify changes in GD for Localization ARG | LOG | FUN | SI | Onshore | Mahoney; Stephen | IBM | Yes | CapEx | Localization | IT - External | 85h | 0h | 85h | 2016-02-29 | 2016-04-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053691 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Run Tests | LOG | FUN | SI | Onshore | Mahoney; Stephen | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053692 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | Cut Over - Support | LOG | FUN | SI | Onshore | Mahoney; Stephen | IBM | Yes | CapEx | Localization | IT - External | 192h | 0h | 192h | 2017-01-02 | 2017-01-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 49 | 44 | 48 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053693 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Break/Fix | LOG | FUN | SI | Onshore | Mahoney; Stephen | IBM | Yes | CapEx | Localization | IT - External | 83h | 0h | 83h | 2017-02-13 | 2017-02-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053694 | No | Yes | No | Argentina | Argentina | 03-Design/Build | Unit testing Configuration Documentation | LOG | FUN | SI | Onshore | Mahoney; Stephen | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-08-22 | 2016-08-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053695 | No | Yes | No | Argentina | Argentina | 04-Test | Mock1 - Support | LOG | FUN | SI | Onshore | Mahoney; Stephen | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-07-15 | 2016-07-15 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053696 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 1 - Run Tests | LOG | FUN | SI | Onshore | Mahoney; Stephen | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2016-09-19 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053697 | No | Yes | No | Argentina | Argentina | 06-Hypercare | HC - Provide end User Support | LOG | FUN | SI | Onshore | Mahoney; Stephen | IBM | Yes | OpEx | Localization | IT - External | 77h | 0h | 77h | 2017-02-06 | 2017-02-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053698 | No | Yes | No | Argentina | Argentina | 05-Cutover/Go-live | UAT - Break/Fix and document work around | LOG | FUN | SI | Onshore | Mahoney; Stephen | IBM | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2016-12-19 | 2016-12-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053699 | No | Yes | No | Argentina | Argentina | 04-Test | LOG - SIT 2 - Run Tests | LOG | FUN | SI | Onshore | Mahoney; Stephen | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-11-03 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053700 | No | Yes | No | Argentina | Argentina | 04-Test | SIT 2 - Prep | LOG | FUN | SI | Onshore | Mahoney; Stephen | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2016-10-11 | 2016-10-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053701 | No | Yes | No | Argentina | Argentina | 04-Test | LOG - SIT 2 - Break/Fix | LOG | FUN | SI | Onshore | Mahoney; Stephen | IBM | Yes | CapEx | Localization | IT - External | 366h | 0h | 366h | 2016-10-31 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053702 | No | No | No | Argentina | Argentina | 05-Cutover/Go-live | Transition to Hypercare - LOG | LOG | FUN | Saputo | Onshore | Singh; Ben | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-12-28 | 2016-12-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053703 | No | Yes | No | Argentina | Argentina | 01-Preparation | Argentina Project - Sharepoint Access - | PMO | PMO | Saputo | Onshore | Patrick; Lara | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2015-12-01 | 2015-12-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053704 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 365h | 0h | 365h | 2016-09-06 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053705 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-MDG-DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053706 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute pre validation - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | OpEx | Localization | IT - Internal | 7h | 0h | 7h | 2016-12-19 | 2016-12-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053707 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover 3 PL - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | OpEx | Localization | IT - Internal | 33h | 0h | 33h | 2016-12-22 | 2017-01-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 6 | 2 | 8 | 6 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053708 | No | No | Yes | Argentina | Argentina | 04-Test | Argentina 3 PL Testing - DC | MDG | DC | Saputo | Onshore | Kreps; Kevin | Saputo | Yes | CapEx | Localization | IT - Internal | 5h | 0h | 5h | 2016-10-31 | 2016-11-18 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053709 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT Prep - DC | MDG | DC | SI | Landed Onshore | Aying; Mae | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053710 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover - DC | MDG | DC | SI | Landed Onshore | Aying; Mae | Accenture | Yes | OpEx | Localization | IT - External | 40h | 0h | 40h | 2016-12-19 | 2016-12-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053711 | No | No | Yes | Argentina | Argentina | 04-Test | SIT2 - Defect Fix - DC | MDG | DC | SI | Landed Onshore | Aying; Mae | Accenture | Yes | CapEx | Localization | IT - External | 98h | 0h | 98h | 2016-11-07 | 2016-11-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053712 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Data verification Signoff sheets - DC | MDG | DC | SI | Landed Onshore | Aying; Mae | Accenture | Yes | CapEx | Localization | IT - External | 57h | 0h | 57h | 2016-12-07 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053713 | No | No | Yes | Argentina | Argentina | 04-Test | M1 - Execute loads - DC | MDG | DC | SI | Landed Onshore | Aying; Mae | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053714 | No | No | Yes | Argentina | Argentina | 04-Test | M1 - Execute pre validation - DC | MDG | DC | SI | Landed Onshore | Aying; Mae | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-11 | 2016-09-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053715 | No | No | Yes | Argentina | Argentina | 04-Test | SIT1 - Defect Fix - DC | MDG | DC | SI | Landed Onshore | Aying; Mae | Accenture | Yes | CapEx | Localization | IT - External | 152h | 0h | 152h | 2016-09-12 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053716 | No | No | Yes | Argentina | Argentina | 04-Test | M2 - Execute pre validation - DC | MDG | DC | SI | Landed Onshore | Aying; Mae | Accenture | Yes | CapEx | Localization | IT - External | 38h | 0h | 38h | 2016-10-10 | 2016-10-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053717 | No | No | Yes | Argentina | Argentina | 04-Test | M2 - Execute loads/reports - DC | MDG | DC | SI | Landed Onshore | Aying; Mae | Accenture | Yes | CapEx | Localization | IT - External | 53h | 0h | 53h | 2016-10-17 | 2016-10-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053718 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute pre validation - DC | MDG | DC | SI | Landed Onshore | Aying; Mae | Accenture | Yes | CapEx | Localization | IT - External | 98h | 0h | 98h | 2016-11-21 | 2016-12-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053719 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute pre validation - DC | MDG | DC | SI | Landed Onshore | Aying; Mae | Accenture | Yes | OpEx | Localization | IT - External | 60h | 0h | 60h | 2016-12-20 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 32 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053720 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute Loads/Reports - DC | MDG | DC | SI | Landed Onshore | Aying; Mae | Accenture | Yes | CapEx | Localization | IT - External | 53h | 0h | 53h | 2016-11-28 | 2016-12-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053721 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute loads/ reports - DC | MDG | DC | SI | Landed Onshore | Aying; Mae | Accenture | Yes | OpEx | Localization | IT - External | 110h | 0h | 110h | 2016-12-14 | 2017-01-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 32 | 24 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053722 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | SI | Landed Onshore | Aying; Mae | Accenture | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2016-09-05 | 2016-09-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053723 | No | No | Yes | Argentina | Argentina | 04-Test | Training Prep - DC | MDG | DC | SI | Landed Onshore | Aying; Mae | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053724 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Hypercare Support - DC | MDG | DC | SI | Landed Onshore | Aying; Mae | Accenture | Yes | OpEx | Localization | IT - External | 16h | 0h | 16h | 2017-02-06 | 2017-02-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053725 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - MDG 333 Mock Closure Memo - DC | MDG | DC | SI | Landed Onshore | Aying; Mae | Accenture | Yes | CapEx | Localization | IT - External | 125h | 0h | 125h | 2016-07-18 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053726 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 1 Load in QA - DC | MDG | DC | SI | Landed Onshore | Aying; Mae | Accenture | Yes | CapEx | Localization | IT - External | 288h | 0h | 288h | 2016-06-27 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053727 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 0 Load in DEV - DC | MDG | DC | SI | Landed Onshore | Aying; Mae | Accenture | Yes | CapEx | Localization | IT - External | 120h | 0h | 120h | 2016-05-30 | 2016-06-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053728 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 0 Load in DEV - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 102h | 0h | 102h | 2016-05-30 | 2016-06-24 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053729 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 1 Load in QA - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 463h | 0h | 463h | 2016-06-27 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053730 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Hypercare Support - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053731 | No | No | Yes | Argentina | Argentina | 04-Test | Training Prep - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053732 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2016-09-05 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053733 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute loads/ reports - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | OpEx | Localization | IT - External | 40.5h | 0h | 40.5h | 2016-12-12 | 2017-01-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053734 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute Loads/Reports - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2016-11-28 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053735 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute pre validation - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | OpEx | Localization | IT - External | 41.5h | 0h | 41.5h | 2016-12-12 | 2016-12-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053736 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute pre validation - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 72.5h | 0h | 72.5h | 2016-11-07 | 2016-11-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053737 | No | No | Yes | Argentina | Argentina | 04-Test | M2 - Execute loads/reports - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 58.5h | 0h | 58.5h | 2016-10-14 | 2016-11-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053738 | No | No | Yes | Argentina | Argentina | 04-Test | M2 - Execute pre validation - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 7h | 0h | 7h | 2016-10-10 | 2016-10-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053739 | No | No | Yes | Argentina | Argentina | 04-Test | SIT1 - Defect Fix - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 119.5h | 0h | 119.5h | 2016-09-12 | 2016-10-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053740 | No | No | Yes | Argentina | Argentina | 04-Test | M1 - Execute pre validation - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-11 | 2016-09-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053741 | No | No | Yes | Argentina | Argentina | 04-Test | M1 - Execute loads - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053742 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Data verification Signoff sheets - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-11-29 | 2016-12-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053743 | No | No | Yes | Argentina | Argentina | 04-Test | SIT2 - Defect Fix - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 49h | 0h | 49h | 2016-10-24 | 2016-11-25 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053744 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | OpEx | Localization | IT - External | 171.5h | 0h | 171.5h | 2016-12-19 | 2017-02-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 13.5 | 18 | 9 | 45 | 41 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053745 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT Prep - DC | MDG | DC | SI | Offshore | Balatbat; Randell | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053746 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | UAT Prep - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053747 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute Cutover - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | OpEx | Localization | IT - External | 163h | 0h | 163h | 2016-12-19 | 2017-02-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053748 | No | No | Yes | Argentina | Argentina | 04-Test | SIT2 - Defect Fix - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2016-11-02 | 2016-11-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053749 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Data verification Signoff sheets - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-29 | 2016-11-29 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053750 | No | No | Yes | Argentina | Argentina | 04-Test | M1 - Execute pre validation - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-11 | 2016-09-11 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053751 | No | No | Yes | Argentina | Argentina | 04-Test | M1 - Execute loads - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-05 | 2016-09-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053752 | No | No | Yes | Argentina | Argentina | 04-Test | SIT1 - Defect Fix - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 199h | 0h | 199h | 2016-09-13 | 2016-10-07 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053753 | No | No | Yes | Argentina | Argentina | 04-Test | M2 - Execute pre validation - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 54h | 0h | 54h | 2016-10-10 | 2016-10-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053754 | No | No | Yes | Argentina | Argentina | 04-Test | M2 - Execute loads/reports - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 120h | 0h | 120h | 2016-10-17 | 2016-10-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053755 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute Loads/Reports - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 71h | 0h | 71h | 2016-11-28 | 2016-12-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053756 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute pre validation - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | OpEx | Localization | IT - External | 115h | 0h | 115h | 2016-12-12 | 2017-01-13 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053757 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Dry Run - Execute pre validation - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 119h | 0h | 119h | 2016-11-07 | 2016-11-21 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053758 | No | No | Yes | Argentina | Argentina | 05-Cutover/Go-live | Execute loads/ reports - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | OpEx | Localization | IT - External | 108h | 0h | 108h | 2016-12-27 | 2017-01-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 18 | 45 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053759 | No | No | Yes | Argentina | Argentina | 04-Test | TEST - Master Data Migration and Governance (Gen) - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2016-09-05 | 2016-09-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053760 | No | No | Yes | Argentina | Argentina | 04-Test | Training Prep - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053761 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Hypercare Support - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | OpEx | Localization | IT - External | 55h | 0h | 55h | 2017-02-06 | 2017-02-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.5 | 17 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053762 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 1 Load in QA - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 466h | 0h | 466h | 2016-06-27 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053763 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Conduct Mock 0 Load in DEV - DC | MDG | DC | SI | Offshore | Jara; Marious | Accenture | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2016-06-15 | 2016-06-16 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053764 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - SDD - OTC | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 19.28h | 0h | 19.28h | 2016-06-21 | 2016-07-22 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053765 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG : DB - Functional Specifications and UT- OTC | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-05-02 | 2016-05-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053766 | No | No | Yes | Argentina | Argentina | 02-Analyze | OTC - Identify Changes in GD for Localization ARG | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 71.17h | 0h | 71.17h | 2016-02-29 | 2016-04-01 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053767 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Solution Design Document (SDD) | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 25.35h | 0h | 25.35h | 2016-08-15 | 2016-09-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053768 | No | No | Yes | Argentina | Argentina | 03-Design/Build | ARG KT visit | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-08-08 | 2016-08-12 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053769 | No | No | Yes | Argentina | Argentina | 04-Test | Management (Planning, reporting, CR, cross stream integration) | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 250h | 0h | 250h | 2016-09-06 | 2016-12-02 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053770 | No | No | Yes | Argentina | Argentina | 03-Design/Build | Unit testing Development Documentation (FUT) | OTC | FUN | SI | Onshore | Rayala; Sudheer | SAP | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-07-18 | 2016-08-05 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053771 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-MDG-DC | MDG | DC | SI | Offshore | Jumamil; Jeff | Accenture | Yes | OpEx | Localization | IT - External | 182h | 0h | 182h | 2017-04-03 | 2017-05-31 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 18 | 45 | 45 | 7 | 9 | 7 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053772 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PMO | PMO | PMO | SI | Offshore | Chandraprakash; Kadam | IBM | Yes | OpEx | Localization | IT - External | 630h | 0h | 630h | 2017-03-06 | 2017-06-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 36 | 45 | 45 | 45 | 45 | 36 | 45 | 45 | 45 | 45 | 45 | 18 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053773 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | SI | Offshore | Singh; Kamna | IBM | Yes | OpEx | Localization | IT - External | 69h | 0h | 69h | 2017-04-12 | 2017-05-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053774 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | SI | Offshore | Kadam; Sandeep | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053775 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | Saputo | Onshore | Soni; Shailendra | Saputo | Yes | OpEx | Localization | IT - Internal | 455h | 0h | 455h | 2017-03-27 | 2017-08-04 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 32 | 26 | 32 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053776 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PMO | PMO | PMO | Saputo | Onshore | Vanourek; Dora | Saputo | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053777 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-RTR | RTR | FUN | SI | Offshore | Radhika; Palivela | IBM | Yes | OpEx | Localization | IT - External | 328.5h | 0h | 328.5h | 2017-03-20 | 2017-06-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 18 | 22.5 | 22.5 | 22.5 | 22.5 | 18 | 22.5 | 22.5 | 22.5 | 22.5 | 22.5 | 22.5 | 22.5 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053778 | No | Yes | No | Argentina | Argentina | 06-Hypercare | ARG tax redesign- RTR | RTR | FUN | SI | Onshore | Nathan; Ram | IBM | Yes | OpEx | Localization | IT - External | 378h | 0h | 378h | 2017-05-30 | 2017-07-28 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 44 | 44 | 44 | 44 | 35 | 44 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053779 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-RTR | RTR | FUN | SI | Onshore | Nathan; Ram | IBM | Yes | OpEx | Localization | IT - External | 345h | 0h | 345h | 2017-04-03 | 2017-05-26 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 44 | 44 | 45 | 45 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053780 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-RTR | RTR | FUN | SI | Offshore | Chaturvedi; Himanshu | IBM | Yes | OpEx | Localization | IT - External | 594h | 0h | 594h | 2017-03-09 | 2017-06-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 36 | 45 | 36 | 45 | 45 | 36 | 45 | 45 | 45 | 45 | 45 | 45 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053781 | No | No | Yes | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Dvn; Satya | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053782 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-CM | CM | CM | SI | Onshore | Brown; Genevieve | Other | Yes | OpEx | Localization | IT - External | 1h | 0h | 1h | 2017-04-19 | 2017-04-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053783 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-LOG | LOG | FUN | SI | Offshore | Kumar; Arun | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053784 | No | Yes | No | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Udekar; Vinay | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053785 | No | No | Yes | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Dhanik; Piyush | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053786 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | Dhanik; Piyush | IBM | Yes | OpEx | Localization | IT - External | 47.8h | 0h | 47.8h | 2017-02-27 | 2017-06-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.8 | 8 | 0 | 0 | 0 | 0 | 4 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053787 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | Nandy; Debanjali | IBM | Yes | OpEx | Localization | IT - External | 49h | 0h | 49h | 2017-02-27 | 2017-05-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053788 | No | Yes | No | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Nandy; Debanjali | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053789 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-OTC | OTC | FUN | SI | Offshore | Gattani; Praveen | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053790 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | SI | Offshore | Patil; Pralhad | IBM | Yes | OpEx | Localization | IT - External | 234h | 0h | 234h | 2017-03-20 | 2017-06-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 14.4 | 14.4 | 18 | 18 | 14.4 | 10.8 | 18 | 18 | 14.4 | 18 | 18 | 18 | 7.2 | 14.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053791 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | SI | Offshore | Chougule; Vinay | IBM | Yes | OpEx | Localization | IT - External | 459.5h | 0h | 459.5h | 2017-03-20 | 2017-06-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.25 | 27 | 33.75 | 27 | 33.75 | 33.75 | 27 | 33.75 | 33.75 | 33.75 | 33.75 | 34 | 27 | 34 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053792 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTP | PTM | FUN | SI | Offshore | Chougule; Vinay | IBM | Yes | OpEx | Localization | IT - External | 152.5h | 0h | 152.5h | 2017-03-06 | 2017-06-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.75 | 9 | 11.25 | 9 | 11.25 | 11.25 | 9 | 11.25 | 11.25 | 11.25 | 11.25 | 11 | 9 | 11 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053793 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | SI | Offshore | Shukla; Anant | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053794 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-BI | BI | BI | SI | Offshore | Cingu; Praveen | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053795 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PMO | PMO | PMO | SI | Onshore | Singh; Swati | IBM | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053796 | No | No | Yes | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Onshore | Villacorta; Junne | Accenture | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053797 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-PTM | PTM | FUN | SI | Offshore | Gaikwad; Pradeep | IBM | Yes | OpEx | Localization | IT - External | 45h | 0h | 45h | 2017-04-12 | 2017-05-19 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053798 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-RTR | RTR | FUN | SI | Offshore | Kumar; Sameer | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-09 | 2017-03-09 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053799 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-DEV | DEV | DEV | SI | Offshore | Singh; Vipul | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053800 | No | No | Yes | Argentina | Argentina |  | Knowledge_Transfer_AMS - DEV | DEV | DEV | SI | Offshore | Singh; Vipul | IBM | Yes | OpEx | Global | IT - External | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053801 | No | Yes | No | Argentina | Argentina | 06-Hypercare | Argentina Production Support-SEC | SEC | SEC | SI | Onshore | Gill; Anand | Accenture | Yes | OpEx | Localization | IT - External | 68.5h | 0h | 68.5h | 2017-04-24 | 2017-06-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2.5 | 5 | 2 | 0 | 10 | 5 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053802 | No | No | Yes | Argentina | Argentina | 06-Hypercare | DMS Argentina Production Support- RTR | RTR | FUN | Saputo | Onshore | Lee; Jihoon | Saputo | Yes | OpEx | Localization | IT - Internal | 116h | 0h | 116h | 2017-06-26 | 2017-07-14 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053803 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-LOG | LOG | FUN | SI | Offshore | Dhyani; Subhash | IBM | Yes | OpEx | Localization | IT - External | 612h | 0h | 612h | 2017-03-20 | 2017-06-30 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 36 | 45 | 45 | 36 | 45 | 36 | 45 | 45 | 45 | 45 | 36 | 45 | 27 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053804 | No | No | Yes | Argentina | Argentina | 06-Hypercare | Argentina Production Support-OTC | LOG | FUN | SI | Offshore | Dhyani; Subhash | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053806 | Yes | No | No | Australia | Australia | 01-Preparation | SAP GRC Process Control RTM) (PP) |  | Missing Stream |  |  | _GD_SEC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  | DELIV.SEC-002B.SAP GRC Process Control RTM | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053807 | Yes | No | No | Australia | Australia | 03-Design/Build | Project team Role Design & Build and Processes |  | Missing Stream |  |  | _GD_SEC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | No |  |  | DELIV.SEC-115.Project team Role Design & Build and Processes | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053808 | Yes | No | No | Australia | Australia | 01-Preparation | Security and Controls Requirements) (PP) |  | Missing Stream |  |  | _GD_SEC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053809 | Yes | No | No | Australia | Australia | 02-Analyze | Project team Role Design & Build and Processes (AN) |  | Missing Stream |  |  | _GD_SEC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-28 | 2016-10-28 | No |  |  | DELIV.SEC-115.Project team Role Design & Build and Processes | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053810 | No | No | No | Australia | Australia | 02-Analyze | SAP GRC PC Post Installation Steps (AN) |  | Missing Stream |  |  | _SEC_OFF GRC PC TBD |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-28 | 2016-11-28 | No |  |  | DELIV.SEC-002B.SAP GRC Process Control RTM | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053811 | No | No | No | Australia | Australia | 02-Analyze | Security Approach (AN) |  | Missing Stream |  |  | _SEC_Resource Onshore |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-07 | 2017-01-07 | No |  |  | DELIV.SEC-001.Security Strategy | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053812 | Yes | No | No | Australia | Australia | 02-Analyze | Security Approach (AN) |  | Missing Stream |  |  | _Saputo SEC Analyst 2 |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-07 | 2017-01-07 | No |  |  | DELIV.SEC-001.Security Strategy | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053813 | Yes | No | No | Australia | Australia | 02-Analyze | GRC Access Controls Requirements (AN) |  | Missing Stream |  |  | _Saputo SEC Analyst 1 |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | No |  |  | DELIV.SEC-002B.SAP GRC Process Control RTM | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053814 | Yes | No | No | Australia | Australia | 02-Analyze | GRC Access Controls Requirements (AN) |  | Missing Stream |  |  | _Saputo SEC Analyst 2 |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | No |  |  | DELIV.SEC-002B.SAP GRC Process Control RTM | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053815 | No | No | No | Australia | Australia | 02-Analyze | Security Requirements Gathering (AN) |  | Missing Stream |  |  | _SEC_Resource Onshore |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-07 | 2017-01-07 | No |  |  | DELIV.SEC-002.Security and Controls Requirements | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053816 | Yes | No | No | Australia | Australia | 02-Analyze | Security Requirements Gathering (AN) |  | Missing Stream |  |  | _Saputo SEC Analyst 2 |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-07 | 2017-01-07 | No |  |  | DELIV.SEC-002.Security and Controls Requirements | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053817 | No | No | No | Australia | Australia | 03-Design/Build | Composite Role Build |  | Missing Stream |  |  | _SEC Resource Onshore |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-09 | 2017-03-09 | No |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053818 | No | No | No | Australia | Australia | 03-Design/Build | Security Detailed Design |  | Missing Stream |  |  | _SEC Resource Onshore |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.SEC-201.Security Role Detailed Design | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053819 | No | No | No | Australia | Australia | 03-Design/Build | Composite Role Design |  | Missing Stream |  |  | _SEC_Resource Onshore |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-17 | 2016-12-17 | No |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053820 | Yes | No | No | Australia | Australia | 03-Design/Build | Composite Role Design |  | Missing Stream |  |  | _Saputo SEC Analyst 2 |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-17 | 2016-12-17 | No |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053821 | No | No | No | Australia | Australia | 03-Design/Build | GRC AC Solution Design |  | Missing Stream |  |  | _SEC_OFF GRC AC TBD |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | No |  |  | DELIV.SEC-215.SAP Security & GRC Processes | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053822 | Yes | No | No | Australia | Australia | 03-Design/Build | GRC AC Solution Design |  | Missing Stream |  |  | _Saputo SEC Analyst 1 |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | No |  |  | DELIV.SEC-215.SAP Security & GRC Processes | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053823 | No | No | No | Australia | Australia | 03-Design/Build | Master Role Design - BUS |  | Missing Stream |  |  | _SEC Resource Onshore |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-17 | 2016-12-17 | No |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053824 | Yes | No | No | Australia | Australia | 03-Design/Build | Master Role Design - BUS |  | Missing Stream |  |  | _Saputo SEC Analyst 2 |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-17 | 2016-12-17 | No |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053825 | No | No | No | Australia | Australia | 03-Design/Build | SAP GRC PC Design |  | Missing Stream |  |  | _SEC_OFF GRC PC TBD |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | No |  |  | DELIV.SEC-215.SAP Security & GRC Processes | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053826 | No | No | No | Australia | Australia | 03-Design/Build | Security Design Workshps |  | Missing Stream |  |  | _SEC Resource Onshore |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053827 | Yes | No | No | Australia | Australia | 03-Design/Build | Security Design Workshps |  | Missing Stream |  |  | _Saputo SEC Analyst 2 |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053828 | Yes | No | No | Australia | Australia | 03-Design/Build | Security Detailed Design |  | Missing Stream |  |  | _Saputo SEC Analyst 2 |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.SEC-201.Security Role Detailed Design | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053829 | No | No | No | Australia | Australia | 03-Design/Build | Derived Role Build - BUS |  | Missing Stream |  |  | _SEC_Resource Onshore |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-10 | 2017-02-10 | No |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053830 | Yes | No | No | Australia | Australia | 03-Design/Build | Composite Role Build |  | Missing Stream |  |  | _Saputo SEC Analyst 2 |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-09 | 2017-03-09 | No |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053831 | No | No | No | Australia | Australia | 03-Design/Build | GRC AC Solution Build |  | Missing Stream |  |  | _SEC_OFF GRC AC TBD |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-10 | 2017-02-10 | No |  |  | DELIV.SEC-215.SAP Security & GRC Processes | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053832 | Yes | No | No | Australia | Australia | 03-Design/Build | GRC AC Solution Build |  | Missing Stream |  |  | _Saputo SEC Analyst 1 |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-10 | 2017-02-10 | No |  |  | DELIV.SEC-215.SAP Security & GRC Processes | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053833 | No | No | No | Australia | Australia | 03-Design/Build | Master Role Build and UT |  | Missing Stream |  |  | _SEC Resource Offshore |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | No |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053834 | No | No | No | Australia | Australia | 03-Design/Build | Master Role Build and UT |  | Missing Stream |  |  | _SEC_Resource Onshore |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | No |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053835 | No | No | No | Australia | Australia | 03-Design/Build | Derived Role Build - BUS |  | Missing Stream |  |  | _SEC Resource Offshore |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-10 | 2017-02-10 | No |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053836 | Yes | No | No | Australia | Australia | 03-Design/Build | Master Role Build and UT |  | Missing Stream |  |  | _Saputo SEC Analyst 2 |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | No |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053837 | No | No | No | Australia | Australia | 03-Design/Build | SAP GRC PC Build |  | Missing Stream |  |  | _SEC_OFF GRC PC TBD |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-20 | 2016-11-20 | No |  |  | DELIV.SEC-215.SAP Security & GRC Processes | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053838 | No | No | No | Australia | Australia | 03-Design/Build | SoD GRC AC Analysis and Remediation |  | Missing Stream |  |  | _SEC_OFF GRC AC TBD |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-11 | 2016-12-11 | No |  |  | DELIV.SEC-215.SAP Security & GRC Processes | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053839 | Yes | No | No | Australia | Australia | 03-Design/Build | SoD GRC AC Analysis and Remediation |  | Missing Stream |  |  | _Saputo SEC Analyst 1 |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-11 | 2016-12-11 | No |  |  | DELIV.SEC-215.SAP Security & GRC Processes | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053840 | No | No | No | Australia | Australia | 03-Design/Build | Security Role FUT |  | Missing Stream |  |  | _SEC Resource Offshore |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | No |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053841 | Yes | No | No | Australia | Australia | 03-Design/Build | Security Role FUT |  | Missing Stream |  |  | _Saputo SEC Analyst 2 |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | No |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053842 | No | No | No | Australia | Australia | 01-Preparation | Prepare Kickoff (PP) |  | Missing Stream |  |  | _SEC Resource Onshore |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-22 | 2016-10-22 | No |  |  | DELIV.TAI-001.Technology Implementation Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053843 | Yes | No | No | Australia | Australia | 02-Analyze | SolMan setup and config for Documentation, Charm and Monitoring (AN) |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-07 | 2017-01-07 | No |  |  | ACT.TAI.SolMan setup & config for Doc | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053844 | Yes | No | No | Australia | Australia | 01-Preparation | Site infrastructure assessment (TAI) (PP) |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | DELIV.TAI-001.Technology Implementation Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053845 | Yes | No | No | Australia | Australia | 01-Preparation | Technology Implementation Plan) (PP) |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | DELIV.TAI-001.Technology Implementation Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053846 | Yes | No | No | Australia | Australia | 03-Design/Build | Network - Deployment Plan - Not TAI |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.TAI-470.Network - Deployment Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053847 | Yes | No | No | Australia | Australia | 03-Design/Build | Performance Test Scripts |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.TST-302.Performance Test Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053848 | Yes | No | No | Australia | Australia | 03-Design/Build | Transport Sequence |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.PMO-035.Transport Sequence | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053849 | Yes | No | No | Australia | Australia | 01-Preparation | SolMan setup and config for Documentation, Charm and Monitoring) (PP) |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  | ACT.TAI.SolMan setup & config for Doc | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053850 | Yes | No | No | Australia | Australia | 01-Preparation | Technical Architecture Specification) (PP) |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  | DELIV.TAI-002.Technical Architecture Specification | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053851 | Yes | No | No | Australia | Australia | 02-Analyze | Network - Solution Network Document (AN) |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | DELIV.TAI-225.Network - Solution Network Document | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053852 | Yes | No | No | Australia | Australia | 02-Analyze | Legacy System Retirement strategy (AN) |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | DELIV.TAI-130.Legacy System Retirement strategy | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053853 | Yes | No | No | Australia | Australia | 02-Analyze | Architecture by release Diagrams (AN) |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | DELIV.TAI-104.Architecture by release Diagrams | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053854 | Yes | No | No | Australia | Australia | 02-Analyze | Development Environment (AN) |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | DELIV.TAI-101.Development Environment | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053855 | Yes | No | No | Australia | Australia | 02-Analyze | Sandbox Environment (AN) |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | DELIV.TAI-103.Sandbox Environment | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053856 | Yes | No | No | Australia | Australia | 02-Analyze | SAP Enablement - Technical Requirements (AN) |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | DELIV.TAI-110.SAP Enablement - Technical Requirements | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053857 | Yes | No | No | Australia | Australia | 04-Test | Technology Implementation Plan |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.TAI-001.Technology Implementation Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053858 | Yes | No | No | Australia | Australia | 04-Test | Network - Solution Network Document |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.TAI-225.Network - Solution Network Document | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053859 | Yes | No | No | Australia | Australia | 04-Test | Network - Deployment Plan |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.TAI-470.Network - Deployment Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053860 | Yes | No | No | Australia | Australia | 04-Test | Technical Operations Manual |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.TAI-501.Technical Operations Manual | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053861 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Technology Implementation Plan |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV.TAI-001.Technology Implementation Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053862 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Technical Operations Manual |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV.TAI-501.Technical Operations Manual | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053863 | No | No | No | Australia | Australia | 03-Design/Build | SAP GRC PC Unit Test |  | Missing Stream |  |  | _SEC_OFF GRC PC TBD |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | No |  |  | DELIV.SEC-215.SAP Security & GRC Processes | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053864 | Yes | No | No | Australia | Australia | 02-Analyze | PCR - 208 - Bring DataServices and Information Steward - TAI |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-21 | 2016-11-21 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053865 | Yes | No | No | Australia | Australia | 01-Preparation | Prepare Kickoff (PP) |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-22 | 2016-10-22 | No |  |  | DELIV.TAI-001.Technology Implementation Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053866 | Yes | No | No | Australia | Australia | 01-Preparation | Conduct Kickoff in Australia (PP) |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-22 | 2016-10-22 | No |  |  | DELIV.TAI-001.Technology Implementation Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053867 | Yes | No | No | Australia | Australia | 01-Preparation | Prepare for KT (PP) |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-22 | 2016-10-22 | No |  |  | DELIV.TAI-001.Technology Implementation Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053868 | Yes | No | No | Australia | Australia | 01-Preparation | Coduct KT Sessions (PP) |  | Missing Stream |  |  | _GD_TAI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-28 | 2016-10-28 | No |  |  | DELIV.TAI-001.Technology Implementation Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053869 | Yes | No | No | Australia | Australia | 03-Design/Build | FLOG021-DEV-Pick List |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-21 | 2017-02-21 | No |  |  | DELIV.DEV-204.Technical Specification - Form | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053870 | Yes | No | No | Australia | Australia | 03-Design/Build | IOTC007-DEV-EDI Outbound Order Response |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-24 | 2017-03-24 | No |  |  | DELIV.DEV-202.Technical Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053871 | Yes | No | No | Australia | Australia | 03-Design/Build | IOTC009-DEV-EDI Outbound Invoice |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-03 | 2017-03-03 | No |  |  | DELIV.DEV-202.Technical Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053872 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-DEV-Placeholderx |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053873 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-DEV-Rebates selement report |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-26 | 2017-05-26 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053874 | Yes | No | No | Australia | Australia | 03-Design/Build | FOTC002-DEV-Domestic Tax Invoice form |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-24 | 2017-02-24 | No |  |  | DELIV.DEV-204.Technical Specification - Form | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053875 | Yes | No | No | Australia | Australia | 03-Design/Build | FOTC007-DEV-Order acknowledgement form - domestic |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-15 | 2017-04-15 | No |  |  | DELIV.DEV-204.Technical Specification - Form | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053876 | Yes | No | No | Australia | Australia | 03-Design/Build | IOTC008-DEV-ECC/GTS to BSM Order |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-17 | 2017-03-17 | No |  |  | DELIV.DEV-202.Technical Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053877 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-DEV-Order acknowledgement form - export |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-17 | 2017-02-17 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053878 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-DEV-Placeholderx |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-10 | 2017-02-10 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053879 | Yes | No | No | Australia | Australia | 03-Design/Build | IOTC006-DEV-EDI Inbound Sales Order |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-31 | 2017-03-31 | No |  |  | DELIV.DEV-202.Technical Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053880 | Yes | No | No | Australia | Australia | 03-Design/Build | FPTM005-DEV-Raw material GI |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-07 | 2017-04-07 | No |  |  | DELIV.DEV-204.Technical Specification - Form | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053881 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-DEV-MTS to MII |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-18 | 2017-04-18 | No |  |  | DELIV.DEV-202.Technical Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053882 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-DEV-Inventory count w/ Bin Location - Out of scope |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-18 | 2017-04-18 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053883 | Yes | No | No | Australia | Australia | 03-Design/Build | FPTM004-DEV-Workorder picklist w/ Bin Location |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-17 | 2017-03-17 | No |  |  | DELIV.DEV-204.Technical Specification - Form | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053884 | Yes | No | No | Australia | Australia | 03-Design/Build | EPTM019-DEV-DTS |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-28 | 2017-04-28 | No |  |  | DELIV.DEV-203.Technical Specification -Enhancement | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053885 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-DEV-Tabular results ( including 6506 ) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-25 | 2017-04-25 | No |  |  | DELIV.DEV-203.Technical Specification -Enhancement | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053886 | Yes | No | No | Australia | Australia | 03-Design/Build | EPTM018-DEV-Chemical analysis machines |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-21 | 2017-04-21 | No |  |  | DELIV.DEV-203.Technical Specification -Enhancement | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053887 | Yes | No | No | Australia | Australia | 03-Design/Build | FPTP003-DEV-GOI Customer COA form |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-21 | 2017-04-21 | No |  |  | DELIV.DEV-204.Technical Specification - Form | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053888 | Yes | No | No | Australia | Australia | 03-Design/Build | FPTP004-DEV-Localise PO output (form) and T&C |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-03 | 2017-03-03 | No |  |  | DELIV.DEV-204.Technical Specification - Form | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053889 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-Argentina Settlement Form |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053890 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-Australian Settlement Form Victoria |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053891 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-Australian Settlement Form Southern Australia |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053892 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-Australia Federal |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053893 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-Enhancement Payment program for bank |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053894 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-Placeholder for RTR Design Issue |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053895 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-Australia Pricing routine Surcharge 1 |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-03 | 2017-03-03 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053896 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-Australia Pricing routine Surcharge 2 |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053897 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-Australia Pricing routine Surcharge 3 |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053898 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-MinAgri 1- XML with liters detail (milk delivery) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-03 | 2017-03-03 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053899 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-MinAgri 2- XML with analysis request (was consolidated with MinAgri1) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-03 | 2017-03-03 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053900 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-MinAgri 3- XML with analysis results (was consolidated with MinAgri1) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-03 | 2017-03-03 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053901 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-Import XML from agriculture agency system (Was consolidated with MinAgri1) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-03 | 2017-03-03 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053902 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-Argentina Pricing routine 1 |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053903 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-Argentina Pricing routine 2 |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053904 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-Argentina Pricing routine 3 |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053905 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-Argentina Pricing routine 4 |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053906 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-Argentina Pricing routine 5 |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053907 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-Argentina Pricing routine 6 |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053908 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-Australia Pricing routine Quality |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053909 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-Australia Pricing routine Incentives/Premiums 1 |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053910 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-Australia Pricing routine Incentives/Premiums 2 |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053911 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-Australia Pricing routine Incentives/Premiums 3 |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053912 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-Australia Pricing routine Incentives/Premiums 4 |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053913 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-Australia Pricing routine Incentives/Premiums 5 |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053914 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-Australia Pricing routine Incentives/Premiums 6 |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053915 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-Australia Pricing routine Incentives/Premiums 7 |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053916 | Yes | No | No | Australia | Australia | 03-Design/Build | ERTR021-DEV-ATO Ref |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-24 | 2017-02-24 | No |  |  | DELIV.DEV-203.Technical Specification -Enhancement | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053917 | Yes | No | No | Australia | Australia | 03-Design/Build | ILOG006-DEV-EDI 3PL Pick Request |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-16 | 2017-02-16 | No |  |  | DELIV.DEV-202.Technical Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053918 | Yes | No | No | Australia | Australia | 03-Design/Build | ILOG007-DEV-EDI 3PL ASN |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | No |  |  | DELIV.DEV-202.Technical Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053919 | Yes | No | No | Australia | Australia | 03-Design/Build | ILOG011-DEV-Lot Status Message to 3PL |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | DELIV.DEV-202.Technical Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053920 | Yes | No | No | Australia | Australia | 03-Design/Build | FLOG019-DEV-BOL + AQIS number |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-20 | 2017-02-20 | No |  |  | DELIV.DEV-204.Technical Specification - Form | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053921 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-DEV-Master BOL |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-03 | 2017-02-03 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053922 | Yes | No | No | Australia | Australia | 03-Design/Build | FLOG020-DEV-Packing List |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-15 | 2017-02-15 | No |  |  | DELIV.DEV-204.Technical Specification - Form | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053923 | Yes | No | No | Australia | Australia | 03-Design/Build | ILOG009-DEV-EDI Outbound ASN sent to customers |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | DELIV.DEV-202.Technical Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053924 | Yes | No | No | Australia | Australia | 03-Design/Build | ILOG008-DEV-ECC to BSM Delivery |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-20 | 2017-02-20 | No |  |  | DELIV.DEV-202.Technical Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053925 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-DEV-ECC/GTS to BSM Order (Transfer OTC) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053926 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-Inbound Milk Receipt information |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053927 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-Milk Swap between external partner |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053928 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-Placeholde for TM Design issue |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053929 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV-Placeholder for RTR Design Issue |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053930 | Yes | No | No | Australia | Australia | 03-Design/Build | FRTR005-DEV-Ability to produce an invoice for direct FI |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | No |  |  | DELIV.DEV-204.Technical Specification - Form | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053931 | Yes | No | No | Australia | Australia | 03-Design/Build | FRTR006-DEV-Need to send payment remittance advice |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | No |  |  | DELIV.DEV-204.Technical Specification - Form | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053932 | Yes | No | No | Australia | Australia | 03-Design/Build | EPTM016-DEV-AU Raw material GI to process order A)(GI to PO and form triggering ) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-17 | 2017-03-17 | No |  |  | DELIV.DEV-203.Technical Specification -Enhancement | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053933 | Yes | No | No | Australia | Australia | 03-Design/Build | EPTM017-DEV-AU Raw material GI to process order B)(Goods Issue reversal program) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-31 | 2017-03-31 | No |  |  | DELIV.DEV-203.Technical Specification -Enhancement | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053934 | Yes | No | No | Australia | Australia | 03-Design/Build | Development (D/B) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053935 | Yes | No | No | Australia | Australia | 04-Test | Development (SIT1) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053936 | Yes | No | No | Australia | Australia | 04-Test | Development (SIT2) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053937 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Development (Cutover/Go-live) - DEV |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-02 | 2017-06-02 | No |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053938 | Yes | No | No | Australia | Australia | 03-Design/Build | ILOG010-DEV-Pick Confirmation to 3PL |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-21 | 2017-04-21 | No |  |  | DELIV.DEV-202.Technical Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053939 | Yes | No | No | Australia | Australia | 06-Hypercare | Development (Hypercare) - DEV |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-04 | 2017-05-04 | No |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053940 | Yes | No | No | Australia | Australia | 03-Design/Build | Developments (D/B) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053941 | Yes | No | No | Australia | Australia | 03-Design/Build | Application Architecture Diagram (D/B) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.DEV-001.Application Architecture Diagram | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053942 | Yes | No | No | Australia | Australia | 03-Design/Build | Development Unit Testing Documentation (D/B) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.DEV-320.Development Unit Testing Documentation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053943 | Yes | No | No | Australia | Australia | 03-Design/Build | Interface Approach and Error Handling Strategy (D/B) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.DEV-144.Interface Approach and Error Handling Strategy | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053944 | Yes | No | No | Australia | Australia | 03-Design/Build | Technical Specification - Report (D/B) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.DEV-201.Technical Specification - Report | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053945 | Yes | No | No | Australia | Australia | 03-Design/Build | Technical Specification - Interface (D/B) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.DEV-202.Technical Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053946 | Yes | No | No | Australia | Australia | 03-Design/Build | Technical Specification -Enhancement (D/B) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.DEV-203.Technical Specification -Enhancement | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053947 | Yes | No | No | Australia | Australia | 03-Design/Build | Technical Specification - Form (D/B) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.DEV-204.Technical Specification - Form | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053948 | Yes | No | No | Australia | Australia | 03-Design/Build | Technical Specification - Workflow (D/B) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.DEV-205.Technical Specification - Workflow | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053949 | Yes | No | No | Australia | Australia | 02-Analyze | Application Architecture Diagram (AN) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-07 | 2017-01-07 | No |  |  | DELIV.DEV-001.Application Architecture Diagram | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053950 | Yes | No | No | Australia | Australia | 01-Preparation | Application Architecture Diagram) (PP) |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-29 | 2016-10-29 | No |  |  | DELIV.DEV-001.Application Architecture Diagram | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053951 | Yes | No | No | Australia | Australia | 01-Preparation | High Level Legacy and EDI impacts |  | Missing Stream |  |  | _GD_DEV-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-29 | 2016-10-29 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053952 | Yes | No | No | Australia | Australia | 04-Test | Regression - Manage defects (Capex) - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053953 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Prep |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.UAT Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053954 | Yes | No | No | Australia | Australia | 01-Preparation | Business Process Master List (BPML)) (PP) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053955 | Yes | No | No | Australia | Australia | 01-Preparation | Requirements Traceability Matrix (RTM)) (PP) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053956 | Yes | No | No | Australia | Australia | 01-Preparation | Consolidated Workshop Schedule) (PP) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  | DELIV.FUN-101.Consolidated Workshop Schedule | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053957 | Yes | No | No | Australia | Australia | 02-Analyze | Demo (AN) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | ACT.FUN.Solution Confirmation Prensentations and Demonstrations | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053958 | Yes | No | No | Australia | Australia | 02-Analyze | Process Documentation in BWL (AN) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | ACT.FUN.Process Documentation in BWL | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053959 | Yes | No | No | Australia | Australia | 02-Analyze | Business Process Master List (BPML) (AN) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053960 | Yes | No | No | Australia | Australia | 03-Design/Build | Process Workarounds (D/B) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053961 | Yes | No | No | Australia | Australia | 03-Design/Build | Support Operational Procedures (SOPs) (D/B) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.FUN-314.Support Operational Procedures (SOPs) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053962 | Yes | No | No | Australia | Australia | 03-Design/Build | Support Operational Procedures Inventory (D/B) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.FUN-214.Support Operational Procedures Inventory | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053963 | Yes | No | No | Australia | Australia | 04-Test | Training Environment Population and Testing |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Training Environment Population and Testing | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053964 | Yes | No | No | Australia | Australia |  | AUS - RTR KT |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053965 | Yes | No | No | Australia | Australia | 04-Test | Documentation |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053966 | Yes | No | No | Australia | Australia | 04-Test | Management (Test) - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053967 | Yes | No | No | Australia | Australia | 04-Test | Regression - Run Tests - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053968 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Document work around |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053969 | Yes | No | No | Australia | Australia | 06-Hypercare | Management (Hypercare) - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | No |  |  | ACT.DEV.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053970 | Yes | No | No | Australia | Australia | 04-Test | SIT1 Preparation |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | No |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053971 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD011-Cost Center Plan |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053972 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD116-Collection - Business partner data |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053973 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Argentina Settlement Form |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053974 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Australian Settlement Form Victoria |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053975 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Australian Settlement Form Southern Australia |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053976 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Australia Federal |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053977 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Enhancement Payment program for bank |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053978 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Placeholder for RTR Design Issue |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053979 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Placeholder for RTR Design Issue |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053980 | Yes | No | No | Australia | Australia | 03-Design/Build | ERTR021-DEV FUT-ATO Ref |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-14 | 2017-03-14 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053981 | Yes | No | No | Australia | Australia | 03-Design/Build | AA_01-CONFIG-Organization Structure |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053982 | Yes | No | No | Australia | Australia | 03-Design/Build | AA_02-CONFIG-Integration with General Ledger Accounting |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-14 | 2017-02-14 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053983 | Yes | No | No | Australia | Australia | 03-Design/Build | AA_03-CONFIG-General Valuation |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053984 | Yes | No | No | Australia | Australia | 03-Design/Build | AP_01-CONFIG-AP-General Settings |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053985 | Yes | No | No | Australia | Australia | 03-Design/Build | AP_02-CONFIG-Automatic Payment |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053986 | Yes | No | No | Australia | Australia | 03-Design/Build | AP_03-CONFIG-Tax on Sale / Purchase |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053987 | Yes | No | No | Australia | Australia | 03-Design/Build | AR_01-CONFIG-FI-AR-Basic Settings |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053988 | Yes | No | No | Australia | Australia | 03-Design/Build | CC_01-CONFIG-Cost Centre Accounting - Planning and Actual |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-20 | 2017-02-20 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053989 | Yes | No | No | Australia | Australia | 03-Design/Build | COC_01-CONFIG-Cost Object Controlling |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053990 | Yes | No | No | Australia | Australia | 03-Design/Build | COC_02-CONFIG-Cost Object Controlling - Cancelled |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053991 | Yes | No | No | Australia | Australia | 03-Design/Build | DMS_04-CONFIG-Dairy Mgmt System - Costing |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053992 | Yes | No | No | Australia | Australia | 03-Design/Build | GL_01-CONFIG-Definition and assignment of Organization structure |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053993 | Yes | No | No | Australia | Australia | 03-Design/Build | GL_02-CONFIG-Fiscal Year and Posting periods |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053994 | Yes | No | No | Australia | Australia | 03-Design/Build | GL_03-CONFIG-New General Ledger |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053995 | Yes | No | No | Australia | Australia | 03-Design/Build | GL_04-CONFIG-GL-General Settings |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053996 | Yes | No | No | Australia | Australia | 03-Design/Build | GL_05-CONFIG-GL Maintenance |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-02 | 2017-02-02 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053997 | Yes | No | No | Australia | Australia | 03-Design/Build | GL_06-CONFIG-GL Assignment |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053998 | Yes | No | No | Australia | Australia | 03-Design/Build | GL_07-CONFIG-Cancelled |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053999 | Yes | No | No | Australia | Australia | 03-Design/Build | GL_08-CONFIG-Cancelled |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054000 | Yes | No | No | Australia | Australia | 03-Design/Build | OI_01-CONFIG-Internal Order |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054001 | Yes | No | No | Australia | Australia | 03-Design/Build | OI_02-CONFIG-Internal Order Planning |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054002 | Yes | No | No | Australia | Australia | 03-Design/Build | PA_02-CONFIG-Profitability Analysis Planning |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054003 | Yes | No | No | Australia | Australia | 03-Design/Build | PA_01-CONFIG-Profitability Analysis Actual |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054004 | Yes | No | No | Australia | Australia | 03-Design/Build | PC_02-CONFIG-Product Cost Planning |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054005 | Yes | No | No | Australia | Australia | 03-Design/Build | PC_01-CONFIG-Actual Costing/Material Ledger |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054006 | Yes | No | No | Australia | Australia | 03-Design/Build | PCA_01-CONFIG-Profit Centre Accounting |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054007 | Yes | No | No | Australia | Australia | 03-Design/Build | AA_01-CONFIG FUT-Organization Structure |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-17 | 2017-02-17 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054008 | Yes | No | No | Australia | Australia | 03-Design/Build | AA_02-CONFIG FUT-Integration with General Ledger Accounting |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054009 | Yes | No | No | Australia | Australia | 03-Design/Build | AA_03-CONFIG FUT-General Valuation |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-28 | 2017-02-28 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054010 | Yes | No | No | Australia | Australia | 03-Design/Build | AP_01-CONFIG FUT-AP-General Settings |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054011 | Yes | No | No | Australia | Australia | 03-Design/Build | AP_02-CONFIG FUT-Automatic Payment |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-23 | 2017-02-23 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054012 | Yes | No | No | Australia | Australia | 03-Design/Build | AP_03-CONFIG FUT-Tax on Sale / Purchase |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-24 | 2017-02-24 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054013 | Yes | No | No | Australia | Australia | 03-Design/Build | AR_01-CONFIG FUT-FI-AR-Basic Settings |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054014 | Yes | No | No | Australia | Australia | 03-Design/Build | BPC_01-CONFIG FUT-Create BPC Backend Objects |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-27 | 2017-01-27 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054015 | Yes | No | No | Australia | Australia | 03-Design/Build | CC_01-CONFIG FUT-Cost Centre Accounting - Planning and Actual |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-28 | 2017-01-28 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054016 | Yes | No | No | Australia | Australia | 03-Design/Build | CO_01-CONFIG FUT-CO Organizational Data |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054017 | Yes | No | No | Australia | Australia | 03-Design/Build | CO_02-CONFIG FUT-CO CONFIG FUTuration Master Data |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054018 | Yes | No | No | Australia | Australia | 03-Design/Build | COC_01-CONFIG FUT-Cost Object Controlling |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054019 | Yes | No | No | Australia | Australia | 03-Design/Build | COC_02-CONFIG FUT-Cancelled |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054020 | Yes | No | No | Australia | Australia | 03-Design/Build | DMS_04-CONFIG FUT-Dairy Mgmt System - Costing |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-06 | 2017-04-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054021 | Yes | No | No | Australia | Australia | 03-Design/Build | GL_01-CONFIG FUT-Definition and assignment of Organization structure |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054022 | Yes | No | No | Australia | Australia | 03-Design/Build | GL_02-CONFIG FUT-Fiscal Year and Posting periods |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054023 | Yes | No | No | Australia | Australia | 03-Design/Build | GL_03-CONFIG FUT-New General Ledger |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054024 | Yes | No | No | Australia | Australia | 03-Design/Build | GL_04-CONFIG FUT-GL-General Settings |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054025 | Yes | No | No | Australia | Australia | 03-Design/Build | GL_05-CONFIG FUT-GL Maintenance |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-10 | 2017-02-10 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054026 | Yes | No | No | Australia | Australia | 03-Design/Build | GL_06-CONFIG FUT-GL Assignment |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054027 | Yes | No | No | Australia | Australia | 03-Design/Build | GL_07-CONFIG FUT-Cancelled |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-20 | 2017-01-20 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054028 | Yes | No | No | Australia | Australia | 03-Design/Build | GL_08-CONFIG FUT-Cancelled |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-20 | 2017-01-20 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054029 | Yes | No | No | Australia | Australia | 03-Design/Build | OI_01-CONFIG FUT-Internal Order |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-28 | 2017-02-28 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054030 | Yes | No | No | Australia | Australia | 03-Design/Build | OI_02-CONFIG FUT-Internal Order Planning |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-01 | 2017-03-01 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054031 | Yes | No | No | Australia | Australia | 03-Design/Build | PA_02-CONFIG FUT-Profitability Analysis Planning |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-23 | 2017-03-23 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054032 | Yes | No | No | Australia | Australia | 03-Design/Build | PA_01-CONFIG FUT-Profitability Analysis Actual |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-10 | 2017-02-10 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054033 | Yes | No | No | Australia | Australia | 03-Design/Build | PC_01-CONFIG FUT-Product Cost Planning |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054034 | Yes | No | No | Australia | Australia | 03-Design/Build | PC_02-CONFIG FUT-Actual Costing/Material Ledger |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-27 | 2017-01-27 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054035 | Yes | No | No | Australia | Australia | 03-Design/Build | PCA_01-CONFIG FUT-Profit Centre Accounting |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-17 | 2017-03-17 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054036 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Argentina Settlement Form |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054037 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Australian Settlement Form Victoria |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054038 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Australian Settlement Form Southern Australia |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054039 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Australia Federal |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054040 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Enhancement Payment program for bank |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054041 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Placeholder for RTR Design Issue |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054042 | Yes | No | No | Australia | Australia | 03-Design/Build | Management (D/B) - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054043 | Yes | No | No | Australia | Australia | 03-Design/Build | BNK_05-CONFIG-FI-AR-Bill of Exchange Receivable |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-04 | 2017-02-04 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054044 | Yes | No | No | Australia | Australia | 03-Design/Build | MM_04-CONFIG-MM Valuation and Acct assignment |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-04 | 2017-02-04 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054045 | Yes | No | No | Australia | Australia | 03-Design/Build | PC_03-CONFIG-Product Costing |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-04 | 2017-02-04 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054046 | Yes | No | No | Australia | Australia | 03-Design/Build | BNK_05-CONFIG FUT-FI-AR-Bill of Exchange Receivable |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-04 | 2017-02-04 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054047 | Yes | No | No | Australia | Australia | 03-Design/Build | MM_09-CONFIG FUT-MM Logistics Invoice Verification |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-17 | 2017-02-17 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054048 | Yes | No | No | Australia | Australia | 06-Hypercare | Management (Hypercare) - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | No |  |  | ACT.DEV.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054049 | Yes | No | No | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | No |  |  | ACT.FUN.Functional Break/Fix | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054050 | Yes | No | No | Australia | Australia | 06-Hypercare | Manage Defects (Hypercare) - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054051 | Yes | No | No | Australia | Australia | 06-Hypercare | Break/Fix (Hypercare) - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054052 | Yes | No | No | Australia | Australia | 04-Test | Documentation |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054053 | Yes | No | No | Australia | Australia | 04-Test | Management (Test) - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054054 | Yes | No | No | Australia | Australia | 04-Test | Regression - Run Tests - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054055 | Yes | No | No | Australia | Australia | 04-Test | Regression - Manage defects (Capex) - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054056 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Prepare |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-14 | 2017-03-14 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054057 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Support |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054058 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Validate |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-04-10 | 2017-04-10 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054059 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Run Tests |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054060 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Manage Defects (Capex) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-27 | 2017-04-27 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054061 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Break/Fix - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054062 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Prepare |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054063 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Support |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-02-20 | 2017-02-20 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054064 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Validate |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-03 | 2017-03-03 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054065 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Run Tests - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054066 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Manage Defects (Capex) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-19 | 2017-05-19 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054067 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Break/Fix - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054068 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Management (Cutover/Go-live) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054069 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054070 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054071 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054072 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Prep |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.UAT Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054073 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054074 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Manage Defects (Capex) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054075 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054076 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Document work around |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054077 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Prepare - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054078 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-19 | 2017-06-19 | No |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054079 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Validate |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | No |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054080 | Yes | No | No | Australia | Australia | 03-Design/Build | BPC_01-CONFIG-Create BPC Backend Objects |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-17 | 2017-01-17 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054081 | Yes | No | No | Australia | Australia | 03-Design/Build | CO_01-CONFIG-CO Organizational Data |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054082 | Yes | No | No | Australia | Australia | 03-Design/Build | CO_02-CONFIG-CO Configuration Master Data |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054083 | Yes | No | No | Australia | Australia | 03-Design/Build | AR_07-CONFIG-FI-AR-Electronic Incoming Payments |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-04 | 2017-02-04 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054084 | Yes | No | No | Australia | Australia | 03-Design/Build | AR_07-CONFIG FUT-FI-AR-Electronic Incoming Payments |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054085 | Yes | No | No | Australia | Australia | 02-Analyze | Management (AN) |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054086 | Yes | No | No | Australia | Australia | 02-Analyze | Kickoff (AN) |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054087 | Yes | No | No | Australia | Australia | 02-Analyze | Fit/Gaps Analysis (AN) |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054088 | Yes | No | No | Australia | Australia | 02-Analyze | Management (AN) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054089 | Yes | No | No | Australia | Australia | 02-Analyze | Kickoff (AN) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054090 | Yes | No | No | Australia | Australia | 02-Analyze | Fit/Gaps Analysis (AN) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054091 | Yes | No | No | Australia | Australia | 02-Analyze | RTM (AN) |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-04 | 2016-11-04 | No |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054092 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Create BPML (AN) |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054093 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Log Gaps (AN) |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-11 | 2016-11-11 | No |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054094 | Yes | No | No | Australia | Australia | 01-Preparation | Prepare KT) (PP) |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054095 | Yes | No | No | Australia | Australia | 01-Preparation | Prepare KT) (PP) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054096 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Conduct Design Workshops (AN) |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-22 | 2016-11-22 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054097 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Perform Gap Resolution (AN) |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-21 | 2016-11-21 | No |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054098 | Yes | No | No | Australia | Australia | 03-Design/Build | PDD-Baseline (D/B) |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054099 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-Baseline (D/B) |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054100 | Yes | No | No | Australia | Australia | 03-Design/Build | FSD-Baseline (D/B) |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054101 | Yes | No | No | Australia | Australia | 03-Design/Build | Support to Developpers (D/B) |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054102 | Yes | No | No | Australia | Australia | 03-Design/Build | DEV FUT- Baseline (D/B) |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054103 | Yes | No | No | Australia | Australia | 03-Design/Build | CONFIG-Baseline (D/B) |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054104 | Yes | No | No | Australia | Australia | 03-Design/Build | SDD Writing |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054105 | Yes | No | No | Australia | Australia | 03-Design/Build | CONFIG FUT-Baseline (D/B) |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-13 | 2016-12-13 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054106 | Yes | No | No | Australia | Australia | 03-Design/Build | Support MDM (D/B) |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-12-03 | 2016-12-03 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054107 | Yes | No | No | Australia | Australia | 03-Design/Build | Contribute to Cut-over Planning (D/B) - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-22 | 2016-11-22 | No |  |  | ACT.FUN.Support Cutover plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054108 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Prepare |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-14 | 2017-03-14 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054109 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Support |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054110 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Validate |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-04-10 | 2017-04-10 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054111 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Run Tests |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054112 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Manage Defects (Capex) |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-27 | 2017-04-27 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054113 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Break/Fix - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054114 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Prepare |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054115 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Support |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-02-20 | 2017-02-20 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054116 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Validate |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-03 | 2017-03-03 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054117 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Run Tests - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054118 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Manage Defects (Capex) |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-19 | 2017-05-19 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054119 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Break/Fix - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054120 | Yes | No | No | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | No |  |  | ACT.FUN.Functional Break/Fix | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054121 | Yes | No | No | Australia | Australia | 06-Hypercare | Manage Defects (Hypercare) - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054122 | Yes | No | No | Australia | Australia | 06-Hypercare | Break/Fix (Hypercare) - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054123 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054124 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054125 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054126 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054127 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Manage Defects (Capex) |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054128 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054129 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Prepare - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054130 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-19 | 2017-06-19 | No |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054131 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Validate |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | No |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054132 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054133 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054134 | Yes | No | No | Australia | Australia | 02-Analyze | RTM (AN) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-04 | 2016-11-04 | No |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054135 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Create BPML (AN) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054136 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Log Gaps (AN) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-11 | 2016-11-11 | No |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054137 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Conduct Design Workshops (AN) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-22 | 2016-11-22 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054138 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Perform Gap Resolution (AN) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-21 | 2016-11-21 | No |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054139 | Yes | No | No | Australia | Australia | 03-Design/Build | PDD-Baseline (D/B) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054140 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-Baseline (D/B) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054141 | Yes | No | No | Australia | Australia | 03-Design/Build | FSD-Baseline (D/B) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054142 | Yes | No | No | Australia | Australia | 03-Design/Build | Support to Developpers (D/B) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054143 | Yes | No | No | Australia | Australia | 03-Design/Build | DEV FUT- Baseline (D/B) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054144 | Yes | No | No | Australia | Australia | 03-Design/Build | CONFIG-Baseline (D/B) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054145 | Yes | No | No | Australia | Australia | 03-Design/Build | SDD Writing |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054146 | Yes | No | No | Australia | Australia | 03-Design/Build | CONFIG FUT-Baseline (D/B) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-13 | 2016-12-13 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054147 | Yes | No | No | Australia | Australia | 03-Design/Build | Support MDM (D/B) |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-12-03 | 2016-12-03 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054148 | Yes | No | No | Australia | Australia | 03-Design/Build | Contribute to Cut-over Planning (D/B) - RTR |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-22 | 2016-11-22 | No |  |  | ACT.FUN.Support Cutover plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054149 | Yes | No | No | Australia | Australia | 03-Design/Build | ERTR021-FSD-ATO Ref |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | DELIV.FUN-203.Functional Specification - Enhancement | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054150 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Placeholder for RTR Design Issue |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054151 | Yes | No | No | Australia | Australia | 03-Design/Build | Management (D/B) - RTR |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054152 | Yes | No | No | Australia | Australia | 03-Design/Build | BPC_02-CONFIG-Dimension management |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054153 | Yes | No | No | Australia | Australia | 03-Design/Build | BPC_03A-CONFIG-Configure Source System Extractors/Interface |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054154 | Yes | No | No | Australia | Australia | 03-Design/Build | BPC_03B-CONFIG-Configure Source System Extractors/Interface |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054155 | Yes | No | No | Australia | Australia | 03-Design/Build | BPC_04-CONFIG-Configure Intercompany Rules |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054156 | Yes | No | No | Australia | Australia | 03-Design/Build | BPC_05-CONFIG-Configure Currency Translation rules |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054157 | Yes | No | No | Australia | Australia | 03-Design/Build | BPC_06-CONFIG-Configure Custom Logic |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-20 | 2017-02-20 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054158 | Yes | No | No | Australia | Australia | 03-Design/Build | BPC_07-CONFIG-Define Business Process Flows |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-20 | 2017-02-20 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054159 | Yes | No | No | Australia | Australia | 03-Design/Build | BPC_08-CONFIG-Reporting |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-20 | 2017-02-20 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054160 | Yes | No | No | Australia | Australia | 03-Design/Build | BPC_02-CONFIG FUT-Dimension management |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-17 | 2017-02-17 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054161 | Yes | No | No | Australia | Australia | 03-Design/Build | BPC_03A-CONFIG FUT-CONFIG FUTure Source System Extractors/Interface |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-17 | 2017-02-17 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054162 | Yes | No | No | Australia | Australia | 03-Design/Build | BPC_03B-CONFIG FUT-CONFIG FUTure Source System Extractors/Interface |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-17 | 2017-02-17 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054163 | Yes | No | No | Australia | Australia | 03-Design/Build | BPC_04-CONFIG FUT-CONFIG FUTure Intercompany Rules |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-17 | 2017-02-17 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054164 | Yes | No | No | Australia | Australia | 03-Design/Build | BPC_05-CONFIG FUT-CONFIG FUTure Currency Translation rules |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-17 | 2017-02-17 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054165 | Yes | No | No | Australia | Australia | 03-Design/Build | BPC_06-CONFIG FUT-CONFIG FUTure Custom Logic |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-24 | 2017-02-24 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054166 | Yes | No | No | Australia | Australia | 03-Design/Build | BPC_07-CONFIG FUT-Define Business Process Flows |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-24 | 2017-02-24 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054167 | Yes | No | No | Australia | Australia | 03-Design/Build | BPC_08-CONFIG FUT-Reporting |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-24 | 2017-02-24 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054168 | Yes | No | No | Australia | Australia | 03-Design/Build | BPC_01-CONFIG-Create BPC Backend Objects |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-17 | 2017-01-17 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054169 | Yes | No | No | Australia | Australia | 03-Design/Build | IO_03-CONFIG-Internal Order Actual Postings |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054170 | Yes | No | No | Australia | Australia | 03-Design/Build | IO_04-CONFIG-Internal Orders as Investment Measures |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054171 | Yes | No | No | Australia | Australia | 03-Design/Build | AA_04-CONFIG FUT-Depreciation |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-01 | 2017-03-01 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054172 | Yes | No | No | Australia | Australia | 03-Design/Build | AA_05-CONFIG FUT-Master Data |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-22 | 2017-02-22 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054173 | Yes | No | No | Australia | Australia | 03-Design/Build | AR_08-CONFIG-FI-AR-Special GL |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054174 | Yes | No | No | Australia | Australia | 03-Design/Build | BNK_02-CONFIG-FI-Check Deposit |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054175 | Yes | No | No | Australia | Australia | 03-Design/Build | BNK_03-CONFIG-FI-BNK-Lockbox |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054176 | Yes | No | No | Australia | Australia | 03-Design/Build | BNK_04-CONFIG-Manual Bank Statement |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054177 | Yes | No | No | Australia | Australia | 03-Design/Build | DM_01-CONFIG-FSCM-CM-Dispute Case Processing |  | Missing Stream |  |  | _GD_RTR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054178 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Management (Cutover/Go-live) |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054179 | Yes | No | No | Australia | Australia | 03-Design/Build | TM_09-CONFIG FUT-Outbound Integration of ERP Shipments (TM-planned; ECC/EWM-executed) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054180 | Yes | No | No | Australia | Australia | 03-Design/Build | TM_10-CONFIG FUT-Inbound Integration of ERP Shipments (ECC-planned;TM-charge calculation) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054181 | Yes | No | No | Australia | Australia | 03-Design/Build | TM_03-CONFIG FUT-Master Data Transfer ECC to TM (Activate Integration Models) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-21 | 2017-02-21 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054182 | Yes | No | No | Australia | Australia | 03-Design/Build | CONFIG FUT-MM Organization Structure |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054183 | Yes | No | No | Australia | Australia | 03-Design/Build | TM_01-CONFIG FUT-Basic Settings in SAP TM / ECC |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054184 | Yes | No | No | Australia | Australia | 03-Design/Build | TM_05-CONFIG FUT-Configuration Settings for Order and Delivery Integration |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054185 | Yes | No | No | Australia | Australia | 03-Design/Build | TM_06-CONFIG FUT-Maintain Output Determination for Sales Documents |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054186 | Yes | No | No | Australia | Australia | 03-Design/Build | TM_07-CONFIG FUT-Maintain Output Determination for Outbound Deliveries |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054187 | Yes | No | No | Australia | Australia | 03-Design/Build | TM_02-CONFIG FUT-General Customizing Settings in SAP TM |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054188 | Yes | No | No | Australia | Australia | 03-Design/Build | TM_08-CONFIG FUT-Maintain Output Determination for Inbound Deliveries |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054189 | Yes | No | No | Australia | Australia | 03-Design/Build | TM_11-CONFIG FUT-Configure SAP TM documents |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054190 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Management (Cutover/Go-live) |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054191 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054192 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054193 | Yes | No | No | Australia | Australia | 02-Analyze | RTM (AN) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054194 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Create BPML (AN) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-20 | 2017-01-20 | No |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054195 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Log Gaps (AN) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-10 | 2016-11-10 | No |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054196 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Conduct Design Workshops (AN) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-28 | 2016-11-28 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054197 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Perform Gap Resolution (AN) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054198 | Yes | No | No | Australia | Australia | 03-Design/Build | PDD-Baseline (D/B) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054199 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-Baseline (D/B) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054200 | Yes | No | No | Australia | Australia | 03-Design/Build | FSD-Baseline (D/B) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054201 | Yes | No | No | Australia | Australia | 03-Design/Build | Support to Developpers (D/B) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054202 | Yes | No | No | Australia | Australia | 03-Design/Build | Config-Baseline (D/B) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054203 | Yes | No | No | Australia | Australia | 03-Design/Build | Support MDM (D/B) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054204 | Yes | No | No | Australia | Australia | 03-Design/Build | Contribute to Cut-over Planning (D/B) - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | No |  |  | ACT.FUN.Support Cutover plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054205 | Yes | No | No | Australia | Australia | 03-Design/Build | DEV FUT- Baseline(D/B) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054206 | Yes | No | No | Australia | Australia | 03-Design/Build | SDD Writing (D/B) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054207 | Yes | No | No | Australia | Australia | 03-Design/Build | CONFIG FUT-Baseline(D/B) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054208 | Yes | No | No | Australia | Australia | 04-Test | Regression - Run Tests - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054209 | Yes | No | No | Australia | Australia | 04-Test | Regression - Manage defects (Capex) - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054210 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Prepare - baseline - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-02 | 2017-06-02 | No |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054211 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - baseline - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-19 | 2017-06-19 | No |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054212 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Validate - baseline |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-19 | 2017-06-19 | No |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054213 | Yes | No | No | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | No |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054214 | Yes | No | No | Australia | Australia | 06-Hypercare | Manage Defects - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054215 | Yes | No | No | Australia | Australia | 06-Hypercare | Break/Fix - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054216 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Support |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-27 | 2017-03-27 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054217 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Validate |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054218 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Run Tests |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054219 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Manage Defects (Capex) |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054220 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Break/Fix - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054221 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Prepare |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054222 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Support |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-02-20 | 2017-02-20 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054223 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Validate |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-03 | 2017-03-03 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054224 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Run Tests - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054225 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Manage Defects (Capex) |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054226 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Break/Fix - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-22 | 2017-05-22 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054227 | Yes | No | No | Australia | Australia | 01-Preparation | Prepare KT) (PP) |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-10-03 | 2016-10-03 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054228 | Yes | No | No | Australia | Australia | 01-Preparation | Prepare KT) (PP) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-03 | 2016-10-03 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054229 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Conduct Design Workshops (AN) |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-28 | 2016-11-28 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054230 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Perform Gap Resolution (AN) |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054231 | Yes | No | No | Australia | Australia | 03-Design/Build | PDD-Baseline (D/B) |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054232 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-Baseline (D/B) |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054233 | Yes | No | No | Australia | Australia | 03-Design/Build | FSD-Baseline (D/B) |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054234 | Yes | No | No | Australia | Australia | 03-Design/Build | Support to Developpers (D/B) |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054235 | Yes | No | No | Australia | Australia | 03-Design/Build | DEV FUT- Baseline(D/B) |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054236 | Yes | No | No | Australia | Australia | 03-Design/Build | Config-Baseline (D/B) |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054237 | Yes | No | No | Australia | Australia | 03-Design/Build | SDD Writing (D/B) |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054238 | Yes | No | No | Australia | Australia | 03-Design/Build | Support MDM (D/B) |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054239 | Yes | No | No | Australia | Australia | 03-Design/Build | Contribute to Cut-over Planning (D/B) - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | No |  |  | ACT.FUN.Support Cutover plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054240 | Yes | No | No | Australia | Australia | 03-Design/Build | CONFIG FUT-Baseline(D/B) |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054241 | Yes | No | No | Australia | Australia | 02-Analyze | RTM (AN) |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054242 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Create BPML (AN) |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-20 | 2017-01-20 | No |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054243 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Log Gaps (AN) |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-10 | 2016-11-10 | No |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054244 | Yes | No | No | Australia | Australia | 04-Test | Management (Test) - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054245 | Yes | No | No | Australia | Australia | 04-Test | Management (Test) - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054246 | Yes | No | No | Australia | Australia | 04-Test | Documentation |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054247 | Yes | No | No | Australia | Australia | 02-Analyze | Kickoff (AN) |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054248 | Yes | No | No | Australia | Australia | 02-Analyze | Kickoff (AN) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054249 | Yes | No | No | Australia | Australia | 02-Analyze | Fit/Gaps Analysis (AN) |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054250 | Yes | No | No | Australia | Australia | 02-Analyze | Fit/Gaps Analysis (AN) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054251 | Yes | No | No | Australia | Australia | 02-Analyze | Management (AN) |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054252 | Yes | No | No | Australia | Australia | 02-Analyze | Management (AN) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054253 | Yes | No | No | Australia | Australia | 03-Design/Build | GTS_01-CONFIG-Global Trade Services - GTS Environment (out of scope) |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-02 | 2017-02-02 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054254 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Management (Cutover/Go-live) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054255 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-29 | 2017-04-29 | No |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054256 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-29 | 2017-04-29 | No |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054257 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054258 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054259 | Yes | No | No | Australia | Australia | 06-Hypercare | Management (Hypercare) - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.DEV.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054260 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Manage Defects (Capex) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054261 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Document work around |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054262 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-FSD-ECC/GTS to BSM Order (Transfer OTC) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054263 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-FSD-ECC/GTS to BSM Order (Transfer OTC) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054264 | Yes | No | No | Australia | Australia | 03-Design/Build | TM_04-CONFIG FUT-Master Data Setup in SAP TM |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-20 | 2017-02-20 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054265 | Yes | No | No | Australia | Australia | 03-Design/Build | TM_12-CONFIG FUT-Planning |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-16 | 2017-03-16 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054266 | Yes | No | No | Australia | Australia | 03-Design/Build | TM_13-CONFIG FUT-Freight Order Management |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054267 | Yes | No | No | Australia | Australia | 03-Design/Build | TM_15-CONFIG FUT-Configure Basic Settings for Charge Calculations (SAP TM) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054268 | Yes | No | No | Australia | Australia | 03-Design/Build | TM_16-CONFIG FUT-Freight Settlement |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054269 | Yes | No | No | Australia | Australia | 03-Design/Build | TM_17-CONFIG FUT-Configure Invoice Integration in SAP ECC |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054270 | Yes | No | No | Australia | Australia | 03-Design/Build | TM_19-CONFIG FUT-Custom Table (ECC) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-20 | 2017-02-20 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054271 | Yes | No | No | Australia | Australia | 03-Design/Build | TM_19-CONFIG-Custom Table (ECC) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054272 | Yes | No | No | Australia | Australia | 03-Design/Build | FLOG019-FSD-BOL + AQIS number |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-09 | 2017-02-09 | No |  |  | DELIV.FUN-204.Functional Specification - Form | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054273 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-FSD-Master BOL |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054274 | Yes | No | No | Australia | Australia | 03-Design/Build | FLOG020-FSD-Packing List |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-08 | 2017-02-08 | No |  |  | DELIV.FUN-204.Functional Specification - Form | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054275 | Yes | No | No | Australia | Australia | 03-Design/Build | ILOG009-FSD-EDI Outbound ASN sent to customers |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-20 | 2017-02-20 | No |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054276 | Yes | No | No | Australia | Australia | 03-Design/Build | ILOG008-FSD-ECC to BSM Delivery |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054277 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-FSD-ECC/GTS to BSM Order (Transfer OTC) |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054278 | Yes | No | No | Australia | Australia | 03-Design/Build | ILOG008-DEV FUT-ECC to BSM Delivery |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-05 | 2017-04-05 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054279 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-DEV FUT-ECC/GTS to BSM Order (Transfer OTC) |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054280 | Yes | No | No | Australia | Australia | 03-Design/Build | ILOG006-DEV FUT-EDI 3PL Pick Request |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054281 | Yes | No | No | Australia | Australia | 03-Design/Build | ILOG007-DEV FUT-EDI 3PL ASN |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-24 | 2017-03-24 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054282 | Yes | No | No | Australia | Australia | 03-Design/Build | ILOG011-DEV FUT-Lot Status Message to 3PL |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-06 | 2017-04-06 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054283 | Yes | No | No | Australia | Australia | 03-Design/Build | FLOG019-DEV FUT-BOL + AQIS number |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-21 | 2017-03-21 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054284 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-DEV FUT-Master BOL |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054285 | Yes | No | No | Australia | Australia | 03-Design/Build | FLOG020-DEV FUT-Packing List |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054286 | Yes | No | No | Australia | Australia | 03-Design/Build | ILOG009-DEV FUT-EDI Outbound ASN sent to customers |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-24 | 2017-03-24 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054287 | Yes | No | No | Australia | Australia | 03-Design/Build | TM_04-CONFIG-Master Data Setup in SAP TM |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-04 | 2017-02-04 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054288 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-DEV FUT-ECC/GTS to BSM Order (Transfer OTC) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-02-20 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054289 | Yes | No | No | Australia | Australia | 03-Design/Build | CONFIG FUT-eWM_01-eWM |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054290 | Yes | No | No | Australia | Australia | 03-Design/Build | ILOG007-FSD-IEDI 3PL ASN |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054291 | Yes | No | No | Australia | Australia | 03-Design/Build | ILOG011-FSD-Lot Status Message to 3PL |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054292 | Yes | No | No | Australia | Australia | 03-Design/Build | ILOG006-FSD-EDI 3PL Pick Request |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054293 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Inbound Milk Receipt information |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054294 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Milk Swap between external partner |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054295 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Placeholder for TM Design issue |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054296 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Inbound Milk Receipt information |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054297 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Milk Swap between external partner |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054298 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Placeholder for TM Design issue |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054299 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Inbound Milk Receipt information |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054300 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Milk Swap between external partner |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054301 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Placeholde for TM Design issue |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054302 | Yes | No | No | Australia | Australia | 03-Design/Build | PDD-Process Freight Plan and Select Carrier(D/B) |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054303 | Yes | No | No | Australia | Australia | 03-Design/Build | CONFIG-TM_01-MM |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054304 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Inbound Milk Receipt information |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054305 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Milk Swap between external partner |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054306 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Placeholde for TM Design issue |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054307 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD163-Inventory Stock |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054308 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD249-GTS - Material to Tariff Numbers |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054309 | Yes | No | No | Australia | Australia | 04-Test | SIT1 Preparation (KT with Test Team) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-27 | 2017-03-27 | No |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054310 | Yes | No | No | Australia | Australia | 03-Design/Build | Management (D/B) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-20 | 2017-01-20 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054311 | Yes | No | No | Australia | Australia | 03-Design/Build | Management (D/B) |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-20 | 2017-01-20 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054312 | Yes | No | No | Australia | Australia | 04-Test | Documentation |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054313 | Yes | No | No | Australia | Australia | 04-Test | Data collection templates - explain and collect - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054314 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX_XX-CONFIG-AirFreight |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-10 | 2017-04-10 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054315 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX_XX-CONFIG FUT-AirFreight |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-10 | 2017-04-10 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054316 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX_XX-CONFIG FUT-AirFreight |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-10 | 2017-04-10 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054317 | Yes | No | No | Australia | Australia | 03-Design/Build | ILOG009-DEV FUT-EDI Outbound ASN sent to customers |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-24 | 2017-03-24 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054318 | Yes | No | No | Australia | Australia | 06-Hypercare | Management (Hypercare) - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.DEV.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054319 | Yes | No | No | Australia | Australia | 02-Analyze | eWM does not provide integration for control of vendor COA fucntioanlity. |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054320 | Yes | No | No | Australia | Australia | 02-Analyze | eWM does not provide integration for control of vendor COA fucntioanlity. |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054321 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Prep (Select Scenarios) (Saputo) - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.UAT Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054322 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Prep (Select Scenarios) (Saputo) - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.UAT Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054323 | Yes | No | No | Australia | Australia | 04-Test | Training Environment Population and Testing |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Training Environment Population and Testing | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054324 | Yes | No | No | Australia | Australia | 03-Design/Build | WPB Recordings (D/B) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.FUN-403.WPB Recordings | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054325 | Yes | No | No | Australia | Australia | 03-Design/Build | Support Operational Procedures (SOPs) (D/B) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.FUN-314.Support Operational Procedures (SOPs) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054326 | Yes | No | No | Australia | Australia | 03-Design/Build | Support Operational Procedures Inventory (D/B) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.FUN-214.Support Operational Procedures Inventory | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054327 | Yes | No | No | Australia | Australia | 03-Design/Build | Process Workarounds (D/B) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054328 | Yes | No | No | Australia | Australia | 02-Analyze | Business Process Master List (BPML) (AN) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054329 | Yes | No | No | Australia | Australia | 02-Analyze | Demo (AN) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | ACT.FUN.Solution Confirmation Prensentations and Demonstrations | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054330 | Yes | No | No | Australia | Australia | 02-Analyze | Process Documentation in BWL (AN) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | ACT.FUN.Process Documentation in BWL | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054331 | Yes | No | No | Australia | Australia | 01-Preparation | Requirements Traceability Matrix (RTM)) (PP) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054332 | Yes | No | No | Australia | Australia | 01-Preparation | Consolidated Workshop Schedule) (PP) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  | DELIV.FUN-101.Consolidated Workshop Schedule | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054333 | Yes | No | No | Australia | Australia |  | AUS - LOG KT |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054334 | Yes | No | No | Australia | Australia | 01-Preparation | Prepare Kick-off) (PP) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-29 | 2016-10-29 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054335 | Yes | No | No | Australia | Australia | 01-Preparation | Conduct kick-off in Australia) (PP) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054336 | Yes | No | No | Australia | Australia | 01-Preparation | Conduct KT sessions) (PP) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | No |  |  | WP.FUN.Requirements/Process Design Workshop Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054337 | Yes | No | No | Australia | Australia | 01-Preparation | Worshop Preparation Decks) (PP) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | No |  |  | WP.FUN-107.Workshop Preparation Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054338 | Yes | No | No | Australia | Australia | 01-Preparation | Business Process Master List (BPML)) (PP) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054339 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Prepare |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054340 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Prepare |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054341 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Support |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-27 | 2017-03-27 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054342 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Validate |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054343 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Run Tests |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054344 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Manage Defects (Capex) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054345 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Break/Fix - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054346 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Prepare |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054347 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Support |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-02-20 | 2017-02-20 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054348 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Validate |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-03 | 2017-03-03 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054349 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Run Tests - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054350 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Manage Defects (Capex) |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054351 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Break/Fix - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-22 | 2017-05-22 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054352 | Yes | No | No | Australia | Australia | 04-Test | Regression - Run Tests - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054353 | Yes | No | No | Australia | Australia | 04-Test | Regression - Manage defects (Capex) - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054354 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - LOG |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054355 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054356 | Yes | No | No | Australia | Australia | 03-Design/Build | eWM_01-eWM - Out of scope |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054357 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Prepare - baseline - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-02 | 2017-06-02 | No |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054358 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - baseline - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-19 | 2017-06-19 | No |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054359 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Validate - baseline |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-19 | 2017-06-19 | No |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054360 | Yes | No | No | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | No |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054361 | Yes | No | No | Australia | Australia | 06-Hypercare | Manage Defects - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-17 | 2017-07-17 | No |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054362 | Yes | No | No | Australia | Australia | 06-Hypercare | Break/Fix - LOG |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054363 | Yes | No | No | Australia | Australia |  | AUS - PTP KT |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-07-06 | 2016-07-06 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054364 | Yes | No | No | Australia | Australia | 04-Test | Regression - Manage defects (Capex) - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054365 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Prep |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.UAT Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054366 | Yes | No | No | Australia | Australia | 03-Design/Build | Process Workarounds (D/B) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054367 | Yes | No | No | Australia | Australia | 03-Design/Build | Support Operational Procedures (SOPs) (D/B) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.FUN-314.Support Operational Procedures (SOPs) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054368 | Yes | No | No | Australia | Australia | 03-Design/Build | Support Operational Procedures Inventory (D/B) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.FUN-214.Support Operational Procedures Inventory | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054369 | Yes | No | No | Australia | Australia | 04-Test | Training Environment Population and Testing |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Training Environment Population and Testing | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054370 | Yes | No | No | Australia | Australia | 01-Preparation | Business Process Master List (BPML)) (PP) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054371 | Yes | No | No | Australia | Australia | 01-Preparation | Requirements Traceability Matrix (RTM)) (PP) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054372 | Yes | No | No | Australia | Australia | 01-Preparation | Consolidated Workshop Schedule) (PP) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  | DELIV.FUN-101.Consolidated Workshop Schedule | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054373 | Yes | No | No | Australia | Australia | 02-Analyze | Business Process Master List (BPML) (AN) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054374 | Yes | No | No | Australia | Australia | 02-Analyze | Demo (AN) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | ACT.FUN.Solution Confirmation Prensentations and Demonstrations | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054375 | Yes | No | No | Australia | Australia | 02-Analyze | Process Documentation in BWL |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | ACT.FUN.Process Documentation in BWL | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054376 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Document work around |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054377 | Yes | No | No | Australia | Australia | 06-Hypercare | Management (Hypercare) - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.DEV.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054378 | Yes | No | No | Australia | Australia | 04-Test | Documentation |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-27 | 2017-03-27 | No |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054379 | Yes | No | No | Australia | Australia | 04-Test | Management (Test) - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054380 | Yes | No | No | Australia | Australia | 04-Test | Regression - Run Tests - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054381 | Yes | No | No | Australia | Australia | 04-Test | SIT1 Preparation |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | No |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054382 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD257-MCP - Processes |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054383 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD258-MCP - Payment |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054384 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD259-MCP - Codes if needed |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054385 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD260-MCP - Extended material master and or payment attibutes |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054386 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD261-MCP -Product Assigment |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054387 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD262-Material Type ZRET - Returnable packaging |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054388 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GDXXX-Material Type ZMPN- Manufacturer Part Number |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054389 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD074-Material Master classification |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054390 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD074-Material Master classification |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054391 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD075-Material Master characteristics |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054392 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD075-Material Master characteristics |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054393 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD069-Material Type ZMAS - Maintenance Assemblies |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054394 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD069-Material Type ZMAS - Maintenance Assemblies |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054395 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Australia Pricing routine Incentives/Premiums 3 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054396 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Australia Pricing routine Incentives/Premiums 4 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054397 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Australia Pricing routine Incentives/Premiums 5 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054398 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Australia Pricing routine Incentives/Premiums 6 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054399 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Australia Pricing routine Incentives/Premiums 7 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054400 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Australia Pricing routine Surcharge 1 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054401 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Australia Pricing routine Surcharge 2 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054402 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Australia Pricing routine Surcharge 3 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054403 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-MinAgri 1- XML with liters detail (milk delivery) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054404 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-MinAgri 2- XML with analysis request (was consolidated with MinAgri1) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054405 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-MinAgri 3- XML with analysis results (was consolidated with MinAgri1) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054406 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Import XML from agriculture agency system (Was consolidated with MinAgri1) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054407 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Pricing routine 1 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054408 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Pricing routine 2 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054409 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Pricing routine 3 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054410 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Pricing routine 4 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054411 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Pricing routine 5 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054412 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Pricing routine 6 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054413 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Australia Pricing routine Quality |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054414 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Australia Pricing routine Incentives/Premiums 1 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054415 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-FSD-Australia Pricing routine Incentives/Premiums 2 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054416 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Argentina Pricing routine 1 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054417 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Argentina Pricing routine 2 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054418 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Argentina Pricing routine 3 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054419 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Argentina Pricing routine 4 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054420 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Argentina Pricing routine 5 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054421 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Argentina Pricing routine 6 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054422 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Australia Pricing routine Quality |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054423 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Australia Pricing routine Incentives/Premiums 1 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054424 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Australia Pricing routine Incentives/Premiums 2 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054425 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Australia Pricing routine Incentives/Premiums 3 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054426 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Australia Pricing routine Incentives/Premiums 4 |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054427 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Australia Pricing routine Incentives/Premiums 5 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054428 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Australia Pricing routine Incentives/Premiums 6 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054429 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Australia Pricing routine Incentives/Premiums 7 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054430 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Australia Pricing routine Surcharge 1 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054431 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Australia Pricing routine Surcharge 2 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054432 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Australia Pricing routine Surcharge 3 |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054433 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-MinAgri 1- XML with liters detail (milk delivery) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-31 | 2017-03-31 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054434 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-MinAgri 2- XML with analysis request (was consolidated with MinAgri1) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-31 | 2017-03-31 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054435 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-MinAgri 3- XML with analysis results (was consolidated with MinAgri1) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-31 | 2017-03-31 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054436 | Yes | No | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Import XML from agriculture agency system (Was consolidated with MinAgri1) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-31 | 2017-03-31 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054437 | Yes | No | No | Australia | Australia | 03-Design/Build | PDD-Manage Milk Swap Processes |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054438 | Yes | No | No | Australia | Australia | 03-Design/Build | MM_02_CONFIG-MM Master Data |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-04 | 2017-02-04 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054439 | Yes | No | No | Australia | Australia | 02-Analyze | Management (AN) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054440 | Yes | No | No | Australia | Australia | 02-Analyze | Kickoff (AN) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054441 | Yes | No | No | Australia | Australia | 02-Analyze | Fit/Gaps Analysis (AN) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | No |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054442 | Yes | No | No | Australia | Australia | 02-Analyze | Fit/Gaps Analysis (AN) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | No |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054443 | Yes | No | No | Australia | Australia | 02-Analyze | Kickoff (AN) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054444 | Yes | No | No | Australia | Australia | 02-Analyze | Management (AN) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054445 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Management (Cutover/Go-live) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-07 | 2017-06-07 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054446 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054447 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054448 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054449 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Prep |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.UAT Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054450 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054451 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Manage Defects (Capex) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054452 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Prepare - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | No |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054453 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | No |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054454 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Validate |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | No |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054455 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054456 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Document work around |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054457 | Yes | No | No | Australia | Australia | 03-Design/Build | FPTP004-FSD-Localise PO output (form) and T&C |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-01 | 2017-02-01 | No |  |  | DELIV.FUN-204.Functional Specification - Form | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054458 | Yes | No | No | Australia | Australia | 06-Hypercare | Management (Hypercare) - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.DEV.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054459 | Yes | No | No | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054460 | Yes | No | No | Australia | Australia | 06-Hypercare | Manage Defects - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | No |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054461 | Yes | No | No | Australia | Australia | 06-Hypercare | Break/Fix - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-04 | 2017-07-04 | No |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054462 | Yes | No | No | Australia | Australia | 03-Design/Build | Management (D/B) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054463 | Yes | No | No | Australia | Australia | 04-Test | Documentation |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-27 | 2017-03-27 | No |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054464 | Yes | No | No | Australia | Australia | 04-Test | Management (Test) - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054465 | Yes | No | No | Australia | Australia | 04-Test | Regression - Run Tests - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054466 | Yes | No | No | Australia | Australia | 04-Test | Regression - Manage defects (Capex) - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054467 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Prepare |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054468 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Support |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054469 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Validate |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-04-07 | 2017-04-07 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054470 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Run Tests |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054471 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Manage Defects (Capex) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054472 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Break/Fix - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054473 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Prepare |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054474 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Support |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-02-20 | 2017-02-20 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054475 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Validate |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-03 | 2017-03-03 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054476 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Run Tests - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054477 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Manage Defects (Capex) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054478 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Break/Fix - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054479 | Yes | No | No | Australia | Australia | 02-Analyze | RTM (AN) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-26 | 2016-10-26 | No |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054480 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Create BPML (AN) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-03 | 2016-11-03 | No |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054481 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Log Gaps (AN) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | No |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054482 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Conduct Design Workshops (AN) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054483 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Perform Gap Resolution (AN) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-15 | 2016-12-15 | No |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054484 | Yes | No | No | Australia | Australia | 03-Design/Build | PDD-Baseline (D/B) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | No |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054485 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-Baseline (D/B) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054486 | Yes | No | No | Australia | Australia | 03-Design/Build | FSD-Baseline (D/B) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054487 | Yes | No | No | Australia | Australia | 03-Design/Build | Support to Developpers (D/B) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054488 | Yes | No | No | Australia | Australia | 03-Design/Build | DEV FUT- Baseline (D/B) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054489 | Yes | No | No | Australia | Australia | 03-Design/Build | CONFIG-Baseline (D/B) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054490 | Yes | No | No | Australia | Australia | 03-Design/Build | SDD Writing (D/B) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-27 | 2017-01-27 | No |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054491 | Yes | No | No | Australia | Australia | 03-Design/Build | CONFIG FUT-Baseline (D/B) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054492 | Yes | No | No | Australia | Australia | 03-Design/Build | Support MDM (D/B) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054493 | Yes | No | No | Australia | Australia | 03-Design/Build | Contribute to Cut-over Planning (D/B) - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Support Cutover plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054494 | Yes | No | No | Australia | Australia | 01-Preparation | Prepare KT) (PP) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054495 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Validate |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-03 | 2017-03-03 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054496 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Run Tests - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054497 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Manage Defects (Capex) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054498 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Break/Fix - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054499 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Prepare |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054500 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Support |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054501 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Validate |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-04-07 | 2017-04-07 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054502 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Run Tests |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054503 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Manage Defects (Capex) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054504 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Break/Fix - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054505 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Prepare |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054506 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Support |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-02-20 | 2017-02-20 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054507 | Yes | No | No | Australia | Australia | 01-Preparation | Prepare KT) (PP) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054508 | Yes | No | No | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054509 | Yes | No | No | Australia | Australia | 06-Hypercare | Manage Defects - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-31 | 2017-07-31 | No |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054510 | Yes | No | No | Australia | Australia | 06-Hypercare | Break/Fix - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-04 | 2017-07-04 | No |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054511 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054512 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054513 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054514 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054515 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Manage Defects (Capex) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054516 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054517 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Prepare - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | No |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054518 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - PTP |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | No |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054519 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Validate |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | No |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054520 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054521 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054522 | Yes | No | No | Australia | Australia | 02-Analyze | RTM (AN) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-26 | 2016-10-26 | No |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054523 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Create BPML (AN) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-03 | 2016-11-03 | No |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054524 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Log Gaps (AN) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | No |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054525 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Conduct Design Workshops (AN) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-14 | 2016-11-14 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054526 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Perform Gap Resolution (AN) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-15 | 2016-12-15 | No |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054527 | Yes | No | No | Australia | Australia | 03-Design/Build | PDD-Baseline (D/B) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | No |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054528 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-Baseline (D/B) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054529 | Yes | No | No | Australia | Australia | 03-Design/Build | FSD-Baseline (D/B) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054530 | Yes | No | No | Australia | Australia | 03-Design/Build | Support to Developpers (D/B) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054531 | Yes | No | No | Australia | Australia | 03-Design/Build | DEV FUT- Baseline (D/B) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054532 | Yes | No | No | Australia | Australia | 03-Design/Build | CONFIG-Baseline (D/B) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054533 | Yes | No | No | Australia | Australia | 03-Design/Build | SDD Writing (D/B) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-27 | 2017-01-27 | No |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054534 | Yes | No | No | Australia | Australia | 03-Design/Build | CONFIG FUT-Baseline (D/B) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054535 | Yes | No | No | Australia | Australia | 03-Design/Build | Support MDM (D/B) |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054536 | Yes | No | No | Australia | Australia | 03-Design/Build | Contribute to Cut-over Planning (D/B) - PTP |  | Missing Stream |  |  | _GD_PTP-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Support Cutover plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054537 | Yes | No | No | Australia | Australia | 03-Design/Build | FPTP004-DEV FUT-Localise PO output (form) and T&C |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054538 | Yes | No | No | Australia | Australia | 03-Design/Build | PDD-Execute Milk Supplier Portal |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054539 | Yes | No | No | Australia | Australia | 03-Design/Build | PDD-Manage Batch and Traceability |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054540 | Yes | No | No | Australia | Australia | 03-Design/Build | PDD-Manage Farm Settlement & Statements |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054541 | Yes | No | No | Australia | Australia | 03-Design/Build | PDD-Manage Milk Receiving Cockpit |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054542 | Yes | No | No | Australia | Australia | 03-Design/Build | PDD-Manage Milk Swap Processes |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054543 | Yes | No | No | Australia | Australia | 03-Design/Build | PDD-Manage Procurement for Milk & Equivalents |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054544 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Management (Cutover/Go-live) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-07 | 2017-06-07 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054545 | Yes | No | No | Australia | Australia | 03-Design/Build | Management (D/B) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054589 | Yes | No | No | Australia | Australia | 01-Preparation | Localized Business Process Master List (BPML)) (PP) |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-29 | 2016-10-29 | No |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054590 | Yes | No | No | Australia | Australia | 01-Preparation | _GD_PMO-Consultant |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-29 | 2016-10-29 | No |  |  | DELIV.PMO-001.Detailed Workplan (MSP) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054591 | Yes | No | No | Australia | Australia |  | Create Detailed Project Plans |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-22 | 2016-10-22 | No |  |  | ACT.PMO.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054592 | Yes | No | No | Australia | Australia |  | Manage Change Requests |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-22 | 2016-10-22 | No |  |  | ACT.PMO.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054593 | Yes | No | No | Australia | Australia | 01-Preparation | Site Assessment) (PP) |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-29 | 2016-10-29 | No |  |  | DELIV.FUN-029.Site Assessment | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054594 | Yes | No | No | Australia | Australia | 01-Preparation | Requirements Traceability Matrix -- Consolidated) (PP) |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-29 | 2016-10-29 | No |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054595 | Yes | No | No | Australia | Australia | 01-Preparation | Resource Plan) (PP) |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-29 | 2016-10-29 | No |  |  | DELIV.PMO-099.Budget for Deployment | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054596 | Yes | No | No | Australia | Australia | 01-Preparation | Team Structure / Org Chart) (PP) |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-29 | 2016-10-29 | No |  |  | WP.PMO-005.Project Organizational Structure | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054597 | Yes | No | No | Australia | Australia | 01-Preparation | PMO Logs |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-29 | 2016-10-29 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054598 | Yes | No | No | Australia | Australia | 01-Preparation | Localization Questionnaire |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-29 | 2016-10-29 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054599 | Yes | No | No | Australia | Australia | 01-Preparation | Budget for Deployment) (PP) |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-29 | 2016-10-29 | No |  |  | DELIV.PMO-099.Budget for Deployment | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054600 | Yes | No | No | Australia | Australia | 01-Preparation | Localization Workshop Schedule |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-29 | 2016-10-29 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054601 | Yes | No | No | Australia | Australia | 01-Preparation | Project Charter) (PP) |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-29 | 2016-10-29 | No |  |  | DELIV.PMO-300.Project Charter | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054602 | Yes | No | No | Australia | Australia | 01-Preparation | Worshop Preparation Decks) (PP) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-10 | 2016-10-10 | No |  |  | WP.FUN-107.Workshop Preparation Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054603 | Yes | No | No | Australia | Australia | 01-Preparation | Prepare KT (Saputo)) (PP) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-09-19 | 2016-09-19 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054604 | Yes | No | No | Australia | Australia | 01-Preparation | Prepare KT (IBM)) (PP) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-09-19 | 2016-09-19 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054605 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Break/Fix - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054606 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Support |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054607 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Validate |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-04-10 | 2017-04-10 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054608 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Run Tests |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054609 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Manage Defects (Capex) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054610 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Break/Fix - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054611 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Prepare |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054612 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Support |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-02-20 | 2017-02-20 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054613 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Validate |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-03 | 2017-03-03 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054614 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Run Tests - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054615 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Manage Defects (Capex) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054616 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054617 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054618 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054619 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054620 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Manage Defects (Capex) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054621 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054622 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Prepare - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054623 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-19 | 2017-06-19 | No |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054624 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Validate |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-19 | 2017-06-19 | No |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054625 | Yes | No | No | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054626 | Yes | No | No | Australia | Australia | 06-Hypercare | Manage Defects - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054627 | Yes | No | No | Australia | Australia | 06-Hypercare | Break/Fix - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054628 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054629 | Yes | No | No | Australia | Australia | 02-Analyze | RTM (AN) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-05 | 2016-11-05 | No |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054630 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Create BPML (AN) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054631 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Log Gaps (AN) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-21 | 2016-11-21 | No |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054632 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Conduct Design Workshops (AN) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054633 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Perform Gap Resolution (AN) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054634 | Yes | No | No | Australia | Australia | 03-Design/Build | PDD-Baseline (D/B) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054635 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-Baseline (D/B) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054636 | Yes | No | No | Australia | Australia | 03-Design/Build | FSD-Baseline (D/B) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054637 | Yes | No | No | Australia | Australia | 03-Design/Build | Support to Developpers (D/B) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054638 | Yes | No | No | Australia | Australia | 03-Design/Build | DEV FUT- Baseline (D/B) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054639 | Yes | No | No | Australia | Australia | 03-Design/Build | CONFIG-Baseline (D/B) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054640 | Yes | No | No | Australia | Australia | 03-Design/Build | SDD Writing (D/B) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054641 | Yes | No | No | Australia | Australia | 03-Design/Build | CONFIG FUT-Baseline (D/B) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054642 | Yes | No | No | Australia | Australia | 03-Design/Build | Support MDM (D/B) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054643 | Yes | No | No | Australia | Australia | 03-Design/Build | Contribute to Cut-over Planning (D/B) - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Support Cutover plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054644 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD223-Batch Determination Condition Records (LE) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054645 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD243-Customer Master - Plants |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054646 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD223-Batch Determination Condition Records (LE) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054647 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Create BPML (AN) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054648 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Log Gaps (AN) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-21 | 2016-11-21 | No |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054649 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054650 | Yes | No | No | Australia | Australia | 02-Analyze | RTM (AN) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-05 | 2016-11-05 | No |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054651 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Conduct Design Workshops (AN) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054652 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Perform Gap Resolution (AN) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054653 | Yes | No | No | Australia | Australia | 03-Design/Build | PDD-Baseline (D/B) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054654 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-Baseline (D/B) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054655 | Yes | No | No | Australia | Australia | 03-Design/Build | FSD-Baseline (D/B) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054656 | Yes | No | No | Australia | Australia | 03-Design/Build | Support to Developpers (D/B) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054657 | Yes | No | No | Australia | Australia | 03-Design/Build | DEV FUT- Baseline (D/B) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054658 | Yes | No | No | Australia | Australia | 03-Design/Build | CONFIG-Baseline (D/B) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054659 | Yes | No | No | Australia | Australia | 03-Design/Build | SDD Writing (D/B) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054660 | Yes | No | No | Australia | Australia | 03-Design/Build | CONFIG FUT-Baseline (D/B) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054661 | Yes | No | No | Australia | Australia | 03-Design/Build | Support MDM (D/B) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054662 | Yes | No | No | Australia | Australia | 03-Design/Build | Contribute to Cut-over Planning (D/B) - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Support Cutover plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054663 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD128-Broker Determination |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054664 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD129-Sales Representatives |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054665 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD146-Pricing - List Price |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054666 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD147-Pricing - Truckload / Swell/ Pickup Allowance |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054667 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD148-Pricing - Deng, Royalty (Accrual) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054668 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD151-Pricing - Non-trade Accruals |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054669 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD152-Pricing - Sales Taxes (all levels) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054670 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD153-Pricing - Cust Specific |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054671 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD154-Pricing - Customer Freight (elements/add) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054672 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD158-All - Sales Reps and Broker Commission Agreements Rebates |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054673 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Management (Cutover/Go-live) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054674 | Yes | No | No | Australia | Australia | 03-Design/Build | IOTC007-FSD-EDI Outbound Order Response |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054675 | Yes | No | No | Australia | Australia | 03-Design/Build | IOTC009-FSD-EDI Outbound Invoice |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054676 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Management (Cutover/Go-live) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054677 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054678 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054679 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054680 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Prep |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.UAT Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054681 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054682 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Manage Defects (Capex) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054683 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054684 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Document work around |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054685 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Prepare - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054686 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-19 | 2017-06-19 | No |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054687 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Validate |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-19 | 2017-06-19 | No |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054688 | Yes | No | No | Australia | Australia | 06-Hypercare | Management (Hypercare) - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.DEV.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054689 | Yes | No | No | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054690 | Yes | No | No | Australia | Australia | 06-Hypercare | Manage Defects - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054691 | Yes | No | No | Australia | Australia | 06-Hypercare | Break/Fix - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054692 | Yes | No | No | Australia | Australia | 03-Design/Build | Management (D/B) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054693 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Prepare |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054694 | Yes | No | No | Australia | Australia | 04-Test | Documentation |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054695 | Yes | No | No | Australia | Australia | 04-Test | Management (Test) - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054696 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Prepare |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054697 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Support |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054698 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Validate |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-04-10 | 2017-04-10 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054699 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Run Tests |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054700 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Manage Defects (Capex) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054701 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Break/Fix - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054702 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Prepare |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054703 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Support |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-02-20 | 2017-02-20 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054704 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Validate |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-03 | 2017-03-03 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054705 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Run Tests - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054706 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Manage Defects (Capex) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054707 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Break/Fix - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054708 | Yes | No | No | Australia | Australia | 04-Test | Regression - Run Tests - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054709 | Yes | No | No | Australia | Australia | 04-Test | Regression - Manage defects (Capex) - OTC |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054710 | Yes | No | No | Australia | Australia | 02-Analyze | Kickoff (AN) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054711 | Yes | No | No | Australia | Australia | 02-Analyze | Management (AN) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054712 | Yes | No | No | Australia | Australia | 02-Analyze | Kickoff (AN) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054713 | Yes | No | No | Australia | Australia | 02-Analyze | Management (AN) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054714 | Yes | No | No | Australia | Australia | 02-Analyze | Fit/Gaps Analysis (AN) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054715 | Yes | No | No | Australia | Australia | 02-Analyze | Fit/Gaps Analysis (AN) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054716 | Yes | No | No | Australia | Australia | 03-Design/Build | IOTC006-FSD-EDI Inbound Sales Order |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054717 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-FSD-Placeholderx |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054718 | Yes | No | No | Australia | Australia | 03-Design/Build | FOTC002-FSD-Domestic Tax Invoice form |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | DELIV.FUN-204.Functional Specification - Form | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054719 | Yes | No | No | Australia | Australia | 03-Design/Build | IOTC008-FSD-ECC/GTS to BSM Order |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054720 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-FSD-Rebates selement report |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-10 | 2017-02-10 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054721 | Yes | No | No | Australia | Australia | 03-Design/Build | FOTC007-FSD-Order acknowledgement form - domestic |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | DELIV.FUN-204.Functional Specification - Form | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054722 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-FSD-Order acknowledgement form - export |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054723 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-FSD-Placeholderx |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054724 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-DEV FUT-Placeholderx |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-10 | 2017-02-10 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054725 | Yes | No | No | Australia | Australia | 03-Design/Build | IOTC006-DEV FUT-EDI Inbound Sales Order |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054726 | Yes | No | No | Australia | Australia | 03-Design/Build | IOTC007-DEV FUT-EDI Outbound Order Response |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-10 | 2017-04-10 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054727 | Yes | No | No | Australia | Australia | 03-Design/Build | IOTC009-DEV FUT-EDI Outbound Invoice |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-31 | 2017-03-31 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054728 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-DEV FUT-Order acknowledgement form - export |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-21 | 2017-03-21 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054729 | Yes | No | No | Australia | Australia | 03-Design/Build | FOTC002-DEV FUT-Domestic Tax Invoice form |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-28 | 2017-03-28 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054730 | Yes | No | No | Australia | Australia | 03-Design/Build | IOTC008-DEV FUT-ECC/GTS to BSM Order |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054731 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-DEV FUT-Rebates selement report |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054732 | Yes | No | No | Australia | Australia | 03-Design/Build | FOTC007-DEV FUT-Order acknowledgement form - domestic |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-27 | 2017-03-27 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054733 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-DEV FUT-Placeholderx |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054734 | Yes | No | No | Australia | Australia | 03-Design/Build | PDD-Process Milk Sales Order and Swaps |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054735 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-DEV FUT-Order acknowledgement form - export |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-21 | 2017-03-21 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054736 | Yes | No | No | Australia | Australia | 06-Hypercare | Management (Hypercare) - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.DEV.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054737 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Document work around |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054738 | Yes | No | No | Australia | Australia | 03-Design/Build | Management (D/B) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054739 | Yes | No | No | Australia | Australia | 04-Test | Documentation |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054740 | Yes | No | No | Australia | Australia | 04-Test | Management (Test) - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054741 | Yes | No | No | Australia | Australia | 04-Test | SIT1 Preparation |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | No |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054742 | Yes | No | No | Australia | Australia | 01-Preparation | Conduct KT sessions) (PP) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-28 | 2016-10-28 | No |  |  | WP.FUN.Requirements/Process Design Workshop Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054743 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD249-Material Master Sales Org 1 Tax |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-24 | 2017-02-24 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054744 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD136-Customer master visit control, geo coding, paym.methods |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054745 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD136-Customer master visit control, geo coding, paym.methods |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054746 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD243-Customer Master - Plants |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054747 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD254-EDI Partner Table (Add EDPAR ) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054748 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD254-EDI Partner Table (Add EDPAR ) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054749 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD255-Assignment of EDI Partner by Sales Org (Add EDSDC) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054750 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD255-Assignment of EDI Partner by Sales Org (Add EDSDC) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054751 | Yes | No | No | Australia | Australia | 02-Analyze | AUS Deep Dive Order to Cash Process Flow (with EDI and 3PLs) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-25 | 2017-01-25 | No |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054752 | Yes | No | No | Australia | Australia | 02-Analyze | AUS Deep Dive Order to Cash Process Flow (with EDI and 3PLs) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-25 | 2017-01-25 | No |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054753 | Yes | No | No | Australia | Australia | 02-Analyze | AUS Deep Dive: One Customer |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-24 | 2017-01-24 | No |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054754 | Yes | No | No | Australia | Australia | 02-Analyze | AUS Deep Dive: One Customer |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-24 | 2017-01-24 | No |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054755 | Yes | No | No | Australia | Australia | 02-Analyze | AUS Deep Dive: Export Process considering BSM In Scope |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-24 | 2017-01-24 | No |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054756 | Yes | No | No | Australia | Australia | 02-Analyze | AUS Deep Dive: Export Process considering BSM In Scope |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-24 | 2017-01-24 | No |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054757 | Yes | No | No | Australia | Australia | 02-Analyze | AUS Deep Dive: Batch Determination |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-24 | 2017-01-24 | No |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054758 | Yes | No | No | Australia | Australia | 02-Analyze | AUS Deep Dive: Batch Determination |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-24 | 2017-01-24 | No |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054759 | Yes | No | No | Australia | Australia | 02-Analyze | AUS Deep Dive: Trade ECC Rebates & Commissions |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-25 | 2017-01-25 | No |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054760 | Yes | No | No | Australia | Australia | 02-Analyze | AUS Deep Dive: Trade ECC Rebates & Commissions |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-25 | 2017-01-25 | No |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054761 | Yes | No | No | Australia | Australia | 02-Analyze | AUS: GOI Joint Venture |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-25 | 2017-01-25 | No |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054762 | Yes | No | No | Australia | Australia | 02-Analyze | AUS: Sell-Through Process |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | No |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054763 | Yes | No | No | Australia | Australia | 02-Analyze | AUS Deep Dive on Pricing upload program |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | No |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054764 | Yes | No | No | Australia | Australia | 02-Analyze | AUS Deep Dive on Pricing upload program |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | No |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054765 | Yes | No | No | Australia | Australia | 02-Analyze | AUS Deep Dive for Master Data (Customer and Material Master) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | No |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054766 | Yes | No | No | Australia | Australia | 02-Analyze | AUS Deep Dive for Master Data (Customer and Material Master) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | No |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054767 | Yes | No | No | Australia | Australia | 02-Analyze | AUS Deep Dive for Billing Corrections |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | No |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054768 | Yes | No | No | Australia | Australia | 01-Preparation | Prepare Kick-off) (PP) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-03 | 2016-10-03 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054769 | Yes | No | No | Australia | Australia | 01-Preparation | Conduct kick-off in Australia) (PP) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054770 | Yes | No | No | Australia | Australia |  | AUS - OTC KT |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054771 | Yes | No | No | Australia | Australia | 02-Analyze | Business Process Master List (BPML) (AN) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054772 | Yes | No | No | Australia | Australia | 02-Analyze | Demo (AN) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | ACT.FUN.Solution Confirmation Prensentations and Demonstrations | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054773 | Yes | No | No | Australia | Australia | 02-Analyze | Process Documentation in BWL (AN) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | ACT.FUN.Process Documentation in BWL | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054774 | Yes | No | No | Australia | Australia | 03-Design/Build | Process Workarounds(D/B) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054775 | Yes | No | No | Australia | Australia | 03-Design/Build | WPB Recordings (D/B) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.FUN-403.WPB Recordings | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054776 | Yes | No | No | Australia | Australia | 03-Design/Build | Support Operational Procedures (SOPs) (D/B) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.FUN-314.Support Operational Procedures (SOPs) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054777 | Yes | No | No | Australia | Australia | 03-Design/Build | Support Operational Procedures Inventory(D/B) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.FUN-214.Support Operational Procedures Inventory | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054778 | Yes | No | No | Australia | Australia | 04-Test | Training Environment Population and Testing |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Training Environment Population and Testing | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054779 | Yes | No | No | Australia | Australia | 01-Preparation | Business Process Master List (BPML)) (PP) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054780 | Yes | No | No | Australia | Australia | 01-Preparation | Requirements Traceability Matrix (RTM)) (PP) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054781 | Yes | No | No | Australia | Australia | 01-Preparation | Consolidated Workshop Schedule) (PP) |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  | DELIV.FUN-101.Consolidated Workshop Schedule | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054782 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD123-Customer Master - Buying Groups |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054783 | Yes | No | No | Australia | Australia | 04-Test | Regression - Run Tests - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054784 | Yes | No | No | Australia | Australia | 04-Test | Regression - Manage defects (Capex) - OTC |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054785 | Yes | No | No | Australia | Australia | 02-Analyze | AUS: Reporting (ECC vs. BI) |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | No |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054786 | Yes | No | No | Australia | Australia | 02-Analyze | AUS Deep Dive for freight |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-25 | 2017-01-25 | No |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054787 | Yes | No | No | Australia | Australia | 02-Analyze | AUS Deep Dive for freight |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-25 | 2017-01-25 | No |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054788 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Prep |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.UAT Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054789 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Prep |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.UAT Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054790 | Yes | No | No | Australia | Australia | 04-Test | Regression - Run Tests - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054791 | Yes | No | No | Australia | Australia | 04-Test | Regression - Manage defects (Capex) - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054792 | Yes | No | No | Australia | Australia | 01-Preparation | Business Process Master List (BPML)) (PP) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054793 | Yes | No | No | Australia | Australia | 01-Preparation | Requirements Traceability Matrix (RTM)) (PP) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054794 | Yes | No | No | Australia | Australia | 01-Preparation | Consolidated Workshop Schedule) (PP) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  | DELIV.FUN-101.Consolidated Workshop Schedule | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054795 | Yes | No | No | Australia | Australia | 04-Test | Training Environment Population and Testing |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Training Environment Population and Testing | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054796 | Yes | No | No | Australia | Australia | 03-Design/Build | Process Workarounds (D/B) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054797 | Yes | No | No | Australia | Australia | 03-Design/Build | WPB Recordings (D/B) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.FUN-403.WPB Recordings | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054798 | Yes | No | No | Australia | Australia | 03-Design/Build | Support Operational Procedures (SOPs) (D/B) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.FUN-314.Support Operational Procedures (SOPs) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054799 | Yes | No | No | Australia | Australia | 03-Design/Build | Support Operational Procedures Inventory (D/B) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.FUN-214.Support Operational Procedures Inventory | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054800 | Yes | No | No | Australia | Australia | 02-Analyze | Business Process Master List (BPML) (AN) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054801 | Yes | No | No | Australia | Australia | 02-Analyze | Demo (AN) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | ACT.FUN.Solution Confirmation Prensentations and Demonstrations | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054802 | Yes | No | No | Australia | Australia | 02-Analyze | Process Documentation in BWL (AN) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | ACT.FUN.Process Documentation in BWL | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054803 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD238-DMS - Extended material master attibutes |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054804 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD239-DMS - Workstations |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054805 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD240-DMS - Product groups assignments |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054806 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD241-DMS - Record types |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-20 | 2017-02-20 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054807 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD242-DMS - Tours |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054808 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD250-Dynamic Modification Rules |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054809 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD250-Dynamic Modification Rules |  | Missing Stream |  |  | _GD_OTC-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054810 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD251-Sampling Drawing Procedures |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-01 | 2017-02-01 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054811 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD252-QM - Master Inspection Characteristic: Inspection Method Assignment Update |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-02 | 2017-02-02 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054812 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD253-QM - Certificate Profile Custom Table maintenance (ZPTP_COA_CUSTOM) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-03 | 2017-02-03 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054813 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD247-Condition record for output determination(VV21) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054814 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD248-Certificate Profiles creation and Assignment (transactions QC01&QC15) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-31 | 2017-01-31 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054815 | Yes | No | No | Australia | Australia | 04-Test | SIT1 Preparation |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-07 | 2017-03-07 | No |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054816 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Perform Gap Resolution (AN) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054817 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Document work around |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054818 | Yes | No | No | Australia | Australia | 04-Test | Documentation |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054819 | Yes | No | No | Australia | Australia | 04-Test | Management (Test) - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-14 | 2017-03-14 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054820 | Yes | No | No | Australia | Australia | 06-Hypercare | Management (Hypercare) - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | No |  |  | ACT.DEV.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054821 | Yes | No | No | Australia | Australia | 03-Design/Build | DM_01-CONFIG-Advanced Planning & Optimization (BW) |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054822 | Yes | No | No | Australia | Australia | 03-Design/Build | PDD-Manage Milk Balancing and Planning |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | No |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054823 | Yes | No | No | Australia | Australia | 03-Design/Build | DMS_01-CONFIG-Dairy Mgmt System - Cross Functional |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-26 | 2017-01-26 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054824 | Yes | No | No | Australia | Australia | 03-Design/Build | DMS_02-CONFIG-Dairy Mgmt System - Planning |  | Missing Stream |  |  | _GD_RTR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054825 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-DEV FUT-MTS to MII |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-16 | 2017-05-16 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054826 | Yes | No | No | Australia | Australia | 03-Design/Build | EPTM019-DEV FUT-DTS |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-02 | 2017-05-02 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054827 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-FSD-MTS to MII |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054828 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-FSD-Inventory count w/ Bin Location - Out of scope |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054829 | Yes | No | No | Australia | Australia | 03-Design/Build | PP_05-CONFIG-Catch weight - Tolerance Group |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054830 | Yes | No | No | Australia | Australia | 03-Design/Build | EPTM018-DEV FUT-Chemical analysis machines |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054831 | Yes | No | No | Australia | Australia | 03-Design/Build | FPTP003-DEV FUT-GOI Customer COA form |  | Missing Stream |  |  | _GD_OTC-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-12 | 2017-05-12 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054832 | Yes | No | No | Australia | Australia | 03-Design/Build | PP_05-CONFIG FUT-Catch weight - Tolerance Group |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-26 | 2017-05-26 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054833 | Yes | No | No | Australia | Australia | 03-Design/Build | FPTM005-FSD-Raw material GI |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | DELIV.FUN-204.Functional Specification - Form | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054834 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-FSD-MTS to MII |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054835 | Yes | No | No | Australia | Australia | 03-Design/Build | FPTM004-FSD-Workorder picklist w/ Bin Location |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | DELIV.FUN-204.Functional Specification - Form | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054836 | Yes | No | No | Australia | Australia | 03-Design/Build | EPTM019-DEV FUT-DTS |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-02 | 2017-05-02 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054837 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-DEV FUT-Tabular results ( including 6506 ) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-06 | 2017-06-06 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054838 | Yes | No | No | Australia | Australia | 03-Design/Build | EPTM018-DEV FUT-Chemical analysis machines |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054839 | Yes | No | No | Australia | Australia | 03-Design/Build | FPTP003-DEV FUT-GOI Customer COA form |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-12 | 2017-05-12 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054840 | Yes | No | No | Australia | Australia | 03-Design/Build | FPTM005-DEV FUT-Raw material GI |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054841 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-DEV FUT-MTS to MII |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-16 | 2017-05-16 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054842 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-DEV FUT-Inventory count w/ Bin Location - Out of scope |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-18 | 2017-04-18 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054843 | Yes | No | No | Australia | Australia | 03-Design/Build | FPTM004-DEV FUT-Workorder picklist w/ Bin Location |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054844 | Yes | No | No | Australia | Australia | 03-Design/Build | EPTM019-FSD-DTS |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | DELIV.FUN-203.Functional Specification - Enhancement | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054845 | Yes | No | No | Australia | Australia | 03-Design/Build | XXX-FSD-Tabular results ( including 6506 ) |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | DELIV.FUN-203.Functional Specification - Enhancement | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054846 | Yes | No | No | Australia | Australia | 03-Design/Build | EPTM018-FSD-Chemical analysis machines |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | DELIV.FUN-203.Functional Specification - Enhancement | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054847 | Yes | No | No | Australia | Australia | 03-Design/Build | FPTP003-FSD-GOI Customer COA form |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | No |  |  | DELIV.FUN-204.Functional Specification - Form | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054848 | Yes | No | No | Australia | Australia | 02-Analyze | Management (AN) |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054849 | Yes | No | No | Australia | Australia | 02-Analyze | Kickoff (AN) |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054850 | Yes | No | No | Australia | Australia | 02-Analyze | Fit/Gaps Analysis (AN) |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-27 | 2016-10-27 | No |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054851 | Yes | No | No | Australia | Australia | 02-Analyze | Fit/Gaps Analysis (AN) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-27 | 2016-10-27 | No |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054852 | Yes | No | No | Australia | Australia | 02-Analyze | Kickoff (AN) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054853 | Yes | No | No | Australia | Australia | 02-Analyze | Management (AN) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054854 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD051-QM-Quality Information Records |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054855 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD053-QM-Recipes/Routings Additions |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054856 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD056-Batch Classifications |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-14 | 2017-03-14 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054857 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD057-Batch Characteristics |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054858 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD076-Batch Master Record |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054859 | Yes | No | No | Australia | Australia | 04-Test | Documentation |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054860 | Yes | No | No | Australia | Australia | 04-Test | Management (Test) - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-14 | 2017-03-14 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054861 | Yes | No | No | Australia | Australia | 04-Test | Regression - Run Tests - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054862 | Yes | No | No | Australia | Australia | 04-Test | Regression - Manage defects (Capex) - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054863 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Run Tests - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054864 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Manage Defects (Capex) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054865 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Break/Fix - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054866 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Prepare |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-27 | 2017-03-27 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054867 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Support |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-02-20 | 2017-02-20 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054868 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Validate |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-03 | 2017-03-03 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054869 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Run Tests |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054870 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Manage Defects (Capex) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054871 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Break/Fix - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054872 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Prepare |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054873 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Support |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054874 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Validate |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-09 | 2017-03-14 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054875 | Yes | No | No | Australia | Australia | 03-Design/Build | Management (D/B) - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054876 | Yes | No | No | Australia | Australia | 06-Hypercare | Management (Hypercare) - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | No |  |  | ACT.DEV.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054877 | Yes | No | No | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | No |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054878 | Yes | No | No | Australia | Australia | 06-Hypercare | Manage Defects - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054879 | Yes | No | No | Australia | Australia | 06-Hypercare | Break/Fix - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054880 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Management (Cutover/Go-live) - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054881 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054882 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054883 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054884 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Prep |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.UAT Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054885 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054886 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Manage Defects (Capex) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054887 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054888 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Document work around |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054889 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Prepare - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054890 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054891 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Validate |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | No |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054892 | Yes | No | No | Australia | Australia | 03-Design/Build | QM_01-CONFIG-Basic Settings |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-04 | 2017-02-04 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054893 | Yes | No | No | Australia | Australia | 03-Design/Build | QM_02-CONFIG-Quality Inspection |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-04 | 2017-02-04 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054894 | Yes | No | No | Australia | Australia | 03-Design/Build | QM_03-CONFIG-Sample Management |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-04 | 2017-02-04 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054895 | Yes | No | No | Australia | Australia | 03-Design/Build | QM_04-CONFIG-Results Recording |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-04 | 2017-02-04 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054896 | Yes | No | No | Australia | Australia | 03-Design/Build | QM_05-CONFIG-QM in Logistics |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-04 | 2017-02-04 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054897 | Yes | No | No | Australia | Australia | 03-Design/Build | QM_06-CONFIG-Quality Planning |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-04 | 2017-02-04 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054898 | Yes | No | No | Australia | Australia | 03-Design/Build | QM_07-CONFIG-Quality Certificates |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-04 | 2017-02-04 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054899 | Yes | No | No | Australia | Australia | 03-Design/Build | QM_08-CONFIG-Quality Notifications |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-04 | 2017-02-04 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054900 | Yes | No | No | Australia | Australia | 03-Design/Build | QM_09-CONFIG-Quality Control |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-04 | 2017-02-04 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054901 | Yes | No | No | Australia | Australia | 03-Design/Build | QM_10-CONFIG-General Activities |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-04 | 2017-02-04 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054902 | Yes | No | No | Australia | Australia | 03-Design/Build | QM_01-CONFIG FUT-Basic Settings |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054903 | Yes | No | No | Australia | Australia | 03-Design/Build | QM_02-CONFIG FUT-Quality Inspection |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054904 | Yes | No | No | Australia | Australia | 03-Design/Build | QM_03-CONFIG FUT-Sample Management |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054905 | Yes | No | No | Australia | Australia | 03-Design/Build | QM_04-CONFIG FUT-Results Recording |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054906 | Yes | No | No | Australia | Australia | 03-Design/Build | QM_05-CONFIG FUT-QM in Logistics |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-04 | 2017-02-04 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054907 | Yes | No | No | Australia | Australia | 03-Design/Build | QM_06-CONFIG FUT-Quality Planning |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-04 | 2017-02-04 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054908 | Yes | No | No | Australia | Australia | 03-Design/Build | QM_07-CONFIG FUT-Quality Certificates |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054909 | Yes | No | No | Australia | Australia | 03-Design/Build | QM_08-CONFIG FUT-Quality Notifications |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054910 | Yes | No | No | Australia | Australia | 03-Design/Build | QM_09-CONFIG FUT-Quality Control |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054911 | Yes | No | No | Australia | Australia | 03-Design/Build | QM_10-CONFIG FUT-General Activities |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054912 | Yes | No | No | Australia | Australia | 03-Design/Build | CIF­_01-CONFIG-Advanced Planning & Optimization (CIF) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054913 | Yes | No | No | Australia | Australia | 03-Design/Build | DP_04-CONFIG-Advanced Planning & Optimization (DP) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054914 | Yes | No | No | Australia | Australia | 03-Design/Build | GLO_01-CONFIG-Advanced Planning & Optimization (GLO) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054915 | Yes | No | No | Australia | Australia | 03-Design/Build | GLO_02-CONFIG-Advanced Planning & Optimization (GLO) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054916 | Yes | No | No | Australia | Australia | 03-Design/Build | PPDS_01- CONFIG-Advanced Planning & Optimization (PPDS) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054917 | Yes | No | No | Australia | Australia | 03-Design/Build | PPDS_02- CONFIG-Advanced Planning & Optimization (PPDS) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054918 | Yes | No | No | Australia | Australia | 03-Design/Build | PPDS_03- CONFIG-Advanced Planning & Optimization (PPDS) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054919 | Yes | No | No | Australia | Australia | 03-Design/Build | PPDS_04- CONFIG-Advanced Planning & Optimization (PPDS) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054920 | Yes | No | No | Australia | Australia | 03-Design/Build | SNP_01-CONFIG-Advanced Planning & Optimization (SNP) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054921 | Yes | No | No | Australia | Australia | 03-Design/Build | SNP_02-CONFIG-Advanced Planning & Optimization (SNP) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054922 | Yes | No | No | Australia | Australia | 03-Design/Build | SNP_03-CONFIG-Advanced Planning & Optimization (SNP) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054923 | Yes | No | No | Australia | Australia | 03-Design/Build | SNP_04-CONFIG-Advanced Planning & Optimization (SNP) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054924 | Yes | No | No | Australia | Australia | 03-Design/Build | CIF­_01-CONFIG FUT-Advanced Planning & Optimization (CIF) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054925 | Yes | No | No | Australia | Australia | 03-Design/Build | DMS_03-CONFIG FUT-Dairy Mgmt System - Operations |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054926 | Yes | No | No | Australia | Australia | 03-Design/Build | GLO_01-CONFIG FUT-Advanced Planning & Optimization (GLO) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054927 | Yes | No | No | Australia | Australia | 03-Design/Build | GLO_02-CONFIG FUT-Advanced Planning & Optimization (GLO) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054928 | Yes | No | No | Australia | Australia | 03-Design/Build | PPDS_01-CONFIG FUT-Advanced Planning & Optimization (PPDS) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054929 | Yes | No | No | Australia | Australia | 03-Design/Build | PPDS_02-CONFIG FUT-Advanced Planning & Optimization (PPDS) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054930 | Yes | No | No | Australia | Australia | 03-Design/Build | PPDS_03-CONFIG FUT-Advanced Planning & Optimization (PPDS) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054931 | Yes | No | No | Australia | Australia | 03-Design/Build | SPN_01-CONFIG FUT-Advanced Planning & Optimization (SNP) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054932 | Yes | No | No | Australia | Australia | 03-Design/Build | SPN_02-CONFIG FUT-Advanced Planning & Optimization (SNP) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054933 | Yes | No | No | Australia | Australia | 03-Design/Build | SPN_03-CONFIG FUT-Advanced Planning & Optimization (SNP) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054934 | Yes | No | No | Australia | Australia | 03-Design/Build | SPN_04-CONFIG FUT-Advanced Planning & Optimization (SNP) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054935 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Management (Cutover/Go-live) - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054936 | Yes | No | No | Australia | Australia | 03-Design/Build | Management (D/B) - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | No |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054937 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD250-Dynamic Modification Rules |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054938 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD250-Dynamic Modification Rules |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054939 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-26 | 2016-10-26 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054940 | Yes | No | No | Australia | Australia | 02-Analyze | RTM (AN) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-13 | 2016-11-13 | No |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054941 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Create BPML (AN) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | No |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054942 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Log Gaps (AN) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-15 | 2016-11-15 | No |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054943 | Yes | No | No | Australia | Australia | 03-Design/Build | PDD-Baseline |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054944 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-Baseline |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054945 | Yes | No | No | Australia | Australia | 03-Design/Build | FSD-Baseline (D/B) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054946 | Yes | No | No | Australia | Australia | 03-Design/Build | Support to Developpers (D/B) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054947 | Yes | No | No | Australia | Australia | 03-Design/Build | DEV FUT-Baseline(D/B) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054948 | Yes | No | No | Australia | Australia | 03-Design/Build | CONFIG-Baseline (D/B) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054949 | Yes | No | No | Australia | Australia | 03-Design/Build | SDD Writing |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054950 | Yes | No | No | Australia | Australia | 03-Design/Build | CONFIG FUT-Baseline (D/B) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054951 | Yes | No | No | Australia | Australia | 03-Design/Build | Support MDM (D/B) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054952 | Yes | No | No | Australia | Australia | 03-Design/Build | Contribute to Cut-over Planning (D/B) - PTM |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Support Cutover plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054953 | Yes | No | No | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | No |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054954 | Yes | No | No | Australia | Australia | 06-Hypercare | Manage Defects - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054955 | Yes | No | No | Australia | Australia | 06-Hypercare | Break/Fix - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054956 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054957 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054958 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054959 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054960 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Manage Defects (Capex) |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054961 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054962 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Prepare - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | No |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054963 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054964 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Validate |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | No |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054965 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Prepare |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054966 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Support |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054967 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Validate |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-09 | 2017-03-14 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054968 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Run Tests |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054969 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Manage Defects (Capex) |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054970 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Break/Fix - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054971 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Prepare |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-27 | 2017-03-27 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054972 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Support |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-02-20 | 2017-02-20 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054973 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Validate |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-03 | 2017-03-03 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054974 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Run Tests - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054975 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Manage Defects (Capex) |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054976 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Break/Fix - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054977 | Yes | No | No | Australia | Australia | 01-Preparation | Prepare KT) (PP) |  | Missing Stream |  |  | _GD_PTM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-09-19 | 2016-09-19 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054978 | Yes | No | No | Australia | Australia | 01-Preparation | Prepare KT) (PP) |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-09-19 | 2016-09-19 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054979 | Yes | No | No | Australia | Australia | 03-Design/Build | PDD-Baseline |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054980 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-Baseline |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054981 | Yes | No | No | Australia | Australia | 03-Design/Build | FSD-Baseline (D/B) |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054982 | Yes | No | No | Australia | Australia | 03-Design/Build | Support to Developpers (D/B) |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054983 | Yes | No | No | Australia | Australia | 03-Design/Build | DEV FUT-Baseline(D/B) |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054984 | Yes | No | No | Australia | Australia | 03-Design/Build | CONFIG-Baseline (D/B) |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054985 | Yes | No | No | Australia | Australia | 03-Design/Build | SDD Writing |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054986 | Yes | No | No | Australia | Australia | 03-Design/Build | CONFIG FUT-Baseline (D/B) |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054987 | Yes | No | No | Australia | Australia | 03-Design/Build | Support MDM (D/B) |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054988 | Yes | No | No | Australia | Australia | 03-Design/Build | Contribute to Cut-over Planning (D/B) - PTM |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.FUN.Support Cutover plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054989 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-26 | 2016-10-26 | No |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054990 | Yes | No | No | Australia | Australia | 02-Analyze | RTM (AN) |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-13 | 2016-11-13 | No |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054991 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Create BPML (AN) |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-07 | 2016-11-07 | No |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054992 | Yes | No | No | Australia | Australia | 02-Analyze | Old - Log Gaps (AN) |  | Missing Stream |  |  | _GD_PTM-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-15 | 2016-11-15 | No |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054993 | Yes | No | No | Australia | Australia | 03-Design/Build | PDD-Manage Quality Inspections |  | Missing Stream |  |  | _GD_PTP-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054994 | Yes | No | No | Australia | Australia | 02-Analyze | Failure Mode Effect Analysis (FMEA) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-11-09 | 2016-11-09 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054995 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests (Accenture) - DM |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054996 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Manage Defects (Saputo) (Capex) - DM |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054997 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix (Saputo) - DM |  | Missing Stream |  |  | _GD_LOG-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054998 | Yes | No | No | Australia | Australia | 04-Test | Training Materials-Elearning course (Test) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | No |  |  | DELIV.CM-401.Training Materials | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054999 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Document work around (Saputo)- DM |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055000 | Yes | No | No | Australia | Australia | 03-Design/Build | MDM Project Management (D/B) |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | ACT.MDG.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055001 | Yes | No | No | Australia | Australia | 03-Design/Build | Concept Deck |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055002 | Yes | No | No | Australia | Australia | 03-Design/Build | WPB Recording |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055003 | Yes | No | No | Australia | Australia | 03-Design/Build | WPB Recording |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055004 | Yes | No | No | Australia | Australia | 04-Test | Documentation |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055005 | Yes | No | No | Australia | Australia | 02-Analyze | Gather Requirements (AN) |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-17 | 2017-01-17 | No |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055006 | Yes | No | No | Australia | Australia | 03-Design/Build | PDD (D/B) |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055007 | Yes | No | No | Australia | Australia | 03-Design/Build | FSD-Baseline (D/B) |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055008 | Yes | No | No | Australia | Australia | 03-Design/Build | DEV FUT- Baseline (D/B) |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | No |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055009 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Execution and fix |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055010 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Execution and fix |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055011 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Execution and fix |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055012 | Yes | No | No | Australia | Australia | 06-Hypercare | HC – Support and fix |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055013 | Yes | No | No | Australia | Australia | 03-Design/Build | CONFIG-Baseline (D/B) |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055014 | Yes | No | No | Australia | Australia | 03-Design/Build | SDD- Baseline (D/B) |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | No |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055015 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Defect Fix - DC |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-09 | 2017-05-09 | No |  |  | ACT.MDG.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055016 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Defect fix |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.MDG.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055017 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cutover - Prepare - DC |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055018 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cutover - Support - DC |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | No |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055019 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Prepare |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055020 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Execute |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055021 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - DC |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.MDG.Mock Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055022 | Yes | No | No | Australia | Australia | 06-Hypercare | MDSS Project Management (Hypercare) - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.MDG.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055023 | Yes | No | No | Australia | Australia | 06-Hypercare | HC - Provide end User Supprt (Opex) - DM |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055024 | Yes | No | No | Australia | Australia | 06-Hypercare | HC - Manage defects - DM |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055025 | Yes | No | No | Australia | Australia | 06-Hypercare | HC - Break/Fix - DM |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055026 | Yes | No | No | Australia | Australia | 03-Design/Build | WRICEFs - DG (D/B) |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.MDG-205.Data Maintenance Functional Specification | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055027 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | MDM Project Management (Cutover/Go-live) |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.MDG.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055028 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | MDM Gouvernance (Cutover/Go-live) |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.MDG.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055029 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Run tests - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055030 | Yes | No | No | Australia | Australia | 06-Hypercare | MDSS Gouvernance (Hypercare) |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.MDG.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055031 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT Prep |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.MDG.UAT Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055032 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Break/fix - MDG |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055033 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Document work around |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055034 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Execute - DC |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.MDG.Mock Load | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055035 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate - DC |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055036 | Yes | No | No | Australia | Australia | 02-Analyze | RTM (AN) |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-20 | 2017-01-20 | No |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055037 | Yes | No | No | Australia | Australia | 02-Analyze | Data Conversion Plan (AN) |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-17 | 2016-12-17 | No |  |  | DELIV.MDG-201.Data Conversion Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055038 | Yes | No | No | Australia | Australia | 04-Test | MDM Project Management (Test) - MDG-DC |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055039 | Yes | No | No | Australia | Australia | 04-Test | MDM Gouvernance (Test) |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055040 | Yes | No | No | Australia | Australia | 03-Design/Build | BPP - DG (D/B) |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055041 | Yes | No | No | Australia | Australia | 03-Design/Build | Functional Specification - DG (D/B) |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.MDG-205.Data Maintenance Functional Specification | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055042 | Yes | No | No | Australia | Australia | 04-Test | Data collection templates - explain and collect - DM |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055043 | Yes | No | No | Australia | Australia | 03-Design/Build | Legacy data archiving strategy - DC (D/B) |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.TAI-140.Legacy Data Archiving strategy | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055044 | Yes | No | No | Australia | Australia | 03-Design/Build | Support FUN - DC (D/B) |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055045 | Yes | No | No | Australia | Australia | 03-Design/Build | Support SEC - DC (D/B) |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055046 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Run tests (Saputo) - DM |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.MDG.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055047 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Manage Defect (Capex) |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | No |  |  | ACT.MDG.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055048 | Yes | No | No | Australia | Australia | 04-Test | Mock2 - Validate |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-17 | 2017-03-17 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055049 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Run tests (Saputo) - DM |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.MDG.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055050 | Yes | No | No | Australia | Australia | 04-Test | SIT 2 - Manage Defect (Capex) |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.MDG.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055051 | Yes | No | No | Australia | Australia | 04-Test | Data collection templates - explain and collect - DC |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055052 | Yes | No | No | Australia | Australia | 04-Test | Mock1 - Validate - DC |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-03-14 | 2017-03-14 | No |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055053 | Yes | No | No | Australia | Australia | 04-Test | Non Regression - Manage defects (Capex) (Saputo) MDG-DM |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-22 | 2017-05-22 | No |  |  | ACT.MDG.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055054 | Yes | No | No | Australia | Australia | 04-Test | Non Regression - Run tests (Saputo) - DM |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | No |  |  | ACT.MDG.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055055 | Yes | No | No | Australia | Australia | 02-Analyze | Data Construction and staging (AN) |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | ACT.MDG.Data Construction | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055056 | Yes | No | No | Australia | Australia |  | Data Governance |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-07-06 | 2016-07-06 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055057 | Yes | No | No | Australia | Australia |  | Data Governance |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-07-06 | 2016-07-06 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055058 | Yes | No | No | Australia | Australia | 04-Test | Data load - DC |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-27 | 2017-01-27 | No |  |  | ACT.MDG.Mock Load | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055059 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD243-HR - Organization Unit |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055060 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD243-HR - Organization Unit |  | Missing Stream |  |  | _GD_HR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055061 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD244-HR - Position |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055062 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD244-HR - Position |  | Missing Stream |  |  | _GD_HR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055063 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD245-HR - Employee |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055064 | Yes | No | No | Australia | Australia | 03-Design/Build | DDD-GD245-HR - Employee |  | Missing Stream |  |  | _GD_HR-Business |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | No |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055065 | Yes | No | No | Australia | Australia | 03-Design/Build | Design Material Master MDG (Saputo) - DM (D/B) |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-01-21 | 2017-01-21 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055066 | No | No | No | Australia | Australia | 04-Test | Mock1 – Manage defect (Capex) - DC |  | Missing Stream |  |  | Chan; J |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | No |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055067 | Yes | No | No | Australia | Australia | 04-Test | SIT 1 - Run tests - DM |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.MDG.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055068 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cutover - Validate - DC |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-06-10 | 2017-06-10 | No |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055069 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect (Capex) - DC |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | No |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055070 | No | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Execute - DC |  | Missing Stream |  |  | Valencia; Jack |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.MDG.Mock Load | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055071 | No | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate - DC |  | Missing Stream |  |  | Solomon; Ron |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | No |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055072 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect - DC |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-10 | 2017-04-10 | No |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055073 | No | No | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect - DC |  | Missing Stream |  |  | Solomon; Ron |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-10 | 2017-04-10 | No |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055074 | Yes | No | No | Australia | Australia | 04-Test | Transport Sequence |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.PMO-035.Transport Sequence | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055075 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Transport Sequence |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV.PMO-035.Transport Sequence | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055076 | Yes | No | No | Australia | Australia | 03-Design/Build | Test Schedule |  | Missing Stream |  |  | _GD_TEST-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.TST-200.Test Schedule | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055077 | Yes | No | No | Australia | Australia | 03-Design/Build | Regression Test Scenarios/Scripts |  | Missing Stream |  |  | _GD_TEST-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.TST-308.Regression Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055078 | Yes | No | No | Australia | Australia | 03-Design/Build | SIT Scenarios/Scripts |  | Missing Stream |  |  | _GD_TEST-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055079 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | User Acceptance Testing Sign-Off |  | Missing Stream |  |  | _GD_TEST-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV.FUN-505.User Acceptance Testing Sign-Off | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055080 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Test Defect Log |  | Missing Stream |  |  | _GD_TEST-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | WP.Testing.Test Defect Log | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055081 | Yes | No | No | Australia | Australia | 04-Test | Test Defect Log |  | Missing Stream |  |  | _GD_TEST-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | WP.Testing.Test Defect Log | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055082 | Yes | No | No | Australia | Australia | 03-Design/Build | Test Defect Log |  | Missing Stream |  |  | _GD_TEST-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | WP.Testing.Test Defect Log | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055083 | Yes | No | No | Australia | Australia | 01-Preparation | Program Plan on a Page) (PP) |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  | DELIV.PGM-100.Program Plan on a Page | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055084 | Yes | No | No | Australia | Australia | 01-Preparation | Stage Gate Criteria) (PP) |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  | DELIV.PMO-008.Stage Gate Criteria | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055085 | Yes | No | No | Australia | Australia | 01-Preparation | Project Kickoff Presentation) (PP) |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  | DELIV.CM-005.Project Kickoff Presentation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055086 | Yes | No | No | Australia | Australia | 01-Preparation | Install / configure BWL/BPM & configure Solution Manager) (PP) |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  | ACT.PMO.Initial setup and configuration of Solution Manager | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055087 | Yes | No | No | Australia | Australia | 02-Analyze | Detailed Workplan (MSP) (AN) |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | DELIV.PMO-001.Detailed Workplan (MSP) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055088 | Yes | No | No | Australia | Australia | 02-Analyze | Program Plan on a Page (AN) |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | DELIV.PGM-100.Program Plan on a Page | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055089 | Yes | No | No | Australia | Australia | 02-Analyze | Resource Plan (AN) |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | DELIV.PGM-100.Resource Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055090 | Yes | No | No | Australia | Australia | 02-Analyze | Stage Gate Criteria (AN) |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | DELIV.PMO-008.Stage Gate Criteria | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055091 | Yes | No | No | Australia | Australia | 02-Analyze | Project Charter (AN) |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | DELIV.PMO-300.Project Charter | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055092 | Yes | No | No | Australia | Australia | 02-Analyze | Configure HPQC Tools (AN) |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | ACT.PMO.Configure HPQC Tools | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055093 | Yes | No | No | Australia | Australia | 03-Design/Build | Detailed Workplan (MSP) |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.PMO-001.Detailed Workplan (MSP) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055094 | Yes | No | No | Australia | Australia | 03-Design/Build | Program Plan on a Page |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.PGM-100.Program Plan on a Page | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055095 | Yes | No | No | Australia | Australia | 03-Design/Build | Resource Plan |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.PMO-099.Budget for Deployment | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055096 | Yes | No | No | Australia | Australia | 03-Design/Build | Stage Gate Criteria |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.PMO-008.Stage Gate Criteria | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055097 | Yes | No | No | Australia | Australia | 03-Design/Build | Project Charter |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.PMO-300.Project Charter | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055098 | Yes | No | No | Australia | Australia | 03-Design/Build | Production Support Approach |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.PMO-290.Production Support Approach | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055099 | Yes | No | No | Australia | Australia | 04-Test | Detailed Workplan (MSP) |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.PMO-001.Detailed Workplan (MSP) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055100 | Yes | No | No | Australia | Australia | 04-Test | Program Plan on a Page |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.PGM-100.Program Plan on a Page | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055101 | Yes | No | No | Australia | Australia | 04-Test | Resource Plan |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.PMO-099.Budget for Deployment | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055102 | Yes | No | No | Australia | Australia | 04-Test | Stage Gate Criteria |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.PMO-008.Stage Gate Criteria | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055103 | Yes | No | No | Australia | Australia | 04-Test | Project Charter |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.PMO-300.Project Charter | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055104 | Yes | No | No | Australia | Australia | 04-Test | Production Support Approach |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.PMO-290.Production Support Approach | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055105 | Yes | No | No | Australia | Australia | 04-Test | Hypercare Approach & Plan |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.PMO-280.Hypercare Approach & Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055106 | Yes | No | No | Australia | Australia | 04-Test | Cutover Plan |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.PMO-404.Cutover Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055107 | Yes | No | No | Australia | Australia | 04-Test | Cutover Control Room Strategy |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.PMO-407.Cutover Control Room Strategy | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055108 | Yes | No | No | Australia | Australia | 04-Test | Business Readiness Ramp-Down/Up Workshops |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055109 | Yes | No | No | Australia | Australia | 04-Test | Cutover Report |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.PMO-408.Cutover Report | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055110 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Detailed Workplan (MSP) |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV.PMO-001.Detailed Workplan (MSP) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055111 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Program Plan on a Page |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV.PGM-100.Program Plan on a Page | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055112 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Resource Plan |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV.PMO-099.Budget for Deployment | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055113 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Stage Gate Criteria |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV.PMO-008.Stage Gate Criteria | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055114 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Production Support Approach |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV.PMO-290.Production Support Approach | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055115 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Hypercare Approach & Plan |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV.PMO-280.Hypercare Approach & Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055116 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cutover Plan |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV.PMO-404.Cutover Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055117 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cutover Control Room Strategy |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV.PMO-407.Cutover Control Room Strategy | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055118 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Business Readiness Ramp-Down/Up Workshops |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  |  | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055119 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cutover Report |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV.PMO-408.Cutover Report | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055120 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | HL Cutover Calendar |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV.PMO-405.HL Cutover Calendar | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055121 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cutover System and Process Freeze |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV.PMO-406.Cutover System and Process Freeze | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055122 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Hypercare Schedule |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV.PMO-502.Hypercare Schedule | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055123 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Cutover and Go-Live Readiness |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV.PMO-009.Cutover and Go-Live Readiness | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055124 | Yes | No | No | Australia | Australia | 06-Hypercare | Hypercare Report |  | Missing Stream |  |  | _GD_PMO-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | DELIV.PMO-602.Hypercare Report | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055125 | Yes | No | No | Australia | Australia | 02-Analyze | Communication plan execution and monitoring (AN) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | ACT.CM.Communication plan execution and monitoring | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055126 | Yes | No | No | Australia | Australia | 03-Design/Build | Communication plan execution and monitoring (D/B) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | ACT.CM.Communication plan execution and monitoring | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055127 | Yes | No | No | Australia | Australia | 03-Design/Build | Process Role Catalog (D/B) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | No |  |  | DELIV.CM-008.Process Role Catalog | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055128 | Yes | No | No | Australia | Australia | 03-Design/Build | Change Impacts Analysis (D/B) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | No |  |  | DELIV.CM-014.Change Impacts Analysis | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055129 | Yes | No | No | Australia | Australia | 03-Design/Build | Execute Train the Trainer (D/B) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | No |  |  | ACT.CM.Execute Train the Trainer | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055130 | Yes | No | No | Australia | Australia | 03-Design/Build | Knowledge Transfer Plan (D/B) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | No |  |  | DELIV.CM-116.Knowledge Transfer Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055131 | Yes | No | No | Australia | Australia | 04-Test | Communication plan execution and monitoring (Test) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.CM.Communication plan execution and monitoring | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055132 | Yes | No | No | Australia | Australia | 04-Test | Change Agents Network Execution and Monitoring (Test) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.CM.Change Agents Network Execution and Monitoring | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055133 | Yes | No | No | Australia | Australia | 04-Test | Business Readiness Execution & Monitoring (Test) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.CM.Business Readiness Execution & Monitoring | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055134 | Yes | No | No | Australia | Australia | 04-Test | Establish Key users Network (Test) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.CM.Establish Key users Network | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055135 | Yes | No | No | Australia | Australia | 04-Test | Role Mapping (Test) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.CM-218.Role Mapping | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055136 | Yes | No | No | Australia | Australia | 04-Test | Training Curriculum (Test) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.CM-320.Training Curriculum | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055137 | Yes | No | No | Australia | Australia | 04-Test | Failure Mode Effect Analysis (Test) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.CM-301.Failure Mode Effect Analysis (FMEA) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055138 | Yes | No | No | Australia | Australia | 04-Test | Knowledge Transfer Execution & Monitoring (Test) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.CM.Knowledge Transfer Execution & Monitoring | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055139 | Yes | No | No | Australia | Australia | 04-Test | Deliver Training to UAT Testers (Test) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | ACT.CM.Deliver Training to UAT Testers | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055140 | Yes | No | No | Australia | Australia | 04-Test | Personalised training Plan (Test) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | WP.CM.Personalised training Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055141 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Communication plan execution and monitoring (C/G) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.CM.Communication plan execution and monitoring | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055142 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Change Agents Network Execution and Monitoring (C/G) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.CM.Change Agents Network Execution and Monitoring | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055143 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Business Readiness Execution & Monitoring (C/G) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.CM.Business Readiness Execution & Monitoring | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055144 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Establish Key users Network (C/G) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.CM.Establish Key users Network | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055145 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Role Mapping (C/G) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | DELIV.CM-218.Role Mapping | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055146 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | Manage Training Logisitics (C/G) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.CM.Manage Training Logisitics | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055147 | Yes | No | No | Australia | Australia | 06-Hypercare | Manage Training Logisitics (HYP) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.CM.Manage Training Logisitics | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055148 | Yes | No | No | Australia | Australia | 06-Hypercare | Monitor Key users Network (HYP) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.CM.Monitor Key users Network | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055149 | Yes | No | No | Australia | Australia | 06-Hypercare | Value Realization Monitoring (HYP) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | No |  |  | ACT.CM.Value Realization Monitoring | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055150 | Yes | No | No | Australia | Australia | 02-Analyze | Data Cleansing and Migration Approach (AN) |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | DELIV.MDM-110.Data Cleansing and Migration Approach | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055151 | Yes | No | No | Australia | Australia | 02-Analyze | Data Object Master (DOM) (AN) |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | DELIV.MDG-150.Data Object Master (DOM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055152 | Yes | No | No | Australia | Australia | 02-Analyze | Data Maintenance process designs (PDDs) (AN) |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | DELIV.MDG-110.Data Maintenance process designs (PDDs) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055153 | Yes | No | No | Australia | Australia | 03-Design/Build | Functional Design Documented and aligned with Benoit at high level to support build (D/B) |  | Missing Stream |  |  | _GD_BI-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | No |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055154 | Yes | No | No | Australia | Australia | 01-Preparation | Stakeholder Assessment |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-10-26 | 2016-10-26 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055155 | Yes | No | No | Australia | Australia | 01-Preparation | Change Management Plan (PP) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  | DELIV.CM-250.Change Management Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055156 | Yes | No | No | Australia | Australia | 01-Preparation | Data Object Master (DOM)) (PP) |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  | DELIV.MDG-150.Data Object Master (DOM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055157 | Yes | No | No | Australia | Australia | 01-Preparation | Source system assessment and map) (PP) |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  | DELIV.MDG-060.Source system assessment and map | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055158 | Yes | No | No | Australia | Australia | 01-Preparation | MDG - Workshop schedule) (PP) |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | No |  |  | WP.MDG-001.MDG - Workshop schedule | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055159 | Yes | No | No | Australia | Australia | 02-Analyze | Project Testing Approach (AN) |  | Missing Stream |  |  | _GD_TEST-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-01-07 | 2017-01-07 | No |  |  | DELIV.TST-201.Testing Approach | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055160 | Yes | No | No | Australia | Australia | 02-Analyze | Business Readiness plan (AN) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | DELIV.CM-112.Business Readiness plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055161 | Yes | No | No | Australia | Australia | 02-Analyze | Business Process Master List (BPML) (AN) |  | Missing Stream |  |  | _GD_HR-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-11-01 | 2016-11-01 | No |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055162 | Yes | No | No | Australia | Australia | 02-Analyze | Kickoff (AN) |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | No |  |  | ACT.MDG.Workshop | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055163 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Manage Defect (Capex) |  | Missing Stream |  |  | _GD_MDG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055164 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests (Saputo) - DM |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055165 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Manage Defects (Accenture) (Capex) - DM |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055166 | Yes | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix (Accenture) - DM |  | Missing Stream |  |  | _GD_LOG-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | No |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055167 | Yes | No | No | Australia | Australia | 03-Design/Build | Change Agents Network Execution and Monitoring (D/B) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.CM.Change Agents Network Execution and Monitoring | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055168 | Yes | No | No | Australia | Australia | 03-Design/Build | CIA |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055169 | Yes | No | No | Australia | Australia | 03-Design/Build | Establish Key users Network (D/B) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.CM.Establish Key users Network | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055170 | Yes | No | No | Australia | Australia | 03-Design/Build | Transition Plan Execution & Monitoring (D/B) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.CM.Transition Plan Execution & Monitoring | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055171 | Yes | No | No | Australia | Australia | 03-Design/Build | Business Readiness Execution & Monitoring (D/B) |  | Missing Stream |  |  | _GD_CM-Consultant |  | Yes | OpEx | Localization |  | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | No |  |  | ACT.CM.Business Readiness Execution & Monitoring | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055172 | Yes | No | No | Australia | Australia | 04-Test | Test Schedule |  | Missing Stream |  |  | _GD_TEST-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.TST-200.Test Schedule | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055173 | Yes | No | No | Australia | Australia | 04-Test | SIT Test Scenarios/Scripts |  | Missing Stream |  |  | _GD_TEST-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055174 | Yes | No | No | Australia | Australia | 04-Test | UAT Schedule |  | Missing Stream |  |  | _GD_TEST-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.TST-200.Test Schedule | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055175 | Yes | No | No | Australia | Australia | 04-Test | UAT Test Scenarios/Test Cases/Test Scripts |  | Missing Stream |  |  | _GD_TEST-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055176 | Yes | No | No | Australia | Australia | 04-Test | Test Closure Summary |  | Missing Stream |  |  | _GD_TEST-Consultant |  | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | No |  |  | DELIV.TST-201.Test Closure Summary | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055177 | No | No | No | Australia | Australia | 01-Preparation | Management (PP) | CM | CM | Saputo | Onshore | Hebert; Dany | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-10-28 | 2016-10-28 | Yes |  |  | ACT.CM.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055178 | No | Yes | No | Australia | Australia | 01-Preparation | Conduct KT sessions) (PP) | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  | WP.FUN.Requirements/Process Design Workshop Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055179 | No | Yes | No | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 11h | 0h | 11h | 2016-11-07 | 2016-12-01 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055180 | No | Yes | No | Australia | Australia | 03-Design/Build | Transition to Australia - (Capex) - (D/B) | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055181 | No | Yes | No | Australia | Australia | 03-Design/Build | Workshops - PTM - APO (Advance Palnning & Optimization) | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 29h | 0h | 29h | 2017-04-03 | 2017-04-07 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055182 | No | Yes | No | Australia | Australia | 03-Design/Build | DP_04-CONFIG FUT-Advanced Planning & Optimization (DP) | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-04-24 | 2017-04-28 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055183 | No | Yes | No | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - PTM | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 146h | 0h | 146h | 2017-07-03 | 2017-07-28 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 25 | 33 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055184 | No | Yes | No | Australia | Australia | 06-Hypercare | Break/Fix - PTM | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2017-07-03 | 2017-07-17 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 41 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055185 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | UAT - Prep | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 26h | 0h | 26h | 2017-05-31 | 2017-06-16 | Yes |  |  | ACT.FUN.UAT Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055186 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - PTM | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055187 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - PTM | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-06-05 | 2017-06-16 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055188 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Prepare - PTM | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 14h | 0h | 14h | 2017-05-29 | 2017-06-09 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055189 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - PTM | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 87h | 0h | 87h | 2017-06-19 | 2017-06-30 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055190 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Validate | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-06-19 | 2017-06-23 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055191 | No | Yes | No | Australia | Australia | 04-Test | SIT 1 - Run Tests | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 64h | 0h | 64h | 2017-04-24 | 2017-05-19 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055192 | No | Yes | No | Australia | Australia | 04-Test | SIT 1 - Break/Fix - PTM | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-04-24 | 2017-05-05 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055193 | No | Yes | No | Australia | Australia | 04-Test | SIT 2 - Run Tests - PTM | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 35h | 0h | 35h | 2017-05-22 | 2017-05-31 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055194 | No | Yes | No | Australia | Australia | 04-Test | SIT 2 - Break/Fix - PTM | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 37h | 0h | 37h | 2017-05-23 | 2017-06-16 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 6 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055195 | No | Yes | No | Australia | Australia | 04-Test | Regression - Run Tests - PTM | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-05-15 | 2017-06-16 | Yes |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055196 | No | Yes | No | Australia | Australia | 04-Test | Regression - Manage defects (Capex) - PTM | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055197 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - PTM | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2017-05-08 | 2017-05-19 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055198 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - PTM | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 17h | 0h | 17h | 2017-05-08 | 2017-06-26 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055199 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate | PTM | FUN | SI | Onshore | Surneni; Parandama | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-06-05 | 2017-06-09 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055200 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | LOG | FUN | SI | Onshore | Palmer; Josh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055201 | No | No | Yes | Australia | Australia | 03-Design/Build | TM_01-CONFIG-Basic Settings in SAP TM / ECC | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055202 | No | No | Yes | Australia | Australia | 03-Design/Build | TM_05-CONFIG-Configuration Settings for Order and Delivery Integration | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055203 | No | No | Yes | Australia | Australia | 03-Design/Build | TM_06-CONFIG-Maintain Output Determination for Sales Documents | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055204 | No | No | Yes | Australia | Australia | 03-Design/Build | TM_07-CONFIG-Maintain Output Determination for Outbound Deliveries | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055205 | No | No | Yes | Australia | Australia | 03-Design/Build | TM_09-CONFIG-Outbound Integration of ERP Shipments (TM-planned; ECC/EWM-executed) | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055206 | No | No | Yes | Australia | Australia | 03-Design/Build | TM_10-CONFIG-Inbound Integration of ERP Shipments (ECC-planned;TM-charge calculation) | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055207 | No | No | Yes | Australia | Australia | 03-Design/Build | TM_03-CONFIG-Master Data Transfer ECC to TM (Activate Integration Models) | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055208 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055209 | No | No | Yes | Australia | Australia | 03-Design/Build | TM_12-CONFIG-Planning | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055210 | No | No | Yes | Australia | Australia | 03-Design/Build | TM_13-CONFIG-Freight Order Management | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-02-27 | 2017-03-03 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055211 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - LOG | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-22 | 2017-05-22 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055212 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Prepare - baseline - LOG | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-02 | 2017-06-02 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055213 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - baseline - LOG | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 64h | 0h | 64h | 2017-06-26 | 2017-07-03 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055214 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - LOG | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 140h | 0h | 140h | 2017-07-03 | 2017-07-14 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055215 | No | No | Yes | Australia | Australia | 03-Design/Build | XXX_XX-CONFIG-Transportation Cockpit | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055216 | No | No | Yes | Australia | Australia | 03-Design/Build | XXX_XX-CONFIG FUT-Transportation Cockpit | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055217 | No | No | Yes | Australia | Australia | 04-Test | Management (Test) - LOG | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 64h | 0h | 64h | 2017-05-01 | 2017-05-19 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055218 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - LOG | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055219 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - LOG | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055220 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - LOG | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 96h | 0h | 96h | 2017-05-29 | 2017-06-09 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055221 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Prepare | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055222 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Support | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-27 | 2017-03-27 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055223 | No | No | Yes | Australia | Australia | 03-Design/Build | Management (D/B) | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 223h | 0h | 223h | 2017-01-23 | 2017-04-21 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 35 | 44 | 44 | 15 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055224 | No | No | Yes | Australia | Australia | 03-Design/Build | CONFIG FUT-TM_01-TM | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055225 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG008-FSD-ECC to BSM Delivery | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055226 | No | No | Yes | Australia | Australia | 03-Design/Build | XXX-FSD-ECC/GTS to BSM Order (Transfer OTC) | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055227 | No | No | Yes | Australia | Australia | 03-Design/Build | PDD-Process Freight Plan and Select Carrier(D/B) | LOG | FUN | SI | Onshore | Canimo; Roland | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055228 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix (Hypercare) - RTR | RTR | FUN | SI | Onshore | Roloff; Patrick | SAP | Yes | CapEx | Localization | IT - External | 26h | 0h | 26h | 2017-07-04 | 2017-09-05 | Yes |  | DMS | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.5 | 10.5 | 0 | 0
1055229 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - RTR | RTR | FUN | SI | Onshore | Roloff; Patrick | SAP | Yes | CapEx | Localization | IT - External | 17.5h | 0h | 17.5h | 2017-06-19 | 2017-06-30 | Yes |  | DMS | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055230 | No | No | Yes | Australia | Australia | 06-Hypercare | DMS HyperCare solution stabilization - RTR | RTR | FUN | SI | Onshore | Roloff; Patrick | SAP | Yes | CapEx | Localization | IT - External | 174.5h | 0h | 174.5h | 2017-07-03 | 2017-08-11 | Yes |  | DMS | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.5 | 28 | 24.5 | 19.5 | 43.75 | 26.25 | 0 | 0 | 0 | 0 | 0 | 0
1055231 | No | No | Yes | Australia | Australia | 04-Test | DMS SIT AUS - Break Fix - RTR | RTR | FUN | SI | Onshore | Roloff; Patrick | SAP | Yes | CapEx | Localization | IT - External | 81.25h | 0h | 81.25h | 2017-04-18 | 2017-05-12 | Yes |  | DMS | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16.5 | 13 | 35.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055232 | No | No | Yes | Australia | Australia | 06-Hypercare | Hypercare | SEC | SEC | SI | Offshore | Aragon; Marvin | Accenture | Yes | CapEx | Localization | IT - External | 171h | 0h | 171h | 2017-07-17 | 2017-08-11 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0
1055233 | No | No | Yes | Australia | Australia | 06-Hypercare | Hypercare | SEC | SEC | SI | Offshore | Ballada; EJ | Accenture | Yes | CapEx | Localization | IT - External | 58.5h | 0h | 58.5h | 2017-07-10 | 2017-07-28 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055234 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | OTC | FUN | Saputo | Onshore | Barreto; Bruno | Saputo | Yes | CapEx | Localization | IT - Internal | 65.6h | 0h | 65.6h | 2017-05-08 | 2017-06-05 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 12 | 12 | 1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055235 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - OTC | OTC | FUN | Saputo | Onshore | Barreto; Bruno | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055236 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - OTC | OTC | FUN | Saputo | Onshore | Barreto; Bruno | Saputo | Yes | CapEx | Localization | IT - Internal | 16h | 0h | 16h | 2017-06-26 | 2017-07-07 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055237 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Prep | OTC | FUN | Saputo | Onshore | Barreto; Bruno | Saputo | Yes | CapEx | Localization | IT - Internal | 34.7h | 0h | 34.7h | 2017-05-19 | 2017-06-16 | Yes |  |  | ACT.FUN.UAT Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055238 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - OTC | OTC | FUN | Saputo | Onshore | Barreto; Bruno | Saputo | Yes | CapEx | Localization | IT - Internal | 47h | 0h | 47h | 2017-05-29 | 2017-06-23 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.2 | 5.8 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055239 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - OTC | OTC | FUN | Saputo | Onshore | Barreto; Bruno | Saputo | Yes | CapEx | Localization | IT - Internal | 66.35h | 0h | 66.35h | 2017-05-29 | 2017-06-26 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.6 | 34.75 | 10 | 9.4 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055240 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - OTC | OTC | FUN | Saputo | Onshore | Barreto; Bruno | Saputo | Yes | CapEx | Localization | IT - Internal | 48h | 0h | 48h | 2017-07-10 | 2017-08-01 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055241 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix - OTC | OTC | FUN | Saputo | Onshore | Barreto; Bruno | Saputo | Yes | CapEx | Localization | IT - Internal | 91.43h | 0h | 91.43h | 2017-07-10 | 2017-08-11 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 16 | 22.88 | 20.55 | 0 | 0 | 0 | 0 | 0 | 0
1055242 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - RTR | RTR | FUN | SI | Offshore | Chakraborty; Sujoy | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-07-04 | 2017-07-28 | Yes |  |  | ACT.FUN.Functional Break/Fix | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055243 | No | No | Yes | Australia | Australia | 06-Hypercare | Development (Hypercare) - DEV | DEV | DEV | SI | Offshore | Nehra; Mohit | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-04 | 2017-05-04 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055244 | No | No | Yes | Australia | Australia | 03-Design/Build | Development (D/B) | DEV | DEV | Saputo | Onshore | Gomare; Shankar | Saputo | Yes | CapEx | Localization | IT - Internal | 65h | 0h | 65h | 2017-03-20 | 2017-04-18 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 10 | 15 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055245 | No | No | Yes | Australia | Australia | 03-Design/Build | Development GRC (D/B) | DEV | DEV | Saputo | Onshore | Gomare; Shankar | Saputo | Yes | CapEx | Localization | IT - Internal | 3h | 0h | 3h | 2017-02-06 | 2017-03-24 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055246 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT1) | DEV | DEV | Saputo | Onshore | Gomare; Shankar | Saputo | Yes | CapEx | Localization | IT - Internal | 95h | 0h | 95h | 2017-04-25 | 2017-05-18 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 21 | 18 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055247 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT2) | DEV | DEV | Saputo | Onshore | Gomare; Shankar | Saputo | Yes | CapEx | Localization | IT - Internal | 20h | 0h | 20h | 2017-05-29 | 2017-06-02 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055248 | No | No | Yes | Australia | Australia |  | AUS - DEV KT | DEV | DEV | Saputo | Onshore | Gomare; Shankar | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-05-31 | 2017-05-31 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055249 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Development (Cutover/Go-live) - DEV | DEV | DEV | Saputo | Onshore | Gomare; Shankar | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-02 | 2017-06-02 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055250 | No | No | Yes | Australia | Australia | 06-Hypercare | HC - Break/Fix - Dev | DEV | DEV | Saputo | Onshore | Gomare; Shankar | Saputo | Yes | CapEx | Localization | IT - Internal | 12h | 0h | 12h | 2017-07-04 | 2017-07-11 | Yes |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055251 | No | No | Yes | Australia | Australia |  | AUS - DEV KT | DEV | DEV | SI | Offshore | Gupta; Debapriya | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-31 | 2017-05-31 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055252 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT1) | DEV | DEV | SI | Offshore | Gupta; Debapriya | IBM | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2017-06-05 | 2017-06-05 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055253 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT2) | DEV | DEV | SI | Offshore | Gupta; Debapriya | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055254 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Development (Cutover/Go-live) - DEV | DEV | DEV | SI | Offshore | Gupta; Debapriya | IBM | Yes | CapEx | Localization | IT - External | 71h | 0h | 71h | 2017-06-19 | 2017-06-30 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055255 | No | No | Yes | Australia | Australia | 06-Hypercare | Development (Hypercare) - DEV | DEV | DEV | SI | Offshore | Gupta; Debapriya | IBM | Yes | CapEx | Localization | IT - External | 215.5h | 0h | 215.5h | 2017-07-03 | 2017-09-15 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 45 | 31 | 45 | 0 | 0 | 0 | 0 | 3.5 | 18 | 16 | 0
1055256 | No | No | Yes | Australia | Australia | 03-Design/Build | Development (D/B) | DEV | DEV | SI | Offshore | Gupta; Debapriya | IBM | Yes | CapEx | Localization | IT - External | 173h | 0h | 173h | 2017-02-14 | 2017-04-07 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 19 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055257 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix - OTC | OTC | FUN | SI | Onshore | Ujeniya; Ashok | IBM | Yes | CapEx | Localization | IT - External | 43h | 0h | 43h | 2017-08-07 | 2017-08-24 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 19 | 4 | 0 | 0 | 0 | 0
1055258 | No | No | Yes | Australia | Australia | 06-Hypercare | Hypercare - Support - TAI | TAI | TAI | Saputo | Onshore | Smith; Alex | Saputo | Yes | CapEx | Localization | IT - Internal | 192h | 0h | 192h | 2017-07-04 | 2017-08-18 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0
1055259 | No | No | Yes | Australia | Australia |  | OpenText Technical Architecture | TAI | TAI | SI | Onshore | Chan; Philip | Accenture | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2017-05-23 | 2017-07-06 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 40 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055260 | No | No | No | Australia | Australia | 04-Test | SIT 1 - Break/Fix - PTP | DMS | DMS | SI | Onshore | Franz; Wolfgang | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  | DMS | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055261 | No | No | No | Australia | Australia | 04-Test | SIT 2 - Break/Fix - PTP | DMS | DMS | SI | Onshore | Franz; Wolfgang | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-17 | Yes |  | DMS | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055262 | No | No | No | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - PTP | DMS | DMS | SI | Onshore | Franz; Wolfgang | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | Yes |  | DMS | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055263 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Break/Fix - LOG | LOG | FUN | SI | Offshore | Rajenderan; Santhosh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055264 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - LOG | LOG | FUN | SI | Offshore | Rajenderan; Santhosh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-23 | 2017-05-26 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055265 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - LOG | LOG | FUN | SI | Offshore | Rajenderan; Santhosh | IBM | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-06-05 | 2017-06-23 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055266 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Execute - DC | MDG | DC | SI | Offshore | Mitra; Kimberly | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | Yes |  |  | ACT.MDG.Mock Load | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055267 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect - DC | MDG | DC | SI | Offshore | Mitra; Kimberly | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-10 | 2017-04-10 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055268 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - DC | MDG | DC | SI | Offshore | Mitra; Kimberly | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | ACT.MDG.Mock Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055269 | No | Yes | No | Australia | Australia | 04-Test | Mock1 – Manage defect (Capex) - DC | MDG | DC | SI | Offshore | Mitra; Kimberly | Accenture | Yes | CapEx | Localization | IT - External | 63h | 0h | 63h | 2017-04-10 | 2017-04-20 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055270 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate - DC | MDG | DC | SI | Offshore | Mitra; Kimberly | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055271 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate - DC | MDG | DC | SI | Offshore | Morales; Veronica | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055272 | No | No | Yes | Australia | Australia | 04-Test | Mock1 – Manage defect (Capex) - DC | MDG | DC | SI | Offshore | Morales; Veronica | Accenture | Yes | CapEx | Localization | IT - External | 117h | 0h | 117h | 2017-04-03 | 2017-05-05 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 45 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055273 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - DC | MDG | DC | SI | Offshore | Morales; Veronica | Accenture | Yes | CapEx | Localization | IT - External | 81h | 0h | 81h | 2017-04-24 | 2017-05-12 | Yes |  |  | ACT.MDG.Mock Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055274 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect - DC | MDG | DC | SI | Offshore | Morales; Veronica | Accenture | Yes | CapEx | Localization | IT - External | 72h | 0h | 72h | 2017-04-10 | 2017-06-02 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055275 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Prepare - DC | MDG | DC | SI | Offshore | Morales; Veronica | Accenture | Yes | OpEx | Localization | IT - External | 36h | 0h | 36h | 2017-06-05 | 2017-06-08 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055276 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Support - DC | MDG | DC | SI | Offshore | Morales; Veronica | Accenture | Yes | OpEx | Localization | IT - External | 86h | 0h | 86h | 2017-06-19 | 2017-06-30 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055277 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Execute - DC | MDG | DC | SI | Offshore | Morales; Veronica | Accenture | Yes | CapEx | Localization | IT - External | 81h | 0h | 81h | 2017-05-15 | 2017-05-26 | Yes |  |  | ACT.MDG.Mock Load | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055278 | No | No | Yes | Australia | Australia | 06-Hypercare | HC - Manage defects - DC | MDG | DC | SI | Offshore | Morales; Veronica | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055279 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Validate - DC | MDG | DC | SI | Offshore | Morales; Veronica | Accenture | Yes | OpEx | Localization | IT - External | 45h | 0h | 45h | 2017-06-12 | 2017-06-16 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055280 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect (Capex) - DC | MDG | DC | SI | Offshore | Morales; Veronica | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055281 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - LOG | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 156h | 0h | 156h | 2017-05-29 | 2017-06-16 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 48 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055282 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG006-ASS Testing-EDI 3PL Pick Request | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 47h | 0h | 47h | 2017-04-17 | 2017-06-28 | Yes |  |  | ACT.FUN.Execute Assembly Tests | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 19 | 0 | 0 | 0 | 14 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055283 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG007-ASS Testing-EDI 3PL ASN | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 60h | 0h | 60h | 2017-05-12 | 2017-06-27 | Yes |  |  | ACT.FUN.Execute Assembly Tests | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 14 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055284 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG010-ASS Testing-Pick Confirmation to 3PL | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 23h | 0h | 23h | 2017-04-24 | 2017-06-29 | Yes |  |  | ACT.FUN.Execute Assembly Tests | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055285 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG011-Ass Testing-Lot Status Message to 3PL | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 3h | 0h | 3h | 2017-05-08 | 2017-06-27 | Yes |  |  | ACT.FUN.Execute Assembly Tests | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055286 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 87h | 0h | 87h | 2017-04-24 | 2017-05-07 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055287 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Break/Fix - LOG | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 41h | 0h | 41h | 2017-05-08 | 2017-05-12 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055288 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Preparation | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 92h | 0h | 92h | 2017-04-03 | 2017-04-21 | Yes |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055289 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - LOG | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 253h | 0h | 253h | 2017-07-04 | 2017-08-09 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 66 | 56.5 | 58.5 | 16 | 12 | 0 | 0 | 0 | 0 | 0 | 0
1055290 | No | No | Yes | Australia | Australia | 04-Test | Regression - Run Tests - LOG | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-05-18 | 2017-05-23 | Yes |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055291 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - LOG | LOG | FUN | SI | Onshore | Perrault; Richard | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-05-25 | 2017-05-25 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055292 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Manage UAT | Test | Test | SI | Offshore | Bandyopadhyay; Koushik | IBM | Yes | CapEx | Localization | IT - External | 40.5h | 0h | 40.5h | 2017-06-12 | 2017-06-30 | Yes |  |  | ACT.Test.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055293 | No | No | Yes | Australia | Australia | 04-Test | Manage SIT | Test | Test | SI | Offshore | Bandyopadhyay; Koushik | IBM | Yes | CapEx | Localization | IT - External | 216h | 0h | 216h | 2017-05-02 | 2017-06-02 | Yes |  |  | ACT.Test.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 45 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055294 | No | No | Yes | Australia | Australia | 03-Design/Build | Test preparation | Test | Test | SI | Offshore | Bandyopadhyay; Koushik | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | DELIV.TST-307.Assembly Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055295 | No | No | Yes | Australia | Australia | 03-Design/Build | SoD GRC AC Analysis and Remediation | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-12-11 | 2016-12-11 | Yes |  |  | DELIV.SEC-215.SAP Security & GRC Processes | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055296 | No | No | Yes | Australia | Australia | 03-Design/Build | GRC AC Solution Design | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | Yes |  |  | DELIV.SEC-215.SAP Security & GRC Processes | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055297 | No | No | Yes | Australia | Australia | 03-Design/Build | Security Design/Build | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 326h | 0h | 326h | 2017-03-06 | 2017-05-19 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 40 | 0 | 0 | 40 | 40 | 41 | 42 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055298 | No | No | Yes | Australia | Australia | 02-Analyze | GRC Access Controls Requirements (AN) | SEC | SEC | Saputo | Onshore | Medina; Julio Victor | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  | DELIV.SEC-002B.SAP GRC Process Control RTM | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055299 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055300 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - LOG | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 150.75h | 0h | 150.75h | 2017-07-03 | 2017-08-16 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 52 | 8 | 9 | 8.75 | 0 | 1 | 0 | 0 | 0 | 0 | 0
1055301 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 22h | 0h | 22h | 2017-05-11 | 2017-05-19 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055302 | No | No | Yes | Australia | Australia | 04-Test | Regression - Run Tests - LOG | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 42h | 0h | 42h | 2017-05-23 | 2017-06-01 | Yes |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055303 | No | No | Yes | Australia | Australia | 06-Hypercare | Manage Defects - LOG | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 102.25h | 0h | 102.25h | 2017-07-18 | 2017-08-31 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 23 | 23.25 | 5 | 6 | 7 | 6 | 0 | 0 | 0
1055304 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix - LOG | LOG | FUN | Saputo | Onshore | Bancoro; Evencio | Saputo | Yes | CapEx | Localization | IT - Internal | 3h | 0h | 3h | 2017-08-17 | 2017-08-18 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0
1055305 | No | No | Yes | Australia | Australia | 04-Test | Data collection templates - explain and collect - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Localization | IT - External | 184h | 0h | 184h | 2016-12-19 | 2017-05-05 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 40 | 32 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055306 | No | No | Yes | Australia | Australia | 04-Test | MDM Project Management (Test) - MDG-DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Localization | IT - External | 429h | 0h | 429h | 2017-03-27 | 2017-07-03 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 8 | 32 | 0 | 0 | 0 | 40 | 40 | 32 | 40 | 0 | 40 | 75 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055307 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Support - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | OpEx | Localization | IT - External | 40h | 0h | 40h | 2017-07-03 | 2017-07-07 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055308 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Prepare - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | OpEx | Localization | IT - External | 40h | 0h | 40h | 2017-06-05 | 2017-06-09 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055309 | No | No | Yes | Australia | Australia | 02-Analyze | Data Construction and staging - DC (AN) | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Localization | IT - External | 200h | 0h | 200h | 2016-10-24 | 2016-12-09 | Yes |  |  | ACT.MDG.Data Construction | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055310 | No | No | Yes | Australia | Australia | 02-Analyze | MDM Project Management (Analyse) - DC (AN) | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Localization | IT - External | 180h | 0h | 180h | 2016-12-12 | 2017-03-10 | Yes |  |  | ACT.MDG.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 40 | 0 | 40 | 0 | 0 | 0 | 40 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055311 | No | No | Yes | Australia | Australia | 03-Design/Build | MDM Project Management (D/B) - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Localization | IT - External | 116h | 0h | 116h | 2017-02-27 | 2017-03-24 | Yes |  |  | ACT.MDG.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 36 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055312 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Validate - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055313 | No | No | Yes | Australia | Australia |  | MDM Project Management (Saputo) - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Localization | IT - External | 124h | 0h | 124h | 2017-07-10 | 2017-07-28 | Yes |  |  | ACT.MDG.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055314 | No | No | Yes | Australia | Australia | 06-Hypercare | HC - Manage defects - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055315 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect (Capex) - DC | MDG | DC | SI | Onshore | Singh; Kuldeep | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055316 | No | No | Yes | Australia | Australia | 03-Design/Build | IOTC006-DEV FUT-EDI Inbound Sales Order | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055317 | No | No | Yes | Australia | Australia | 03-Design/Build | IOTC007-DEV FUT-EDI Outbound Order Response | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-10 | 2017-04-10 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055318 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Create BPML (AN) | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055319 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Log Gaps (AN) | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-21 | 2016-11-21 | Yes |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055320 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia(D/B) | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2017-02-04 | 2017-02-26 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055321 | No | No | Yes | Australia | Australia | 01-Preparation | Worshop Preparation Decks) (PP) | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 49h | 0h | 49h | 2016-10-10 | 2016-10-27 | Yes |  |  | WP.FUN-107.Workshop Preparation Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055322 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055323 | No | No | Yes | Australia | Australia | 02-Analyze | RTM (AN) | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-05 | 2016-11-05 | Yes |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055324 | No | No | Yes | Australia | Australia | 01-Preparation | Prepare KT (IBM)) (PP) | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2016-10-10 | 2016-10-20 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055325 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG008-DEV FUT-ECC to BSM Delivery | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-05 | 2017-04-05 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055326 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG011-FSD-Lot Status Message to 3PL | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055327 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG008-FSD-ECC to BSM Delivery | OTC | FUN | SI | Onshore | Kovacevich; Vladimir | IBM | Yes | CapEx | Localization | IT - External | 52h | 0h | 52h | 2017-02-06 | 2017-02-17 | Yes |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055328 | No | Yes | No | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055329 | No | Yes | No | Australia | Australia | 01-Preparation | Prepare Kick-off) (PP) | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-03 | 2016-10-03 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055330 | No | Yes | No | Australia | Australia | 03-Design/Build | KT sessions (D/B) | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055331 | No | Yes | No | Australia | Australia | 02-Analyze | Old - Create BPML (AN) | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055332 | No | Yes | No | Australia | Australia | 02-Analyze | Old - Log Gaps (AN) | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-11 | 2016-11-11 | Yes |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055333 | No | Yes | No | Australia | Australia | 02-Analyze | Old - Conduct Design Workshops (AN) | RTR | FUN | SI | Onshore | Reed; Rodney | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-22 | 2016-11-22 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055334 | No | Yes | No | Australia | Australia | 03-Design/Build | Transition to Australia(D/B) | OTC | FUN | SI | Onshore | Kothari; Sanjay | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055335 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - HR | HR | HR | Saputo | Onshore | Freire; Roberto | Saputo | Yes | CapEx | Localization | IT - Internal | 3h | 0h | 3h | 2017-05-29 | 2017-05-29 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055336 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - HR | HR | HR | Saputo | Onshore | Freire; Roberto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055337 | No | No | Yes | Australia | Australia | 04-Test | Regression - Run Tests - HR | HR | HR | Saputo | Onshore | Freire; Roberto | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-05-17 | 2017-05-17 | Yes |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055338 | No | Yes | No | Australia | Australia | 02-Analyze | Old - Conduct Design Workshops (AN) | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-22 | 2016-11-22 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055339 | No | Yes | No | Australia | Australia | 02-Analyze | Old - Log Gaps (AN) | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2016-11-18 | 2016-12-09 | Yes |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055340 | No | Yes | No | Australia | Australia | 02-Analyze | Old - Create BPML (AN) | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055341 | No | Yes | No | Australia | Australia | 02-Analyze | Old - Perform Gap Resolution (AN) | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 38h | 0h | 38h | 2016-11-21 | 2016-12-14 | Yes |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055342 | No | Yes | No | Australia | Australia | 03-Design/Build | PDD-Baseline (D/B) | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055343 | No | Yes | No | Australia | Australia | 03-Design/Build | DDD-Baseline (D/B) | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055344 | No | Yes | No | Australia | Australia | 03-Design/Build | FSD-Baseline (D/B) | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055345 | No | Yes | No | Australia | Australia | 03-Design/Build | Support to Developpers (D/B) | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055346 | No | Yes | No | Australia | Australia | 03-Design/Build | DEV FUT- Baseline (D/B) | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055347 | No | Yes | No | Australia | Australia | 03-Design/Build | CONFIG-Baseline (D/B) | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055348 | No | Yes | No | Australia | Australia | 03-Design/Build | SDD Writing | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055349 | No | Yes | No | Australia | Australia | 03-Design/Build | CONFIG FUT-Baseline (D/B) | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2016-12-13 | 2017-01-03 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055350 | No | Yes | No | Australia | Australia | 03-Design/Build | Support MDM (D/B) | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | OpEx | Localization | IT - External | 38h | 0h | 38h | 2016-12-03 | 2016-12-19 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055351 | No | Yes | No | Australia | Australia | 03-Design/Build | Contribute to Cut-over Planning (D/B) - RTR | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-11-22 | 2016-12-16 | Yes |  |  | ACT.FUN.Support Cutover plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055352 | No | Yes | No | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2016-11-01 | 2016-11-02 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055353 | No | Yes | No | Australia | Australia | 02-Analyze | RTM (AN) | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-04 | 2016-11-04 | Yes |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055354 | No | Yes | No | Australia | Australia | 01-Preparation | Prepare KT) (PP) | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055355 | No | Yes | No | Australia | Australia | 01-Preparation | Conduct KT sessions) (PP) | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-29 | 2016-10-29 | Yes |  |  | WP.FUN.Requirements/Process Design Workshop Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055356 | No | Yes | No | Australia | Australia | 01-Preparation | Worshop Preparation Decks) (PP) | RTR | FUN | SI | Onshore | Gupta; Ajay | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2016-10-22 | 2016-10-30 | Yes |  |  | WP.FUN-107.Workshop Preparation Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055357 | No | Yes | No | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | LOG | FUN | SI | Onshore | Mauro; JuanPablo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055358 | No | Yes | No | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | LOG | FUN | SI | Onshore | Sniezyk; Sebastian | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055359 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia(D/B) | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055360 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - OTC | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 8h | 0h | 8h | 2017-05-15 | 2017-05-26 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055361 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - OTC | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-19 | 2017-06-19 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055362 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - OTC | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055363 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix - OTC | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 108h | 0h | 108h | 2017-07-10 | 2017-08-18 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 6 | 0 | 10 | 32 | 0 | 0 | 0 | 0 | 0
1055364 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - OTC | OTC | FUN | Saputo | Onshore | Esteves; Euler | Saputo | Yes | CapEx | Localization | IT - Internal | 58h | 0h | 58h | 2017-07-17 | 2017-08-04 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 2 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055365 | No | Yes | No | Australia | Australia | 02-Analyze | MCP Task | SEC | SEC | SI |  | Igwenazor; Stella | Other | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055366 | No | Yes | No | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | LOG | FUN | SI | Onshore | Iozzo; Tony | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-01-23 | 2017-02-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055367 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Preparation | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2017-03-13 | 2017-03-24 | Yes |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055368 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG010-FSD-Pick Confirmation to 3PL | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-27 | 2017-03-27 | Yes |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055369 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG006-FSD-EDI 3PL Pick Request | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2017-01-16 | 2017-02-15 | Yes |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055370 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG007-FSD-IEDI 3PL ASN | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-02-27 | 2017-03-03 | Yes |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055371 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG011-FSD-Lot Status Message to 3PL | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-01-16 | 2017-02-24 | Yes |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055372 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Preparation (KT with Test Team) | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-03-27 | 2017-04-05 | Yes |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055373 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - LOG | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 69h | 0h | 69h | 2017-06-01 | 2017-06-16 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 36 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055374 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - LOG | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2017-05-23 | 2017-06-01 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055375 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG006-DEV FUT-EDI 3PL Pick Request | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-03-06 | 2017-03-10 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055376 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG007-DEV FUT-EDI 3PL ASN | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2017-03-24 | 2017-04-07 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055377 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG011-DEV FUT-Lot Status Message to 3PL | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-06 | 2017-04-06 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055378 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG009-DEV FUT-EDI Outbound ASN sent to customers | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 23h | 0h | 23h | 2017-03-27 | 2017-04-06 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055379 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Break/Fix - LOG | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 120h | 0h | 120h | 2017-04-26 | 2017-05-26 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 27 | 9 | 30 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055380 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG007-ASS Prep-EDI 3PL ASN | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2017-03-27 | 2017-04-13 | Yes |  |  | ACT.FUN.Execute Assembly Tests | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055381 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG007-ASS Testing-EDI 3PL ASN | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 60h | 0h | 60h | 2017-04-17 | 2017-05-10 | Yes |  |  | ACT.FUN.Execute Assembly Tests | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 18 | 4 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055382 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG006-ASS Prep-EDI 3PL Pick Request | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2017-03-27 | 2017-04-06 | Yes |  |  | ACT.FUN.Execute Assembly Tests | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055383 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG006-ASS Testing-EDI 3PL Pick Request | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 38h | 0h | 38h | 2017-04-17 | 2017-06-01 | Yes |  |  | ACT.FUN.Execute Assembly Tests | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 4 | 3 | 10 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055384 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG010-ASS Prep-Pick Confirmation to 3PL | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2017-03-27 | 2017-04-13 | Yes |  |  | ACT.FUN.Execute Assembly Tests | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055385 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG010-ASS Testing-Pick Confirmation to 3PL | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 21h | 0h | 21h | 2017-04-17 | 2017-05-25 | Yes |  |  | ACT.FUN.Execute Assembly Tests | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055386 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG011-ASS Prep-Lot Status Message to 3PL | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2017-04-10 | 2017-04-13 | Yes |  |  | ACT.FUN.Execute Assembly Tests | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055387 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG011-Ass Testing-Lot Status Message to 3PL | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-05-08 | 2017-05-11 | Yes |  |  | ACT.FUN.Execute Assembly Tests | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055388 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Prepare - baseline - LOG | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2017-06-02 | 2017-06-02 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055389 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - LOG | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 74h | 0h | 74h | 2017-06-26 | 2017-07-03 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055390 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - LOG | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-05-01 | 2017-05-05 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055391 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Prepare | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055392 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG010-DEV FUT-Pick Confirmation to 3PL | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-27 | 2017-03-27 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055393 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - baseline - LOG | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 35h | 0h | 35h | 2017-06-20 | 2017-06-23 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055394 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - LOG | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 265h | 0h | 265h | 2017-07-03 | 2017-07-28 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 65 | 91 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055395 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | LOG | FUN | SI | Onshore | Ragothaman; Ramkumar | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-01-23 | 2017-01-27 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055396 | No | Yes | No | Australia | Australia | 03-Design/Build | Localization Vendor - DM (D/B) | MDG | DC | SI | Onshore | Mierski; Pawel | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055397 | No | Yes | No | Australia | Australia | 01-Preparation | Data Profiling (SAP) - DC) (PP) | MDG | DC | SI | Onshore | Mierski; Pawel | SAP | Yes | CapEx | Localization | IT - External | 584h | 0h | 584h | 2016-10-03 | 2017-03-10 | Yes |  |  | DELIV.MDG-050.Data Profiling | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 40 | 40 | 32 | 0 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055398 | No | Yes | No | Australia | Australia | 02-Analyze | Data Construction and staging - DC (AN) | MDG | DC | SI | Onshore | Mierski; Pawel | SAP | Yes | CapEx | Localization | IT - External | 224h | 0h | 224h | 2016-11-07 | 2017-01-06 | Yes |  |  | ACT.MDG.Data Construction | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055399 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - RTR | RTR | FUN | Saputo | Onshore | Valin; Eric | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055400 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - RTR | RTR | FUN | Saputo | Onshore | Valin; Eric | Saputo | Yes | CapEx | Localization | IT - Internal | 16h | 0h | 16h | 2017-05-15 | 2017-05-30 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055401 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - RTR | RTR | FUN | Saputo | Onshore | Valin; Eric | Saputo | Yes | CapEx | Localization | IT - Internal | 23h | 0h | 23h | 2017-05-15 | 2017-06-02 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055402 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - RTR | RTR | FUN | Saputo | Onshore | Valin; Eric | Saputo | Yes | CapEx | Localization | IT - Internal | 30h | 0h | 30h | 2017-06-05 | 2017-06-09 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055403 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - RTR | RTR | FUN | Saputo | Onshore | Valin; Eric | Saputo | Yes | CapEx | Localization | IT - Internal | 24h | 0h | 24h | 2017-06-20 | 2017-06-22 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055404 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix (Hypercare) - RTR | RTR | FUN | Saputo | Onshore | Valin; Eric | Saputo | Yes | CapEx | Localization | IT - Internal | 128h | 0h | 128h | 2017-07-06 | 2017-08-18 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 10 | 27 | 0 | 5 | 38 | 40 | 0 | 0 | 0 | 0 | 0
1055405 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - RTR | RTR | FUN | Saputo | Onshore | Valin; Eric | Saputo | Yes | CapEx | Localization | IT - Internal | 70h | 0h | 70h | 2017-07-24 | 2017-08-04 | Yes |  |  | ACT.FUN.Functional Break/Fix | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055406 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Prep-Data quality | RTR | FUN | Saputo | Onshore | Valin; Eric | Saputo | Yes | CapEx | Localization | IT - Internal | 34h | 0h | 34h | 2017-04-13 | 2017-04-28 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055407 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | ACT.MDG.Mock Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055408 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Execute - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | Yes |  |  | ACT.MDG.Mock Load | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055409 | No | No | Yes | Australia | Australia | 04-Test | Data collection templates - explain and collect - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 79.5h | 0h | 79.5h | 2016-12-19 | 2017-03-26 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 19 | 0 | 23 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055410 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Validate - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | OpEx | Localization | IT - External | 72h | 0h | 72h | 2017-04-17 | 2017-05-05 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055411 | No | No | Yes | Australia | Australia | 04-Test | Data load - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 154.5h | 0h | 154.5h | 2017-03-27 | 2017-04-13 | Yes |  |  | ACT.MDG.Mock Load | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 54.5 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055412 | No | No | Yes | Australia | Australia | 02-Analyze | Data Construction and staging - DC (AN) | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 189h | 0h | 189h | 2016-12-19 | 2017-03-13 | Yes |  |  | ACT.MDG.Data Construction | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 40.5 | 22.5 | 19 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055413 | No | No | Yes | Australia | Australia | 04-Test | Mock1 – Manage defect (Capex) - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-04-24 | 2017-04-28 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055414 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-10 | 2017-04-10 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055415 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate - DC | MDG | DC | SI | Offshore | Valentino; Kevin | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-05-08 | 2017-05-12 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055416 | No | No | Yes | Australia | Australia | 03-Design/Build | FOTC007-FSD-Order acknowledgement form - domestic | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | DELIV.FUN-204.Functional Specification - Form | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055417 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD128-Broker Determination | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055418 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD129-Sales Representatives | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055419 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia(D/B) | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055420 | No | No | Yes | Australia | Australia | 03-Design/Build | FOTC007-DEV FUT-Order acknowledgement form - domestic | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 37h | 0h | 37h | 2017-03-27 | 2017-03-31 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055421 | No | No | Yes | Australia | Australia | 02-Analyze | AUS Deep Dive for freight | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-25 | 2017-01-27 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055422 | No | No | Yes | Australia | Australia | 02-Analyze | AUS Deep Dive for Billing Corrections | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055423 | No | No | Yes | Australia | Australia | 03-Design/Build | XXX-DEV FUT-Order acknowledgement form - export | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-21 | 2017-03-21 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055424 | No | No | Yes | Australia | Australia | 03-Design/Build | Security Roles - Support (D/B) | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 135h | 0h | 135h | 2017-02-27 | 2017-04-07 | Yes |  |  | DELIV.SEC-201.Security Role Detailed Design | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 45 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055425 | No | No | Yes | Australia | Australia | 03-Design/Build | Training Materials Localization - Support (D/B) - OTC | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | OpEx | Localization | IT - External | 125h | 0h | 125h | 2017-03-06 | 2017-04-21 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 8 | 0 | 45 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055426 | No | No | Yes | Australia | Australia | 02-Analyze | AUS Deep Dive: Batch Determination | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 2.5h | 0h | 2.5h | 2017-01-24 | 2017-01-27 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055427 | No | No | Yes | Australia | Australia | 02-Analyze | AUS Deep Dive: Trade ECC Rebates & Commissions | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-01-25 | 2017-01-25 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055428 | No | No | Yes | Australia | Australia | 02-Analyze | AUS: Sell-Through Process | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055429 | No | No | Yes | Australia | Australia | 02-Analyze | AUS: Reporting (ECC vs. BI) | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055430 | No | No | Yes | Australia | Australia | 02-Analyze | AUS Deep Dive on Pricing upload program | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055431 | No | No | Yes | Australia | Australia | 03-Design/Build | IOTC008-FSD-ECC/GTS to BSM Order | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055432 | No | No | Yes | Australia | Australia | 03-Design/Build | OTC_02-CONFIG FUT-Customer and Material Master | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055433 | No | No | Yes | Australia | Australia | 03-Design/Build | XXX-FSD-Placeholderx | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055434 | No | No | Yes | Australia | Australia | 03-Design/Build | IOTC008-DEV FUT-ECC/GTS to BSM Order | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055435 | No | No | Yes | Australia | Australia | 03-Design/Build | XXX-DEV FUT-Rebates selement report | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055436 | No | No | Yes | Australia | Australia | 02-Analyze | AUS Deep Dive: Export Process considering BSM In Scope | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-24 | 2017-01-24 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055437 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Prepare | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055438 | No | No | Yes | Australia | Australia | 03-Design/Build | DEV FUT- Baseline (D/B) | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055439 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD243-Customer Master - Plants | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055440 | No | No | Yes | Australia | Australia | 03-Design/Build | OTC_02-CONFIG-Customer and Material Master | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055441 | No | No | Yes | Australia | Australia | 02-Analyze | AUS Deep Dive for Master Data (Customer and Material Master) | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-01-23 | 2017-01-27 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055442 | No | No | Yes | Australia | Australia | 02-Analyze | AUS: GOI Joint Venture | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-01-25 | 2017-01-25 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055443 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - OTC | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055444 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - OTC | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 17h | 0h | 17h | 2017-06-05 | 2017-06-09 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055445 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - OTC | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-06-19 | 2017-07-02 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055446 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Prepare - OTC | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055447 | No | No | Yes | Australia | Australia | 02-Analyze | AUS Deep Dive: One Customer | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 1.3h | 0h | 1.3h | 2017-01-24 | 2017-01-24 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055448 | No | No | Yes | Australia | Australia | 02-Analyze | AUS Deep Dive Order to Cash Process Flow (with EDI and 3PLs) | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2017-01-25 | 2017-02-03 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055449 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD145-Sales, Delivery and Billing pre-defined Texts | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-01-23 | 2017-02-16 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055450 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD132-Contact Person | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 19h | 0h | 19h | 2017-01-16 | 2017-02-17 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055451 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD127-Customer Hierarchy - Assignment | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2017-02-22 | 2017-02-24 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055452 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD137-EDI Partner Profile | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-02-06 | 2017-02-10 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055453 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD138-Material Determination | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-01-30 | 2017-02-03 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055454 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD139-Customer Material Info Record | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 15.4h | 0h | 15.4h | 2017-01-23 | 2017-02-03 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 5.4 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055455 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD144-Output Order (EDI, Printout, Fax, e-mail) | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-01-23 | 2017-02-10 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055456 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD118-Customer Master - Indirect Customers (End-User) | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055457 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD119-Customer Master - Brokers | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-02-20 | 2017-02-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055458 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD120-Customer Master - Ports | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2017-02-20 | 2017-02-22 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055459 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD121-Customer Master - Inter/Intra-company | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-02-20 | 2017-02-24 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055460 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD122-Customer Master - EDI Trading Partners | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2017-02-20 | 2017-02-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055461 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD124-Customer Master - Financial Customers / Farmers | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055462 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD125-Customer Master - One time customers | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 13h | 0h | 13h | 2017-01-27 | 2017-02-24 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055463 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD126-Customer Hierarchy - Nodes | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2017-02-22 | 2017-02-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055464 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD117-Customer Master - Direct customers (SP,SH,BP,PY) | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-01-25 | 2017-02-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 15 | 20 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055465 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 144h | 0h | 144h | 2017-04-24 | 2017-05-14 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 51 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055466 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Preparation | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 54h | 0h | 54h | 2017-03-20 | 2017-04-18 | Yes |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055467 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - OTC | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 84.3h | 0h | 84.3h | 2017-05-15 | 2017-06-04 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 17.5 | 31.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055468 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix - OTC | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055469 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Prep | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2017-05-18 | 2017-06-02 | Yes |  |  | ACT.FUN.UAT Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055470 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - OTC | OTC | FUN | SI | Offshore | Mali; Harshal | IBM | Yes | CapEx | Localization | IT - External | 21.2h | 0h | 21.2h | 2017-05-08 | 2017-05-30 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055471 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - RTR | RTR | FUN | Saputo | Onshore | Therien; Stephane | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055472 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - RTR | RTR | FUN | Saputo | Onshore | Therien; Stephane | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055473 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - RTR | RTR | FUN | Saputo | Onshore | Therien; Stephane | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055474 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - RTR | RTR | FUN | Saputo | Onshore | Therien; Stephane | Saputo | Yes | CapEx | Localization | IT - Internal | 40h | 0h | 40h | 2017-06-19 | 2017-06-22 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055475 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - RTR | RTR | FUN | Saputo | Onshore | Therien; Stephane | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT.FUN.Functional Break/Fix | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055476 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix (Hypercare) - RTR | RTR | FUN | Saputo | Onshore | Therien; Stephane | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055477 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Communication Plan (C/G) | CM | CM | Saputo | Onshore | Gabra; Rania | Saputo | Yes | OpEx | Localization | IT - Internal | 87h | 0h | 87h | 2017-06-05 | 2017-06-29 | Yes |  |  | DELIV.CM-106.Communication Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 22 | 23 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055478 | No | No | Yes | Australia | Australia | 06-Hypercare | Communication plan execution and monitoring (HYP) | CM | CM | Saputo | Onshore | Gabra; Rania | Saputo | Yes | OpEx | Localization | IT - Internal | 52h | 6h | 58h | 2017-07-03 | 2017-09-29 | Yes |  |  | ACT.CM.Communication plan execution and monitoring | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 5 | 0 | 0 | 4 | 1 | 15 | 4 | 4 | 0 | 3 | 0
1055479 | No | No | Yes | Australia | Australia | 04-Test | Communication Plan (Test) | CM | CM | Saputo | Onshore | Gabra; Rania | Saputo | Yes | OpEx | Localization | IT - Internal | 53h | 0h | 53h | 2017-05-01 | 2017-06-02 | Yes |  |  | DELIV.CM-106.Communication Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 16 | 0 | 6 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055480 | No | No | Yes | Australia | Australia | 03-Design/Build | Communication Plan (D/B) | CM | CM | Saputo | Onshore | Gabra; Rania | Saputo | Yes | OpEx | Localization | IT - Internal | 102.5h | 0h | 102.5h | 2017-03-13 | 2017-04-28 | Yes |  |  | DELIV.CM-106.Communication Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 4 | 15 | 17 | 5 | 16.5 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055481 | No | No | Yes | Australia | Australia | 02-Analyze | Communication plan(AN) | CM | CM | Saputo | Onshore | Gabra; Rania | Saputo | Yes | OpEx | Localization | IT - Internal | 112h | 0h | 112h | 2017-02-06 | 2017-03-10 | Yes |  |  | DELIV.CM-106.Communication Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 4 | 37 | 26 | 42.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055482 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-26 | 2016-10-26 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055483 | No | No | Yes | Australia | Australia | 01-Preparation | Conduct KT sessions) (PP) | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  | WP.FUN.Requirements/Process Design Workshop Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055484 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia - (Capex) - (D/B) | PTM | FUN | SI | Onshore | Narayanan; Arun | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055485 | No | No | No | Australia | Australia | 03-Design/Build | Legacy System Retirement Strategy | PMO | PMO | Saputo | Onshore | Keen; Peter | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | DELIV.TAI-130.Legacy System Retirement strategy | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055486 | No | No | No | Australia | Australia | 04-Test | Mock1 - Prepare |  | Missing Stream | Saputo | Onshore | McCarthy; Peter | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055487 | No | Yes | No | Australia | Australia | 03-Design/Build | Technical Architecture Specification (D/B) | TAI | TAI | SI | Onshore | Kingbo; David | Accenture | Yes | CapEx | Localization | IT - External | 352h | 0h | 352h | 2016-12-12 | 2017-03-03 | Yes |  |  | DELIV.TAI-002.Technical Architecture Specification | Complete | NA | NA | 0 |  |  | 0 | 0 | 8 | 32 | 40 | 40 | 40 | 32 | 0 | 16 | 32 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055488 | No | Yes | No | Australia | Australia | 02-Analyze | Technology Implementation plan (update) (AN) | TAI | TAI | SI | Onshore | Kingbo; David | Accenture | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2016-11-21 | 2016-12-09 | Yes |  |  | DELIV.TAI-001.Technology Implementation Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055489 | No | Yes | No | Australia | Australia | 03-Design/Build | Transition to Australia - (Capex) - (D/B) |  | Missing Stream | Saputo | Onshore | Westerveld; Bruce | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055490 | No | No | Yes | Australia | Australia | 03-Design/Build | PDD-Manage Quality Inspections | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055491 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia - (Capex) - (D/B) | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055492 | No | No | Yes | Australia | Australia | 03-Design/Build | Management (D/B) - PTM | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 18h | 0h | 18h | 2017-01-31 | 2017-02-08 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055493 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - PTM | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 92h | 0h | 92h | 2017-07-03 | 2017-07-20 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 46 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055494 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix - PTM | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055495 | No | No | Yes | Australia | Australia | 02-Analyze | Fit/Gaps Analysis (AN) | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 42h | 0h | 42h | 2017-01-09 | 2017-01-13 | Yes |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055496 | No | No | Yes | Australia | Australia | 02-Analyze | RTM (AN) | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 21h | 0h | 21h | 2016-11-13 | 2017-01-20 | Yes |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055497 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD249-Material Master Sales Org 1 Tax | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-24 | 2017-02-24 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055498 | No | No | Yes | Australia | Australia | 03-Design/Build | PDD-Manage Procurement for Milk & Equivalents | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 32h | 0h | 32h | 2017-01-30 | 2017-04-07 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 12 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055499 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Preparation | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 63h | 0h | 63h | 2017-03-13 | 2017-04-21 | Yes |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 14 | 13 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055500 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Support | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | OpEx | Localization | IT - Internal | 16h | 0h | 16h | 2017-03-20 | 2017-04-13 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055501 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD096-Purchasing Contract | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-15 | 2017-02-15 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055502 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD099-Source Lists | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 12h | 0h | 12h | 2017-03-13 | 2017-03-24 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055503 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD100-Open Purchase Orders | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-20 | 2017-02-20 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055504 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 300h | 0h | 300h | 2017-04-24 | 2017-06-29 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 49 | 48 | 27 | 0 | 48 | 49 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055505 | No | No | Yes | Australia | Australia | 03-Design/Build | SDD Writing (D/B) | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 20h | 0h | 20h | 2017-01-27 | 2017-04-19 | Yes |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055506 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD060-Material Type ZFG - Finished Products | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055507 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD064-Material Type ZRAW - Raw Materials | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 25h | 0h | 25h | 2017-02-13 | 2017-03-24 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 5 | 8 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055508 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD065-Material Type ZPAC - Packaging Materials | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 29h | 0h | 29h | 2017-02-13 | 2017-03-24 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 5 | 8 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055509 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD062-Material Type ZTRA - Trading Goods | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055510 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD061-Material Type ZSFG - Semi-Finished Products | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055511 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD067-Material Type ZSPA - Spare parts | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 9h | 0h | 9h | 2017-02-13 | 2017-03-17 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055512 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD068-Material Type ZSER - Service Materials | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055513 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD069-Material Type ZMAS - Maintenance Assemblies | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055514 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD070-Material Type ZMIL - DMS Copy from UNBW | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055515 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD071-Material Type ZCMP - DMS Copy from ROH (differentiated) | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055516 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD074-Material Master classification | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055517 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD075-Material Master characteristics | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055518 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD262-Material Type ZRET - Returnable packaging | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055519 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GDXXX-Material Type ZMPN- Manufacturer Part Number | PTM | FUN | Saputo | Onshore | Habib; Mustafa | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055520 | No | No | Yes | Australia | Australia | 03-Design/Build | IOTC007-DEV FUT-EDI Outbound Order Response | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-10 | 2017-04-10 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055521 | No | No | Yes | Australia | Australia | 03-Design/Build | IOTC009-DEV FUT-EDI Outbound Invoice | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 55h | 0h | 55h | 2017-04-03 | 2017-04-21 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055522 | No | No | Yes | Australia | Australia | 02-Analyze | AUS Deep Dive: One Customer | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 4.5h | 0h | 4.5h | 2017-01-24 | 2017-02-01 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055523 | No | No | Yes | Australia | Australia | 02-Analyze | AUS Deep Dive Order to Cash Process Flow (with EDI and 3PLs) | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 1.5h | 0h | 1.5h | 2017-01-25 | 2017-01-25 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055524 | No | No | Yes | Australia | Australia | 03-Design/Build | XXX-FSD-Rebates selement report | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-10 | 2017-02-10 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055525 | No | No | Yes | Australia | Australia | 02-Analyze | AUS Deep Dive on Pricing upload program | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055526 | No | No | Yes | Australia | Australia | 02-Analyze | AUS Deep Dive for Master Data (Customer and Material Master) | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055527 | No | No | Yes | Australia | Australia | 02-Analyze | AUS: Reporting (ECC vs. BI) | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-01-23 | 2017-02-01 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055528 | No | No | Yes | Australia | Australia | 02-Analyze | AUS: Sell-Through Process | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2017-01-23 | 2017-01-31 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055529 | No | No | Yes | Australia | Australia | 02-Analyze | AUS Deep Dive: Batch Determination | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 3.5h | 0h | 3.5h | 2017-01-24 | 2017-01-30 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055530 | No | No | Yes | Australia | Australia | 02-Analyze | AUS Deep Dive: Export Process considering BSM In Scope | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-01-24 | 2017-02-03 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055531 | No | No | Yes | Australia | Australia | 02-Analyze | AUS Deep Dive: Trade ECC Rebates & Commissions | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-25 | 2017-01-25 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055532 | No | No | Yes | Australia | Australia | 02-Analyze | AUS: GOI Joint Venture | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-01-25 | 2017-02-03 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055533 | No | No | Yes | Australia | Australia | 03-Design/Build | Training Materials Localization - Support (D/B) - OTC | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | OpEx | Localization | IT - External | 84h | 0h | 84h | 2017-03-06 | 2017-04-21 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 8 | 15 | 16 | 5 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055534 | No | No | Yes | Australia | Australia | 03-Design/Build | Security Roles - Support (D/B) | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 77h | 0h | 77h | 2017-03-06 | 2017-04-21 | Yes |  |  | DELIV.SEC-201.Security Role Detailed Design | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 8 | 15 | 4 | 5 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055535 | No | No | Yes | Australia | Australia | 02-Analyze | AUS Deep Dive for Billing Corrections | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055536 | No | No | Yes | Australia | Australia | 02-Analyze | AUS Deep Dive for freight | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-25 | 2017-01-25 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055537 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia(D/B) | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2017-01-30 | 2017-02-03 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055538 | No | No | Yes | Australia | Australia | 03-Design/Build | IOTC009-FSD-EDI Outbound Invoice | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 77h | 0h | 77h | 2017-02-06 | 2017-03-03 | Yes |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 25 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055539 | No | No | Yes | Australia | Australia | 03-Design/Build | IOTC007-FSD-EDI Outbound Order Response | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2017-02-06 | 2017-03-03 | Yes |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055540 | No | No | Yes | Australia | Australia | 03-Design/Build | FOTC007-FSD-Order acknowledgement form - domestic | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-02-06 | 2017-02-10 | Yes |  |  | DELIV.FUN-204.Functional Specification - Form | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055541 | No | No | Yes | Australia | Australia | 03-Design/Build | XXX-FSD-Order acknowledgement form - export | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055542 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Support | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | OpEx | Localization | IT - External | 10h | 0h | 10h | 2017-04-03 | 2017-04-07 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055543 | No | No | Yes | Australia | Australia | 03-Design/Build | XXX-DEV FUT-Rebates selement report | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2017-03-13 | 2017-03-16 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055544 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - OTC | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 19h | 0h | 19h | 2017-06-03 | 2017-06-16 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055545 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Prep | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-05-15 | 2017-05-19 | Yes |  |  | ACT.FUN.UAT Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055546 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix - OTC | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 210h | 0h | 210h | 2017-07-10 | 2017-08-04 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055547 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - OTC | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 52h | 0h | 52h | 2017-05-15 | 2017-06-04 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055548 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Preparation | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 59h | 0h | 59h | 2017-03-13 | 2017-04-15 | Yes |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 15 | 16 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055549 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 47h | 0h | 47h | 2017-04-24 | 2017-05-14 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 13 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055550 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Break/Fix - OTC | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 37h | 0h | 37h | 2017-04-24 | 2017-05-14 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 12 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055551 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - OTC | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 52h | 0h | 52h | 2017-05-22 | 2017-06-04 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055552 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Prepare - OTC | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 92h | 0h | 92h | 2017-06-26 | 2017-07-09 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055553 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - OTC | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2017-06-26 | 2017-06-30 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055554 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - OTC | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 75h | 0h | 75h | 2017-06-05 | 2017-06-23 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 20 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055555 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - OTC | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 30h | 0h | 30h | 2017-06-05 | 2017-06-16 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055556 | No | No | Yes | Australia | Australia | 03-Design/Build | IOTC007-ASS Testing-EDI Outbound Order Response | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 52h | 0h | 52h | 2017-04-24 | 2017-05-19 | Yes |  |  | ACT.FUN.Execute Assembly Tests | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 12 | 20 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055557 | No | No | Yes | Australia | Australia | 03-Design/Build | IOTC009-ASS Testing-EDI Outbound Invoice | OTC | FUN | SI | Offshore | Hasan; Niyazul | IBM | Yes | CapEx | Localization | IT - External | 38h | 0h | 38h | 2017-04-24 | 2017-05-19 | Yes |  |  | ACT.FUN.Execute Assembly Tests | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055558 | No | No | Yes | Australia | Australia |  | Data Governance – Change Process - DG | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055559 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Vendor Master - Saputo - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055560 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Financial Objects - Saputo - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055561 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Vendor Master - Saputo - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-19 | 2017-06-19 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055562 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Financial Objects - Saputo - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-19 | 2017-06-19 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055563 | No | No | Yes | Australia | Australia | 03-Design/Build | Test preparation (Saputo) - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 40h | 0h | 40h | 2017-04-10 | 2017-04-21 | Yes |  |  | DELIV.TST-307.Assembly Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055564 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Validate - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-19 | 2017-06-19 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055565 | No | No | Yes | Australia | Australia | 06-Hypercare | HC - Provide end User Supprt (Opex) - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055566 | No | No | Yes | Australia | Australia | 04-Test | Test Preparation (Saputo) - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 10h | 0h | 10h | 2017-04-24 | 2017-04-28 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055567 | No | No | Yes | Australia | Australia | 06-Hypercare | HC - Vendor Master - Saputo - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055568 | No | No | Yes | Australia | Australia | 06-Hypercare | HC - Financial Objects - Saputo - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055569 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run tests (Saputo) - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 86h | 0h | 86h | 2017-05-01 | 2017-05-12 | Yes |  |  | ACT.MDG.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055570 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run tests (Saputo) - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 65h | 0h | 65h | 2017-05-15 | 2017-05-26 | Yes |  |  | ACT.MDG.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055571 | No | No | Yes | Australia | Australia | 04-Test | Non Regression - Run tests (Saputo) - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 5h | 0h | 5h | 2017-05-29 | 2017-06-02 | Yes |  |  | ACT.MDG.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055572 | No | No | Yes | Australia | Australia | 04-Test | Non Regression - Manage defects (Capex) (Saputo) MDG-DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | CapEx | Localization | IT - Internal | 7h | 0h | 7h | 2017-05-23 | 2017-05-31 | Yes |  |  | ACT.MDG.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055573 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Prep (Select Scenarios) (Saputo) - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 9h | 0h | 9h | 2017-05-23 | 2017-06-02 | Yes |  |  | ACT.MDG.UAT Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055574 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests (Saputo) - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055575 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Manage Defects (Saputo) (Capex) - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055576 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix (Saputo) - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055577 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Document work around (Saputo)- DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055578 | No | No | Yes | Australia | Australia | 03-Design/Build | Training Train-the-Trainer Vendor - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055579 | No | No | Yes | Australia | Australia | 03-Design/Build | Training Train-the-Trainer Finance - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055580 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Support (Dual maintenance) - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055581 | No | No | Yes | Australia | Australia | 04-Test | Retrofit Testing (Saputo) - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 5h | 0h | 5h | 2017-05-29 | 2017-06-02 | Yes |  |  | ACT.MDG.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055582 | No | No | Yes | Australia | Australia |  | Data Governance – Change Process - DG | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 32h | 0h | 32h | 2017-04-10 | 2017-04-13 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055583 | No | No | Yes | Australia | Australia | 04-Test | Functional Testing (Saputo) - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-18 | 2017-04-18 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055584 | No | No | Yes | Australia | Australia | 04-Test | Harmoni Program Governance and Cross Functional Work (Saputo) - DM | MDG | DM | Saputo | Onshore | Sferlazza; Vincent | Saputo | Yes | OpEx | Localization | IT - Internal | 26h | 0h | 26h | 2017-04-24 | 2017-06-02 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055585 | No | No | Yes | Australia | Australia | 03-Design/Build | Development (D/B) | DEV | DEV | SI | Offshore | Trivedi; Mohit | IBM | Yes | CapEx | Localization | IT - External | 74.2h | 0h | 74.2h | 2017-03-06 | 2017-04-21 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 22.5 | 18 | 11.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055586 | No | No | Yes | Australia | Australia | 06-Hypercare | Development (Hypercare) - DEV | DEV | DEV | SI | Offshore | Trivedi; Mohit | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-04 | 2017-05-04 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055587 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Development (Cutover/Go-live) - DEV | DEV | DEV | SI | Offshore | Trivedi; Mohit | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-06-19 | 2017-06-20 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055588 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT1) | DEV | DEV | SI | Offshore | Trivedi; Mohit | IBM | Yes | CapEx | Localization | IT - External | 67.5h | 0h | 67.5h | 2017-04-24 | 2017-06-09 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.2 | 11.2 | 11.2 | 11.2 | 11.2 | 0 | 11.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055589 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT2) | DEV | DEV | SI | Offshore | Trivedi; Mohit | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-05-29 | 2017-06-16 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055590 | No | No | Yes | Australia | Australia |  | AUS - DEV KT | DEV | DEV | SI | Offshore | Trivedi; Mohit | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-31 | 2017-05-31 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055591 | No | Yes | No | Australia | Australia | 04-Test | Mock1 - Support | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | OpEx | Localization | IT - External | 14h | 0h | 14h | 2017-03-27 | 2017-04-28 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055592 | No | Yes | No | Australia | Australia | 04-Test | Mock1 - Validate | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | OpEx | Localization | IT - External | 17h | 0h | 17h | 2017-05-01 | 2017-05-26 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055593 | No | Yes | No | Australia | Australia | 03-Design/Build | KT sessions (D/B) | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-03-17 | 2017-06-08 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 10 | 0 | 2 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055594 | No | Yes | No | Australia | Australia | 04-Test | SIT 2 - Break/Fix - RTR | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 30h | 0h | 30h | 2017-05-15 | 2017-06-04 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055595 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - RTR | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2017-06-05 | 2017-06-30 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 13 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055596 | No | Yes | No | Australia | Australia | 02-Analyze | RTM (AN) | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-04 | 2016-11-09 | Yes |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055597 | No | Yes | No | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055598 | No | Yes | No | Australia | Australia | 03-Design/Build | Contribute to Cut-over Planning (D/B) - RTR | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-22 | 2016-11-22 | Yes |  |  | ACT.FUN.Support Cutover plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055599 | No | Yes | No | Australia | Australia | 03-Design/Build | Support MDM (D/B) | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-03 | 2016-12-03 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055600 | No | Yes | No | Australia | Australia | 03-Design/Build | CONFIG FUT-Baseline (D/B) | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-13 | 2016-12-13 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055601 | No | Yes | No | Australia | Australia | 03-Design/Build | SDD Writing | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055602 | No | Yes | No | Australia | Australia | 03-Design/Build | DEV FUT- Baseline (D/B) | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055603 | No | Yes | No | Australia | Australia | 03-Design/Build | CONFIG-Baseline (D/B) | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055604 | No | Yes | No | Australia | Australia | 03-Design/Build | FSD-Baseline (D/B) | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055605 | No | Yes | No | Australia | Australia | 03-Design/Build | Support to Developpers (D/B) | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055606 | No | Yes | No | Australia | Australia | 03-Design/Build | DDD-Baseline (D/B) | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2017-01-10 | 2017-01-12 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055607 | No | Yes | No | Australia | Australia | 03-Design/Build | PDD-Baseline (D/B) | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055608 | No | Yes | No | Australia | Australia | 02-Analyze | Old - Perform Gap Resolution (AN) | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-21 | 2016-11-21 | Yes |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055609 | No | Yes | No | Australia | Australia | 02-Analyze | Old - Conduct Design Workshops (AN) | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-22 | 2016-11-22 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055610 | No | Yes | No | Australia | Australia | 02-Analyze | Old - Log Gaps (AN) | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-11 | 2016-11-11 | Yes |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055611 | No | Yes | No | Australia | Australia | 02-Analyze | Old - Create BPML (AN) | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055612 | No | Yes | No | Australia | Australia | 03-Design/Build | DDD-GD015-G/L Balances | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 52h | 0h | 52h | 2017-02-13 | 2017-02-19 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055613 | No | Yes | No | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 14h | 0h | 14h | 2017-01-30 | 2017-02-03 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055614 | No | Yes | No | Australia | Australia | 06-Hypercare | Break/Fix (Hypercare) - RTR | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-07-04 | 2017-07-23 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055615 | No | Yes | No | Australia | Australia | 01-Preparation | Worshop Preparation Decks) (PP) | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2016-10-14 | 2016-10-17 | Yes |  |  | WP.FUN-107.Workshop Preparation Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055616 | No | Yes | No | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - RTR | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 33h | 0h | 33h | 2017-07-04 | 2017-07-30 | Yes |  |  | ACT.FUN.Functional Break/Fix | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055617 | No | Yes | No | Australia | Australia | 03-Design/Build | GL_01-CONFIG-Definition and assignment of Organization structure | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-01-30 | 2017-02-03 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055618 | No | Yes | No | Australia | Australia | 03-Design/Build | GL_02-CONFIG-Fiscal Year and Posting periods | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-01-30 | 2017-02-03 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055619 | No | Yes | No | Australia | Australia | 03-Design/Build | GL_03-CONFIG-New General Ledger | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-02-06 | 2017-02-10 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055620 | No | Yes | No | Australia | Australia | 03-Design/Build | GL_04-CONFIG-GL-General Settings | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055621 | No | Yes | No | Australia | Australia | 03-Design/Build | GL_06-CONFIG-GL Assignment | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055622 | No | Yes | No | Australia | Australia | 03-Design/Build | Conversion AUS support (D/B) | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 71h | 0h | 71h | 2017-03-06 | 2017-04-02 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 4 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055623 | No | Yes | No | Australia | Australia | 03-Design/Build | Workaround Procedures (D/B) | RTR | FUN | SI | Onshore | Docot; William | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055624 | No | Yes | No | Australia | Australia | 06-Hypercare | Development (Hypercare) - DEV | DEV | DEV | SI | Onshore | Gilbert; Marc | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-04 | 2017-05-04 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055625 | No | Yes | No | Australia | Australia | 04-Test | Development (SIT1) | DEV | DEV | SI | Onshore | Gilbert; Marc | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055626 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Development (Cutover/Go-live) - DEV | DEV | DEV | SI | Onshore | Gilbert; Marc | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-02 | 2017-06-02 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055627 | No | Yes | No | Australia | Australia | 04-Test | Development (SIT2) | DEV | DEV | SI | Onshore | Gilbert; Marc | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055628 | No | Yes | No | Australia | Australia |  | AUS - DEV KT | DEV | DEV | SI | Onshore | Gilbert; Marc | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-31 | 2017-05-31 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055629 | No | Yes | No | Australia | Australia | 03-Design/Build | Development (D/B) | DEV | DEV | SI | Onshore | Gilbert; Marc | IBM | Yes | CapEx | Localization | IT - External | 54h | 0h | 54h | 2017-03-06 | 2017-03-28 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 18 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055630 | No | Yes | No | Australia | Australia | 03-Design/Build | Transition to Australia(D/B) | OTC | FUN | SI | Onshore | Teixeira; Adilson | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055631 | No | Yes | No | Australia | Australia | 03-Design/Build | XXX-FSD-MTS to MII | PTM | FUN | SI | Onshore | Sulyman; Ola | IBM | Yes | CapEx | Localization | IT - External | 284h | 0h | 284h | 2017-03-06 | 2017-04-18 | Yes |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 44 | 44 | 44 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055632 | No | Yes | No | Australia | Australia | 02-Analyze | Kickoff (AN) | PTM | FUN | SI | Onshore | Sulyman; Ola | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055633 | No | Yes | No | Australia | Australia | 02-Analyze | RTM (AN) | PTM | FUN | SI | Onshore | Sulyman; Ola | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2017-01-09 | 2017-01-20 | Yes |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055634 | No | Yes | No | Australia | Australia | 03-Design/Build | Transition to Australia - (Capex) - (D/B) | PTM | FUN | SI | Onshore | Sulyman; Ola | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055635 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Preparation | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 162h | 0h | 162h | 2017-03-07 | 2017-04-21 | Yes |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 45 | 27 | 18 | 9 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055636 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Support | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | OpEx | Localization | IT - External | 72h | 0h | 72h | 2017-03-27 | 2017-04-13 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 27 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055637 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 125.35h | 0h | 125.35h | 2017-04-24 | 2017-05-14 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.35 | 45 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055638 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Break/Fix - PTM | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 11.65h | 0h | 11.65h | 2017-04-24 | 2017-04-28 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055639 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - PTM | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 85h | 0h | 85h | 2017-05-15 | 2017-05-26 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055640 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - PTM | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-05-29 | 2017-06-02 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055641 | No | No | Yes | Australia | Australia | 02-Analyze | Kickoff (AN) | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 117h | 0h | 117h | 2016-10-24 | 2017-01-20 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 27 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055642 | No | No | Yes | Australia | Australia | 02-Analyze | RTM (AN) | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-13 | 2016-11-13 | Yes |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055643 | No | No | Yes | Australia | Australia | 03-Design/Build | PP_01-CONFIG FUT-PP Enterprise Structure | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-02-06 | 2017-02-10 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055644 | No | No | Yes | Australia | Australia | 03-Design/Build | PP_02-CONFIG FUT-Basic Data | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-24 | 2017-02-24 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055645 | No | No | Yes | Australia | Australia | 03-Design/Build | PP_03-CONFIG FUT-Material Requirements Planning | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-24 | 2017-02-24 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055646 | No | No | Yes | Australia | Australia | 03-Design/Build | PP_04-CONFIG FUT-Production Planning for Process Industries | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-02-13 | 2017-02-17 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055647 | No | No | Yes | Australia | Australia | 03-Design/Build | PP_02-CONFIG-Basic Data | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-01-23 | 2017-01-27 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055648 | No | No | Yes | Australia | Australia | 03-Design/Build | PP_03-CONFIG-Material Requirements Planning | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-01-30 | 2017-02-03 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055649 | No | No | Yes | Australia | Australia | 03-Design/Build | PP_04-CONFIG-Production Planning for Process Industries | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-02-20 | 2017-02-24 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055650 | No | No | Yes | Australia | Australia | 03-Design/Build | PP_01-CONFIG-PP Enterprise Structure | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-20 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055651 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Validate | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | OpEx | Localization | IT - External | 18h | 0h | 18h | 2017-03-09 | 2017-03-10 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055652 | No | No | Yes | Australia | Australia | 04-Test | Regression - Run Tests - PTM | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-06-05 | 2017-06-08 | Yes |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055653 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-01-23 | 2017-03-03 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055654 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-05-08 | 2017-05-12 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055655 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - PTM | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-05-15 | 2017-05-19 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055656 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - PTM | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055657 | No | No | Yes | Australia | Australia | 04-Test | Regression - Manage defects (Capex) - PTM | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055658 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Validate | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055659 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - PTM | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-06-27 | 2017-06-30 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055660 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - PTM | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-06-19 | 2017-06-23 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055661 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - PTM | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055662 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Prep | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-06-12 | 2017-06-16 | Yes |  |  | ACT.FUN.UAT Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055663 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix - PTM | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 135h | 0h | 135h | 2017-07-03 | 2017-08-11 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0
1055664 | No | No | Yes | Australia | Australia | 03-Design/Build | FPTM005-DEV FUT-Raw material GI | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055665 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - PTM | PTM | FUN | SI | Offshore | Parulekar; Manisha | IBM | Yes | CapEx | Localization | IT - External | 216h | 0h | 216h | 2017-07-10 | 2017-07-28 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 72 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055666 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix - OTC | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055667 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Prep | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2017-05-19 | 2017-05-26 | Yes |  |  | ACT.FUN.UAT Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055668 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - OTC | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055669 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - OTC | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 72h | 0h | 72h | 2017-05-15 | 2017-05-25 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055670 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 110h | 0h | 110h | 2017-04-24 | 2017-05-14 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 36 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055671 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - OTC | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 53h | 0h | 53h | 2017-06-01 | 2017-06-08 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055672 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - OTC | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 123h | 0h | 123h | 2017-05-29 | 2017-06-23 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 8 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055673 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - OTC | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-19 | 2017-06-19 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055674 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Prepare - OTC | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055675 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - OTC | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055676 | No | No | Yes | Australia | Australia | 04-Test | Regression - Manage defects (Capex) - OTC | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055677 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD145-Sales, Delivery and Billing pre-defined Texts | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-02-24 | 2017-02-27 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055678 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Preparation | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 73h | 0h | 73h | 2017-03-31 | 2017-04-21 | Yes |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 26 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055679 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Manage Defects (Capex) | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055680 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Manage Defects (Capex) | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2017-04-24 | 2017-04-28 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055681 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Break/Fix - OTC | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 14h | 0h | 14h | 2017-05-05 | 2017-05-07 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055682 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia(D/B) | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 70h | 0h | 70h | 2017-02-20 | 2017-03-03 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055683 | No | No | Yes | Australia | Australia | 03-Design/Build | FLOG019-DEV FUT-BOL + AQIS number | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-21 | 2017-03-21 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055684 | No | No | Yes | Australia | Australia | 03-Design/Build | FLOG020-DEV FUT-Packing List | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055685 | No | No | Yes | Australia | Australia | 03-Design/Build | FLOG021-DEV FUT-Pick List | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2017-02-27 | 2017-02-27 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055686 | No | No | Yes | Australia | Australia | 03-Design/Build | FLOG019-FSD-BOL + AQIS number | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 43h | 0h | 43h | 2017-02-09 | 2017-02-17 | Yes |  |  | DELIV.FUN-204.Functional Specification - Form | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055687 | No | No | Yes | Australia | Australia | 03-Design/Build | FLOG020-FSD-Packing List | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-02-08 | 2017-02-14 | Yes |  |  | DELIV.FUN-204.Functional Specification - Form | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055688 | No | No | Yes | Australia | Australia | 03-Design/Build | FLOG021-FSD-Pick List | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2017-02-07 | 2017-02-20 | Yes |  |  | DELIV.FUN-204.Functional Specification - Form | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055689 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG011-FSD-Lot Status Message to 3PL | OTC | FUN | SI | Onshore | Garapati; Sri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055690 | No | No | No | Australia | Australia | 04-Test | SIT 1 - Run Tests |  | Missing Stream | Saputo | Onshore | Kang; Wish | Saputo | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055691 | No | No | No | Australia | Australia | 04-Test | SIT 2 - Run Tests - OTC |  | Missing Stream | Saputo | Onshore | Kang; Wish | Saputo | Yes | CapEx | Localization |  | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055692 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | RTR | FUN | SI | Onshore | Lucinda; Mariana | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055693 | No | No | Yes | Australia | Australia | 03-Design/Build | PDD-Milk payment process | RTR | FUN | SI | Onshore | Lucinda; Mariana | IBM | Yes | CapEx | Localization | IT - External | 132h | 0h | 132h | 2017-01-30 | 2017-03-03 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055694 | No | No | Yes | Australia | Australia | 03-Design/Build | PDD-Milk payment process | RTR | FUN | SI | Onshore | Lucinda; Mariana | IBM | Yes | CapEx | Localization | IT - External | 176h | 0h | 176h | 2017-01-16 | 2017-02-10 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055695 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Argentina Settlement Form | RTR | FUN | SI | Onshore | Lucinda; Mariana | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055696 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Australian Settlement Form Victoria | RTR | FUN | SI | Onshore | Lucinda; Mariana | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055697 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Australian Settlement Form Southern Australia | RTR | FUN | SI | Onshore | Lucinda; Mariana | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055698 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Australia Federal | RTR | FUN | SI | Onshore | Lucinda; Mariana | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055699 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Enhancement Payment program for bank | RTR | FUN | SI | Onshore | Lucinda; Mariana | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055700 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-FSD-Argentina Settlement Form | RTR | FUN | SI | Onshore | Lucinda; Mariana | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055701 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-FSD-Australian Settlement Form Victoria | RTR | FUN | SI | Onshore | Lucinda; Mariana | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055702 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-FSD-Australian Settlement Form Southern Australia | RTR | FUN | SI | Onshore | Lucinda; Mariana | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055703 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-FSD-Australia Federal | RTR | FUN | SI | Onshore | Lucinda; Mariana | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055704 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-FSD-Enhancement Payment program for bank | RTR | FUN | SI | Onshore | Lucinda; Mariana | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055705 | No | Yes | No | Australia | Australia | 03-Design/Build | Development MDG (D/B) | DEV | DEV | SI | Offshore | Sorino; Irezar | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-03-06 | 2017-03-10 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055706 | No | Yes | No | Australia | Australia | 03-Design/Build | Localization Vendor - DM (D/B) | MDG | DM | SI | Onshore | Josephson; Jacob | Accenture | Yes | CapEx | Localization | IT - External | 200h | 0h | 200h | 2017-02-24 | 2017-03-31 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055707 | No | No | Yes | Australia | Australia | 06-Hypercare | HC - Manage defects - Dev | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 12.5h | 0h | 12.5h | 2017-07-03 | 2017-07-12 | Yes |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055708 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Development (Cutover/Go-live) - DEV | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 12.5h | 0h | 12.5h | 2017-06-05 | 2017-06-16 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055709 | No | No | Yes | Australia | Australia | 02-Analyze | WRICEFs inventory (AN) | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 58h | 0h | 58h | 2016-12-05 | 2017-02-24 | Yes |  |  | DELIV.DEV-102.RICEFW Inventory | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 4 | 15.5 | 26.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055710 | No | No | Yes | Australia | Australia |  | AUS - DEV KT | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-05-31 | 2017-05-31 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055711 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT1) | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 56.5h | 0h | 56.5h | 2017-04-24 | 2017-05-12 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 17 | 19.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055712 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT2) | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 43h | 0h | 43h | 2017-05-15 | 2017-06-02 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055713 | No | No | Yes | Australia | Australia | 02-Analyze | WRICEFs inventory (AN) | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 0.5h | 0h | 0.5h | 2016-11-09 | 2017-01-09 | Yes |  |  | DELIV.DEV-102.RICEFW Inventory | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055714 | No | No | Yes | Australia | Australia | 03-Design/Build | Development (D/B) | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 65.5h | 0h | 65.5h | 2017-02-13 | 2017-04-21 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 16.5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055715 | No | No | Yes | Australia | Australia | 03-Design/Build | Development GRC (D/B) | DEV | DEV | Saputo | Onshore | Policarpio; Raphael | Saputo | Yes | CapEx | Localization | IT - Internal | 88h | 0h | 88h | 2017-02-06 | 2017-03-24 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 8 | 8 | 13 | 12.5 | 0 | 25.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055716 | No | No | Yes | Australia | Australia | 06-Hypercare | Development (Hypercare) - DEV | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | CapEx | Localization | IT - External | 105h | 0h | 105h | 2017-07-03 | 2017-08-31 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 36 | 24 | 3 | 0 | 11 | 6 | 7 | 7 | 0 | 0 | 0
1055717 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Development (Cutover/Go-live) - DEV | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-06-28 | 2017-06-29 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055718 | No | No | Yes | Australia | Australia | 03-Design/Build | Development (D/B) | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | CapEx | Localization | IT - External | 505.5h | 0h | 505.5h | 2017-02-20 | 2017-08-14 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 18 | 31 | 0 | 11 | 28 | 45 | 45 | 18 | 27 | 36 | 0 | 22.5 | 36 | 45 | 36 | 28 | 0 | 9 | 28 | 0 | 3 | 19 | 4 | 4 | 5 | 0 | 0 | 0 | 0 | 0
1055719 | No | No | Yes | Australia | Australia |  | AUS - DEV KT | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-31 | 2017-05-31 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055720 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT1) | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-05-08 | 2017-05-12 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055721 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT2) | DEV | DEV | SI | Offshore | Shukla; Yogesh | IBM | Yes | CapEx | Localization | IT - External | 30h | 0h | 30h | 2017-05-26 | 2017-06-27 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 4 | 6 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055722 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - LOG | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 302h | 0h | 302h | 2017-06-26 | 2017-07-27 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 77 | 77 | 70 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055723 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 193h | 0h | 193h | 2017-04-24 | 2017-05-19 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 53 | 52 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055724 | No | No | Yes | Australia | Australia | 03-Design/Build | CONFIG-MM_02-MM Master Data | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055725 | No | No | Yes | Australia | Australia | 03-Design/Build | FLOG020-FSD-Packing List | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-08 | 2017-02-08 | Yes |  |  | DELIV.FUN-204.Functional Specification - Form | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055726 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - LOG | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 191h | 0h | 191h | 2017-05-29 | 2017-06-23 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 54 | 45 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055727 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Preparation | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 151h | 0h | 151h | 2017-03-14 | 2017-04-20 | Yes |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 44 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055728 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Prepare | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | OpEx | Localization | IT - External | 80h | 0h | 80h | 2017-02-27 | 2017-03-09 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055729 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Support | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-27 | 2017-03-27 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055730 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - LOG | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 35h | 0h | 35h | 2017-05-23 | 2017-05-26 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055731 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Preparation (KT with Test Team) | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-27 | 2017-03-27 | Yes |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055732 | No | No | Yes | Australia | Australia | 03-Design/Build | IM_01-CONFIG FUT-IM Organization Structure | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-01-16 | 2017-01-20 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055733 | No | No | Yes | Australia | Australia | 03-Design/Build | CONFIG FUT-MM_02-MM Master Data | LOG | FUN | SI | Onshore | Soufi; Sammy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055734 | No | No | Yes | Australia | Australia | 04-Test | Training Materials-Work Instructions/Job aids (Test) | CM | CM | SI | Onshore | Goel; Ronika | IBM | Yes | OpEx | Localization | IT - External | 364h | 0h | 364h | 2017-03-20 | 2017-06-02 | Yes |  |  | DELIV.CM-451.Work Instructions | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 27 | 45 | 28 | 12 | 18 | 9 | 45 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055735 | No | No | No | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | CDP | CDP | SI | Onshore | Kayur; Goyal | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055736 | No | No | Yes | Australia | Australia | 04-Test | Data collection templates - explain and collect - DC | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 171h | 0h | 171h | 2016-12-19 | 2017-04-14 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 44 | 45 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055737 | No | No | Yes | Australia | Australia | 02-Analyze | Data Construction and staging - DC (AN) | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 418.5h | 0h | 418.5h | 2016-10-24 | 2017-03-24 | Yes |  |  | ACT.MDG.Data Construction | Complete | NA | NA | 0 |  |  | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45.5 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055738 | No | No | Yes | Australia | Australia | 02-Analyze | Kickoff - DC (AN) | MDG | DC | Saputo | Onshore | Ombisi; Mercy | Saputo | Yes | CapEx | Localization | IT - Internal | 218.5h | 0h | 218.5h | 2016-10-25 | 2017-02-10 | Yes |  |  | ACT.MDG.Workshop | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055739 | No | Yes | No | Australia | Australia | 03-Design/Build | Transition to Australia(D/B) | OTC | FUN | SI | Onshore | Gamez; Valerie | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055740 | No | Yes | No | Australia | Australia | 02-Analyze | Old - Create BPML (AN) | OTC | FUN | SI | Onshore | Gamez; Valerie | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055741 | No | Yes | No | Australia | Australia | 02-Analyze | Old - Log Gaps (AN) | OTC | FUN | SI | Onshore | Gamez; Valerie | SAP | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2016-11-21 | 2016-11-21 | Yes |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055742 | No | Yes | No | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) | OTC | FUN | SI | Onshore | Gamez; Valerie | SAP | Yes | CapEx | Localization | IT - External | 120h | 0h | 120h | 2016-10-31 | 2016-11-18 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055743 | No | Yes | No | Australia | Australia | 02-Analyze | RTM (AN) | OTC | FUN | SI | Onshore | Gamez; Valerie | SAP | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2016-11-21 | 2016-11-23 | Yes |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055744 | No | No | Yes | Australia | Australia | 04-Test | Data load - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 211h | 0h | 211h | 2017-03-27 | 2017-05-29 | Yes |  |  | ACT.MDG.Mock Load | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 55 | 48 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055745 | No | No | Yes | Australia | Australia | 04-Test | Data collection templates - explain and collect - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 94h | 0h | 94h | 2016-12-19 | 2017-02-24 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055746 | No | No | Yes | Australia | Australia | 02-Analyze | Data Construction and staging - DC (AN) | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 399h | 0h | 399h | 2016-12-19 | 2017-03-26 | Yes |  |  | ACT.MDG.Data Construction | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 60 | 40 | 0 | 40 | 50 | 64 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055747 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Prepare - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | OpEx | Localization | IT - External | 61h | 0h | 61h | 2017-06-05 | 2017-06-12 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055748 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-04-10 | 2017-04-21 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055749 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Validate - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-14 | 2017-03-14 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055750 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Support - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | OpEx | Localization | IT - External | 56h | 0h | 56h | 2017-06-12 | 2017-06-16 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055751 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Validate - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | OpEx | Localization | IT - External | 80h | 0h | 80h | 2017-06-19 | 2017-06-25 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055752 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect (Capex) - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 35h | 0h | 35h | 2017-06-27 | 2017-06-29 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055753 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 58h | 0h | 58h | 2017-05-29 | 2017-06-02 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055754 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Execute - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 96.5h | 0h | 96.5h | 2017-05-08 | 2017-05-19 | Yes |  |  | ACT.MDG.Mock Load | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.5 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055755 | No | No | Yes | Australia | Australia | 06-Hypercare | HC - Manage defects - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-07-10 | 2017-07-14 | Yes |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055756 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - DC | MDG | DC | SI | Onshore | Chan; Jonathan | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-05-01 | 2017-05-07 | Yes |  |  | ACT.MDG.Mock Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055757 | No | No | Yes | Australia | Australia | 04-Test | Harmoni Program Governance and Cross Functional Work (Saputo) - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 46h | 0h | 46h | 2017-05-03 | 2017-06-16 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 8 | 30 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055758 | No | No | Yes | Australia | Australia | 04-Test | Retrofit Testing (Saputo) - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 8h | 0h | 8h | 2017-05-30 | 2017-06-02 | Yes |  |  | ACT.MDG.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055759 | No | No | Yes | Australia | Australia | 04-Test | Functional Testing (Saputo) - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 8h | 0h | 8h | 2017-04-24 | 2017-05-05 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055760 | No | No | Yes | Australia | Australia | 04-Test | Non Regression - Run tests (Saputo) - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 16h | 0h | 16h | 2017-05-22 | 2017-05-25 | Yes |  |  | ACT.MDG.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055761 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run tests (Saputo) - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 40h | 0h | 40h | 2017-05-15 | 2017-05-19 | Yes |  |  | ACT.MDG.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055762 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run tests (Saputo) - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 57h | 0h | 57h | 2017-04-24 | 2017-05-12 | Yes |  |  | ACT.MDG.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 9 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055763 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Support (Dual maintenance) - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 80h | 0h | 80h | 2017-06-12 | 2017-06-30 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055764 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Document work around (Saputo)- DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 5h | 0h | 5h | 2017-06-12 | 2017-06-16 | Yes |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055765 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix (Saputo) - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-05 | 2017-06-16 | Yes |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055766 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Manage Defects (Saputo) (Capex) - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | CapEx | Localization | IT - Internal | 20h | 0h | 20h | 2017-06-05 | 2017-06-23 | Yes |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055767 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests (Saputo) - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055768 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Prep (Select Scenarios) (Saputo) - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 22h | 0h | 22h | 2017-05-03 | 2017-06-02 | Yes |  |  | ACT.MDG.UAT Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055769 | No | No | Yes | Australia | Australia | 04-Test | Non Regression - Manage defects (Capex) (Saputo) MDG-DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | CapEx | Localization | IT - Internal | 16h | 0h | 16h | 2017-05-22 | 2017-05-25 | Yes |  |  | ACT.MDG.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055770 | No | No | Yes | Australia | Australia | 03-Design/Build | Test preparation (Saputo) - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-10 | 2017-04-14 | Yes |  |  | DELIV.TST-307.Assembly Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055771 | No | No | Yes | Australia | Australia | 04-Test | Test Preparation (Saputo) - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 7h | 0h | 7h | 2017-04-12 | 2017-04-21 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055772 | No | No | Yes | Australia | Australia | 06-Hypercare | HC - Provide end User Supprt (Opex) - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 160h | 0h | 160h | 2017-07-03 | 2017-07-28 | Yes |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055773 | No | No | Yes | Australia | Australia | 03-Design/Build | Localization Customer (Saputo) - DM (D/B) | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 60h | 0h | 60h | 2017-02-24 | 2017-04-07 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055774 | No | No | Yes | Australia | Australia | 03-Design/Build | Localization Vendor - DM (D/B) | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 60h | 0h | 60h | 2017-02-24 | 2017-04-07 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055775 | No | No | Yes | Australia | Australia | 03-Design/Build | Offline Process Vendor (Saputo) - DM (D/B) | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055776 | No | No | Yes | Australia | Australia | 03-Design/Build | Offline Process Customer (Saputo) - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055777 | No | No | Yes | Australia | Australia | 03-Design/Build | Update Recordings Customer/Work Instructions - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055778 | No | No | Yes | Australia | Australia | 03-Design/Build | Update Recordings Vendor/Work Instructions - DM | MDG | DM | Saputo | Onshore | Battles; Shanell | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055779 | No | No | Yes | Australia | Australia | 03-Design/Build | PDD-Process Milk Sales Order and Swaps | PTP | FUN | SI | Onshore | Deng; Roy | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-02-06 | 2017-02-10 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055780 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | PTP | FUN | SI | Onshore | Deng; Roy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055781 | No | No | Yes | Australia | Australia | 03-Design/Build | PDD-Process Milk Sales Order and Swaps | PTP | FUN | SI | Onshore | Deng; Roy | IBM | Yes | CapEx | Localization | IT - External | 84h | 0h | 84h | 2017-01-31 | 2017-03-09 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 44 | 0 | 12 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055782 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - PTP | PTP | FUN | SI | Onshore | Deng; Roy | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-05-29 | 2017-05-30 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055783 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - PTP | PTP | FUN | SI | Onshore | Deng; Roy | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-05-15 | 2017-05-31 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055784 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Preparation | PTP | FUN | SI | Onshore | Deng; Roy | IBM | Yes | CapEx | Localization | IT - External | 95h | 0h | 95h | 2017-04-10 | 2017-05-14 | Yes |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055785 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | PTP | FUN | SI | Onshore | Deng; Roy | IBM | Yes | CapEx | Localization | IT - External | 76h | 0h | 76h | 2017-04-24 | 2017-05-07 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055786 | No | No | Yes | Australia | Australia | 02-Analyze | Kickoff (AN) | PTP | FUN | SI | Onshore | Deng; Roy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055787 | No | No | Yes | Australia | Australia | 02-Analyze | RTM (AN) | PTP | FUN | SI | Onshore | Deng; Roy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-26 | 2016-10-26 | Yes |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055788 | No | No | Yes | Australia | Australia | 03-Design/Build | PDD-Baseline (D/B) | PTP | FUN | SI | Onshore | Deng; Roy | IBM | Yes | CapEx | Localization | IT - External | 92h | 0h | 92h | 2017-01-09 | 2017-01-20 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 44 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055789 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-Baseline (D/B) | PTP | FUN | SI | Onshore | Deng; Roy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055790 | No | No | Yes | Australia | Australia | 03-Design/Build | CONFIG-Baseline (D/B) | PTP | FUN | SI | Onshore | Deng; Roy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055791 | No | No | Yes | Australia | Australia | 03-Design/Build | SDD Writing (D/B) | PTP | FUN | SI | Onshore | Deng; Roy | IBM | Yes | CapEx | Localization | IT - External | 84h | 0h | 84h | 2017-01-27 | 2017-02-23 | Yes |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 28 | 4 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055792 | No | No | Yes | Australia | Australia | 03-Design/Build | CONFIG FUT-Baseline (D/B) | PTP | FUN | SI | Onshore | Deng; Roy | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055793 | No | No | Yes | Australia | Australia | 04-Test | Data collection templates - explain and collect - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 349h | 0h | 349h | 2016-12-19 | 2017-03-17 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 47 | 57 | 42 | 59 | 0 | 0 | 48 | 0 | 36 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055794 | No | No | Yes | Australia | Australia | 04-Test | Mock1 – Manage defect (Capex) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 114h | 0h | 114h | 2017-04-28 | 2017-05-19 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055795 | No | No | Yes | Australia | Australia | 04-Test | Data load - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 315h | 0h | 315h | 2017-03-20 | 2017-05-08 | Yes |  |  | ACT.MDG.Mock Load | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 59 | 50 | 0 | 44.5 | 55.5 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055796 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Prepare - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | OpEx | Localization | IT - Internal | 82h | 0h | 82h | 2017-06-05 | 2017-06-12 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055797 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Support - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | OpEx | Localization | IT - Internal | 46h | 0h | 46h | 2017-06-12 | 2017-06-16 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055798 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Validate - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | OpEx | Localization | IT - Internal | 44h | 0h | 44h | 2017-06-19 | 2017-06-25 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055799 | No | No | Yes | Australia | Australia | 06-Hypercare | HC - Manage defects - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055800 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect (Capex) - DC | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 70h | 0h | 70h | 2017-06-26 | 2017-06-30 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055801 | No | No | Yes | Australia | Australia | 02-Analyze | Data Construction and staging - DC (AN) | MDG | DC | Saputo | Onshore | Segarra; Josefina | Saputo | Yes | CapEx | Localization | IT - Internal | 430h | 0h | 430h | 2016-11-21 | 2017-03-03 | Yes |  |  | ACT.MDG.Data Construction | Complete | NA | NA | 0 |  |  | 0 | 0 | 24 | 30 | 0 | 0 | 0 | 0 | 54 | 48 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055802 | No | No | Yes | Australia | Australia |  | Data Profiling (Saputo) - DG | MDG | DG | Saputo | Onshore | Lentz; Jared | Saputo | Yes | OpEx | Localization | IT - Internal | 9.8h | 0h | 9.8h | 2017-05-22 | 2017-06-30 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 4 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055803 | No | No | Yes | Australia | Australia |  | Data Cleansing - DG | MDG | DG | Saputo | Onshore | Lentz; Jared | Saputo | Yes | OpEx | Localization | IT - Internal | 15h | 0h | 15h | 2017-05-08 | 2017-07-28 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055804 | No | No | Yes | Australia | Australia |  | Data quality - DG | MDG | DG | Saputo | Onshore | Lentz; Jared | Saputo | Yes | OpEx | Localization | IT - Internal | 725h | 0h | 725h | 2017-02-06 | 2017-08-03 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15.5 | 15 | 20 | 44 | 44 | 12.5 | 12 | 15 | 24 | 20 | 24 | 32 | 30 | 40 | 40 | 32 | 16 | 32 | 40 | 30 | 40 | 40 | 40 | 20 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055805 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Development (Cutover/Go-live) - DEV | DEV | DEV | SI | Offshore | Ghoshbiswas; Veena | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-02 | 2017-06-02 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055806 | No | Yes | No | Australia | Australia | 04-Test | Development (SIT2) | DEV | DEV | SI | Offshore | Ghoshbiswas; Veena | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055807 | No | Yes | No | Australia | Australia | 03-Design/Build | Development (D/B) | DEV | DEV | SI | Offshore | Ghoshbiswas; Veena | IBM | Yes | CapEx | Localization | IT - External | 216h | 0h | 216h | 2017-02-14 | 2017-03-24 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 36 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055808 | No | Yes | No | Australia | Australia | 04-Test | Development (SIT1) | DEV | DEV | SI | Offshore | Ghoshbiswas; Veena | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055809 | No | Yes | No | Australia | Australia |  | AUS - DEV KT | DEV | DEV | SI | Offshore | Ghoshbiswas; Veena | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-31 | 2017-05-31 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055810 | No | Yes | No | Australia | Australia | 06-Hypercare | Development (Hypercare) - DEV | DEV | DEV | SI | Offshore | Ghoshbiswas; Veena | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-04 | 2017-05-04 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055811 | No | Yes | No | Australia | Australia | 03-Design/Build | Update Recordings Finance/Work Instructions - DM | MDG | DM | SI | Onshore | Gireesh; Mangeshi | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055812 | No | Yes | No | Australia | Australia | 03-Design/Build | Offline Process Financial Object - Australia Review (Accenture) - DM (D/B) | MDG | DM | SI | Onshore | Gireesh; Mangeshi | Accenture | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2017-02-27 | 2017-03-17 | Yes |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055813 | No | Yes | No | Australia | Australia | 03-Design/Build | Design Material Master MDG (Accenture) - DM (D/B) | MDG | DM | SI | Onshore | Gireesh; Mangeshi | Accenture | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2017-02-27 | 2017-04-21 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 8 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055814 | No | Yes | No | Australia | Australia | 03-Design/Build | Test preparation (Accenture) - DM | MDG | DM | SI | Onshore | Gireesh; Mangeshi | Accenture | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2017-04-10 | 2017-04-13 | Yes |  |  | DELIV.TST-307.Assembly Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055815 | No | Yes | No | Australia | Australia | 04-Test | Functional Testing (Accenture) - DM | MDG | DM | SI | Onshore | Gireesh; Mangeshi | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-04-24 | 2017-04-28 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055816 | No | Yes | No | Australia | Australia | 04-Test | Test Preparation (Accenture) - DM | MDG | DM | SI | Onshore | Gireesh; Mangeshi | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-04-03 | 2017-04-07 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055817 | No | Yes | No | Australia | Australia | 04-Test | Functional Testing (Accenture) - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-04-17 | 2017-04-21 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055818 | No | Yes | No | Australia | Australia | 04-Test | Retrofit Testing (Accenture) - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.MDG.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055819 | No | Yes | No | Australia | Australia | 03-Design/Build | Test preparation (Accenture) - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-04-10 | 2017-04-14 | Yes |  |  | DELIV.TST-307.Assembly Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055820 | No | Yes | No | Australia | Australia | 03-Design/Build | SDD - Edit, Review, or Approve - Material Master - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055821 | No | Yes | No | Australia | Australia | 04-Test | Test Preparation (Accenture) - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-04-03 | 2017-04-07 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055822 | No | Yes | No | Australia | Australia | 06-Hypercare | HC - Manage defects - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055823 | No | Yes | No | Australia | Australia | 06-Hypercare | HC - Break/Fix - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055824 | No | Yes | No | Australia | Australia | 04-Test | Documentation and Program Work (Accenture) - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055825 | No | Yes | No | Australia | Australia | 06-Hypercare | HC - Material Master - SI - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 112h | 0h | 112h | 2017-07-03 | 2017-07-28 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055826 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Cutover - Material Master - SI - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-06-19 | 2017-06-23 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055827 | No | Yes | No | Australia | Australia | 04-Test | SIT 1 - Run tests (Accenture) - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 112h | 0h | 112h | 2017-04-24 | 2017-05-12 | Yes |  |  | ACT.MDG.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055828 | No | Yes | No | Australia | Australia | 04-Test | SIT 2 - Run tests (Saputo) - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-05-15 | 2017-05-19 | Yes |  |  | ACT.MDG.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055829 | No | Yes | No | Australia | Australia | 04-Test | Non Regression - Run tests (Saputo) - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.MDG.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055830 | No | Yes | No | Australia | Australia | 04-Test | Non Regression - Manage defects (Capex) (Accenture) MDG - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.MDG.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055831 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | UAT - Prep (Select Scenarios) (Accenture) - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 64h | 0h | 64h | 2017-05-22 | 2017-06-02 | Yes |  |  | ACT.MDG.UAT Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055832 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests (Accenture) - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055833 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | UAT - Manage Defects (Accenture) (Capex) - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-06-05 | 2017-06-09 | Yes |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055834 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix (Accenture) - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055835 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Cutover - Prepare - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055836 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | UAT - Document work around (Accenture) - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055837 | No | Yes | No | Australia | Australia | 03-Design/Build | Build Material Master - Functional Support (Accenture) - DM (D/B) | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055838 | No | Yes | No | Australia | Australia | 03-Design/Build | Design Material Master MDG (Accenture) - DM (D/B) | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 236h | 0h | 236h | 2017-01-30 | 2017-03-31 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055839 | No | Yes | No | Australia | Australia | 03-Design/Build | Write SDD's Material Master (Accenture) - DM (D/B) | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | OpEx | Localization | IT - External | 120h | 0h | 120h | 2017-02-06 | 2017-02-24 | Yes |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055840 | No | Yes | No | Australia | Australia | 03-Design/Build | Update BWL MM (Accenture) - DM (D/B) | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055841 | No | Yes | No | Australia | Australia | 03-Design/Build | FUN Material Master (Accenture) - DM (D/B) | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055842 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | UAT - Material Master - SI - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 48h | 0h | 48h | 2017-06-12 | 2017-06-19 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055843 | No | Yes | No | Australia | Australia | 03-Design/Build | PDD - Edit, Review, or Approve - Maintain Material Master - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055844 | No | Yes | No | Australia | Australia | 03-Design/Build | PDD - Edit, Review, or Approve - Maintain Material Master: Creation - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055845 | No | Yes | No | Australia | Australia | 03-Design/Build | PDD - Edit, Review, or Approve - Maintain Material Master: Extend - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055846 | No | Yes | No | Australia | Australia | 03-Design/Build | PDD - Edit, Review, or Approve - Maintain Material Master: Mark for Deletion - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055847 | No | Yes | No | Australia | Australia | 03-Design/Build | PDD - Edit, Review, or Approve - Maintain Material Master: Update - DM | MDG | DM | SI | Onshore | Kaji; Varun | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055848 | No | Yes | No | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | LOG | FUN | SI | Onshore | McDonough; Alan | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055849 | No | Yes | No | Australia | Australia | 03-Design/Build | ILOG009-DEV FUT-EDI Outbound ASN sent to customers | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-24 | 2017-03-24 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055850 | No | Yes | No | Australia | Australia | 03-Design/Build | ILOG007-DEV FUT-EDI 3PL ASN | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-24 | 2017-03-24 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055851 | No | Yes | No | Australia | Australia | 03-Design/Build | ILOG006-DEV FUT-EDI 3PL Pick Request | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055852 | No | Yes | No | Australia | Australia | 03-Design/Build | ILOG009-FSD-EDI Outbound ASN sent to customers | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2017-02-20 | 2017-02-24 | Yes |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055853 | No | Yes | No | Australia | Australia | 03-Design/Build | ILOG007-FSD-IEDI 3PL ASN | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-02-20 | 2017-02-24 | Yes |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055854 | No | Yes | No | Australia | Australia | 03-Design/Build | Transition to Australia(D/B) | OTC | FUN | SI | Onshore | Haraida; Ricardo | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-02-13 | 2017-02-17 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055855 | No | No | Yes | Australia | Australia | 06-Hypercare | Development (Hypercare) - DEV | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2017-07-03 | 2017-08-11 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0
1055856 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Development (Cutover/Go-live) - DEV | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | CapEx | Localization | IT - External | 35h | 0h | 35h | 2017-06-08 | 2017-06-22 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055857 | No | No | Yes | Australia | Australia | 03-Design/Build | Development (D/B) | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | CapEx | Localization | IT - External | 339h | 0h | 339h | 2017-02-27 | 2017-05-05 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 36 | 34 | 17 | 45 | 45 | 45 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055858 | No | No | Yes | Australia | Australia |  | AUS - DEV KT | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | OpEx | Localization | IT - External | 3h | 0h | 3h | 2017-05-31 | 2017-05-31 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055859 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT1) | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | CapEx | Localization | IT - External | 39h | 0h | 39h | 2017-04-24 | 2017-05-12 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055860 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT2) | DEV | DEV | SI | Offshore | Prasad; Suresh | IBM | Yes | CapEx | Localization | IT - External | 54h | 0h | 54h | 2017-05-19 | 2017-06-29 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 17 | 21 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055861 | No | Yes | No | Australia | Australia | 02-Analyze | System Security Handover Activities (AN) | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2016-11-08 | 2016-12-13 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055862 | No | Yes | No | Australia | Australia | 03-Design/Build | System Security Handover Activities | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-29 | 2016-11-29 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055863 | No | Yes | No | Australia | Australia | 02-Analyze | Security Requirements Gathering (AN) | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-07 | 2017-01-07 | Yes |  |  | DELIV.SEC-002.Security and Controls Requirements | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055864 | No | Yes | No | Australia | Australia | 03-Design/Build | Composite Role Design | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-17 | 2016-12-21 | Yes |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055865 | No | Yes | No | Australia | Australia | 03-Design/Build | Master Role Design - BUS | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-17 | 2016-12-21 | Yes |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055866 | No | Yes | No | Australia | Australia | 03-Design/Build | Security Design Workshps | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055867 | No | Yes | No | Australia | Australia | 03-Design/Build | Security Detailed Design | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | DELIV.SEC-201.Security Role Detailed Design | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055868 | No | Yes | No | Australia | Australia | 03-Design/Build | Composite Role Build | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-09 | 2017-03-09 | Yes |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055869 | No | Yes | No | Australia | Australia | 03-Design/Build | Derived Role Build - BUS | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-10 | 2017-02-10 | Yes |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055870 | No | Yes | No | Australia | Australia | 03-Design/Build | Master Role Build and UT | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055871 | No | Yes | No | Australia | Australia | 03-Design/Build | Security Role FUT | SEC | SEC | SI | Onshore | Jaffery; Ikram | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055872 | No | No | Yes | Australia | Australia | 03-Design/Build | GRC AC Solution Design | SEC | SEC | SI | Offshore | Olvida; Julio | Accenture | Yes | CapEx | Localization | IT - External | 225h | 0h | 225h | 2017-01-09 | 2017-02-10 | Yes |  |  | DELIV.SEC-215.SAP Security & GRC Processes | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055873 | No | No | Yes | Australia | Australia | 03-Design/Build | GRC AC Solution Build | SEC | SEC | SI | Offshore | Olvida; Julio | Accenture | Yes | CapEx | Localization | IT - External | 261h | 0h | 261h | 2017-02-13 | 2017-03-24 | Yes |  |  | DELIV.SEC-215.SAP Security & GRC Processes | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 36 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055874 | No | No | Yes | Australia | Australia | 03-Design/Build | SoD GRC AC Analysis and Remediation | SEC | SEC | SI | Offshore | Olvida; Julio | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-11 | 2016-12-11 | Yes |  |  | DELIV.SEC-215.SAP Security & GRC Processes | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055875 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT | SEC | SEC | SI | Offshore | Olvida; Julio | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  | ACT.SEC.Executive UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055876 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover | SEC | SEC | SI | Offshore | Olvida; Julio | Accenture | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-06-21 | 2017-06-23 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055877 | No | Yes | No | Australia | Australia | 02-Analyze | GRC Access Controls Requirements (AN) | SEC | SEC | SI | Onshore | Jayasim; Franklin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-11 | 2016-10-11 | Yes |  |  | DELIV.SEC-002B.SAP GRC Process Control RTM | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055878 | No | Yes | No | Australia | Australia | 03-Design/Build | GRC AC Solution Design | SEC | SEC | SI | Onshore | Jayasim; Franklin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | Yes |  |  | DELIV.SEC-215.SAP Security & GRC Processes | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055879 | No | Yes | No | Australia | Australia | 03-Design/Build | GRC AC Solution Build | SEC | SEC | SI | Onshore | Jayasim; Franklin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-10 | 2017-02-10 | Yes |  |  | DELIV.SEC-215.SAP Security & GRC Processes | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055880 | No | Yes | No | Australia | Australia | 03-Design/Build | SoD GRC AC Analysis and Remediation | SEC | SEC | SI | Onshore | Jayasim; Franklin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-11 | 2016-12-11 | Yes |  |  | DELIV.SEC-215.SAP Security & GRC Processes | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055881 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - RTR | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT.FUN.Functional Break/Fix | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055882 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - RTR | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-06-07 | 2017-06-07 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055883 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 147h | 0h | 147h | 2017-04-24 | 2017-05-14 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 48 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055884 | No | No | Yes | Australia | Australia | 04-Test | Regression - Run Tests - RTR | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055885 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - RTR | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 33h | 0h | 33h | 2017-05-16 | 2017-06-13 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055886 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Break/Fix - RTR | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2017-04-26 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055887 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - RTR | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 131h | 0h | 131h | 2017-05-15 | 2017-06-04 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 35 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055888 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Preparation | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 162h | 0h | 162h | 2017-03-06 | 2017-04-21 | Yes |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 26 | 14 | 31 | 32 | 14 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055889 | No | No | Yes | Australia | Australia | 03-Design/Build | KT sessions (D/B) | RTR | FUN | SI | Offshore | Shukla; Swati | IBM | Yes | CapEx | Localization | IT - External | 139h | 0h | 139h | 2017-02-06 | 2017-04-28 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 15 | 2 | 5 | 4 | 9 | 10 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055890 | No | Yes | No | Australia | Australia | 04-Test | Development (SIT2) | DEV | DEV | SI | Offshore | Kumar; Bijendra | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055891 | No | Yes | No | Australia | Australia | 04-Test | Development (SIT1) | DEV | DEV | SI | Offshore | Kumar; Bijendra | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055892 | No | Yes | No | Australia | Australia | 03-Design/Build | Development (D/B) | DEV | DEV | SI | Offshore | Kumar; Bijendra | IBM | Yes | CapEx | Localization | IT - External | 207h | 0h | 207h | 2017-02-13 | 2017-04-28 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 45 | 36 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055893 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Development (Cutover/Go-live) - DEV | DEV | DEV | SI | Offshore | Kumar; Bijendra | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-02 | 2017-06-02 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055894 | No | Yes | No | Australia | Australia | 06-Hypercare | Development (Hypercare) - DEV | DEV | DEV | SI | Offshore | Kumar; Bijendra | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-04 | 2017-05-04 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055895 | No | Yes | No | Australia | Australia |  | Manage Project | PMO | PMO | SI | Onshore | Round; Andrew | IBM | Yes | CapEx | Localization | IT - External | 999h | 0h | 999h | 2016-09-05 | 2017-08-11 | Yes |  |  | ACT.PMO.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 44 | 31 | 44 | 44 | 44 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0
1055896 | No | Yes | No | Australia | Australia |  | Team Lead - Cutover planners | PMO | PMO | SI | Onshore | Round; Andrew | IBM | Yes | CapEx | Localization | IT - External | 871h | 0h | 871h | 2017-04-18 | 2017-08-06 | Yes |  |  | ACT.PMO.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 63 | 50 | 50 | 50 | 54 | 75 | 50 | 53 | 53 | 82 | 52 | 51 | 54 | 44 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055897 | No | Yes | No | Australia | Australia | 02-Analyze | Analyze-PMO-Management (AN) | PMO | PMO | SI | Onshore | Round; Andrew | IBM | Yes | CapEx | Localization | IT - External | 106h | 0h | 106h | 2017-01-23 | 2017-02-10 | Yes |  |  | ACT.PMO.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 35 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055898 | No | Yes | No | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | PTP | FUN | SI | Onshore | Melville; Steven | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055899 | No | Yes | No | Australia | Australia | 02-Analyze | Old - Log Gaps (AN) | PTP | FUN | SI | Onshore | Melville; Steven | IBM | Yes | CapEx | Localization | IT - External | 30h | 0h | 30h | 2016-11-14 | 2017-01-25 | Yes |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055900 | No | Yes | No | Australia | Australia | 01-Preparation | Prepare KT) (PP) | PTP | FUN | SI | Onshore | Melville; Steven | IBM | Yes | OpEx | Localization | IT - External | 123h | 0h | 123h | 2016-09-12 | 2016-10-28 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055901 | No | Yes | No | Australia | Australia | 01-Preparation | Prepare Kick-off (SI)) (PP) | PTP | FUN | SI | Onshore | Melville; Steven | IBM | Yes | CapEx | Localization | IT - External | 121h | 0h | 121h | 2016-10-03 | 2016-10-21 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055902 | No | Yes | No | Australia | Australia | 01-Preparation | Conduct kick-off in Australia) (PP) | PTP | FUN | SI | Onshore | Melville; Steven | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-29 | 2016-10-29 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055903 | No | Yes | No | Australia | Australia | 01-Preparation | Conduct KT sessions) (PP) | PTP | FUN | SI | Onshore | Melville; Steven | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | Yes |  |  | WP.FUN.Requirements/Process Design Workshop Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055904 | No | Yes | No | Australia | Australia | 01-Preparation | Worshop Preparation Decks) (PP) | PTP | FUN | SI | Onshore | Melville; Steven | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-03 | 2016-10-03 | Yes |  |  | WP.FUN-107.Workshop Preparation Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055905 | No | Yes | No | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) | PTP | FUN | SI | Onshore | Melville; Steven | IBM | Yes | CapEx | Localization | IT - External | 349h | 0h | 349h | 2016-10-31 | 2016-12-23 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055906 | No | Yes | No | Australia | Australia | 02-Analyze | RTM (AN) | PTP | FUN | SI | Onshore | Melville; Steven | IBM | Yes | CapEx | Localization | IT - External | 123h | 0h | 123h | 2016-10-26 | 2017-01-20 | Yes |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 35 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055907 | No | Yes | No | Australia | Australia | 02-Analyze | Old - Create BPML (AN) | PTP | FUN | SI | Onshore | Melville; Steven | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-03 | 2016-11-03 | Yes |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055908 | No | Yes | No | Australia | Australia | 03-Design/Build | DDD-GD249-Material Master Sales Org 1 Tax | PTP | FUN | SI | Onshore | Melville; Steven | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-03-20 | 2017-03-24 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055909 | No | Yes | No | Australia | Australia | 03-Design/Build | XXX-DEV FUT-Tabular results ( including 6506 ) | PTP | FUN | SI | Onshore | Melville; Steven | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-06 | 2017-06-06 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055910 | No | Yes | No | Australia | Australia | 03-Design/Build | XXX-FSD-Tabular results ( including 6506 ) | PTP | FUN | SI | Onshore | Melville; Steven | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-01-30 | 2017-02-03 | Yes |  |  | DELIV.FUN-203.Functional Specification - Enhancement | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055911 | No | Yes | No | Australia | Australia | 03-Design/Build | MCP-FSD-MinAgri 1- XML with liters detail (milk delivery) | PTP | FUN | SI | Onshore | Melville; Steven | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055912 | No | Yes | No | Australia | Australia | 03-Design/Build | Management (D/B) | PTP | FUN | SI | Onshore | Melville; Steven | IBM | Yes | CapEx | Localization | IT - External | 414h | 0h | 414h | 2017-02-06 | 2017-04-21 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 44 | 44 | 35 | 0 | 44 | 44 | 36 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055913 | No | Yes | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-MinAgri 1- XML with liters detail (milk delivery) | PTP | FUN | SI | Onshore | Melville; Steven | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-31 | 2017-03-31 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055914 | No | Yes | No | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Import XML from agriculture agency system (Was consolidated with MinAgri1) | PTP | FUN | SI | Onshore | Melville; Steven | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-31 | 2017-03-31 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055915 | No | Yes | No | Australia | Australia | 03-Design/Build | MCP-FSD-Import XML from agriculture agency system (Was consolidated with MinAgri1) | PTP | FUN | SI | Onshore | Melville; Steven | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055916 | No | Yes | No | Australia | Australia | 03-Design/Build | FPTP004-DEV FUT-Localise PO output (form) and T&C | PTP | FUN | SI | Onshore | Melville; Steven | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055917 | No | Yes | No | Australia | Australia | 06-Hypercare | Management (Hypercare) - PTP | PTP | FUN | SI | Onshore | Melville; Steven | IBM | Yes | CapEx | Localization | IT - External | 292h | 0h | 292h | 2017-07-03 | 2017-08-11 | Yes |  |  | ACT.DEV.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 50 | 50 | 49 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0
1055918 | No | Yes | No | Australia | Australia | 04-Test | Management (Test) - PTP | PTP | FUN | SI | Onshore | Melville; Steven | IBM | Yes | CapEx | Localization | IT - External | 273h | 0h | 273h | 2017-05-01 | 2017-06-09 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 44 | 53 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055919 | No | No | Yes | Australia | Australia | 01-Preparation | Prepare KT) (PP) | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | OpEx | Localization | IT - External | 212h | 0h | 212h | 2016-09-12 | 2016-10-25 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055920 | No | No | Yes | Australia | Australia | 03-Design/Build | FRTR005-FSD-Ability to produce an invoice for direct FI | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-02-21 | 2017-02-22 | Yes |  |  | DELIV.FUN-204.Functional Specification - Form | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055921 | No | No | Yes | Australia | Australia | 03-Design/Build | FRTR006-FSD-Need to send payment remittance advice | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 42h | 0h | 42h | 2017-02-23 | 2017-03-17 | Yes |  |  | DELIV.FUN-204.Functional Specification - Form | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 24 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055922 | No | No | Yes | Australia | Australia | 03-Design/Build | FRTR005-DEV FUT-Ability to produce an invoice for direct FI | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-04-10 | 2017-04-21 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055923 | No | No | Yes | Australia | Australia | 03-Design/Build | FRTR006-DEV FUT-Need to send payment remittance advice | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-03-16 | 2017-04-05 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055924 | No | No | Yes | Australia | Australia | 03-Design/Build | AP_03-CONFIG-Tax on Sale / Purchase | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-02-13 | 2017-02-20 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055925 | No | No | Yes | Australia | Australia | 03-Design/Build | TX_01-CONFIG FUT-FI-Output Taxes | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-02-27 | 2017-03-03 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055926 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - RTR | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 394h | 88h | 482h | 2017-07-02 | 2017-09-15 | Yes |  |  | ACT.FUN.Functional Break/Fix | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 45 | 43 | 46 | 40 | 44 | 44 | 44 | 44 | 0 | 0 | 0
1055927 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix (Hypercare) - RTR | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2017-07-20 | 2017-08-03 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055928 | No | No | Yes | Australia | Australia | 01-Preparation | Worshop Preparation Decks) (PP) | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2016-10-10 | 2016-10-10 | Yes |  |  | WP.FUN-107.Workshop Preparation Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055929 | No | No | Yes | Australia | Australia | 01-Preparation | Conduct KT sessions) (PP) | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-29 | 2016-10-29 | Yes |  |  | WP.FUN.Requirements/Process Design Workshop Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055930 | No | No | Yes | Australia | Australia | 01-Preparation | Prepare Kick-off) (PP) | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-10-17 | 2016-10-21 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055931 | No | No | Yes | Australia | Australia | 01-Preparation | Conduct kick-off) (PP) | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-29 | 2016-10-29 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055932 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 71h | 0h | 71h | 2017-01-23 | 2017-02-03 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055933 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Prep-Data quality | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 35h | 0h | 35h | 2017-04-10 | 2017-04-13 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055934 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Prepare | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | OpEx | Localization | IT - External | 67h | 0h | 67h | 2017-03-14 | 2017-04-07 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055935 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 220h | 0h | 220h | 2016-11-07 | 2016-12-09 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055936 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Support | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | OpEx | Localization | IT - External | 88h | 0h | 88h | 2017-03-20 | 2017-03-31 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055937 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 137h | 0h | 137h | 2017-04-24 | 2017-05-14 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055938 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Break/Fix - RTR | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-05-15 | 2017-05-19 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055939 | No | No | Yes | Australia | Australia | 03-Design/Build | BNK_01-CONFIG-FI-EBS Electronic Bank Statement | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-20 | 2017-02-20 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055940 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - RTR | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 109h | 0h | 109h | 2017-05-29 | 2017-06-19 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 47 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055941 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - RTR | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-06-12 | 2017-06-16 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055942 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - RTR | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-06-21 | 2017-07-03 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055943 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - RTR | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055944 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - RTR | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-05-22 | 2017-05-26 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055945 | No | No | Yes | Australia | Australia | 03-Design/Build | CONFIG FUT-Baseline (D/B) | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-13 | 2016-12-13 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055946 | No | No | Yes | Australia | Australia | 03-Design/Build | Contribute to Cut-over Planning (D/B) - RTR | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-11-22 | 2017-01-20 | Yes |  |  | ACT.FUN.Support Cutover plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055947 | No | No | Yes | Australia | Australia | 03-Design/Build | Support MDM (D/B) | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-03 | 2016-12-03 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055948 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - RTR | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055949 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - RTR | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 39h | 0h | 39h | 2017-05-22 | 2017-05-26 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055950 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Prepare - RTR | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-06-20 | 2017-06-20 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055951 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Create BPML (AN) | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055952 | No | No | Yes | Australia | Australia | 02-Analyze | RTM (AN) | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-04 | 2016-11-04 | Yes |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055953 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Log Gaps (AN) | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-11 | 2016-11-11 | Yes |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055954 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct Design Workshops (AN) | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 114h | 0h | 114h | 2016-12-19 | 2017-01-13 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 26 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055955 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Perform Gap Resolution (AN) | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-21 | 2016-11-21 | Yes |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055956 | No | No | Yes | Australia | Australia | 03-Design/Build | PDD-Baseline (D/B) | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055957 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-Baseline (D/B) | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-12-12 | 2016-12-16 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055958 | No | No | Yes | Australia | Australia | 03-Design/Build | Support to Developpers (D/B) | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055959 | No | No | Yes | Australia | Australia | 03-Design/Build | FSD-Baseline (D/B) | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055960 | No | No | Yes | Australia | Australia | 03-Design/Build | DEV FUT- Baseline (D/B) | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055961 | No | No | Yes | Australia | Australia | 03-Design/Build | CONFIG-Baseline (D/B) | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055962 | No | No | Yes | Australia | Australia | 03-Design/Build | SDD Writing | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055963 | No | No | Yes | Australia | Australia | 03-Design/Build | ERTR021-FSD-ATO Ref | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 61h | 0h | 61h | 2017-02-06 | 2017-02-17 | Yes |  |  | DELIV.FUN-203.Functional Specification - Enhancement | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055964 | No | No | Yes | Australia | Australia | 03-Design/Build | ERTR021-DEV FUT-ATO Ref | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2017-03-15 | 2017-03-15 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055965 | No | No | Yes | Australia | Australia | 03-Design/Build | TX_01-CONFIG-FI-Output Taxes | RTR | FUN | SI | Onshore | Shaw; Graham | IBM | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2017-02-13 | 2017-02-15 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055966 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055967 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Preparation | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2017-04-10 | 2017-04-13 | Yes |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055968 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Prepare | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055969 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - LOG | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2017-05-23 | 2017-06-02 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055970 | No | No | Yes | Australia | Australia | 04-Test | Regression - Run Tests - LOG | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055971 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Support | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | OpEx | Localization | IT - External | 6h | 0h | 6h | 2017-04-03 | 2017-04-03 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055972 | No | No | Yes | Australia | Australia | 03-Design/Build | TM_16-CONFIG-Freight Settlement | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055973 | No | No | Yes | Australia | Australia | 03-Design/Build | TM_17-CONFIG-Configure Invoice Integration in SAP ECC | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055974 | No | No | Yes | Australia | Australia | 03-Design/Build | TM_15-CONFIG-Configure Basic Settings for Charge Calculations (SAP TM) | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055975 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - LOG | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 52h | 0h | 52h | 2017-07-10 | 2017-07-14 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055976 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 89h | 0h | 89h | 2017-04-28 | 2017-05-19 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055977 | No | No | Yes | Australia | Australia | 03-Design/Build | XXX_XX-CONFIG-AirFreight | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-10 | 2017-04-10 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055978 | No | No | Yes | Australia | Australia | 03-Design/Build | XXX_XX-CONFIG FUT-AirFreight | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-04-10 | 2017-04-28 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 5 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055979 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - LOG | LOG | FUN | SI | Onshore | Morgan; Wilishia | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2017-06-05 | 2017-06-16 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055980 | No | No | Yes | Australia | Australia | 03-Design/Build | DM_01-CONFIG-Advanced Planning & Optimization (BW) | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2017-01-30 | 2017-02-01 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055981 | No | No | Yes | Australia | Australia | 03-Design/Build | DM_01-CONFIG FUT-Advanced Planning & Optimization (BW) | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-02-27 | 2017-03-03 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055982 | No | No | Yes | Australia | Australia | 03-Design/Build | CIF­_02-CONFIG-Advanced Planning & Optimization (CIF) | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-03-06 | 2017-03-07 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055983 | No | No | Yes | Australia | Australia | 03-Design/Build | DP_01-CONFIG FUT-Advanced Planning & Optimization (DP) | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-03 | 2017-03-03 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055984 | No | No | Yes | Australia | Australia | 03-Design/Build | DP_02-CONFIG FUT-Advanced Planning & Optimization (DP) | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-03 | 2017-03-03 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055985 | No | No | Yes | Australia | Australia | 03-Design/Build | DP_03-CONFIG FUT-Advanced Planning & Optimization (DP) | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-03 | 2017-03-03 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055986 | No | No | Yes | Australia | Australia | 03-Design/Build | CIF­_02-CONFIG FUT-Advanced Planning & Optimization (CIF) | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-03-14 | 2017-03-14 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055987 | No | No | Yes | Australia | Australia | 03-Design/Build | CTM_01-CONFIG FUT-Advanced Planning & Optimization (CTM) | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-03-15 | 2017-03-15 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055988 | No | No | Yes | Australia | Australia | 03-Design/Build | CTM_02-CONFIG FUT-Advanced Planning & Optimization (CTM) | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-14 | 2017-03-14 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055989 | No | No | Yes | Australia | Australia | 03-Design/Build | CTM_03-CONFIG FUT-Advanced Planning & Optimization (CTM) | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-03 | 2017-03-03 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055990 | No | No | Yes | Australia | Australia | 03-Design/Build | CTM_04-CONFIG FUT-Advanced Planning & Optimization (CTM) | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055991 | No | No | Yes | Australia | Australia | 03-Design/Build | CTM_01-CONFIG-Advanced Planning & Optimization (CTM) | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-03-16 | 2017-03-17 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055992 | No | No | Yes | Australia | Australia | 03-Design/Build | CTM_02-CONFIG-Advanced Planning & Optimization (CTM) | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2017-03-08 | 2017-03-10 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055993 | No | No | Yes | Australia | Australia | 03-Design/Build | CTM_03-CONFIG-Advanced Planning & Optimization (CTM) | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055994 | No | No | Yes | Australia | Australia | 03-Design/Build | CTM_04-CONFIG-Advanced Planning & Optimization (CTM) | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-04 | 2017-02-04 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055995 | No | No | Yes | Australia | Australia | 03-Design/Build | DP_01-CONFIG-Advanced Planning & Optimization (DP) | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055996 | No | No | Yes | Australia | Australia | 03-Design/Build | DP_02-CONFIG-Advanced Planning & Optimization (DP) | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055997 | No | No | Yes | Australia | Australia | 03-Design/Build | DP_03-CONFIG-Advanced Planning & Optimization (DP) | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055998 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia - (Capex) - (D/B) | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2017-02-08 | 2017-02-10 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055999 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - PTM | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-05-15 | 2017-05-19 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056000 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - PTM | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056001 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Break/Fix - PTM | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 54h | 0h | 54h | 2017-05-08 | 2017-05-14 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056002 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-05-02 | 2017-05-07 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056003 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Support | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056004 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Preparation | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-04-17 | 2017-04-21 | Yes |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056005 | No | No | Yes | Australia | Australia | 04-Test | Regression - Run Tests - PTM | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056006 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Validate | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-09 | 2017-03-14 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056007 | No | No | Yes | Australia | Australia | 04-Test | Regression - Manage defects (Capex) - PTM | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056008 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - PTM | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2017-06-07 | 2017-06-09 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056009 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056010 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - PTM | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-06-05 | 2017-06-06 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056011 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - PTM | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056012 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix - PTM | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-04 | 2017-08-07 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056013 | No | No | Yes | Australia | Australia | 03-Design/Build | DP_04-CONFIG FUT-Advanced Planning & Optimization (DP) | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-04-24 | 2017-04-28 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056014 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Prep | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.UAT Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056015 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - PTM | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056016 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - PTM | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056017 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Validate | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056018 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - PTM | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056019 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Prepare - PTM | PTM | FUN | SI | Offshore | Remane; Rajan | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056020 | No | No | Yes | Australia | Australia | 04-Test | Training Materials-Traininng Data (exercise book) (Test) | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | WP.CM.Exercises Book and Data | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056021 | No | No | Yes | Australia | Australia | 04-Test | Training Materials-Training materials translation(Test) | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  | DELIV.CM-401.Training Materials | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056022 | No | No | Yes | Australia | Australia | 04-Test | Training Materials-Concept slides (Test) | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | OpEx | Localization | IT - Internal | 177h | 0h | 177h | 2017-03-27 | 2017-06-02 | Yes |  |  | DELIV.CM-401.Training Materials | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 16 | 42 | 42 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056023 | No | No | Yes | Australia | Australia | 04-Test | Training Materials-Concept slides (Localization) (Test) | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | OpEx | Localization | IT - Internal | 33h | 0h | 33h | 2017-03-13 | 2017-06-16 | Yes |  |  | DELIV.CM-401.Training Materials | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056024 | No | No | Yes | Australia | Australia | 04-Test | Training Materials-Concept slides (Interim) (Test) | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | DELIV.CM-401.Training Materials | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056025 | No | No | Yes | Australia | Australia | 03-Design/Build | Training Courses-Create/Update course ppt (D/B) | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | OpEx | Localization | IT - Internal | 165h | 0h | 165h | 2017-04-03 | 2017-06-09 | Yes |  |  | DELIV.CM-220.Training Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 8 | 0 | 0 | 39 | 42 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056026 | No | No | Yes | Australia | Australia | 06-Hypercare | Train end-users (HYP) | CM | CM | Saputo | Onshore | Doucet; Caroline | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | ACT.CM.Deliver Training to End Users | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056027 | No | No | Yes | Australia | Australia | 03-Design/Build | System Security Handover Activities | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-29 | 2016-11-29 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056028 | No | No | Yes | Australia | Australia | 02-Analyze | System Security Handover Activities (AN) | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-08 | 2016-11-08 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056029 | No | No | Yes | Australia | Australia | 04-Test | SIT1 | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  | ACT.SEC.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056030 | No | No | Yes | Australia | Australia | 03-Design/Build | Composite Role Build | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Localization | IT - External | 11.25h | 0h | 11.25h | 2017-03-16 | 2017-03-20 | Yes |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.25 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056031 | No | No | Yes | Australia | Australia | 03-Design/Build | Derived Role Build - BUS | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Localization | IT - External | 11.25h | 0h | 11.25h | 2017-02-10 | 2017-03-20 | Yes |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.25 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056032 | No | No | Yes | Australia | Australia | 03-Design/Build | Master Role Build and UT | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056033 | No | No | Yes | Australia | Australia | 03-Design/Build | Security Role FUT | SEC | SEC | SI | Offshore | Baque; Jim | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056034 | No | No | Yes | Australia | Australia | 03-Design/Build | Management (D/B) | TAI | TAI | Saputo | Onshore | Tengler; David | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-09 | 2017-01-13 | Yes |  |  | ACT.TAI.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056035 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT2) | DEV | DEV | Saputo | Onshore | Boisvert; Claude MIS | Saputo | Yes | CapEx | Localization | IT - Internal | 28h | 0h | 28h | 2017-05-29 | 2017-06-06 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056036 | No | No | Yes | Australia | Australia | 03-Design/Build | Development GRC (D/B) | DEV | DEV | Saputo | Onshore | Boisvert; Claude MIS | Saputo | Yes | CapEx | Localization | IT - Internal | 174h | 0h | 174h | 2017-02-06 | 2017-03-09 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49.5 | 52 | 50 | 16 | 6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056037 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT1) | DEV | DEV | Saputo | Onshore | Boisvert; Claude MIS | Saputo | Yes | CapEx | Localization | IT - Internal | 4h | 0h | 4h | 2017-04-24 | 2017-05-08 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056038 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Development (Cutover/Go-live) - DEV | DEV | DEV | Saputo | Onshore | Boisvert; Claude MIS | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-02 | 2017-06-02 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056039 | No | No | Yes | Australia | Australia |  | AUS - DEV KT | DEV | DEV | Saputo | Onshore | Boisvert; Claude MIS | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-05-31 | 2017-05-31 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056040 | No | No | Yes | Australia | Australia | 06-Hypercare | HC - Break/Fix - Dev | DEV | DEV | Saputo | Onshore | Boisvert; Claude MIS | Saputo | Yes | CapEx | Localization | IT - Internal | 11.5h | 0h | 11.5h | 2017-07-03 | 2017-07-11 | Yes |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056041 | No | No | Yes | Australia | Australia | 06-Hypercare | Hypercare - Support - TAI | TAI | TAI | Saputo | Onshore | Shindadkar; Amol | Saputo | Yes | CapEx | Localization | IT - Internal | 59h | 0h | 59h | 2017-07-03 | 2017-08-04 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 7 | 12 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056042 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Support | TAI | TAI | Saputo | Onshore | Shindadkar; Amol | Saputo | Yes | CapEx | Localization | IT - Internal | 62h | 0h | 62h | 2017-06-19 | 2017-07-07 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 32 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056043 | No | No | Yes | Australia | Australia | 06-Hypercare | Hypercare | SEC | SEC | SI | Offshore | Bobiles; CharmaineAnn | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-04 | 2017-07-04 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056044 | No | No | Yes | Australia | Australia | 04-Test | SIT1 | SEC | SEC | SI | Offshore | Bobiles; CharmaineAnn | Accenture | Yes | CapEx | Localization | IT - External | 43.5h | 0h | 43.5h | 2017-04-24 | 2017-05-19 | Yes |  |  | ACT.SEC.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3.5 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056045 | No | No | Yes | Australia | Australia | 06-Hypercare | Hypercare - FUN - BI | BI | BI | SI | Onshore | Tata; SreeRama | IBM | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2017-07-03 | 2017-07-13 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056046 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Configuration - BI | BI | BI | SI | Onshore | Tata; SreeRama | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2017-06-29 | 2017-06-30 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056047 | No | No | Yes | Australia | Australia | 04-Test | SIT1 | BI | BI | SI | Onshore | Tata; SreeRama | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-04-24 | 2017-05-04 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056048 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | PTM | FUN | Saputo | Onshore | Turner; Jonathan | Saputo | Yes | CapEx | Localization | Business | 4h | 0h | 4h | 2017-04-24 | 2017-05-10 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056049 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - PTM | PTM | FUN | Saputo | Onshore | Turner; Jonathan | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056050 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - PTM | PTM | FUN | Saputo | Onshore | Turner; Jonathan | Saputo | Yes | CapEx | Localization | Business | 14h | 0h | 14h | 2017-06-02 | 2017-06-30 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056051 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - PTM | PTM | FUN | Saputo | Onshore | Turner; Jonathan | Saputo | Yes | CapEx | Localization | Business | 75h | 0h | 75h | 2017-06-12 | 2017-06-30 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 24 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056052 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - PTM | PTM | FUN | Saputo | Onshore | Turner; Jonathan | Saputo | Yes | CapEx | Localization | Business | 100h | 0h | 100h | 2017-07-11 | 2017-08-04 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 34 | 26 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056053 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix - PTM | PTM | FUN | Saputo | Onshore | Turner; Jonathan | Saputo | Yes | CapEx | Localization | Business | 108h | 0h | 108h | 2017-07-10 | 2017-08-04 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 38 | 30 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056054 | No | No | Yes | Australia | Australia | 03-Design/Build | XXX-DEV FUT-Tabular results ( including 6506 ) | PTM | FUN | Saputo | Onshore | Turner; Jonathan | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-06-06 | 2017-06-06 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056055 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - PTM | PTM | FUN | Saputo | Onshore | Montgomery; David | Saputo | Yes | CapEx | Localization | IT - Internal | 59h | 0h | 59h | 2017-05-29 | 2017-07-07 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 8 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056056 | No | No | Yes | Australia | Australia | 03-Design/Build | PDD-Manage Batch and Traceability | PTM | FUN | Saputo | Onshore | Montgomery; David | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056057 | No | No | Yes | Australia | Australia | 03-Design/Build | XXX-FSD-MTS to MII | PTM | FUN | Saputo | Onshore | Montgomery; David | Saputo | Yes | CapEx | Localization | IT - Internal | 90h | 0h | 90h | 2017-02-27 | 2017-03-31 | Yes |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056058 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - PTM | PTM | FUN | Saputo | Onshore | Montgomery; David | Saputo | Yes | CapEx | Localization | IT - Internal | 64h | 0h | 64h | 2017-06-19 | 2017-06-30 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056059 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix - PTM | PTM | FUN | Saputo | Onshore | Montgomery; David | Saputo | Yes | CapEx | Localization | IT - Internal | 109h | 0h | 109h | 2017-07-03 | 2017-08-17 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 16 | 40 | 0 | 38 | 6 | 1 | 0 | 0 | 0 | 0 | 0
1056060 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia - (Capex) - (D/B) | PTM | FUN | Saputo | Onshore | Montgomery; David | Saputo | Yes | CapEx | Localization | IT - Internal | 148h | 0h | 148h | 2017-01-30 | 2017-03-10 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 8 | 40 | 40 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056061 | No | No | Yes | Australia | Australia | 03-Design/Build | GBT_02-CONFIG-Set Up from ERP | PTM | FUN | Saputo | Onshore | Montgomery; David | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-04 | 2017-02-04 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056062 | No | No | Yes | Australia | Australia | 03-Design/Build | GBT_02-CONFIG FUT-Set Up from ERP | PTM | FUN | Saputo | Onshore | Montgomery; David | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-03 | 2017-03-03 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056063 | No | No | Yes | Australia | Australia | 03-Design/Build | GBT_03-CONFIG-Tranfer Data from SAP ERP | PTM | FUN | Saputo | Onshore | Montgomery; David | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-20 | 2017-02-20 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056064 | No | No | Yes | Australia | Australia | 03-Design/Build | GBT_03-CONFIG FUT-Tranfer Data from SAP ERP | PTM | FUN | Saputo | Onshore | Montgomery; David | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-03 | 2017-03-03 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056065 | No | No | Yes | Australia | Australia | 03-Design/Build | GBT_01-CONFIG FUT-Filter Plant | PTM | FUN | Saputo | Onshore | Montgomery; David | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056066 | No | No | Yes | Australia | Australia | 03-Design/Build | GBT_01-CONFIG-Filter Plant | PTM | FUN | Saputo | Onshore | Montgomery; David | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056067 | No | No | Yes | Australia | Australia | 03-Design/Build | PDD-Process Milk Sales Order and Swaps | OTC | FUN | SI | Onshore | Debasis; Dey | IBM | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2017-03-29 | 2017-03-31 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056068 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - OTC | OTC | FUN | SI | Onshore | Debasis; Dey | IBM | Yes | CapEx | Localization | IT - External | 17h | 0h | 17h | 2017-06-12 | 2017-06-29 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056069 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Prep | OTC | FUN | SI | Onshore | Debasis; Dey | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2017-06-01 | 2017-06-26 | Yes |  |  | ACT.FUN.UAT Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056070 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Prepare - OTC | OTC | FUN | SI | Onshore | Debasis; Dey | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2017-06-19 | 2017-06-26 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056071 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix - OTC | OTC | FUN | SI | Onshore | Debasis; Dey | IBM | Yes | CapEx | Localization | IT - External | 204h | 0h | 204h | 2017-07-10 | 2017-08-11 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 44 | 44 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0
1056072 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - OTC | OTC | FUN | SI | Onshore | Debasis; Dey | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056073 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - OTC | OTC | FUN | SI | Onshore | Debasis; Dey | IBM | Yes | CapEx | Localization | IT - External | 19h | 0h | 19h | 2017-05-31 | 2017-06-09 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056074 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - OTC | OTC | FUN | SI | Onshore | Debasis; Dey | IBM | Yes | CapEx | Localization | IT - External | 3h | 0h | 3h | 2017-06-28 | 2017-06-28 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056075 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - OTC | OTC | FUN | SI | Onshore | Debasis; Dey | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-06-12 | 2017-07-04 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056076 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - OTC | OTC | FUN | SI | Onshore | Debasis; Dey | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-06-06 | 2017-07-06 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056077 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | OTC | FUN | SI | Onshore | Debasis; Dey | IBM | Yes | CapEx | Localization | IT - External | 34h | 0h | 34h | 2017-04-24 | 2017-05-02 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056078 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Break/Fix - OTC | OTC | FUN | SI | Onshore | Debasis; Dey | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-04-24 | 2017-04-28 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056079 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - PTM | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | CapEx | Localization | IT - Internal | 87h | 0h | 87h | 2017-06-05 | 2017-06-15 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056080 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia - (Capex) - (D/B) | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056081 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix - PTM | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | CapEx | Localization | IT - Internal | 110.5h | 0h | 110.5h | 2017-07-10 | 2017-08-18 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.5 | 12 | 24 | 24 | 17 | 18 | 0 | 0 | 0 | 0 | 0
1056082 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - PTM | PTM | FUN | Saputo | Onshore | McFadden; Jennifer | Saputo | Yes | CapEx | Localization | IT - Internal | 54h | 0h | 54h | 2017-06-20 | 2017-06-30 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056083 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - LOG | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | CapEx | Localization | Business | 118h | 0h | 118h | 2017-05-30 | 2017-06-16 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056084 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | CapEx | Localization | Business | 60h | 0h | 60h | 2016-10-31 | 2016-12-16 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056085 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct Design Workshops (AN) | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | CapEx | Localization | Business | 60h | 0h | 60h | 2016-11-28 | 2016-12-16 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056086 | No | No | Yes | Australia | Australia | 01-Preparation | Prepare KT) (PP) | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | OpEx | Localization | Business | 14h | 0h | 14h | 2016-10-11 | 2016-10-14 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056087 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Support | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | OpEx | Localization | Business | 18h | 0h | 18h | 2017-04-10 | 2017-04-13 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056088 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Validate | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | OpEx | Localization | Business | 14h | 0h | 14h | 2017-04-17 | 2017-04-20 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056089 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - LOG | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | CapEx | Localization | Business | 80h | 0h | 80h | 2017-05-01 | 2017-06-27 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 13 | 18 | 18 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056090 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Prepare - baseline - LOG | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | CapEx | Localization | Business | 34h | 0h | 34h | 2017-06-19 | 2017-06-23 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056091 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - LOG | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | CapEx | Localization | Business | 43h | 0h | 43h | 2017-05-09 | 2017-06-29 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 8 | 14 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056092 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | CapEx | Localization | Business | 8h | 0h | 8h | 2017-05-08 | 2017-05-18 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056093 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - LOG | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | CapEx | Localization | Business | 183h | 0h | 183h | 2017-07-03 | 2017-08-10 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 32 | 32 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0
1056094 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - baseline - LOG | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | CapEx | Localization | Business | 15h | 0h | 15h | 2017-06-23 | 2017-06-30 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056095 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Validate - baseline | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | CapEx | Localization | Business | 8h | 0h | 8h | 2017-06-26 | 2017-06-30 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056096 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | LOG | FUN | Saputo | Onshore | Sturm; George | Saputo | Yes | CapEx | Localization | Business | 9h | 0h | 9h | 2017-02-27 | 2017-03-02 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056097 | No | No | Yes | Australia | Australia | 02-Analyze | WRICEFs inventory (AN) | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-12-05 | 2017-01-20 | Yes |  |  | DELIV.DEV-102.RICEFW Inventory | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056098 | No | No | Yes | Australia | Australia | 02-Analyze | WRICEFs inventory (AN) | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-11-09 | 2016-11-09 | Yes |  |  | DELIV.DEV-102.RICEFW Inventory | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056099 | No | No | Yes | Australia | Australia |  | AUS - DEV KT | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-05-31 | 2017-05-31 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056100 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Development (Cutover/Go-live) - DEV | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | CapEx | Localization | IT - Internal | 40h | 0h | 40h | 2017-06-12 | 2017-06-16 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056101 | No | No | Yes | Australia | Australia | 06-Hypercare | Development (Hypercare) - DEV | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | CapEx | Localization | IT - Internal | 20h | 0h | 20h | 2017-07-24 | 2017-07-28 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056102 | No | No | Yes | Australia | Australia | 01-Preparation | RICEFW Inventory (PP) | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-09-25 | 2016-09-25 | Yes |  |  | DELIV.DEV-102.RICEFW Inventory | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056103 | No | No | Yes | Australia | Australia | 03-Design/Build | Development (D/B) | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | CapEx | Localization | IT - Internal | 220h | 0h | 220h | 2017-02-14 | 2017-04-28 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 16 | 20 | 24 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056104 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT1) | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | CapEx | Localization | IT - Internal | 80h | 0h | 80h | 2017-05-01 | 2017-05-12 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056105 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT2) | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | CapEx | Localization | IT - Internal | 90h | 0h | 90h | 2017-05-15 | 2017-06-02 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 20 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056106 | No | No | Yes | Australia | Australia | 06-Hypercare | HC - Manage defects - Dev | DEV | DEV | Saputo | Onshore | Bitton; Daniel | Saputo | Yes | CapEx | Localization | IT - Internal | 40h | 0h | 40h | 2017-07-03 | 2017-07-07 | Yes |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056107 | No | No | Yes | Australia | Australia | 03-Design/Build | Management (D/B) | CM | CM | Saputo | Onshore | Lochner; Andrea | Saputo | Yes | OpEx | Localization | IT - Internal | 77h | 0h | 77h | 2017-03-20 | 2017-04-21 | Yes |  |  | ACT.CM.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 20 | 10 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056108 | No | No | Yes | Australia | Australia | 02-Analyze | Communication plan(AN) | CM | CM | Saputo | Onshore | Lochner; Andrea | Saputo | Yes | OpEx | Localization | IT - Internal | 6h | 0h | 6h | 2016-12-13 | 2017-02-07 | Yes |  |  | DELIV.CM-106.Communication Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056109 | No | No | Yes | Australia | Australia | 02-Analyze | Change Impacts Analysis (AN) | CM | CM | Saputo | Onshore | Lochner; Andrea | Saputo | Yes | OpEx | Localization | IT - Internal | 7h | 0h | 7h | 2016-12-12 | 2017-02-06 | Yes |  |  | DELIV.CM-014.Change Impacts Analysis | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056110 | No | No | Yes | Australia | Australia | 02-Analyze | Change Agents Network (AN) | CM | CM | Saputo | Onshore | Lochner; Andrea | Saputo | Yes | OpEx | Localization | IT - Internal | 129h | 0h | 129h | 2016-12-13 | 2017-03-20 | Yes |  |  | DELIV.CM-124.Change Agents Network | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 40 | 40 | 40 | 6 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056111 | No | No | Yes | Australia | Australia | 02-Analyze | Management (AN) | CM | CM | Saputo | Onshore | Lochner; Andrea | Saputo | Yes | OpEx | Localization | IT - Internal | 224h | 0h | 224h | 2016-11-07 | 2017-01-13 | Yes |  |  | ACT.CM.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056112 | No | No | Yes | Australia | Australia | 02-Analyze | Process Role Catalog (AN) | CM | CM | Saputo | Onshore | Lochner; Andrea | Saputo | Yes | OpEx | Localization | IT - Internal | 4h | 0h | 4h | 2016-12-12 | 2017-02-06 | Yes |  |  | DELIV.CM-008.Process Role Catalog | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056113 | No | No | Yes | Australia | Australia | 04-Test | Management (Test) - CM | CM | CM | Saputo | Onshore | Lochner; Andrea | Saputo | Yes | CapEx | Localization | IT - Internal | 40h | 0h | 40h | 2017-05-01 | 2017-05-05 | Yes |  |  | ACT.CM.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056114 | No | No | Yes | Australia | Australia | 03-Design/Build | Role Mapping (D/B) | CM | CM | Saputo | Onshore | Lochner; Andrea | Saputo | Yes | OpEx | Localization | IT - Internal | 40h | 0h | 40h | 2017-03-06 | 2017-03-10 | Yes |  |  | DELIV.CM-218.Role Mapping | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056115 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition Plan (D/B) | CM | CM | Saputo | Onshore | Lochner; Andrea | Saputo | Yes | OpEx | Localization | IT - Internal | 4h | 0h | 4h | 2017-03-16 | 2017-03-31 | Yes |  |  | DELIV.CM-117.Transition Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056116 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect - DC | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 72h | 0h | 72h | 2017-05-23 | 2017-06-02 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056117 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Cutover - Support - DC | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | OpEx | Localization | IT - External | 32h | 0h | 32h | 2017-06-27 | 2017-06-30 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056118 | No | Yes | No | Australia | Australia | 04-Test | Retrofit Testing (Accenture) - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.MDG.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056119 | No | Yes | No | Australia | Australia | 04-Test | Functional Testing (Accenture) - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-17 | 2017-04-17 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056120 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Cutover - Validate - DC | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056121 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect (Capex) - DC | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056122 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - DC | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | ACT.MDG.Mock Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056123 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate - DC | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056124 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Execute - DC | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2017-05-08 | 2017-05-19 | Yes |  |  | ACT.MDG.Mock Load | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056125 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Cutover - Prepare - DC | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | OpEx | Localization | IT - External | 40h | 0h | 40h | 2017-06-05 | 2017-06-09 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056126 | No | Yes | No | Australia | Australia | 03-Design/Build | PDD - Edit, Review, or Approve - Manage Cost Centre - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2017-03-20 | 2017-03-21 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056127 | No | Yes | No | Australia | Australia | 03-Design/Build | PDD - Edit, Review, or Approve - Manage Cost Centre Hierarchy - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-04-03 | 2017-04-07 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056128 | No | Yes | No | Australia | Australia | 03-Design/Build | PDD - Edit, Review, or Approve - Manage Cost Centre: Block/Unblock Cost Centre - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056129 | No | Yes | No | Australia | Australia | 03-Design/Build | PDD - Edit, Review, or Approve - Manage Cost Centre: Create Cost Centre - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056130 | No | Yes | No | Australia | Australia | 03-Design/Build | PDD - Edit, Review, or Approve - Manage Cost Centre: Update Cost Centre - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056131 | No | Yes | No | Australia | Australia | 03-Design/Build | PDD - Edit, Review, or Approve - Manage Cost Element - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056132 | No | Yes | No | Australia | Australia | 03-Design/Build | PDD - Edit, Review, or Approve - Manage Cost Element Hierarchy - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056133 | No | Yes | No | Australia | Australia | 03-Design/Build | PDD - Edit, Review, or Approve - Manage Cost Element: Create Cost Element - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056134 | No | Yes | No | Australia | Australia | 03-Design/Build | PDD - Edit, Review, or Approve - Manage Cost Element: Delete/Deactivate Cost Element - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056135 | No | Yes | No | Australia | Australia | 03-Design/Build | PDD - Edit, Review, or Approve - Manage Cost Element: Update Cost Element - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056136 | No | Yes | No | Australia | Australia | 03-Design/Build | PDD - Edit, Review, or Approve - Manage G/L Account Centrally - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056137 | No | Yes | No | Australia | Australia | 03-Design/Build | PDD - Edit, Review, or Approve - Manage G/L Account Centrally: Block G/L Account - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056138 | No | Yes | No | Australia | Australia | 03-Design/Build | PDD - Edit, Review, or Approve - Manage G/L Account Centrally: Create New G/L Account - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056139 | No | Yes | No | Australia | Australia | 03-Design/Build | PDD - Edit, Review, or Approve - Manage G/L Account Centrally: Mark Existing G/L Account for Deletion - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056140 | No | Yes | No | Australia | Australia | 03-Design/Build | PDD - Edit, Review, or Approve - Manage G/L Account Centrally: Update Existing G/L Account - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056141 | No | Yes | No | Australia | Australia | 03-Design/Build | PDD - Edit, Review, or Approve - Manage Profit Centre - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056142 | No | Yes | No | Australia | Australia | 03-Design/Build | PDD - Edit, Review, or Approve - Manage Profit Centre Hierarchy - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056143 | No | Yes | No | Australia | Australia | 03-Design/Build | PDD - Edit, Review, or Approve - Manage Profit Centre: Block/Unblock Profit Centre - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056144 | No | Yes | No | Australia | Australia | 03-Design/Build | PDD - Edit, Review, or Approve - Manage Profit Centre: Create Profit Centre - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056145 | No | Yes | No | Australia | Australia | 03-Design/Build | PDD - Edit, Review, or Approve - Manage Profit Centre: Update Profit Centre - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056146 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Cutover - Financial Objects - SI - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-06-19 | 2017-06-23 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056147 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | UAT - Financial Objects - SI - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056148 | No | Yes | No | Australia | Australia | 03-Design/Build | PDD - Edit, Review, or Approve - Maintain G/L Account Collectively - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-03-13 | 2017-03-17 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056149 | No | Yes | No | Australia | Australia | 03-Design/Build | PDD - Edit, Review, or Approve - Maintain G/L Account Collectively: Create Mass Change Request for Accounts - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-03-27 | 2017-03-31 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056150 | No | Yes | No | Australia | Australia | 03-Design/Build | SDD - Edit, Review, or Approve - Profit Centre Accounting - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056151 | No | Yes | No | Australia | Australia | 03-Design/Build | SDD - Edit, Review, or Approve - Cost Center - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056152 | No | Yes | No | Australia | Australia | 03-Design/Build | SDD - Edit, Review, or Approve - General Ledger - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056153 | No | Yes | No | Australia | Australia | 03-Design/Build | Test preparation (Accenture) - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-10 | 2017-04-10 | Yes |  |  | DELIV.TST-307.Assembly Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056154 | No | Yes | No | Australia | Australia | 04-Test | Documentation and Program Work (Accenture) - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 72h | 0h | 72h | 2017-04-10 | 2017-05-05 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056155 | No | Yes | No | Australia | Australia | 06-Hypercare | HC - Break/Fix - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2017-07-04 | 2017-07-07 | Yes |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056156 | No | Yes | No | Australia | Australia | 06-Hypercare | HC - Manage defects - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-07-04 | 2017-07-28 | Yes |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056157 | No | Yes | No | Australia | Australia | 04-Test | Test Preparation (Accenture) - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056158 | No | Yes | No | Australia | Australia | 06-Hypercare | HC - Saputo - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2017-07-10 | 2017-07-21 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056159 | No | Yes | No | Australia | Australia | 04-Test | SIT 2 - Run tests (Saputo) - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.MDG.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056160 | No | Yes | No | Australia | Australia | 04-Test | SIT 1 - Run tests (Accenture) - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | ACT.MDG.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056161 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | UAT - Document work around (Accenture) - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056162 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Cutover - Prepare - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-06-12 | 2017-06-16 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056163 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix (Accenture) - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056164 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | UAT - Manage Defects (Accenture) (Capex) - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056165 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests (Accenture) - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056166 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | UAT - Prep (Select Scenarios) (Accenture) - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-10 | 2017-05-10 | Yes |  |  | ACT.MDG.UAT Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056167 | No | Yes | No | Australia | Australia | 04-Test | Non Regression - Manage defects (Capex) (Accenture) MDG - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.MDG.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056168 | No | Yes | No | Australia | Australia | 04-Test | Non Regression - Run tests (Saputo) - DM | MDG | DM | SI | Offshore | Colak; Ihsan | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.MDG.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056169 | No | Yes | No | Australia | Australia | 03-Design/Build | SAP GRC PC Unit Test | SEC | SEC | SI | Onshore | Kumar; Sathish | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-03-06 | 2017-03-10 | Yes |  |  | DELIV.SEC-215.SAP Security & GRC Processes | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056170 | No | Yes | No | Australia | Australia | 03-Design/Build | SAP GRC PC Build | SEC | SEC | SI | Onshore | Kumar; Sathish | Accenture | Yes | CapEx | Localization | IT - External | 384h | 0h | 384h | 2016-11-21 | 2017-03-22 | Yes |  |  | DELIV.SEC-215.SAP Security & GRC Processes | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 40 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056171 | No | Yes | No | Australia | Australia | 03-Design/Build | SAP GRC PC Design | SEC | SEC | SI | Onshore | Kumar; Sathish | Accenture | Yes | CapEx | Localization | IT - External | 246h | 0h | 246h | 2016-11-14 | 2016-12-30 | Yes |  |  | DELIV.SEC-215.SAP Security & GRC Processes | Complete | NA | NA | 0 |  |  | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056172 | No | Yes | No | Australia | Australia | 02-Analyze | SAP GRC PC Post Installation Steps (AN) | SEC | SEC | SI | Onshore | Kumar; Sathish | Accenture | Yes | CapEx | Localization | IT - External | 58h | 0h | 58h | 2016-11-28 | 2017-01-06 | Yes |  |  | DELIV.SEC-002B.SAP GRC Process Control RTM | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056173 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Management (Cutover/Go-live) - PTM | PTM | FUN | SI | Onshore | Nagarajan; Harish | IBM | Yes | CapEx | Localization | IT - External | 94h | 0h | 94h | 2017-06-05 | 2017-06-25 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056174 | No | No | Yes | Australia | Australia | 06-Hypercare | Management (Hypercare) - PTM | PTM | FUN | SI | Onshore | Nagarajan; Harish | IBM | Yes | CapEx | Localization | IT - External | 531h | 0h | 531h | 2017-06-26 | 2017-08-25 | Yes |  |  | ACT.DEV.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 79 | 65 | 72 | 58 | 58 | 44 | 44 | 44 | 0 | 0 | 0 | 0
1056175 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD248-Certificate Profiles creation and Assignment (transactions QC01&QC15) | PTM | FUN | SI | Onshore | Nagarajan; Harish | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-01-31 | 2017-01-31 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056176 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD247-Condition record for output determination(VV21) | PTM | FUN | SI | Onshore | Nagarajan; Harish | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-01-30 | 2017-01-30 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056177 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD253-QM - Certificate Profile Custom Table maintenance (ZPTP_COA_CUSTOM) | PTM | FUN | SI | Onshore | Nagarajan; Harish | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-02-03 | 2017-02-03 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056178 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD252-QM - Master Inspection Characteristic: Inspection Method Assignment Update | PTM | FUN | SI | Onshore | Nagarajan; Harish | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-02-02 | 2017-02-02 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056179 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD251-Sampling Drawing Procedures | PTM | FUN | SI | Onshore | Nagarajan; Harish | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-02-01 | 2017-02-01 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056180 | No | No | Yes | Australia | Australia | 03-Design/Build | EPTM019-FSD-DTS | PTM | FUN | SI | Onshore | Nagarajan; Harish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | DELIV.FUN-203.Functional Specification - Enhancement | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056181 | No | No | Yes | Australia | Australia | 03-Design/Build | Management (D/B) - PTM | PTM | FUN | SI | Onshore | Nagarajan; Harish | IBM | Yes | CapEx | Localization | IT - External | 460h | 0h | 460h | 2017-01-24 | 2017-04-21 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 44 | 44 | 36 | 44 | 44 | 44 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056182 | No | No | Yes | Australia | Australia | 03-Design/Build | FPTM005-DEV FUT-Raw material GI | PTM | FUN | SI | Onshore | Nagarajan; Harish | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-04-24 | 2017-04-28 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056183 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Create BPML (AN) | PTM | FUN | SI | Onshore | Nagarajan; Harish | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2016-11-18 | 2016-11-18 | Yes |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056184 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Log Gaps (AN) | PTM | FUN | SI | Onshore | Nagarajan; Harish | IBM | Yes | CapEx | Localization | IT - External | 172h | 0h | 172h | 2016-11-18 | 2017-01-25 | Yes |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056185 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) | PTM | FUN | SI | Onshore | Nagarajan; Harish | IBM | Yes | CapEx | Localization | IT - External | 132h | 0h | 132h | 2016-10-31 | 2016-11-25 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056186 | No | No | Yes | Australia | Australia | 01-Preparation | Worshop Preparation Decks) (PP) | PTM | FUN | SI | Onshore | Nagarajan; Harish | IBM | Yes | CapEx | Localization | IT - External | 48h | 0h | 48h | 2016-10-14 | 2016-10-21 | Yes |  |  | WP.FUN-107.Workshop Preparation Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056187 | No | No | Yes | Australia | Australia | 02-Analyze | RTM (AN) | PTM | FUN | SI | Onshore | Nagarajan; Harish | IBM | Yes | CapEx | Localization | IT - External | 141h | 0h | 141h | 2016-11-15 | 2017-01-20 | Yes |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 26 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056188 | No | No | Yes | Australia | Australia | 01-Preparation | Conduct kick-off in Australia (IBM)) (PP) | PTM | FUN | SI | Onshore | Nagarajan; Harish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-27 | 2016-10-27 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056189 | No | No | Yes | Australia | Australia | 01-Preparation | Prepare KT) (PP) | PTM | FUN | SI | Onshore | Nagarajan; Harish | IBM | Yes | OpEx | Localization | IT - External | 76h | 0h | 76h | 2016-10-11 | 2016-10-28 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056190 | No | No | Yes | Australia | Australia | 01-Preparation | Conduct KT sessions) (PP) | PTM | FUN | SI | Onshore | Nagarajan; Harish | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  | WP.FUN.Requirements/Process Design Workshop Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056191 | No | No | Yes | Australia | Australia | 01-Preparation | Prepare Kick-off (IBM)) (PP) | PTM | FUN | SI | Onshore | Nagarajan; Harish | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2016-10-10 | 2016-10-10 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056192 | No | No | Yes | Australia | Australia | 04-Test | Management (Test) - PTM | PTM | FUN | SI | Onshore | Nagarajan; Harish | IBM | Yes | CapEx | Localization | IT - External | 236h | 0h | 236h | 2017-04-24 | 2017-06-04 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 50 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056193 | No | No | Yes | Australia | Australia | 03-Design/Build | Design/Build-Open Text-SEC | SEC | SEC | SI | Onshore | Kothapalli; Omni | Accenture | Yes | CapEx | Localization | IT - External | 172h | 0h | 172h | 2017-04-27 | 2017-06-02 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 32 | 34 | 40 | 31 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056194 | No | No | Yes | Australia | Australia | 06-Hypercare | Hypercare | SEC | SEC | SI | Onshore | Kothapalli; Omni | Accenture | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2017-07-17 | 2017-07-28 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056195 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover | SEC | SEC | SI | Onshore | Kothapalli; Omni | Accenture | Yes | CapEx | Localization | IT - External | 94h | 0h | 94h | 2017-06-19 | 2017-07-03 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056196 | No | No | Yes | Australia | Australia | 03-Design/Build | Security Design/Build | SEC | SEC | SI | Onshore | Kothapalli; Omni | Accenture | Yes | CapEx | Localization | IT - External | 60h | 0h | 60h | 2017-03-20 | 2017-06-05 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056197 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT | SEC | SEC | SI | Onshore | Kothapalli; Omni | Accenture | Yes | CapEx | Localization | IT - External | 89h | 0h | 89h | 2017-06-05 | 2017-06-19 | Yes |  |  | ACT.SEC.Executive UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056198 | No | No | Yes | Australia | Australia | 04-Test | SIT1 | SEC | SEC | SI | Onshore | Kothapalli; Omni | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  | ACT.SEC.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056199 | No | No | Yes | Australia | Australia | 04-Test | SIT2 | SEC | SEC | SI | Onshore | Kothapalli; Omni | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.SEC.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056200 | No | No | Yes | Australia | Australia | 04-Test | Training Materials-Work Instructions/Job aids (Test) | CM | CM | SI | Offshore | Basak; Dipannita | IBM | Yes | OpEx | Localization | IT - External | 342h | 0h | 342h | 2017-03-20 | 2017-06-02 | Yes |  |  | DELIV.CM-451.Work Instructions | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 36 | 0 | 0 | 0 | 36 | 45 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056201 | No | Yes | No | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | LOG | FUN | SI | Onshore | Thippanna; Ashok | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056202 | No | Yes | No | Australia | Australia | 03-Design/Build | Derived Role Build - BUS | SEC | SEC | SI | Offshore | DeBlas; RahpRelly | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-10 | 2017-02-10 | Yes |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056203 | No | Yes | No | Australia | Australia | 03-Design/Build | Master Role Build and UT | SEC | SEC | SI | Offshore | DeBlas; RahpRelly | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056204 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Management (Cutover/Go-live) | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | CapEx | Localization | IT - External | 56h | 0h | 56h | 2017-06-12 | 2017-06-30 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056205 | No | No | Yes | Australia | Australia | 06-Hypercare | Management (Hypercare) - PTP | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | CapEx | Localization | IT - External | 112h | 0h | 112h | 2017-07-03 | 2017-07-21 | Yes |  |  | ACT.DEV.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 42 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056206 | No | No | Yes | Australia | Australia | 04-Test | Management (Test) - PTP | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | CapEx | Localization | IT - External | 124h | 0h | 124h | 2017-04-24 | 2017-06-02 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 20 | 24 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056207 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Create BPML (AN) | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-03 | 2016-11-03 | Yes |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056208 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Log Gaps (AN) | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-31 | 2016-11-04 | Yes |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056209 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct Design Workshops (AN) | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | CapEx | Localization | IT - External | 299h | 0h | 299h | 2016-11-14 | 2017-01-13 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056210 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Perform Gap Resolution (AN) | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-15 | 2016-12-15 | Yes |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056211 | No | No | Yes | Australia | Australia | 03-Design/Build | PDD-Baseline (D/B) | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-09 | 2017-01-09 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056212 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-Baseline (D/B) | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056213 | No | No | Yes | Australia | Australia | 03-Design/Build | FSD-Baseline (D/B) | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056214 | No | No | Yes | Australia | Australia | 03-Design/Build | Support to Developpers (D/B) | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056215 | No | No | Yes | Australia | Australia | 03-Design/Build | DEV FUT- Baseline (D/B) | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056216 | No | No | Yes | Australia | Australia | 03-Design/Build | SDD Writing (D/B) | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-27 | 2017-01-27 | Yes |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056217 | No | No | Yes | Australia | Australia | 03-Design/Build | CONFIG FUT-Baseline (D/B) | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056218 | No | No | Yes | Australia | Australia | 03-Design/Build | Support MDM (D/B) | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056219 | No | No | Yes | Australia | Australia | 03-Design/Build | Contribute to Cut-over Planning (D/B) - PTP | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | ACT.FUN.Support Cutover plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056220 | No | No | Yes | Australia | Australia | 03-Design/Build | Management (D/B) | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | CapEx | Localization | IT - External | 166h | 0h | 166h | 2017-02-06 | 2017-04-20 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 44 | 20 | 24 | 0 | 16 | 20 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056221 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | PTP | FUN | SI | Onshore | Rao; Dinkar | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056222 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  | DMS | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056223 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | Yes |  | DMS | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056224 | No | No | Yes | Australia | Australia | 03-Design/Build | PDD-Baseline (D/B) | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  | DMS | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056225 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-Baseline (D/B) | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | Yes |  | DMS | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056226 | No | No | Yes | Australia | Australia | 03-Design/Build | FSD-Baseline (D/B) | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  | DMS | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056227 | No | No | Yes | Australia | Australia | 03-Design/Build | Support to Developpers (D/B) | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  | DMS | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056228 | No | No | Yes | Australia | Australia | 03-Design/Build | CONFIG-Baseline (D/B) | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  | DMS | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056229 | No | No | Yes | Australia | Australia | 03-Design/Build | SDD Writing | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  | DMS | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056230 | No | No | Yes | Australia | Australia | 03-Design/Build | CONFIG FUT-Baseline (D/B) | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-13 | 2016-12-13 | Yes |  | DMS | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056231 | No | No | Yes | Australia | Australia | 03-Design/Build | Support MDM (D/B) | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-03 | 2016-12-03 | Yes |  | DMS | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056232 | No | No | Yes | Australia | Australia | 03-Design/Build | Contribute to Cut-over Planning (D/B) - RTR | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2016-11-22 | 2017-05-19 | Yes |  | DMS | ACT.FUN.Support Cutover plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056233 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix (Hypercare) - RTR | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 48h | 0h | 48h | 2017-07-04 | 2017-09-01 | Yes |  | DMS | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 40 | 0 | 0 | 0
1056234 | No | No | Yes | Australia | Australia | 03-Design/Build | Workaround Procedures (D/B) | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  | DMS | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056235 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - RTR | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-05-29 | 2017-06-02 | Yes |  | DMS | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056236 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD235-DMS - Processes | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-02-07 | 2017-02-13 | Yes |  | DMS | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056237 | No | No | Yes | Australia | Australia | 03-Design/Build | DMS_04-CONFIG FUT-Dairy Mgmt System - Costing | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2017-04-06 | 2017-04-06 | Yes |  | DMS | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056238 | No | No | Yes | Australia | Australia | 03-Design/Build | DMS_04-CONFIG-Dairy Mgmt System - Costing | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 13h | 0h | 13h | 2017-01-14 | 2017-03-30 | Yes |  | DMS | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056239 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD256-DMS Production Volume | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2017-02-20 | 2017-02-20 | Yes |  | DMS | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056240 | No | No | Yes | Australia | Australia | 03-Design/Build | DMS Configuration/UT - Costing AUS - RTR | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 26h | 0h | 26h | 2017-04-18 | 2017-04-21 | Yes |  | DMS | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056241 | No | No | Yes | Australia | Australia | 06-Hypercare | DMS HyperCare solution stabilization - RTR | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 209h | 0h | 209h | 2017-07-03 | 2017-08-14 | Yes |  | DMS | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 48 | 0 | 0 | 52 | 56 | 0 | 0 | 0 | 0 | 0 | 0
1056242 | No | No | Yes | Australia | Australia | 04-Test | DMS SIT AUS - RTR | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 81h | 0h | 81h | 2017-05-01 | 2017-05-31 | Yes |  | DMS | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 28 | 16 | 6 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056243 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | DMS Cut Over - execute - RTR | RTR | FUN | SI | Onshore | Wollberg; Olaf | SAP | Yes | CapEx | Localization | IT - External | 61h | 0h | 61h | 2017-06-14 | 2017-07-07 | Yes |  | DMS | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 48 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056244 | No | No | Yes | Australia | Australia | 04-Test | DMS SIT AUS - RTR | RTR | FUN | SI | Onshore | Strobel; Lars | SAP | Yes | CapEx | Localization | IT - External | 52h | 0h | 52h | 2017-05-22 | 2017-06-02 | Yes |  | DMS | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056245 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | DMS Cut Over - execute - RTR | RTR | FUN | SI | Onshore | Strobel; Lars | SAP | Yes | CapEx | Localization | IT - External | 58h | 0h | 58h | 2017-06-05 | 2017-07-03 | Yes |  | DMS | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 12 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056246 | No | No | Yes | Australia | Australia | 03-Design/Build | DMS Configuration/UT - Costing AUS - RTR | RTR | FUN | SI | Onshore | Strobel; Lars | SAP | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2017-04-18 | 2017-04-24 | Yes |  | DMS | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056247 | No | No | Yes | Australia | Australia | 06-Hypercare | DMS HyperCare solution stabilization - RTR | RTR | FUN | SI | Onshore | Strobel; Lars | SAP | Yes | CapEx | Localization | IT - External | 164h | 0h | 164h | 2017-07-03 | 2017-09-01 | Yes |  | DMS | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 24 | 49 | 24 | 0 | 0 | 15 | 0 | 20 | 0 | 0 | 0
1056248 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD235-DMS - Processes | RTR | FUN | SI | Onshore | Strobel; Lars | SAP | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2017-02-07 | 2017-03-29 | Yes |  | DMS | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056249 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD236-DMS - Manufacturing Processes | RTR | FUN | SI | Onshore | Strobel; Lars | SAP | Yes | CapEx | Localization | IT - External | 22h | 0h | 22h | 2017-02-06 | 2017-03-03 | Yes |  | DMS | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056250 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD237-DMS - Cost Categories assignments | RTR | FUN | SI | Onshore | Strobel; Lars | SAP | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-02-06 | 2017-03-13 | Yes |  | DMS | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056251 | No | No | Yes | Australia | Australia | 03-Design/Build | DMS_04-CONFIG-Dairy Mgmt System - Costing | RTR | FUN | SI | Onshore | Strobel; Lars | SAP | Yes | CapEx | Localization | IT - External | 120h | 0h | 120h | 2017-01-14 | 2017-04-10 | Yes |  | DMS | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 32 | 24 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056252 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - RTR | RTR | FUN | SI | Onshore | Strobel; Lars | SAP | Yes | CapEx | Localization | IT - External | 63h | 0h | 63h | 2017-06-05 | 2017-06-23 | Yes |  | DMS | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 12 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056253 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | RTR | FUN | SI | Onshore | Strobel; Lars | SAP | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2017-01-23 | 2017-01-30 | Yes |  | DMS | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056254 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia - (Capex) - (D/B) | PTM | FUN | SI | Onshore | Poggenbeck; Carsten | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  | DMS | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056255 | No | No | Yes | Australia | Australia | 03-Design/Build | DMS_03-CONFIG-Dairy Mgmt System - Operations | PTM | FUN | SI | Onshore | Poggenbeck; Carsten | SAP | Yes | CapEx | Localization | IT - External | 144h | 0h | 144h | 2017-03-06 | 2017-04-28 | Yes |  | DMS | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 24 | 8 | 24 | 32 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056256 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD239-DMS - Workstations | PTM | FUN | SI | Onshore | Poggenbeck; Carsten | SAP | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-01-16 | 2017-03-27 | Yes |  | DMS | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056257 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD241-DMS - Record types | PTM | FUN | SI | Onshore | Poggenbeck; Carsten | SAP | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-02-20 | 2017-03-28 | Yes |  | DMS | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056258 | No | No | Yes | Australia | Australia | 03-Design/Build | DMS Configuration/UT - Planning AUS - PTM (D/B) | PTM | FUN | SI | Onshore | Poggenbeck; Carsten | SAP | Yes | CapEx | Localization | IT - External | 58h | 0h | 58h | 2017-04-10 | 2017-06-09 | Yes |  | DMS | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056259 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | DMS Cut Over - execute - PTM | PTM | FUN | SI | Onshore | Poggenbeck; Carsten | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  | DMS | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056260 | No | No | Yes | Australia | Australia | 04-Test | DMS SIT AUS - PTM | PTM | FUN | SI | Onshore | Poggenbeck; Carsten | SAP | Yes | CapEx | Localization | IT - External | 68h | 0h | 68h | 2017-05-08 | 2017-05-30 | Yes |  | DMS | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 4 | 28 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056261 | No | No | Yes | Australia | Australia | 06-Hypercare | DMS HyperCare solution stabilization - PTM | PTM | FUN | SI | Onshore | Poggenbeck; Carsten | SAP | Yes | CapEx | Localization | IT - External | 182h | 0h | 182h | 2017-07-03 | 2017-08-11 | Yes |  | DMS | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 38 | 48 | 32 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0
1056262 | No | Yes | No | Australia | Australia | 02-Analyze | Old - Log Gaps (AN) | OTC | FUN | SI | Onshore | Sundaram; Vijay | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-21 | 2016-11-21 | Yes |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056263 | No | Yes | No | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) | OTC | FUN | SI | Onshore | Sundaram; Vijay | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056264 | No | Yes | No | Australia | Australia | 02-Analyze | Old - Create BPML (AN) | OTC | FUN | SI | Onshore | Sundaram; Vijay | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056265 | No | Yes | No | Australia | Australia | 02-Analyze | RTM (AN) | OTC | FUN | SI | Onshore | Sundaram; Vijay | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-05 | 2016-11-05 | Yes |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056266 | No | No | Yes | Australia | Australia | 04-Test | SIT2 | SEC | SEC | SI | Offshore | Valencia; Jackie | Accenture | Yes | CapEx | Localization | IT - External | 126h | 0h | 126h | 2017-05-15 | 2017-06-02 | Yes |  |  | ACT.SEC.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056267 | No | No | Yes | Australia | Australia | 04-Test | SIT1 | SEC | SEC | SI | Offshore | Valencia; Jackie | Accenture | Yes | CapEx | Localization | IT - External | 117h | 0h | 117h | 2017-03-20 | 2017-04-12 | Yes |  |  | ACT.SEC.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056268 | No | No | Yes | Australia | Australia | 06-Hypercare | Hypercare | SEC | SEC | SI | Offshore | Valencia; Jackie | Accenture | Yes | CapEx | Localization | IT - External | 31.25h | 0h | 31.25h | 2017-07-10 | 2017-08-17 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 9.5 | 7.75 | 0 | 0 | 0 | 0 | 0
1056269 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover | SEC | SEC | SI | Offshore | Valencia; Jackie | Accenture | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-06-22 | 2017-07-10 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056270 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT | SEC | SEC | SI | Offshore | Valencia; Jackie | Accenture | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-06-05 | 2017-06-08 | Yes |  |  | ACT.SEC.Executive UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056271 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Prepare - DC | SEC | SEC | SI | Offshore | Valencia; Jackie | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056272 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Support - DC | SEC | SEC | SI | Offshore | Valencia; Jackie | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056273 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - DC | SEC | SEC | SI | Offshore | Valencia; Jackie | Accenture | Yes | CapEx | Localization | IT - External | 78h | 0h | 78h | 2017-05-01 | 2017-06-21 | Yes |  |  | ACT.MDG.Mock Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 9 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056274 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect (Capex) - DC | SEC | SEC | SI | Offshore | Valencia; Jackie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056275 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Validate - DC | SEC | SEC | SI | Offshore | Valencia; Jackie | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056276 | No | Yes | No | Australia | Australia | 02-Analyze | Data Construction and staging (AN) | MDG | To Define | Saputo | Onshore | Patrick; Scarlett | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  | ACT.MDG.Data Construction | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056277 | No | No | Yes | Australia | Australia | 03-Design/Build | Offline Process Material Master - Australia Update (Saputo) - DM (D/B) | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | OpEx | Localization | IT - Internal | 1h | 0h | 1h | 2017-03-01 | 2017-04-03 | Yes |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056278 | No | No | Yes | Australia | Australia | 03-Design/Build | Training Train-the-Trainer Materials - Spanish Translation - DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056279 | No | No | Yes | Australia | Australia | 03-Design/Build | Design Material Master MDG (Saputo) - DM (D/B) | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | OpEx | Localization | IT - Internal | 34.5h | 0h | 34.5h | 2017-01-30 | 2017-02-03 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056280 | No | No | Yes | Australia | Australia | 03-Design/Build | Training - Concept Slide Material Master MDG - DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | OpEx | Localization | IT - Internal | 46.5h | 0h | 46.5h | 2017-03-06 | 2017-03-13 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056281 | No | No | Yes | Australia | Australia | 03-Design/Build | Training - Concept Slide Material Master MDG- Translation to Spanish for Arg - DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | OpEx | Localization | IT - Internal | 52.5h | 0h | 52.5h | 2017-03-13 | 2017-03-20 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056282 | No | No | Yes | Australia | Australia | 03-Design/Build | Recording Material Master MDG/Work Instructions- Spanish Translation for Arg - DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | OpEx | Localization | IT - Internal | 47h | 0h | 47h | 2017-02-27 | 2017-03-06 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056283 | No | No | Yes | Australia | Australia | 04-Test | Non Regression - Manage defects (Capex) (Saputo) MDG-DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  | ACT.MDG.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056284 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Prep (Select Scenarios) (Saputo) - DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | OpEx | Localization | IT - Internal | 42h | 0h | 42h | 2017-06-12 | 2017-06-19 | Yes |  |  | ACT.MDG.UAT Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056285 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests (Saputo) - DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | OpEx | Localization | IT - Internal | 52.5h | 0h | 52.5h | 2017-06-05 | 2017-06-12 | Yes |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056286 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Manage Defects (Saputo) (Capex) - DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | CapEx | Localization | IT - Internal | 42.75h | 0h | 42.75h | 2017-06-19 | 2017-06-26 | Yes |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056287 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix (Saputo) - DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056288 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Document work around (Saputo)- DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056289 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Support (Dual maintenance) - DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056290 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run tests (Saputo) - DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | OpEx | Localization | IT - Internal | 16.5h | 0h | 16.5h | 2017-05-29 | 2017-06-05 | Yes |  |  | ACT.MDG.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056291 | No | No | Yes | Australia | Australia | 04-Test | Non Regression - Run tests (Saputo) - DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-05-23 | 2017-05-23 | Yes |  |  | ACT.MDG.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056292 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run tests (Saputo) - DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | OpEx | Localization | IT - Internal | 24.5h | 0h | 24.5h | 2017-05-08 | 2017-05-26 | Yes |  |  | ACT.MDG.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 7.5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056293 | No | No | Yes | Australia | Australia | 04-Test | Test Preparation (Saputo) - DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056294 | No | No | Yes | Australia | Australia | 06-Hypercare | HC - Provide end User Supprt (Opex) - DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | OpEx | Localization | IT - Internal | 97.25h | 0h | 97.25h | 2017-07-03 | 2017-07-24 | Yes |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52.75 | 0 | 44.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056295 | No | No | Yes | Australia | Australia | 03-Design/Build | Test preparation (Saputo) - DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-10 | 2017-04-10 | Yes |  |  | DELIV.TST-307.Assembly Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056296 | No | No | Yes | Australia | Australia | 04-Test | Functional Testing (Saputo) - DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-18 | 2017-04-18 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056297 | No | No | Yes | Australia | Australia | 04-Test | Retrofit Testing (Saputo) - DM | MDG | DM | Saputo | Onshore | Lafrance; Francine | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | Yes |  |  | ACT.MDG.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056298 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Validate - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | OpEx | Localization | IT - External | 41h | 0h | 41h | 2017-06-10 | 2017-06-30 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 10 | 15 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056299 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect (Capex) - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056300 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Execute - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2017-05-15 | 2017-06-09 | Yes |  |  | ACT.MDG.Mock Load | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056301 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Prepare - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | OpEx | Localization | IT - External | 10h | 0h | 10h | 2017-06-12 | 2017-06-23 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056302 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | CapEx | Localization | IT - External | 46h | 0h | 46h | 2017-05-15 | 2017-06-09 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 11 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056303 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-05-15 | 2017-06-09 | Yes |  |  | ACT.MDG.Mock Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056304 | No | No | Yes | Australia | Australia | 06-Hypercare | HC - Manage defects - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-07-17 | 2017-07-31 | Yes |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 36 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056305 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | CapEx | Localization | IT - External | 191h | 0h | 191h | 2017-04-10 | 2017-06-09 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 27 | 27 | 20 | 30 | 31 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056306 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Support - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | OpEx | Localization | IT - External | 192h | 0h | 192h | 2017-06-10 | 2017-07-14 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 36 | 32 | 30 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056307 | No | No | Yes | Australia | Australia | 04-Test | Mock1 – Manage defect (Capex) - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | CapEx | Localization | IT - External | 50h | 0h | 50h | 2017-04-17 | 2017-04-28 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056308 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Validate - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | OpEx | Localization | IT - External | 31h | 0h | 31h | 2017-04-17 | 2017-04-28 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056309 | No | No | Yes | Australia | Australia | 04-Test | Data collection templates - explain and collect - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | CapEx | Localization | IT - External | 107h | 0h | 107h | 2017-02-24 | 2017-03-24 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056310 | No | No | Yes | Australia | Australia | 04-Test | Data load - DC | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-03-27 | 2017-04-07 | Yes |  |  | ACT.MDG.Mock Load | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056311 | No | No | Yes | Australia | Australia | 02-Analyze | Data Construction and staging - DC (AN) | MDG | DC | SI | Offshore | Moya; Christopher | Accenture | Yes | CapEx | Localization | IT - External | 524h | 0h | 524h | 2016-12-01 | 2017-03-10 | Yes |  |  | ACT.MDG.Data Construction | Complete | NA | NA | 0 |  |  | 0 | 0 | 18 | 45 | 45 | 36 | 45 | 0 | 36 | 45 | 45 | 45 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056312 | No | Yes | No | Australia | Australia | 06-Hypercare | HC - Break/Fix - Dev | DEV | DEV | SI | Onshore | Lu; Richard | Accenture | Yes | CapEx | Localization | IT - External | 171h | 0h | 171h | 2017-07-04 | 2017-07-31 | Yes |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 36 | 45 | 45 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056313 | No | Yes | No | Australia | Australia | 04-Test | Development (SIT1) | DEV | DEV | SI | Onshore | Lu; Richard | Accenture | Yes | CapEx | Localization | IT - External | 85h | 0h | 85h | 2017-04-24 | 2017-05-12 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056314 | No | Yes | No | Australia | Australia | 04-Test | Development (SIT2) | DEV | DEV | SI | Onshore | Lu; Richard | Accenture | Yes | CapEx | Localization | IT - External | 131h | 0h | 131h | 2017-05-15 | 2017-06-02 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 41 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056315 | No | Yes | No | Australia | Australia |  | AUS - DEV KT | DEV | DEV | SI | Onshore | Lu; Richard | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-31 | 2017-05-31 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056316 | No | Yes | No | Australia | Australia | 03-Design/Build | Development MDG (D/B) | DEV | DEV | SI | Onshore | Lu; Richard | Accenture | Yes | CapEx | Localization | IT - External | 288h | 0h | 288h | 2017-03-06 | 2017-04-28 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 36 | 45 | 45 | 36 | 0 | 36 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056317 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Development (Cutover/Go-live) - DEV | DEV | DEV | SI | Onshore | Lu; Richard | Accenture | Yes | CapEx | Localization | IT - External | 157h | 0h | 157h | 2017-06-05 | 2017-06-30 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 36 | 40 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056318 | No | Yes | No | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | PTP | FUN | SI | Onshore | Luna; Sandra | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-01-23 | 2017-03-17 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056319 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | LOG | FUN | SI | Onshore | Talwar; Vikram | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056320 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - PTM | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 17h | 0h | 17h | 2017-05-29 | 2017-06-23 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056321 | No | No | Yes | Australia | Australia | 03-Design/Build | EPTM018-DEV FUT-Chemical analysis machines | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056322 | No | No | Yes | Australia | Australia | 03-Design/Build | XXX-FSD-MTS to MII | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056323 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix - PTM | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 128h | 0h | 128h | 2017-07-03 | 2017-08-18 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 42 | 12 | 0 | 4 | 8 | 20 | 0 | 0 | 0 | 0 | 0
1056324 | No | No | Yes | Australia | Australia | 03-Design/Build | Management (D/B) - PTM | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 35h | 0h | 35h | 2017-02-14 | 2017-03-10 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 22 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056325 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia - (Capex) - (D/B) | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056326 | No | No | Yes | Australia | Australia | 03-Design/Build | FSD-Baseline (D/B) | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 64h | 0h | 64h | 2017-04-17 | 2017-05-24 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 16 | 16 | 4 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056327 | No | No | Yes | Australia | Australia | 03-Design/Build | DEV FUT-Baseline(D/B) | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 80.5h | 0h | 80.5h | 2017-04-17 | 2017-06-16 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 5 | 11 | 19 | 5 | 4 | 3.5 | 3 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056328 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 48h | 0h | 48h | 2017-05-15 | 2017-06-09 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 24 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056329 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - PTM | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 10h | 0h | 10h | 2017-05-08 | 2017-05-26 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056330 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Prepare - PTM | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056331 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - PTM | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 40h | 0h | 40h | 2017-06-19 | 2017-06-30 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056332 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - PTM | PTM | FUN | Saputo | Onshore | Anderson; John | Saputo | Yes | CapEx | Localization | IT - Internal | 179h | 0h | 179h | 2017-07-03 | 2017-08-11 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 42 | 48 | 0 | 31 | 16 | 0 | 0 | 0 | 0 | 0 | 0
1056333 | No | Yes | No | Australia | Australia | 02-Analyze | Kickoff (AN) | MDG | To Define | SI | Onshore | Manlapaz; Carmel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  | ACT.MDG.Workshop | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056334 | No | Yes | No | Australia | Australia | 02-Analyze | Data Construction and staging (AN) | MDG | To Define | SI | Onshore | Manlapaz; Carmel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  | ACT.MDG.Data Construction | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056335 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - PTM | PTM | FUN | Saputo | Onshore | Atkins; Aaon | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056336 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix - PTM | PTM | FUN | Saputo | Onshore | Atkins; Aaon | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-04 | 2017-07-04 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056337 | No | No | Yes | Australia | Australia | 03-Design/Build | IOTC008-DEV FUT-ECC/GTS to BSM Order | PTM | FUN | Saputo | Onshore | Atkins; Aaon | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056338 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG008-DEV FUT-ECC to BSM Delivery | PTM | FUN | Saputo | Onshore | Atkins; Aaon | Saputo | Yes | CapEx | Localization | IT - Internal | 2h | 0h | 2h | 2017-04-05 | 2017-04-07 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056339 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - LOG | PTM | FUN | Saputo | Onshore | Atkins; Aaon | Saputo | Yes | CapEx | Localization | IT - Internal | 51h | 0h | 51h | 2017-07-24 | 2017-07-28 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056340 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | PTM | FUN | Saputo | Onshore | Atkins; Aaon | Saputo | Yes | CapEx | Localization | IT - Internal | 51h | 0h | 51h | 2017-04-25 | 2017-05-05 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056341 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - PTM | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 288h | 0h | 288h | 2017-07-03 | 2017-08-04 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 84 | 75 | 54 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056342 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix - PTM | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-04 | 2017-07-04 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056343 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Prepare - PTM | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-06-26 | 2017-06-30 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056344 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - PTM | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-06-19 | 2017-06-23 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056345 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Validate | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056346 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - PTM | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-06-12 | 2017-06-23 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056347 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Prep | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-05-29 | 2017-06-02 | Yes |  |  | ACT.FUN.UAT Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056348 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - PTM | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-06-26 | 2017-06-30 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056349 | No | No | Yes | Australia | Australia | 03-Design/Build | DEV FUT-Baseline(D/B) | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-01-14 | 2017-06-09 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056350 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 46h | 0h | 46h | 2017-04-24 | 2017-05-12 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056351 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - PTM | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-05-15 | 2017-05-19 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056352 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Break/Fix - PTM | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-04-24 | 2017-05-19 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056353 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-06-12 | 2017-06-16 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056354 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - PTM | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 30h | 0h | 30h | 2017-05-22 | 2017-06-09 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056355 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - PTM | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-05-22 | 2017-05-26 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056356 | No | No | Yes | Australia | Australia | 04-Test | Regression - Manage defects (Capex) - PTM | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-05-15 | 2017-06-02 | Yes |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056357 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - PTM | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-05-15 | 2017-06-02 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056358 | No | No | Yes | Australia | Australia | 04-Test | WPB recording (PTM) | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | OpEx | Localization | IT - External | 30h | 0h | 30h | 2017-05-08 | 2017-05-12 | Yes |  |  | DELIV.FUN-403.WPB Recordings | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056359 | No | No | Yes | Australia | Australia | 04-Test | Management (Test) - PTM | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 19h | 0h | 19h | 2017-05-08 | 2017-06-16 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056360 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia - (Capex) - (D/B) | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056361 | No | No | Yes | Australia | Australia | 03-Design/Build | EPTM018-FSD-Chemical analysis machines | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 126h | 0h | 126h | 2017-03-20 | 2017-04-21 | Yes |  |  | DELIV.FUN-203.Functional Specification - Enhancement | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 16 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056362 | No | No | Yes | Australia | Australia | 03-Design/Build | EPTM018-DEV FUT-Chemical analysis machines | PTM | FUN | SI | Offshore | Kumbhare; Vaibhav | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-04-03 | 2017-04-28 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056363 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056364 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - LOG | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | CapEx | Localization | IT - Internal | 94h | 0h | 94h | 2017-07-03 | 2017-07-21 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 42 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056365 | No | No | Yes | Australia | Australia | 06-Hypercare | Manage Defects - LOG | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | CapEx | Localization | IT - Internal | 61h | 0h | 61h | 2017-07-17 | 2017-08-04 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 17.5 | 34.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056366 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix - LOG | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | CapEx | Localization | IT - Internal | 54h | 0h | 54h | 2017-07-03 | 2017-07-21 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 14 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056367 | No | No | Yes | Australia | Australia | 04-Test | Regression - Run Tests - LOG | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056368 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG006-FSD-EDI 3PL Pick Request | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | CapEx | Localization | IT - Internal | 56h | 0h | 56h | 2017-01-16 | 2017-01-26 | Yes |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 20 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056369 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG011-FSD-Lot Status Message to 3PL | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | CapEx | Localization | IT - Internal | 10h | 0h | 10h | 2017-01-16 | 2017-01-20 | Yes |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056370 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG007-FSD-IEDI 3PL ASN | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056371 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG010-FSD-Pick Confirmation to 3PL | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | CapEx | Localization | IT - Internal | 10h | 0h | 10h | 2017-03-27 | 2017-03-31 | Yes |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056372 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | LOG | FUN | Saputo | Onshore | Ramkahlawan; Peter | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056373 | No | No | No | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  | DMS | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056374 | No | No | No | Australia | Australia | 06-Hypercare | DMS HyperCare support-Break Fix - RTR | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  | DMS | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056375 | No | No | No | Australia | Australia | 03-Design/Build | Contribute to Cut-over Planning (D/B) - RTR | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-22 | 2016-11-22 | Yes |  | DMS | ACT.FUN.Support Cutover plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056376 | No | No | No | Australia | Australia | 04-Test | DMS SIT AUS - Break Fix - RTR | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-18 | 2017-04-18 | Yes |  | DMS | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056377 | No | No | No | Australia | Australia | 03-Design/Build | Support MDM (D/B) | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-03 | 2016-12-03 | Yes |  | DMS | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056378 | No | No | No | Australia | Australia | 03-Design/Build | CONFIG FUT-Baseline (D/B) | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-13 | 2016-12-13 | Yes |  | DMS | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056379 | No | No | No | Australia | Australia | 03-Design/Build | SDD Writing | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  | DMS | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056380 | No | No | No | Australia | Australia | 03-Design/Build | CONFIG-Baseline (D/B) | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  | DMS | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056381 | No | No | No | Australia | Australia | 03-Design/Build | DEV FUT- Baseline (D/B) | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  | DMS | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056382 | No | No | No | Australia | Australia | 03-Design/Build | FSD-Baseline (D/B) | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  | DMS | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056383 | No | No | No | Australia | Australia | 03-Design/Build | Support to Developpers (D/B) | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  | DMS | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056384 | No | No | No | Australia | Australia | 03-Design/Build | DDD-Baseline (D/B) | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | Yes |  | DMS | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056385 | No | No | No | Australia | Australia | 03-Design/Build | PDD-Baseline (D/B) | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  | DMS | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056386 | No | No | No | Australia | Australia | 02-Analyze | Old - Perform Gap Resolution (AN) | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-21 | 2016-11-21 | Yes |  | DMS | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056387 | No | No | No | Australia | Australia | 03-Design/Build | DMS_03-CONFIG-Dairy Mgmt System - Operations | RTR | FUN | SI | Onshore | Khatchikian; Grigor | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  | DMS | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056388 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Support | TAI | TAI | SI | Offshore | Lledo; Philip | Accenture | Yes | CapEx | Localization | IT - External | 99h | 0h | 99h | 2017-06-19 | 2017-07-03 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056389 | No | No | Yes | Australia | Australia | 06-Hypercare | Hypercare - Support - TAI | TAI | TAI | SI | Offshore | Lledo; Philip | Accenture | Yes | CapEx | Localization | IT - External | 225h | 0h | 225h | 2017-07-03 | 2017-08-04 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056390 | No | No | Yes | Australia | Australia | 02-Analyze | Data Construction and staging - DC (AN) | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 545h | 0h | 545h | 2016-10-24 | 2017-05-19 | Yes |  |  | ACT.MDG.Data Construction | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 8 | 12 | 0 | 0 | 10 | 6 | 10 | 15 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056391 | No | No | Yes | Australia | Australia | 02-Analyze | Kickoff - DC (AN) | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 21h | 0h | 21h | 2016-10-24 | 2016-12-02 | Yes |  |  | ACT.MDG.Workshop | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056392 | No | No | Yes | Australia | Australia | 01-Preparation | Data Profiling (Saputo) - DC) (PP) | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | OpEx | Localization | IT - Internal | 16h | 0h | 16h | 2016-10-03 | 2017-03-10 | Yes |  |  | DELIV.MDG-050.Data Profiling | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056393 | No | No | Yes | Australia | Australia | 04-Test | Mock1 – Manage defect (Capex) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 111h | 0h | 111h | 2017-04-17 | 2017-05-29 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 37 | 40 | 9 | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056394 | No | No | Yes | Australia | Australia | 04-Test | Data collection templates - explain and collect - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 280h | 0h | 280h | 2016-12-19 | 2017-03-17 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 28 | 40 | 40 | 30 | 34 | 30 | 25 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056395 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Prepare - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | OpEx | Localization | IT - Internal | 55h | 0h | 55h | 2017-06-05 | 2017-07-02 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056396 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Support - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | OpEx | Localization | IT - Internal | 120h | 0h | 120h | 2017-06-12 | 2017-06-30 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 22 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056397 | No | No | Yes | Australia | Australia | 04-Test | Data load - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 345h | 0h | 345h | 2017-03-20 | 2017-05-29 | Yes |  |  | ACT.MDG.Mock Load | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 70 | 76 | 58 | 30 | 0 | 0 | 0 | 0 | 62 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056398 | No | No | Yes | Australia | Australia | 06-Hypercare | HC - Manage defects - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 31h | 0h | 31h | 2017-07-03 | 2017-07-07 | Yes |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056399 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect (Capex) - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | CapEx | Localization | IT - Internal | 27h | 0h | 27h | 2017-06-13 | 2017-06-28 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056400 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Validate - DC | MDG | DC | Saputo | Onshore | Quintero; Juan | Saputo | Yes | OpEx | Localization | IT - Internal | 60h | 0h | 60h | 2017-06-19 | 2017-07-01 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056401 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix - OTC | OTC | FUN | SI | Onshore | Nieva; Ricardo | Accenture | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2017-07-24 | 2017-07-31 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056402 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - OTC | OTC | FUN | SI | Onshore | Nieva; Ricardo | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056403 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - OTC | OTC | FUN | SI | Onshore | Nieva; Ricardo | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056404 | No | No | Yes | Australia | Australia | 04-Test | Regression - Run Tests - OTC | OTC | FUN | SI | Onshore | Nieva; Ricardo | Accenture | Yes | CapEx | Localization | IT - External | 60h | 0h | 60h | 2017-05-15 | 2017-06-01 | Yes |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056405 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia(D/B) | OTC | FUN | SI | Onshore | Nieva; Ricardo | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056406 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | PTP | FUN | SI | Onshore | Smith; Adam | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-02-20 | 2017-02-24 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056407 | No | No | Yes | Australia | Australia | 03-Design/Build | PDD-Execute Milk Supplier Portal | PTP | FUN | SI | Onshore | Smith; Adam | IBM | Yes | CapEx | Localization | IT - External | 46h | 0h | 46h | 2017-02-06 | 2017-03-03 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056408 | No | No | Yes | Australia | Australia | 03-Design/Build | PDD-Manage Milk Receiving Cockpit | PTP | FUN | SI | Onshore | Smith; Adam | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2017-02-06 | 2017-03-06 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 44 | 0 | 22 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056409 | No | No | Yes | Australia | Australia | 04-Test | Data load - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | CapEx | Localization | IT - External | 156h | 0h | 156h | 2017-03-20 | 2017-04-07 | Yes |  |  | ACT.MDG.Mock Load | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 54 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056410 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Validate - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | OpEx | Localization | IT - External | 45h | 0h | 45h | 2017-04-17 | 2017-04-21 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056411 | No | No | Yes | Australia | Australia | 04-Test | Mock1 – Manage defect (Capex) - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-04-28 | 2017-05-05 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056412 | No | No | Yes | Australia | Australia | 02-Analyze | Kickoff - DC (AN) | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-03-13 | 2017-03-16 | Yes |  |  | ACT.MDG.Workshop | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056413 | No | No | Yes | Australia | Australia | 02-Analyze | Data Construction and staging - DC (AN) | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | CapEx | Localization | IT - External | 48h | 0h | 48h | 2017-02-27 | 2017-03-03 | Yes |  |  | ACT.MDG.Data Construction | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056414 | No | No | Yes | Australia | Australia | 04-Test | Data collection templates - explain and collect - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | CapEx | Localization | IT - External | 162h | 0h | 162h | 2017-02-13 | 2017-03-13 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056415 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Validate - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | OpEx | Localization | IT - External | 99h | 0h | 99h | 2017-06-19 | 2017-06-30 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056416 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect (Capex) - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-30 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056417 | No | No | Yes | Australia | Australia | 06-Hypercare | HC - Manage defects - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | CapEx | Localization | IT - External | 180h | 0h | 180h | 2017-07-03 | 2017-07-28 | Yes |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056418 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2017-04-24 | 2017-04-27 | Yes |  |  | ACT.MDG.Mock Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056419 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056420 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Prepare - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | OpEx | Localization | IT - External | 54h | 0h | 54h | 2017-06-05 | 2017-06-11 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056421 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Execute - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | CapEx | Localization | IT - External | 145h | 0h | 145h | 2017-05-08 | 2017-05-28 | Yes |  |  | ACT.MDG.Mock Load | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 45 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056422 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Support - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | OpEx | Localization | IT - External | 58h | 0h | 58h | 2017-06-12 | 2017-06-16 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056423 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect - DC | MDG | DC | SI | Offshore | Quimpo; Leah | Accenture | Yes | CapEx | Localization | IT - External | 86h | 0h | 86h | 2017-04-10 | 2017-06-02 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056424 | No | No | Yes | Australia | Australia | 03-Design/Build | FLOG019-DEV FUT-BOL + AQIS number | LOG | FUN | SI | Onshore | Steve; Leslie | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-21 | 2017-03-21 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056425 | No | No | Yes | Australia | Australia | 03-Design/Build | XXX-DEV FUT-Master BOL | LOG | FUN | SI | Onshore | Steve; Leslie | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056426 | No | No | Yes | Australia | Australia | 03-Design/Build | FLOG020-DEV FUT-Packing List | LOG | FUN | SI | Onshore | Steve; Leslie | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056427 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Create BPML (AN) | LOG | FUN | SI | Onshore | Steve; Leslie | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-20 | 2017-01-20 | Yes |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056428 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Log Gaps (AN) | LOG | FUN | SI | Onshore | Steve; Leslie | IBM | Yes | CapEx | Localization | IT - External | 147h | 0h | 147h | 2016-11-10 | 2016-12-16 | Yes |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056429 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - LOG | LOG | FUN | SI | Onshore | Steve; Leslie | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2017-06-05 | 2017-06-16 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056430 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Management (Cutover/Go-live) | LOG | FUN | SI | Onshore | Steve; Leslie | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-06-26 | 2017-06-30 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056431 | No | No | Yes | Australia | Australia | 06-Hypercare | Management (Hypercare) - LOG | LOG | FUN | SI | Onshore | Steve; Leslie | IBM | Yes | CapEx | Localization | IT - External | 170h | 0h | 170h | 2017-07-03 | 2017-07-23 | Yes |  |  | ACT.DEV.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 62 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056432 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) | LOG | FUN | SI | Onshore | Steve; Leslie | IBM | Yes | CapEx | Localization | IT - External | 232h | 0h | 232h | 2016-10-24 | 2017-01-13 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056433 | No | No | Yes | Australia | Australia | 04-Test | Management (Test) - LOG | LOG | FUN | SI | Onshore | Steve; Leslie | IBM | Yes | CapEx | Localization | IT - External | 256h | 0h | 256h | 2017-04-24 | 2017-06-04 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 36 | 44 | 44 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056434 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | LOG | FUN | SI | Onshore | Steve; Leslie | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-01-30 | 2017-02-02 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056435 | No | No | Yes | Australia | Australia | 03-Design/Build | Management (D/B) | LOG | FUN | SI | Onshore | Steve; Leslie | IBM | Yes | CapEx | Localization | IT - External | 440h | 0h | 440h | 2017-02-06 | 2017-04-21 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 0 | 44 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056436 | No | No | Yes | Australia | Australia | 01-Preparation | Prepare KT) (PP) | LOG | FUN | SI | Onshore | Steve; Leslie | IBM | Yes | CapEx | Localization | IT - External | 113h | 0h | 113h | 2016-10-03 | 2016-10-21 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056437 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD250-Dynamic Modification Rules | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056438 | No | No | Yes | Australia | Australia | 03-Design/Build | Workshops - PTM - QM (Quality Management) | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 100h | 0h | 100h | 2017-03-27 | 2017-04-28 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 18 | 21 | 18 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056439 | No | No | Yes | Australia | Australia | 03-Design/Build | XXX-FSD-Tabular results ( including 6506 ) | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 83h | 0h | 83h | 2017-02-27 | 2017-04-21 | Yes |  |  | DELIV.FUN-203.Functional Specification - Enhancement | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 18 | 0 | 21 | 6 | 7 | 7 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056440 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix - PTM | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 158h | 0h | 158h | 2017-07-04 | 2017-08-11 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 35 | 44 | 38 | 0 | 0 | 0 | 0 | 0 | 0
1056441 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - PTM | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 29h | 0h | 29h | 2017-05-29 | 2017-06-09 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056442 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - PTM | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2017-05-29 | 2017-06-23 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 14 | 33 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056443 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056444 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Create BPML (AN) | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2016-11-03 | 2016-12-07 | Yes |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056445 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Log Gaps (AN) | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-11-01 | 2016-11-10 | Yes |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056446 | No | No | Yes | Australia | Australia | 01-Preparation | Prepare KT) (PP) | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | OpEx | Localization | IT - External | 13h | 0h | 13h | 2016-10-24 | 2016-10-26 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056447 | No | No | Yes | Australia | Australia | 01-Preparation | Conduct KT sessions) (PP) | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | OpEx | Localization | IT - External | 2h | 0h | 2h | 2016-10-31 | 2016-11-02 | Yes |  |  | WP.FUN.Requirements/Process Design Workshop Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056448 | No | No | Yes | Australia | Australia | 02-Analyze | RTM (AN) | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 29h | 0h | 29h | 2016-10-26 | 2017-01-20 | Yes |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 8 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056449 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 31h | 0h | 31h | 2016-10-31 | 2016-12-20 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056450 | No | No | Yes | Australia | Australia | 01-Preparation | Worshop Preparation Decks) (PP) | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2016-10-12 | 2016-10-28 | Yes |  |  | WP.FUN-107.Workshop Preparation Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056451 | No | No | Yes | Australia | Australia | 03-Design/Build | XXX-DEV FUT-Tabular results ( including 6506 ) | PTM | FUN | SI | Onshore | Iancu; Nora | IBM | Yes | CapEx | Localization | IT - External | 3h | 0h | 3h | 2017-06-06 | 2017-06-09 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056452 | No | Yes | No | Australia | Australia |  | Team Lead - Cutover planners | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | CapEx | Localization | IT - Internal | 433h | 0h | 433h | 2017-04-17 | 2017-07-02 | Yes |  |  | ACT.PMO.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 90 | 48 | 12 | 19 | 21 | 16 | 53 | 42 | 56 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056453 | No | Yes | No | Australia | Australia | 03-Design/Build | Cutover Planning | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | OpEx | Localization | IT - Internal | 289h | 0h | 289h | 2017-02-27 | 2017-04-17 | Yes |  |  | ACT.PMO.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 11 | 54 | 58 | 47 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056454 | No | Yes | No | Australia | Australia | 03-Design/Build | Hypercare Planning | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | OpEx | Localization | IT - Internal | 21h | 0h | 21h | 2017-03-20 | 2017-04-13 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 12 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056455 | No | Yes | No | Australia | Australia | 04-Test | Cut Over Prepare | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056456 | No | Yes | No | Australia | Australia | 04-Test | Failure Mode Effect Analysis | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-21 | 2017-04-21 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056457 | No | Yes | No | Australia | Australia | 04-Test | Hypercare Planning | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056458 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Cutover Execution | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056459 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Failure Mode Effect Analysis | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | OpEx | Localization | IT - Internal | 7h | 0h | 7h | 2017-06-05 | 2017-06-09 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056460 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Hypercare Prep | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056461 | No | Yes | No | Australia | Australia | 06-Hypercare | Hypercare Execution | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056462 | No | Yes | No | Australia | Australia | 06-Hypercare | Failure Mode Effect Analysis | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056463 | No | Yes | No | Australia | Australia | 03-Design/Build | Business Risk Assessment | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | OpEx | Localization | IT - Internal | 15h | 0h | 15h | 2017-03-21 | 2017-04-10 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056464 | No | Yes | No | Australia | Australia | 03-Design/Build | Value Realization Plan (D/B) | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | OpEx | Localization | IT - Internal | 1h | 0h | 1h | 2017-03-20 | 2017-03-20 | Yes |  |  | DELIV.CM-210.Value Realization Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056465 | No | Yes | No | Australia | Australia | 03-Design/Build | Failure Mode Effect Analysis (D/B) | CM | CM | Saputo | Onshore | Lemay; Johane | Saputo | Yes | OpEx | Localization | IT - Internal | 18h | 0h | 18h | 2017-03-22 | 2017-04-10 | Yes |  |  | DELIV.CM-301.Failure Mode Effect Analysis (FMEA) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056466 | No | Yes | No | Australia | Australia | 03-Design/Build | Transition to Australia - (Capex) - (D/B) | PTM | FUN | SI | Onshore | Arce; Hugo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056467 | No | No | Yes | Australia | Australia |  | AUS - DEV KT | DEV | DEV | SI | Offshore | Bhat; Lavleen | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-31 | 2017-05-31 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056468 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Support | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | OpEx | Localization | IT - External | 6h | 0h | 6h | 2017-04-26 | 2017-04-26 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056469 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 68h | 0h | 68h | 2016-11-07 | 2016-11-25 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056470 | No | No | Yes | Australia | Australia | 02-Analyze | RTM (AN) | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-04 | 2016-11-04 | Yes |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056471 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Validate | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | OpEx | Localization | IT - External | 5h | 0h | 5h | 2017-04-26 | 2017-04-26 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056472 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Perform Gap Resolution (AN) | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 42h | 0h | 42h | 2016-12-05 | 2017-01-13 | Yes |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056473 | No | No | Yes | Australia | Australia | 03-Design/Build | PDD-Baseline (D/B) | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056474 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct Design Workshops (AN) | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-22 | 2016-11-22 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056475 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Log Gaps (AN) | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 43h | 0h | 43h | 2016-11-14 | 2016-11-18 | Yes |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056476 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Create BPML (AN) | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056477 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-Baseline (D/B) | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056478 | No | No | Yes | Australia | Australia | 03-Design/Build | FSD-Baseline (D/B) | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056479 | No | No | Yes | Australia | Australia | 03-Design/Build | Support to Developpers (D/B) | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056480 | No | No | Yes | Australia | Australia | 03-Design/Build | DEV FUT- Baseline (D/B) | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056481 | No | No | Yes | Australia | Australia | 03-Design/Build | CONFIG-Baseline (D/B) | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056482 | No | No | Yes | Australia | Australia | 03-Design/Build | SDD Writing | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056483 | No | No | Yes | Australia | Australia | 03-Design/Build | Support MDM (D/B) | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-03 | 2016-12-03 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056484 | No | No | Yes | Australia | Australia | 03-Design/Build | CONFIG FUT-Baseline (D/B) | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-13 | 2016-12-13 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056485 | No | No | Yes | Australia | Australia | 03-Design/Build | Contribute to Cut-over Planning (D/B) - RTR | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2016-11-22 | 2017-05-26 | Yes |  |  | ACT.FUN.Support Cutover plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056486 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - RTR | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 35h | 0h | 35h | 2017-06-26 | 2017-07-07 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056487 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Prepare - RTR | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2017-05-29 | 2017-06-23 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056488 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - RTR | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2017-05-23 | 2017-05-26 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056489 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - RTR | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 54h | 0h | 54h | 2017-06-05 | 2017-06-16 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056490 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - RTR | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2017-05-29 | 2017-05-30 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056491 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - RTR | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 86h | 0h | 86h | 2017-06-05 | 2017-06-21 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 26 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056492 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Manage Defects (Capex) | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 53h | 0h | 53h | 2017-05-01 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056493 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Manage Defects (Capex) | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 34h | 0h | 34h | 2017-05-23 | 2017-06-01 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056494 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Break/Fix - RTR | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 62h | 0h | 62h | 2017-04-28 | 2017-05-19 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 16 | 18 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056495 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - RTR | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 52h | 0h | 52h | 2017-05-16 | 2017-05-26 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056496 | No | No | Yes | Australia | Australia | 04-Test | Regression - Manage defects (Capex) - RTR | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056497 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056498 | No | No | Yes | Australia | Australia | 03-Design/Build | Workaround Procedures (D/B) | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-02-13 | 2017-02-17 | Yes |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056499 | No | No | Yes | Australia | Australia | 03-Design/Build | Reviewing AUS Configuration | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | OpEx | Localization | IT - External | 19h | 0h | 19h | 2017-04-17 | 2017-04-20 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056500 | No | No | Yes | Australia | Australia | 03-Design/Build | Reviewing AUS Design (D/B) | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 81h | 0h | 81h | 2017-03-22 | 2017-04-06 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 45 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056501 | No | No | Yes | Australia | Australia | 01-Preparation | Prepare Kick-off) (PP) | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-03 | 2016-10-03 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056502 | No | No | Yes | Australia | Australia | 01-Preparation | Worshop Preparation Decks) (PP) | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-03 | 2016-10-03 | Yes |  |  | WP.FUN-107.Workshop Preparation Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056503 | No | No | Yes | Australia | Australia | 01-Preparation | Prepare KT) (PP) | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056504 | No | No | Yes | Australia | Australia | 01-Preparation | Conduct KT sessions) (PP) | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-29 | 2016-10-29 | Yes |  |  | WP.FUN.Requirements/Process Design Workshop Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056505 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - RTR | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 138h | 0h | 138h | 2017-06-26 | 2017-08-30 | Yes |  |  | ACT.FUN.Functional Break/Fix | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 23 | 46 | 18 | 13 | 4 | 2 | 1 | 0 | 4 | 0 | 0 | 0
1056506 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix (Hypercare) - RTR | RTR | FUN | SI | Onshore | McHugh; Murray | IBM | Yes | CapEx | Localization | IT - External | 66h | 0h | 66h | 2017-07-19 | 2017-08-17 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 14 | 12 | 18 | 15 | 0 | 0 | 0 | 0 | 0
1056507 | No | Yes | No | Australia | Australia | 04-Test | Training Materials-Work Instructions/Job aids (Test) | CM | CM | SI | Offshore | Kundu; Lakshmi | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  | DELIV.CM-451.Work Instructions | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056508 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Development (Cutover/Go-live) - DEV | DEV | DEV | SI | Offshore | Revil; Dianne | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-02 | 2017-06-02 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056509 | No | No | Yes | Australia | Australia | 03-Design/Build | Development MDG (D/B) | DEV | DEV | SI | Offshore | Revil; Dianne | Accenture | Yes | CapEx | Localization | IT - External | 131h | 0h | 131h | 2017-04-03 | 2017-05-12 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 27 | 45 | 5 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056510 | No | No | Yes | Australia | Australia |  | AUS - DEV KT | DEV | DEV | SI | Offshore | Revil; Dianne | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-31 | 2017-05-31 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056511 | No | No | Yes | Australia | Australia | 06-Hypercare | HC - Break/Fix - Dev | DEV | DEV | SI | Offshore | Revil; Dianne | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-04 | 2017-07-04 | Yes |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056512 | No | Yes | No | Australia | Australia |  | Manage Project | PMO | PMO | SI | Onshore | Imaogene; Bugie | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2016-09-26 | 2016-11-18 | Yes |  |  | ACT.PMO.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056513 | No | No | Yes | Australia | Australia | 06-Hypercare | Hypercare | SEC | SEC | SI | Onshore | Vanderveer; Monina | Accenture | Yes | CapEx | Localization | IT - External | 120h | 0h | 120h | 2017-07-10 | 2017-08-18 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 40 | 0 | 0 | 0 | 0 | 0
1056514 | No | No | Yes | Australia | Australia | 04-Test | Management (Test) - PTM | PTM | FUN | Saputo | Onshore | Pavlovski; Victor | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-03-14 | 2017-03-14 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056515 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Management (Cutover/Go-live) - PTM | PTM | FUN | Saputo | Onshore | Pavlovski; Victor | Saputo | Yes | CapEx | Localization | Business | 3h | 0h | 3h | 2017-06-26 | 2017-06-29 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056516 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia - (Capex) - (D/B) | PTM | FUN | Saputo | Onshore | Pavlovski; Victor | Saputo | Yes | CapEx | Localization | Business | 113h | 0h | 113h | 2017-01-16 | 2017-04-27 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 28 | 24 | 0 | 0 | 19 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056517 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | PTM | FUN | Saputo | Onshore | Pavlovski; Victor | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056518 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - PTM | PTM | FUN | Saputo | Onshore | Pavlovski; Victor | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056519 | No | No | Yes | Australia | Australia | 04-Test | Regression - Run Tests - PTM | PTM | FUN | Saputo | Onshore | Pavlovski; Victor | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056520 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - PTM | PTM | FUN | Saputo | Onshore | Pavlovski; Victor | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056521 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate | PTM | FUN | Saputo | Onshore | Pavlovski; Victor | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056522 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - PTM | PTM | FUN | Saputo | Onshore | Pavlovski; Victor | Saputo | Yes | CapEx | Localization | Business | 72h | 0h | 72h | 2017-06-05 | 2017-06-16 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056523 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - PTM | PTM | FUN | Saputo | Onshore | Pavlovski; Victor | Saputo | Yes | CapEx | Localization | Business | 40h | 0h | 40h | 2017-06-26 | 2017-08-03 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056524 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - PTM | PTM | FUN | Saputo | Onshore | Pavlovski; Victor | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056525 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia - (Capex) - (D/B) | PTM | FUN | SI | Onshore | Laferrara; Melisa | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056526 | No | Yes | No | Australia | Australia | 03-Design/Build | Transition to Australia - (Capex) - (D/B) | PTM | FUN | SI | Onshore | Dirndorfer; Johann | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  | DMS | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056527 | No | No | Yes | Australia | Australia | 06-Hypercare | Communication plan execution and monitoring (HYP) | CM | CM | Saputo | Onshore | Goldstein; Evan | Saputo | Yes | OpEx | Localization | IT - Internal | 95h | 3h | 98h | 2017-07-03 | 2017-09-22 | Yes |  |  | ACT.CM.Communication plan execution and monitoring | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 20 | 15 | 5 | 5 | 10 | 5 | 5 | 0 | 14 | 0
1056528 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Communication Plan (C/G) | CM | CM | Saputo | Onshore | Goldstein; Evan | Saputo | Yes | OpEx | Localization | IT - Internal | 81.02h | 0h | 81.02h | 2017-06-07 | 2017-06-29 | Yes |  |  | DELIV.CM-106.Communication Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.02 | 25 | 14 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056529 | No | No | Yes | Australia | Australia | 04-Test | Communication Plan (Test) | CM | CM | Saputo | Onshore | Goldstein; Evan | Saputo | Yes | OpEx | Localization | IT - Internal | 50h | 0h | 50h | 2017-05-15 | 2017-06-02 | Yes |  |  | DELIV.CM-106.Communication Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 16 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056530 | No | No | Yes | Australia | Australia | 03-Design/Build | Communication Plan (D/B) | CM | CM | Saputo | Onshore | Goldstein; Evan | Saputo | Yes | OpEx | Localization | IT - Internal | 60h | 0h | 60h | 2017-03-20 | 2017-04-21 | Yes |  |  | DELIV.CM-106.Communication Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 10 | 0 | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056531 | No | No | Yes | Australia | Australia | 02-Analyze | Communication Plan (AN) | CM | CM | Saputo | Onshore | Goldstein; Evan | Saputo | Yes | OpEx | Localization | IT - Internal | 223.25h | 0h | 223.25h | 2016-11-07 | 2017-03-17 | Yes |  |  | DELIV.CM-106.Communication Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 3 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 35 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056532 | No | No | Yes | Australia | Australia | 02-Analyze | Change Agents Network (AN) | CM | CM | Saputo | Onshore | Goldstein; Evan | Saputo | Yes | OpEx | Localization | IT - Internal | 43.5h | 0h | 43.5h | 2016-11-07 | 2016-12-16 | Yes |  |  | DELIV.CM-124.Change Agents Network | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056533 | No | No | Yes | Australia | Australia | 06-Hypercare | HC - Break/Fix - Dev | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | CapEx | Localization | IT - Internal | 16h | 0h | 16h | 2017-07-10 | 2017-08-03 | Yes |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056534 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT1) | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | CapEx | Localization | IT - Internal | 52h | 0h | 52h | 2017-05-01 | 2017-05-19 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 11 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056535 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Development (Cutover/Go-live) - DEV | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | CapEx | Localization | IT - Internal | 32h | 0h | 32h | 2017-06-05 | 2017-06-29 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 8 | 4 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056536 | No | No | Yes | Australia | Australia |  | AUS - DEV KT | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-05-31 | 2017-05-31 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056537 | No | No | Yes | Australia | Australia | 03-Design/Build | Development (D/B) | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | CapEx | Localization | IT - Internal | 136h | 0h | 136h | 2017-03-13 | 2017-04-21 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 25 | 20 | 25 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056538 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT2) | DEV | DEV | Saputo | Onshore | Ramappa; Yeshwanth | Saputo | Yes | CapEx | Localization | IT - Internal | 28h | 0h | 28h | 2017-05-23 | 2017-06-09 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056539 | No | Yes | No | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | PTP | FUN | SI | Onshore | Vergara; Roberto | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056540 | No | Yes | No | Australia | Australia | 02-Analyze | Communication Plan (AN) | CM | CM | SI | Onshore | Fernandez; Ruth | IBM | Yes | OpEx | Localization | IT - External | 45h | 0h | 45h | 2016-11-21 | 2016-12-09 | Yes |  |  | DELIV.CM-106.Communication Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056541 | No | Yes | No | Australia | Australia | 02-Analyze | Communication plan(AN) | CM | CM | SI | Onshore | Fernandez; Ruth | IBM | Yes | OpEx | Localization | IT - External | 47h | 0h | 47h | 2016-11-21 | 2016-12-16 | Yes |  |  | DELIV.CM-106.Communication Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056542 | No | No | Yes | Australia | Australia |  | Australia | PMO | PMO | Saputo | Onshore | Steringa; Dan | Saputo | Yes |  |  | Business | 0h | 0h | 0h | 2016-07-06 | 2016-07-06 | Yes |  |  |  |  | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056543 | No | Yes | No | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | CDP | CDP | SI | Onshore | Bahloul; Nassim | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056544 | No | Yes | No | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | CDP | CDP | SI | Onshore | McLaren; Leanne | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056545 | No | No | Yes | Australia | Australia | 04-Test | MDM Project Management (Test) - MDG-DC | MDG | DC | SI | Onshore | Masri; Remi | Accenture | Yes | CapEx | Localization | IT - External | 267h | 0h | 267h | 2017-04-17 | 2017-06-02 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 45 | 40 | 35 | 32 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056546 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Manage Defect (Capex) | MDG | DC | SI | Onshore | Masri; Remi | Accenture | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-05-13 | 2017-06-15 | Yes |  |  | ACT.MDG.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 5 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056547 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Defect Fix - DC | MDG | DC | SI | Onshore | Masri; Remi | Accenture | Yes | CapEx | Localization | IT - External | 13h | 0h | 13h | 2017-05-31 | 2017-06-15 | Yes |  |  | ACT.MDG.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056548 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Support - DC | MDG | DC | SI | Onshore | Masri; Remi | Accenture | Yes | OpEx | Localization | IT - External | 20h | 0h | 20h | 2017-06-12 | 2017-06-14 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056549 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Prepare - DC | MDG | DC | SI | Onshore | Masri; Remi | Accenture | Yes | OpEx | Localization | IT - External | 40h | 0h | 40h | 2017-06-05 | 2017-06-09 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056550 | No | No | Yes | Australia | Australia | 03-Design/Build | MDM Project Management (D/B) - DC | MDG | DC | SI | Onshore | Masri; Remi | Accenture | Yes | CapEx | Localization | IT - External | 272h | 0h | 272h | 2017-01-23 | 2017-04-13 | Yes |  |  | ACT.MDG.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056551 | No | No | Yes | Australia | Australia | 06-Hypercare | HC - Manage defects - DC | MDG | DC | SI | Onshore | Masri; Remi | Accenture | Yes | CapEx | Localization | IT - External | 48h | 0h | 48h | 2017-07-03 | 2017-07-07 | Yes |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056552 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect (Capex) - DC | MDG | DC | SI | Onshore | Masri; Remi | Accenture | Yes | CapEx | Localization | IT - External | 71h | 0h | 71h | 2017-06-26 | 2017-07-03 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056553 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Validate - DC | MDG | DC | SI | Onshore | Masri; Remi | Accenture | Yes | OpEx | Localization | IT - External | 32h | 0h | 32h | 2017-06-16 | 2017-06-21 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056554 | No | No | Yes | Australia | Australia |  | MDM Project Management (Saputo) - DC | MDG | DC | SI | Onshore | Masri; Remi | Accenture | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2017-07-14 | 2017-07-28 | Yes |  |  | ACT.MDG.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056555 | No | Yes | Yes | Australia | Australia | 06-Hypercare | Hypercare - Support - TAI | TAI | TAI | Saputo | Onshore | Patel; Rupesh | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056556 | No | Yes | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Support | TAI | TAI | Saputo | Onshore | Patel; Rupesh | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056557 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) | RTR | FUN | Saputo | Onshore | Ethier; Patrice | Saputo | Yes | CapEx | Localization | IT - Internal | 3h | 0h | 3h | 2016-11-14 | 2016-12-22 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056558 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Management (Cutover/Go-live) | RTR | FUN | Saputo | Onshore | Ethier; Patrice | Saputo | Yes | CapEx | Localization | IT - Internal | 75h | 0h | 75h | 2017-06-05 | 2017-06-29 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 20 | 8 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056559 | No | No | Yes | Australia | Australia | 06-Hypercare | Management (Hypercare) - RTR | RTR | FUN | Saputo | Onshore | Ethier; Patrice | Saputo | Yes | CapEx | Localization | IT - Internal | 180h | 0h | 180h | 2017-07-03 | 2017-08-18 | Yes |  |  | ACT.DEV.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 20 | 25 | 20 | 15 | 20 | 0 | 0 | 0 | 0 | 0
1056560 | No | No | Yes | Australia | Australia | 03-Design/Build | Management (D/B) - RTR | RTR | FUN | Saputo | Onshore | Ethier; Patrice | Saputo | Yes | CapEx | Localization | IT - Internal | 68h | 0h | 68h | 2017-02-27 | 2017-04-18 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 10 | 5 | 10 | 15 | 8 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056561 | No | No | Yes | Australia | Australia | 04-Test | Management (Test) - RTR | RTR | FUN | Saputo | Onshore | Ethier; Patrice | Saputo | Yes | CapEx | Localization | IT - Internal | 19h | 0h | 19h | 2017-05-08 | 2017-06-02 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 4 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056562 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct Design Workshops (AN) | RTR | FUN | Saputo | Onshore | Ethier; Patrice | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-11-22 | 2016-11-22 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056563 | No | No | Yes | Australia | Australia | 01-Preparation | Prepare KT) (PP) | RTR | FUN | Saputo | Onshore | Ethier; Patrice | Saputo | Yes | OpEx | Localization | IT - Internal | 37h | 0h | 37h | 2016-09-19 | 2016-09-23 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056564 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | RTR | FUN | Saputo | Onshore | Ethier; Patrice | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056565 | No | Yes | No | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | RTR | FUN | SI | Onshore | Holyk; Vic | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-01-30 | 2017-02-03 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056566 | No | Yes | No | Australia | Australia | 01-Preparation | Prepare KT) (PP) | RTR | FUN | SI | Onshore | Holyk; Vic | IBM | Yes | OpEx | Localization | IT - External | 24h | 0h | 24h | 2016-09-26 | 2016-10-21 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056567 | No | Yes | No | Australia | Australia | 01-Preparation | Prepare Kick-off) (PP) | RTR | FUN | SI | Onshore | Holyk; Vic | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-10-03 | 2016-10-07 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056568 | No | Yes | No | Australia | Australia | 01-Preparation | Conduct KT sessions) (PP) | RTR | FUN | SI | Onshore | Holyk; Vic | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-29 | 2016-10-29 | Yes |  |  | WP.FUN.Requirements/Process Design Workshop Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056569 | No | Yes | No | Australia | Australia | 01-Preparation | Conduct kick-off) (PP) | RTR | FUN | SI | Onshore | Holyk; Vic | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-29 | 2016-10-29 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056570 | No | Yes | No | Australia | Australia | 01-Preparation | Worshop Preparation Decks) (PP) | RTR | FUN | SI | Onshore | Holyk; Vic | IBM | Yes | CapEx | Localization | IT - External | 8.5h | 0h | 8.5h | 2016-10-03 | 2016-10-19 | Yes |  |  | WP.FUN-107.Workshop Preparation Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056571 | No | Yes | No | Australia | Australia | 02-Analyze | Old - Conduct Design Workshops (AN) | RTR | FUN | SI | Onshore | Holyk; Vic | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-22 | 2016-11-22 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056572 | No | Yes | No | Australia | Australia | 03-Design/Build | Management (D/B) - RTR | RTR | FUN | SI | Onshore | Holyk; Vic | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056573 | No | Yes | No | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) | RTR | FUN | SI | Onshore | Holyk; Vic | IBM | Yes | CapEx | Localization | IT - External | 11h | 0h | 11h | 2016-10-31 | 2016-11-18 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056574 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition Plan (D/B) | CM | CM | SI | Onshore | Fischer; Gillian | IBM | Yes | OpEx | Localization | IT - External | 12h | 0h | 12h | 2017-05-08 | 2017-05-09 | Yes |  |  | DELIV.CM-117.Transition Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056575 | No | No | Yes | Australia | Australia | 03-Design/Build | Role Mapping (D/B) | CM | CM | SI | Onshore | Fischer; Gillian | IBM | Yes | OpEx | Localization | IT - External | 241h | 0h | 241h | 2017-03-13 | 2017-05-05 | Yes |  |  | DELIV.CM-218.Role Mapping | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 32 | 44 | 40 | 25 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056576 | No | No | Yes | Australia | Australia | 02-Analyze | Process Role Catalog (AN) | CM | CM | SI | Onshore | Fischer; Gillian | IBM | Yes | OpEx | Localization | IT - External | 48h | 0h | 48h | 2016-11-07 | 2016-12-09 | Yes |  |  | DELIV.CM-008.Process Role Catalog | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056577 | No | No | Yes | Australia | Australia | 04-Test | Transition Plan Execution & Monitoring (Test) | CM | CM | SI | Onshore | Fischer; Gillian | IBM | Yes | OpEx | Localization | IT - External | 27h | 0h | 27h | 2017-05-23 | 2017-06-02 | Yes |  |  | ACT.CM.Transition Plan Execution & Monitoring | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056578 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Transition Plan Execution & Monitoring (C/G) | CM | CM | SI | Onshore | Fischer; Gillian | IBM | Yes | OpEx | Localization | IT - External | 2h | 0h | 2h | 2017-07-07 | 2017-07-07 | Yes |  |  | ACT.CM.Transition Plan Execution & Monitoring | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056579 | No | No | Yes | Australia | Australia | 06-Hypercare | Change Agents Network Execution and Monitoring (HYP) | CM | CM | SI | Onshore | Fischer; Gillian | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | ACT.CM.Change Agents Network Execution and Monitoring | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056580 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Knowledge Transfer Execution & Monitoring (C/G) | CM | CM | SI | Onshore | Fischer; Gillian | IBM | Yes | OpEx | Localization | IT - External | 26h | 0h | 26h | 2017-06-05 | 2017-06-21 | Yes |  |  | ACT.CM.Knowledge Transfer Execution & Monitoring | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 10 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056581 | No | Yes | No | Australia | Australia | 03-Design/Build | Development (D/B) | DEV | DEV | SI | Offshore | D; Kavya | IBM | Yes | CapEx | Localization | IT - External | 189.5h | 0h | 189.5h | 2017-02-14 | 2017-03-31 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 3 | 8.5 | 44 | 18 | 45 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056582 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia - (Capex) - (D/B) | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056583 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-26 | 2016-10-26 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056584 | No | No | Yes | Australia | Australia | 01-Preparation | Conduct KT sessions) (PP) | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  | WP.FUN.Requirements/Process Design Workshop Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056585 | No | No | Yes | Australia | Australia | 03-Design/Build | BI for Operational KPI report - PTM | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-03-13 | 2017-03-15 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056586 | No | No | Yes | Australia | Australia | 03-Design/Build | Cheese Aging report - PTM | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 139h | 0h | 139h | 2017-03-13 | 2017-04-07 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 44 | 44 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056587 | No | No | Yes | Australia | Australia | 03-Design/Build | Workshops - PTM - APO (Advance Palnning & Optimization) | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2017-04-10 | 2017-04-13 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056588 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - PTM | PTM | FUN | SI | Onshore | Nabar; Nitin | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2017-05-23 | 2017-05-26 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056589 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-01-23 | 2017-03-07 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056590 | No | No | Yes | Australia | Australia | 03-Design/Build | Ariba Build/Configuration (D/B) | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-04-03 | 2017-04-19 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056591 | No | No | Yes | Australia | Australia | 03-Design/Build | Ariba Unit Testing (D/B) | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2017-04-05 | 2017-04-11 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056592 | No | No | Yes | Australia | Australia | 03-Design/Build | Finalize AUS Design Workshop Material Requierement (D/B) | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056593 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - PTP | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2017-05-31 | 2017-06-16 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056594 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - PTP | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2017-06-19 | 2017-06-30 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056595 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - PTP | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 164h | 0h | 164h | 2017-07-03 | 2017-08-31 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 32 | 32 | 0 | 8 | 0 | 16 | 16 | 4 | 0 | 0 | 0
1056596 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Preparation | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 104h | 0h | 104h | 2017-03-13 | 2017-04-21 | Yes |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 32 | 8 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056597 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2017-04-26 | 2017-05-12 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 24 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056598 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Break/Fix - PTP | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-04-24 | 2017-05-05 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056599 | No | No | Yes | Australia | Australia | 04-Test | Regression - Run Tests - PTP | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-05-18 | 2017-05-18 | Yes |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056600 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - PTP | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 64h | 0h | 64h | 2017-05-17 | 2017-06-06 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 24 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056601 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - PTP | PTP | FUN | SI | Onshore | Pawankumar; Agrawal | Accenture | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2017-05-15 | 2017-05-23 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056602 | No | No | Yes | Australia | Australia | 04-Test | Regression - Run Tests - PTM | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056603 | No | No | Yes | Australia | Australia | 04-Test | Regression - Manage defects (Capex) - PTM | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056604 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - PTM | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056605 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - PTM | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056606 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056607 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - PTM | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 66h | 0h | 66h | 2017-05-15 | 2017-05-25 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056608 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - PTM | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056609 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 47h | 0h | 47h | 2017-04-24 | 2017-05-12 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056610 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Break/Fix - PTM | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056611 | No | No | Yes | Australia | Australia | 03-Design/Build | XXX-DEV FUT-Tabular results ( including 6506 ) | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-06 | 2017-06-06 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056612 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix - PTM | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 104h | 0h | 104h | 2017-07-03 | 2017-07-19 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056613 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - PTM | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 66h | 0h | 66h | 2017-07-10 | 2017-07-14 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056614 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - PTM | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-05-29 | 2017-06-04 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056615 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Prep | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 99h | 0h | 99h | 2017-05-15 | 2017-06-16 | Yes |  |  | ACT.FUN.UAT Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 6 | 0 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056616 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - PTM | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056617 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Validate | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056618 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - PTM | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 38h | 0h | 38h | 2017-06-26 | 2017-06-30 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056619 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Prepare - PTM | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-06-19 | 2017-06-23 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056620 | No | No | Yes | Australia | Australia | 03-Design/Build | Workshops - PTM - QM (Quality Management) | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 120h | 0h | 120h | 2017-03-27 | 2017-05-01 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 33 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056621 | No | No | Yes | Australia | Australia | 03-Design/Build | DMS Configuration/UT - Planning AUS - PTM (D/B) | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 50h | 0h | 50h | 2017-04-26 | 2017-05-07 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056622 | No | No | Yes | Australia | Australia | 03-Design/Build | DMS_01-CONFIG FUT-Dairy Mgmt System - Cross Functional | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-21 | 2017-03-21 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056623 | No | No | Yes | Australia | Australia | 03-Design/Build | DMS_01-CONFIG-Dairy Mgmt System - Cross Functional | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-03-06 | 2017-03-10 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056624 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Support | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056625 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Validate | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-09 | 2017-03-09 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056626 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Preparation | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 56h | 0h | 56h | 2017-03-30 | 2017-04-13 | Yes |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 11 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056627 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia - (Capex) - (D/B) | PTM | FUN | SI | Onshore | Collin-Demers; Julien | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056628 | No | No | Yes | Australia | Australia | 03-Design/Build | Security Role FUT | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 14.45h | 0h | 14.45h | 2016-12-05 | 2016-12-12 | Yes |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056629 | No | No | Yes | Australia | Australia | 06-Hypercare | Hypercare | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 117h | 0h | 117h | 2017-07-17 | 2017-08-04 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 45 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056630 | No | No | Yes | Australia | Australia | 03-Design/Build | Security Design/Build | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 81h | 0h | 81h | 2017-04-03 | 2017-04-13 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056631 | No | No | Yes | Australia | Australia | 03-Design/Build | SIT1 prep | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-04-17 | 2017-04-21 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056632 | No | No | Yes | Australia | Australia | 04-Test | SIT1 | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 162h | 0h | 162h | 2017-04-24 | 2017-05-19 | Yes |  |  | ACT.SEC.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 27 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056633 | No | No | Yes | Australia | Australia | 04-Test | SIT2 | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-05-29 | 2017-06-09 | Yes |  |  | ACT.SEC.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056634 | No | No | Yes | Australia | Australia | 02-Analyze | System Security Handover Activities (AN) | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-08 | 2016-11-08 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056635 | No | No | Yes | Australia | Australia | 03-Design/Build | System Security Handover Activities | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-29 | 2016-11-29 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056636 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-06-08 | 2017-06-23 | Yes |  |  | ACT.SEC.Executive UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056637 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 54h | 0h | 54h | 2017-06-05 | 2017-07-03 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056638 | No | No | Yes | Australia | Australia | 03-Design/Build | Composite Role Build | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-09 | 2017-03-09 | Yes |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056639 | No | No | Yes | Australia | Australia | 03-Design/Build | Derived Role Build - BUS | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-03-13 | 2017-03-17 | Yes |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056640 | No | No | Yes | Australia | Australia | 03-Design/Build | Master Role Build and UT | SEC | SEC | SI | Offshore | Taguiam; Norwin | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056641 | No | No | Yes | Australia | Australia | 03-Design/Build | Master Role Build and UT | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056642 | No | No | Yes | Australia | Australia | 03-Design/Build | Derived Role Build - BUS | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-10 | 2017-02-10 | Yes |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056643 | No | No | Yes | Australia | Australia | 03-Design/Build | Composite Role Build | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-09 | 2017-03-09 | Yes |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056644 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 80.25h | 0h | 80.25h | 2017-06-07 | 2017-06-30 | Yes |  |  | ACT.SEC.Executive UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5 | 36 | 38 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056645 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 105.25h | 0h | 105.25h | 2017-06-19 | 2017-07-07 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 53.25 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056646 | No | No | Yes | Australia | Australia | 03-Design/Build | System Security Handover Activities | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 1.5h | 0h | 1.5h | 2016-11-29 | 2017-01-09 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056647 | No | No | Yes | Australia | Australia | 03-Design/Build | SIT1 prep | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 41h | 0h | 41h | 2017-05-22 | 2017-05-29 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056648 | No | No | Yes | Australia | Australia | 04-Test | SIT2 | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 104.5h | 0h | 104.5h | 2017-05-22 | 2017-06-09 | Yes |  |  | ACT.SEC.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 54 | 42.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056649 | No | No | Yes | Australia | Australia | 04-Test | SIT1 | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 156h | 0h | 156h | 2017-04-24 | 2017-05-19 | Yes |  |  | ACT.SEC.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 36 | 39 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056650 | No | No | Yes | Australia | Australia | 06-Hypercare | Hypercare | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 261h | 0h | 261h | 2017-07-10 | 2017-08-18 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 36 | 45 | 45 | 0 | 0 | 0 | 0 | 0
1056651 | No | No | Yes | Australia | Australia | 03-Design/Build | Security Design/Build | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 158.5h | 0h | 158.5h | 2017-03-16 | 2017-04-21 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3.5 | 45 | 45 | 27 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056652 | No | No | Yes | Australia | Australia | 03-Design/Build | Security Role FUT | SEC | SEC | SI | Offshore | Deduque; Melanie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-05 | 2016-12-05 | Yes |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056653 | No | Yes | No | Australia | Australia | 04-Test | Development (SIT2) | DEV | DEV | SI | Offshore | Acosta; Junel | Accenture | Yes | CapEx | Localization | IT - External | 81h | 0h | 81h | 2017-05-15 | 2017-05-26 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056654 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Development (Cutover/Go-live) - DEV | DEV | DEV | SI | Offshore | Acosta; Junel | Accenture | Yes | CapEx | Localization | IT - External | 117h | 0h | 117h | 2017-06-19 | 2017-07-07 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056655 | No | Yes | No | Australia | Australia |  | AUS - DEV KT | DEV | DEV | SI | Offshore | Acosta; Junel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-31 | 2017-05-31 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056656 | No | Yes | No | Australia | Australia | 03-Design/Build | Development MDG (D/B) | DEV | DEV | SI | Offshore | Acosta; Junel | Accenture | Yes | CapEx | Localization | IT - External | 342h | 0h | 342h | 2017-03-06 | 2017-05-12 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 27 | 45 | 45 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056657 | No | Yes | No | Australia | Australia | 06-Hypercare | HC - Break/Fix - Dev | DEV | DEV | SI | Offshore | Acosta; Junel | Accenture | Yes | CapEx | Localization | IT - External | 144h | 0h | 144h | 2017-07-10 | 2017-07-31 | Yes |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056658 | No | No | Yes | Australia | Australia | 03-Design/Build | CONFIG-Baseline (D/B) | HR | HR | SI | Onshore | Robbins; Doug | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-02-13 | 2017-04-20 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056659 | No | No | Yes | Australia | Australia | 03-Design/Build | SDD- Baseline (D/B) | HR | HR | SI | Onshore | Robbins; Doug | IBM | Yes | CapEx | Localization | IT - External | 10.5h | 0h | 10.5h | 2017-02-23 | 2017-04-11 | Yes |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 3 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056660 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Execution and fix | HR | HR | SI | Onshore | Robbins; Doug | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056661 | No | No | Yes | Australia | Australia | 06-Hypercare | HC – Support and fix | HR | HR | SI | Onshore | Robbins; Doug | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2017-07-10 | 2017-08-04 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056662 | No | No | Yes | Australia | Australia | 02-Analyze | Gather Requirements (AN) | HR | HR | SI | Onshore | Robbins; Doug | IBM | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2017-02-06 | 2017-02-06 | Yes |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056663 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Execution and fix | HR | HR | SI | Onshore | Robbins; Doug | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056664 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Execution and fix | HR | HR | SI | Onshore | Robbins; Doug | IBM | Yes | CapEx | Localization | IT - External | 7h | 0h | 7h | 2017-04-24 | 2017-05-02 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056665 | No | No | Yes | Australia | Australia | 03-Design/Build | PDD (D/B) | HR | HR | SI | Onshore | Robbins; Doug | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-02-27 | 2017-03-02 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056666 | No | No | Yes | Australia | Australia | 03-Design/Build | FSD-Baseline (D/B) | HR | HR | SI | Onshore | Robbins; Doug | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-20 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056667 | No | No | Yes | Australia | Australia | 03-Design/Build | DEV FUT- Baseline (D/B) | HR | HR | SI | Onshore | Robbins; Doug | IBM | Yes | CapEx | Localization | IT - External | 19h | 0h | 19h | 2017-03-20 | 2017-03-24 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056668 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - HR | HR | HR | SI | Onshore | Robbins; Doug | IBM | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2017-05-08 | 2017-06-09 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 5 | 1 | 5 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056669 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - HR | HR | HR | SI | Onshore | Robbins; Doug | IBM | Yes | CapEx | Localization | IT - External | 3h | 0h | 3h | 2017-06-28 | 2017-07-04 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056670 | No | No | Yes | Australia | Australia | 04-Test | Regression - Run Tests - HR | HR | HR | SI | Onshore | Robbins; Doug | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-17 | 2017-05-17 | Yes |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056671 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - LOG | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 149h | 0h | 149h | 2017-07-03 | 2017-07-21 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 56 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056672 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | LOG | FUN | SI | Onshore | Phutane; Sachin | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056673 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia - (Capex) - (D/B) | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056674 | No | No | Yes | Australia | Australia | 04-Test | WPB recording (PTM) | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | OpEx | Localization | IT - External | 23h | 0h | 23h | 2017-05-24 | 2017-05-31 | Yes |  |  | DELIV.FUN-403.WPB Recordings | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056675 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Prepare | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | OpEx | Localization | IT - External | 5h | 0h | 5h | 2017-03-13 | 2017-03-17 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056676 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Support | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | OpEx | Localization | IT - External | 45h | 0h | 45h | 2017-03-13 | 2017-03-24 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056677 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Validate | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-09 | 2017-03-14 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056678 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - PTM | PTM | FUN | SI | Offshore | Hajare; Deven | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-06-01 | 2017-06-02 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056679 | No | Yes | No | Australia | Australia | 06-Hypercare | Hypercare - Support - TAI | TAI | TAI | SI | Offshore | Javier; Kristine | Accenture | Yes | CapEx | Localization | IT - External | 131h | 0h | 131h | 2017-07-03 | 2017-07-31 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 45 | 0 | 36 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056680 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Cutover - Support | TAI | TAI | SI | Offshore | Javier; Kristine | Accenture | Yes | CapEx | Localization | IT - External | 159h | 0h | 159h | 2017-06-05 | 2017-07-03 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 39 | 36 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056681 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - PTP | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 13h | 0h | 13h | 2017-06-19 | 2017-06-30 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056682 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - PTP | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 233h | 0h | 233h | 2017-07-03 | 2017-09-08 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 60 | 0 | 50 | 18 | 17 | 6 | 16 | 5 | 10 | 0 | 0
1056683 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Preparation | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 39h | 0h | 39h | 2017-03-13 | 2017-04-21 | Yes |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056684 | No | No | Yes | Australia | Australia | 03-Design/Build | WPB-PTP (D/B) | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | OpEx | Localization | IT - External | 45h | 0h | 45h | 2017-04-12 | 2017-05-30 | Yes |  |  | DELIV.FUN-403.WPB Recordings | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 18 | 0 | 3 | 6 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056685 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD083-Vendor Master - Milk and Milk related Z003 | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 17h | 0h | 17h | 2017-01-30 | 2017-03-03 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056686 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD096-Purchasing Contract | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 11h | 0h | 11h | 2017-02-22 | 2017-03-03 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056687 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Argentina Pricing routine 2 | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056688 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Argentina Pricing routine 5 | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056689 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Australia Pricing routine Incentives/Premiums 1 | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056690 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Australia Pricing routine Incentives/Premiums 4 | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056691 | No | No | Yes | Australia | Australia | 03-Design/Build | MM_08-CONFIG-MM Release Procedures | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 14h | 0h | 14h | 2017-03-01 | 2017-03-07 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056692 | No | No | Yes | Australia | Australia | 03-Design/Build | MM_08-CONFIG FUT-MM Release Procedures | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 76h | 0h | 76h | 2017-03-15 | 2017-05-09 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 5 | 3 | 20 | 0 | 9 | 8 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056693 | No | No | Yes | Australia | Australia | 03-Design/Build | MM_05-CONFIG-MM Purchasing | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 14h | 0h | 14h | 2017-02-09 | 2017-03-03 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056694 | No | No | Yes | Australia | Australia | 03-Design/Build | MM_05-CONFIG FUT-MM Purchasing | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-03-06 | 2017-03-21 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 13 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056695 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix - PTP | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 52h | 0h | 52h | 2017-07-06 | 2017-08-04 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 36 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056696 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-FSD-Australia Pricing routine Incentives/Premiums 7 | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056697 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-FSD-Australia Pricing routine Surcharge 2 | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056698 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD100-Open Purchase Orders | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-02-20 | 2017-02-24 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056699 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Australia Pricing routine Incentives/Premiums 7 | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056700 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Australia Pricing routine Surcharge 2 | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056701 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-FSD-Pricing routine 2 | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056702 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-FSD-Pricing routine 5 | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056703 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-FSD-Australia Pricing routine Incentives/Premiums 1 | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056704 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-FSD-Australia Pricing routine Incentives/Premiums 4 | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056705 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD099-Source Lists | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056706 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-05-05 | 2017-06-02 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 11 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056707 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Break/Fix - PTP | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 54h | 0h | 54h | 2017-05-02 | 2017-05-14 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056708 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - PTP | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 64h | 0h | 64h | 2017-05-18 | 2017-06-09 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 22 | 11 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056709 | No | No | Yes | Australia | Australia | 04-Test | Regression - Run Tests - PTP | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 57h | 0h | 57h | 2017-05-15 | 2017-05-30 | Yes |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 17 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056710 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - PTP | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-05-15 | 2017-06-09 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056711 | No | No | Yes | Australia | Australia | 03-Design/Build | SDD Writing (D/B) | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 41h | 0h | 41h | 2017-01-27 | 2017-04-10 | Yes |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 3 | 0 | 0 | 5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056712 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | PTP | FUN | SI | Offshore | Shaikh; Gufran | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056713 | No | Yes | No | Australia | Australia | 04-Test | Development (SIT1) | DEV | DEV | SI | Offshore | Dongare; Pranouti | IBM | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2017-04-26 | 2017-04-28 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056714 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Development (Cutover/Go-live) - DEV | DEV | DEV | SI | Offshore | Dongare; Pranouti | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-02 | 2017-06-02 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056715 | No | Yes | No | Australia | Australia | 04-Test | Development (SIT2) | DEV | DEV | SI | Offshore | Dongare; Pranouti | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-05-29 | 2017-05-29 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056716 | No | Yes | No | Australia | Australia |  | AUS - DEV KT | DEV | DEV | SI | Offshore | Dongare; Pranouti | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-31 | 2017-05-31 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056717 | No | Yes | No | Australia | Australia | 03-Design/Build | Development (D/B) | DEV | DEV | SI | Offshore | Dongare; Pranouti | IBM | Yes | CapEx | Localization | IT - External | 156h | 0h | 156h | 2017-02-15 | 2017-04-21 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 36 | 27 | 34 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056718 | No | Yes | No | Australia | Australia | 06-Hypercare | Development (Hypercare) - DEV | DEV | DEV | SI | Offshore | Dongare; Pranouti | IBM | Yes | CapEx | Localization | IT - External | 17h | 0h | 17h | 2017-05-04 | 2017-05-05 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056719 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - LOG | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 214h | 0h | 214h | 2017-07-03 | 2017-08-14 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 66 | 60 | 58 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0
1056720 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 111h | 0h | 111h | 2017-04-24 | 2017-05-14 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 36 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056721 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Defect Fix - LOG | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-05-15 | 2017-05-19 | Yes |  |  | ACT.MDG.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056722 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Manage Defect (Capex) - LOG | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-05-15 | 2017-05-19 | Yes |  |  | ACT.MDG.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056723 | No | No | Yes | Australia | Australia | 03-Design/Build | FLOG020-DEV FUT-Packing List | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2017-03-20 | 2017-03-21 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056724 | No | No | Yes | Australia | Australia | 03-Design/Build | FLOG021-DEV FUT-Pick List | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2017-02-27 | 2017-03-16 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 9 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056725 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056726 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Preparation | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2017-03-22 | 2017-04-12 | Yes |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056727 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG010-FSD-Pick Confirmation to 3PL | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-03-27 | 2017-04-20 | Yes |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056728 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG010-DEV FUT-Pick Confirmation to 3PL | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 67h | 0h | 67h | 2017-03-27 | 2017-04-15 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 24 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056729 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Defect Fix - LOG | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-06-19 | 2017-07-04 | Yes |  |  | ACT.MDG.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056730 | No | No | Yes | Australia | Australia | 03-Design/Build | IM_05-CONFIG-IM Output Control | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056731 | No | No | Yes | Australia | Australia | 03-Design/Build | CONFIG-MM_02-MM Master Data | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056732 | No | No | Yes | Australia | Australia | 03-Design/Build | MM_03-CONFIG-MM Inventory Management | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056733 | No | No | Yes | Australia | Australia | 03-Design/Build | IM_03-CONFIG-IM/LE Integration | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056734 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG011-DEV FUT-Lot Status Message to 3PL | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2017-04-06 | 2017-04-10 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056735 | No | No | Yes | Australia | Australia | 03-Design/Build | IM_02-CONFIG-IM Movements | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056736 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Prepare | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | OpEx | Localization | IT - External | 13h | 0h | 13h | 2017-03-20 | 2017-03-24 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056737 | No | No | Yes | Australia | Australia | 03-Design/Build | IM_03-CONFIG FUT-IM/LE Integration | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-03-06 | 2017-03-07 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056738 | No | No | Yes | Australia | Australia | 03-Design/Build | IM_04-CONFIG FUT-IM RF Transactions | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056739 | No | No | Yes | Australia | Australia | 03-Design/Build | IM_02-CONFIG FUT-IM Movements | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056740 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - LOG | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | CapEx | Localization | IT - External | 53h | 0h | 53h | 2017-05-22 | 2017-06-02 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056741 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Support | LOG | FUN | SI | Offshore | Surjan; Ashish | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-27 | 2017-03-27 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056742 | No | Yes | No | Australia | Australia | 06-Hypercare | Train end-users (HYP) | CM | CM | SI | Onshore | Faleyimu; Dele | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | ACT.CM.Deliver Training to End Users | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056743 | No | Yes | No | Australia | Australia | 04-Test | Training Materials-Training materials translation(Test) | CM | CM | SI | Onshore | Faleyimu; Dele | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  | DELIV.CM-401.Training Materials | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056744 | No | Yes | No | Australia | Australia | 04-Test | Training Materials-Work Instructions/Job aids (Test) | CM | CM | SI | Onshore | Faleyimu; Dele | IBM | Yes | OpEx | Localization | IT - External | 250.48h | 0h | 250.48h | 2017-03-23 | 2017-05-12 | Yes |  |  | DELIV.CM-451.Work Instructions | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 35.48 | 36 | 44 | 44 | 39 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056745 | No | No | Yes | Australia | Australia | 04-Test | Management (Test) - LOG | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 11h | 0h | 11h | 2017-04-24 | 2017-05-19 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056746 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056747 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - baseline - LOG | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-06-23 | 2017-06-23 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056748 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - LOG | LOG | FUN | SI | Offshore | Dahake; Sudhir | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056749 | No | No | No | Australia | Australia | 01-Preparation | Workplan next phases (PP) | CM | CM | Saputo | Onshore | Morrow; Frith | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-10-05 | 2016-10-05 | Yes |  |  | ACT.CM.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056750 | No | No | No | Australia | Australia | 01-Preparation | Stakeholder Map (PP) | CM | CM | Saputo | Onshore | Morrow; Frith | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-10-29 | 2016-10-29 | Yes |  |  | DELIV.CM-123a.Stakeholder Map and Assessment | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056751 | No | No | No | Australia | Australia | 01-Preparation | Project Kick-Off (PP) | CM | CM | Saputo | Onshore | Morrow; Frith | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-10-29 | 2016-10-29 | Yes |  |  | ACT.CM.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056752 | No | No | No | Australia | Australia | 01-Preparation | Business Readiness Plan (PP) | CM | CM | Saputo | Onshore | Morrow; Frith | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-10-26 | 2016-10-26 | Yes |  |  | DELIV.CM-112.Business Readiness plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056753 | No | No | No | Australia | Australia | 01-Preparation | Communication Plan (PP) | CM | CM | Saputo | Onshore | Morrow; Frith | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-10-25 | 2016-10-25 | Yes |  |  | DELIV.CM-106.Communication Plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056754 | No | No | No | Australia | Australia | 01-Preparation | Audience Analysis (PP) | CM | CM | Saputo | Onshore | Morrow; Frith | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-10-29 | 2016-10-29 | Yes |  |  | DELIV.CM-019.Audience Analysis | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056755 | No | No | No | Australia | Australia | 01-Preparation | Change Strategy documents (PP) | CM | CM | Saputo | Onshore | Morrow; Frith | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-10-29 | 2016-10-29 | Yes |  |  | ACT.CM.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056756 | No | No | No | Australia | Australia | 01-Preparation | Communication plan execution and monitoring (PP) | CM | CM | Saputo | Onshore | Morrow; Frith | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-11-11 | 2016-11-11 | Yes |  |  | ACT.CM.Communication plan execution and monitoring | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056757 | No | No | Yes | Australia | Australia | 02-Analyze | Gather Requirements (AN) | HR | HR | Saputo | Onshore | Centeno; Katya | Saputo | Yes | CapEx | Localization | IT - Internal | 1h | 0h | 1h | 2017-01-30 | 2017-02-01 | Yes |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056758 | No | No | Yes | Australia | Australia | 03-Design/Build | FSD-Baseline (D/B) | HR | HR | Saputo | Onshore | Centeno; Katya | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056759 | No | No | Yes | Australia | Australia | 03-Design/Build | PDD (D/B) | HR | HR | Saputo | Onshore | Centeno; Katya | Saputo | Yes | CapEx | Localization | IT - Internal | 10.5h | 0h | 10.5h | 2017-02-20 | 2017-03-24 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 | 1.5 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056760 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Execution and fix | HR | HR | Saputo | Onshore | Centeno; Katya | Saputo | Yes | CapEx | Localization | IT - Internal | 8h | 0h | 8h | 2017-05-15 | 2017-05-30 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056761 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Execution and fix | HR | HR | Saputo | Onshore | Centeno; Katya | Saputo | Yes | CapEx | Localization | IT - Internal | 9h | 0h | 9h | 2017-06-05 | 2017-06-16 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056762 | No | No | Yes | Australia | Australia | 06-Hypercare | HC – Support and fix | HR | HR | Saputo | Onshore | Centeno; Katya | Saputo | Yes | CapEx | Localization | IT - Internal | 10.5h | 0h | 10.5h | 2017-07-03 | 2017-07-18 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056763 | No | No | Yes | Australia | Australia | 03-Design/Build | SDD- Baseline (D/B) | HR | HR | Saputo | Onshore | Centeno; Katya | Saputo | Yes | CapEx | Localization | IT - Internal | 24.5h | 0h | 24.5h | 2017-02-13 | 2017-06-02 | Yes |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 4 | 2 | 8 | 0 | 4.5 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056764 | No | No | Yes | Australia | Australia | 03-Design/Build | CONFIG-Baseline (D/B) | HR | HR | Saputo | Onshore | Centeno; Katya | Saputo | Yes | CapEx | Localization | IT - Internal | 8.5h | 0h | 8.5h | 2017-04-13 | 2017-04-28 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056765 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Execution and fix | HR | HR | Saputo | Onshore | Centeno; Katya | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056766 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - HR | HR | HR | Saputo | Onshore | Centeno; Katya | Saputo | Yes | CapEx | Localization | IT - Internal | 27h | 0h | 27h | 2017-06-26 | 2017-07-03 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056767 | No | No | Yes | Australia | Australia | 04-Test | Regression - Run Tests - HR | HR | HR | Saputo | Onshore | Centeno; Katya | Saputo | Yes | CapEx | Localization | IT - Internal | 1.5h | 0h | 1.5h | 2017-05-17 | 2017-06-02 | Yes |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056768 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - HR | HR | HR | Saputo | Onshore | Centeno; Katya | Saputo | Yes | CapEx | Localization | IT - Internal | 4.5h | 0h | 4.5h | 2017-05-08 | 2017-05-24 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056769 | No | Yes | No | Australia | Australia | 03-Design/Build | IOTC008-FSD-ECC/GTS to BSM Order | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2017-02-20 | 2017-03-17 | Yes |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056770 | No | Yes | No | Australia | Australia | 03-Design/Build | DDD-GD223-Batch Determination Condition Records (LE) | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056771 | No | Yes | No | Australia | Australia | 03-Design/Build | IOTC007-DEV FUT-EDI Outbound Order Response | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-04-10 | 2017-04-15 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056772 | No | Yes | No | Australia | Australia | 04-Test | Mock1 - Support | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | OpEx | Localization | IT - External | 15h | 0h | 15h | 2017-04-03 | 2017-04-07 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056773 | No | Yes | No | Australia | Australia | 03-Design/Build | Transition to Australia(D/B) | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-02-13 | 2017-03-03 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056774 | No | Yes | No | Australia | Australia | 02-Analyze | AUS Deep Dive for Billing Corrections | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056775 | No | Yes | No | Australia | Australia | 02-Analyze | AUS Deep Dive for freight | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-25 | 2017-01-25 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056776 | No | Yes | No | Australia | Australia | 04-Test | Mock1 - Prepare | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | OpEx | Localization | IT - External | 8h | 0h | 8h | 2017-02-06 | 2017-03-31 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056777 | No | Yes | No | Australia | Australia | 03-Design/Build | Security Roles - Support (D/B) | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2017-03-27 | 2017-03-31 | Yes |  |  | DELIV.SEC-201.Security Role Detailed Design | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056778 | No | Yes | No | Australia | Australia | 03-Design/Build | Training Materials Localization - Support (D/B) - OTC | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | OpEx | Localization | IT - External | 35h | 0h | 35h | 2017-02-27 | 2017-04-21 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056779 | No | Yes | No | Australia | Australia | 02-Analyze | AUS: Sell-Through Process | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2017-01-23 | 2017-02-03 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056780 | No | Yes | No | Australia | Australia | 02-Analyze | AUS: GOI Joint Venture | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-25 | 2017-01-25 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056781 | No | Yes | No | Australia | Australia | 02-Analyze | AUS Deep Dive: Batch Determination | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-24 | 2017-01-24 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056782 | No | Yes | No | Australia | Australia | 02-Analyze | AUS Deep Dive: Trade ECC Rebates & Commissions | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-01-25 | 2017-02-03 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056783 | No | Yes | No | Australia | Australia | 02-Analyze | AUS Deep Dive for Master Data (Customer and Material Master) | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-01-23 | 2017-02-03 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056784 | No | Yes | No | Australia | Australia | 02-Analyze | AUS: Reporting (ECC vs. BI) | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2017-01-23 | 2017-02-03 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056785 | No | Yes | No | Australia | Australia | 02-Analyze | AUS Deep Dive on Pricing upload program | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056786 | No | Yes | No | Australia | Australia | 03-Design/Build | FOTC007-FSD-Order acknowledgement form - domestic | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-02-06 | 2017-04-15 | Yes |  |  | DELIV.FUN-204.Functional Specification - Form | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056787 | No | Yes | No | Australia | Australia | 03-Design/Build | XXX-FSD-Order acknowledgement form - export | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-02-13 | 2017-02-17 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056788 | No | Yes | No | Australia | Australia | 03-Design/Build | IOTC006-DEV FUT-EDI Inbound Sales Order | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-03-20 | 2017-04-15 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056789 | No | Yes | No | Australia | Australia | 03-Design/Build | IOTC006-FSD-EDI Inbound Sales Order | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2017-02-06 | 2017-03-31 | Yes |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 20 | 15 | 0 | 15 | 15 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056790 | No | Yes | No | Australia | Australia | 03-Design/Build | IOTC007-FSD-EDI Outbound Order Response | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2017-01-30 | 2017-03-24 | Yes |  |  | DELIV.FUN-202.Functional Specification - Interface | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 10 | 0 | 0 | 0 | 5 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056791 | No | Yes | No | Australia | Australia | 03-Design/Build | OTC_03-CONFIG FUT-OTC Process | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-02-06 | 2017-02-10 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056792 | No | Yes | No | Australia | Australia | 03-Design/Build | OTC_05-CONFIG FUT-Foreign Trade | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-02-15 | 2017-04-07 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056793 | No | Yes | No | Australia | Australia | 03-Design/Build | OTC_06-CONFIG FUT-Output Determination (Billing, Sales, Deliveries) | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-02-06 | 2017-02-10 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056794 | No | Yes | No | Australia | Australia | 02-Analyze | AUS Deep Dive: One Customer | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-01-24 | 2017-02-03 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056795 | No | Yes | No | Australia | Australia | 02-Analyze | AUS Deep Dive Order to Cash Process Flow (with EDI and 3PLs) | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-01-25 | 2017-02-03 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056796 | No | Yes | No | Australia | Australia | 02-Analyze | AUS Deep Dive: Export Process considering BSM In Scope | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-01-24 | 2017-02-03 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056797 | No | Yes | No | Australia | Australia | 03-Design/Build | IOTC008-DEV FUT-ECC/GTS to BSM Order | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 77h | 0h | 77h | 2017-03-13 | 2017-04-14 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 20 | 12 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056798 | No | Yes | No | Australia | Australia | 03-Design/Build | OTC_05-CONFIG-Foreign Trade | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-08 | 2017-02-08 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056799 | No | Yes | No | Australia | Australia | 03-Design/Build | OTC_06-CONFIG-Output Determination (Billing, Sales, Deliveries) | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-02-06 | 2017-02-10 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056800 | No | Yes | No | Australia | Australia | 03-Design/Build | OTC_03-CONFIG-OTC Process | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-02-06 | 2017-02-10 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056801 | No | Yes | No | Australia | Australia | 06-Hypercare | Break/Fix - OTC | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 68h | 0h | 68h | 2017-07-03 | 2017-08-11 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 8 | 15 | 0 | 20 | 15 | 0 | 0 | 0 | 0 | 0 | 0
1056802 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | UAT - Prep | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2017-06-03 | 2017-06-04 | Yes |  |  | ACT.FUN.UAT Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056803 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - OTC | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2017-05-15 | 2017-06-04 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056804 | No | Yes | No | Australia | Australia | 03-Design/Build | IOTC006-ASS Testing-EDI Inbound Sales Order | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | ACT.FUN.Execute Assembly Tests | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056805 | No | Yes | No | Australia | Australia | 03-Design/Build | IOTC008-ASS Testing-ECC/GTS to BSM Order | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-04-17 | 2017-05-05 | Yes |  |  | ACT.FUN.Execute Assembly Tests | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056806 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - OTC | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-06-12 | 2017-06-16 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056807 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - OTC | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-06-12 | 2017-06-16 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056808 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - OTC | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-06-19 | 2017-06-23 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056809 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Cut Over - Prepare - OTC | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-06-12 | 2017-06-16 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056810 | No | Yes | No | Australia | Australia | 04-Test | SIT 1 - Break/Fix - OTC | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 59h | 0h | 59h | 2017-04-24 | 2017-06-02 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 16 | 15 | 3 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056811 | No | Yes | No | Australia | Australia | 04-Test | SIT 1 - Run Tests | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 14h | 0h | 14h | 2017-05-01 | 2017-05-19 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056812 | No | Yes | No | Australia | Australia | 04-Test | SIT 2 - Break/Fix - OTC | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 17h | 0h | 17h | 2017-05-18 | 2017-06-02 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056813 | No | Yes | No | Australia | Australia | 04-Test | SIT 2 - Run Tests - OTC | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-05-15 | 2017-05-19 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056814 | No | Yes | No | Australia | Australia | 04-Test | SIT1 Preparation | OTC | FUN | SI | Offshore | Bhirangi; Harshali | IBM | Yes | CapEx | Localization | IT - External | 31h | 0h | 31h | 2017-03-27 | 2017-04-21 | Yes |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 5 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056815 | No | Yes | No | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | PTM | FUN | SI | Onshore | Gudipudi; Raghu | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056816 | No | Yes | No | Australia | Australia | 03-Design/Build | DDD-GD052-QM-Inspection Plans | PTM | FUN | SI | Onshore | Gudipudi; Raghu | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056817 | No | Yes | No | Australia | Australia | 03-Design/Build | DDD-GD050-QM-Sampling Procedures | PTM | FUN | SI | Onshore | Gudipudi; Raghu | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056818 | No | No | Yes | Australia | Australia | 02-Analyze | Kickoff - DC (AN) | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2017-02-02 | Yes |  |  | ACT.MDG.Workshop | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056819 | No | No | Yes | Australia | Australia | 02-Analyze | Data Construction and staging - DC (AN) | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  | ACT.MDG.Data Construction | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056820 | No | No | Yes | Australia | Australia | 04-Test | Mock1 – Manage defect (Capex) - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-04-17 | 2017-05-05 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056821 | No | No | Yes | Australia | Australia | 04-Test | Data collection templates - explain and collect - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 218h | 0h | 218h | 2016-12-19 | 2017-03-24 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 49 | 67 | 45 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056822 | No | No | Yes | Australia | Australia | 04-Test | Data load - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 105h | 0h | 105h | 2017-03-27 | 2017-04-07 | Yes |  |  | ACT.MDG.Mock Load | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056823 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Validate - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | OpEx | Localization | IT - External | 87h | 0h | 87h | 2017-03-20 | 2017-04-28 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 27 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056824 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-10 | 2017-04-10 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056825 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Support - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056826 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Prepare - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056827 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Validate - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056828 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect (Capex) - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056829 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-05-08 | 2017-05-12 | Yes |  |  | ACT.MDG.Mock Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056830 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Execute - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-05-08 | 2017-05-12 | Yes |  |  | ACT.MDG.Mock Load | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056831 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate - DC | MDG | DC | SI | Offshore | Sobrevilla; Leizel | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056832 | No | Yes | No | Australia | Australia | 04-Test | Data collection templates - explain and collect - DC | MDG | DC | SI | Offshore | Paniza; Rolly | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2017-01-09 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056833 | No | Yes | No | Australia | Australia | 02-Analyze | Data Construction and staging - DC (AN) | MDG | DC | SI | Offshore | Paniza; Rolly | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  | ACT.MDG.Data Construction | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056834 | No | Yes | No | Australia | Australia | 02-Analyze | Kickoff - DC (AN) | MDG | DC | SI | Offshore | Paniza; Rolly | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  | ACT.MDG.Workshop | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056835 | No | Yes | No | Australia | Australia | 02-Analyze | Kickoff - DC (AN) | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | CapEx | Localization | IT - External | 207h | 0h | 207h | 2016-11-07 | 2017-01-06 | Yes |  |  | ACT.MDG.Workshop | Complete | NA | NA | 0 |  |  | 0 | 0 | 27 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056836 | No | Yes | No | Australia | Australia | 02-Analyze | Data Construction and staging - DC (AN) | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | CapEx | Localization | IT - External | 213h | 0h | 213h | 2017-01-09 | 2017-02-10 | Yes |  |  | ACT.MDG.Data Construction | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056837 | No | Yes | No | Australia | Australia | 04-Test | Data load - DC | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | CapEx | Localization | IT - External | 81h | 0h | 81h | 2017-03-20 | 2017-03-30 | Yes |  |  | ACT.MDG.Mock Load | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056838 | No | Yes | No | Australia | Australia | 04-Test | Mock1 - Validate - DC | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | OpEx | Localization | IT - External | 90h | 0h | 90h | 2017-04-03 | 2017-04-28 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056839 | No | Yes | No | Australia | Australia | 04-Test | Mock1 – Manage defect (Capex) - DC | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | CapEx | Localization | IT - External | 72h | 0h | 72h | 2017-04-17 | 2017-05-05 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056840 | No | Yes | No | Australia | Australia | 03-Design/Build | Build Material Master - Functional Support (Accenture) - DM (D/B) | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-03-06 | 2017-03-17 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056841 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate - DC | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056842 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Cutover - Prepare - DC | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056843 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Execute - DC | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-05-08 | 2017-06-14 | Yes |  |  | ACT.MDG.Mock Load | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056844 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - DC | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-05-08 | 2017-06-09 | Yes |  |  | ACT.MDG.Mock Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056845 | No | Yes | No | Australia | Australia | 06-Hypercare | HC - Manage defects - DC | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-04 | 2017-07-04 | Yes |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056846 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect (Capex) - DC | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-06-19 | 2017-06-22 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056847 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Cutover - Validate - DC | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056848 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Cutover - Support - DC | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056849 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect - DC | MDG | DM | SI | Offshore | Restauro; Kharla | Accenture | Yes | CapEx | Localization | IT - External | 144h | 0h | 144h | 2017-04-10 | 2017-06-02 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 45 | 27 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056850 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | CapEx | Localization | IT - External | 23h | 0h | 23h | 2017-05-15 | 2017-06-09 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 10 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056851 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Cutover - Support - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | OpEx | Localization | IT - External | 12h | 0h | 12h | 2017-06-12 | 2017-06-15 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056852 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect (Capex) - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2017-06-12 | 2017-06-15 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056853 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Cutover - Validate - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | OpEx | Localization | IT - External | 12h | 0h | 12h | 2017-06-12 | 2017-06-15 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056854 | No | Yes | No | Australia | Australia | 06-Hypercare | HC - Manage defects - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056855 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | CapEx | Localization | IT - External | 54h | 0h | 54h | 2017-05-01 | 2017-05-26 | Yes |  |  | ACT.MDG.Mock Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 8 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056856 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Execute - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | CapEx | Localization | IT - External | 23h | 0h | 23h | 2017-05-15 | 2017-06-09 | Yes |  |  | ACT.MDG.Mock Load | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 10 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056857 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | CapEx | Localization | IT - External | 92h | 0h | 92h | 2017-05-08 | 2017-05-30 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 12 | 15 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056858 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Cutover - Prepare - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | OpEx | Localization | IT - External | 35h | 0h | 35h | 2017-06-05 | 2017-06-09 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056859 | No | Yes | No | Australia | Australia | 04-Test | Mock1 – Manage defect (Capex) - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-04-24 | 2017-04-27 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056860 | No | Yes | No | Australia | Australia | 04-Test | Data collection templates - explain and collect - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | CapEx | Localization | IT - External | 68h | 0h | 68h | 2017-02-10 | 2017-03-03 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 18 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056861 | No | Yes | No | Australia | Australia | 04-Test | Mock1 - Validate - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | OpEx | Localization | IT - External | 92h | 0h | 92h | 2017-03-20 | 2017-04-07 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056862 | No | Yes | No | Australia | Australia | 04-Test | Data load - DC | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | CapEx | Localization | IT - External | 29h | 0h | 29h | 2017-04-10 | 2017-04-12 | Yes |  |  | ACT.MDG.Mock Load | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056863 | No | Yes | No | Australia | Australia | 02-Analyze | Kickoff - DC (AN) | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-11-03 | Yes |  |  | ACT.MDG.Workshop | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056864 | No | Yes | No | Australia | Australia | 02-Analyze | Data Construction and staging - DC (AN) | MDG | DC | SI | Offshore | Baterisna; Ellen | Accenture | Yes | CapEx | Localization | IT - External | 266.5h | 0h | 266.5h | 2017-02-20 | 2017-04-21 | Yes |  |  | ACT.MDG.Data Construction | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 74 | 43 | 0 | 55.5 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056865 | No | No | Yes | Australia | Australia | 02-Analyze | Kickoff - DC (AN) | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 186h | 0h | 186h | 2016-12-05 | 2017-03-17 | Yes |  |  | ACT.MDG.Workshop | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 36 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056866 | No | No | Yes | Australia | Australia | 02-Analyze | Data Construction and staging - DC (AN) | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  | ACT.MDG.Data Construction | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056867 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056868 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 52h | 0h | 52h | 2017-05-29 | 2017-06-02 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056869 | No | No | Yes | Australia | Australia | 04-Test | Data collection templates - explain and collect - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 165h | 0h | 165h | 2016-12-19 | 2017-03-13 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 27 | 25 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056870 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Manage Defect (Capex) | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-01 | 2017-05-01 | Yes |  |  | ACT.MDG.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056871 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Defect Fix - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-09 | 2017-05-09 | Yes |  |  | ACT.MDG.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056872 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Validate - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-14 | 2017-03-14 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056873 | No | No | Yes | Australia | Australia | 04-Test | Data load - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 208h | 0h | 208h | 2017-03-20 | 2017-04-13 | Yes |  |  | ACT.MDG.Mock Load | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 56.5 | 56 | 45.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056874 | No | No | Yes | Australia | Australia | 04-Test | Mock1 – Manage defect (Capex) - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 81h | 0h | 81h | 2017-04-17 | 2017-04-27 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056875 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Execute - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 151h | 0h | 151h | 2017-05-08 | 2017-05-28 | Yes |  |  | ACT.MDG.Mock Load | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056876 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 30.5h | 0h | 30.5h | 2017-05-03 | 2017-05-07 | Yes |  |  | ACT.MDG.Mock Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056877 | No | No | Yes | Australia | Australia | 06-Hypercare | HC - Manage defects - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056878 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect (Capex) - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056879 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Validate - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | OpEx | Localization | IT - External | 48h | 0h | 48h | 2017-06-19 | 2017-06-25 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056880 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Prepare - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | OpEx | Localization | IT - External | 53h | 0h | 53h | 2017-06-05 | 2017-06-11 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056881 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Support - DC | MDG | DC | SI | Offshore | Solomon; Ronnie | Accenture | Yes | OpEx | Localization | IT - External | 126h | 0h | 126h | 2017-06-12 | 2017-07-13 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 62 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056882 | No | No | Yes | Australia | Australia | 04-Test | Management (Test) - LOG | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | CapEx | Localization | IT - Internal | 89h | 0h | 89h | 2017-05-08 | 2017-06-09 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 24 | 30 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056883 | No | No | Yes | Australia | Australia | 06-Hypercare | Management (Hypercare) - LOG | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | CapEx | Localization | IT - Internal | 208h | 0h | 208h | 2017-07-04 | 2017-08-25 | Yes |  |  | ACT.DEV.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 56 | 0 | 24 | 0 | 0 | 32 | 40 | 0 | 0 | 0 | 0
1056884 | No | No | Yes | Australia | Australia | 01-Preparation | Prepare KT) (PP) | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2016-10-03 | 2016-10-03 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056885 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056886 | No | No | Yes | Australia | Australia | 03-Design/Build | Management (D/B) | LOG | FUN | Saputo | Onshore | Toney; Alwin | Saputo | Yes | CapEx | Localization | IT - Internal | 88h | 0h | 88h | 2017-02-21 | 2017-04-11 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 38 | 40 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056887 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 50h | 0h | 50h | 2017-02-01 | 2017-02-24 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 25 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056888 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-FSD-Placeholder for RTR Design Issue | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056889 | No | No | Yes | Australia | Australia | 03-Design/Build | KT sessions (D/B) | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 29h | 0h | 29h | 2017-03-17 | 2017-05-04 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056890 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - RTR | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056891 | No | No | Yes | Australia | Australia | 03-Design/Build | AR_01-CONFIG-FI-AR-Basic Settings | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056892 | No | No | Yes | Australia | Australia | 03-Design/Build | AP_03-CONFIG-Tax on Sale / Purchase | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056893 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Placeholder for RTR Design Issue | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056894 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-FSD-Placeholder for RTR Design Issue | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056895 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Placeholder for RTR Design Issue | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056896 | No | No | Yes | Australia | Australia | 03-Design/Build | FRTR006-DEV FUT-Need to send payment remittance advice | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-03 | 2017-03-03 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056897 | No | No | Yes | Australia | Australia | 03-Design/Build | FRTR005-DEV FUT-Ability to produce an invoice for direct FI | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056898 | No | No | Yes | Australia | Australia | 03-Design/Build | AR_01-CONFIG FUT-FI-AR-Basic Settings | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056899 | No | No | Yes | Australia | Australia | 03-Design/Build | AP_03-CONFIG FUT-Tax on Sale / Purchase | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-24 | 2017-02-24 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056900 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 61h | 0h | 61h | 2017-04-27 | 2017-05-14 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 16 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056901 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - RTR | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 23h | 0h | 23h | 2017-05-29 | 2017-06-02 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056902 | No | No | Yes | Australia | Australia | 04-Test | Regression - Run Tests - RTR | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2017-05-16 | 2017-05-19 | Yes |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056903 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Break/Fix - RTR | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056904 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - RTR | RTR | FUN | SI | Offshore | Kanade; Dhanashri | IBM | Yes | CapEx | Localization | IT - External | 37h | 0h | 37h | 2017-05-22 | 2017-06-09 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056905 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056906 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - LOG | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 46h | 0h | 46h | 2017-04-29 | 2017-05-05 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056907 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - baseline - LOG | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 42h | 0h | 42h | 2017-06-19 | 2017-06-29 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056908 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD250-GTS - Material to FDA Codes | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056909 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD251-GTS - Material to Preference Indicator | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056910 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD229-GTS - Tariff Numbers | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056911 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD230-GTS - SPL List | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056912 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD231-GTS - Customs Offices | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056913 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD233-GTS - Licenses | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056914 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD234-GTS - FDA Codes | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056915 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD249-GTS - Material to Tariff Numbers | LOG | FUN | SI | Offshore | Phegade; Atul | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056916 | No | No | No | Australia | Australia | 02-Analyze | Kickoff (AN) | PTM | FUN | Saputo | Onshore | McGowan; Sharon | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056917 | No | No | No | Australia | Australia | 02-Analyze | RTM (AN) | PTM | FUN | Saputo | Onshore | McGowan; Sharon | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-11-13 | 2016-11-13 | Yes |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056918 | No | No | No | Australia | Australia | 03-Design/Build | Transition to Australia - (Capex) - (D/B) | PTM | FUN | Saputo | Onshore | McGowan; Sharon | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056919 | No | No | No | Australia | Australia | 02-Analyze | Old - Log Gaps (AN) | PTM | FUN | Saputo | Onshore | McGowan; Sharon | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | Yes |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056920 | No | No | No | Australia | Australia | 01-Preparation | Conduct KT sessions) (PP) | PTM | FUN | Saputo | Onshore | McGowan; Sharon | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | Yes |  |  | WP.FUN.Requirements/Process Design Workshop Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056921 | No | No | No | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) | PTM | FUN | Saputo | Onshore | McGowan; Sharon | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056922 | No | No | No | Australia | Australia | 02-Analyze | RTM (AN) | PTM | FUN | Saputo | Onshore | McGowan; Sharon | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-10-26 | 2016-10-26 | Yes |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056923 | No | No | No | Australia | Australia | 01-Preparation | Prepare Kick-off (Saputo)) (PP) | PTM | FUN | Saputo | Onshore | McGowan; Sharon | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-10-03 | 2016-10-03 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056924 | No | No | No | Australia | Australia | 01-Preparation | Conduct kick-off in Australia) (PP) | PTM | FUN | Saputo | Onshore | McGowan; Sharon | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-10-29 | 2016-10-29 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056925 | No | No | Yes | Australia | Australia | 03-Design/Build | Management (D/B) | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | CapEx | Localization | IT - Internal | 122h | 0h | 122h | 2017-03-20 | 2017-05-26 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | 8 | 5 | 9 | 0 | 0 | 32 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056926 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia - (Capex) - (D/B) | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056927 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Management (Cutover/Go-live) | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | CapEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-07 | 2017-06-07 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056928 | No | No | Yes | Australia | Australia | 04-Test | Management (Test) - PTP | PTP | FUN | Saputo | Onshore | Ranjan; Amit | Saputo | Yes | CapEx | Localization | IT - Internal | 35h | 0h | 35h | 2017-05-01 | 2017-06-02 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 8 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056929 | No | No | Yes | Australia | Australia | 03-Design/Build | Reviewing AUS Design (D/B) | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 84.6h | 0h | 84.6h | 2017-03-20 | 2017-06-11 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.13 | 16 | 35.47 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056930 | No | No | Yes | Australia | Australia | 03-Design/Build | Reviewing AUS Configuration | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | OpEx | Localization | IT - External | 20h | 0h | 20h | 2017-03-07 | 2017-03-28 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056931 | No | No | Yes | Australia | Australia | 03-Design/Build | Workaround Procedures (D/B) | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2017-02-13 | 2017-02-17 | Yes |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056932 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - RTR | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 56.35h | 0h | 56.35h | 2017-06-19 | 2017-07-03 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.35 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056933 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - RTR | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-05-29 | 2017-06-29 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056934 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix (Hypercare) - RTR | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 167.3h | 0h | 167.3h | 2017-07-03 | 2017-08-18 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 10.65 | 0 | 31 | 22.65 | 22 | 31 | 0 | 0 | 0 | 0 | 0
1056935 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD013-Activity Types | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056936 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - RTR | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 148.35h | 0h | 148.35h | 2017-07-10 | 2017-08-25 | Yes |  |  | ACT.FUN.Functional Break/Fix | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.35 | 0 | 0 | 30 | 49 | 21 | 44 | 0 | 0 | 0 | 0
1056937 | No | No | Yes | Australia | Australia | 03-Design/Build | TP_01-CONFIG-Transfer Pricing | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056938 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056939 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Break/Fix - RTR | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 132.6h | 0h | 132.6h | 2017-04-24 | 2017-06-04 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.6 | 0 | 67 | 3 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056940 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - RTR | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 63h | 0h | 63h | 2017-05-15 | 2017-05-21 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056941 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - RTR | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-06-05 | 2017-06-09 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056942 | No | No | Yes | Australia | Australia | 03-Design/Build | Contribute to Cut-over Planning (D/B) - RTR | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-22 | 2017-05-29 | Yes |  |  | ACT.FUN.Support Cutover plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056943 | No | No | Yes | Australia | Australia | 03-Design/Build | Support MDM (D/B) | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-03 | 2016-12-03 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056944 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct Design Workshops (AN) | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2016-11-22 | 2016-11-23 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056945 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Log Gaps (AN) | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-11 | 2016-11-11 | Yes |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056946 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Create BPML (AN) | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056947 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Perform Gap Resolution (AN) | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-21 | 2016-11-21 | Yes |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056948 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-Baseline (D/B) | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056949 | No | No | Yes | Australia | Australia | 03-Design/Build | CONFIG FUT-Baseline (D/B) | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-13 | 2016-12-13 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056950 | No | No | Yes | Australia | Australia | 03-Design/Build | SDD Writing | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-04-03 | 2017-04-07 | Yes |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056951 | No | No | Yes | Australia | Australia | 03-Design/Build | CONFIG-Baseline (D/B) | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056952 | No | No | Yes | Australia | Australia | 03-Design/Build | DEV FUT- Baseline (D/B) | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056953 | No | No | Yes | Australia | Australia | 03-Design/Build | Support to Developpers (D/B) | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056954 | No | No | Yes | Australia | Australia | 03-Design/Build | FSD-Baseline (D/B) | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056955 | No | No | Yes | Australia | Australia | 03-Design/Build | PA_02-CONFIG-Profitability Analysis Planning | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056956 | No | No | Yes | Australia | Australia | 03-Design/Build | PA_01-CONFIG-Profitability Analysis Actual | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056957 | No | No | Yes | Australia | Australia | 03-Design/Build | PC_02-CONFIG-Product Cost Planning | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056958 | No | No | Yes | Australia | Australia | 03-Design/Build | PC_01-CONFIG-Actual Costing/Material Ledger | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056959 | No | No | Yes | Australia | Australia | 03-Design/Build | PCA_01-CONFIG-Profit Centre Accounting | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056960 | No | No | Yes | Australia | Australia | 03-Design/Build | CO_01-CONFIG-CO Organizational Data | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056961 | No | No | Yes | Australia | Australia | 03-Design/Build | CO_02-CONFIG-CO Configuration Master Data | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056962 | No | No | Yes | Australia | Australia | 03-Design/Build | COC_01-CONFIG-Cost Object Controlling | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056963 | No | No | Yes | Australia | Australia | 03-Design/Build | COC_02-CONFIG-Cost Object Controlling - Cancelled | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056964 | No | No | Yes | Australia | Australia | 03-Design/Build | CC_01-CONFIG FUT-Cost Centre Accounting - Planning and Actual | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056965 | No | No | Yes | Australia | Australia | 03-Design/Build | CO_01-CONFIG FUT-CO Organizational Data | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056966 | No | No | Yes | Australia | Australia | 03-Design/Build | CO_02-CONFIG FUT-CO CONFIG FUTuration Master Data | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056967 | No | No | Yes | Australia | Australia | 03-Design/Build | COC_01-CONFIG FUT-Cost Object Controlling | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056968 | No | No | Yes | Australia | Australia | 03-Design/Build | COC_02-CONFIG FUT-Cancelled | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056969 | No | No | Yes | Australia | Australia | 03-Design/Build | PA_01-CONFIG FUT-Profitability Analysis Actual | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-10 | 2017-02-10 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056970 | No | No | Yes | Australia | Australia | 03-Design/Build | PC_01-CONFIG FUT-Product Cost Planning | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056971 | No | No | Yes | Australia | Australia | 03-Design/Build | PC_02-CONFIG FUT-Actual Costing/Material Ledger | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-27 | 2017-01-27 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056972 | No | No | Yes | Australia | Australia | 03-Design/Build | PCA_01-CONFIG FUT-Profit Centre Accounting | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-17 | 2017-03-17 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056973 | No | No | Yes | Australia | Australia | 03-Design/Build | CC_01-CONFIG-Cost Centre Accounting - Planning and Actual | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-02-20 | 2017-02-24 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056974 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD247-Profit Center Plan | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 7h | 0h | 7h | 2017-02-13 | 2017-03-24 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056975 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD025-Statistical Key Figures | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056976 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD014-Activity Type Rates | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056977 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD024-Profit Centre Groups - ECC | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056978 | No | No | Yes | Australia | Australia | 02-Analyze | RTM (AN) | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 86.1h | 0h | 86.1h | 2016-11-04 | 2017-01-22 | Yes |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 42.1 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056979 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Support | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | OpEx | Localization | IT - External | 19.88h | 0h | 19.88h | 2017-03-20 | 2017-04-18 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3.57 | 0 | 7.32 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056980 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Preparation | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2017-03-06 | 2017-04-24 | Yes |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056981 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Validate | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | OpEx | Localization | IT - External | 10h | 0h | 10h | 2017-04-10 | 2017-04-24 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4 | 4 | 1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056982 | No | No | Yes | Australia | Australia | 03-Design/Build | Conversion AUS support (D/B) | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2017-03-07 | 2017-06-02 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 19 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056983 | No | No | Yes | Australia | Australia | 03-Design/Build | KT sessions (D/B) | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 68h | 0h | 68h | 2017-03-17 | 2017-05-03 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 11 | 10 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056984 | No | No | Yes | Australia | Australia | 03-Design/Build | Derived Role Build - BUS | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-10 | 2017-02-10 | Yes |  |  | DELIV.SEC-003.Security Role Design & Build | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056985 | No | No | Yes | Australia | Australia | 03-Design/Build | CONFIG-MM_01-QM | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056986 | No | No | Yes | Australia | Australia | 03-Design/Build | DMS_01-CONFIG-Dairy Mgmt System - Cross Functional | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 3h | 0h | 3h | 2017-02-13 | 2017-02-15 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056987 | No | No | Yes | Australia | Australia | 03-Design/Build | DM_01-CONFIG-Advanced Planning & Optimization (BW) | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056988 | No | No | Yes | Australia | Australia | 03-Design/Build | DMS_02-CONFIG-Dairy Mgmt System - Planning | RTR | FUN | SI | Onshore | Deac; Csaba | IBM | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2017-02-13 | 2017-02-17 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056989 | No | Yes | No | Australia | Australia | 03-Design/Build | Transition to Australia - (Capex) - (D/B) | PTM | FUN | SI | Onshore | Ferrante; Alfredo | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056990 | No | Yes | No | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | LOG | FUN | SI | Onshore | Avila; Rafael | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056991 | No | Yes | No | Australia | Australia | 03-Design/Build | GBT_01-CONFIG-Filter Plant | PTP | FUN | SI | Onshore | Ruetz; Christoph | SAP | Yes | CapEx | Localization | IT - External | 3h | 0h | 3h | 2017-03-06 | 2017-03-07 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056992 | No | Yes | No | Australia | Australia | 03-Design/Build | GBT_02-CONFIG-Set Up from ERP | PTP | FUN | SI | Onshore | Ruetz; Christoph | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-04 | 2017-02-04 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056993 | No | Yes | No | Australia | Australia | 03-Design/Build | GBT_03-CONFIG-Tranfer Data from SAP ERP | PTP | FUN | SI | Onshore | Ruetz; Christoph | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-20 | 2017-02-20 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056994 | No | Yes | No | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | PTP | FUN | SI | Onshore | Ruetz; Christoph | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056995 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056996 | No | No | Yes | Australia | Australia | 03-Design/Build | AA_04-CONFIG FUT-Depreciation | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2017-03-01 | 2017-03-17 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 8 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056997 | No | No | Yes | Australia | Australia | 03-Design/Build | IO_03-CONFIG FUT-Internal Order Actual Postings | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 17h | 0h | 17h | 2017-02-23 | 2017-03-09 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056998 | No | No | Yes | Australia | Australia | 03-Design/Build | IO_04-CONFIG FUT-Internal Orders as Investment Measures | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-02-24 | 2017-02-24 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056999 | No | No | Yes | Australia | Australia | 03-Design/Build | PE_01-CONFIG FUT-Period End Processing | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2017-03-24 | 2017-04-07 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057000 | No | No | Yes | Australia | Australia | 03-Design/Build | AA_05-CONFIG FUT-Master Data | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-02-22 | 2017-02-22 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057001 | No | No | Yes | Australia | Australia | 03-Design/Build | AA_06-CONFIG FUT-Asset Data Transfer | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 30h | 0h | 30h | 2017-03-07 | 2017-03-16 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057002 | No | No | Yes | Australia | Australia | 03-Design/Build | PE_01-CONFIG-Period End Processing | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2017-03-13 | 2017-03-31 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057003 | No | No | Yes | Australia | Australia | 03-Design/Build | AA_04-CONFIG-Depreciation | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057004 | No | No | Yes | Australia | Australia | 03-Design/Build | OI_01-CONFIG-Internal Order | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057005 | No | No | Yes | Australia | Australia | 03-Design/Build | IO_03-CONFIG-Internal Order Actual Postings | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057006 | No | No | Yes | Australia | Australia | 03-Design/Build | IO_04-CONFIG-Internal Orders as Investment Measures | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057007 | No | No | Yes | Australia | Australia | 03-Design/Build | AA_01-CONFIG-Organization Structure | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 7h | 0h | 7h | 2017-02-14 | 2017-02-17 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057008 | No | No | Yes | Australia | Australia | 03-Design/Build | AA_02-CONFIG-Integration with General Ledger Accounting | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2017-02-15 | 2017-02-17 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057009 | No | No | Yes | Australia | Australia | 03-Design/Build | AA_03-CONFIG-General Valuation | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057010 | No | No | Yes | Australia | Australia | 03-Design/Build | AA_05-CONFIG-Master Data | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057011 | No | No | Yes | Australia | Australia | 03-Design/Build | AA_06-CONFIG-Asset Data Transfer | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057012 | No | No | Yes | Australia | Australia | 06-Hypercare | Management (Hypercare) - RTR | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 56h | 0h | 56h | 2017-06-26 | 2017-09-03 | Yes |  |  | ACT.DEV.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 10 | 5 | 10 | 5 | 7 | 0 | 4 | 5 | 0 | 0 | 0
1057013 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Management (Cutover/Go-live) | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-06-22 | 2017-06-30 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057014 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Preparation | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2017-03-22 | 2017-04-21 | Yes |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3 | 9 | 27 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057015 | No | No | Yes | Australia | Australia | 03-Design/Build | KT sessions (D/B) | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 30h | 0h | 30h | 2017-03-17 | 2017-06-09 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 3 | 0 | 0 | 0 | 0 | 6 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057016 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Prepare - RTR | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-06-23 | 2017-06-23 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057017 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - RTR | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-06-23 | 2017-06-23 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057018 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_02-CONFIG-Fiscal Year and Posting periods | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-02-01 | 2017-02-17 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057019 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_06-CONFIG-GL Assignment | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057020 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_05-CONFIG-GL Maintenance | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-02-02 | 2017-02-03 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057021 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_04-CONFIG-GL-General Settings | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-02-13 | 2017-02-17 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057022 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_03-CONFIG-New General Ledger | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-02-07 | 2017-02-13 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057023 | No | No | Yes | Australia | Australia | 03-Design/Build | OI_02-CONFIG-Internal Order Planning | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057024 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_08-CONFIG-Cancelled | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057025 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_07-CONFIG-Cancelled | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057026 | No | No | Yes | Australia | Australia | 03-Design/Build | AA_02-CONFIG FUT-Integration with General Ledger Accounting | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-02-27 | 2017-02-28 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057027 | No | No | Yes | Australia | Australia | 03-Design/Build | AA_03-CONFIG FUT-General Valuation | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 17h | 0h | 17h | 2017-02-28 | 2017-03-10 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057028 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_01-CONFIG-Definition and assignment of Organization structure | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2017-01-30 | 2017-02-09 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057029 | No | No | Yes | Australia | Australia | 04-Test | Management (Test) - RTR | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 34h | 0h | 34h | 2017-04-24 | 2017-06-09 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057030 | No | No | Yes | Australia | Australia | 03-Design/Build | AA_01-CONFIG FUT-Organization Structure | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-02-20 | 2017-03-10 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057031 | No | No | Yes | Australia | Australia | 03-Design/Build | OI_02-CONFIG FUT-Internal Order Planning | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-03-01 | 2017-03-01 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057032 | No | No | Yes | Australia | Australia | 03-Design/Build | OI_01-CONFIG FUT-Internal Order | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2017-02-28 | 2017-03-02 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057033 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_08-CONFIG FUT-Cancelled | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-20 | 2017-01-20 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057034 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_07-CONFIG FUT-Cancelled | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-20 | 2017-01-20 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057035 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_06-CONFIG FUT-GL Assignment | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057036 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_05-CONFIG FUT-GL Maintenance | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-10 | 2017-02-10 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057037 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_04-CONFIG FUT-GL-General Settings | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057038 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_03-CONFIG FUT-New General Ledger | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057039 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_02-CONFIG FUT-Fiscal Year and Posting periods | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2017-02-06 | 2017-02-07 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057040 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_01-CONFIG FUT-Definition and assignment of Organization structure | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-02-06 | 2017-02-17 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057041 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Break/Fix - RTR | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 39h | 0h | 39h | 2017-05-02 | 2017-06-06 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 0 | 1 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057042 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 109h | 0h | 109h | 2017-04-24 | 2017-05-14 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 37 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057043 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - RTR | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-05-17 | 2017-06-09 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 6 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057044 | No | No | Yes | Australia | Australia | 04-Test | Regression - Run Tests - RTR | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-05-17 | 2017-06-06 | Yes |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057045 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - RTR | RTR | FUN | SI | Offshore | Kumthekar; Minal | IBM | Yes | CapEx | Localization | IT - External | 42h | 0h | 42h | 2017-05-15 | 2017-06-02 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 8 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057046 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-FSD-Australia Pricing routine Incentives/Premiums 5 | PTP | FUN | SI | Onshore | Pethtel; Melanie | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057047 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-FSD-Australia Pricing routine Incentives/Premiums 2 | PTP | FUN | SI | Onshore | Pethtel; Melanie | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057048 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-FSD-Pricing routine 6 | PTP | FUN | SI | Onshore | Pethtel; Melanie | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057049 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-FSD-Pricing routine 3 | PTP | FUN | SI | Onshore | Pethtel; Melanie | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057050 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Australia Pricing routine Surcharge 1 | PTP | FUN | SI | Onshore | Pethtel; Melanie | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057051 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-FSD-Australia Pricing routine Surcharge 1 | PTP | FUN | SI | Onshore | Pethtel; Melanie | SAP | Yes | CapEx | Localization | IT - External | 80h | 0h | 80h | 2017-02-13 | 2017-02-24 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057052 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Australia Pricing routine Incentives/Premiums 5 | PTP | FUN | SI | Onshore | Pethtel; Melanie | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057053 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Australia Pricing routine Incentives/Premiums 2 | PTP | FUN | SI | Onshore | Pethtel; Melanie | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057054 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Argentina Pricing routine 6 | PTP | FUN | SI | Onshore | Pethtel; Melanie | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057055 | No | No | Yes | Australia | Australia | 03-Design/Build | MCP-DEV FUT-Argentina Pricing routine 3 | PTP | FUN | SI | Onshore | Pethtel; Melanie | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057056 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | PTP | FUN | SI | Onshore | Pethtel; Melanie | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057057 | No | No | Yes | Australia | Australia | 03-Design/Build | PDD-Manage Farm Settlement & Statements | PTP | FUN | SI | Onshore | Pethtel; Melanie | SAP | Yes | CapEx | Localization | IT - External | 34h | 0h | 34h | 2017-01-30 | 2017-02-09 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057058 | No | No | Yes | Australia | Australia | 04-Test | Training Schedule-Course Offerings (Test) | Test | Test | Saputo | Onshore | Wong; Justin | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | DELIV.CM-402.Training Schedule and Logistics | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057059 | No | No | Yes | Australia | Australia | 04-Test | Training Schedule-End-User Enrollments (Test) | Test | Test | Saputo | Onshore | Wong; Justin | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  | DELIV.CM-402.Training Schedule and Logistics | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057060 | No | No | Yes | Australia | Australia | 06-Hypercare | Train end-users (HYP) | Test | Test | Saputo | Onshore | Wong; Justin | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | ACT.CM.Deliver Training to End Users | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057061 | No | No | Yes | Australia | Australia | 06-Hypercare | Development (Hypercare) - DEV | DEV | DEV | SI | Offshore | Singh; Virender | IBM | Yes | CapEx | Localization | IT - External | 145h | 0h | 145h | 2017-07-03 | 2017-07-28 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 50 | 19 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057062 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Development (Cutover/Go-live) - DEV | DEV | DEV | SI | Offshore | Singh; Virender | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2017-06-12 | 2017-06-14 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057063 | No | No | Yes | Australia | Australia | 03-Design/Build | Development (D/B) | DEV | DEV | SI | Offshore | Singh; Virender | IBM | Yes | CapEx | Localization | IT - External | 185h | 0h | 185h | 2017-03-02 | 2017-04-12 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 13 | 20 | 45 | 45 | 36 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057064 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT1) | DEV | DEV | SI | Offshore | Singh; Virender | IBM | Yes | CapEx | Localization | IT - External | 19h | 0h | 19h | 2017-04-24 | 2017-05-26 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057065 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT2) | DEV | DEV | SI | Offshore | Singh; Virender | IBM | Yes | CapEx | Localization | IT - External | 42h | 0h | 42h | 2017-05-30 | 2017-06-14 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057066 | No | No | Yes | Australia | Australia |  | AUS - DEV KT | DEV | DEV | SI | Offshore | Singh; Virender | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-31 | 2017-05-31 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057067 | No | No | Yes | Australia | Australia |  | AUS - DEV KT | DEV | DEV | SI | Offshore | Subhedar; Adheesh | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-31 | 2017-05-31 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057068 | No | No | Yes | Australia | Australia | 03-Design/Build | Development (D/B) | DEV | DEV | SI | Offshore | Subhedar; Adheesh | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057069 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT1) | DEV | DEV | SI | Offshore | Subhedar; Adheesh | IBM | Yes | CapEx | Localization | IT - External | 7h | 0h | 7h | 2017-04-24 | 2017-04-24 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057070 | No | No | Yes | Australia | Australia | 06-Hypercare | Development (Hypercare) - DEV | DEV | DEV | SI | Offshore | Subhedar; Adheesh | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2017-07-03 | 2017-08-18 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
1057071 | No | Yes | No | Australia | Australia | 01-Preparation | Coduct KT Sessions (Accenture)- DM) (PP) | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2016-10-17 | 2016-10-19 | Yes |  |  | ACT.MDG.Workshop | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057072 | No | Yes | No | Australia | Australia | 03-Design/Build | Localization Customer (Accenture) - DM (D/B) | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 133h | 0h | 133h | 2017-01-30 | 2017-04-21 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 8 | 11 | 12 | 20 | 20 | 12 | 0 | 0 | 18 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057073 | No | Yes | No | Australia | Australia | 03-Design/Build | Localization Vendor - DM (D/B) | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 133h | 0h | 133h | 2017-01-30 | 2017-04-21 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 8 | 11 | 12 | 20 | 20 | 12 | 0 | 0 | 18 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057074 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | UAT - Customer Master - SI - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2017-06-14 | 2017-06-16 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057075 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | UAT - Vendor Master - SI - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-15 | 2017-06-15 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057076 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Cutover - Customer Master - SI - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2017-06-19 | 2017-06-28 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057077 | No | Yes | No | Australia | Australia | 03-Design/Build | Test preparation (Accenture) - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 33h | 0h | 33h | 2017-04-10 | 2017-06-02 | Yes |  |  | DELIV.TST-307.Assembly Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 11 | 0 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057078 | No | Yes | No | Australia | Australia | 06-Hypercare | HC - Manage defects - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-03 | 2017-07-07 | Yes |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057079 | No | Yes | No | Australia | Australia | 04-Test | Test Preparation (Accenture) - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-04-19 | 2017-05-09 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 10 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057080 | No | Yes | No | Australia | Australia | 06-Hypercare | HC - Break/Fix - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057081 | No | Yes | No | Australia | Australia | 04-Test | Harmoni Program Governance and Cross Functional Work (Accenture) - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 26h | 0h | 26h | 2017-05-26 | 2017-06-30 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 7 | 2 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057082 | No | Yes | No | Australia | Australia | 04-Test | Documentation and Program Work (Accenture) - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 23h | 0h | 23h | 2017-04-03 | 2017-06-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 2 | 3 | 5 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057083 | No | Yes | No | Australia | Australia | 03-Design/Build | Update BWL MM (Accenture) - DM (D/B) | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057084 | No | Yes | No | Australia | Australia | 04-Test | SIT 2 - Run tests (Accenture) - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 53h | 0h | 53h | 2017-05-15 | 2017-05-26 | Yes |  |  | ACT.MDG.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057085 | No | Yes | No | Australia | Australia | 04-Test | SIT 1 - Run tests (Accenture) - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 59h | 0h | 59h | 2017-04-28 | 2017-05-14 | Yes |  |  | ACT.MDG.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057086 | No | Yes | No | Australia | Australia | 02-Analyze | Data Construction and staging (Accenture) - DM (AN) | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 76h | 0h | 76h | 2016-12-19 | 2017-01-27 | Yes |  |  | ACT.MDG.Data Construction | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 16 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057087 | No | Yes | No | Australia | Australia | 06-Hypercare | HC - Customer Master - SI - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 34h | 0h | 34h | 2017-07-03 | 2017-07-28 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057088 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Cutover - Vendor Master - SI - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-06-19 | 2017-06-28 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057089 | No | Yes | No | Australia | Australia | 06-Hypercare | HC - Vendor Master - SI - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2017-07-03 | 2017-07-28 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 8 | 7 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057090 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | Cutover - Prepare - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 17h | 0h | 17h | 2017-06-12 | 2017-06-15 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057091 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | UAT - Document work around (Accenture) - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057092 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix (Accenture) - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2017-06-05 | 2017-06-09 | Yes |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057093 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | UAT - Manage Defects (Accenture) (Capex) - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2017-06-05 | 2017-06-16 | Yes |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057094 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests (Accenture) - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  | ACT.MDG.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057095 | No | Yes | No | Australia | Australia | 05-Cutover/Go-live | UAT - Prep (Select Scenarios) (Accenture) - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2017-05-10 | 2017-06-02 | Yes |  |  | ACT.MDG.UAT Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057096 | No | Yes | No | Australia | Australia | 04-Test | Non Regression - Manage defects (Capex) (Accenture) MDG - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-05-15 | 2017-05-19 | Yes |  |  | ACT.MDG.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057097 | No | Yes | No | Australia | Australia | 04-Test | Non Regression - Run tests (Accenture) - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-18 | 2017-05-19 | Yes |  |  | ACT.MDG.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057098 | No | Yes | No | Australia | Australia | 04-Test | Retrofit Testing (Accenture) - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-05-15 | 2017-05-24 | Yes |  |  | ACT.MDG.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057099 | No | Yes | No | Australia | Australia | 04-Test | Functional Testing (Accenture) - DM | MDG | DM | SI | Onshore | Ottenstein; David | Accenture | Yes | CapEx | Localization | IT - External | 46h | 0h | 46h | 2017-04-24 | 2017-05-05 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057100 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - LOG | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 88h | 0h | 88h | 2017-07-10 | 2017-07-21 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057101 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | LOG | FUN | SI | Landed Onshore | Mishra; Jagat | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-03-03 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057102 | No | No | Yes | Australia | Australia | 04-Test | Data load - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 99h | 0h | 99h | 2017-03-20 | 2017-03-31 | Yes |  |  | ACT.MDG.Mock Load | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057103 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Validate - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | OpEx | Localization | IT - External | 27h | 0h | 27h | 2017-04-10 | 2017-04-12 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057104 | No | No | Yes | Australia | Australia | 04-Test | Mock1 – Manage defect (Capex) - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 70h | 0h | 70h | 2017-04-17 | 2017-05-05 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 25 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057105 | No | No | Yes | Australia | Australia | 04-Test | Data collection templates - explain and collect - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 179.5h | 0h | 179.5h | 2016-12-19 | 2017-03-13 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 39 | 48 | 74.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057106 | No | No | Yes | Australia | Australia | 02-Analyze | Data Construction and staging - DC (AN) | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 115h | 0h | 115h | 2016-10-24 | 2017-05-05 | Yes |  |  | ACT.MDG.Data Construction | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 47 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057107 | No | No | Yes | Australia | Australia | 02-Analyze | Kickoff - DC (AN) | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2016-11-21 | 2016-11-25 | Yes |  |  | ACT.MDG.Workshop | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057108 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Validate - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057109 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect (Capex) - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057110 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-04-24 | 2017-04-28 | Yes |  |  | ACT.MDG.Mock Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057111 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Execute - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 22.5h | 0h | 22.5h | 2017-05-08 | 2017-05-12 | Yes |  |  | ACT.MDG.Mock Load | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057112 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057113 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Prepare - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057114 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Support - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-12 | 2017-06-12 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057115 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect - DC | MDG | DC | SI | Offshore | Casipong; Joanna | Accenture | Yes | CapEx | Localization | IT - External | 22.5h | 0h | 22.5h | 2017-04-12 | 2017-05-12 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057116 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Support - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | OpEx | Localization | IT - External | 1.5h | 0h | 1.5h | 2017-07-02 | 2017-07-03 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057117 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 110h | 0h | 110h | 2017-05-22 | 2017-06-09 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 29 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057118 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Prepare - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | OpEx | Localization | IT - External | 41h | 0h | 41h | 2017-06-14 | 2017-06-18 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057119 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057120 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | ACT.MDG.Mock Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057121 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Execute - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 122h | 0h | 122h | 2017-05-08 | 2017-06-13 | Yes |  |  | ACT.MDG.Mock Load | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 45 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057122 | No | No | Yes | Australia | Australia | 06-Hypercare | HC - Manage defects - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-07-03 | 2017-07-03 | Yes |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057123 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect (Capex) - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-06-27 | 2017-06-30 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057124 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Validate - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | OpEx | Localization | IT - External | 36h | 0h | 36h | 2017-06-20 | 2017-06-23 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057125 | No | No | Yes | Australia | Australia | 02-Analyze | Kickoff - DC (AN) | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  | ACT.MDG.Workshop | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057126 | No | No | Yes | Australia | Australia | 02-Analyze | Data Construction and staging - DC (AN) | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 110h | 0h | 110h | 2016-12-19 | 2017-04-12 | Yes |  |  | ACT.MDG.Data Construction | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 0 | 0 | 36 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057127 | No | No | Yes | Australia | Australia | 04-Test | Mock1 – Manage defect (Capex) - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-04-17 | 2017-04-28 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057128 | No | No | Yes | Australia | Australia | 04-Test | Data collection templates - explain and collect - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 185h | 0h | 185h | 2016-12-19 | 2017-03-13 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 32 | 47 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057129 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Validate - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | OpEx | Localization | IT - External | 36h | 0h | 36h | 2017-05-01 | 2017-05-05 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057130 | No | No | Yes | Australia | Australia | 04-Test | Data load - DC | MDG | DC | SI | Offshore | Canada; Eriberta | Accenture | Yes | CapEx | Localization | IT - External | 100h | 0h | 100h | 2017-03-20 | 2017-03-31 | Yes |  |  | ACT.MDG.Mock Load | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057131 | No | No | Yes | Australia | Australia | 03-Design/Build | DMS_03-CONFIG-Dairy Mgmt System - Operations | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 93h | 0h | 93h | 2017-02-27 | 2017-04-28 | Yes |  | DMS | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 9 | 20 | 0 | 0 | 36 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057132 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD241-DMS - Record types | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 34h | 0h | 34h | 2017-02-27 | 2017-03-17 | Yes |  | DMS | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 6 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057133 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia - (Capex) - (D/B) | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  | DMS | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057134 | No | No | Yes | Australia | Australia | 01-Preparation | Conduct KT sessions) (PP) | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  | DMS | WP.FUN.Requirements/Process Design Workshop Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057135 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-26 | 2016-10-26 | Yes |  | DMS | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057136 | No | No | Yes | Australia | Australia | 03-Design/Build | DMS_02-CONFIG-Dairy Mgmt System - Planning | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  | DMS | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057137 | No | No | Yes | Australia | Australia | 04-Test | Regression - Run Tests - PTM | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  | DMS | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057138 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - PTM | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2017-05-22 | 2017-06-02 | Yes |  | DMS | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057139 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - PTM | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2017-05-22 | 2017-06-02 | Yes |  | DMS | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057140 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  | DMS | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057141 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Break/Fix - PTM | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 12h | 0h | 12h | 2017-04-24 | 2017-06-08 | Yes |  | DMS | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057142 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Support | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | OpEx | Localization | IT - External | 12h | 0h | 12h | 2017-03-27 | 2017-03-30 | Yes |  | DMS | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057143 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Validate | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-09 | 2017-03-14 | Yes |  | DMS | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057144 | No | No | Yes | Australia | Australia | 03-Design/Build | DMS_02-CONFIG FUT-Dairy Mgmt System - Planning | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  | DMS | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057145 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD239-DMS - Workstations | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 19h | 0h | 19h | 2017-02-27 | 2017-03-10 | Yes |  | DMS | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057146 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD238-DMS - Extended material master attibutes | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  | DMS | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057147 | No | No | Yes | Australia | Australia | 06-Hypercare | DMS HyperCare solution stabilization - PTM | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-07-03 | 2017-07-07 | Yes |  | DMS | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057148 | No | No | Yes | Australia | Australia | 04-Test | DMS SIT AUS - PTM | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 62h | 0h | 62h | 2017-05-02 | 2017-06-14 | Yes |  | DMS | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 12 | 10 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057149 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | DMS Cut Over - execute - PTM | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-06-27 | 2017-07-03 | Yes |  | DMS | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057150 | No | No | Yes | Australia | Australia | 03-Design/Build | Workshops - PTM - DMS (Dairy Management System) | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2017-03-27 | 2017-03-31 | Yes |  | DMS | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057151 | No | No | Yes | Australia | Australia | 03-Design/Build | DMS Configuration/UT - Operations AUS - PTM (D/B) | PTM | FUN | SI | Onshore | Weber; Lars | SAP | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-04-10 | 2017-04-28 | Yes |  | DMS | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 24 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057152 | No | Yes | No | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | LOG | FUN | SI | Onshore | Pascual; Diego | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057153 | No | No | Yes | Australia | Australia | 06-Hypercare | Hypercare - Support - TAI | TAI | TAI | SI | Onshore | Barman; Tapan | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-07-17 | 2017-07-21 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057154 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Support | TAI | TAI | SI | Onshore | Barman; Tapan | Accenture | Yes | CapEx | Localization | IT - External | 64h | 0h | 64h | 2017-06-12 | 2017-07-03 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057155 | No | No | Yes | Australia | Australia | 02-Analyze | PCR - 208 - Bring DataServices and Information Steward - TAI | TAI | TAI | SI | Onshore | Barman; Tapan | Accenture | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2016-11-21 | 2016-11-25 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057156 | No | No | Yes | Australia | Australia | 06-Hypercare | Development (Hypercare) - DEV | DEV | DEV | SI | Offshore | Agrawal; Purvi | IBM | Yes | CapEx | Localization | IT - External | 173h | 0h | 173h | 2017-07-03 | 2017-08-08 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 45 | 45 | 31 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
1057157 | No | No | Yes | Australia | Australia | 03-Design/Build | Development (D/B) | DEV | DEV | SI | Offshore | Agrawal; Purvi | IBM | Yes | CapEx | Localization | IT - External | 132h | 0h | 132h | 2017-02-24 | 2017-04-18 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 13 | 36 | 27 | 15 | 0 | 9 | 10 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057158 | No | No | Yes | Australia | Australia |  | AUS - DEV KT | DEV | DEV | SI | Offshore | Agrawal; Purvi | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-31 | 2017-05-31 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057159 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT1) | DEV | DEV | SI | Offshore | Agrawal; Purvi | IBM | Yes | CapEx | Localization | IT - External | 33h | 0h | 33h | 2017-05-12 | 2017-05-26 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057160 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Development (Cutover/Go-live) - DEV | DEV | DEV | SI | Offshore | Agrawal; Purvi | IBM | Yes | CapEx | Localization | IT - External | 54h | 0h | 54h | 2017-06-16 | 2017-07-03 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 4 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057161 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT2) | DEV | DEV | SI | Offshore | Agrawal; Purvi | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-05-31 | 2017-06-05 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057162 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Break/Fix - PTP | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 50.5h | 0h | 50.5h | 2017-04-24 | 2017-05-12 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 18 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057163 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 65.5h | 0h | 65.5h | 2017-04-24 | 2017-05-12 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 18 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057164 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - PTP | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 85.5h | 0h | 85.5h | 2017-05-15 | 2017-06-08 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 22.5 | 22.5 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057165 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - PTP | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-05-15 | 2017-05-26 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057166 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - PTP | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 68.5h | 0h | 68.5h | 2017-05-29 | 2017-06-16 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 18 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057167 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - PTP | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 82h | 0h | 82h | 2017-06-19 | 2017-07-07 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 39 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057168 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - PTP | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 194h | 0h | 194h | 2017-07-03 | 2017-08-25 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 43 | 45 | 0 | 0 | 0 | 36 | 35 | 0 | 0 | 0 | 0
1057169 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 172h | 0h | 172h | 2017-02-06 | 2017-03-31 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 22 | 22.5 | 20 | 17.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057170 | No | No | Yes | Australia | Australia | 03-Design/Build | Ariba Build/Configuration (D/B) | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 32.5h | 0h | 32.5h | 2017-04-17 | 2017-04-28 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057171 | No | No | Yes | Australia | Australia | 03-Design/Build | Finalize AUS Design Workshop Material Requierement (D/B) | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-03 | 2017-04-03 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057172 | No | No | Yes | Australia | Australia | 03-Design/Build | Ariba Unit Testing (D/B) | PTP | FUN | SI | Offshore | Borja; Roz | Accenture | Yes | CapEx | Localization | IT - External | 22.5h | 0h | 22.5h | 2017-04-17 | 2017-04-21 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057173 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | PTP | FUN | SI | Offshore | Ragusante; Paul | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057174 | No | No | Yes | Australia | Australia | 03-Design/Build | GTS_01-CONFIG-Global Trade Services - GTS Environment (out of scope) | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-02 | 2017-02-02 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057175 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-01-30 | 2017-02-03 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057176 | No | No | Yes | Australia | Australia | 03-Design/Build | CONFIG-TM_01-MM | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057177 | No | No | Yes | Australia | Australia | 03-Design/Build | KT sessions (D/B) | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 7h | 0h | 7h | 2017-04-10 | 2017-04-11 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057178 | No | No | Yes | Australia | Australia | 03-Design/Build | Reviewing AUS Configuration | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | OpEx | Localization | IT - External | 10h | 0h | 10h | 2017-03-27 | 2017-04-12 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057179 | No | No | Yes | Australia | Australia | 03-Design/Build | Reviewing AUS Design (D/B) | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2017-03-13 | 2017-03-30 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057180 | No | No | Yes | Australia | Australia | 03-Design/Build | Conversion AUS support (D/B) | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2017-03-06 | 2017-06-09 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 5 | 0 | 0 | 0 | 0 | 9 | 0 | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057181 | No | No | Yes | Australia | Australia | 03-Design/Build | Management (D/B) - RTR | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 255h | 0h | 255h | 2017-01-30 | 2017-04-28 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 28 | 18 | 27 | 34 | 34 | 18 | 24 | 18 | 8 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057182 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - RTR | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 16h | 0h | 16h | 2017-07-17 | 2017-08-24 | Yes |  |  | ACT.FUN.Functional Break/Fix | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 8 | 0 | 4 | 0 | 0 | 0 | 0
1057183 | No | No | Yes | Australia | Australia | 06-Hypercare | Management (Hypercare) - RTR | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 200h | 0h | 200h | 2017-06-26 | 2017-09-01 | Yes |  |  | ACT.DEV.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 30 | 35 | 0 | 36 | 24 | 12 | 8 | 0 | 0 | 0
1057184 | No | No | Yes | Australia | Australia | 01-Preparation | Worshop Preparation Decks) (PP) | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2016-10-12 | 2016-10-20 | Yes |  |  | WP.FUN-107.Workshop Preparation Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057185 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Management (Cutover/Go-live) | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 90h | 0h | 90h | 2017-06-12 | 2017-06-23 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057186 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - RTR | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-19 | 2017-06-19 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057187 | No | No | Yes | Australia | Australia | 01-Preparation | Conduct KT sessions) (PP) | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-29 | 2016-10-29 | Yes |  |  | WP.FUN.Requirements/Process Design Workshop Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057188 | No | No | Yes | Australia | Australia | 01-Preparation | Prepare KT) (PP) | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | OpEx | Localization | IT - External | 1h | 0h | 1h | 2016-10-19 | 2016-10-19 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057189 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix (Hypercare) - RTR | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 137h | 0h | 137h | 2017-07-04 | 2017-08-18 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 44 | 10 | 9 | 29 | 0 | 15 | 0 | 0 | 0 | 0 | 0
1057190 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD016-Fixed Assets | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057191 | No | No | Yes | Australia | Australia | 03-Design/Build | AA_06-CONFIG-Asset Data Transfer | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057192 | No | No | Yes | Australia | Australia | 03-Design/Build | AP_04-CONFIG-ERS Invoicing | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-17 | 2017-02-17 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057193 | No | No | Yes | Australia | Australia | 03-Design/Build | AA_04-CONFIG-Depreciation | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 7h | 0h | 7h | 2017-02-13 | 2017-02-17 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057194 | No | No | Yes | Australia | Australia | 03-Design/Build | AA_05-CONFIG-Master Data | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057195 | No | No | Yes | Australia | Australia | 03-Design/Build | IO_04-CONFIG-Internal Orders as Investment Measures | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2017-02-13 | 2017-02-14 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057196 | No | No | Yes | Australia | Australia | 03-Design/Build | AA_06-CONFIG FUT-Asset Data Transfer | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-28 | 2017-02-28 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057197 | No | No | Yes | Australia | Australia | 03-Design/Build | AP_04-CONFIG FUT-ERS Invoicing | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-17 | 2017-02-17 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057198 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Validate | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | OpEx | Localization | IT - External | 4h | 0h | 4h | 2017-04-10 | 2017-04-26 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057199 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Prepare | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | OpEx | Localization | IT - External | 1h | 0h | 1h | 2017-03-14 | 2017-03-29 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057200 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 31h | 0h | 31h | 2016-11-14 | 2016-12-02 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057201 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Support | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | OpEx | Localization | IT - External | 11h | 0h | 11h | 2017-04-06 | 2017-05-03 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057202 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Break/Fix - RTR | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 17h | 0h | 17h | 2017-04-26 | 2017-05-12 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057203 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - RTR | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 26h | 0h | 26h | 2017-05-23 | 2017-06-02 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057204 | No | No | Yes | Australia | Australia | 04-Test | Management (Test) - RTR | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 151h | 0h | 151h | 2017-05-01 | 2017-06-09 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 27 | 30 | 25 | 24 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057205 | No | No | Yes | Australia | Australia | 03-Design/Build | Configuration for Australia-Co code AU09 and AU10 | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057206 | No | No | Yes | Australia | Australia | 03-Design/Build | CONFIG FUT-Baseline (D/B) | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-12-13 | 2016-12-16 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057207 | No | No | Yes | Australia | Australia | 03-Design/Build | Support MDM (D/B) | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-03 | 2016-12-03 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057208 | No | No | Yes | Australia | Australia | 03-Design/Build | Contribute to Cut-over Planning (D/B) - RTR | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-11-22 | 2017-01-20 | Yes |  |  | ACT.FUN.Support Cutover plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057209 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - RTR | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 14h | 0h | 14h | 2017-05-23 | 2017-05-31 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057210 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-Baseline (D/B) | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057211 | No | No | Yes | Australia | Australia | 03-Design/Build | CONFIG-Baseline (D/B) | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-12-19 | 2016-12-19 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057212 | No | No | Yes | Australia | Australia | 03-Design/Build | SDD Writing | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 11h | 0h | 11h | 2017-04-10 | 2017-05-19 | Yes |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057213 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Perform Gap Resolution (AN) | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-21 | 2016-11-21 | Yes |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057214 | No | No | Yes | Australia | Australia | 02-Analyze | RTM (AN) | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-11-04 | 2017-01-18 | Yes |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057215 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Create BPML (AN) | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057216 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Log Gaps (AN) | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-11 | 2016-11-11 | Yes |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057217 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct Design Workshops (AN) | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2016-12-15 | 2016-12-15 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057218 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_02-CONFIG-Fiscal Year and Posting periods | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057219 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_03-CONFIG-New General Ledger | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057220 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_04-CONFIG-GL-General Settings | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057221 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_05-CONFIG-GL Maintenance | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-02 | 2017-02-02 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057222 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_06-CONFIG-GL Assignment | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057223 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_07-CONFIG-Cancelled | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057224 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_08-CONFIG-Cancelled | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057225 | No | No | Yes | Australia | Australia | 03-Design/Build | OI_01-CONFIG-Internal Order | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057226 | No | No | Yes | Australia | Australia | 03-Design/Build | OI_02-CONFIG-Internal Order Planning | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057227 | No | No | Yes | Australia | Australia | 03-Design/Build | AA_02-CONFIG-Integration with General Ledger Accounting | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 3h | 0h | 3h | 2017-02-14 | 2017-02-16 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057228 | No | No | Yes | Australia | Australia | 03-Design/Build | AA_03-CONFIG-General Valuation | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 14h | 0h | 14h | 2017-02-13 | 2017-02-28 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057229 | No | No | Yes | Australia | Australia | 03-Design/Build | IO_03-CONFIG-Internal Order Actual Postings | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2017-02-13 | 2017-02-13 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057230 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_01-CONFIG FUT-Definition and assignment of Organization structure | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057231 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_02-CONFIG FUT-Fiscal Year and Posting periods | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057232 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_03-CONFIG FUT-New General Ledger | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057233 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_04-CONFIG FUT-GL-General Settings | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057234 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_05-CONFIG FUT-GL Maintenance | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-10 | 2017-02-10 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057235 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_06-CONFIG FUT-GL Assignment | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057236 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_07-CONFIG FUT-Cancelled | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-20 | 2017-01-20 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057237 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_08-CONFIG FUT-Cancelled | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-20 | 2017-01-20 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057238 | No | No | Yes | Australia | Australia | 03-Design/Build | OI_01-CONFIG FUT-Internal Order | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-28 | 2017-02-28 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057239 | No | No | Yes | Australia | Australia | 03-Design/Build | OI_02-CONFIG FUT-Internal Order Planning | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-01 | 2017-03-01 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057240 | No | No | Yes | Australia | Australia | 03-Design/Build | GL_01-CONFIG-Definition and assignment of Organization structure | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057241 | No | No | Yes | Australia | Australia | 03-Design/Build | AA_01-CONFIG-Organization Structure | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2017-02-13 | 2017-02-17 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057242 | No | No | Yes | Australia | Australia | 03-Design/Build | PE_01-CONFIG-Period End Processing | RTR | FUN | SI | Onshore | Kristen; Lanoix | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-03-13 | 2017-03-31 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057243 | No | No | Yes | Australia | Australia | 02-Analyze | Milk global design gaps | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 103.5h | 0h | 103.5h | 2017-01-30 | 2017-02-10 | Yes |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 52.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057244 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GDXXX-Material Type ZMPN- Manufacturer Part Number | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057245 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD262-Material Type ZRET - Returnable packaging | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057246 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD261-MCP -Product Assigment | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057247 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD257-MCP - Processes | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 59h | 0h | 59h | 2017-01-16 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057248 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD258-MCP - Payment | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057249 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD260-MCP - Extended material master and or payment attibutes | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057250 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD259-MCP - Codes if needed | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057251 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Log Gaps (AN) | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | Yes |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057252 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-03-17 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057253 | No | No | Yes | Australia | Australia | 03-Design/Build | PDD-Manage Milk Swap Processes | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 42h | 0h | 42h | 2017-02-13 | 2017-02-17 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057254 | No | No | Yes | Australia | Australia | 01-Preparation | Prepare KT) (PP) | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057255 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Create BPML (AN) | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-03 | 2016-11-03 | Yes |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057256 | No | No | Yes | Australia | Australia | 02-Analyze | RTM (AN) | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 55h | 0h | 55h | 2016-10-26 | 2017-01-30 | Yes |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057257 | No | No | Yes | Australia | Australia | 01-Preparation | Conduct KT sessions) (PP) | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | Yes |  |  | WP.FUN.Requirements/Process Design Workshop Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057258 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 106h | 0h | 106h | 2016-11-14 | 2016-11-28 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057259 | No | No | Yes | Australia | Australia | 01-Preparation | Worshop Preparation Decks) (PP) | PTP | FUN | SI | Onshore | Vance; Darlene | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-10-19 | 2016-10-19 | Yes |  |  | WP.FUN-107.Workshop Preparation Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057260 | No | No | Yes | Australia | Australia |  | MDM Gouvernance - DG | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | OpEx | Localization | IT - Internal | 57h | 0h | 57h | 2017-05-01 | 2017-06-08 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 7 | 8 | 10 | 7 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057261 | No | No | Yes | Australia | Australia |  | Data Governance – Change Process - DG | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | OpEx | Localization | IT - Internal | 38h | 0h | 38h | 2017-05-01 | 2017-06-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 4 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057262 | No | No | Yes | Australia | Australia |  | Data Governance – Change Process - DG | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | OpEx | Localization | IT - Internal | 150h | 0h | 150h | 2017-01-17 | 2017-08-03 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 12 | 4 | 4 | 6 | 8 | 8 | 3 | 4 | 4 | 12 | 6 | 8 | 0 | 0 | 2 | 0 | 0 | 2 | 3 | 0 | 10 | 10 | 12 | 10 | 6 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057263 | No | No | Yes | Australia | Australia |  | Policies, Standards, Business Rules and Metrics - DG | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | OpEx | Localization | IT - Internal | 302h | 0h | 302h | 2016-12-13 | 2017-08-03 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 16 | 10 | 7 | 15 | 16 | 13 | 18 | 22 | 0 | 7 | 5 | 8 | 6 | 10 | 8 | 6 | 26 | 26 | 19 | 12 | 21 | 2 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057264 | No | No | Yes | Australia | Australia |  | Data quality - DG | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | OpEx | Localization | IT - Internal | 175h | 0h | 175h | 2016-12-15 | 2017-08-11 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 15 | 3 | 14 | 9 | 8 | 6 | 5 | 5 | 8 | 8 | 5 | 4 | 6 | 5 | 5 | 4 | 2 | 7 | 7 | 4 | 7 | 6 | 2 | 4 | 20 | 0 | 0 | 0 | 0 | 0 | 0
1057265 | No | No | Yes | Australia | Australia | 03-Design/Build | MDM Gouvernance (D/B) - DG | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | OpEx | Localization | IT - Internal | 83h | 0h | 83h | 2017-03-01 | 2017-04-28 | Yes |  |  | ACT.MDG.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 11 | 10 | 8 | 3 | 10 | 12 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057266 | No | No | Yes | Australia | Australia | 03-Design/Build | MDM Project Management (D/B) - DG | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | OpEx | Localization | IT - Internal | 44h | 0h | 44h | 2017-03-13 | 2017-04-07 | Yes |  |  | ACT.MDG.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4 | 11 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057267 | No | No | Yes | Australia | Australia | 02-Analyze | MDM Project Management (Analyse) - DG (AN) | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | OpEx | Localization | IT - Internal | 59.5h | 0h | 59.5h | 2016-11-14 | 2017-03-10 | Yes |  |  | ACT.MDG.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 6 | 6 | 3 | 2 | 0 | 7 | 6 | 1 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057268 | No | No | Yes | Australia | Australia | 02-Analyze | MDM Gouvernance (Analyse) - DG (AN) | MDG | DG | Saputo | Onshore | Berntsen; Robert | Saputo | Yes | OpEx | Localization | IT - Internal | 127h | 0h | 127h | 2016-11-14 | 2017-03-14 | Yes |  |  | ACT.MDG.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 22 | 0 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 2 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057269 | No | Yes | No | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | PTP | FUN | SI | Onshore | Fernandez; Pablo | IBM | Yes | CapEx | Localization | IT - External | 31h | 0h | 31h | 2017-01-23 | 2017-03-03 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057270 | No | No | Yes | Australia | Australia | 02-Analyze | Data Construction and staging - DC (AN) | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 293h | 0h | 293h | 2017-02-20 | 2017-03-24 | Yes |  |  | ACT.MDG.Data Construction | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 52 | 90 | 57 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057271 | No | No | Yes | Australia | Australia | 02-Analyze | Kickoff - DC (AN) | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  | ACT.MDG.Workshop | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057272 | No | No | Yes | Australia | Australia | 04-Test | Data load - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 117h | 0h | 117h | 2017-03-27 | 2017-04-07 | Yes |  |  | ACT.MDG.Mock Load | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057273 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Validate - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | OpEx | Localization | IT - External | 43h | 0h | 43h | 2017-04-10 | 2017-04-13 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057274 | No | No | Yes | Australia | Australia | 04-Test | Mock1 – Manage defect (Capex) - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 81h | 0h | 81h | 2017-04-17 | 2017-04-28 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057275 | No | No | Yes | Australia | Australia | 04-Test | Data collection templates - explain and collect - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2016-12-19 | 2017-02-17 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057276 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect (Capex) - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 56h | 0h | 56h | 2017-06-26 | 2017-06-30 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057277 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Validate - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | OpEx | Localization | IT - External | 51h | 0h | 51h | 2017-06-12 | 2017-06-16 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057278 | No | No | Yes | Australia | Australia | 06-Hypercare | HC - Manage defects - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-07-12 | 2017-07-13 | Yes |  |  | ACT.MDG.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057279 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 74h | 0h | 74h | 2017-05-01 | 2017-06-02 | Yes |  |  | ACT.MDG.Mock Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057280 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Validate - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 96h | 0h | 96h | 2017-05-08 | 2017-05-18 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057281 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Execute - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-05-22 | 2017-05-25 | Yes |  |  | ACT.MDG.Mock Load | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057282 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Prepare - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057283 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Manage Defect - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | CapEx | Localization | IT - External | 45h | 0h | 45h | 2017-06-05 | 2017-06-09 | Yes |  |  | ACT.MDG.Mock Validation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057284 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cutover - Support - DC | MDG | DC | SI | Offshore | Espina; Milagros | Accenture | Yes | OpEx | Localization | IT - External | 54h | 0h | 54h | 2017-06-19 | 2017-06-25 | Yes |  |  | ACT.MDG.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057285 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Development (Cutover/Go-live) - DEV | DEV | DEV | SI | Offshore | Tayal; Nidhi | IBM | Yes | CapEx | Localization | IT - External | 47h | 0h | 47h | 2017-06-12 | 2017-06-30 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 21 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057286 | No | No | Yes | Australia | Australia | 06-Hypercare | Development (Hypercare) - DEV | DEV | DEV | SI | Offshore | Tayal; Nidhi | IBM | Yes | CapEx | Localization | IT - External | 238h | 0h | 238h | 2017-07-03 | 2017-08-18 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 63 | 54 | 45 | 15 | 5 | 2 | 0 | 0 | 0 | 0 | 0
1057287 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT1) | DEV | DEV | SI | Offshore | Tayal; Nidhi | IBM | Yes | CapEx | Localization | IT - External | 39h | 0h | 39h | 2017-04-28 | 2017-06-16 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 15 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057288 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT2) | DEV | DEV | SI | Offshore | Tayal; Nidhi | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057289 | No | No | Yes | Australia | Australia |  | AUS - DEV KT | DEV | DEV | SI | Offshore | Tayal; Nidhi | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-31 | 2017-05-31 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057290 | No | No | Yes | Australia | Australia | 03-Design/Build | Development (D/B) | DEV | DEV | SI | Offshore | Tayal; Nidhi | IBM | Yes | CapEx | Localization | IT - External | 267h | 0h | 267h | 2017-03-16 | 2017-06-01 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.5 | 39 | 34 | 35 | 36 | 68 | 12 | 0 | 0 | 0 | 0 | 27.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057291 | No | Yes | No | Australia | Australia |  | AUS - DEV KT | DEV | DEV | SI | Offshore | Dipankar; Saha | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-31 | 2017-05-31 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057292 | No | No | Yes | Australia | Australia |  | AUS - DEV KT | DEV | DEV | SI | Offshore | Agarwal; Khushbu | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-31 | 2017-05-31 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057293 | No | No | Yes | Australia | Australia | 03-Design/Build | Development (D/B) | DEV | DEV | SI | Offshore | Agarwal; Khushbu | IBM | Yes | CapEx | Localization | IT - External | 259h | 0h | 259h | 2017-02-13 | 2017-06-16 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 12 | 36 | 20 | 18 | 42 | 36 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057294 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT1) | DEV | DEV | SI | Offshore | Agarwal; Khushbu | IBM | Yes | CapEx | Localization | IT - External | 77.2h | 0h | 77.2h | 2017-04-24 | 2017-05-19 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 16 | 7.2 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057295 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Development (Cutover/Go-live) - DEV | DEV | DEV | SI | Offshore | Agarwal; Khushbu | IBM | Yes | CapEx | Localization | IT - External | 27h | 0h | 27h | 2017-06-05 | 2017-06-07 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057296 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT2) | DEV | DEV | SI | Offshore | Agarwal; Khushbu | IBM | Yes | CapEx | Localization | IT - External | 62.7h | 0h | 62.7h | 2017-05-22 | 2017-06-04 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 47.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057297 | No | No | Yes | Australia | Australia | 06-Hypercare | Development (Hypercare) - DEV | DEV | DEV | SI | Offshore | Agarwal; Khushbu | IBM | Yes | CapEx | Localization | IT - External | 108.5h | 0h | 108.5h | 2017-07-03 | 2017-07-31 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 45 | 34 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057298 | No | No | Yes | Australia | Australia |  | MDM Project Management (Saputo) - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 270h | 0h | 270h | 2017-06-05 | 2017-07-07 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 60 | 48 | 48 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057299 | No | No | Yes | Australia | Australia | 03-Design/Build | Training Train-the-Trainer Finance - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057300 | No | No | Yes | Australia | Australia | 01-Preparation | Prepare Kickoff (Saputo) - DM (PP) | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 2h | 0h | 2h | 2016-09-19 | 2016-10-31 | Yes |  |  | ACT.MDG.Workshop | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057301 | No | No | Yes | Australia | Australia | 03-Design/Build | Design Material Master MDG (Saputo) - DM (D/B) | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 78h | 0h | 78h | 2017-01-23 | 2017-03-10 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 15 | 15 | 15 | 10 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057302 | No | No | Yes | Australia | Australia | 03-Design/Build | Offline Process Financial Object - Australia Review (Saputo) - DM (D/B) | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  | DELIV.FUN-601.Process Workarounds | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057303 | No | No | Yes | Australia | Australia | 03-Design/Build | Training - Update Concept Slide Finance - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057304 | No | No | Yes | Australia | Australia | 03-Design/Build | MDM Project Management (D/B)- DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 5h | 0h | 5h | 2016-12-12 | 2016-12-16 | Yes |  |  | ACT.MDG.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057305 | No | No | Yes | Australia | Australia | 02-Analyze | MDM Gouvernance (Analyse) (Saputo) - DM (AN) | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 15h | 0h | 15h | 2016-12-19 | 2017-03-10 | Yes |  |  | ACT.MDG.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057306 | No | No | Yes | Australia | Australia | 03-Design/Build | MDM Gouvernance (D/B) (Saputo) - DM | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 361h | 0h | 361h | 2017-02-20 | 2017-05-05 | Yes |  |  | ACT.MDG.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 48 | 15 | 48 | 0 | 48 | 48 | 48 | 0 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057307 | No | No | Yes | Australia | Australia | 02-Analyze | MDM Project Management (Analyse) (Saputo) - DM (AN) | MDG | DM | Saputo | Onshore | Larios; Sandra | Saputo | Yes | OpEx | Localization | IT - Internal | 169h | 0h | 169h | 2016-11-14 | 2017-02-24 | Yes |  |  | ACT.MDG.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 24 | 0 | 0 | 25 | 10 | 25 | 25 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057308 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Development (Cutover/Go-live) - DEV | DEV | DEV | SI | Offshore | Kalra; Inderjeet | IBM | Yes | CapEx | Localization | IT - External | 105h | 0h | 105h | 2017-06-02 | 2017-06-30 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 24 | 28 | 27 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057309 | No | No | Yes | Australia | Australia | 06-Hypercare | Development (Hypercare) - DEV | DEV | DEV | SI | Offshore | Kalra; Inderjeet | IBM | Yes | CapEx | Localization | IT - External | 253h | 0h | 253h | 2017-07-01 | 2017-08-22 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 52 | 48 | 42 | 39 | 27 | 0 | 20 | 8 | 0 | 0 | 0 | 0
1057310 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT2) | DEV | DEV | SI | Offshore | Kalra; Inderjeet | IBM | Yes | CapEx | Localization | IT - External | 86h | 0h | 86h | 2017-05-15 | 2017-06-02 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 23 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057311 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT1) | DEV | DEV | SI | Offshore | Kalra; Inderjeet | IBM | Yes | CapEx | Localization | IT - External | 62h | 0h | 62h | 2017-04-24 | 2017-05-10 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 21 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057312 | No | No | Yes | Australia | Australia |  | AUS - DEV KT | DEV | DEV | SI | Offshore | Kalra; Inderjeet | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-31 | 2017-05-31 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057313 | No | No | Yes | Australia | Australia | 03-Design/Build | Development (D/B) | DEV | DEV | SI | Offshore | Kalra; Inderjeet | IBM | Yes | CapEx | Localization | IT - External | 232h | 0h | 232h | 2017-03-06 | 2017-04-21 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 40 | 35 | 32 | 32 | 26 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057314 | No | No | Yes | Australia | Australia | 03-Design/Build | Development (D/B) | DEV | DEV | SI | Offshore | Prakash; Gaurav | IBM | Yes | CapEx | Localization | IT - External | 167.5h | 0h | 167.5h | 2017-02-17 | 2017-04-27 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 3 | 7 | 22 | 24 | 13 | 25 | 25 | 22 | 18 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057315 | No | No | Yes | Australia | Australia |  | AUS - DEV KT | DEV | DEV | SI | Offshore | Prakash; Gaurav | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-31 | 2017-05-31 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057316 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT1) | DEV | DEV | SI | Offshore | Prakash; Gaurav | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-06-08 | 2017-06-08 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057317 | No | No | Yes | Australia | Australia | 04-Test | Development (SIT2) | DEV | DEV | SI | Offshore | Prakash; Gaurav | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057318 | No | No | Yes | Australia | Australia | 06-Hypercare | Development (Hypercare) - DEV | DEV | DEV | SI | Offshore | Prakash; Gaurav | IBM | Yes | CapEx | Localization | IT - External | 230h | 0h | 230h | 2017-07-03 | 2017-09-13 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 63 | 54 | 45 | 0 | 1 | 0 | 0 | 0 | 4 | 9 | 0
1057319 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Development (Cutover/Go-live) - DEV | DEV | DEV | SI | Offshore | Prakash; Gaurav | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-02 | 2017-06-02 | Yes |  |  | ACT.DEV.Execute Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057320 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Prepare | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | OpEx | Localization | Business | 71h | 0h | 71h | 2017-02-06 | 2017-03-31 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 5 | 40 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057321 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia(D/B) | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 30h | 0h | 30h | 2017-01-30 | 2017-02-24 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 20 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057322 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Preparation | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 65h | 0h | 65h | 2017-03-13 | 2017-04-13 | Yes |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 7 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057323 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Support | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | OpEx | Localization | Business | 33h | 0h | 33h | 2017-03-27 | 2017-04-13 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 15 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057324 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Validate | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | OpEx | Localization | Business | 14h | 0h | 14h | 2017-04-10 | 2017-04-21 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057325 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 35h | 0h | 35h | 2017-04-24 | 2017-05-12 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 15 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057326 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - OTC | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 36h | 0h | 36h | 2017-05-15 | 2017-05-26 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057327 | No | No | Yes | Australia | Australia | 04-Test | Regression - Run Tests - OTC | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 5h | 0h | 5h | 2017-05-15 | 2017-05-19 | Yes |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057328 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD117-Customer Master - Direct customers (SP,SH,BP,PY) | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 10h | 0h | 10h | 2017-01-30 | 2017-02-03 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057329 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD118-Customer Master - Indirect Customers (End-User) | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 15h | 0h | 15h | 2017-01-23 | 2017-01-27 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057330 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD127-Customer Hierarchy - Assignment | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-25 | 2017-01-25 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057331 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD126-Customer Hierarchy - Nodes | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 5h | 0h | 5h | 2017-01-23 | 2017-01-27 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057332 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD125-Customer Master - One time customers | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057333 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD124-Customer Master - Financial Customers / Farmers | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057334 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD122-Customer Master - EDI Trading Partners | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057335 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD121-Customer Master - Inter/Intra-company | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057336 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD120-Customer Master - Ports | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057337 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD119-Customer Master - Brokers | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057338 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD145-Sales, Delivery and Billing pre-defined Texts | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057339 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD139-Customer Material Info Record | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 5h | 0h | 5h | 2017-01-24 | 2017-02-03 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057340 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - OTC | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 42h | 0h | 42h | 2017-06-26 | 2017-07-07 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057341 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - OTC | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 88h | 0h | 88h | 2017-06-05 | 2017-06-23 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 45 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057342 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - OTC | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 37h | 0h | 37h | 2017-06-05 | 2017-06-23 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057343 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Prep | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 13h | 0h | 13h | 2017-05-19 | 2017-06-09 | Yes |  |  | ACT.FUN.UAT Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057344 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - OTC | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 59h | 0h | 59h | 2017-07-10 | 2017-08-03 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 20 | 20 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057345 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix - OTC | OTC | FUN | Saputo | Onshore | Kotlikova; Olga | Saputo | Yes | CapEx | Localization | Business | 65h | 0h | 65h | 2017-07-10 | 2017-08-04 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 20 | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057346 | No | No | Yes | Australia | Australia | 06-Hypercare | Management (Hypercare) - OTC | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 100h | 0h | 100h | 2017-07-10 | 2017-09-01 | Yes |  |  | ACT.DEV.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 30 | 35 | 0 | 0 | 0 | 10 | 5 | 0 | 0 | 0
1057347 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Management (Cutover/Go-live) | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 76h | 0h | 76h | 2017-06-05 | 2017-06-29 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057348 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia(D/B) | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 15h | 0h | 15h | 2017-01-30 | 2017-02-03 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057349 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Log Gaps (AN) | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 5h | 0h | 5h | 2016-12-05 | 2017-01-20 | Yes |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057350 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Create BPML (AN) | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | DELIV.BPM-001.Business Process Master List (BPML) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057351 | No | No | Yes | Australia | Australia | 01-Preparation | Prepare KT (Saputo)) (PP) | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 5h | 0h | 5h | 2016-09-19 | 2016-09-23 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057352 | No | No | Yes | Australia | Australia | 04-Test | Management (Test) - OTC | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 56h | 0h | 56h | 2017-04-24 | 2017-06-09 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 3 | 10 | 15 | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057353 | No | No | Yes | Australia | Australia | 03-Design/Build | Management (D/B) | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 150h | 0h | 150h | 2017-01-30 | 2017-04-21 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 25 | 20 | 10 | 10 | 10 | 5 | 15 | 20 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057354 | No | No | Yes | Australia | Australia | 02-Analyze | RTM (AN) | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 4h | 0h | 4h | 2016-11-07 | 2017-01-20 | Yes |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057355 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) | OTC | FUN | Saputo | Onshore | Ginther; Gerald | Saputo | Yes | CapEx | Localization | Business | 87h | 0h | 87h | 2016-10-31 | 2017-01-20 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057356 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Management (Cutover/Go-live) - PTM | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | CapEx | Localization | Business | 102h | 0h | 102h | 2017-06-05 | 2017-07-03 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 23 | 25 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057357 | No | No | Yes | Australia | Australia | 06-Hypercare | Management (Hypercare) - PTM | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | CapEx | Localization | Business | 160h | 0h | 160h | 2017-07-03 | 2017-07-17 | Yes |  |  | ACT.DEV.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057358 | No | No | Yes | Australia | Australia | 03-Design/Build | Management (D/B) - PTM | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | CapEx | Localization | Business | 219h | 0h | 219h | 2017-01-23 | 2017-04-11 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 28 | 41 | 39 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057359 | No | No | Yes | Australia | Australia | 01-Preparation | Prepare KT) (PP) | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | OpEx | Localization | Business | 10h | 0h | 10h | 2016-09-19 | 2016-09-23 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057360 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia - (Capex) - (D/B) | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | CapEx | Localization | Business | 6h | 0h | 6h | 2017-01-16 | 2017-01-20 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057361 | No | No | Yes | Australia | Australia | 04-Test | Management (Test) - PTM | PTM | FUN | Saputo | Onshore | Roehl; Darryl | Saputo | Yes | CapEx | Localization | Business | 84h | 0h | 84h | 2017-03-14 | 2017-06-08 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 16 | 18 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057362 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Management (Cutover/Go-live) | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | CapEx | Localization | Business | 74h | 0h | 74h | 2017-06-05 | 2017-06-30 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 19 | 20 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057363 | No | No | Yes | Australia | Australia | 06-Hypercare | Management (Hypercare) - RTR | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | CapEx | Localization | Business | 256h | 0h | 256h | 2017-06-30 | 2017-08-25 | Yes |  |  | ACT.DEV.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 50 | 35 | 0 | 30 | 40 | 40 | 40 | 15 | 0 | 0 | 0 | 0
1057364 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | CapEx | Localization | Business | 120.5h | 0h | 120.5h | 2016-10-31 | 2017-01-06 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 2.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057365 | No | No | Yes | Australia | Australia | 03-Design/Build | Management (D/B) - RTR | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | CapEx | Localization | Business | 185.45h | 0h | 185.45h | 2017-02-06 | 2017-05-12 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 10 | 13.95 | 10 | 5 | 10 | 5 | 30.5 | 50 | 0 | 4 | 14 | 10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057366 | No | No | Yes | Australia | Australia | 02-Analyze | RTM (AN) | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | CapEx | Localization | Business | 15.5h | 0h | 15.5h | 2016-11-07 | 2017-01-19 | Yes |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057367 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct Design Workshops (AN) | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | CapEx | Localization | Business | 32.5h | 0h | 32.5h | 2016-12-05 | 2017-01-19 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 2.5 | 5 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057368 | No | No | Yes | Australia | Australia | 04-Test | Management (Test) - RTR | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | CapEx | Localization | Business | 53h | 0h | 53h | 2017-04-24 | 2017-06-02 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 20 | 8 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057369 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057370 | No | No | Yes | Australia | Australia | 01-Preparation | Prepare KT) (PP) | RTR | FUN | Saputo | Onshore | Dalip; Dave | Saputo | Yes | OpEx | Localization | Business | 1h | 0h | 1h | 2016-09-22 | 2016-09-22 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057371 | No | No | Yes | Australia | Australia | 03-Design/Build | Management (D/B) | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 140h | 0h | 140h | 2017-02-20 | 2017-03-31 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 25 | 40 | 5 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057372 | No | No | Yes | Australia | Australia | 01-Preparation | Prepare KT) (PP) | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | OpEx | Localization | Business | 9h | 0h | 9h | 2016-10-24 | 2016-10-28 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057373 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057374 | No | No | Yes | Australia | Australia | 06-Hypercare | Management (Hypercare) - LOG | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 90h | 0h | 90h | 2017-07-10 | 2017-07-17 | Yes |  |  | ACT.DEV.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057375 | No | No | Yes | Australia | Australia | 04-Test | Management (Test) - LOG | LOG | FUN | Saputo | Onshore | Ferrari; Luigi | Saputo | Yes | CapEx | Localization | Business | 92h | 0h | 92h | 2017-04-24 | 2017-06-02 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 20 | 13 | 22 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057376 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - OTC | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 28h | 0h | 28h | 2017-06-05 | 2017-06-23 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057377 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD144-Output Order (EDI, Printout, Fax, e-mail) | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057378 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - OTC | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 31h | 0h | 31h | 2017-06-05 | 2017-06-16 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057379 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - OTC | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 190h | 0h | 190h | 2017-07-03 | 2017-09-01 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 50 | 3 | 25 | 5 | 20 | 2 | 0 | 15 | 0 | 0 | 0
1057380 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - OTC | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 39h | 0h | 39h | 2017-06-28 | 2017-07-03 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057381 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD138-Material Determination | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057382 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - OTC | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 4h | 0h | 4h | 2017-05-17 | 2017-06-02 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057383 | No | No | Yes | Australia | Australia | 04-Test | Regression - Run Tests - OTC | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 49h | 0h | 49h | 2017-05-15 | 2017-06-01 | Yes |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057384 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 5h | 0h | 5h | 2017-04-24 | 2017-05-10 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057385 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Validate | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | OpEx | Localization | Business | 5h | 0h | 5h | 2017-04-17 | 2017-04-21 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057386 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Preparation | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 8h | 0h | 8h | 2017-03-27 | 2017-04-13 | Yes |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057387 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Support | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | OpEx | Localization | Business | 27h | 0h | 27h | 2017-03-20 | 2017-04-13 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057388 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix - OTC | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 68h | 0h | 68h | 2017-07-17 | 2017-09-01 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 25 | 0 | 15 | 0 | 16 | 0 | 0 | 0
1057389 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Prepare | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | OpEx | Localization | Business | 12h | 0h | 12h | 2017-02-28 | 2017-03-31 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057390 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia(D/B) | OTC | FUN | Saputo | Onshore | Nicolle; Amanda | Saputo | Yes | CapEx | Localization | Business | 4h | 0h | 4h | 2017-01-30 | 2017-01-31 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057391 | No | No | Yes | Australia | Australia | 03-Design/Build | Contribute to Cut-over Planning (D/B) - RTR | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-11-22 | 2016-11-22 | Yes |  |  | ACT.FUN.Support Cutover plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057392 | No | No | Yes | Australia | Australia | 03-Design/Build | Support MDM (D/B) | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-12-03 | 2016-12-03 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057393 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct Design Workshops (AN) | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-11-22 | 2016-11-22 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057394 | No | No | Yes | Australia | Australia | 03-Design/Build | PDD-Baseline (D/B) | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057395 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Perform Gap Resolution (AN) | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-11-21 | 2016-11-21 | Yes |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057396 | No | No | Yes | Australia | Australia | 02-Analyze | RTM (AN) | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 160h | 0h | 160h | 2016-11-04 | 2016-12-16 | Yes |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057397 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-Baseline (D/B) | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057398 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD256-DMS Production Volume | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057399 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD237-DMS - Cost Categories assignments | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057400 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD246-Secondary Cost Elements | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057401 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD247-Profit Center Plan | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057402 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD235-DMS - Processes | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057403 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD236-DMS - Manufacturing Processes | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057404 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD010-Cost Centres - ECC | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057405 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD012-Profit Centres - ECC | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057406 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD013-Activity Types | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057407 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD014-Activity Type Rates | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057408 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD025-Statistical Key Figures | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057409 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD024-Profit Centre Groups - ECC | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057410 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD023-Cost Centre Groups - ECC | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057411 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - RTR | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 120h | 0h | 120h | 2017-07-04 | 2017-08-18 | Yes |  |  | ACT.FUN.Functional Break/Fix | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0
1057412 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057413 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Prepare - RTR | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057414 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - RTR | RTR | FUN | Saputo | Onshore | Faulkner; Patrick | Saputo | Yes | CapEx | Localization | Business | 40h | 0h | 40h | 2017-07-03 | 2017-07-07 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057415 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - PTM | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 54h | 0h | 54h | 2017-07-04 | 2017-07-28 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057416 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia - (Capex) - (D/B) | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057417 | No | No | Yes | Australia | Australia | 01-Preparation | Conduct KT sessions) (PP) | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-10-24 | 2016-10-24 | Yes |  |  | WP.FUN.Requirements/Process Design Workshop Decks | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057418 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) | PTM | FUN | Saputo | Onshore | In; Volak | Saputo | Yes | CapEx | Localization | Business | 203h | 0h | 203h | 2016-10-26 | 2017-01-19 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 12 | 11 | 15 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057419 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD115-Credit Master - Business partner | OTC | FUN | Saputo | Onshore | Cook; Darrius | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-02-03 | 2017-02-03 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057420 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD143-Output Billing (EDI, Printout, Fax, e-mail) | OTC | FUN | Saputo | Onshore | Cook; Darrius | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057421 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD128-Broker Determination | OTC | FUN | Saputo | Onshore | Cook; Darrius | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057422 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD129-Sales Representatives | OTC | FUN | Saputo | Onshore | Cook; Darrius | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057423 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD132-Contact Person | OTC | FUN | Saputo | Onshore | Cook; Darrius | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057424 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD158-All - Sales Reps and Broker Commission Agreements Rebates | OTC | FUN | Saputo | Onshore | Cook; Darrius | Saputo | Yes | CapEx | Localization | Business | 5h | 0h | 5h | 2017-02-20 | 2017-02-24 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057425 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia(D/B) | OTC | FUN | Saputo | Onshore | Cook; Darrius | Saputo | Yes | CapEx | Localization | Business | 155h | 0h | 155h | 2017-02-06 | 2017-03-03 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 35 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057426 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia(D/B) | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 120h | 0h | 120h | 2017-01-30 | 2017-02-17 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057427 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD154-Pricing - Customer Freight (elements/add) | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057428 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD152-Pricing - Sales Taxes (all levels) | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057429 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD153-Pricing - Cust Specific | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 25h | 0h | 25h | 2017-02-27 | 2017-03-03 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057430 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD146-Pricing - List Price | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 40h | 0h | 40h | 2017-01-16 | 2017-01-20 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057431 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD147-Pricing - Truckload / Swell/ Pickup Allowance | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 50h | 0h | 50h | 2017-01-23 | 2017-03-03 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057432 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD148-Pricing - Deng, Royalty (Accrual) | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057433 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD151-Pricing - Non-trade Accruals | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057434 | No | No | Yes | Australia | Australia | 04-Test | Regression - Run Tests - OTC | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057435 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Validate | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2017-04-10 | 2017-04-10 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057436 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Support | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057437 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Prepare | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057438 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 15h | 0h | 15h | 2017-05-01 | 2017-05-05 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057439 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Preparation | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057440 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - OTC | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057441 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - OTC | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 13h | 0h | 13h | 2017-06-26 | 2017-07-07 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057442 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Manage Defects (Capex) | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-06-05 | 2017-06-05 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057443 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - OTC | OTC | FUN | Saputo | Onshore | Miller; Stephanie | Saputo | Yes | CapEx | Localization | Business | 13h | 0h | 13h | 2017-07-03 | 2017-07-21 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057444 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Support | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | OpEx | Localization | Business | 10h | 0h | 10h | 2017-03-27 | 2017-04-13 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057445 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Validate | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | OpEx | Localization | Business | 9h | 0h | 9h | 2017-04-17 | 2017-04-21 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057446 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - LOG | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 238h | 0h | 238h | 2017-07-10 | 2017-09-01 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 40 | 20 | 20 | 20 | 20 | 42 | 42 | 0 | 0 | 0
1057447 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057448 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG006-DEV FUT-EDI 3PL Pick Request | LOG | FUN | Saputo | Onshore | Koch; Doug | Saputo | Yes | CapEx | Localization | Business | 40h | 0h | 40h | 2017-03-06 | 2017-03-10 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057449 | No | No | Yes | Australia | Australia | 03-Design/Build | PDD-Milk payment process | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 7h | 0h | 7h | 2017-02-06 | 2017-02-17 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057450 | No | No | Yes | Australia | Australia | 06-Hypercare | Management (Hypercare) - PTP | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 46h | 0h | 46h | 2017-07-17 | 2017-08-11 | Yes |  |  | ACT.DEV.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0
1057451 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Management (Cutover/Go-live) | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 6h | 0h | 6h | 2017-06-07 | 2017-06-29 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057452 | No | No | Yes | Australia | Australia | 04-Test | Management (Test) - PTP | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 65h | 0h | 65h | 2017-04-25 | 2017-06-16 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 | 10 | 25 | 8 | 8 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057453 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Log Gaps (AN) | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 81h | 0h | 81h | 2016-11-14 | 2016-12-09 | Yes |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057454 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057455 | No | No | Yes | Australia | Australia | 01-Preparation | Prepare KT) (PP) | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-09-12 | 2016-09-12 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057456 | No | No | Yes | Australia | Australia | 03-Design/Build | Management (D/B) | PTP | FUN | Saputo | Onshore | Newman; Karen | Saputo | Yes | CapEx | Localization | Business | 94h | 0h | 94h | 2017-02-08 | 2017-06-16 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 3 | 2 | 2 | 10 | 9 | 18 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 25 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057457 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 2h | 0h | 2h | 2017-01-31 | 2017-02-01 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057458 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Prepare - RTR | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 22.5h | 0h | 22.5h | 2017-06-12 | 2017-06-30 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5 | 8 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057459 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - RTR | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 11h | 0h | 11h | 2017-07-03 | 2017-07-07 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057460 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - RTR | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057461 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - RTR | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 7h | 0h | 7h | 2017-05-08 | 2017-06-08 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057462 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-10-31 | 2016-10-31 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057463 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - RTR | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 240h | 0h | 240h | 2017-07-03 | 2017-08-18 | Yes |  |  | ACT.FUN.Functional Break/Fix | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0
1057464 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Prep-Data quality | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 12h | 0h | 12h | 2017-04-10 | 2017-04-12 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057465 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD022-Internal Orders | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057466 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD015-G/L Balances | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057467 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD016-Fixed Assets | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057468 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD017-Vendor Open Items (AP) | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-30 | 2017-01-30 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057469 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD018-Customer Open Items (AR) | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057470 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD008-G/L Acc Master Data - Company Code Level - ECC | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057471 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD007-G/L Account Master Data - Chart of Accounts Level - ECC | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057472 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD030-Internal Order Groups | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057473 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD027-Bank Master | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057474 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD028-Internal Order Budget | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057475 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD029-Internal Order Plan | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057476 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-Baseline (D/B) | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-12-12 | 2016-12-12 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057477 | No | No | Yes | Australia | Australia | 02-Analyze | RTM (AN) | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-11-04 | 2016-11-04 | Yes |  |  | DELIV.RTM-001.Requirements Traceability Matrix (RTM) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057478 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Perform Gap Resolution (AN) | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-11-21 | 2016-11-21 | Yes |  |  | WP.FUN.Gap Definition | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057479 | No | No | Yes | Australia | Australia | 03-Design/Build | PDD-Baseline (D/B) | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | DELIV.FUN-110.PDDs | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057480 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct Design Workshops (AN) | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 0h | 0h | 0h | 2016-11-22 | 2016-11-22 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057481 | No | No | Yes | Australia | Australia | 03-Design/Build | Support MDM (D/B) | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | OpEx | Localization | Business | 0h | 0h | 0h | 2016-12-03 | 2016-12-03 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057482 | No | No | Yes | Australia | Australia | 03-Design/Build | Contribute to Cut-over Planning (D/B) - RTR | RTR | FUN | Saputo | Onshore | McNaughton; Sue | Saputo | Yes | CapEx | Localization | Business | 34h | 0h | 34h | 2016-11-22 | 2017-01-20 | Yes |  |  | ACT.FUN.Support Cutover plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057483 | No | No | Yes | Australia | Australia | 03-Design/Build | Configuration for Australia-Co code AU09 and AU10 | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-04-10 | 2017-04-15 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057484 | No | No | Yes | Australia | Australia | 03-Design/Build | Contribute to Cut-over Planning (D/B) - RTR | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2017-04-11 | 2017-04-11 | Yes |  |  | ACT.FUN.Support Cutover plan | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057485 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 132h | 0h | 132h | 2017-04-24 | 2017-05-12 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 47 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057486 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Break/Fix - RTR | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2017-04-25 | 2017-05-02 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057487 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - RTR | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-29 | 2017-05-29 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057488 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - RTR | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 13h | 0h | 13h | 2017-05-15 | 2017-05-19 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057489 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - RTR | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 40h | 0h | 40h | 2017-05-15 | 2017-06-02 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 2 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057490 | No | No | Yes | Australia | Australia | 03-Design/Build | AR_03-CONFIG FUT-FI-AR-Correspondence | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-03 | 2017-03-03 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057491 | No | No | Yes | Australia | Australia | 03-Design/Build | AR_06-CONFIG FUT-FI-AR-Payment Advices (Incoming) | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | OpEx | Localization | IT - External | 6h | 0h | 6h | 2017-02-13 | 2017-03-03 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057492 | No | No | Yes | Australia | Australia | 03-Design/Build | CM_01-CONFIG FUT-FSCM-CM-Basic Settings | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-02-13 | 2017-03-10 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 5 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057493 | No | No | Yes | Australia | Australia | 03-Design/Build | CM_02-CONFIG FUT-FSCM-CM Integration with AR | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-02-20 | 2017-03-10 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057494 | No | No | Yes | Australia | Australia | 03-Design/Build | AR_04-CONFIG-FI-AR-Dunning | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-02-13 | 2017-02-15 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057495 | No | No | Yes | Australia | Australia | 03-Design/Build | AR_06-CONFIG-FI-AR-Payment Advices (Incoming) | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-02-13 | 2017-02-15 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057496 | No | No | Yes | Australia | Australia | 03-Design/Build | BNK_01-CONFIG-FI-EBS Electronic Bank Statement | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 24h | 0h | 24h | 2017-02-20 | 2017-03-17 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 3 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057497 | No | No | Yes | Australia | Australia | 03-Design/Build | CM_01-CONFIG-FSCM-CM-Basic Settings | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2017-02-15 | 2017-02-22 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057498 | No | No | Yes | Australia | Australia | 03-Design/Build | CM_02-CONFIG-FSCM-CM Integration with AR | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057499 | No | No | Yes | Australia | Australia | 03-Design/Build | AR_10-CONFIG-FI-AR-Payment Cards | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057500 | No | No | Yes | Australia | Australia | 03-Design/Build | WPB-RTR (D/B) | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | OpEx | Localization | IT - External | 25h | 0h | 25h | 2017-04-03 | 2017-04-21 | Yes |  |  | DELIV.FUN-403.WPB Recordings | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 8 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057501 | No | No | Yes | Australia | Australia | 03-Design/Build | FRTR005-DEV FUT-Ability to produce an invoice for direct FI | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 33h | 0h | 33h | 2017-04-03 | 2017-05-26 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057502 | No | No | Yes | Australia | Australia | 03-Design/Build | KT sessions (D/B) | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 33.5h | 0h | 33.5h | 2017-03-20 | 2017-04-21 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 5.5 | 8 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057503 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Preparation | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 13.5h | 0h | 13.5h | 2017-03-27 | 2017-04-15 | Yes |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 3.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057504 | No | No | Yes | Australia | Australia | 03-Design/Build | AR_03-CONFIG-FI-AR-Correspondence | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-02-27 | 2017-03-03 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057505 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - RTR | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057506 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057507 | No | No | Yes | Australia | Australia | 03-Design/Build | AR_01-CONFIG FUT-FI-AR-Basic Settings | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-02-06 | 2017-02-10 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057508 | No | No | Yes | Australia | Australia | 03-Design/Build | AR_02-CONFIG FUT-FI-AR-Manual Incoming Payments | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2017-02-06 | 2017-02-13 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057509 | No | No | Yes | Australia | Australia | 03-Design/Build | AR_04-CONFIG FUT-FI-AR-Dunning | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 3h | 0h | 3h | 2017-02-13 | 2017-02-22 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057510 | No | No | Yes | Australia | Australia | 03-Design/Build | AR_05-CONFIG FUT-FI-AR-Over / Under Payment | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-02-06 | 2017-02-10 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057511 | No | No | Yes | Australia | Australia | 03-Design/Build | AR_08-CONFIG FUT-FI-AR-Special GL | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-02-06 | 2017-02-10 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057512 | No | No | Yes | Australia | Australia | 03-Design/Build | AR_09-CONFIG FUT-FI-AR-Open Item Clearing | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-02-13 | 2017-02-15 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057513 | No | No | Yes | Australia | Australia | 03-Design/Build | AR_10-CONFIG FUT-FI-AR-Payment Cards | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057514 | No | No | Yes | Australia | Australia | 03-Design/Build | BNK_01-CONFIG FUT-FI-EBS Electronic Bank Statement | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-20 | 2017-03-20 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057515 | No | No | Yes | Australia | Australia | 03-Design/Build | BNK_02-CONFIG FUT-FI-Check Deposit | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057516 | No | No | Yes | Australia | Australia | 03-Design/Build | BNK_03-CONFIG FUT-FI-BNK-Lockbox | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057517 | No | No | Yes | Australia | Australia | 03-Design/Build | BNK_04-CONFIG FUT-Manual Bank Statement | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057518 | No | No | Yes | Australia | Australia | 03-Design/Build | DM_01-CONFIG FUT-FSCM-CM-Dispute Case Processing | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2017-02-15 | 2017-02-17 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057519 | No | No | Yes | Australia | Australia | 03-Design/Build | DM_02-CONFIG FUT-FSCM-DM-Future Enhancement | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-24 | 2017-02-24 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057520 | No | No | Yes | Australia | Australia | 03-Design/Build | DM_03-CONFIG FUT-FSCM-DM-Transfer Cases to TPM | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-24 | 2017-02-24 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057521 | No | No | Yes | Australia | Australia | 03-Design/Build | DM_04-CONFIG FUT-FSCM-DM-AR Integration | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-24 | 2017-02-24 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057522 | No | No | Yes | Australia | Australia | 03-Design/Build | DM_02-CONFIG-FSCM-DM-Future Enhancement | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 3h | 0h | 3h | 2017-02-20 | 2017-02-24 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057523 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix (Hypercare) - RTR | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 37h | 0h | 37h | 2017-07-03 | 2017-08-18 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 12 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0
1057524 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - RTR | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-06-26 | 2017-06-26 | Yes |  |  | ACT.FUN.Functional Break/Fix | Future Task | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057525 | No | No | Yes | Australia | Australia | 03-Design/Build | DM_04-CONFIG-FSCM-DM-AR Integration | RTR | FUN | SI | Offshore | Choudhury; Prantika | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-02-20 | 2017-02-24 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057526 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia(D/B) | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057527 | No | No | Yes | Australia | Australia | 03-Design/Build | XXX-FSD-Rebates selement report | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 29h | 0h | 29h | 2017-02-10 | 2017-05-26 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 6 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057528 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Prepare | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | OpEx | Localization | IT - External | 79h | 0h | 79h | 2017-02-06 | 2017-03-24 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 12 | 25 | 30 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057529 | No | No | Yes | Australia | Australia | 03-Design/Build | OTC_07-CONFIG-Credit Management | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-02-13 | 2017-02-24 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057530 | No | No | Yes | Australia | Australia | 03-Design/Build | OTC_01-CONFIG FUT-Definition and assignment of Commercial Organization structure | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-02-08 | 2017-02-09 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057531 | No | No | Yes | Australia | Australia | 03-Design/Build | OTC_04-CONFIG-Pricing & Account Determination | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-02-13 | 2017-02-15 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057532 | No | No | Yes | Australia | Australia | 03-Design/Build | FOTC007-DEV FUT-Order acknowledgement form - domestic | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-27 | 2017-03-27 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057533 | No | No | Yes | Australia | Australia | 03-Design/Build | XXX-DEV FUT-Placeholderx | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057534 | No | No | Yes | Australia | Australia | 03-Design/Build | XXX-DEV FUT-Placeholderx | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-10 | 2017-02-10 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057535 | No | No | Yes | Australia | Australia | 02-Analyze | AUS Deep Dive Order to Cash Process Flow (with EDI and 3PLs) | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-01-25 | 2017-01-25 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057536 | No | No | Yes | Australia | Australia | 02-Analyze | AUS Deep Dive: Batch Determination | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 1.5h | 0h | 1.5h | 2017-01-24 | 2017-01-24 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057537 | No | No | Yes | Australia | Australia | 02-Analyze | AUS: GOI Joint Venture | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2017-01-25 | 2017-02-02 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057538 | No | No | Yes | Australia | Australia | 02-Analyze | AUS Deep Dive: One Customer | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2017-01-24 | 2017-01-24 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057539 | No | No | Yes | Australia | Australia | 03-Design/Build | OTC_07-CONFIG FUT-Credit Management | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2017-02-23 | 2017-02-24 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057540 | No | No | Yes | Australia | Australia | 03-Design/Build | OTC_04-CONFIG FUT-Pricing & Account Determination | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-02-08 | 2017-02-09 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057541 | No | No | Yes | Australia | Australia | 03-Design/Build | XXX-FSD-Placeholderx | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-02-06 | 2017-02-10 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057542 | No | No | Yes | Australia | Australia | 03-Design/Build | OTC_01-CONFIG-Definition and assignment of Commercial Organization structure | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 33.5h | 0h | 33.5h | 2017-01-30 | 2017-02-03 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057543 | No | No | Yes | Australia | Australia | 03-Design/Build | Security Roles - Support (D/B) | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-03-06 | 2017-03-10 | Yes |  |  | DELIV.SEC-201.Security Role Detailed Design | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057544 | No | No | Yes | Australia | Australia | 03-Design/Build | Training Materials Localization - Support (D/B) - OTC | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | OpEx | Localization | IT - External | 38h | 0h | 38h | 2017-03-06 | 2017-05-05 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 11 | 4 | 0 | 5 | 5 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057545 | No | No | Yes | Australia | Australia | 03-Design/Build | XXX-DEV FUT-Rebates selement report | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | To delete.To delete.To delete | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057546 | No | No | Yes | Australia | Australia | 02-Analyze | AUS Deep Dive for Billing Corrections | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057547 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct requirements Workshops (AN) | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 231h | 0h | 231h | 2016-11-14 | 2017-01-20 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 8 | 10 | 4 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057548 | No | No | Yes | Australia | Australia | 02-Analyze | AUS Deep Dive: Trade ECC Rebates & Commissions | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-01-25 | 2017-01-25 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057549 | No | No | Yes | Australia | Australia | 02-Analyze | AUS: Reporting (ECC vs. BI) | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 3h | 0h | 3h | 2017-01-23 | 2017-02-01 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057550 | No | No | Yes | Australia | Australia | 02-Analyze | AUS: Sell-Through Process | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 2.5h | 0h | 2.5h | 2017-01-23 | 2017-01-31 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057551 | No | No | Yes | Australia | Australia | 02-Analyze | AUS Deep Dive for Master Data (Customer and Material Master) | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057552 | No | No | Yes | Australia | Australia | 02-Analyze | AUS Deep Dive for freight | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-25 | 2017-01-25 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057553 | No | No | Yes | Australia | Australia | 02-Analyze | AUS Deep Dive on Pricing upload program | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057554 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - OTC | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 34h | 0h | 34h | 2017-06-19 | 2017-07-03 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057555 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - OTC | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2017-06-12 | 2017-06-28 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057556 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Run Tests - OTC | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-06-05 | 2017-06-09 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057557 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Manage Defects (Capex) | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 13h | 0h | 13h | 2017-05-15 | 2017-05-25 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057558 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - OTC | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-05-15 | 2017-05-19 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057559 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - OTC | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-05-22 | 2017-05-23 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057560 | No | No | Yes | Australia | Australia | 04-Test | Management (Test) - OTC | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-05-03 | 2017-06-01 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 5 | 5 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057561 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Preparation | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2017-03-13 | 2017-03-21 | Yes |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057562 | No | No | Yes | Australia | Australia | 04-Test | Regression - Manage defects (Capex) - OTC | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057563 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-05-03 | 2017-05-05 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057564 | No | No | Yes | Australia | Australia | 03-Design/Build | OTC_05-CONFIG FUT-Foreign Trade | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2017-03-01 | 2017-03-03 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057565 | No | No | Yes | Australia | Australia | 03-Design/Build | OTC_05-CONFIG-Foreign Trade | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2017-03-01 | 2017-03-03 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057566 | No | No | Yes | Australia | Australia | 03-Design/Build | Management (D/B) | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 57h | 0h | 57h | 2017-02-13 | 2017-04-21 | Yes |  |  | ACT.FUN.Management | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 0 | 5 | 15 | 4 | 6 | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057567 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Manage Defects (Capex) | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057568 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Break/Fix - OTC | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-05-03 | 2017-05-05 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057569 | No | No | Yes | Australia | Australia | 02-Analyze | AUS Deep Dive: Export Process considering BSM In Scope | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-01-24 | 2017-02-02 | Yes |  |  | WP.FUN.Fit/Gap Workshop Note | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057570 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix - OTC | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 133h | 0h | 133h | 2017-07-03 | 2017-07-31 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 18 | 33 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057571 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Prepare - OTC | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-06-05 | 2017-06-16 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057572 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - OTC | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-05-15 | 2017-05-19 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057573 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Prep | OTC | FUN | SI | Offshore | Pathakamuri; Sudheer | IBM | Yes | CapEx | Localization | IT - External | 11h | 0h | 11h | 2017-05-19 | 2017-06-01 | Yes |  |  | ACT.FUN.UAT Preparation | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057574 | No | No | Yes | Australia | Australia | 03-Design/Build | DMS_01-CONFIG-Dairy Mgmt System - Cross Functional | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2017-01-26 | 2017-03-10 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057575 | No | No | Yes | Australia | Australia | 03-Design/Build | CONFIG-MM_01-QM | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057576 | No | No | Yes | Australia | Australia | 03-Design/Build | DMS_02-CONFIG-Dairy Mgmt System - Planning | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057577 | No | No | Yes | Australia | Australia | 03-Design/Build | TP_01-CONFIG-Transfer Pricing | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057578 | No | No | Yes | Australia | Australia | 03-Design/Build | PA_02-CONFIG-Profitability Analysis Planning | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 21h | 0h | 21h | 2017-03-20 | 2017-03-24 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057579 | No | No | Yes | Australia | Australia | 03-Design/Build | TP_01-CONFIG FUT-Transfer Pricing | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-20 | 2017-02-20 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057580 | No | No | Yes | Australia | Australia | 03-Design/Build | KT sessions (D/B) | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 22h | 0h | 22h | 2017-03-14 | 2017-05-05 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 5 | 6 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057581 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Preparation | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 50h | 0h | 50h | 2017-03-27 | 2017-04-28 | Yes |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 10 | 3 | 13 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057582 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057583 | No | No | Yes | Australia | Australia | 03-Design/Build | MM_04-CONFIG FUT-MM Valuation and Acct assignment | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-13 | 2017-02-13 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057584 | No | No | Yes | Australia | Australia | 03-Design/Build | PA_02-CONFIG FUT-Profitability Analysis Planning | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-03-23 | 2017-03-24 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057585 | No | No | Yes | Australia | Australia | 03-Design/Build | AA_01-CONFIG FUT-Organization Structure | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-17 | 2017-02-17 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057586 | No | No | Yes | Australia | Australia | 03-Design/Build | PCA_01-CONFIG FUT-Profit Centre Accounting | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-17 | 2017-03-17 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057587 | No | No | Yes | Australia | Australia | 03-Design/Build | PC_02-CONFIG FUT-Actual Costing/Material Ledger | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-01-27 | 2017-02-02 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057588 | No | No | Yes | Australia | Australia | 03-Design/Build | PC_01-CONFIG FUT-Product Cost Planning | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-27 | 2017-02-27 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057589 | No | No | Yes | Australia | Australia | 03-Design/Build | PA_01-CONFIG FUT-Profitability Analysis Actual | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-10 | 2017-02-10 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057590 | No | No | Yes | Australia | Australia | 03-Design/Build | COC_02-CONFIG FUT-Cancelled | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057591 | No | No | Yes | Australia | Australia | 03-Design/Build | COC_01-CONFIG FUT-Cost Object Controlling | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 11h | 0h | 11h | 2017-01-30 | 2017-01-30 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057592 | No | No | Yes | Australia | Australia | 03-Design/Build | CC_01-CONFIG FUT-Cost Centre Accounting - Planning and Actual | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 11h | 0h | 11h | 2017-01-28 | 2017-04-07 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057593 | No | No | Yes | Australia | Australia | 03-Design/Build | CO_02-CONFIG FUT-CO CONFIG FUTuration Master Data | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057594 | No | No | Yes | Australia | Australia | 03-Design/Build | CO_01-CONFIG FUT-CO Organizational Data | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 4h | 0h | 4h | 2017-01-30 | 2017-01-30 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057595 | No | No | Yes | Australia | Australia | 03-Design/Build | PC_03-CONFIG FUT-Product Costing | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-06 | 2017-03-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057596 | No | No | Yes | Australia | Australia | 03-Design/Build | CC_01-CONFIG-Cost Centre Accounting - Planning and Actual | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-20 | 2017-02-20 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057597 | No | No | Yes | Australia | Australia | 03-Design/Build | CO_01-CONFIG-CO Organizational Data | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057598 | No | No | Yes | Australia | Australia | 03-Design/Build | CO_02-CONFIG-CO Configuration Master Data | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057599 | No | No | Yes | Australia | Australia | 03-Design/Build | COC_01-CONFIG-Cost Object Controlling | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 22h | 0h | 22h | 2017-01-14 | 2017-01-31 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057600 | No | No | Yes | Australia | Australia | 03-Design/Build | COC_02-CONFIG-Cost Object Controlling - Cancelled | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-14 | 2017-01-14 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057601 | No | No | Yes | Australia | Australia | 03-Design/Build | PCA_01-CONFIG-Profit Centre Accounting | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-13 | 2017-03-13 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057602 | No | No | Yes | Australia | Australia | 03-Design/Build | PC_01-CONFIG-Actual Costing/Material Ledger | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 9h | 0h | 9h | 2017-01-14 | 2017-02-01 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057603 | No | No | Yes | Australia | Australia | 03-Design/Build | PC_02-CONFIG-Product Cost Planning | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057604 | No | No | Yes | Australia | Australia | 03-Design/Build | PA_01-CONFIG-Profitability Analysis Actual | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057605 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Break/Fix - RTR | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 11h | 0h | 11h | 2017-04-25 | 2017-05-05 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057606 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - RTR | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-05-22 | 2017-05-26 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057607 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - RTR | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 25h | 0h | 25h | 2017-05-15 | 2017-06-02 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057608 | No | No | Yes | Australia | Australia | 04-Test | Regression - Run Tests - RTR | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute Regression Test | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057609 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 53h | 0h | 53h | 2017-04-27 | 2017-05-14 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 27 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057610 | No | No | Yes | Australia | Australia | 06-Hypercare | Break/Fix (Hypercare) - RTR | RTR | FUN | SI | Offshore | Shanbhag; Govindray | IBM | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2017-07-03 | 2017-07-25 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 5 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057611 | No | No | Yes | Australia | Australia | 03-Design/Build | PCA_01-CONFIG-Profit Centre Accounting | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 32h | 0h | 32h | 2017-03-13 | 2017-03-17 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057612 | No | No | Yes | Australia | Australia | 03-Design/Build | PCA_01-CONFIG FUT-Profit Centre Accounting | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-20 | 2017-03-22 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057613 | No | No | Yes | Australia | Australia | 02-Analyze | Old - Conduct Design Workshops (AN) | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2016-11-22 | 2016-11-22 | Yes |  |  | ACT.FUN.Requirements/Process Design Workshops | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057614 | No | No | Yes | Australia | Australia | 03-Design/Build | OI_01-CONFIG-Internal Order | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057615 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 119h | 0h | 119h | 2017-04-24 | 2017-05-14 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 38 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057616 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Break/Fix - RTR | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 17h | 0h | 17h | 2017-05-01 | 2017-05-14 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057617 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - RTR | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 70h | 0h | 70h | 2017-05-15 | 2017-06-09 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 5 | 5 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057618 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Break/Fix - RTR | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-15 | 2017-05-15 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057619 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Preparation | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 44h | 0h | 44h | 2017-03-06 | 2017-04-21 | Yes |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057620 | No | No | Yes | Australia | Australia | 03-Design/Build | SDD Writing | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-04-03 | 2017-04-07 | Yes |  |  | DELIV.FUN-220.Solution Design Document (SDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057621 | No | No | Yes | Australia | Australia | 03-Design/Build | KT sessions (D/B) | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 1h | 0h | 1h | 2017-03-17 | 2017-04-27 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057622 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 36h | 0h | 36h | 2017-02-06 | 2017-02-09 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057623 | No | No | Yes | Australia | Australia | 03-Design/Build | CC_01-CONFIG-Cost Centre Accounting - Planning and Actual | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 21h | 0h | 21h | 2017-02-20 | 2017-03-10 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057624 | No | No | Yes | Australia | Australia | 03-Design/Build | GTS_01-CONFIG-Global Trade Services - GTS Environment (out of scope) | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 18h | 0h | 18h | 2017-02-02 | 2017-02-03 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057625 | No | No | Yes | Australia | Australia | 03-Design/Build | CONFIG-TM_01-MM | RTR | FUN | SI | Offshore | Mahajan; Prajakta | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057626 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD170-TM - Enhance Locations | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057627 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD171-TM - Transportation Zones | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-03 | 2017-02-03 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057628 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD172-TM - Transportation Lanes | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057629 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD175-TM - Vehicle Resources | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057630 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD176-TM - Calendar Resources | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057631 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD177-TM - Freight Agreements | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057632 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD178-TM - Calculation Sheets | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057633 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD179-TM - Rate Tables | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057634 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD180-TM - Scales | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-23 | 2017-01-23 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057635 | No | No | Yes | Australia | Australia | 03-Design/Build | ILOG008-DEV FUT-ECC to BSM Delivery | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 21.5h | 0h | 21.5h | 2017-04-06 | 2017-04-17 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 11.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057636 | No | No | Yes | Australia | Australia | 03-Design/Build | XXX_XX-CONFIG FUT-Transportation Cockpit | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-04-24 | 2017-04-24 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057637 | No | No | Yes | Australia | Australia | 03-Design/Build | XXX_XX-CONFIG-Per Pallet rate | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 6h | 0h | 6h | 2017-03-24 | 2017-04-03 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057638 | No | No | Yes | Australia | Australia | 03-Design/Build | XXX_XX-CONFIG FUT-Per Pallet rate | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-04-17 | 2017-04-21 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057639 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | UAT - Break/Fix - LOG | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 69.5h | 0h | 69.5h | 2017-06-06 | 2017-07-03 | Yes |  |  | ACT.FUN.Execute UAT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 13 | 8 | 32.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057640 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Support - baseline - LOG | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 2h | 0h | 2h | 2017-06-19 | 2017-06-22 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057641 | No | No | Yes | Australia | Australia | 06-Hypercare | HyperCare solution stabilization - LOG | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 121h | 0h | 121h | 2017-07-03 | 2017-08-18 | Yes |  |  | ACT.FUN.Functional Break/Fix | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 23 | 8 | 10 | 10 | 15 | 15 | 0 | 0 | 0 | 0 | 0
1057642 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Break/Fix - LOG | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 22h | 0h | 22h | 2017-04-24 | 2017-05-26 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057643 | No | No | Yes | Australia | Australia | 04-Test | SIT 1 - Run Tests | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 54h | 0h | 54h | 2017-04-24 | 2017-05-12 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 31.5 | 17.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057644 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Prepare - LOG | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 4.5h | 0h | 4.5h | 2017-05-15 | 2017-06-09 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057645 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Dry Run - Support - LOG | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-05-08 | 2017-05-08 | Yes |  |  | ACT.FUN.Dry Run activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057646 | No | No | Yes | Australia | Australia | 05-Cutover/Go-live | Cut Over - Prepare - baseline - LOG | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-06-15 | 2017-06-28 | Yes |  |  | ACT.FUN.Cutover activities | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057647 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 42h | 0h | 42h | 2017-02-06 | 2017-02-24 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057648 | No | No | Yes | Australia | Australia | 03-Design/Build | TM_08-CONFIG-Maintain Output Determination for Inbound Deliveries | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057649 | No | No | Yes | Australia | Australia | 03-Design/Build | TM_11-CONFIG-Configure SAP TM documents | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057650 | No | No | Yes | Australia | Australia | 03-Design/Build | TM_01-CONFIG-Basic Settings in SAP TM / ECC | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057651 | No | No | Yes | Australia | Australia | 03-Design/Build | CONFIG-TM_01-MM | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057652 | No | No | Yes | Australia | Australia | 03-Design/Build | TM_02-CONFIG-General Customizing Settings in SAP TM | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-02-06 | 2017-02-10 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057653 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Preparation | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-04-17 | 2017-04-21 | Yes |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057654 | No | No | Yes | Australia | Australia | 04-Test | SIT 2 - Run Tests - LOG | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 56h | 0h | 56h | 2017-05-15 | 2017-06-05 | Yes |  |  | ACT.FUN.Execute SIT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 16 | 22.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057655 | No | No | Yes | Australia | Australia | 04-Test | SIT1 Preparation (KT with Test Team) | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-27 | 2017-03-27 | Yes |  |  | DELIV.TST-301.SIT Test Scenarios/Scripts | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057656 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Support | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | OpEx | Localization | IT - External | 0h | 0h | 0h | 2017-03-27 | 2017-03-27 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057657 | No | No | Yes | Australia | Australia | 03-Design/Build | TM_12-CONFIG-Planning | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 34.5h | 0h | 34.5h | 2017-03-06 | 2017-03-16 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057658 | No | No | Yes | Australia | Australia | 03-Design/Build | TM_13-CONFIG-Freight Order Management | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 5h | 0h | 5h | 2017-02-27 | 2017-03-03 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057659 | No | No | Yes | Australia | Australia | 03-Design/Build | TM_03-CONFIG-Master Data Transfer ECC to TM (Activate Integration Models) | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-02-13 | 2017-02-20 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057660 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GDID-xxx - Route Determination | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-02-06 | 2017-02-10 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057661 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GDID-xxx - Route | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 10h | 0h | 10h | 2017-02-06 | 2017-02-10 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057662 | No | No | Yes | Australia | Australia | 03-Design/Build | CONFIG FUT-TM_01-TM | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-06 | 2017-02-06 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057663 | No | No | Yes | Australia | Australia | 04-Test | Mock1 - Prepare | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | OpEx | Localization | IT - External | 43h | 0h | 43h | 2017-02-06 | 2017-02-24 | Yes |  |  | ACT.FUN.Mock Support | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057664 | No | No | Yes | Australia | Australia | 03-Design/Build | IOTC008-DEV FUT-ECC/GTS to BSM Order | LOG | FUN | SI | Offshore | Lal; Neeraj | IBM | Yes | CapEx | Localization | IT - External | 8h | 0h | 8h | 2017-03-13 | 2017-04-16 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057665 | No | No | Yes | Australia | Australia | 03-Design/Build | OTC_07-CONFIG-Credit Management | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 11h | 0h | 11h | 2017-02-16 | 2017-03-02 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057666 | No | No | Yes | Australia | Australia | 03-Design/Build | OTC_07-CONFIG FUT-Credit Management | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 15h | 0h | 15h | 2017-02-27 | 2017-03-20 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057667 | No | No | Yes | Australia | Australia | 03-Design/Build | DDD-GD146-Pricing - List Price | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-01-16 | 2017-01-16 | Yes |  |  | DELIV.FUN-149.Data Definition Documents (DDD) | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057668 | No | No | Yes | Australia | Australia | 03-Design/Build | Transition to Australia (D/B) | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 20h | 0h | 20h | 2017-02-20 | 2017-02-23 | Yes |  |  | TBD.Tobedefine.Tbd | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057669 | No | No | Yes | Australia | Australia | 03-Design/Build | AP_04-CONFIG-ERS Invoicing | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 0h | 0h | 0h | 2017-02-17 | 2017-02-17 | Yes |  |  | ACT.FUN.Configuration | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057670 | No | No | Yes | Australia | Australia | 03-Design/Build | FRTR006-DEV FUT-Need to send payment remittance advice | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 76h | 0h | 76h | 2017-03-03 | 2017-04-18 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 17 | 0 | 0 | 0 | 35 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057671 | No | No | Yes | Australia | Australia | 03-Design/Build | ERTR021-DEV FUT-ATO Ref | RTR | FUN | SI | Offshore | Gadre; Kirti | IBM | Yes | CapEx | Localization | IT - External | 28h | 0h | 28h | 2017-03-14 | 2017-03-31 | Yes |  |  | ACT.FUN.Execute FUT | Complete | NA | NA | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0